BUSINESS CASE ADDENDUM

PROGRAMME TITLE	Sustainable Energy and Economic Development (SEED) Programme
Directorate/ Post	Afghanistan and Pakistan Directorate	Contact name	Ali Javed, SRO
Original programme budget	Original £37.5m, reduced to £31.5m (£6m CDEL reduced) in May 2024 through first addendum to Business Case	Country or region targeted	Pakistan
Cost extension value (if applicable)	N/A	Original BC approver (Minister, DG, HoM, Director, Dep. Director)	Minister
New increased or reduced programme budget (if applicable)	N/A	Original programmes start and end dates	8 Oct 2018 – 7 October 2026
Latest AR programme score	A	New programme end date (if applicable)	30th June, 2027
		Programme ID	300141

Detailed information
Programme summary	(250 words maximum) / A brief summary of the programme and its purpose, as approved in the Business Case - noting any caveats from Minister/approver at CN or BC approval stages. / SEED is a £31.5 million programme designed to support sustainable economic development and renewable energy/energy efficiency (RE/EE) in Pakistan over eight years (2018–2026)[1]. / Describe what the programme has achieved so far and what lessons have been learned. / Achievements & Lesson Learn: / SEED mobilised $228 million (GBP 169.62 million) in private investment exceeding its $225 million (GBP 167.76 million) target and handed over a $445 (GBP 358 million) million project pipeline to Government of Khyber Pakhtunkhwa (GoKP). Of this, $38.2 (GBP 28.48 million) million relates to private climate finance. / The Public Private Partnership (‘PPP’) framework became operational independently of SEED, while PIM tools raised the PIMA score from 4.11 to 4.78, surpassing the 4.7 target. / Climate-resilient infrastructure proposals secured GoKP funding, potentially benefiting over 224,000 people under ICF KPI-1. / The contributory pension scheme now covers 60,000+ eligible civil service recruits projected to generate annual savings of around PKR 13 billion (GBP 35 million) and PKR 700 billion (GBP 105 million) by 2049. / Post 2022 floods, SEED provided technical assistance to prioritise reconstruction of vital infrastructure. / Through Karandaaz, SEED supported 18.7MW in RE commitments (14.6MW commissioned), leveraging PKR 6.02 billion (GBP 17.2 million) from the private sector with a 4.2x leverage factor. / SEED mobilised $25 million (£18.25 million) from GCF via NRSP and submitted nine additional proposals to global climate finance entities. / SEED’s success shows that institutional embedding, adaptive engagement, and targeted, demand-driven interventions drive sustainable reform. Political dynamics and recurring risks require proactive, iterative management. Investment efficiency and alignment with government priorities yield strong Value for Money outcomes.
Changes	(300 words maximum) / Has the programme been amended previously? If so - provide a brief overview of dates of changes and purpose of changes. / In May 2024, the SEED Business Case underwent its first amendment for a no-cost extension, aimed to expand the geographical scope of a specific set of activities from Khyber Pakhtunkhwa (KP) to other provinces. The previous addendum aimed to: (1) strengthen public investment management and monitor fund utilisation in response to the 2022 floods in Sindh; (2) continue technical assistance to the Climate Resourcing Coordination Cell (CRCC) to enhance Pakistan’s access to climate finance; and (3) support locally driven economic reform agendas of provincial governments , including undertaking research to increase efficacy of economic planning and influencing. / What is the objective or purpose of making this change? What are the drivers of that change (e.g. context change, under-performance of programme or partner). / The core component of the SEED programme focused on supporting improved economic and urban planning through demand-led technical assistance and investment facilitation via PPP (implemented by ASI) concluded on 6 October 2025. With ~£5.1 million (RDEL) and £2.22 million (CDEL) remaining, SEED seeks a no-cost extension until 30 June 2027 to continue its economic reform work across Pakistan while future ODA economic portfolio is designed and comes online. Proposed no cost extension aims to: / Provide demand-led technical assistance to support partnership with the World Bank under the PAK@100 Trust Fund, focusing on economic reform in Punjab, Sindh, and KP (up to £1.4m) / Collaborate with the Asian Development Bank to continue investment facilitation through PPPs, across Pakistan (up to £2m RDEL and up to £2.22m CDEL) / Sign a new Accountable grant agreement, delayed due to ODA spend pause, now will have more than a year to support locally driven targeted research, technical assistance, and capacity building/influencing to strengthen economic planning and policy across both federal and provincial governments. (up to £1.5m RDEL) / To support the effective implementation of new components, particularly as we engage on economic reforms and PPP transaction in new geographies in Sindh and deepen our engagement with provinces, SEED will introduce three new programme-funded roles: / Two CBS Advisers at G7 level, with dedicated focus on reforms for growth in Sindh and Punjab (Growth adviser Sindh, Growth adviser Punjab) (up to £200,000) / A CBS Administrative Engagement Officer at AO grade, to facilitate the activities of these advisers (up to £25,000) / The final allocation of unspent RDEL and CDEL will be determined upon receipt of proposals from ADB and WB, and the completion of the AGA with local research organisations. Funds may be reallocated between these components based on actual needs. / How will the programme deviate from the original business case? How significant is the change (be clear if this is a material change which requires re-approval)? Where there is a material change, describe that change and the overall impact you expect it to have. / This addendum is aligned with the original SEED Business Case and there is no material change to ToC and outcome level indicators. With the same mandate, as we move into new geographies, we will look at the ToC to ensure we clearly capture the new outputs with a clear links to outcome and impact level indicators. / Describe the change(s) to the programme outcome(s), including any adjustments required to the theory of change and VfM assumptions. / The proposed addendum will introduce milestones at outcome-level indicators - such as investment raised, fiscal space created, and improvements brought to the way public investments are managed - across provinces to cover our proposed additional work in Sindh and Punjab / Proposed interventions through WB, ADB and AG are not only aligned with the ongoing IMF programme but go a step forward to invest in reforms which are critical for pakistan to maintain the hard-earned macroeconomic stability, and move from economic stabilisation to sustainable economic growth. / . / Is there any new evidence from ongoing monitoring, evaluation or learning work which supports/justifies making the change? / Yes, there is emerging evidence supporting the proposed change. Our sustained economic influencing efforts, the steady implementation of the 24th IMF programme, and delivery through SEED and other reform initiatives such as SNG and NGP combined with BHC’s broader engagement with key stakeholders, collectively point to timely opportunity to advance economic reforms across all levels of government. This convergence of programme delivery and stakeholder alignment offers credible assurance that reform momentum can be sustained. The programme will remain adaptive, focusing support on reforms that demonstrate political appetite, feasibility, and strategic relevance. / What would be the result if the proposed change were not approved? / If the proposed change is not approved, SEED will be unable to continue to support economic reform agenda at the provincial level till the new ODA programmes are approved and implementing partners are procured, leaving a lag between our recently concluded economic and economic governance components. It will also limit our ability to enhance our engagement particularly in Sindh and Punjab, despite having instruments and funding available under SEED. This would hamper programme’s ability to build on its proven successes, reduce its overall Value for Money argument, and miss opportunities to support timely and impactful initiatives led by the World Bank, Asian Development Bank and local institutions.
Implementation	(100 words maximum) / Describe how the change(s) to the programme will be implemented. / Will changes be required to the existing management arrangements as a result of the amendments to the Business Case? / The proposed reforms and PPP facilitation will be implemented in partnership with the World Bank and ADB, leveraging their technical expertise and existing programmes aligned with SEED’s objectives. As SEED expands into Sindh and Punjab, some changes to management arrangements are required to ensure effective delivery. Two CBS Growth Advisers (G7) will be recruited to enhance oversight and responsiveness, while one Administrative Engagement Officer (AO) will support coordination and stakeholder engagement. These programme-funded roles will strengthen SEED’s capacity to adapt to evolving priorities.
Budget	(100 words maximum) / For cost extensions, set out the pre/post amendment finance profile over the life of the programme including: / original budget / total amount already spent. / amount of cost extension / revised total(s) / Confirm that any cost extension is financially affordable within the Post/Directorate allocation, i.e. where will the Post/Directorate find the funding for any cost extension, and whether the proposed cost extension will take the programme beyond this SR period? (See Section 5 of the PrOF Guide to Programme Approvals for further guidance. / No additional funding is required for the proposed extension of the SEED programme. The amendment only involves reallocating the remaining unspent SEED funds (approximately £5.1m RDEL and £2.2m CDEL) to support the newly identified interventions.
Impact	Impact of cost/time extensions on VfM (check relevant box): / ☒ Positive impact – Business Case delivery ambition is being increased at the same time as the cost/time extension. / ☐ No impact – no/negligible change to Business Case delivery ambition. / ☐ Negative impact – decrease in Business Case delivery ambition.
Risk	(100 words maximum) / Describe any new key risks arising as a result of this change. How will they be mitigated? / Despite the introduction of new interventions, SEED will maintain an overall "moderate" risk rating. Key risks arising from the extension and delivery through MDBs include potential constraints on future ODA allocations, which could impact disbursements and pose reputational risks to FCDO. These will be mitigated through close coordination with the finance team and timely communication with MDBs. Operational risks related to MDBs’ budget forecasting will be addressed by requiring accurate monthly forecasts. All identified risks are considered minor and manageable, with mitigation measures in place to ensure continued programme stability.
Results/Monitoring and Evaluation	(100 words maximum) / Describe the new/additional results that you would expect to see from these changes. Outline at what level changes to the results will be seen, e.g. what is expected at outcome or output level? / At the outcome level, the changes will contribute to SEED’s indicators including additional investment facilitated (US$m), improved PIM effectiveness (PIMA), and increased fiscal space. / At the output level and under the MBD’s the following will be added: / Strengthening PFM systems for service delivery / Agricultural and property tax reform / Provincial pension reform / Land valuation and registration to support revenue and urban development / Investment facilitation including debt/equity/PPP/ other investment / Policy reforms and institutional support to create fiscal space. / Policy reforms and institutional support to attract private investments. / Support local driven research to generate demand and facilitate implementation of critical economic reforms. / Review the Theory of Change for the Business Case and outline whether the approach taken is still valid based on the evidence for the BC addendum and whether any updates are needed. / The current Theory of Change remains valid and aligned with the Business Case addendum. The expected benefits continue to demonstrate strong value for money. The logframe will be extended to March 2027 and refined in consultation with existing and new delivery partners to reflect updated outputs and outcomes. / Outline any additional monitoring and evaluation activity that will be needed in the programme as a result of the changes proposed. / Monitoring of economic reforms and investment facilitation through MDBs will be integrated into SEED’s quarterly review process, ensuring effective fund utilisation and risk management. At the end of the programme, an independent evaluation will be commissioned to assess programme impact, capture lessons learned and inform future portfolio design and delivery.
[1] SEED programme got a 1 year no cost extension in May 2024 to allow programme to deliver its commitments on ICF results committed through NRSP-CRCC and ability to fund new activities to improve quality of flood related spend in Sindh and undertake research to support localisation agenda and economic reforms at provincial level. SEED’s original budget was £37.5m, but through this amendment we released the