## Annual Review Template

Title: Hunger Safety Net Programme Phase 3 (HSNP 3)
Programme Value £ (full life): £91,881,210.25		Review date: March 2026
Programme Code: 300143	AMP start date: 03 October 2018	AMP end date: 31 March 2027

Summary of Programme Performance
Year	2019	2020	2021	2022	2023	2024	2025
Overall Output Score	A	A	A	A	A	A	A
Risk Rating	Major	Major	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300143/documents
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300143/documents

A. SUMMARY AND OVERVIEW
Description of programme
This Annual Review (AR) covers the programme progress for the period April 2025 - March 2026. The UK has supported Government of Kenya (GoK) to establish and institutionalise the Hunger Safety Net Programme (HSNP) to provide unconditional cash transfers to the poorest and most vulnerable populations in Kenya’s eight drought prone counties of Turkana, Marsabit, Mandera, Isiolo, Samburu, Tana River, Garissa and Wajir. HSNP is one of the four cash transfer programmes under the GoK flagship social protection programme, the National Safety Net Programme (NSNP), also known as Inua Jamii - a central pillar of the Government’s development strategy – Vision 2030. The NSNP includes: (i) Older Persons Cash Transfer (OPCT); (ii) Cash Transfers for Orphans and Vulnerable Children (CT-OVC); and (iii) Persons with Severe Disability Cash Transfer (PwSD-CT). The National Drought Management Authority (NDMA)[1] under the Ministry of the East African Community, Arid and Semi-Arid Lands and Regional Development (MEACARD) is responsible for implementing HSNP, the State Department for Children Services at the Ministry of Gender, Culture and Children Services manages the Cash Transfers for Orphans and Vulnerable Children (CT-OVC) whilst the other two programmes are managed under the State Department of Social Protection and Senior Citizen Affairs (SDSP) within the Ministry of Labour and Social Protection (ML&SP).
[1] The National Drought Management Authority (NDMA) is a public body established by the National Drought Management Authority (NDMA) Act, 2016. https://ndma.go.ke/about-ndma/

Phase One (2007-2012) and Two (2012-2018)
Under Phases 1 and 2, the UK contributed to set up the government systems and processes for HSNP to provide cash transfers as an alternative to costly, and often poorly targeted, food aid during periods of drought. Over this period, HSNP continued to reach over 100,000 of the poorest households, termed as ‘Group 1’ (600,000[2] people, 60% of whom were women), with regular, bimonthly electronic cash transfers of KShs. 5,400 (£31.0691)[3] paid directly into their bank accounts. Phase two introduced an innovative shock-responsive mechanism, which enabled the programme to scale up its coverage during periods of drought to an additional 270,000 households (approximately 1.62 million people). These households, termed as ‘Group 2’, were entitled to receive one-time cash payments of KShs. 2,700 (£15.5345) when emergency payments were triggered[4]. This phase saw government starting to take ownership, and by the end of 2018 GoK was co-financing 64% of the regular HSNP cash transfers, a key element for sustainability.
[2] Average household size in HSNP counties is estimated at six people (HSNP registration database)
[3] On 5 March 2025 (oanda.com) exchange rates KShs.2700 = £15.5345 and KShs.5400= £31.0691
[4] Emergency payments are triggered when pasture condition are shown to be depleted to a crisis level due to drought using the Vegetation Condition Index (VCI). VCI levels are measured using satellite imagery.

Phase Three (2019-2027)
The third phase was designed to transition HSNP to full GoK ownership and financing though building government capacity to lead and manage the programme, invest in disaster risk financing, and provide evidence for poverty graduation[5][6][7] approaches to guarantee stronger sustainability. The programme supports timeliness and predictable payments to 133,800 households (802,800 people, 70% female-headed households[8]) with the potential to scale up during periods of shock (drought) to address resilience, enabling them to access food, education and health. Secondly, it focuses on strengthening GoK’s institutions and ability to lead, coordinate and manage drought response to ensure full government ownership, and to increase linkages and alignment between all cash transfer programmes. Third, it aims to increase evidence of economic graduation/inclusion to enable GoK options to graduate people from poverty allowing new individuals to benefit from cash transfers. HSNP’s delivery is underpinned by a fourth component of evidence generation, delivering data, analysis and learning.
[5] Poverty graduation approaches include savings schemes, skills training, business development combined with lump sum cash transfers (or similar) aimed at lifting people out of poverty. The goal is to create a sustainable pathway out of poverty by addressing immediate needs and building long-term capabilities.
[6] MacLennan, M. (ed). (2017). Debating Graduation. Policy in Focus 14 (2). The International Policy Centre for Inclusive Growth. http://www.ipc-undp.org/policy-focus-39-debating-graduation
[7] Hashemi, S. et al (2016). Graduation Pathways: Increasing income and resilience for the extreme poor. CGAP Brief., Washington, D.C.
[8] NDMA MIS. Accessed on 20th March 2024

The GoK finances 100% of the cash transfers, covering both regular and emergency payments, from domestic resources. UK financing is therefore increasingly used to incentivise policy and programme reforms that enhance coverage, improve delivery systems, and strengthen the long‑term financial sustainability. In 2023, the GoK classified all Inua Jamii cash transfers, including HSNP, as priority expenditure within the national budget. Consequently, over the last two years, UK financing has prioritised evidence that poverty graduation and economic inclusion models work at scale. The Economic Inclusion Programme (EIP) provided critical evidence on scalable, cost‑effective approaches to supporting ultra-poor and vulnerable households to build assets, strengthen livelihoods, and transition towards greater economic resilience. The evidence also demonstrated the role of Village Savings and Loans Associations (VSLAs) as effective entry points for the private sector, particularly financial institutions, into communities that are otherwise perceived as too risky or unbankable, linking community-based socio-economic structures to the formal financial architecture.

The BHC Programme Monitoring, Evaluation and Learning (PMEL) team is planning an evaluation that assesses the cumulative outcomes, impact, effectiveness, and sustainability of the Hunger Safety Net Programme (HSNP) from 2007 to 2027, covering all programme components and involving comprehensive methodologies to inform future social protection programming and policy in Kenya and beyond.

Summary supporting narrative for the overall score in this review.
The programme has achieved an overall rating of ‘A,’ Met Expectations. The GoK continues to demonstrate commitment and political will to finance cash transfers from domestic sources and have continued to pay bi-monthly transfers to 133,000 households up to January 2026 (up to date), albeit with some delays in disbursements. As noted above, the programme successfully transitioned to full GoK financing and management. The review period saw the expansion of the EIP, with positive impacts on poverty reduction and household income, laying the foundation for the transition and nationwide scale-up through the GoK World Bank-funded Second Kenya Social and Economic Inclusion Project (KSEIP2).

The UK co-designed the KSEIP2, alongside WB and GoK, using the evidence developed during EIP pilot. KSEIP2 was approved by the Bank’s Board, and the programme was declared effective by the government on 26th February. In summary, the UK was able to unlock $127m from the World Bank to scale up the EIP into 20 counties, and additional $26.6m from Children Investment Fund Foundation (CIFF) for the adolescent girl’s education component. This further illustrates that the UK’s role has shifted from service delivery to unlock finance and continue to build government systems. The programme has requested a one-year extension to help the GoK roll-out the programme with targeted TA.

Changes in Operating Context
HSNP operated in a particularly challenging environment during this reporting period, shaped mainly by constrained domestic financing and reduced predictability of external support.

Severe fiscal pressures affecting GoK capacity to meet HSNP obligations - Kenya continues to face significant fiscal strain, marked by high debt and loan repayment obligations, persistent deficits, weak export performance, and sluggish investment growth. Despite this challenge, most of the payment to HSNP beneficiaries was processed although sometimes with months delay. A positive achievement to counterbalance government approach is that the World Bank (WB) included cash transfer payments as a condition for the upcoming Development Policy Operation.

Impact of Climate change – North-Eastern Kenya continues to experience severe climate‑related stress, with failed/below average October–December (OND) 2025 short rains driving a deepening drought across the eight HSNP counties. Analyses indicate ~3.3–3.5m people nationwide are acutely food insecure and in need of assistance, with pastoral areas of the ASALs experiencing Crisis (IPC Phase 3), resulting in forage and water deficits eroding livestock productivity and large losses, milk availability, and incomes. Malnutrition has escalated, with >810,000 children under five and ~116,800 pregnant/breastfeeding women requiring urgent treatment. At times like this, HSNP transfers remain a critical lifeline, stabilising consumption and helping households avoid negative coping strategies.

Delay in UK funding confirmations - driven by the UK Government’s decision to reduce its Official Development Assistance (ODA) from 0.5% to 0.3% of GNI by 2028. This policy shift, announced in early 2025, required significant internal restructuring and reprioritisation locally, prompting the UK to pause or slow new aid spending decisions in the financial year 2025/26 as departments adjusted to the new budget trajectory. As a result, HSNP partners experienced later than usual confirmation of funds, which affected planning cycles, slowed contracting, and created temporary uncertainty during a period of escalating needs in ASAL counties. Continuous scenarios planning with partners mitigated the effects of the delays.

Major lessons and recommendations for the year ahead
Recommendation	Description	Responsibility	Timelines
Continuous advocacy for GoK to prioritise cash transfers	The UK should continue advocating for the prioritisation of the cash transfers, using levers like the WB DPO and political persuasion to maintain momentum.	Programme Team, / DD and HoM	Continuous
Support KSEIP2 roll out	With the foundations set and KSEIP2 declared effective to start implementation, the UK will provide Technical Assistance to support the rollout of the programme in 20 counties, helping in the initial steps towards institutionalisation of EIP into GoK budgeting processes.	Programme Team	June 2026
Transfer EIP systems, structures, assets and select staff to KSEIP2	To ensure sustainability and avoid parallel systems in the next phase, EIP structures, systems, and responsibilities should be formally transitioned to KSEIP2 to enable full GoK ownership and continuity.	Programme Team	May 2026

Lessons:
1. Evidence is strategic and key tool to influence governments to adopt and scale-up programmes: Through systematic pilots, rigorous evidence gathering, and practical demonstration of the EIP model at scale, the UK demonstrated that the intervention is both effective, achieves VfM and can reduce poverty. This evidence directly informed the Government’s decision to scale EIP countrywide (with the support from WB- KSEIP2). At the same time, intentional efforts to build government capacity and strengthen delivery systems ensured a smooth foundation for the transition, reinforcing that scaling is only sustainable when government systems are deliberately prepared and there is strong ownership for a transition.
2. Private sector engagement thrives when risks are minimised and profit pathways are clear: Private sector is willing and ready to engage with community based economic initiatives when their risks are reduced and the profit opportunity is clearly defined. Through the establishment of VSLAs, collectively saving approximately £600,000 in 6 months, the programme demonstrated a viable and growing financial ecosystem at the community level. Presenting these savings as a bankable business opportunity successfully attracted interest from private sector actors, particularly financial institutions. Overall, the experience shows that private sector engagement is not only possible but highly impactful when community structures are strong, financial flows are visible, and incentives are aligned. This creates a foundation for sustainable, market‑driven support to vulnerable households.
3. Leveraging strategic partnerships to influence large scale social protection reform: Close collaboration with the World Bank enabled the UK to shape and co-design both KSEIP2 and ensuring that cash transfers were included as a key policy conditionality on the DPO tied to system strengthening and timely cash transfer payments. By jointly lobbying Government to prioritise timely cash transfer disbursements, the UK and the Bank reinforced sector discipline and created stronger incentives for reform. This coordinated approach demonstrated that early, unified technical and policy engagement significantly enhances donor influence and leads to more coherent, government-owned social protection outcomes.
4. The long‑term nature of development advocacy and systems strengthening: sustained and continuous influencing efforts from partners contributed directly to the first version of the Social Protection Bill (2025), whose core purpose is to provide coherence and establish a unified legal framework for social protection in the country. The bill has since progressed through the legislative process and was enacted into law. The Bill creates the National Board for SP as a central governance body to coordinate, oversee, and regulate all non‑contributory social protection interventions in Kenya, marking a major milestone in institutionalising harmonised social protection systems. This demonstrates that system and institution reforms take time, effort, continuous lobbying and champions within the political arena, but the result is a stronger government ownership, institutions, legal framework/ processes.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The expected impact of HSNP Phase 3 remains to reduce poverty and improve resilience of households in the Arid and Semi-arid Lands (ASALs). At the start of Covid-19 outbreak, the programme allocated resources to support the urban poor and generate knowledge and evidence related to this response.

In 2023, the BC was amended to bring back graduation models (which was cut due to reduced funds), with a focus on “cash plus” interventions, including EIP and the Nutrition Improvement through Cash and Health Education (NICHE), building on evidence and the pilots as the best next steps for the programme, increase cash for small investments rather than cash for consumption, thereby allowing households to diversify income, assets, and savings as a potential model for poverty graduation. The logframe was updated accordingly.

With the systems that focus on government capacity to manage and fund the consumption cash transfers transitioned to GoK, the programme, and the social protection sector as whole, has shifted focus to pathway 4 of the ToC, demonstrating that the EIP can be implemented at scale, especially in the North East, otherwise considered “difficult-to-operate”. Consequently, this AR will be heavy on the EIP and the shift towards countrywide expansion through KSEIP2. The Logframe has been updated accordingly.

The assumptions against which the original ToC pathways are based remain valid that: i) households in the ASALs continue to experience shocks; ii) GoK continues to place importance on social protection, as reflected in national budget allocations; iii) GoK has an interest in an effective and efficient social protection sector, and designs and implements policies accordingly; and iv) prior investments in HSNP by the UK and GoK are protected and infrastructure built, continue to be used in Phase Three.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

HSNP has evolved into a sustainable, government-financed system for addressing food insecurity, replacing ad hoc drought appeals with a shock responsive cash transfer mechanism that supports 133,800 households regularly and can scale to 750,000 more during crises. It continues to deliver monthly transfers of KShs. 2,700 across eight counties, with the latest payments made in January 2026. While payment delays highlight the need for continued fiscal prioritisation, the programme demonstrates stronger institutional capacity and a more predictable safety net for food, education, and health needs.

Recent evaluations of the EIP demonstrate strong and promising outcomes. In the pilot phase, implemented across five counties, the programme contributed to a 17% reduction in poverty in targeted households in Kisumu, Taveta, and Mwatate, with no reduction observed in Marsabit. Partner endline evaluation of Kuza Jamii 1 indicate 94% of all target household had at least two meals per day in the last seven days recall period, 76% of the participants had active membership in a functional, registered savings group with savings, credit, and social fund services, and 75% having diversified income sources. These results are consistent with the programme’s Theory of Change, reinforcing the validity of its graduation approach and offering a scalable model for driving systemic extreme poverty reduction and inclusive economic growth nationwide.

The EIP model was expanded to include 1,000 refugee households in each of the Dadaab and Kakuma refugee camps. Expanding the EIP into the camps demonstrates that the same government‑led graduation model can be successfully applied in refugee settings, reducing aid dependency and supporting implementation of the Shirika Plan[9]. With this foundation set, we hope to influence the World Bank, through the Window for Host Communities and Refugees (WHR), to expand KSEIP2 into the refugee camps in the future.
[9] The Shirika Plan is Kenya’s flagship national refugee inclusion and integration policy, launched in March 2025 by the Government of Kenya. It represents a major shift from traditional humanitarian aid toward long-term, development-oriented solutions for refugees and host communities.

We also worked with the World Bank to connect vulnerable groups, including refugees, to employability opportunities. Through our lobbying, HSNP beneficiaries were linked to the NYOTA youth programme, creating potential pathways for ~28,000 EIP and ~30,000 NICHE households whose youth can now access NYOTA’s employability and entrepreneurship support.

Looking ahead, the priority in the coming year is to provide comprehensive support to the roll‑out of KSEIP2 and continue to create/link the most vulnerable to other opportunities. This includes targeted technical assistance, capacity strengthening, and coordination support to enhance delivery across participating counties. Strengthening these systems will also enable the effective integration and scale‑up of both EIP and NICHE within the broader KSEIP2 framework, ensuring a more harmonised and impactful national approach to economic inclusion and poverty graduation. Additionally, the seeds to further the discussion on integrating refugee response into KSEIP2 have been planted. We will continue to influence the Bank to access the WHR to unlock and scale up EIP in the camps.

The table provides a progress summary against milestones for this period.
Indicator(s)	Milestone(s) for this review	Progress
Outcome Indicator 1 / Change in the HSNP Programme Quality Assessment Score	Retired	This indicator measures the operational capacity of NDMA to deliver the programme to ensure sustainability. It was achieved in 2024 after HSNP was 100% transitioned to GoK management and financing.
Outcome Indicator 2 / Change in GoK capacity assessment score	Retired	This indicator measures NDMA personnel and organisational capacity to deliver HSNP for sustainability. It was achieved in 2024 after GoK transitioned all HSNP contractual staff into GoK employees.
Outcome Indicator 3 / Number of households supported to improve resilience against the impacts of shocks / (Includes people supported with cash transfer to support livelihoods through the economic inclusion graduation model in 8 HSNP counties)	17,000	A: Met expectations. / This indicator measures improvement in household resilience to shocks through sustainable incomes and jobs. The heart of this indicator is household economic inclusion modelled on poverty graduation programming. During the reporting period, 14,401 households received direct support through EIP, including 2,200 refugees. Additionally, ~28,000 EIP and ~30,000 NICHE households’ youth have been profiled to access NYOTA’s employability and entrepreneurship support.
Outcome Indicator 4 / Proportion of target NICHE (Nutritional Improvements through Cash and Health Education) households in the HSNP counties with a Minimum Dietary Diversity (MDD)[10] Rates of >45% (PLW and <2yrs)	N/A	Due to funding prioritisation during the year, NICHE was not funded.
Outcome Indicator 5 / Number of people supported to better adapt to the effects of climate change as a result of International Climate Finance (ICF).	123,096	A+: Exceeded expectations / 227,338 people continued to be supported through the year. / (97% of HSNP3 budget is ICF and contributes 45% to FCDO Kenya’s overall ICF budget allocation).
[10] The minimum dietary diversity (MDD) score is a population-level indicator to assess diet diversity as part of infant and young child feeding (IYCF) practices. This indicator is part of the suite of complementary feeding indicators for IYCF developed by WHO and UNICEF to provide simple, valid, and reliable metrics for assessing IYCF practices at the population level (WHO/UNICEF, 2021). The MDD is also a component of the Minimum Acceptable Diet (MAD) indicator, which is a composite indicator described in the same 2021 guidelines. https://inddex.nutrition.tufts.edu/data4diets/indicator/minimum-dietary-diversity-mdd-iycf

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio.
Despite ongoing fiscal challenges, the programme continues to perform well and meet expectations. A recent STAAR review[11] concluded that Kenya has made significant progress over the past two decades in building a safety net capable of scaling in response to shocks. It highlighted that Kenya’s leadership in Africa in developing a high‑tech, shock‑responsive system and taking fully responsibility of financing its own cash transfers. However, although the government has shown political commitments and continues to make payments, financial pressures from a narrow fiscal space have led to delays in disbursements. Given this context, continued engagement with Government remains essential to protect the gains achieved.
[11] A review of the shock-responsive social protection system in Kenya | socialprotection.org

EIP pilots, implemented at scale in 8 ASAL counties, have demonstrated that economic inclusion models can be delivered effectively and cost‑efficiently in ASAL contexts, even under significant fiscal and operational pressure. The pilots showed that combining cash transfers with livelihood support, coaching, and financial inclusion interventions can lead to sustained improvements in household incomes, food security, and resilience.

VSLAs have also proven to be effective platforms for savings, credit access, and financial discipline. During the reporting period, 701 VSLAs accumulated over KShs. 26m in savings over the last 2 months. These significant levels of savings mobilised through VSLAs have enabled otherwise vulnerable and traditionally unbankable households to build financial track records, improving their ability to access formal financial services. This has begun to open new business opportunities for the private sector, especially financial institutions, who are increasingly recognising these groups as viable clients. For example, during the reporting period, seven (7) livestock offtake agreements were signed between our participant cooperatives and VSLAs, and a private-sector buyer, Oltotoi Ranch, facilitating KShs. 28.3m livestock trade in Garissa County. Similarly, Oltotoi Ranch signed agreements with Kuza Jamii 2 supported Laramatak Cooperative in Samburu County. The cooperative aggregated 112 bulls from the VSLAs worth KShs. 8.512m. The initial stock of animals was financed through start-up grants, complemented through VSLAs credit and aggregated by cooperatives.

In addition to this trade directly with participant VSLAs and cooperatives, Oltotoi and Meat & Livestock Exporters Industry Council of Kenya (KeMLEIC), accessed surrounding markets, buying KShs. 460m and KShs. 55.65m worth of livestock, respectively, representing a significant early outcome of market linkage efforts. These agreements mark an important transition from informal, spot-market sales toward structured and more predictable market relationships. Key early contributions include improved market certainty through defined buyer relationships; enhanced collective marketing through aggregation of livestock volumes at ward and sub-county level; reduced reliance on intermediaries, contributing to fairer pricing and improved producer margins; and strengthened trust between producers and buyers, supporting repeat transactions and longer-term engagement.

These results provide strong evidence base for national expansion and reinforce the case for continued investment in social protection as a pathway to poverty graduation and long‑term economic transformation.

## C. DETAILED OUTPUT SCORING

Output Title	Maintained timeliness and predictability of payments to HSNP households for both regular and emergency payments
Output number:		1	Output Score:	A: Met Expectations
Impact weighting (%):		30%	Weighting revised since last AR.	No

Indicator(s)	Milestone(s) for this review	Progress
Output Indicator 1.1: Timeliness: % of payments that are made on time to Payment Service Provider for transfer to regular HSNP beneficiaries	100% - approximately 6 out of 6 annual bimonthly (12 monthly) payments made on time	B: Moderately did not meet expectations / GoK has made payments up to Jan 2026, covering the period April 2025 and January 2026. However, there were delays, with catch-up payments making the bulk of the releases.
Output indicator 1.2: / Percentage of regular cash transfers financed by GoK in the original four HSNP counties.	100%	A: Met expectations / 100% of the cash transfer payments to Group 1 (regular) beneficiaries in all 8 HSNP counties (133,800 HH) were paid from GoK domestic sources as a recurrent expenditure to GoK finances.
Output indicator 1.3: / Enhanced financing mechanism for HSNP scalability is implemented using GoK funds.	Emergency payments made to 100% of households triggered in 4 HSNP counties	N/A in the reporting period. / Despite the current drought, HSNP drought triggers were not reached.

Briefly describe the output’s activities and provide supporting narrative for the score.
This output ensures GoK’s commitment to regular and predictable financing for cash transfers, both regular and emergency, for institutionalisation and sustainability. It supports predictable planning of expenditure by beneficiaries, including small scale livelihood projects. Cash transfers transitioned to 100% GoK management and financing, with payments made up to January 2026. Despite this, payment delays occurred. FCDO worked with the WB, leveraging the DPO and other instruments and engaged with broader stakeholders to find champions. Overall, the output met expectations.

Output Indicator 1.1 – B: Moderately did not meet expectations – This indicator measures the timeliness of payments for Group 1, where a payment is considered timely if households receive their transfers monthly or bimonthly. Although staggered and with some delays, the payments have been made up to date. Reports show scattered releases in July–August 2025 and two catch‑up tranches in January (covering arrears for Sept–Nov 2025 and Dec 2025–Jan 2026, respectively). NDMA attributed the delays primarily to irregular exchequer releases and significant funding shortfalls, reporting a gap of KShs. 3.9 billion for HSNP in the 2024/25 financial year, occasioned by Kenya’s constrained fiscal environment.

Output Indicator 1.2 – A: Met expectations - 100% of the cash transfer payments in the eight counties of Marsabit, Mandera, Turkana, Wajir, Isiolo, Samburu, Tana River and Garissa were paid from GoK domestic finances. This is significant progress compared with previous years. Our field visits and discussions with beneficiaries have demonstrated that HHs continue to rely on monthly payments for their basic needs - food, education, and health care.

Output Indicator 1.3 – Not Assessed – This indicator measures the GoK’s efficiency in financing emergency (Group 2) payments from its own budget when HSNP drought triggers are reached and formally declared. Although drought conditions persisted across the HSNP operating counties during the reporting period, the anticipated trigger thresholds were not met, and no official drought trigger declarations were issued. Consequently, Group 2 emergency payments were not activated, and GoK was not required to mobilise emergency financing for HSNP during this period.

Economic Impact of Cash Transfers
HSNP cash transfers represent a substantial injection of cash with impressive multiplier effects. According to the 2018 evaluation, each KShs.1 of HSNP transfer that enters the local economy generates an additional KShs. 0.93 of total income. In practical terms, the KShs.778.5 million disbursed in the December 2025–January 2026 HSNP payment cycle is estimated to generate between KShs. 1.44 billion and Kshs.1.59 billion in nominal local income, based on the 2018 evaluation’s multipliers. When adjusted for inflation, this translates into between KShs. 1.05 billion and KShs. 1.11 billion in real income gains for ASAL communities. These results reinforce HSNP’s critical role not only in protecting consumption but also in stimulating local markets, supporting small enterprises, and strengthening economic resilience during periods of drought and economic stress.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph] There is no material change to this output during the past one year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]. The main recommendation from the previous annual review was the closure of Output Indicator 1.4, which has been fully achieved. The Logframe has been updated accordingly.

Recommendations for the year ahead
Recommendation	Description	Responsibility	Timelines
Continuous advocacy for GoK to prioritise cash transfers	Although the HSNP consumption cash transfers have completely transitioned to GoK, delays and risk of reprioritisation as a result of constrained fiscal space remain significant. The UK should continue advocating for the prioritisation of the cash transfers, using levers like the WB DPO and political persuasion to maintain momentum.	Programme Team (technical level and PS level) / DD/DDD and HC (Governor, Ministerial and Presidency level)	Continuous

Output Title	The National Drought Management Authority (NDMA) strengthened to lead, coordinate, and manage drought response including cash transfer programmes in the HSNP ASAL counties
Output number:		2	Output Score:	B: Moderately did not meet expectations
Impact weighting (%):		15%	Weighting revised since last AR.	Yes – from 25% to 15%

Indicator(s)	Milestone(s) for this review	Progress
Output Indicator 2.2: Improve financial capacity of NDMA to finance emergency cash transfers through Disaster Risk Financing (DRF)	NDMA manages drought emergencies in accordance with the DRF Plan	B: Moderately did not meet expectations. The National Drought Emergency Fund (NDEF) was funded, receiving KShs165.6 million in 2025, and the HSNP shock‑responsive trigger and scalability mechanism continues to exist by design. However, the DRF strategy that previously enabled pre‑arranged financing instruments expired in 2018, and although the National Treasury is finalising a new strategy, it was not yet in place.

Briefly describe the output’s activities and provide supporting narrative for the score.
This output seeks to support NDMA to fully take over the management, leadership and coordination functions required to deliver the HSNP, including transition from outsourcing technical assistance and embed staff within the NDMA and to lead on disaster preparedness and response. Overall, the output scored a ‘B’ supported by the following narrative.

Output Indicator 2.2 – B: Moderately did not meet expectations – This indicator measures the financial capacity of NDMA to finance emergency HSNP (Group 2) cash transfers through Disaster Risk Financing (DRF) mechanisms. The HSNP Financing Plan[12] allows GoK to fund emergency scale-ups through risk layering, including National Drought Emergency Fund (NDEF) and risk transfer components. During the reporting period, NDEF is funded and received at least KShs. 165.6 million in 2025. Additionally, evidence confirms the design of HSNP’s shock‑responsive, trigger‑based scalability mechanism. However, the DRF strategy that allows for pre‑arranged DRF financing instruments expired in 2018. The National Treasury, with the support from the UK, is finalising the new strategy.
[12] The HSNP Financing Plan is the Government of Kenya’s structured approach for ensuring that predictable, adequate, and timely financing is available for both: i) Regular (Group 1) cash transfers, and ii) Emergency (Group 2) shock‑responsive cash transfers delivered through Disaster Risk Financing (DRF) mechanisms. It sets out how NDMA should finance emergency HSNP payments, the sources of funding, and the trigger‑based rules that determine when funding should be released. The plan outlines the risk‑layered financing structure, including: i) Exchequer‑allocated contingency budgets; ii) The National Drought Emergency Fund (NDEF); iii) Early/anticipatory action financing; and iv) Any pre‑arranged or scalable DRF instruments. These collectively determine NDMA’s ability to pay Group 2 beneficiaries when drought triggers are met.

The failed/below average OND rainy season led to a devastating drought, with the Famine Early Warning Systems Network (FEWs NET) estimating that approximately 3.45 million people in the country are at risk of hunger. In Mandera, Garissa, and Wajir counties, acute food insecurity outcomes (IPC 3 and 4) persist, with 287,700, 139,050, and 130,650 people respectively facing Integrated Food Security Phase Classification (IPC) 3+ food insecurity. Approximately 80–90 percent of the population in these areas depend on pastoral and agro-pastoral livelihoods, making households highly vulnerable to extreme weather shocks. However, the drought national triggers have not been met for HSNP to disburse funds to Group 2. As a result, the UK funded a two‑month drought response in Wajir, Garissa, and Mandera counties, delivering lifesaving nutrition services, KShs. 7,000 cash transfers, and child protection support to 79,523 vulnerable people through integrated screening, treatment, mobile outreaches, and unconditional cash linked to behaviour‑change messaging, all targeted using the HSNP Enhanced Single Registry to prevent duplication and coordinated closely with county authorities and humanitarian partners. This support will help ensure HHs resilience during this period.

Describe any changes to this output during the past year, and any planned changes as a result of this review. No changes were made to this output during the reporting year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.
The key recommendation from last annual review was the closure of output indicator 2.1 which has been completely achieved. The Logframe has been updated accordingly.

Recommendations for the year ahead

Recommendation	Description	Responsibility	Timelines
Early warning systems	Discuss with government if the triggers agreed in early stages of this programme remain valid due to the frequency of disaster (including drought and floods).	Programme Team	December 2026

Output Title	Improved coordination and alignment of HSNP with the wider National Safety Net Programme (NSNP)
Output number:		3	Output Score:	Not assessed
Impact weighting (%):		0%	Weighting revised since last AR.	Yes. Reduced from 20% to 0%

Indicator(s)	Milestone(s) for this review	Progress
Output Indicator 3.3: a) Number of households receiving NICHE package of nutrition sensitive social protection services (Indicate number in HSNP counties) / b) Number of HSNP households receiving monthly visits from a community health volunteer with nutrition counselling (Indicate number in HSNP counties)	a) 13,800 / b) 13,800	Not assessed / Due to funding prioritisation, the NICHE component was not funded.

Briefly describe the output’s activities and provide supporting narrative for the score.

Most of the indicators were achieved in the previous years. Due to reduction of funding the last indicator on nutrition was deprioritised this year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

The main recommendation from the previous AR focused on institutionalising of the NICHE programme, including ODR, through demonstration at scale. However, due to fund prioritisation, NICHE was not funded. As a result, we reduced the weight of this output.
Lessons:
The long‑term nature of development advocacy and systems strengthening- Under this output, the target was to support the wider National Safety Net Programme (NSNP) to adopt coordinated and harmonised systems and approaches across all non‑contributory safety net programmes.
Throughout the programme lifetime, continuous policy dialogue, technical working sessions, and multi‑stakeholder consultations were held to advance the harmonisation agenda. These engagements focused on aligning processes for non‑contributory cash transfers, promoting coherence in targeting, delivery systems, grievance mechanisms, and governance structures across the NSNP.
These sustained influencing efforts contributed directly to the drafting of the first version of the Social Protection Bill (2025), whose core purpose is to provide coherence and establish a unified legal framework for social protection in the country. The bill has since progressed through the legislative process and was enacted into law. The National Board for Social Protection is the central governance body created by the Social Protection Act 2025 to coordinate, oversee, and regulate all non‑contributory social protection interventions in Kenya, marking a major milestone in institutionalising harmonised social protection systems.

Output Title	Increased access to evidence on economic inclusion/graduation interventions and shock responsive social protection interventions
Output number:	4	Output Score:	A – Met Expectations
Impact weighting (%):	50%	Weighting revised since last AR.	Yes – Increased from 5% to 50%

Indicator(s)	Milestone(s) for this review	Progress
Output Indicator 4.1: Evidence on testing graduation/ economic inclusion approaches generated through independent M&E	Graduation programmes working effectively and at scale, both in 5 pilot counties and expansion counties	A: Met expectations. / The EIP is working effectively and scaled to 8 HSNP counties. See details in the narrative below.
Output Indicator 4.2: Evidence generated on impacts of cash transfers in improving resilience against the impacts of covariate shocks (including COVID-19)	Number of policy or programme changes made by the GoK regarding shock responsiveness as a result of evidence generated / (# 3 changes)	A: Met expectations. / Various programme and policy changes were implemented from evidence gathered. / The National Ultra‑Poor Graduation Strategy. / County Governments agreed to integrate Ultra‑Poor Graduation into their County Integrated Development Plans (CIDPs). / The Mentor training curriculum was validated and adopted for KSEIP2.

Briefly describe the output’s activities and provide supporting narrative for the score.

The focus of this output is to generate evidence, promote learning and testing complementary graduation and economic inclusion models necessary to improve the resilience of poor and vulnerable households. The output indicators met expectations. Over the last two years, the programme has focused on demonstrating EIP at scale across the eight counties, transforming HSNP into a platform for poverty graduation.

Output Indicator 4.1 – A: Met expectations – During the reporting period, EIP operated effectively in all 8 counties. Programme level results indicate the foundations have been set, achievements:

- Effective Outreach and Engagement: The programme's ability to reach 14,401 direct participants, and 68,440 people indirectly demonstrate its effectiveness in engaging the target population. This outreach is crucial for fostering economic inclusion and ensuring that vulnerable groups have access to resources and support.
- Business Development and Growth: The reported 25% increase in Total Business Value (TBV) among 9.44% of Business Groups within 2 months indicates that the EIP is successfully facilitating business growth. This growth not only enhances individual livelihoods but also contributes to local economic development, creating jobs and stimulating the economy.
- Enhanced Food Security: The significant rise in meal uptake, with over 90% of households now reporting access to at least two meals daily, suggests that increased income levels are directly improving food security among participants. This suggests that HHs are prioritising nutrition, which is critical for overall health and productivity. Further analysis could explore the health outcomes associated with improved food security, such as reductions in malnutrition rates or improvements in child health indicators.
- Income Stability and Growth: The consistent monthly increase in participants' contributions, with the average monthly savings reaching Kshs.2,430.46 within 2 months (January to February 2026), reflects a positive trend in income stability. In addition, 67.39% of participants have already met or exceeded the KShs.4,000 savings target. This improvement is essential for long-term economic resilience, allowing households to invest in education, health, and other critical areas.
- Financial Empowerment through Savings: The accumulation of KShs.26,570,466 in savings within 2 months by VSLAs highlights the programme's role in promoting financial literacy and empowerment. By facilitating savings, the EIP enables participants to build financial security and access funds for emergencies or business expansion.
- Market Access and Opportunities: The establishment of market linkages through trade fairs and partnerships, exemplified by the various agreements for livestock supply between Oltotoi Ranch and Kuza Jamii supported cooperatives, demonstrates the EIP's success in enhancing market access. This access is vital for ensuring that participants can sell their products and services, thereby increasing their income potential.
In summary, the EIP is making significant strides in promoting economic inclusion, improving livelihoods, and fostering sustainable business practices. The programme's focus on outreach, business development, food security, financial empowerment, and market access is creating a positive impact on participants and the wider community, contributing to long-term economic resilience and growth.

VSLAs face significant challenges with physical cashboxes and low digital literacy, limiting access to formal finance. The UK’s Digital Access Programme (DAP) tackles these barriers by promoting basic digital inclusion for underserved groups, supporting Kenya’s goal to connect three million youth to digital jobs, and strengthening cybersecurity and online safety. So far, 532 VSLAs/cooperatives have been sensitised, reaching 4,480 beneficiaries. 224 Community Digital Champions (CDCs) are delivering training and 6,160 VSLA members have begun digital literacy training. Beyond basics, 371 CDCs completed AI Literacy training modules, enhancing their capacity to deliver AI literacy sensitisation to communities. At intermediate level, 46 learners completed courses on Digital Agriculture, 36 on IT Technician, 38 on Gig Economy, and 33 on Creative Economy. These efforts expand economic opportunities and support VSLA members’ safe transition into digitally enabled financial services.

### Impact of the Economic Inclusion Programme (EIP)
The EIP has demonstrated significant effectiveness in enhancing the livelihoods of vulnerable populations by providing targeted support through business start-up grants and fostering entrepreneurship and economic self-sufficiency. Within 2 months, 3,041 Business Groups (BGs) had been successfully established, with 9.45% of them having more than 25% increase in Total Business Value (TBV), indicating that the EIP is not only facilitating initial capital access but also promoting sustainable business growth. This growth is crucial for reducing poverty levels and improving overall economic resilience within communities.
The endline evaluation of the first year of scaled up implementation in the 8 ASAL counties, known as Kuza Jamii 1, indicate the foundations for the household economic resilience and graduation trajectory have been set. To meet the graduation criteria, households had to demonstrate attainment of thresholds in the three core areas (food security, savings, and income) with a minimum pass rate of 75%, while improvements in social inclusion were assessed to track broader empowerment outcomes. The following are the reported impact;

On improved food security and nutrition outcome area, 94% of all household members had at least two meals per day in the last seven days recall period.

Increased savings and access to credit was observed: 76% of the participants had active membership in a functional, registered savings group with savings, credit, and social fund services, and a minimum total savings of KShs,4,000 at exit. Savings behaviour transformed, participants with savings increasing from 31% at baseline to 99% at endline and the amount saved increased from KShs. 1,309.98 to KShs. 14,669.14 - a significant mean difference in savings of KShs. 13,359.16. In total, the VSLAs held KShs. 103m (approx. 600,000 GBP) in savings within 6 months.

Increased income and sustainable livelihoods was a major impact area, with 75% of the HH having diversified income sources. The average monthly income across all households increased from KShs.5,074 at baseline to KShs.10,752 at endline, an 89% increase. 71% of the business start-ups showed a total business value (TBV) increase of 25% of total seed capital (start-up grant).

Overall Human Development Index (HDI) Score[13] - At baseline, 63% fell into the low HDI category, with 32% in the moderate range and only 5% achieving a high score. By endline, a significant transformation was evident: 94% of participants were classified in the moderate HDI category, while those in the low category dropped to just 2%. These trends underscore the broad and meaningful improvements across multiple development dimensions, highlighting EIP’s impact in advancing household stability, resilience, and well-being.
[13] The Human Development Index (HDI) is a widely recognized composite measure that captures multidimensional aspects of human well-being, including health, education, and standard of living. Within the endline evaluation, the HDI assessment was adapted to assess participants’ individual and household-level progress across these domains, providing a more holistic view of poverty graduation beyond income alone.
Output Indicator 4.2 – A: Met expectations – 3 policy changes were implemented; i) The National Ultra‑Poor Graduation Strategy was finalised, providing a unified national framework for scaling economic inclusion and integrating graduation pathways across Kenya’s social protection system; ii) County Governments agreed to integrate Ultra‑Poor Graduation into their County Integrated Development Plans (CIDPs), following negotiations facilitated through the Council of Governors (CoG), thereby institutionalising graduation approaches within county‑level planning, budgeting, and service delivery systems; iii) Following requests to harmonise the Mentor Training Curriculum for the operationalisation of the Ultra Poor Graduation Strategy, Kuza Jamii supported the GoK to draft the new curriculum. The curriculum was developed together with the Kenya School of Government and the Kenya Institute of Curriculum Development for both quality assurance and acceptance as a government curriculum. The curriculum was validated and adopted for use in KSEIP2.

Describe any changes to this output during the past year, and any planned changes as a result of this review. There were no changes to the output during the past year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.
The key recommendation/action from the previous AR was to expand the EIP to additional counties, which was achieved through expansion to 8 HSNP counties.

Recommendations for the year ahead:

Recommendation	Description	Responsibility	Timelines
Support KSEIP2 roll out	The UK used evidence to prove that EIP is a strong vehicle to provide poor and vulnerable households a pathway out of poverty, this was used to design the KSEIP2 (approved by the Board). With the foundations set and declared effective to start implementation, the UK will provide Technical Assistance to support the roll of the programme in 20 counties, helping in the initial steps towards institutionalisation of EIP into GoK budgeting processes.	Programme Team	June 2026
Transfer EIP systems, structures, assets and select staff to KSEIP2	During the EIP scale‑up in the eight HSNP counties, the programme recruited and trained mentors, procured productive assets, established governance structures, strengthened data systems, and built the capacity of government officers. To ensure sustainability and avoid parallel systems in the next phase, these structures, systems, and responsibilities should be formally transitioned to KSEIP2 to enable full GoK ownership and continuity.	Programme Team	May 2026

Lessons:

1. Evidence‑driven demonstration convinces successful government adoption and scale-up - A key lesson from the past two years is that generating strong evidence and demonstrating feasibility at scale are critical for government ownership and nationwide adoption. Through systematic pilots, rigorous evidence gathering, and practical demonstration of the EIP model at scale, we demonstrated that the intervention is both effective and operationally realistic within government systems. This evidence directly informed the Government’s decision to scale EIP countrywide, illustrating the power of an evidence‑based influencing approach. At the same time, intentional efforts to build the capacity of government officers and strengthen delivery systems ensured a smooth foundation for the transition, reinforcing that scaling is only sustainable when government systems are deliberately prepared to take over.
2. Private sector engagement thrives when risks are minimised and profit pathways are clear - A key lesson emerging from the programme is that the private sector is willing and ready to engage with community‑based economic initiatives when their risks are reduced and the profit opportunity is clearly defined. Through the establishment of VSLAs, collectively saving approximately USD 1 million in 6 months, the programme demonstrated a viable and growing financial ecosystem at the community level. Presenting these savings as a bankable business opportunity successfully attracted interest from private sector actors, particularly financial institutions. Overall, the experience shows that private sector engagement is not only possible but highly impactful when community structures are strong, financial flows are visible, and incentives are aligned. This creates a foundation for sustainable, market‑driven support to vulnerable households.
Output Title	Monitoring, evidence, and learning improve poverty graduation and capacity building programme quality of HSNP
Output number:		5	Output Score:	A: Met Expectations
Impact:		5%	Weighting revised since last AR	Yes – reduced from 20% to 5%

Indicator(s)	Milestone(s)	Progress
Output Indicator 5.1: # of programme changes made as a result of robust and performance-based monitoring data (to include assessing the capacity building element).	2	A: Met Expectations / Kuza Jamii 1 End of Project Report was shared during the period under review. This report, together with field monitoring visits in Samburu and Isiolo Counties on the performance and learning led to programme changes in Kuza Jamii II, including; / Embedding a clear transition strategy as a deliverable for the programme; / Embedding basic digital literacy and cybersecurity training in the design of the programme
Output Indicator 5.2: # of improvements made to programme delivery based on evidence from evaluations	2	A: Met Expectations / Kuza Jamii I Endline Evaluation Report Kuza Jamii 1 Learning Report and the Gender Equality and Social Inclusion (GESI) Analysis Report for the Kuza Jamii 1 Project were shared during the reporting period, leading to changes in programme delivery, including; / Joint implementation and monitoring with government officials to build capacity and lay the foundation for a sustainable programme transition / Group-based mentorship and separation of mentorship and monitoring roles offering a promising, scalable model. / Introduction of household methodologies such as Gender Action Learning Systems (GALs) approach and male champions to improve power and decision making of women and girls.
Output Indicator 5.3: # of case study/ deep dives written and disseminated	2	A: Met Expectations / Political Economy Analysis (PEA) of GoK Policymakers’ support and resourcing for resilience policies, systems and investments deep dive was written and disseminated.

Briefly describe the output’s activities and provide supporting narrative for the score.

This output aims to improve the monitoring, evaluation, and learning elements of the programme. While the output met expectations, the evidence base is primarily drawn from partner reports, rather than independent monitoring or evaluation.

Output Indicator 5.1 – A: Met Expectations. This indicator tracks the count of documented programme adjustments - policy, operational, technical, or implementation changes - that are directly informed by monitoring data. These changes must be linked to evidence from: i) Routine performance monitoring; ii) Process monitoring; iii) Capacity‑building assessments; iv) Data quality assessments; and v) Evaluation feedback incorporated into programme redesign. A programme change includes any modification that alters programme design, delivery, targeting, operational procedures, stakeholder coordination, or capacity‑strengthening approaches.

Kuza Jamii 1 End of Project Report (Annex 2): The overarching conclusion from the report was Kuza Jamii 1 marked a decisive shift in how economic inclusion is designed, delivered, and institutionalised in Kenya. Rather than operating on the margins of government systems, the programme was structured from the outset to test whether an ultra-poor graduation model could be implemented at scale, through public infrastructure, in fragile contexts, and with a clear path to sustainability. To institutionalise and make this process measurable, Kuza Jamii 2 developed a clear transition strategy as a deliverable for the programme. The strategy provides a clear six-month roadmap for transferring programme leadership, governance structures, delivery systems, select staff like mentors, select programme assets like motorbikes, and delivery functions from Kuza Jamii to KSEIP2. The transition process is led by the Directorate of Social Development (DSD) in close collaboration with NDMA, the Council of Governors, respective County Governments, the World Bank and other national actors, with operational transition managed by Kuza Jamii consortium partners.

During a joint field visit, (UK, MoH, Directorate of Children Services (DCS), Directorate of Social Development (DSD) and UNICEF) to Samburu and Isiolo, the team witnessed one of the VSLAs in Kina, Isiolo accumulated KShs.373,200 in regular savings, Kes. 28,100 in a social fund, and KShs. 27,290 in SWAP contributions, with a total net worth of KShs.450,290 and official certification. However, these savings were kept in metal boxes, posing both a safeguarding and security risk. To mitigate against these risks, the programme has enlisted the Digital Access Programme to train VSLA members on basic digital literacy and cybersecurity, allowing them to digitise their records and transactions in safe and secure digital platforms.

Output Indicator 5.2 – A: Met Expectations. This indicator measures the count of concrete, documented changes made to programme delivery that are directly informed by evaluation findings, including; Mid‑term evaluations, End‑line evaluations, Thematic or special studies, Process evaluations and/or Impact assessments. An improvement refers to any modification that enhances effectiveness, efficiency, relevance, timeliness, targeting accuracy, accountability, or beneficiary experience.

Kuza Jamii I Endline Evaluation Report (Annex 2): The report recommended the sustenance of the learning platforms for Kuza Jamii 1 by institutionalising joint monitoring, governance structures, and inter-county exchanges as core program features to drive policy uptake and scale. This recommendation was adopted by Kuza Jamii 2 onset, which developed clear governance structures, based on KSEIP2 operational manuals, both at the national and subnational level. These structures are led by GoK officials as envisaged in KSEIP2, including the leadership of joint implementation and monitoring. This is also spelt out in the transition strategy.

Kuza Jamii 1 Learning Report (Annex 2): The report highlights that EIP’s most effective feature, mentorship, is strongest when delivered through group-based sessions and when mentorship and monitoring roles are separated. Kuza Jamii adopted this scalable model by introducing VSLA-level group mentorship and hiring enumerators for data collection, allowing mentors to focus on coaching and improving data quality. While it requires strong facilitation to ensure inclusive support, the model is both cost-efficient and scalable and has now been embedded in Kuza Jamii 2 and the design of KSEIP2.

Gender Equality and Social Inclusion (GESI) (Annex 2): the analysis Report for the Kuza Jamii 1 Project found that restrictive gender and social norms limit women’s and PWDs’ participation in economic decisions: men dominate household decision-making, PWDs are viewed as outcasts, and cultural and religious norms discourage women’s leadership and autonomy. These findings informed Kuza Jamii 2 and KSEIP2, which now incorporates household methodologies such as Gender Action Learning Systems (GALs) to promote shared decision-making and reduce unpaid care burdens, and targeted engagement of men and boys to challenge harmful stereotypes and foster male allyship.

Output Indicator 5.3: Met Expectations - Political Economy Analysis (PEA) of GoK policymakers’ support and resourcing for resilience policies, systems and investments deep dives (Annex 2): The new four‑pillar financing framework offers promising avenues for sustaining and expanding these systems:
1. Domestic Resource Mobilization - Agenda 2063 emphasises Africa financing its own development by strengthening domestic resource mobilization to create virtuous cycles of growth and expanded fiscal space. Evidence of the strong returns from resilience investments boosts political commitment and enhances Africa’s influence in the global development arena.
2. New Roles for Development Partners - Development partners are transitioning from funding major programmes to providing technical assistance, strengthening capacities, generating knowledge, and protecting global public goods. These new roles help sustain trust and cooperation, ensuring partnerships continue to deliver mutual benefit.
3. Green Finance - National leadership, supported by development partners, is enabling countries to tap into green finance, the only rapidly expanding development resource, by aligning resilience and climate investments. Embedding these initiatives in NDCs accelerates access to green funding and fosters “prosperity magnets” through resilience programmes that create green jobs.
4. Philanthropic Public‑Private Alliances - The fourth pillar mobilizes innovative public‑private‑philanthropic partnerships that bring entrepreneurial, managerial, and financial capabilities into national development. This new philanthropy strengthens good governance and revitalizes global cooperation, with African countries benefiting from diverse and aligned support.
This deep dive, aligning with UK Minister for International Development and Africa’s four shifts, redefines our approach to development by refocusing our plan for the next years to;
1. Advocating for the government to continue prioritising social protection in its domestic budget processes;
2. Providing technical assistance to KSEIP2, leveraging WB IDA financing to provide service delivery at scale and using evidence to influence strategic direction;
3. Engaging philanthropies and foundations to invest in social protection. For example, we influenced CIFF, who have committed $25m to KSEIP2, and the Gates Foundation, committing $2m. We are exploring new partnerships with Mastercard Foundation through BRAC.
4. Consider lessons learned by other countries that use green finance and share with GoK.
Describe any changes to this output during the past year, and any planned changes as a result of this review. No changes were made to this output during the reporting year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead. Lessons learnt presented together with output findings.

## D: VALUE FOR MONEY

VfM performance compared to the original VfM proposition in the business case.

The assessment of VfM is carried out using the FCDO’s approach for VfM. The framework outlines the ‘4Es’ approach: Economy, Efficiency, Effectiveness, and Equity of interventions.

The original BC VFM proposition was anchored on an independent evaluation by OPM which found that HSNP2 had increased spending on food, improved food security including during drought, and thus had reduced extreme poverty of benefitting households[14]. The paragraphs below describe the VfM based on the 4Es approach.
[14] Otulana, S. et al (2016). Evaluation of the Kenya Hunger Safety Net Programme Phase 2. OPM, Oxford. http://www.opml.co.uk/sites/default/files/Evaluation_of_the_Kenya_Hunger_Safety_Net_Programme_Phase_2_Impact_Evaluation_Qualitative_Research_Study_Round_1_2_0.pdf

Economy - buying inputs of appropriate quality at the right price (Cost-Effective Resource Utilization)
The UK’s investment of £10 million delivered strong economy by purchasing high‑quality inputs that generated substantial results at competitive cost, enabling the programme to reach 14,401 direct participants and 68,440 indirect beneficiaries, demonstrating wide outreach and deep community penetration. With this spend, the programme established 3,041 Business Groups in two months, with 9.44% achieving a 25% increase in Total Business Value, reflecting strong early returns on modest start‑up grants and business coaching. These inputs translated into rapid improvements in household welfare: over 90% of participants now eat at least two meals a day, rising to 94% at endline; average savings increased to KShs. 2,430 within two months, with 67.39% already meeting the KES 4,000 target; and VSLAs mobilised KShs. 26.57 million in two months, demonstrating exceptional financial empowerment and disciplined saving at low delivery cost. Households achieved major economic gains, including 75% income diversification, an 89% rise in monthly income (KShs. 5,074 to 10,752), and 71% of start‑ups recording at least 25% TBV growth, showing strong returns on the inputs purchased. Human development impacts were achieved at low marginal cost. The programme also secured cost‑efficient market access, with structured partnerships enabling livestock sales worth KShs. 28.3m in Garissa and KShs. 8.5m in Samburu, improving producer incomes without heavy operational expenditure. To further maximise value, the UK invested in digital literacy and safe financial access, training 532 VSLAs, 224 Community Digital Champions, and 6,160 VSLA members, alongside AI and digital skills training, enabling a low‑cost transition to digital systems. Together, these results demonstrate that the UK’s £10m spend purchased cost‑effective, high‑quality inputs that generated large‑scale welfare improvements, strong livelihood gains, and systems‑level strengthening representing excellent economy.

Efficiency - how well inputs convert to outputs (Streamlined Processes and Operations)
HSNP continues to operate efficiently because GoK has fully institutionalised the programme as a recurrent monthly expenditure, allowing payments to continue up to January 2026 despite fiscal pressures. Delivery systems have become more efficient through the Enhanced Single Registry and integrated MIS, which reduce duplication and streamline processes across NSNP programmes. At community level, UK funded delivery teams supported the formation of 3,041 Business Groups, outreach to 14,401 direct participants, and rapid mobilisation of KShs. 26.57m in VSLA savings within two months, achieved through low-cost community structures and group-based mentorship. UK resources enabled efficient market linkage facilitation, resulting in livestock sales worth KShs. 28.3m in Garissa and KShs. 8.5m in Samburu, without costly subsidies. Digital investments through DAP trained 224 Community Digital Champions, sensitised 532 VSLAs, and enrolled 6,160 members in digital literacy, improving record keeping and reducing administrative burden. Established governance structures also enabled rapid, low-cost delivery of the UK funded drought response by using ESR data for accurate targeting. Ongoing digitisation of VSLAs through the DAP is expected to further improve operational efficiency by strengthening business management and record-keeping.

Effectiveness - how well outputs produced by an intervention have the intended effect (Achieving Intended Outcomes) e.g., reduction in poverty and inequality
The programme continues to demonstrate strong effectiveness. HSNP provided regular payments to 133,800 households, stabilising consumption and protecting resilience during drought. Evidence shows high economic returns, with every KSh. 1 transferred generating KSh. 0.93 in additional income, creating substantial local multiplier effects. EIP results indicate major improvements in welfare: 94 percent of participants consumed at least two meals a day, average savings rose from KShs. 1,309 to KShs. 14,669, monthly income increased by 89 percent, and 75 percent of households diversified their livelihoods. Refugee integration pilots in Dadaab and Kakuma further show that extending national systems to camp settings is feasible and cost-effective. With an investment of £10m, the programme reached 14,401 direct participants and 68,440 indirect beneficiaries, equivalent to around £694 per direct household for a full graduation package including grants, coaching, market linkages, digital inclusion, and systems strengthening. Market linkage supports enabled livestock sales worth KShs. 28.3m (Garissa) and KShs. 8.5m (Samburu) at minimal delivery cost. Evidence funded by the UK informed the National Ultra‑Poor Graduation Strategy, integration of graduation into county CIDPs, and national adoption of the Mentor Training Curriculum, showing the UK’s investment was highly cost‑effective in achieving both household‑level outcomes and systems‑level reforms. At the systems level, the inclusion of cash transfers as a conditionality in the World Bank DPO strengthened incentives for timely GoK payments. Overall, the programme delivers high impact both at household level and through national policy and systems reforms.

Equity - interventions that reach marginalised or hard to reach populations (Fair and Inclusive Access)
The programme delivers strong equity by targeting the eight ASAL counties with the highest poverty and climate vulnerability, ensuring resources reach the most marginalised. Seventy percent of HSNP beneficiaries are female-headed households, advancing gender inclusion. EIP further strengthens equity by integrating 1,000 refugees in both Dadaab and Kakuma, demonstrating practical alignment with the GoK Shirika Plan. The use of GALs and male-champion approaches in Kuza Jamii has driven improvements in nutrition, savings participation, and women’s decision-making power. Overall, the programme consistently prioritises the hardest-to-reach households and demonstrates inclusive, pro-poor delivery.

Assessment of whether the programme continues to represent value for money.
Drawing on evidence presented above, HSNP3 represents strong Value for Money through;
- Exceptional leverage of domestic and multilateral financing.
- Efficient use of existing systems, reducing duplication and long‑term operational costs.
- Highly effective results on poverty reduction, resilience, and food security.
- Deep equity focus, reaching and empowering the poorest households, women, and refugees.
The programme demonstrates a compelling VfM proposition, anchored in systems strengthening, sustainability, and long‑term reduction of humanitarian need.

E: RISK
Overview of risk management
The programme was assessed as a “moderate” risk programme for this review, with all risks across the seven categories remaining within FCDO’s risk appetite n FCDO’s risk appetite. Key potential risk related to delayed GoK funding due to fiscal pressure which partially materialised. As at the time of this review, HSNP cash transfers payments are up to date. The key risks remained under policy and programme delivery, contextual and climate shocks, however this review has updated the context under the summary section.
- Delayed payments of cash transfers and/or reprioritisation of social protection: Social protection sector could be de-prioritised given Kenya’s constrained fiscal environment. Whilst the social protection sector has classified cash transfers as a recurrent budget, lobbying needs to be sustained to ensure that the funds are released for timely payments to beneficiaries. FCDO will work closely with the World Bank via the DPO to ensure GoK delivers on its commitments.
- Climate shocks: Intensifying climate variability continues to threaten household resilience in ASAL counties. Below-average October–December 2025 rains have already driven drought conditions, increasing household reliance on HSNP transfers and placing pressure on local systems. Prolonged shocks risk eroding livelihoods faster than the programme can buffer them. Continued strengthening of Disaster Risk Financing within the 2026-2030 strategy remains essential to ensure predictable, multi-hazard resources for HSNP scaleups during future climate events.
- Safeguarding Risks: Safeguarding remains a significant area of vigilance given the vulnerability of HSNP beneficiaries and the complexity of operating contexts. During the review period, a whistleblower report from a partner organisation raised concerns including leadership misconduct, sexual harassment, and HR irregularities. An independent investigation confirmed isolated cases of misconduct but found no financial misappropriation. The partner has since implemented all required actions, and activities resumed following mitigation. To strengthen long-term safeguards, the programme integrates GBV-sensitive approaches within economic empowerment interventions, addresses harmful gender and power dynamics, and requires delivery partners to conduct regular community and household safety audits with mitigation plans. This ensures safeguarding remains embedded in both systems and frontline delivery.
- Fiduciary: Misuse of funds e.g. risk of agency malpractice. The programme team working to ensure that all implementing partners have adequate control systems in place to prevent and detect any misuse of funds including carrying out external audits should there be a concern.  Programme Management team to continue to monitor the risks closely. The whistle-blower, mentioned above on safeguarding risk, also raised allegations of fraud; however, following a full investigation, it was confirmed that no HMG funds were lost.
- Transition of assets, systems, and staff to GoK: The programme is undergoing a major transition as assets, systems, structures, selected staff (such as mentors) move to GoK for integration under KSEIP2. While the transition is progressing on track, the scale of the handover introduces risks related to variable county capacity and inconsistent documentation. Joint verification in five counties in January confirmed strong asset control and accountability, with minor inconsistencies in asset tagging gaps in Isiolo. The programme team conducted a follow-up spot check in Isiolo in March and confirmed that the inconsistences had been addressed and the asset register updated accordingly. A structured, phased process using standard government templates and oversight from DSD, is helping to maintain continuity and reduce fragmentation risks.
- Donor Reprioritisation / External Financing Uncertainty: Reduced predictability of external financing for social protection and humanitarian sectors affected complementary programmes and partner delivery capacity. This trend informed the request for RAF support to mitigate short‑term funding uncertainties. The risk was rated moderate and RAF allocation was secured as a mitigation.
Programme risks are actively monitored through an online risk register, discussed and reviewed regularly with partners during quarterly and mid-year missions. Escalated risks, e.g. the safeguarding and fraud risk noted above, are escalated and formally reported to Reporting Concerns investigations team. High level risks requiring government support from GoK are raised in monthly Social Protection Working Group meetings, and the HMG Aid Management Platform system is updated accordingly. The risk register was last updated in January 2026.

Despite the key risks, HSNP implementation has remained within its cautious risk appetite and aligned with appetites across all seven categories.

Recommendation: Following completion fraud and safeguard, it is recommended that the case be formally closed with the Investigations Department and a cross-office lessons-learnt session be delivered. Action: Programme Team by April 2026.

Update on Partnership Principles

The PPs note that the UK should not provide its bilateral funding through GoK’s Public Financial Management systems referred to as ‘direct Government-to-Government bilateral financial aid’[15]. During the reporting period, there was no bilateral funding through GoK’s Public Financial Management systems.
[15] This is where finance provided directly by HMG to an official partner government account, usually earmarked to support specified activities.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
Summarise the performance of partners and FCDO, notably on commercial and financial issues

During this review period, the programme had the following components:
- MoUs with UNICEF and World Food Programme (WFP)
- Accountable Grants with BOMA; Village Enterprise and Save the Children UK
- Dual Lock Agreement with the Digital Access Programme (DAP)
- Contract with EPRI
The UK Government decided to reduce ODA from 0.5% to 0.3% of GNI by 2028 triggered internal restructuring and slowed new aid spending decisions for the FY2025/26. Consequently, HSNP partners received delayed funding confirmation, affecting onboarding partners, which was further exacerbated by safeguarding investigations involving one of the partners. Once onboarded, relationships and partnerships were managed through regular performance meetings to review of risks, trends, and overall compliance. Relationships between UK and partners grew significantly enabling frank and honest dialogue to solve problems/challenges as soon as they arose. Reporting shows all partners are performing well - no partner required a performance improvement plan, on track to spend as forecast and deliver against their results frameworks. The UK remains a trusted leader in Kenya’s social protection sector and co-chairs the sector working group.
Commercial: The programme received a one-year no-cost extension up to March 2027 to: i) Provide TA to the Phase 2 of the World Bank funded GoK’s KSEIP2; and ii) strengthen linkages between the private sector actors (market, financial institutions and inclusive insurance) and households supported though KSEIP2’s economic inclusion component.

Asset management and control: Village Enterprise and BOMA maintain up-to-date asset registers. As HSNP transitions to Government, all programme assets will be formally transferred to GoK using standardised government templates to ensure transparency and auditability. Joint planning with DSD agreed a phased verification and transfer process across all counties. The first verification (26–30 January 2026) confirmed strong asset control, with only minor serial number recording updates required in Isiolo. An additional spot check is planned for 11–13 March to confirm corrections before final handover in March 2026. Partners will submit updated registers afterwards. Overall, the findings demonstrate a high level of asset control and accountability within the programme.

Financial Management: The original £94.5m five-year budget (International Climate Finance (ICF) and RDEL spend) was reduced following government wide ODA cuts. The Programme has since received a three-year no-cost extension. During the period under review, the programme secured £1m from the Resilience & Adaptation Fund (RAF), split equally between WFP and UNICEF each to support KSEIP2 preparations. The revised total budget is £91,881,210.25 including £3m planned for next financial year to leverage UK expertise in social protection system strengthening and complement wider investments for long-term sustainability and GoK ownership.

Below is a summary of the programme budget and spend per partner/agreement:

All partners submitted accurate quarterly financial and expenditure reports. Forecasting performance has been satisfactory for all partners. Where variances were expected discussions and adjustments were made on time.

G: MONITORING, EVIDENCE AND LEARNING
Programme team uses the process outlined below to monitor implementation.
Day to day engagement with implementing partners to address tactical programme delivery needs.
Monthly meetings: to track progress against the workplans, aiming to address any emerging operational challenges as they arise. This approach is effective as delivery risks are detected and corrected in a timely manner.
Quarterly progress meetings and reports: to monitor quarterly achievements (programmatic, financial and activity level), as per the results framework. These are also useful for risk deep dive discussions, including analysing and assessing risks in the horizon.
Stakeholder engagement/field visits: field visits to Marsabit, Isiolo and Wajir enabled engagement with stakeholders and beneficiaries, improving understanding of implementation realities and programme impact. The visits confirmed strong foundations for sustainability and readiness for transition to KSEIP2, while identifying the need for better donor coordination and formalised mentor recognition. The START team also conducted a safeguarding spot check in Wajir following concerns regard a partner. They found safeguarding to be well integrated across staff, mentors and beneficiaries, with low fiduciary risk due to limited cash handling, minimal procurement and no prior issues.
Senior leadership and the programme team maintained active engagement with the Governors of Mandera, Wajir and Garissa, as well as with national GoK officials, including the PS for Social Protection. Regular meetings with partners, World Bank, WFP, UNICEF, DRC, UNHCR, BOMA, Save the Children and Village Enterprise, helped sustain dialogue, coordination, track progress and reinforce priorities.
Evidence and Learning: a Political Economy Analysis (PEA) was commissioned, and the findings has been reflected under the relevant output. In addition, the PEA highlighted that Kenya’s progress is being shaped by three waves of policy innovation;
- First Wave: Reducing Vulnerability and Strengthening Household Resilience - Initial reforms focused on poverty reduction and shock absorption. Programmes like HSNP provided predictable cash transfers that stabilised household welfare during crises and established Kenya’s core social protection architecture.
- Second Wave: Cash Transfers Plus – Integrating Human Capital and Livelihoods - The next phase integrated cash with human capital and livelihoods interventions. Programmes such as NICHE and KSEIP demonstrated how combining cash with nutrition, coaching, and economic inclusion support generates stronger development outcomes and more inclusive growth.
- Third Wave: Climate‑Resilient Systems for Long‑Term Prosperity - The emerging wave aligns social protection with climate resilience and long-term prosperity. In Kenya’s arid counties, investments in water and other infrastructure are linked to platforms like HSNP and KSEIP, treating these systems as the backbone of climate resilient development: a trend echoed globally.
The PEA products have been shared and discussed with a range of stakeholders, helping to validate insights and deepen collective understanding of the political dynamics shaping social protection. The team is actively engaging peers and partners to learn from their experiences, particularly on unlocking green finance for resilience and social protection, and additional consultations are planned in the coming weeks. This includes upcoming meetings with parliamentarians to articulate the benefits of safety nets and build broader political support for sustainable, climate resilient social protection systems.
Audit Statements: BOMA audited report for the period ended December 2024 was received and reviewed by the programme team. The auditors presented an unqualified opinion, with no major issues noted. The next report for the year ended December 2025 will be submitted in April 2026. The UNICEF audited report will be submitted eighteen months after programme closure as per the framework arrangement.

Date of last narrative financial report	January 2025	Date of last audited annual statement	August 2025

ANNEXES
## Annex 1: HSNP original Theory of Change

Figure 1: HSNP original theory of change

## Annex 2: Annual Review Supporting Reports

To be shared if needed

## Annex 3: References