## Umoyo Wathu Annual Review
## (December 2023 – November 2024)

Title: Umoyo Wathu Health System Strengthening Programme
Programme Value £ (full life): £119,000,000		Review date: 21 Feb 2025
Programme Code: 300150	AMP start date: Nov 2019	AMP end date: Mar 2028 (extended from Oct 2025 following Business Case amendment in Jul 2023)

Summary of Programme Performance
Year	2020	2021	2022	2023	2024	2025	2026	2027
Overall Output Score	A	B	A	A	B
Risk Rating	Major	Major	Major	Major	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/52097342.odt
DevTracker Link to results framework:	DevTracker Programme GB-GOV-1-300150 Documents

Acronyms used in this Annual Review:

AGA	Accountable Grant Arrangement	KUHeS	Kamuzu University of Health Sciences
AMR	Antimicrobial Resistance	MDHS	Malawi Demographic & Health Survey
CHAM	Christian Health Association of Malawi	MN(C)H	Maternal & Newborn (Child) Health
CSE	Comprehensive sexuality education	MoH	Ministry of Health
DDA	Due Diligence Assessment	MOU	Memorandum of Understanding
DFF	Direct Facility Financing	MPTF	Multi Partner Trust Fund
DHIS2	District Health Information System	NAPHS	National Action Plan for Health Security
DHMT	District Health Management Teams	ODA	Official Development Assistance
DIP	District Implementation Plan	OHSP	One Health Surveillance Platform
DP	Development Partners	PHC	Primary Health Care
DPPD	Department for Policy & Planning, MoH	PHIM	Public Health Institute of Malawi
DSA	Daily Substance Allowances	PPE	Personal Protective Equipment
EHP	Essential Health Package	QI	Quality Improvement
EmONC	Emergency Obstetric and Newborn Care	QMD	Quality Management Directorate, MoH
EPD	Ending Preventable Deaths (of mothers, newborns and children)	QoC	Quality of Care
FA / FPOA	HSJF Fiscal & Procurement Oversight Agent/ Fiscal Agent	QoCLC	Quality of Care Learning Centre (MoH/KUHeS)
FP	Family Planning	RBF	Results Based Financing
FCDO	Foreign, Commonwealth and Development Office	RCO	UN Resident Coordinators Office
FHS	Family Health Services	RHD	Reproductive Health Division, MoH
GCF	Green Climate Fund	RNE	Royal Norwegian Embassy
GHS	Global Health Security	RRT	Rapid Response Team
GoM	Government of Malawi	SLA	Service Level Agreement
HCMC	Health Centre Management Committee	SRHR	Sexual Reproductive Health and Rights
HCIG	Health Centre Improvement Grant	TDDAP2	Tackling Deadly Diseases Across Africa Phase 2 (FCDO central programme)
HDG	Health Donor Group	TIC	Technical Implementation Consultant
HEPU	Health Economics & Policy Unit (KUHeS)	TA	Technical Assistance
HSJF	Health Services Joint Fund	TLP	Tsogolo Langa Programme
HSS	Health System Strengthening	TOC	Theory of Change
HSSPIII	Health Sector Strategic Plan III	UHC	Universal Health Coverage
HTA	Health Technology Assessment	UNJP	UN Joint Programme
IDSR	Integrated disease surveillance and response	UW	Umoyo Wathu (Our Health) Programme
IHAM	Islamic Health Association of Malawi	VfM	Value for Money
IPC	Infection, Prevention and Control	WHO	World Health Organisation
ISS	Integrated Supportive Supervision	4Ps	People Product Place Policy (essential elements of quality service delivery)
KfW	German development bank

## A. SUMMARY AND OVERVIEW

Description of programme
The objective of the Umoyo Wathu (Our Health) programme is to improve the health and survival of the most vulnerable in Malawi, and to establish a framework for sustained improvements. This health system strengthening (HSS) programme aims to increase the provision of quality, cost-effective life-saving primary health services (including through increasing uptake of the Health Benefits Package); improve cost-effective and equitable priority setting, resourcing and management of services; and strengthen accountability of district-level health service delivery. The programme aligns closely with Malawi’s health strategy (the Health Sector Strategic Plan, HSSP III, launched in 2023) and aims to deliver UK commitments including Healthy Women, Children and Newborns (HWCN), championing SDG3.8 on Universal Health Coverage (UHC) with a focus on vulnerable groups such as women and girls, and supporting global health security (GHS) through a resilience based HSS approach. Until this year, the programme had two main components:
[note] Formerly Essential Health Package (EHP), a cost-effective free-to-user priority health service package focused on maternal, neonatal and child health, and infectious diseases: https://www.health.gov.mw/index.php/essential-health-package. The HBP and its relationship to the EHP is described further in the HSSP III (2022-2030): https://dms.hiv.health.gov.mw/link/d9nbvzwn
[note] Formerly ‘ending preventable deaths’ (EPD) of mothers, children and newborns
1. Health Sector Joint Fund (HSJF) supports delivery of essential health services at national level through a bilateral agreement with the Government of Malawi (GoM) with joint funding with Norway (RNE) and Germany (KfW) and third-party fund management through a Fiscal / Procurement Oversight Agent (FPOA).
2. UN Joint Programme (UNJP) supports a package of primary care strengthening initiatives at district level in 6 districts including health system leadership and governance, and with a particular focus on maternal, neonatal and child health (MNCH) services as markers of a functioning system. It includes a component to strengthen preparedness and response to health shocks such as outbreaks. It is currently delivered through UN partners (UNICEF, WHO, UNFPA) with support from the Resident Coordinator’s Office (RCO).
However, during the reporting period, a few other components have been initiated:
1. Neotree – aims to improve newborn care in low-resource settings. The component is delivered through an Accountable Grant Arrangement (AGA) from Sept 2024 to Dec 2027, focusing on implementation and scale up, following two years of FCDO research funding through the Southern Africa Research Hub. It was originally to have been a downstream partner to UNICEF under the UNJP, but after consideration, it was set up under a separate component to ensure timely fund transfer. Despite this, Neotree is well linked with UNICEF at district level as part of the work on quality of care and reducing child mortality.
2. Family Health Services (FHS) - delivered through an AGA (Jun 2024 to Aug 2025). This Sexual Reproductive Health and Rights (SRHR) component aims to increase access to services and modern family planning methods, with a focus on reaching youth and people with disabilities. The component was brought into the UW programme at the closure of Tsogolo Langa (TLP), and was to have been delivered through HSJF from Apr 2024. As the Memorandum of Understanding (MOU) was not signed in time between FHS and the Ministry of Health, FCDO initiated a separate time-limited AGA to ensure service continuity. The component will be delivered through HSJF from April 2025.
3. El Nino nutrition response - delivered through an MOU with UNICEF (Oct 2024 to Aug 2025). This is one-off funding responding to the impact of the El Nino weather system on food insecurity and resulting rising levels of malnutrition. It aims to foster resilience and ensure enhanced and equitable access to nutrition services to prevent and manage malnutrition, including wasting and micronutrient deficiencies, with a focus on Chikwawa, Nsanje, Kasungu, Lilongwe and Mangochi districts.

Headline changes to the operating context since the last Annual Review in Feb 2024:
- Malawi’s debt crisis continues. Foreign Exchange (Forex) is in increasingly short supply, leading to recurrent fuel shortages and reports of increasing stock outs of essential drugs (given poor forecasting and supply chain data, it is hard to tell whether this is substantially worse than previous years). HSJF DPs are experiencing increased demands for support to commodity procurement, as well as initiatives to increase government access to Forex. Some of these are at odds with the way that the HSJF has been set up outside government systems, potentially risking the viability of the HSJF arrangement. FCDO continues to engage with GoM on this, since Forex availability is unlikely to improve in the short term, and over the longer term the fiscal space will continue to be squeezed by population growth which outpaces economic growth.
- Malawi’s health sector has made strides despite economic constraints, but systemic challenges hinder sustained improvements. Gaps in Public Sector Reform (PSR) and Public Financial Management (PFM) as well as fragmented financing exacerbate inefficiencies. Health spending per capita is $16, far below the WHO-recommended $86, and debt servicing comprised 24.5% of the 2024/25 budget. While the health budget increased to MK550 billion in 2024/25 – a 50% jump – inflation >20% rendered it a 17.6% real terms increase. There is some evidence that the Government is increasingly unable to meet health co-financing commitments, for instance GAVI co-financing and staffing of not-for-profit health facilities under a Service Level Agreement (SLA). The World Bank’s Health Emergency Project has been able to plug some financing gaps across the sector, but this ends in late 2025 and the GoM’s longer term approach to some of these health financing challenges is unclear. Although not within the Review period, the Jan 2025 Presidential Executive Order on Reevaluating United States Foreign Aid will heavily impact the sector.
- 2025 is an election year for Malawi – this may impact on delivery of health services and programmes, potentially making it easier in some cases to implement reforms where there is political imperative, or harder in others where government and stakeholders have other priorities, until after a new government is in place. It is important to consider where and how much effort to put into systems reforms until after the elections.
- MoH continues to push HSSP3 reforms with a focus on integration, yet implementation remains a challenge. In the second year of roll out, much of the focus remains at national rather than sub-national level. The Policy-to-Action gap in Malawi is significant: while frameworks like HSSP III exist, translating them into effective reforms remains a persistent issue. The health team continues to encourage coordination and alignment of health sector funding in line with GoM ambitions for “One Plan One Budget One M&E”, particularly given our involvement in the HSJF as a key joint financing mechanism. Malawi is a self-nominated ‘pathfinder’ for the Lusaka Agenda (working to drive operational coherence of Global Health Initiatives such as Global Fund and GAVI), and FCDO is providing technical assistance through CHAI to MoH to help develop a clear pathway to change. Other ways that we are looking to address inefficiencies in the system is by reviewing Daily Subsistence Allowances (DSAs), working with development partners to agree harmonised DSA rates to mitigate incentives that take central civil servants and frontline health workers away from their day jobs. Alongside this, we are rebalancing our programme investment towards support for pre-service rather than in-service training, and ensuring that where we do fund training, there is careful consideration of where, who and how many should attend, to make best use of scarce resource.
- UK bilateral budgets are less tight and more stable this year – UW programme funding has increased from £4m in 2023/24 to £18m in 2024/25 FY, closer to the levels originally planned in the Business Case (although this now includes £4.5m of SRHR work which was previously delivered through the separate Tsogolo Langa programme). A Business Case amendment approved in July 2023 extends the programme to 2028 and integrated our SRHR work into the UW programme from April 2024. A full Theory of Change review was undertaken as a result, and the Logframe updated to include SRHR indicators and to align expected results with the higher levels of funding – discussed further in Section B.
- New UK investment into the health system: Malawi is now an FCDO focal country for Healthy Women, Children and Newborns (formerly ‘Ending Preventable Deaths’), unlocking additional technical resources and funding, for example on climate and health, and WASH in Health Systems. Malawi is also now a focal country for Phase 2 of the centrally managed Tackling Deadly Diseases Across Africa (TDDAP2) health security programme which is now into inception phase and will run until 2026, as well a central Health Systems Connect programme, building relationships between the Malawi and UK health systems. There is also new UK Department for Health and Social Care (DHSC) investment in Malawi from late 2024 through the Global Health Workforce programme on human resources for health. Whilst these bring in welcome resource, they require significant engagement and capacity from the in-country health team to avoid duplication and maximise synergies with our bilateral health programming.
- Changes to the UN Joint Programme - The gaps in both UNICEF and UNFPA leads have now been filled. However, because of decreasing evidence of clear benefit from joint UN arrangements, UNJP implementation arrangements will shift from April 2025 to individual UN partners who will implement a package of interventions based on what each partner can deliver well. Implementation will no longer be coordinated through UN RCO; however, we continue to push continued collaboration among UN partners.

Summary supporting narrative for the overall score in this review
This is the fifth Umoyo Wathu annual review. This year, the programme scores a B, reflecting the challenges in both HSJF and UNJP components during the reporting period, and the cumulative challenges of responding to multiple years of reduced ODA, the tough Malawi economic context, and the limited sectoral improvements which would have enhanced the delivery of this programme. We have redesigned the programme to respond to the changing operating environment to ensure that programme continues to meet the original objectives of the Business Case (set out in the first paragraph of this Section of the Review). We have restructured the programme (and updated the Logframe accordingly) to focus on components that are best positioned to deliver impact within this changed operating context, as well as to support the underlying reforms necessary to drive longer term sustainable health systems strengthening. It has also been important to ensure sufficient flexibility in design that the programme can continue to be able to respond to emerging priorities such as El Nino nutritional needs, rehabilitation of health facilities following Cyclone Freddy and Cyclone Chido, as well as GoM demands to meet gaps in essential commodities and GAVI co-financing, whilst continuing to maintain a systems approach.
The return to higher levels of ODA during the reporting period is one reason for the variable progress in indicators this year – scaling both UNJP and HSJF activities back up (3x for UNJP, 4x for HSJF) took much longer than anticipated to ensure funds would be directed to good value for money and impactful areas. Neither UNJP nor HSJF budgets/workplans were approved until halfway through 2024/25, losing 6 months of implementation.
- The appointment of an HSJF programme manager last year and an M&E officer within the reporting period have improved Fund administration and reporting of results, but there remain significant delays to budget approval, partly due to the number of new motions through increased FCDO funding (including on climate and health, DFF, and knowledge management for quality of care), but also due to MoH not engaging donors at an early enough stage in the development of motions, and ongoing capacity issues within DPPD. Despite early engagement from FCDO before the end of the TLP, there were also challenges to integrate the SRHR work into the HSJF in a timely way, due to delays in signing of an MOU between FHS and MoH, resulting in a gap in service delivery and the need for FCDO to develop an alternative medium-term fix.
- The time taken to develop a coherent UNJP 2024/25 workplan led to significant delays in funds reaching implementing partners and districts, and delayed activities. FCDO has now made the decision to close the UNJP arrangement by the end of 2024/25, moving forward with bilateral agreements with individual UN agencies to streamline this process and improve transparency of reporting and accountability for results. We believe this structure will reduce delays in agreeing budgets and allow us to set more ambitious indicators than this year where indicators were set in the context of implementation challenges. This is in line with the Umoyo Wathu Programme Business Case which set out that the Joint Programme arrangement would be a trial, to be reviewed if it was not effective.
Despite these challenges, the programme has made progress in a number of areas. Key achievements include:
- Bringing in additional partners to the HSJF: UK engagement with MoH and partners continues to be instrumental in encouraging development partners to put funds through the HSJF. For example, Scottish Government is channeling its Non-Communicable Disease (NCD) funding through HSJF, Save the Children has been brought in through our partnership on the Green Climate Fund (GCF), and the Beginnings Fund is considering HSJF as a financing mechanism. Ongoing UK support to the HSJF helps maintain and improve this key mechanism for coordinating health financing, in line with Malawi’s HSSPIII ambitions.
- Ongoing support to Service Level Agreements (SLAs) – core to Malawi’s UHC ambitions, and ability to maintain essential services for vulnerable rural populations, women and girls in particular, and especially during public health emergencies such as cholera. This year we have been able to return our support to previous levels, and together with Norway, we continue to support digitalisation of SLA invoicing to improve the timeliness of payments and reduce the risk of fraud.
- Continued support to strengthening systems for knowledge generation and use including the Health Economics and Policy Unit (HEPU) at Kamuzu University of Health Sciences (KUHeS), and now the Quality-of-Care Learning Centre (QoCLC), a collaboration between MoH Quality Management Directorate (QMD) and KUHeS, both funded by the UK through HSJF. These provide mechanisms to influence health policy, and support effective prioritisation of limited funding and implementation of HSSPIII priorities, especially around health financing reforms (for example future funding models with not-for-profit private providers to improve UHC, and national roll out of Direct Facility Financing) as well as to link quality improvement policy with realities of ‘on the ground’ implementation and try to bridge the ‘policy into action’ gap. In addition to the direct impact on our programmatic areas of work, this is an important component of our broader support to the health sector, strengthening sectoral academic capacity as part of a modern partnership approach to development.
- The start of national roll out of Direct Facility Financing (DFF), following lessons learned from DFID/FCDO-funded Health Centre Improvement Grants (HCIG): UK health programming has directly influenced GoM’s national health financing plans (a key HSSP3 reform), and we have supported both the setup of the national DFF Taskforce led by MoH, as well as the roll out of governance structures and the grants themselves in Rumphi through the UNJP, with plans for additional districts through the HSJF. The GoM’s plans for DFF aim to transform how health facilities receive, manage and account for funds to deliver health services, and introduces the potential for them to receive additional funds from Council or community development funds, or community insurance schemes, to respond to locally identified needs. Given the critical role of district and health facility governance mechanisms for equitable decision making and mitigation of fiduciary risk, as well as our own requirements that funds remain outside government systems, we will continue to work with GoM and the HSJF fiscal agent to ensure that this remains central as we support the national roll out.
- Initiation of bilateral programming support to Neotree, an innovative digital tool for improving quality of care for small and sick newborns. Our UW funding follows several years of UK research funding via the FCDO Southern Africa Research Hub to test the model. Now that it has demonstrated the potential to reduce neonatal mortality by up to 60%, we are now supporting the roll out of this tool across UNJP districts (starting with Kasungu) as part of our broader work on quality of care, in recognition of the significant contribution of neonatal mortality to overall child mortality in Malawi, and the lack of specialist neonatal health workers, as the tool also acts as an on-the-job training aid.
- Stepping up our work on climate resilience, including support to one of the first climate and health programmes globally awarded by the Green Climate Fund – focusing on strengthened climate resilient health facility infrastructure and climate sensitive surveillance and early warning systems – as well as work with CHAI and the MoH to enhance coordination and sustainability of health facility solar electrification investments and develop a renewable energy certification in Malawi for carbon offset. We have also been able to respond rapidly to the impacts of El Nino weather patterns on food security and undernutrition and respond to other climate events such as Cyclone Freddy and Cyclone Chido.

The programme team are confident that the full review of the programme that has been undertaken, together with the shift in approach to the UNJP, puts it in a better place to deliver to 2028, although we continue to assess the operating context and its impact on our programming so we can be flexible to respond. The programme should also be seen within the broader work of the UK to support the Government of Malawi to respond to profound challenges and multiple shocks that Malawi and its health system is facing. The UK in Malawi continues to be a key player in supporting the GoM’s response to the macroeconomic crisis, and in the health sector, including through our relationships with the Health Donor Group (HDG) and HSJF donors. The UK both globally and bilaterally was instrumental in leading the Covid-19 response, and more recently, in helping to galvanize cholera and Cyclone responses and crowding in funding to mitigate the impact of multiple emergencies.
Major lessons learned from the last year:
1. We need to balance ‘supporting the basics’ with a health system strengthening approach that sets foundations for future improvements. We continue to consider how to deliver ‘the basics’ – direct service delivery and gap-filling commodity procurement – in a way that strengthens (and at a minimum, doesn’t undermine) the wider system. We previously supported infrastructure and equipment through HSJF but pulled out as a result of ODA cuts – we know how important these are to the delivery of quality care (see the 4Ps model in the updated Theory of Change - Section B), and are considering how best to support these now that budgets are more stable. This year, we have also been asked by GoM to support procurement of MNH commodities, following Forex-related shortages. We already invest in family planning commodities specifically because of the high return on investment over the life course, the impact on women and girls’ life chances and the links with demographic dividend; however, there is weaker justification for recurrently funding general health commodities, given Malawi’s development rather than humanitarian context, and the principle of not taking over what is ultimately government’s responsibility. We continue to keep this under review given the tough fiscal situation. We also want to balance any investment in ‘the basics’ with support to generating evidence and strengthening the systems that enable better forecasting and supply, to maximise longer-term impact and sustainability rather than short-term solutions that do not address root causes.
  [note] Eric Sarriot, William T Story, On learning about efforts to strengthen (and reduce harm to) systems for health, Health Policy and Planning, Volume 37, Issue 4, April 2022, Pages 535 – 538 https://doi.org/10.1093/heapol/czac013
  [note] 4Ps model – good quality of care demands the simultaneous availability of well-trained staff (Person), the right drugs and equipment (Product) within an appropriate Place with reliable utilities (Place) + the right Policies in place and adhered to.
2. We need to be realistic about what we can achieve in this context. Domestic financing for health is unlikely to increase, and donor financing is increasingly precarious. The population is projected to more than double to 45 million by 2050, adding pressure on already dilapidated and under-resourced public services. We need to take a pragmatic approach, based on need but also on political feasibility (particularly given upcoming elections) and what is likely to have most impact over the remainder of the programme. Whilst “external actors [like FCDO] can contribute to strengthening or weakening a system… leadership of national actors is critical in guiding assistance projects towards more sustainable contributions to health systems.”
  [note] Sarriot & Story (2022), ibid.https://doi.org/10.1093/heapol/czac013
3. We must continue to address the ‘policy to action’ implementation gap, building in feedback loops between evidence generation activities and implementation on the ground (for instance between the QOCLC and our work in districts), and considering how the totality of our investment strengthens the 4Ps needed for quality health service delivery. For example, to improve quality of care at the primary care level, we not only need to address gaps in service delivery through the adoption of digital tools (like Neotree) and appropriate clinical training, but also appropriate and functional medical equipment and infrastructure, a stable supply of electricity, reliable transport system for referrals, and a culture of reviewing data for decision making.
4. Through the UK-funded work as well as global evidence on financial autonomy of health facilities, we know that robust governance structures are essential for effective oversight and roll out of DFF. There is a risk that the GoM’s desire for rapid national roll out of DFF grants compromises the quality of work to strengthen PFM at District level and through Health Centre Management Committees. FCDO and our partners will continue to ensure that sufficient focus on governance mechanisms is maintained as we support the scale up of DFF.
  [note] Sophie Witter, Maria Paola Bertone, Lucas Sempé, et al. Financial autonomy of facilities providing primary health care services in low and middle income countries: assessing the evidence to inform the development of a typology and conceptual framework. Authorea. April 20, 2024. 10.22541/au.171359960.00520382/v1
5. Integration of SRHR work offers opportunities for greater impact. Including SRHR services within HSJF provides opportunity to improve equity, for instance delivering tailored outreach in SLA catchment areas served by Roman Catholic facilities, as well as giving MoH Reproductive Health Department (RHD) more oversight of SRHR investments and promoting better coordination, avoiding duplication and promoting lesson sharing. There is opportunity to consider how we might expand our SRHR work through links with other sectors such as education, growth and resilience. There is demand from young people for income generating activities alongside SRHR services. We know that economically empowered girls can be more assertive, have more control over their sexual choices and are less likely to have unprotected sex, and that comprehensive sexuality education (CSE) has strong links to delayed pregnancy and improved education outcomes. However, it has become clear through this Annual Review that we haven’t yet got the right programme SRHR indicators to be able to track progress and hold partners to account.
  [note] TLP impact survey results: CSE activities resulted in improved school retention (35.5% in 2016 to 54.0% in 2022), contributing to improved school completion (41.7% in 2016 to 67.2% in 2022), and tripling of selection to higher education.
Major recommendations for the year ahead:
1. Work with DPs and MoH to ensure finalisation and approval of the 2025/26 HSJF budget in a timely way, including consideration of some multi-year motions, scaling up our health financing and our work on climate and health. Continue to push MoH to use HSJF more strategically – putting requests to DPs with all the background information, forecasting etc to enable an evidence-based decision on funding to be made.
2. Ensure the PFM aspects of DFF are robust as it is scaled up nationally, using our financial levers and fiduciary oversight through HSJF; consider bringing in additional PFM expertise from FCDO’s HQ Public Finance Resource Centre (PFRC).
3. Finalise the restructured UNJP plans with UN agencies by 31 March 2024, and update the Logframe accordingly
4. Ensure the FHS-delivered SRHR services are transitioned effectively into HSJF from April 2025, through ongoing consultation and engagement with FHS, HSJF, and RHD, and ensure reporting timeframes are aligned, and milestones finalised for future years of the programme. This should include work with UNICEF and UNFPA to report on relevant SRHR indicators through their post-UNJP programmes.
5. Consider how to better link SRHR work to education, livelihoods, technical skills and economic empowerment, responding to demand and impacting on a broader range of outcomes, particularly for girls.
6. Continue to strengthen the programme’s inclusion focus, including disaggregation of data, especially women and children, the poor, and for people with disabilities.
7. Continue to develop our Healthy Women, Children and Newborns (EPD) vision for Malawi, including a cohesive approach to UK investment in Malawi’s health system – bilateral, multilateral, CMPs and OGDs.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
The 2019 Business Case sets out that the UW programme will address critical issues in the health sector to strengthen the health system, focusing on three of the six WHO health systems building blocks to improve health outcomes – service delivery, leadership and governance, and health financing – aiming to improve the quality of primary healthcare (PHC), and the effective devolution of financing and accountability to district level.
[note] WHO, Geneva 2007. Everybody’s Business: Strengthening Health Systems to Improve Health Outcomes.
Major changes since the programme started and impact on the Theory of Change
As discussed in the last Annual Review, much of the global evidence continues to support the UW programme’s overarching approach, but the context within which the programme is operating has changed significantly since the original Business Case was developed, with the Covid-19 pandemic, a global economic downturn followed by multiple rounds of ODA reductions, and Malawi-specific crises including cholera and cyclones. As a result, a key recommendation from last year’s Review was to review the whole programme Theory of Change (TOC) and Logframe, following approval of a Business Case amendment by Ministers in July 2023 and more clarity about the scale of programme budgets in future years. The Business Case amendment extended the UW programme by 2.5 years to 2028 and integrated previously standalone SRHR work into the UW programme from 2024/25.

Figure 1: Updated Umoyo Wathu Programme Theory of Change 2024

In addition to absorbing the SRHR work previously delivered through the Tsogolo Langa programme, we have strengthened programme focus on neonatal quality of care through new work with Neotree and stepped-up work on resilience to public health shocks including climate through both HSJF and UNJP components. The review took place from Sept 2023 to Jul 2024, including workshops with partners, and the updated TOC (Figure 1) and programme Logframe were approved in August 2024. Key changes include:
- A simpler programme narrative and clearer ownership around how interventions build into a coherent programme (whilst recognising that health systems are complex and non-linear), and greater clarity over which inputs are being delivered through the HSJF and which through the UNJP. A hierarchy of interventions has been introduced to reflect how the programme is operating at different levels of the health system.
- The programme’s new focus on SRHR reflected throughout the TOC, a new INTERMEDIATE OUTCOME added to reflect the programme’s work at central level to provide basic services and create an enabling environment for improved health outcomes, complementing district level work, and a new OUTPUT added to reflect the programme’s work on resilience, climate shocks and disease outbreaks.
- At ACTIVITY level, the inputs have been updated to reflect the current shape of the programme, for instance inclusion of support to health financing through Direct Facility Financing (DFF) and work at both the district and national level to improve governance, coordination and prioritisation of scarce resources.

This review also made significant changes to the Logframe. All indicators were reviewed, and milestones and targets from to 2028 updated, and, where possible, aligned with HSSPIII indicators, milestones and targets.
IMPACT level indicators: the stunting indicator was removed as the programme does not include any nutrition interventions which would impact on chronic undernutrition and a new indicator on Total Fertility Rate added to reflect the integration of SRHR activities into UW.
[note] N.B. The impact of nutrition interventions planned through UNICEF in 2024/25 to respond to the El Nino effects on food security will be captured in the ICF indicator under OUTPUT 3 of the Logframe but will respond to acute malnutrition and would not be expected to have any impact on chronic undernutrition and stunting.
OUTCOME level indicators: these were reordered in a more logical order, and:
- The indicator tracking domestic health financing was expanded to better assess progress of domestic resource mobilisation for Universal Health Coverage, and to include measures of domestic financing for new areas of work including Direct Facility Financing and for Family Planning commodities.
- “Proportion of under 12-month-olds that are fully immunised” was removed as although this is a good measure of a functioning health system, the Umoyo Wathu programme is not working specifically on immunisations, and there are other indicators (e.g. access to Antenatal Care) that better reflect this.
- Addition of an indicator on health security and health system preparedness, tracking International Health Regulations (IHR) capacity, to reflect the increasing work on health system resilience and emergency preparedness and response.
- Addition of two SRHR indicators, tracking availability of modern family planning methods, and abortions averted – two key indicators from the now-closed Tsogolo Langa programme.
- Updating of the indicator on accountability to one around patient satisfaction that we will have more control over, as we have had ongoing concerns raised in previous Annual Reviews about the data quality of the former indicator tracking ombudsperson functionality.
- Due to the addition of several new outcome level indicators to reflect the work on health security and SRHR, the indicator on Post Partum Coverage has been removed, to keep the Logframe manageable.
OUTPUT level indicators: weightings have been revised, to reflect the increasing focus on resilience (OUTPUT 3, increased to 25% from 15%), and a more equal split between OUTPUT 1 Access to quality essential services at 40% (down from 55%) and OUTPUT 2 Enhanced management and accountability of the public health system at 35% (up from 30%). Changes to indicators include:
- New indicators to track SRHR work across both family planning commodities, and SRHR outreach services that has been integrated into the UW programme following the closure of the Tsogolo Langa programme, and a new indicator to track our new investment into Neotree, a digital quality improvement tool to better count and care for sick and small newborns which we are rolling out in Kasungu District.
- Integration of several quality-of-care indicators and a shift in focus away from training of quality improvement (QI) teams and initiation of QI projects, towards tracking the impact that the training and the projects have had on patient outcomes and on hospital ‘star’ ratings, given we are now four years into implementation.
- Simplification of indicators tracking HSJF governance, to focus on fund utilisation rate, addition of a new indicator to reflect new funding and technical assistance (TA) through HSJF to the Ministry of Health’s Quality Management Directorate (QMD), and expansion of a previous indicator tracking the impact of FCDO-funded research, analysis and evidence in improving policy making, to include the new investments into Neotree and the Quality of Care Learning Centre (QoCLC), in addition to existing work with HEPU.
- Updating of indicators tracking the Health Centre Improvement Grant pilot through the UNJP to instead reflect the national scale up of the Ministry of Health’s Direct Facility Financing ambitions through the HSJF, based on lessons learned from the FCDO-funded pilot.
- New indicators to better track the programme’s increasing focus on health system resilience and preparedness through work with Save the Children on the GCF grant, and with CHAI on models of sustainable financing for health facility solarisation. This includes introducing reporting against standard ICF indicators on numbers with improved access to clean energy, and with improved climate resilience.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
Progress on outcome indicators is summarised in Table 1 (page 9), with progress on impact indicators outlined in Annex 1. There continue to be challenges with availability of comparable data over time, given the delay in the Malawi Demographic and Health Survey (MDHS), last published in 2015/16 and then delayed due to Covid-19 and again over the last few years due to funding shortfalls. This was finally undertaken in 2024, and the MDHS 2024 Key Indicator Report was launched in January 2025, which included a few indicators relevant to programme impact (Annex 1). However, we are still awaiting the full data set, and this will now be further delayed by the US funding freeze as technical assistance to statistical analysis was being provided through USAID. We are also still awaiting the report of the Joint External Evaluation (JEE) of Malawi’s health security capabilities which was undertaken in December 2024.
In terms of impact indicators, MDHS 2024 data on early childhood mortality rates shows Malawi has made progress in reducing Under 5 mortality, but little progress on neonatal mortality, which validates the UW’s new focus on neonatal care through our new Neotree funding. Data is not yet available on maternal mortality. Total fertility rate is down to 3.7, but we do not yet have the breakdown in adolescents. However, we expect this to remain intractable, and again, to validate our focus on youth through the SRHR components of Umoyo Wathu.
Progress against outcome indicators has been variable, given both the tough economic context and the fluctuating programme funding. The main success story is likely to have been the improvements in IHR core capabilities, to which our programme has made some contributions, but again, we are awaiting the final JEE report to confirm this and identify where progress has been made and where gaps remain, in order to best focus our resilience work going forward, in partnership with the MoH. In other areas, from the GoM side there has been some progress in allocating domestic financing for both DFF and FP commodities alongside donor funds, but we now need to ensure that commitments result in disbursement and utilisation of these allocations.
Regarding the UN Joint Programme component, the original Business Case developed in 2019 proposed to work directly with UNICEF, but a subsequent decision was taken to work jointly across the three UN agencies and the RCO for a trial period, to support the UN reform agenda. It was hoped that this arrangement would maximise delivery of results on the ground, and support coherence across UN agencies. Since inception, the programme has been negatively impacted by the UK funding cuts that took place from 2020-2023, and unexpected shocks, such as COVID, cyclones, and cholera. UN agencies have worked hard with FCDO over this period to navigate these shocks, and flexibly adapt the programme to meet the new programming reality, including a more modest budget for the programme lifetime. However, delivery challenges have continued and the external operating context in Malawi (outlined above) is becoming harder, including the negative effects of forex scarcity. Given this, we decided to streamline delivery to maximise results for the remaining years of the programme, returning to the original proposition with UNICEF as the main delivery agency for district level components. The programme team are working with WHO and UNFPA to discuss separate arrangements based on their core mandates, albeit at reduced scale. The UK remains committed to the office of the RCO through our wider relationship. Future business case design will be informed by lessons from this programme.
Given the integration of SRHR into the programme, we will continue to review whether we have included sufficient indicators to effectively track our investments into both SRHR commodities and outreach services, as well as to strengthen an SRHR lens to other investments within the broader UW programme. We also continue to keep an eye on the global dialogue around a common set of health system strengthening metrics (with input from HQ Health Advisers in the health systems team) to assess whether there are common indicators that we could use to better track UHC and health system resilience in future.
Overall, with the changes that we have made to the programme, the programme team are confident that we will see further improvements at outcome level, and certainly at output level. The B score this year is in part due to the lag effect of lower and unpredictable funding in previous years. The wider sectoral challenges mean that even with increased funding, we may not see significant improvements in outcome indicators over time.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
The programme delivers a good balance between direct service delivery (SRHR outreach, SLAs), provision of the basics (FP commodities, fuel and basic equipment), and system strengthening activities (district leadership and governance, Direct Facility Financing, HEPU for resource prioritisation, Learning Centre to better capture good practice), as well as innovation (Neotree) and M&E (HEPU, Learning Centre). It provides a strong platform to pull in additional technical assistance and resource from other UK investment (TDDAP2, Health System Connect, etc). It fits well with the Foreign Secretary’s development priorities and outcomes, including that ‘Government health systems are strong and sustainable, contributing to lives saved, disease averted, protection of gender equality and SRHR and delivering economic benefits.’ We continue to review what a tailored approach to health systems strengthening in lower-income and fiscally challenged contexts looks like, including the importance of laying the foundations for future improvements and opportunities for more substantive shifts.
Table 1: Umoyo Wathu programme outcome indicators (N.B. all indicator data is from DHIS2 since MDHS has not been done since baseline in 2015/16)
OUTCOME: Increased access to and use of free, quality, essential life-saving and preventive health services by poor and vulnerable women of reproductive age, newborns, children and adolescents, delivered by an increasingly resilient, responsive, accountable public health system
Outcome indicator		Baseline / (2015/16)	Previous AR (Feb 2021)	Previous AR (Feb 2022)	Previous AR (Feb 2023)	Previous AR (Feb 2024)	This Review (Feb 2025)	Trajectory and commentary
1	UPDATED: Gov’t budget for health: / a) Proportion of Gov budget allocated and disbursed to the health sector (% and absolute USD) / b) Proportion of Gov budget allocated and disbursed to DFF (% and absolute USD). / c) Proportion and value (US$) of MOH health budget allocation and expenditure for FP commodities / d) Expenditure on health by Gov as a % of total expenditure on health (HSSP3)	10.8%	No LF target 2020	LF target 2021: 11% / 9.4% (UNICEF Analysis of the 2020/21 approved Health Budget) / Not achieved	LF target 2022: 12% / 10.0% (UNICEF Analysis of 2021/22 approved Health Budget) / Not achieved (but an increase on last year)	LF target 2023: 13% / 8.5% (UNICEF Analysis of 2022/23 approved Health Budget) / Not achieved (and reduction on last year)	LF target 2024: / a) 11% / b) 0% / c) 100% expenditure (baseline: USD 288,000 in 2024/25) / d) 36.20% (HSSP3) / Partly achieved / a) 9.2% (MK 550 billion) / b) 0% to date but GoM has agreed to allocate$200k to DFF / c) Data not yet available (data from treasury in April, outside review period) / d) 24.1%	Target partly achieved: stagnant financing for health compared to 15% Abuja target; promising move to allocate domestic financing for DFF and FP commodities but this needs to be tracked; spend on health hindered by rising debt servicing (24.5% of 2024/25 budget)
2	NEW: Improved capacity in the following technical areas of the IHR Core Capacities: / - Surveillance / - Human resources / - Emergency Preparedness / - Emergency response operations	Overall IHR score: 22/60 (JEE 2019) / Sub-scores: / - Surveillance (6/15); / - HR (9/20); / - Emergency Preparedness (3/10); / - Emergency response ops (4/15)					LF target 2024: 24/60 / Data not yet available (JEE held Dec 2024) but evidence presented in the JEE assessment suggests improvements across most IHR areas	Trajectory highly likely to be positive since the 2019 JEE, based on evidence shared in the JEE sessions held in Dec 2024 but full report not yet received
3	Proportion of pregnant women with 4+ antenatal care visits	26% (MDHS 2025/26)	LF target 2020: 34% / National: 36.9% / UW Districts: 34.6% / Achieved	LF target 2021: 42% / National: 47.6% / UW Districts: 46.4% / Achieved	LF target 2022: 49% / National: 35.7% / UW Districts: 33.1% / Not achieved	LF target 2023: 57% / National: 29.3% / UW District: 29.4% / Not achieved	LF target 2024: 55% / National: 37.7% / UW District: 23.6% (DHIS2) / Not achieved / However, MDHS 2024 (released 23 Jan 2025) gives a figure of 62%	Target not achieved if using DHIS2 data; / However, target achieved if using recently released MDHS data (62%) No district level data available until August 2025.
4	NEW: Demand for family planning satisfied with modern methods, by age (incl. adolescents) and marital status	79.9% (MICS 2020 for currently married women)				TLP operational until March 2024. Rolled into UW from 1 April 2024 but implementation only started in June 2024	LF target 2024: 80% / Data not yet available (FHS survey conducted annually. Likely to be available by Sept 2025)	N/A – data not yet available	N/A
5	NEW: Number of abortions averted	92,000 (2023/24)				Ditto	LF target 2024: 40,000 / June to Nov 2024 (6 months): 4,691 / Not achieved (SRHR reporting periods mistakenly not aligned with UW reporting)	Target not achieved: delayed SRHR service transition from TLPàUW, + misalignment of reporting periods. It was consistently well achieved during TLP, we expect it to improve
6	UPDATED: Proportion of people satisfied with services of health facilities	0%	No LF target 2020 / National: 59.5%	LF target 2021: 0% / [not available: DHIS data quality issues]	LF target 2022: 70% / National: 69.7% / UNJP Districts: N/A (only 2 UW districts reported) / Achieved	LF target 2022: 70% / National: 60.8% / UNJP Districts: 71.5% / Not achieved (achieved in UW districts)	LF target 2024: / People's Voice Survey ready for implementation / PVS survey work started to adapt to Malawi context	Target partly met	N/A
[note] N.B. Many of the targets were reduced from the original trajectory when the TOC/Logframe Review was conducted in 2024, taking into account the impact of Covid-19 and other shocks
[note] [PREVIOUSLY ‘Proportion of government budget allocated to the health sector’]
[note] PREVIOUSLY: ‘% facilities with functional ombudsman or other feedback mechanism’
[note] Sources: DHIS2 for numerator data on facilities with functional ombudsman; Health facility master list for denominator data on total number of health facilities by district

## C. DETAILED OUTPUT SCORING

Output Title	Increased readiness of the primary health platform to deliver free quality essential health services to poor communities at facility level
Output number:		1	Output Score:	B
Impact weighting (%):		40%	Weighting revised since last AR?	Y – revised down from 55%

Indicator(s)	Milestone(s) for this review	Progress
Reach of HSJF funded Maternal, Newborn, Child and other EHP medical services, measured through number of facilities and people served through SLAs (% FCDO attributed)	Milestone 5 (Nov 2024): / a) 5.9 million people in / b) 170 eligible health facilities	a) in 2024/25, 5.9m catchment population (57% or 3.4m attributed to FCDO). This was 2.5m during 2023/24 of which 1.2m attributed to FCDO (47%) – see narrative / b) 168 SLA facilities of which 96 attributed to FCDO (57%). This was 74 facilities in FY2023/24 of which 35 (47%) attributed to FCDO. / Score: A. Met (Scored B last AR)
NEW: Number of adolescents and youth reached with comprehensive adolescent-friendly SRHR services (excluding contraceptives) disaggregated by age and sex (Attributed to UW)	Milestone 5 (Nov 2024): / (a) 10-14 years: 8,000 / (b) 15-19 years: 10,000 / (c) 20-24 years: 15,000 / (d) Youth with disabilities: 430 / (e) Sex: 33,430 (M/F 40/60%) / Revised FHS milestones (Jun-Nov 2024) / (a) 10-14 years = 552 / (b) 15-19 years = 5,603 / (c) 20-24 years = 9,029 / (d) Youth with disabilities =744 / (e) Sex: Total:15,183 (40/60)	FHS progress (Jun-Nov 2024) / (a) 10-14 years = 35 (6%) / (b) 15-19 years = 3901 (70%) / (c) 20-24 years = 5,139 (57%) / (d) Youth with disabilities = 19 (3%) / (e) Sex: M = 3,300 (54%) F=5,776 (63%), Total: 9,076 (60%) / Score: C. Not met (new indicator for UW, but in previous TLP, FHS usually met this indicator. Further discussion in narrative)
NEW: Number of additional users of modern methods of family planning through UK support	Milestone 5 (Nov 2024): / 100,000 / Revised FHS milestone for AGA (Jun-Nov 2024): 51,603	FHS progress (Jun-Nov 2024): / 39,753 (77%) / Score: B. Partially met (new UW indicator, but in previous TLP, FHS usually met this. Further discussion in narrative)
Number and impact of Quality Improvement (QI) projects in UNJP districts: / a) No. districts with at least one QI project completed in the last year per Health Centre and 2 per hospital. b) No. districts with at least 3 ‘impact’ case studies	Milestone 5 (Nov 2024): / a) 6 districts / b) 6 districts	a). Met: 6 (Chikwawa, Kasungu, Nsanje, Ntchisi, Mzimba, Rumphi) / b). Part met: 4 districts (Rumphi and Kasungu each only had one ‘impact’ case study, likely due to the late start of UNJP activities in these districts in 2024/25). / Score: B. Partly met (scored A in last AR)
[note] When developing the updated UW Logframe and integrating SRHR indicators, annual milestones aligning to the financial year (Apr 2024 to Mar 2025) were mistakenly included for FHS, rather than milestones which reflect the AR reporting period (Dec 2024 to Nov 2025), and the fact that FHS activities up to 31 Mar 2024 were to be captured in the TLP rather than the UW Logframe.
[note] This refers to UK support to service delivery and demand creation via FHS rather than to FP commodity procurement

NEW: % of target health facilities in UNJP districts that have had a positive change in their quality of care star rating	Milestone 5 (Nov 2024): / Narrative on progress with supporting the star rating assessments	No progress has made on this indicator to date, as no support has been provided to the districts for health facility accreditation (due to competing MoH activities in late 2024). Activities planned for Q1 of 2025. / Score: C. Not Met (new indicator, not rated in last AR)
NEW: Number of health facilities with a functioning NEOTREE system. / (functioning is that at least 80% of admissions are recorded in the Neotree system).	Milestone 5 (Nov 2024): 3	The Neotree system is functional in 3 facilities in Lilongwe District: / Kamuzu Central Hospital: 100% utilisation rate. / Kabadula Community Hospital: 40% average utilisation / Lumbadzi Health Centre: 70% average utilisation. / (see narrative for explanation) / Score: B. Partly met (new indicator, not rated in last AR)
Percentage of delivery facilities in the selected districts providing EmONC signal functions in the 3 months prior to assessment	Milestone 5 (Nov 2024): 40%	16% consistently maintaining all 7-9 signal functions (although 80% of facilities in the 6 districts offer some degree of EMONC services) / Score: B. Partly met (scored C in previous AR)
UPDATED: Data-driven approach to quality improvement: / a) % maternal deaths audited (per district) / b) No. districts that carry out a near-miss audit at least once per quarter / c) No. districts conducting perinatal death audits at least once per quarter	Milestone 5 (Nov 2024): / a) 70% / b) 3 districts / c) 3 districts	a. Met (all 6 districts at 100%) / b. 3 (Chikwawa, Nsanje, Ntchisi) / c. 6 districts / Score: A+. Exceeded expectations (similar indicator scored A+ in last AR)
NEW: Response plans for EMONC: / a) No. districts that have developed and costed response plans to improve EmONC services (based on MPDSR audits, near miss audits, action points from mentorship programme and data analysis) and that are part of annual DIP (district implementation plans) / b) No. districts that produce at least 1 case study per year (analysis, planning and implementation)	Milestone 5 (Nov 2024): / a) 3 / b) 3	a. 6 districts developed costed response plans following MPDSR audits. 4/6 districts have implemented the actions from these plans: / Nsanje:80% / Kasungu:33% / Ntchisi:81% / Mzimba South:76% / b. 3 Districts (Nsanje, Chikwawa and Mzimba South) / Score: A. Met expectations (similar indicator scored B in last AR)

Briefly describe the output’s activities and provide supporting narrative for the score.
The activities under this output are designed to increase access to good quality, free essential health services for poor communities in Malawi. They fall into three main areas:
- Service Level Agreements (SLAs) with not-for-profit health facilities to enable those living in remote areas far from government facilities to access to basic services for free, improving UHC.
- Increasing access to SRHR services and modern family planning methods, with a focus on reaching youth and people with disabilities.
- Improving the quality of care for pregnant women before, during and after delivery, and for newborns, through embedding a data-driven approach to quality improvement in health facilities.
There has been a mixed picture under this output. After a particularly lean year for the health programme in 2023/24, we have been able to increase HSJF funding to SLAs – a major pillar of our work to drive UHC – as well as to initiate some exciting and innovative work around newborn quality of care with Neotree. However, there were delays to sign off of both the HSJF and UNJP budgets/workplans for 2024/25, which delayed activities in the first 6 months (corresponding to the second half of the Annual Review reporting period). The TOC review confirms that the activities under this output are central to increasing availability of good quality primary healthcare and the more streamlined package of interventions now being delivered through the HSJF, and planned through post-UNJP proposals provide a good foundation to deliver results for the remainder of the programme. Detail about the specific activities and indicators:
Service Level Agreements with not-for-profit health facilities (Indicator 1.1)
- HSJF donor support to SLAs was scaled down to 74 facilities in 2023/24 (based on agreed criteria) due to reduced FCDO and RNE funding. This was recognised in last year’s AR, where this indicator was partly met. Out of the total 5.9 million catchment population of CHAM and IHAM facilities under the SLA arrangement, HSJF support covered a population of 2.5 million (of which 1.2 million was attributed to FCDO funds). In fact, due to exchange rate gains following re-alignment of the Kwacha in late 2023, the available HSJF funding was able to support 104 facilities through savings that were identified, and the World Bank’s Health Emergency Project funding was able to close the gap. In 2024/25, HSJF funds (FCDO, RNE) have been sufficient to cover all 168 (100%) target facilities.
- There continue to be delays in SLA payments. FCDO is supporting the digitisation of the SLA invoicing which should improve timeliness, but in the meantime, any delays are exacerbated by inflation and the devaluation of the Kwacha, eroding the reimbursed fund value.
- The HSJF funding from FCDO and RNE – with the emergency bridge funding from World Bank in 2023/24 to cover the shortfall – has ensured continuity of SLA services for over 5 years, sustaining health coverage in hard-to-reach areas. The FCDO-funded VfM study conducted by HEPU concludes that SLAs represent good VfM, and that besides promoting equity in health care, GoM is also making net savings on infrastructure investment through this model.
- Whilst HSJF donors cover the cost of the service activities under the SLA arrangement, the MoH is supposed to recruit and pay CHAM/IHAM staff in SLA-covered facilities. However, during the reporting period, there have been recruitment freezes which risk service delivery. HSJF donors raised concerns with the MoH and MoF in October 2024 but have not yet received a satisfactory response. There are concerns over the future of this arrangement if the government commitment to pay for staff at CHAM facilities continues to go unmet.
- We are working with HSJF M&E Officer to see if SLA utilisation could in future be broken down by adolescents and people with disabilities, in order to better link SLAs with access to SRHR services.
SRHR activities through FHS (Indicators 1.2, 1.3)
UW’s SRHR outreach activities are being implemented by FHS in 8 districts since June 2024, with comprehensive adolescent friendly SRHR services provided to young people through integrated outreach services, girls’ and boys' conferences, school health days and in school comprehensive sexuality education (CSE) sessions. This follows on from the previous FDCO-funded SRHR programme Tsogolo Langa which ran from 2019 to 2024, which was merged into the UW programme from April 2024 albeit at a reduced scale. This year, FHS is implementing through a one-year AGA rather than through the HSJF as originally planned due to delayed signing of an MOU between FHS and MoH. The AGA was set-up to ensure continuity of services while agreements are beings put in place, FHS will fully transition to HSJF from April 2025.Activities under Indicator 1.2 were delayed due to these issues (TLP ended in March 2024 and UW was expected to start in April rather than June 2024, 2 months late); some key activities such as CSE then coincided with school holidays. Through TLP, FHS has previously either met or overachieved this indicator, and will develop an acceleration plan to ensure more beneficiaries are reached, to catch-up. Indicator 1.3 has been partially achieved. FHS recruited new service delivery and demand creation staff who needed time to settle and create demand for more beneficiaries to access the services, especially in Balaka, a new district for FHS to operate in, compounded by a challenging district entry process. We expect results to improve as new staff settle and build relationships with Balaka District Health Management Team (DHMT).

Improving quality of care and integration (Indicators 1.4 to 1.9)
UNJP activities on quality improvement and integration (Indicators 1.4, 1.5, 1.7, 1.8, 1.9)
The UNJP has been implementing a package of interventions at district level in the 6 UNJP districts to improve quality of care, seeking to improve the work environment, workforce, and patient safety; improve the clinical processes of care through Continuous Quality Improvement (CQI); and implement Total Quality Management (TQM) approaches across both clinical and administrative functions. However, many of these activities were delayed by the time taken to develop and agree the joint UNJP workplan for 2024/25, and whilst individual activities delivered by each of the agencies were of acceptable quality, the added value of the joint approach was not clear, especially with the delays in funding that the joint mechanism introduced, with funds taking several additional months even after budget approval and FCDO disbursement to get to districts for implementation of activities (see VfM section and Annex 3 for further discussion). Quicker agreement on budgets and disbursement of funds would have allowed for more ambitious targets and results.
- Quality Improvement projects continue to be initiated and supported through MNCH QI mentorship in the 6 UNJP districts, aiming to sustainably build the capacity of health facility staff to apply the nine QoC standards to plan, implement, and monitor QI projects for better health outcomes, within a data-driven Maternal Perinatal Death Surveillance and Response (MPDSR) approach to identifying QI priorities. This is the main area that all three UN partners are directly engaged in, taking into account their different mandates. The evidence increasingly suggests that a more impactful and VfM approach is for mentorship to be embedded within a facility team rather than from the district or zonal level, so we are exploring new approaches for developing facility-based mentorship in our post-UNJP plans, linked closely with the development of a national mentorship strategy under the MNH Acceleration Plan, and with the new QoCLC between MoH QMD and KUHeS (supported by FCDO via HSJF). We are also linking UNJP with national work on Health Facility Accreditation (star assessments) – this was due to start during the reporting period but has been delayed and will kick off in early 2025. See links to some of the quality improvement Case Studies in Annex 2.
- The ability of health facilities to delivery good quality Emergency Obstetric and Newborn Care (EmONC) EMONC continues to be a challenge – both the availability of appropriately skilled staff and the necessary drugs, equipment and infrastructure – and is something that will continue to be a focus of the post-UNJP activities, as well as discussions on re/starting funding for essential drugs and equipment (and potentially infrastructure) through HSJF in future. In the meantime, UNJP has procured essential equipment and medical supplies in the 6 districts, that have been identified through QI projects as bottlenecks for improving quality.
- UNJP through UNICEF has supported improved referral systems between primary and secondary care through providing fuel and servicing for ambulances to facilitate referrals and established communications forums (e.g. district WhatsApp groups) for better referral planning and processes, although there continue to be lengthy delays in districts receiving UNJP funds in a timely way.
- The programme has also supported the provision of integrated outreach clinics to underserved communities for FP services, ANC, HIV testing and counselling, U5 vaccination, nutrition and development, through provision of fuel for outreach as well as training of 240 newly appointed Community Health Surveillance Assistants (CMAs) in the six districts. UNICEF is also providing support to the MoH to develop a comprehensive integration strategy.
Neotree activities on quality of care (Indicator 1.6)
Neotree is a digital QI tool which can bring improvements in real time data on small and sick newborns and strengthen MPDSR. It also provides real-time on-the-job training to help address the lack of staff in health facilities with experience of caring for these newborns. FCDO (through the regional research hub) previously funded adaptation of the tool for use in primary health facilities in Malawi, and from 2024/25 has started to support implementation, linked with the UNJP as part of our broader work on quality of care, targeted particularly at neonatal mortality which now makes up 50% of all under 5 mortality (MDHS 2024 – see Annex 1). Neotree is currently operational in three sites in Lilongwe District - Kamuzu Central Hospital, Kabudula Community Hospital and Lumbadzi Health Centre. Key activities during the reporting period include i) refining and optimising the Neotree system, including developing a criteria for which babies should be treated at the primary level vs which babies need to be transferred to a higher level facility, and enabling the transfer of their data on referral, creating a network of care; ii) setting up hardware, software, and stakeholder engagements in preparation for the upcoming roll out of Neotree to facilities in Kasungu District (linked to the UNJP work on QI).
The Neotree system has shown strong evidence of acceptability and feasibility across all current sites, though utilisation has fluctuated with periods of high and low adoption. This is a result of frequent staff turnover and high attrition within the facilities, electricity shortages, high burden of paper-based documentation by facilities, and high volumes of babies with respective to the staff available. The Neotree team is working with the facility teams to identify key barriers and short- and long-term solutions where possible, and carrying forward learnings when implementing in new sites, aligned with the UNJP districts and broader quality improvement activities.

Describe any changes to this output during the past year, and planned changes as a result of this review:
The weighting of this output has reduced from 55% to 40%, to reflect a more balanced allocation across the three output areas, and an increase in focus on accountability and management (output 2) and resilience (output 3). The main change during the reporting period is the inclusion of SRHR activities under the UW programme, and the initiation of Neotree activities to strengthen newborn care, as well as the shift from QI training towards a focus on the impact of QI work. Next year, the main changes planned under this output are the separate post-UNJP streams of work with UNICEF at the district level, potential UNFPA activities focused on EmONC, the entry and scaling up of Neotree work in Kasungu district, as well as shifting SRHR outreach services under HSJF as originally planned.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead

Progress on recommendations from last year’s Annual Review:
- The UW logframe has been revised to reflect the new areas of work. We will continue to align it with the HSJF Results Framework and the broader HSSP3 M&E framework currently in development.
- We have worked with HSJF DPs to ensure that the TIC is used effectively across a broader range of motions (including SLAs and DFF, rather than just infrastructure) and have informed the ToRs for the forthcoming TIC procurement to ensure this broader approach is built into the new TIC.
- We continue to discuss the implementation of multi-year motions, which was not possible for 2024/25 due to the very delayed budgeting process but is under discussion for 2025/26 and beyond, as well as the implementation of RBF in more HSJF motions
- We have worked with MoH, KUHeS and other partners to develop the national Learning Centre architecture to support HSSPIII implementation which we are now funding through HSJF from 2024/25, and with MoH/HEPU to broaden their work into an HSSPIII policy engagement platform. In addition to the direct impact on UW programmatic areas and an attempt to bridge the ‘evidence into action’ implementation gap, we see this as a public good in itself, an important part of our broader health system work, strengthening Malawian intellectual capital in the sector.
- We have reviewed the UNJP operating model in districts and are in the process of wrapping up the UNJP arrangement by the end of 2024/25 and will go ahead with separate bilateral arrangements with UN partners on a more defined set of activities in 2025/26. This will include a larger budget for equipment, to address basic gaps at facility level, but we are also in discussion with MoH about the potential to come back in to support equipment through HSJF from 2025/26.
- Through the roll out of DFF, we continue to work with UN partners and MoH to strengthen the links between HSJF and district level work, centred around the DIP.

Lessons learned:
- The World Bank’ Health Emergency Project was instrumental in bridging the gap in HSJF funding for SLAs but will end in December 2025. There is need for a strategic review of the SLA implementation and financing model in order to ensure predictability and sustainability in future.
- The UN Joint Programme approach has been increasingly difficult to justify, given the lack of clear added value of a joint mechanism rather than bilateral funding which is more easily tracked, the time taken for UN partners to develop a jointly agreed workplan and budget, and the lengthy process for funds to reach districts for implementation of activities. This has led to a review of the operating model and a decision to move away from a joint mechanism.
- Embedding QI mentorship within a facility team rather than from the district or zonal level is likely to be more sustainable and better VfM.

Recommendations for the year ahead:
1. Work with MoH, MoF and CHAM to better understand the long-term vision for the SLA arrangement, as well as sustainable financing plans, including committed domestic resources for CHAM staffing.
2. Ensure FHS SRHR services are integrated into the HSJF from 2025/26 rather than a separate AGA.
3. Continue discussions with MoH about shifting from annual to medium-term planning in the HSJF especially for strategic interventions such as the SLAs and SRHR services, and knowledge generation work. Increased predictability will enhance better targeting and evaluation of outcomes.
4. Continue to explore new approaches for developing sustainable mentorship models in our post-UNJP plans, linked with the national mentorship strategy under the MNH Acceleration Plan. And continue to work with UN partners to develop a cohesive package of supportive interventions, for example complementing mentorship with online Continuing Professional Development (CPD) to help bridge the gaps left by staff attrition.
5. Strengthen evidence generation and implementation research by continuing to strengthen the partnership between UNJP and the new QoCLC and integrating this research into programme development for more impactful interventions.

Output Title	Enhanced management of resources at national and district level and improved accountability between levels of the public health system
Output number:		2	Output Score:	B
Impact weighting (%):		35%	Weighting revised since last AR?	Y – increased from 30% last year

Indicator(s)	Milestone(s) for this review	Progress
2.1 NEW: % HSJF funds that are utilised, by financial year a) FCDO HSJF funds, b) all HSJF funds	Milestone 5 (Nov 2024): / a) 75% b) 75%	For 2023/24: Partly met / (a) FCDO funds 64% (actual) / 82% (including commitments); / (b) all HSJF funds 38% (actual) / 59% (including commitments) / For 2024/25: Not met / a) FCDO funds: 19% (actual) / 44% (including commitments) by Nov 2024. / b) all HSJF funds: 34%. / Low absorption due to late HSJF budget approval Oct ’24. / Score: C. Not met (new indicator, but tracked in the financial section in previous ARs)
2.2 UPDATED: Effectiveness of FCDO-funded research, analysis and evidence in improving policy and implementation decisions (including NEOTREE, HEPU and QOCLC), measured through: / a) Number of policy briefs, case studies and study reports produced (and delivered on schedule). / b) Number of the above leading into changes in policy or implementations, documented through case reports.	Milestone 5 (Nov 2024): / [indicator wording change] a) 3 b) 3	5 reports and policy briefs (4 HEPU (CHAM VfM report, DFF ex-ante/ex-post evaluation reports, health financing M&E handbook, HTA institutionalisation framework) and 1 QOCLC (DHIS2 QI Tracker) / 4 influenced policy decisions; 3 HEPU; 1 LC – see narrative for detail. / [Neotree grant started in Sept 2024, will contribute to this indicator in future] / Score: A+. Exceeded expectations (similar indicator scored B in last AR)
2.3 NEW: Effectiveness and sustainability of the MoH Quality of Care Learning Centre (QOCLC) activities in facilitating comprehensive learning within the healthcare system to enhance delivery of quality healthcare. Measured by: / a) Development of: / 1- a functional reporting system, / 2- a website for sharing learning, / 3- a design for process and impact evaluation for HSSPIII reform areas, / 4- pre-service and in-service QI courses / 5- a QOCLC sustainability plan/business model incl. alternative financing sources / b) Number of health staff completed training on QoC (per year)	Milestone 5 (Nov 2024): QOCLC functional (staff hired, etc.)	QOCLC staff hired, centre is fully operational. In addition: / Reporting system (a1) for QI developed [DHIS2 QI tracker] / Pre-service and in-service fundamental QI courses developed (a4) / QOCLC sustainability plan developed (a5) / Score: A+. Exceeded expectations (new indicator, not scored in last AR)

Indicator(s)	Milestone(s) for this review	Progress
2.4 Percentage and value (US$) of national forecasted need for FP commodities met by FCDO / [This indicator is for tracking purposes only, no targets set]	Milestone 5 (Nov 2024): / No target - tracking only	N/A – there was no FCDO funding provided for commodities during the reporting period to Nov 2024 (due to delays in HSJF motion sign off)
2.5 Percentage (in terms of value) of commodities arriving in time in the country, according to the plan	Milestone 5 – Nov 2024: / 80%	No data available – we agreed this indicator with UNFPA during Logframe discussions in 2024; however, on trying to obtain this for the Annual Review, neither MoH nor UNFPA (who procure the FP commodities) collect nor report on this data. Consider removing indicator or working with MoH / UNFPA to track in future. See recommendations. / Score: C. Not met
2.6 % of funded activities implemented (fully and partially) according to the selected districts' 'Detailed Implementation Plan' (DIP) using the annual DIP report	Milestone 5 – Nov 2024: / 70%	National: 70% / UNJP Districts: 77.4% / Score: A. Met expectations (scored A in last AR)
2.7 Proportion of health facilities in the UNJP districts that have undergone an Integrated Supportive Supervision at least once in a quarter during the previous 12 months	Milestone 5 – Nov 2024: / 75%	100% / Score: A. Met expectation (not reported last year; previously A+)
2.8 Effective roll out of Direct Facility Financing: / (a) Mechanism for funding agreed and bank accounts/governance mechanisms set up; / b) Percentage of facilities receiving FCDO-funded DFF that have a functional* Health Centre Management Committee (HCMC) / (c) Number of Health Facilities that have received Health Centre Improvement grant or DFF payment / (d) proportion of facilities that utilised and accounted for 100% of their grant / *Functional is at least four meetings per year and minutes available"	Milestone 5 – Nov 2024 / a) Complete / b) 100% of facilities / c) 30 (two districts) / d) 100%	Complete – as set out in the approved HSJF DFF motion / Not met - HSJF DFF motion only approved at end of reporting period (Nov 2024), so no DFF funds yet flowing via HSJF. No UNJP DFF activity took place during the reporting period either due to delayed UNJP budget approval. / Not met - 29 health facilities (16 in Rumphi, 13 in Ntchisi) are due to receive DFF funds via UNJP but funds not yet disbursed (scheduled for Jan 2025 to allow time for capacity-building activities for HCMCs and District Council team to strengthen accountability). / Not met - 0% (no DFF grants disbursed during reporting period, either through UNJP or HSJF) / Score: C. Not met (similar UNJP indicator scored A+ in previous AR)
2.9 NEW: Percentage of facilities with no stock-outs of FP commodities in the last month	Milestone 5 – Nov 2024 / 75%	82% for primary facilities / 75% for secondary facilities / 100% for tertiary facilities / Score: A. Met expectations (new indicator, not scored in last AR)
2.10 Percentage of family planning commodities procured and distributed in time according to distribution plan at district level	Milestone 5 – Nov 2024 / 60%	No data available – we agreed this indicator with UNFPA during Logframe discussions in 2024; however, on trying to obtain this for the Annual Review, neither MoH nor UNFPA (who procure the FP commodities) collect nor report on this data. Consider removing indicator or working with MoH / UNFPA to track in future. See recommendations. / Score: C. Not met

Briefly describe the output’s activities and provide supporting narrative for the score.

The output covers a range of indicators aiming to track and strengthen management of resources at national and district level and the accountability between levels. It covers the following activities:
- Overall HSJF efficiency, measured through utilisation
- Generation and use of evidence for decision making in the health sector
- Support to procurement of FP commodities at national level (and an increasing focus on the effectiveness of forecasting as well as distribution to the last mile)
- District level activities to improve governance, planning and implementation
- Roll out of Direct Facility Financing first through the UNJP and now transitioning to HSJF
As elsewhere throughout this Annual Review, there has been variability in progress, mainly due to delayed approval of HSJF and UNJP budgets impacting on activities during the reporting period.

HSJF efficiency (Indicator 2.1)
Under HSJF, the 64% budget absorption and 82% budget utilisation (inclusive of pipeline invoices as of 31st March 2024) that was recorded in the 2023/24 fiscal year represented an improved performance compared to 60% absorption rate during the previous financial year. However, this then stalled due to the time taken to approve the 2024/25 budgets, resulting in substantially reduced absorption since March 2024. This is now getting back on track, following approval of the majority of motions in Sept/Oct 2024. We continue to work with HSJF Secretariat to improve processes, including the development of an HSJF Operational module setting out procedures and timelines, and the proposal for multi-year motions for areas such as SLAs and DFF to reduce the annual burden of motion development. We also continue to work with GoM to better use HSJF as a strategic fund – part of a comprehensive approach to sector financing – rather than to reactively fill funding gaps.

Generation and use of evidence for decision making (Indicators 2.2, 2.3)
FCDO has supported the Health Economics and Policy Unit (HEPU) at KUHeS through the HSJF for a few years now, to support evidence-based policy and decision making in the health sector, given Malawi’s limited financial resources. This year we also provided funding to the Quality-of-Care Learning Centre (QOCLC), a collaboration between the MoH and KUHeS to strengthen the generation, collation and utilisation of evidence on quality improvement. The funds we provided aim to be catalytic, used to kick start the work and to develop a sustainability business model, such that the QOCLC can increasingly sustain itself through grants and donor funding can reduce. During the period under review:
- HEPU completed the VfM assessment of CHAM-MoH SLAs, which concluded that SLAs represent VfM and was used to inform development of a new MoU between Malawi Government and CHAM which should have come into force from Jan 2025, but which has not yet been finalised.
- HEPU completed a health financing baseline M&E framework which will be utilised by MoH for mid-term and end term evaluation of the health financing strategy. This is the first time that a GoM health financing strategy has had a robust M&E framework to evaluate effectiveness of approach.
HEPU’s evaluation of DFF roll out in Rumphi through UNJP has informed the national scale up model. For example, the resource allocation formula which came out of the study recommendations was directly incorporated in DFF guidelines for immediate operationalisation.
- HEPU finalised the Health Technology Assessment (HTA) institutionalisation framework, which is yet to be adopted, but will guide prioritisation and adoption of cost-effective health technologies (drugs, medical devices, diagnostic tests, medical procedures).
- HEPU has also continued delivering ‘Think Tanks’ that bring together researchers and policy makers on priority topics. The past two years have seen increased demand from policy makers for knowledge generation, in part due to HEPU’s work to increase frequency of this engagement. This has led to growing calls for a shift to HSSPIII Think Tanks, expanding the spectrum of policy discussions beyond HEPU’s health economics work streams.

Despite becoming operational only from Q2 FY2024/25, QOCLC has developed: DHIS2 QI Tracker, to enable projects to be monitored alongside other health data; a pre-service and in-service ‘Fundamental QI’ course to be rolled out in 2025/26; a QOCLC sustainability plan and 5-year strategy, seeking to diversify resource mobilisation avenues; and an evaluation protocol for HSSPIII Integration reforms.

While considerable evidence is being generated to inform decision making and policy direction within MoH, there is opportunity to better maximise this, as use of evidence in decision making remains limited.

Support to procurement of FP commodities at national level and effectiveness of distribution to the last mile (Indicators 2.4, 2.5, 2.9 and 2.10)
During the reporting period FCDO did not disburse funds for FP commodity procurement because the previous programme (TLP) was transitioning to UW and shifting the funds into the HSJF, and there were lengthy delays in development and approval of new motions on both FP commodity procurement (through UNFPA – with the motion only signed in Sept 2024) and SRHR service delivery (through FHS, discussed earlier under Output 1).
There is general agreement that despite the national efforts to coordinate FP commodity forecasting, the estimates do not match the actual national need. The whole process of FP commodity forecasting needs to be revisited starting from population data which feeds into commodity estimates. Continuous FP commodity stock outs and gaps in last mile remain a manifestation of a supply chain management system which is not working effectively to meets FP needs of users.
The common definitions of ‘stock out’ used are also misleading, as at lower levels of service delivery (primary and secondary) availability of three methods means no stock-out, whereas at tertiary level availability of at least five methods means no stock out. However, the definition does not consider the absence of popular methods in high demand, and as a result, field visits and beneficiary feedback are still important sources of anecdotal evidence around the true picture of stock-outs.
FHS has been supporting district level stock management through supporting reallocation of FP commodities from overstocked facilities to those with need, however this is a short-term intervention as it is based on available commodities within the district. It does not contribute towards accurate forecasting and establishing the need. FHS continue to support coordination platforms to monitor FP commodity stock status at district level, this has helped to track commodities and ensure availability of commodities in the facilities, however this is based on the available stock within the districts. FHS will need to work more with RHD and UNFPA to influence FP commodity availability and evidence-based procurement from national level, down to facility level.

UNJP activities to strengthen district planning and implementation (Indicators 2.6, 2.7)
The program has supported the development, implementation, and monitoring of evidence-based and risk-informed annual operational workplans in all six target districts. UNJP through UNICEF engaged all District Commissioners (DC) and key District Health Management Team (DHMT) members, emphasising the DCs' accountability for district results. We continue to work with UN partners to bring down the DSA costs and increase the sustainability for these planning processes.
The programme supported all six districts in conducting two rounds of quarterly integrated supportive supervision (ISS) visits across all 149 health facilities. These visits focused on ensuring the availability of facility reports, reviewing records of DHMT meetings, and examining existing supervision reports. This is in part because the ISS tool is lengthy making it challenging to review all the indicators in one sitting. UNJP is engaging the Quality Management Directorate (QMD) to review and revise the ISS tool to be more streamlined and informative, enhancing its usefulness for evidence-based decision-making in the districts and zones. This revision will include a review and reconstitution of ISS teams to ensure a balanced, representative team approach, strengthening the integrated nature of supervision efforts.

Roll out of Direct Facility Financing (Indicator 2.8)
In collaboration with partners, UNJP through UNICEF provided technical support to finalise the national DFF Guidelines, a key framework empowering health facility with financial autonomy to address local needs. Following the guideline approval, the UNJP provided technical support to develop a comprehensive DFF Training Manual. This manual is an essential resource for district trainers, mentors, and health facility staff, who will provide further training to Health Centre Management Committees (HCMCs). Although activities were delayed for 6 months due to delays in approving the UNJP workplan for 2024/25, the UNJP continued the work started during the last reporting period, rolling out DFF in two districts Rumphi and Ntchisi with District Engagement meeting to orient the District Executive Committee (DEC) on the DFF approach; conducting training of trainers (ToTs) on DFF; reconstituting Health Centre Management Committees (HCMCs) and HCMC training. Following these preparatory steps, capacity building of District Council DFF team officers in accountability and risk assurance will follow suit in January 2025 followed by the disbursement of the DFF grants to health facilities, and implementation and monitoring. A joint stakeholder visit will conclude this phase, appraising the DFF projects' effectiveness and alignment with district health priorities.
Work is underway to bring other development partners on board with national DFF roll out, with a new HSJF DFF motion signed by FCDO and RNE in late 2024 which will initially cover 144 public health facilities across 6 districts (Balaka, Chikwawa, Dedza, Kasungu, Lilongwe, Salima) in addition to the two districts currently supported through UNJP. The plan is to transition the grants for Rumphi and Ntchisi into the HSJF from 2025/26, leaving UNICEF to do the capacity building and TA in those districts.
Describe any changes to this output during the past year, and planned changes as a result of this review:
This output has had the most change to indicators since the last annual review, and the weighting has increased from 30% to 35%. Previously, it focused only on four district-focused UNJP specific indicators (around the District Implementation Plans, ISS, Health Centre Management Committees and Health Centre Improvement Grants). With the take up of DFF by the government and the national roll out, as well as the integration of FCDO’s SRHR components into UW including procurement of FP commodities, this output has been expanded to focus on a broader range of indicators that aim to track management of resources at both national and district level as well as accountability between levels of the health system. The main planned change under this output in the next year are:
- Increasing work with RHD, UNFPA and districts to support evidence-based forecasting that is informed by harmonised data platforms, and last mile delivery of FP commodities, linking this with work at district level through UNICEF and the Central Medical Stores Trust (CMST).
- Continued transition of DFF grants into HSJF, although we are likely to maintain some funding for technical assistance through UNICEF, given the importance of the governance arrangements for successful roll out, including donor confidence in management of fiduciary risk.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead
Progress on recommendations from last year’s Annual Review:
1. Through both HSJF and UNJP, FCDO continues to support institutionalisation of DFF within Public Financial Management systems, with the development of the DFF Roadmap and DFF Taskforce, and agreement for the modality through which HSJF donor funds (FCDO, KfW, RNE) will flow.
2. FCDO continues to work with MoH and other DPs to advocate for "One plan, One budget and One monitoring report" between government and partners for coordinated district implementation.

Lessons learned:
- The significant delays to approving both the HSJF and the UNJP 2024/25 budgets (for different reasons) have directly led to low fund utilisation rates in the HSJF, and to delays in conducting district level activities in the UNJP. We continue to work with MoH to start the budgeting process earlier and for HSJF motions to be developed in partnership with DPs so that it can be concluded before the start of the next financial year (see recommendations). Given the challenges in justifying the added value of a joint UN model on the ground rather than on paper, we are reviewing the delivery mechanism, as discussed in Section A.
- HEPU-led Think Tanks appear to be encouraging ‘research to policy’ adoption: they engage policymakers in a collaborative approach that ensures research addresses real policy needs. The platform allows instant feedback and HEPU reports that some policy recommendations have been adopted immediately after the Think Tank. Given that we often then see a ‘policy to action’ gap, we should continue to consider how to better drive implementation of best practice. We are working on building this into the relationship between the national QOCLC and our district UN work.
- FCDO’s condition that funding to the QOCLC was contingent on the integration of sustainability plans into the implementation model has been key in diversifying funding sources for QI activities. The Centre has been proactive in securing more grants to complement FCDO’s commitment. FCDO’s provision of core funding (including staffing) has enabled it to get up and running quickly, increasing its visibility and it is already experiencing demand for its services, increasing the likelihood for knowledge utilisation.
- There is confusion among districts and implementing partners around FP commodity stock management platforms: some districts are more inclined to use e-HIN while others are solely using LMIS. This brings inconsistency in stock management and FP commodity forecasting. There were challenges in measuring some of the chosen indicators, which we will need to address in the next Logframe revision (see recommendations)

Recommendations for the year ahead:
1. As DFF transitions to national roll out, ensure maintained focus on the critical role of well-trained HCMCs/District teams for equitable decision making and good governance to mitigate fiduciary risk.
2. Work with the MoH HSJF team to consider which motions would work better as multi-year motions, to streamline the planning process, enhance funding predictability and improve implementation. It is likely that this would include the knowledge generation activities under HSJF (HEPU, LCQOC)
3. FCDO to ask FHS to work with UNFPA to identify an effective way of using data systems (e-HIN, LMIS, DHIS2) to manage the confusion and inaccuracy in FP stock management and forecasting. While interoperability is an option the work should focus on having a platform that is user friendly, lower maintenance costs and sustainable.
4. Definition of FP commodity stock-out needs to be reconsidered presence of three or five methods should not be the only criteria, Feedback from beneficiaries considers a service delivery point out of stock if commonly used methods such as DEPOPROVERA and Emergency contraceptives are absent. FCDO to work with FHS to take the discussion to RHD and UNFPA
5. FCDO programme team to review SRHR indicators as part of the broader Logframe review following this Annual Review, to ensure that they are fit for purpose and able to be tracked.

Output Title	Improved ability of the health system to prepare, prevent, detect and respond to health threats including climate shocks and disease outbreaks
Output number:		3	Output Score:	A
Impact weighting (%):		25%	Weighting revised since last AR?	Y – revised up from 15% last year

Indicator(s)	Milestone for this review	Progress
3.1 NEW: # of UNJP districts that have developed costed evidence-based annual multi-sectoral and multi-hazard public health emergency plans and included in the DIP	Milestone 5 (Nov 2024) / 3 districts	6 Districts: all six districts are in the process of revising their costed, evidence-based, annual multi-sectoral, and multi-hazard public health emergency plans to ensure alignment with the newly released DODMA 2025 Plans. / Score: A+. Exceeded expectations (similar indicator scored A+ in last AR)
3.2 NEW: % of public health events detected and responded to within 48 hours of detection in targeted UNJP districts.	Milestone 5 (Nov 2024) / 100%	100% / Chikwawa detected, reported, and responded to a Cholera case within 48hrs. This was documented as well managed. / Rumphi detected, reported and responded to two events: Measles and Cholera within 48hrs. / Score: A. Met expectations (new indicator, not scored in last AR)
3.3 Timeliness and completeness of IDSR in UNJP districts: / a) % of targeted health units (health facilities) reporting on time (timeliness of IDSR) / b) % of targeted health units (health facilities) attaining completeness in IDSR reporting	Milestone 5 (Nov 2024) / a) 80% of health facilities reporting on time / b) 80% of health facilities attaining completeness"	Data timeliness: Source: DHIS2 / Nationally: 80%; / UNJP districts: 100% / Data completeness: Source: DHIS2 / Nationally: 85%; / UNJP districts: 100% / Score: A+. Exceeded expectations (scored A in last AR)
3.4 Percentage of health care facilities in the selected districts with functional hand hygiene facilities (with water and soap and/or alcohol-based hand rub) available at points of care, and within 5 metres of toilets [MOVED FROM OUTPUT 1]	Milestone 5 (Nov 2024) / 30% (reduced from the previous 40% milestone)	40% (although variability in the utilisation and functionality has been observed in the UNJP districts with some having no soap and periods of lack of water) / Score: A. Met expectations (not scored in last AR)
3.5 NEW: No. people and social institutions with improved access to clean energy: / a) Development of sustainable health financing models for clean energy / b) Additional number of health facilities with improved access to clean energy	Milestone 5 (Nov 2024) / a) Health financing for solarisation consultations held and pilot developed / b) 3	a) Met - HSJF motion for a ‘health financing for solarisation’ pilot developed and approved for funding / b) Not met – delay to global GCF approval and to HSJF motion approval means the Save the Children climate work has only just started. Tool for assessing health facility climate resilience (including access to clean energy) developed but not yet implemented. / Score: B. Partly met (new indicator, not scored in last AR)
3.6. NEW: No. people with improved (climate) resilience	Milestone 5 (Nov 2024) / a) Number of people reached by UNICEF El Nino Nutrition interventions - 1,009,130 (753,006 children under five and 256,124 pregnant and breastfeeding women). / b) determine whether planned GCF climate and health work will contribute to this indicator, and if so, set milestones	Exceeded: Number of people reached: 943,241 (August 2024 to date) – 93% of 2024/25 target / 784,933 Under fives / 158,308 pregnant and breastfeeding women / Met: Planned GCF climate and health work likely to contribute to this indicator, milestones not yet set as GCF global approval delayed and HSJF motion signed in late 2024 / Score: A. Met expectations (not scored in last AR)
[note] Target of 1,009,130 to be reached by UNICEF El Nino interventions is through the original £800k of FCDO funding in 2024/25. A further £500k has been provided to support the El Nino response, so the targets have been increased to 1,850,000 (1,250,000 <5s and 600,000 pregnant and breastfeeding women) by end March 2025.

Briefly describe the output’s activities and provide supporting narrative for the score.
Across the Umoyo Wathu programme, we have stepped up and consolidated our work to support the health system to better prevent, prepare for, detect and respond to health threats, including climate shocks. Through the UNJP we have focused on supporting districts to plan for public health emergencies, to improve WASH and IPC in health facilities as a core component of quality of care, to preposition essential cholera and other health/WASH supplies in outbreak prone districts, and to strengthen disease surveillance systems. Through the HSJF Emergency Preparedness motion, we initially supported the response to Malawi’s worst cholera outbreak and over the last year have shifted the focus of the motion to strengthening preparedness through funding a range of activities including development of a national One Health strategy, an assessment on the burden of zoonotic disease in Malawi, conducting Simulation Exercises, training of first responders, procurement of PPE, chlorine and water testing kits, reagents for sample collection and provision of fuel for sample transport to reference laboratories during outbreaks.
There is evidence that this is paying off, with improvement in timeliness and completeness of surveillance data (a prerequisite for being able to respond in a timely way) demonstrated through more regular and complete IDSR reporting (timeliness of reports in UNJP districts increasing from 47% to 100% and completeness rising from 86% to 100%), as well through the draft findings of Malawi’s Joint External Evaluation (JEE) which was undertaken in early December 2024 – the evidence presented suggested that Malawi has made significant improvements across a number of dimensions including surveillance but we have yet to see the final report with the full scores.
We have also stepped up our climate and health work, providing match funding to the Green Climate Fund MoH/Save the Children climate resilient health systems project, funding an assessment of climate resilient health facility infrastructure and initial work on climate sensitive surveillance and early warning systems. We are also funding CHAI to work with MoH to enhance coordination and sustainability of health facility solar electrification investments and develop a renewable energy certification in Malawi for carbon offset. These have taken longer to get off the ground than anticipated (on the GCF side, mainly due to global delays in project sign off, outside our control), but kicked off towards the end of the reporting period. In addition, recognising the impacts of El Nino weather patterns on food security, we allocated an initial £800k and then an additional £500k of our health funds towards nutrition services via UNICEF, focusing on early identification, referral, and management of children and pregnant and breastfeeding women with acute malnutrition. More recently, Mozambique’s post-election violence has caused an influx of asylum-seekers entering Malawi through Nsanje District, and FCDO funded and prepositioned RUTF through UNICEF is being utilised to support the response to high rates of malnourishment/wasting in children from displaced populations. The nutrition status of the vulnerable population is already compromised, and more children are expected to become malnourished due to inadequate intake of food at the settlement sites.
Describe any changes to this output during the past year, and planned changes as a result of this review:
The increased focus on a purposeful rather than reactive approach to resilience is reflected in the increased weighting for this output from 15% to 25%. The Joint External Evaluation (JEE) of Malawi’s preparedness capacities for timely detection, prevention, and effective response to public health emergencies was completed in December 2024, and the findings will help to shape the focus of the UW programme (as well as the new TDDAP2 programme). Post-UNJP, we plan to continue to support emergency preparedness activities at district level through UNICEF, and nationally through an expanded HSJF motion on emergency preparedness, with delivery through WHO and PHIM. WASH capacity in Malawi continues to be a significant gap, with consequences both for quality of care (sepsis is the leading cause of maternal deaths), and spread of AMR, as well as ability to prevent and respond to outbreaks such as cholera and typhoid, and so we are working with UNICEF to increase the focus on IPC/WASH in health facilities through the post-UNJP plans, and will continue to work with the Wash Systems for Health CMP under the Healthy Women, Children and Newborns (EPD) programme of work.
Our match funding to the Save/GCF work on climate and health in Malawi was initially only for one year, but we plan to continue funding, potentially expanding the programme to the more climate-impacted UNJP districts. We also plan to continue to work with CHAI, MoH, Ministry of Energy and others on developing and implementing sustainable financing plans for health facility solarisation.
The UNICEF nutrition component in 2024/25 was always intended as a one-off response to help mitigate the anticipated undernutrition associated with El Nino effects, As we plan budgets for 2025/26, we will consider whether to continue with nutrition interventions for another year.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead

Progress on recommendations from last year’s Annual Review:
- Thorough the TOC/Logframe review, the programme team have considered how the programme can best support resilient health systems, to strengthen climate resilience and Global Health Security. This includes reviewing the balance between proactive and reactive response, and between bringing in external support and strengthening local systems. This should continue to be a focus of the programme this coming year, especially as the centrally managed TDDAP2 programme and the Save/GCF work starts in earnest, and we consider the balance of bilateral and central funding around investment in systematic and integrated surveillance and climate-informed early warning systems. We continue to work with WHO through the HDG health security subgroup to better coordinate and communicate what all partners are doing around emergency preparedness and response.
- As we integrate SRHR into UW, we continue to consider how to strengthen SRHR in emergencies.
Lessons learned:
There is lots of new funding for pandemic preparedness and emergency response but a lack of coordination, and an overfocus on costly response (Emergency Medical Teams, PHEOCs) rather than better VfM upstream preparedness and resilience. The JEE presents an opportunity to align partners around a national Health Security Action Plan (NAPHS).
Recommendations for the year ahead:
- Post UNJP, shift the work on surveillance systems and emergency preparedness that WHO was doing through UNJP into the HSJF motion on emergency preparedness. Consider how UNICEF can best work on resilience activities at district level, integrating interventions across sectors (health, WASH, RCCE) to ensure a coordinated and holistic response, with links to national level.
- Continue to consider how UW can best support resilient health systems, to strengthen climate resilience and Global Health Security – as per the lessons above, balancing proactive and reactive response, bringing in external support vs strengthening local systems, and bilateral vs CMP. We should ensure that our investments into health security – support to PHIM through HSJF as well as through other UK funding (TDDAP2, Fleming Fund/AMR) – are building the systems and workforce to detect not just to respond. And that there is investment into coordinated structures from national to community level, and across sectors beyond health.
- Given the increasing funding for preparedness and response (World Bank, USAID, WHO Flagship) and following the JEE in December 2024, continue to support better coordination around health security investments, for instance through the HDG health security subgroup.
## D: VALUE FOR MONEY

Key cost drivers and performance, and VfM performance compared to the business case
Value for Money of the programme as a whole
Changes to the operating context (Section A) are likely to have impacted on programme VfM, including increases in global commodities prices and delays to programme implementation due to ODA uncertainties. However, overall, the programme still represents good VfM, with a robust evidence base for the areas of focus and the approach. To sustainably strengthen health systems, we need to focus on catalytic, short, and medium interventions, while laying foundations for long-term action. This includes supporting health ministries to effectively pool and align funds; implement public financial management reforms, strengthen efficiency and accountability; and deliver prioritised, cost-effective essential services that meet needs of the most vulnerable. These are all UW programme focal areas. Efforts within the year to improve VfM include supporting new partners to join the HSJF to improve VfM of governance mechanisms such that the fixed costs (FA/TIC) constitute a smaller proportion of overall spend and driving better use of the TIC across motions. We continue to strengthen MoH capacity to effectively manage the HSJF including through the recurrent RBF discretionary budget motion, and introduction of RBF into other motions such as the TIC contract. We continue to promote evidence-based decision-making through targeted funding to HEPU and new support to an HSSPIII QoC Learning Centre. Digitisation of some processes within the HSJF has enabled time efficiencies in programme delivery. Overall, the UNJP mechanism contributed to low VFM. Funds disbursed to UNJP partners took approximately 2 months from FCDO to the UN Agencies via the Multi- Partner Trust Fund (MPTF)/ UN Resident Coordinator’s Office. This was against a target of 20 days. This meant district level partners receiving the funds quite late for effective implementation. The delay in budget approval for UNJP also contributed to time lag. For the future, the UNJP is being replaced with a bilateral funding mechanism which we anticipate – through previous experience – will reduce the timeline to approximately 10 days. The change in funding mechanism is an opportunity for the programme to be more focused, streamline results and maximise programme delivery efficiencies. Quicker agreement on budgets and disbursement of funds should allow for more ambitious targets and results. The programme team and partners continued to use the VfM framework (Annex 3). This is designed to complement the Logframe and will be reviewed when the Logframe is next reviewed. A summary of performance against FCDO’s VfM framework is given below:
[note] FCDO 2021: Health Systems Strengthening for Global Health Security and Universal Health Coverage

Economy:
- The macroeconomic crisis and shortage of forex has led to significant increases in unit cost of many commodities, and to rising fuel and transportation costs. This has put pressure across the health sector. For instance, SLAs use fixed national prices normally reviewed once a year based on market prices and jointly agreed by CHAM and MoH. For the reporting period, prices were adjusted by 16.5% in April to cushion escalating costs, but this was not sufficient to mitigate the full impact. Drugs and PPE are the major cost drivers, resulting in reimbursement rates which do not match actual costs. Conversely, the continued real devaluation of the Malawi Kwacha in the year has led to a favourable HSJF dollar exchange rate, leading to realisation of an additional MK1bn for SLAs compared to expected, as SLA prices at that point had not been adjusted following devaluation. In future, the new MoU between MoH and CHAM will increase reimbursement costs from 70% to 80%. Planned workshops have been affected by increased transport costs for district and national participants. Most price increases happened when activities were already far advanced in planning and dates set. Fuel scarcity has led to delays or failure to implement some of the interventions. Water and electricity utility bills took much of ORT resources that should have been used for direct implementation of health interventions at district level.
- The main cost drivers within the HSJF include salaries and allowances for the FA and TIC (fixed costs), and programme delivery related costs for SLA medical services, SRH outreach activities under FHS, research activities under HEPU and the Learning Centre. Salaries for the FA and TIC did not change in the reporting period. These fixed costs have been included as an indicator in the VfM matrix (see Annex 3: for instance, 20% of FCDO’s HSJF budget went towards these fixed costs in 2022/23; 19% in 2023/24, down to 16% during 2024/25 following increased FCDO HSJF funds). The HSJF DPs are reviewing the Terms of Reference for the TIC re-procurement to maximise available staff and associated costs.
- Through the UNJP, economies have been realised through revised DSA rates, use of the UN procurement system as well as through vehicle-sharing, minimising transport costs by combining field visits for different purposes. Additionally, UN agencies are making use of existing staffing (e.g. comms) and of central offices for physical meetings, avoiding new structures and capital expenditure. As a technical assistance programme, key UNJP cost drivers include technical staff salaries which made 35% of the programme budget. Technical staff are recruited using UN recruitment systems. As the UNJP budget was increased during the reporting period, staffing costs also rose, with a more ambitious programme requiring technical assistance across a broader range of areas. However, the programme largely operates through government structure, minimising salary costs for implementing staff.
- The FCDO-funded VfM study conducted by HEPU concluded that SLAs with not-for-profit health facilities represent good VfM: SLA prices under CHAM are lower than private facilities and even CMST, and besides promoting equity, GoM is also making net savings on infrastructure investment.
- FHS drives demand creation for their services at relatively low cost, through engaging with youth clubs to organise youth open days and clubs as well as using Health Surveillance Assistants (HSAs).
- Neotree‘s approach to sourcing certain equipment from the UK (such as android tablets) at a lower cost and greater reliability than readily available in Malawi is also enhancing VfM.
Efficiency:
- The HSJF Fiscal Agent and Procurement Oversight Agent (FPOA) undertakes a VfM approach on all HSJF payments. They verify procedures and whether expenditure deliver good value through checking payment request alignment to donor guidance, accuracy and reasonableness of payment request e.g. distances and claims of fuel, and use of sufficient documentation for paying. They also ensure payments align to the motion and budget approvals. During the reporting period, the TIC has continued to provide cross-cutting support to the HSJF beyond infrastructure. Influencing the composition of key TIC staff to cover broader HSJF activities means FCDO is getting more out of the TIC this year compared to previously when the TIC’s technical expertise was heavily weighted towards construction. We will continue to keep this under review through the TIC re-procurement
- Digitisation of the SLA invoicing process has helped with accuracy and easy generation of data resulting in less time required for verification of data for payments. The planned SLA Financial Management Information System should impact on timelines for payments positively.
- The introduction of the HSJF RBF Discretionary Budget continues to enable a reduction in the number of small motions, each of which take time to administrate. It gives MoH access to more flexible and responsive funding, improves efficiency of administering motions, and incentivises MoH to improve HSJF governance. RBF metrics are updated each year to focus on areas of greatest inefficiency.
- The long HSJF and UNJP budget approval in 2024/25 has reduced time for effective implementation. We are working with both HSJF and UNJP to ensure 2025/26 budgets are approved well in time.
The HSJF utilisation of funds has been include in the VfM Matrix 2. Utilisation of FCDO 2023/24 budget was 64% actual and 82% including pipeline invoices as of 31st March 2024 (above HSJF average of 38% and 59% respectively). However, at 30 Nov 2024, FCDO utilisation was at 19%, below HSJF overall utilisation of 34%, mainly due to delayed approval of the HSJF budget.
- FHS is collaborating with other catalytic projects like DISC 2.0 and Hormonal IUD project on re-distribution of commodities and open days, reducing programme expenditures.
- UNJP works within decentralised government structures to maximise financial efficiencies and ownership of interventions and knowledge building. However, this was undermined by systemic coordination challenges amongst the three agencies as already highlighted.

Effectiveness:
- HEPU’s Think Tanks and policy labs continue to provide policy engagement platforms that enhance joint working between HEPU and MoH. In the reporting year, 90% of attendees have reported value in the think tank through feedback forms. In year the HJSF evaluation was finalised, providing evidence for strengthening effectiveness of donor funds executed through the HSJF; and the CHAM SLA VfM assessment provided evidence for continuing to fund not-for-profit service providers. Work is underway to transition the HEPU Think Tanks to cover a broader range of HSSPIII pillars. However, timeliness of outputs and therefore ability to effectively influence policy direction continues to be a concern; we are working with HEPU/MoH to better incentivise timely delivery of outputs to meet policy windows.
- UNJP has incorporated both service delivery and system strengthening elements to maximise impact on saving lives within the focal districts. In the reporting year, the UNJP continued to strengthen the use of District Implementation Plans (DIP) in districts. Under the ‘One Plan, One Budget, One Report’ reform, there is increasing partner coordination at the district level with 77.4% of funded activities implemented according to the selected districts' DIPs.
- The focus on capacity building at the sub- level, should help to increase the sustainability of results. However, UNJP activities slowed down again this year, due to prolonged proposal and budget approval processes; and delays in disbursed funds reaching downstream implementing partners. Funds went through 2 partner tiers before reaching the implementing partners in the districts as funds disbursed from FCDO in May 2024 to the Multi Partner Trust Fund (MPTF), reached the UN agencies in August 2024. Such delays meant limited implementation time for district level partners who got their funding mostly in the last quarter of 2024. Proposal and budget approval processes were affected by limited coordination among the UN agencies and challenges in agreeing funding areas, in line with each agency’s proposed mandate. This meant less implementation time for agreed activities hence impacting on effectiveness. A review of the UNJP funding mechanism was done to assess how well the programme component was delivering results. A decision was made to revisit the funding mechanism and options have been agreed to change the mechanism to single agency delivery with a streamlined focus of activities. This is in line with the Umoyo Wathu Programme Business Case which set out that the Joint Programme arrangement would be a trial, to be reviewed if it was not effective.
- FHS supports integration of various services to maximise reach and impact, providing opportunities for clients to access a wide range of services: FP, GBV, HTS, STIs, and cervical cancer screening.

Cost effectiveness:
- Support to SLAs enables the delivery of the Health Benefits Package (HBP) to all districts in Malawi, and the increased funding has meant HSJF funding has scaled back up from 78 facilities in 2023 to supporting all 168 facilities in 2024. The package is cost effective (see original BC VfM calculations) and the SLAs enable access to the EHP for remote communities without access to public facilities. Analysis suggests that the SLA’s Incremental Cost Effectiveness Ration (ICER) is around $135 per QALY gained, representing 37% of Malawi’s per capita GDP. Using the threshold of 1.5 times per capita GDP, MCH services provided through the SLAs are demonstrably cost-effective. An assessment of CHAM Value for Money conducted in 2024 by HEPU (using FCDO funds) outlines that CHAM efficiency scores are higher that MoH ones.
  [note] Zeng W, Sun D, Mphwanthe H, et al. The impact and cost-effectiveness of user fee exemption by contracting out essential health package services in Malawi. BMJ Glob Health 2019;4 doi:10.1136/bmjgh-2018-001286
- While the UNJP funding mechanism attempted to coordinate efforts at district level to maximise cost effectiveness for example, QI teams using identified challenges and causes of deaths arising from MPDSR audits to develop QI projects, and to guide EmONC and QI mentorships (each of these activities delivered by a different UN partner according to their individual mandates), this was undermined by lack of effective coordination amongst the UN partners resulting protracted conversations about the direction of the programme, which in turn resulted in lower VfM.
Equity:
- CHAM SLAs expand access to free healthcare especially in hard-to-reach areas and for vulnerable population groups including women and children. Most SLA contracts prioritise MNH/MNCH packages. DPs were able to support an increased number of facilities, enabling more beneficiaries to be reached.
- Similarly, FHS continued to provide services in areas where access is difficult. The Programme ensured that all clients regardless of age, sex and background were able to access services of their choice and focuses in particular on outreach to youth and people with disabilities.
- DFF which allows more fiscal autonomy to the primary level care should enable facilities to access funds for local priorities. The funds are administered by a Health Centre management Committee which should include community representation from youth, elderly, women, and those with disabilities.
- The UNJP continued to focus primarily on the community and facility levels to reach those who most need access to quality and free primary health care. In addition to this, the programme has specific interventions for reaching those in the hardest-to-reach areas (such as the EmONC Network which looks at population spread and the corresponding access to facilities).

E: RISK

Overall programme risk rating is Major resulting mainly from budget uncertainties, rising cost of living and the overall macroeconomic environment in Malawi. Specific risk categories summarised below:
- Strategy and Context risk is rated as major in line with FCDO Malawi risk rating due to the country’s political economic instability. Continued weak systems, weak political will, and other contextual challenges pose ongoing risks. The worsening economic context including continuous foreign exchange fluctuations, exchange control regulations and the upcoming general elections in 2025, which continue to erode the ability of GoM to give sufficient fiscal space or priority to the health sector. The programme team continues to engage MoH and like-minded development partners on programme specific impact and use office-wide portfolio mitigations.
- Policy & Programme delivery risk is major and in line with FCDO Malawi risk rating. The capacity of the UNJP to deliver programme outcomes was reviewed in the year and a decision made for alternative funding mechanisms. Programme team has been engaging UN agencies for programming options for 2025 and beyond. There are also concerns around the transition of SRHR service delivery from AGA to the HSJF. The new DFF motion with disbursements to many health facilities, and associated fiduciary risk, is likely to stretch the capacity of the HSJF FA. The MoH request to use HSJF account for forex swap to support essential commodities could impact of the programme if effected. The programme team continue to engage the ministry of health on the forex swap and HSJF Secretariat to assess the impact on FPOA’s effectiveness as well as the transition of FHS SRHR implementation.
- Public service delivery & operations risk is moderate in line with FCDO Malawi risk rating. Technology changes such as OSPREY, and HERA as well as changes in AMP have impacted on programme implementation. There is ongoing support to address challenges related to these platforms.
- People risk is moderate and in line with the FCDO risk rating. There are concerns over capacity of implementing partners, and the programme team are working through new arrangements for UNJP and keeping under review the capacity of the FPOA in the HSJF. The HSJF DFF motion includes some TA support at district level provided by CHAI to strengthen DFF work with FPOA. Staffing challenges in CHAM facilities affect implementation. We continue to engage with MoH and CHAM to address challenges.
- Safeguarding risk is at moderate and in line with FCDO Malawi risk rating and risk appetite. Key safeguarding risks in the health sector include limited presence and awareness of reporting mechanisms in health facilities; weak disability inclusion approaches by Implementing Partners and the intrusive nature of SRHR services. The government has enhanced awareness of safeguarding through the role of ombudsperson in health facilities. However, there is a varied understanding and application of safeguarding initiatives by health facilities due to different capacity levels of the Ombudspersons. Government facilities seem to lag behind not-for-profit facilities. There is opportunity through the HDG to engage with government more on this to ensure implementation of this in their own as well as CHAM facilities. There are efforts through FHS SRHR outreach activities to deliberately reach PWD. FHS continues to conduct client exit interviews, use anonymous reporting mechanism through Deloitte and mystery client mechanism to report on safeguarding issues. FCDO conducted safeguarding sessions for all the partners in November 2024 to raise fraud awareness. The programme will continue to monitor effectiveness of these channels.
- Financial & Fiduciary risk is rated as cautious in line with FCDO Malawi risk appetite. The programme has robust fiduciary controls in place and ensures no funds channelled through government systems- The HSJF has a standalone account for its activities and have oversight roles including procurement Oversight, monitoring and verification of activities and invoicing for HSJF activities and financial audits. Government introduced a new Exchange Control Act in late 2024 which has the potential for negative implications on the viability of the HSJF mechanism which was set up to operate outside government. The programme will be closely monitoring its application and the risks associated with it. The programme team and partners conducted asset reviews and spot checks and no major issues were identified. Partners also participated in the FCDO facilitated away day where fraud awareness was raised.
- Reputational risk is rated moderate and in line with FCDO Malawi risk rating. Proximity to working with Malawi government systems increases reputational risks. In addition, uncertainties over programme budgets increase this risk. Following the new UK government in place in July 2024, we are awaiting the outcome of the one year and three-year Spending Reviews to confirm programme budgets to the end of the programme. The team continues to engage implementing partners and other development partners on budgets.

Update on Partnership Principles
The UW programme is built upon the Partnership Principles, so it is desirable to use these to assess the effectiveness of programme delivery. MoH National Health Accounts continue to single out the HSJF – in the absence of options for budget support – as the best model of harmonised donor support to strengthen national systems and offer closest alignment to shared priorities and strategic goals in HSSP-III. GoM Health Sector financial audits continue to delay with a backlog since 2016. The introduction of an HSJF discretionary budget allows MoH to draw down on some flexible funds, against results-based conditions to improve HSJF governance including progress towards completion of sector audits. UW components on improved cost-effectiveness of prioritisation and budget management contribute directly to strengthened financial management through training sessions offered across the MoH by the HSJF Financial Agent. Improved facility and district performance management and accountability deliver progress towards stronger delivery and accountability to beneficiaries and communities. Through UNJP, the programme is working with district level structures to improve district coordination and planning, and facility performance.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise performance of partners and FCDO, on commercial and financial issues.
The programme Business Case budget was reduced from £130m to £119m following the approval of the BC amendment in July 2023 which allowed for extension to March 2028. Overall financial disbursements to date amount to £52,368,233.85 representing 44% of the approved budget. The 2024/25 disbursement of £15,237,814 is 300% higher than the 2023/24 total disbursements representing 85% of the £18m allocated annual budget and 79% of the initial BC budget of £19,250,000 for the year.
Partnerships: FCDO budget increased in the reporting year making it easier to manage the partnership with the MoH. There is still room for improved coordination among the DPs as both RNE and KfW are renewing their agreement arrangements with MoH in the reporting year. Discussions by the other DPs and the MoH on their new commitments has resulted in a level of uncertainty around existing as well as new funding areas such as DFF. Due to forex challenges, the HSJF DPs are experiencing increased demands for support to commodity procurement, as well as initiatives to increase government access to Forex. Some of these are at odds with the way that the HSJF has been set up outside government systems. Discussions to mitigate the associated risks are underway. FCDOs annual contribution has increased through both the HSJF and UNJP this year and the programme has expanded to incorporate SRHR activities within the HSJF portfolio The approval process for the HSJF budget and associated motions was delayed, partly due to protracted budget approvals by DPs compounded by capacity issues within the MoH. Discussions on how to improve the budgeting process have been conducted, culminating in the development of a draft operational manual to guide all HSJF processes going forward.
[note] Motion: a proposal submitted by MoH to DPs seeking approval to spend resources on a particular activity
The UNJP is funded through the UN Multi Partner Trust Fund (MPTF) through a standard agreement arrangement implemented by UNICEF, UNFPA and WHO. Continued uncertainty and funding changes to the UNJP made it difficult for the partners to plan and implement a long term ‘systems strengthening’ approach to the programme, thereby focusing on shorter term activities. The aim of working through a ‘One UN’ Joint Programme is to provide a strong combination of technical expertise particularly on Quality of Care, programmatic and management experience, district presence, and high influencing capability to effectively contribute to delivery of programme objectives, as well as leveraging in other UN funding. The risk was that partners continued to work as three separate UN agencies despite UNICEF continuing being an active lead of UNJP and a link between FCDO and the UNJP partners. As the overall custodian of the arrangement, the RCO MPTF Office lead has not been visible in the year. Following a vacancy in the role for most of the reporting period, the RCO's engagement with the UNJP has been minimal resulting in poor quality financial reports and delays with funds disbursement to all partners along the chain. Feedback from districts indicated the long disbursement time as a key risk affecting implementation. The programme continues to engage with the RCO to address these risks. FCDO reviewed the UNJP funding and delivery mechanism to maximise results. From 2025, the UNJP will be replaced with single agency programme delivery. We continue to discuss the way forward with individual agencies regarding activities for 2025.
Risk management: HSJF continues to work with the MoH at the central level. However, funds are not channelled through government financial systems. The HSJF Fiscal Agent and MoH embeds risk management in each HSJF motion at all levels. The HSJF took a proactive approach in risk management in the year to ensure that downstream partners are more aware of risk management including fraud and safeguarding. They conducted a risk management workshop which FCDO also participated. Most key staff in the HSJF are new and reflected limited knowledge of risk management. There is need to work closely with the FPOA and their team on this to ensure they are well versed and can cascade this down to implementing partners. HSJF need to strengthen their risk management processes with downstream partners to ensure that there is continued flow of information and standardisation of risk management across the spectrum. FCDO should engage the HSJF in the year to strengthen their information flow on risk management. Both the programme and its implementing partners have risk registers that guide risk management which are discussed regularly. FHS has been proactive in embedding risk management including developing a robust risk appetite statement. Other partners such as Neotree are fairly new and have just been set up. There is opportunity for cross learning in the programme with implementing partners sharing notes on risk management. Implementing partners use monthly and quarterly meetings to update FCDO on risk management and raise risk notes when risks occur. There have been risks around the embedding of FCDO’s SRHR work into the HSJF. Though the MoU between MoH and FHS has been signed for FHS to join the HSJF by April 2025, there are concerns that the discussions prolonged raising delivery risks in the following year. The Fiscal Agent has continued robust management of the fund itself including support during the 2024/25 budgeting process to ensure alignment with donor requirements, development of a Fiscal Accountability Plan – a tool aimed at strengthening financial management services – and has worked with downstream partners to build capacity, for instance on grant management regulations. An HSJF Operational Manual was developed for use from FY2024/25, setting out clearly all partners’ roles and responsibilities and the processes for motion development and budget forecasting, approval, disbursement, and reporting.
With the ongoing changes to UNJP funding and implementation mechanism, there is further work needed to review delivery chain maps for the individual agencies as they develop their activity concepts for 2025. Further work is also needed to ensure the UN agencies reporting aligns to the results framework. FHS approach to risk management has been robust and would be good to see how this is embedded in the HSJF once they become part of that in 2025. Neotree and UNICEF El Nino have just began their activities with FCDO Malawi. Though a one-off nutrition component, there is opportunity for UNICEF El Nino team to enhance their risk management approach.
Reporting: HSJF reporting has continued to improve, with the sharing of good quality, satisfactory monthly, quarterly, and annual reports. The frequency and management of HSJF Executive Committee and administrative meetings has not worked out well in the reporting year. It could help if documents could be shared in advance to allow DPs to review and prepare for meetings. The roles of the HSJF M&E officer and programme Manager in the HSJF have helped to strengthen the HSJF Results Framework. However, significant issues with capacity to manage the HSJF within the Directorate of Planning and Policy remain. The programme team will continue to engage MoH to strengthen these gaps. UNJP narrative reporting and feedback process has been protracted in the reporting year. Reports were not coming timely with feedback taking long to address hence taking more time to conclude a reporting cycle. There is still room for improving reporting to align to the programme results framework. The concerns over delayed and unsatisfactory financial reporting continued. Financial reporting which comes through the Resident Coordinator's Office has continued to delay. The absence of timely and clear narrative and financial reporting impacts on programme delivery as it makes it unclear how the programme is utilising funds. FCDO continued to engage the UNJP partners, the RC’s office and the global MPTF office to address the challenges and monitor timeliness of the reports. Quarterly meetings were held to discuss programme progress, chaired by FCDO with participation by all three implementing UN partners and the RCO.
Financial reporting: The HSJF Fiscal Agent role is provided by DT Global (formerly called Cardno), through an open tender contract between MoH and DT Global which is funded by the Development Partners who have ‘No Objection rights’. The Fiscal Agent produces monthly, quarterly and annual reports which are reviewed by all partners. Disbursements by FCDO to the HSJF are usually on a 6-monthly cycle. For the reporting year, £8,760,000 was disbursed to the Fund with £4,500,000 in July 2024 and £4,260,000 in December 2024 (just outside the reporting period). The HSJF was audited in the reporting year and reports have just been shared with Development partners. The UNJP receive bi-annual disbursements and so provides biannual financial updates to FCDO. A total of £4,200,000 was disbursed to the UNJP in 2024/25 with £3,150,000 in May 2024 and £1,050,000 in November 2024. As the UNJP funding mechanism ends by March 2025, there will be need for the UNJP partners and FCDO to decide the way forward on the assets procured under the UNJP.
Asset Management and control: The UNJP conducted annual spot checks of their assets in the reporting year. No substantial issues were noted. The FPOA also conducted an asset verification during the reporting period. This highlighted the need for tagging and branding assets. One asset was also found stolen due to break in into one of the offices of the partner. FHS conducted routine asset verifications in the reporting year with no substantial issues identified, however2 laptops were reported missing and were replaced through FHS insurance cover. These were immediately reported to FCDO, and the cases were managed with support from FCDO Internal central fraud team. Following the closure of the Tsogolo Langa programme, FHS transitioned assets into the Umoyo Wathu programme to ensure continued use for the SRHR service delivery. Neotree and El Nino components will need to ensure robust asset management processes and more will be reported in the next annual review. The programme team and partners need to continue conducting asset reviews and spot checks to manage the risk of loss and fraud.

Programme management recommendations:
- Recommendation: The programme team plans to work closely with the HSJF FPOA to strengthen risk management across the HSJF.
- Recommendation: The programme team to work with UN agencies as they transition from UNJP to bilateral agreements to ensure robust risk and asset management
- Recommendation: The programme team to strengthen DP coordination in the HSJF
- Recommendation: Programme team to work at strengthening the partnership with MoH.
- Recommendation: The programme team to work with partners to maintain up to date asset registers.

Summary of partner fund disbursements/utilisation over the reporting period (Dec 2023 to Nov 2024):
	HSJF (MoH)	UNJP (UNICEF, WHO, UNFPA)	FHS	UNICEF- Nutrition	Neotree
2024/25 budget / (AR period)	£8,760,000	£4,200,000	£3,000,000	£1,300,000	£22,720
Disbursed	£8,760,000 (Nov 2024). 100% of planned budget)	£4,200,000 (Nov 2024) 100% of planned budget)	£899,988 (Oct 2024). 30% of planned budget	£1,300,000 (Nov 2024). 100% of planned budget	£77,826 (Oct 2024) 33% of planned budget
% Utilisation	FA projects 86% utilisation by Mar 2025. Overall HSJF utilisation (rollover and new funds) is at 34% while FCDO is at 19% as of Nov 2024.	UNJP projects 100% utilisation by Mar 2025.	Projected 90% by March 2025	Projected 100% by March 2025	Projected 94% by March 2025

Date of last narrative financial report	Nov 2024 HSJF Annual Report / Dec 2024 FHS quarterly report / Nov 2024 UNJP Bi-annual Progress report / Dec 2024 Neotree Quarterly Report.	Date of last audited annual statement	Apr 2023 – Mar 2024 HSJF Audit report / Jan – Dec 2023 Consolidated Annual Financial Report (SDG Acceleration - UNJP) / Jan – Dec 2023 FHS Audit

G: MONITORING, EVIDENCE AND LEARNING (MEL)

The Business Case included a cross-cutting learning and monitoring to be led by an external evaluator, but due to budget constraints, this component was never activated. Instead, the programme developed innovative approaches to fill this gap by working with the HEPU and more recently the Learning Centre, and support to selected evaluations to monitor progress and provide the evidence to shape the programme and whether we are investing in the right interventions. The programme continues to use in-house capacity through Health Advisors and Programme managers to monitor progress and impact.

Monitoring
During the reporting period, an HSJF results framework has been developed to tracks activities, outputs and outcomes and the UNJP team recruited an M&E consultant to develop M&E tools and systems which are now collecting real time data for the programme. UNJP uses field visits/ programme monitoring reports to track progress and to adapt the programme’s delivery in response to challenges identified. Bi-annual and annual reports submitted to FCDO are used to track programme outputs and capture lessons learned. A UNJP asset register had been developed to monitor usage of assets that forms part of key tools and enablers for service delivery, HSJF governance meetings provide a good forum for reviewing progress against each motion and adapting programme delivery, as well understanding programmatic and financial bottlenecks, leading to development of approaches to reduce delays in motion approval and practical suggestions for improving funds absorption. Similarly, UNJP Quarterly Review Meetings have been invaluable in thinking through how to deliver the programme in difficult funding context, building a foundation for future delivery. The FCDO Health team undertakes regular visits to the districts to get feedback on UW implementation by visiting health facilities, talking to beneficiaries, health care providers and DHMTs, this approach helps to triangulate information shared with FCDO through reports and meetings. The fuel situation has impacted on the number of field visits undertaken this year. The team could also consider conducting more unannounced spot checks in future. At the national level the team participates in high level monitoring events such as health sector Joint Annual Review and the recent JEE which provides a bigger picture on the sector performance attributed to the support that comes from partners including FCDO.

Evidence
As discussed in Section B, whilst the global evidence continues to support the UW programme’s overarching approach (for instance around ending preventable deaths, and health systems strengthening approaches), the context within which the programme is operating has changed significantly since original Business Case design. For this reason, the TOC and the assumptions between the levels continue to be regularly reviewed.
Our HSJF funding has been channelled to support specific work on evidence generation which contributes to policy influence and improving service delivery. For instance, HEPU’s DFF Evaluation provided implementation evidence on the oversight and fiscal complexities which are key for sustainability to inform the roll out and encourage other partners to join. There is also work underway to transition the HEPU think tank model into a broader HSSP 3 platform, to align evidence generating effort to meet HSSP3 needs. Ultimately this approach should inform sound formulation and implementation of programmes at all levels of the health sector and help to fast-track progress towards UHC goals for Malawi.
During the reporting period, and given our limited bilateral funds in 2023/24, we made use of the FCDO Southern Africa Research Team’s Evidence Fund to support the adaptation and then piloting of the Neotree digital tool for improving care of neonates for use in primary healthcare facilities – this has provided the evidence to enable us to be confident about integrating Neotree into our bilateral plans for 2024 to 2028. 1

Learning
During the reporting period, UW has supported the establishment of the Quality of Care learning Centre which links the Ministry of Health with academic institutions to establish learning platforms from National to district level. The LC approach is to institutionalise learning, drive evidence generation through research, document evidence and make evidence available to inform quality improvements. Through the Learning Centre UW is supporting the Peoples Voice Survey designed to integrate people’s voices into health system measurement, with a focus on population health needs and expectations as well as people’s perspectives on processes of care and confidence in the system. It should enable assessment of health system performance from the population perspective to inform health system planning.
Given the investments made in evidence generation UW seeks to strengthen implementation, scale-up and inclusion of evidence into programmes. A key effort going forward is aligning the ambitions to Thanzi la Onse (TLO) disease model. TLO is a systems model developed as a tool for resource prioritisation and allocation by MoH and Imperial College London, University of York and University College London. HEPU is taking a lead in supporting MoH to utilise the model which has been instrumental in the design of the health benefit package for the HSSP III. HEPU will continue to work with MoH to use of the model for priority setting and resource allocation in various priority areas of HSSP 3 such as integration of health services.
ANNEXES
Annex 1 – Umoyo Wathu programme impact indicators
Annex 2 – UNJP quality improvement case studies
Annex 3 – Umoyo Wathu VfM tracking matrix

Annex 1: Umoyo Wathu programme impact indicators

Impact Indicator		Baseline (2015-16)	Milestone 3 / (Nov 2022)	Milestone 4 / (Nov 2023)	Milestone 5 (Nov 2024)
1	Maternal Mortality Ratio (MMR) per 100,000 live births	439	Target: 350 / Actual: Not possible to track (no MDHS)	Actual: Not possible to track (no MDHS)	Target: 304 (HSSP3) / Actual: Not possible to track (not included in MDHS Key Indicator Report launched Jan 2025; should be available Aug 2025)
2	Neonatal Mortality Rate (NMR) per 1,000 live births	27	Target: 22 / Actual: Not possible to track (no MDHS)	Actual: Not possible to track (no MDHS)	Target: 19 (HSSP3) / Actual: 24 / (MDHS 2024) / NOT MET
3	Child Mortality Rate (CMR)	64	48	Actual: Not possible to track (no MDHS)	Target: 50 (HSSP3) / Actual: 48 / (MDHS 2024) / MET
4	NEW Fertility rate: / total / adolescent (ages 15-19)	4.2 (MICS, 2020) / 136 (MICS 2020)	Not tracked as part of UW programme (covered by Tsogolo Langa)	Not tracked as part of UW programme (covered by Tsogolo Langa)	Target: 4 (HSSP3). / Actual: 3.7 (MDHS 2024) / MET
					Target: 100 (HSSP3). / Actual: Not possible to track (not included in MDHS Key Indicator Report launched Jan 2025; may be available Aug 2025)

Data from recently released MDHS 2024 on early childhood mortality rates:

Annex 2: Umoyo Wathu programme quality improvement case studies
A selection of Case Studies
1. Every maternal death tells a story: Every maternal death tells a story | UNICEF Malawi
2. Mentorship restores women's smiles: Mentorship restores women’s smiles | UNICEF Malawi
3. Staff audit expose staffing gaps: Staff audit expose staffing gaps | UNICEF Malawi
4. With community involvement everyone wins: ‘With community involvement, everyone wins’ | UNICEF Malawi

Annex 3: Umoyo Wathu VfM tracking matrix
VfM area	VFM Indicators	Reporting against indicator			Data Source
		2022 – 23 Annual Review	2023 – 2024 Annual Review	This Annual Review (Feb 2025)
Cost efficiency (output unit cost)	% of SLA invoices paid within the target timeframe (60 days)	This will be explored for future reports	Significant delays in making payments: at least 50% of invoices paid after > 60 days	Significant delays in making payments: at least 50% of invoices paid after > 60 days	MoH SLA Unit
	Unit cost of delivering a Health Economics and Policy Unit (HEPU) Think Tank	This will be explored for future reports	Mk6,770,000 ($4,000) – to be tracked over time	Mk9,250,000 ($5,200) - substantial increase in prices due to rate of currency adjustment	HEPU
	Number (and unit cost) of health workers trained e.g., in PSEA, QI (disaggregated by gender/location)	This will be explored for future reports	This will be explored for future reports	2,557 (1197 Males, 818 Females) health workers from the six UNJP districts were trained in PSEA (a module included in the training programmes conducted in the period). In addition, 58 (45 Males and 23 Females) were also trained in PSEA as a stand-alone training.	UNJP
Economy	FA and TIC contract fees as a proportion of FCDO's total HSJF costs (and of total HSJF funds). / N.B. no official FCDO guidance on % but programme team are using 80/20 activities/overheads benchmark for VfM	20% of FCDO budget went towards FA and TIC fees [awaiting split by FA/TIC]	18.76 % of 2023/24 FY budget under FCDO went to FPOA/TIC fees. (NB this excludes Apr to Jun 2024 TIC budget; if included, it is 21%). Consider splitting into FA and TIC.	16% of 2024/25 FY budget under FCDO went to FPOA/TIC fees, a reduction due to increased overall FCDO HSJF funds. (NB this excludes Apr to Jun 2024 TIC budget)	FA Analysis
	Unit cost of delivering PHC services in CHAM compared to government facilities	This may be possible to track through the ongoing CHAM VfM study - TBC	This may be possible to track through ongoing CHAM VfM study – TBC for future reports	The VfM study did not look at this – a system to compute PHC unit cost in CHAM or govt is not in place. / Indicator to be reviewed.	HEPU
	Placeholder: a measure of economy from UNJP programme e.g., cost savings against budget	This will be explored for future reports	UNJP report no cost savings due to inflation. However, funds to UNJP are Forex so the devaluation may have cushioned inflation. To be explored further for future reports	UNJP has cost saving resulting from the decrease of lunch allowance from MKW17,500 to MKW 8,000. This cost savings will be used to increase the DFF grant for Ntchisi and Nsanje District Hospitals from the planned MKW 5Million to MKW 7Million. Also, the extra cost will be used to provide grant funds for some health facilities in Nsanje. The actual savings and distribution will be reported in future.	UNJP
Efficiency	% utilisation rate of FCDO funds in the HSJF (compared to the overall utilisation figure)	69%. The FCDO utilisation is slightly above the overall Fund’s utilisation at 61%. It is envisaged that FCDO utilisation is forecasted at 100% by March 2023. This considers the limited but focused motions that FCDO is supporting.	Utilisation of FCDO 2022/23 budget is at 60.37% which is above the overall HSJF fund utilisation at 56.74%. At 30 Nov 2023, FCDO utilisation for 2023/24 is at 44% which is above HSJF overall utilization of 21%	Utilisation of FCDO 2023/24 budget was 64% actual and 82% including pipeline invoices as of 31st March 2024 (above HSJF average of 38% and 59% respectively). However, at 30 Nov 2024, FCDO utilisation was at 19%, below HSJF overall utilisation of 34%	HSJF FPOA
	Efficiency of UNJP fund transfer - tracked time between leaving FCDO bank account and being available in UN partners bank accounts (target: 20 days)	"Two months [however, this was a one off event for one of the tranches, caused by a miscalculation of the exchange rate from GBP to USD] / UNJP will set up a tracker and monitor in order to identify bottlenecks and reduce delays"	18 days from FCDO to UNICEF (May 2023 tranche was disbursed on 31 May from FCDO, received by RCO on 5 June and received by UNICEF on 19 June.	Over 2 months. - 28th May 2024 : Funding request letter sent to FCDO. / 31st May 2024: FCDO transfers money to MPTFO. 10th June 2024: MPTFO Confirms receipt of funds transfer; Agencies request clearance process. 25th - 31st July 2024: Malawi SDG Fund funds allocation approved; Funds Transfer Request submitted to MPFO.9 August 2024: MPTFO funds released to agencies. / There were significant delays in submitting Funds Transfer Request to MPTFO because the national steering committee that approves all SDG fund processes convened in July. .	UNJP RCO
	Ratio of cost per complete service delivered (CHAM facility via SLAs vs Government facility via public funding)	This may be possible to track through the ongoing CHAM VfM study - TBC for future reports	Data not yet available – TBC for future reports	A system to compute unit cost in CHAM/SLA or govt is not in place. Indicator to be reviewed.	MoH/HEPU
	[LF INDICATOR] Proportion of HCMC that have utilised and accounted for 100% of their HCIG	Grants not yet disbursed	100%	100% in 2023/24 (but no grants disbursed yet during 2024/25 due to UNJP approval delays)	UNJP
Effectiveness	[LF INDICATOR in 2023 and 2024 but not in 2025] No. (%) of attendees reporting value of participation in HEPU convened events	A feedback tool has been developed, and this indicator will be reported on for future reports	Feedback tool not yet fully implemented; anecdotal reports that events are valued	90% of attendees have reported value in the think tank through feedback forms that are shared at the sessions	HEPU
	[LF INDICATOR] Proportion of health facilities that have undergone Integrated Supportive Supervision at least once in a quarter during the previous 12 months (UW vs non-UW districts)	100% of health facilities have undergone ISS in UNJP districts in the current reporting period (December 2021 to November 2022), This is an improvement on last year. Data from the non-UNJP districts is currently difficult to obtain due to ongoing DHIS2 data issues	Not to report on in 2023	149 facilities (100%)	UNJP and QMD
	[LF INDICATOR] % of funded activities implemented according to the selected districts' 'District Implementation Plan' (DIP) Action Tracker Summary (UNJP vs non-UNJP districts)	Kasungu and Chikwawa conducted a DIP review but did not make use of the DIP Tracker. UNJP to support roll out of the DUP Action Tracker.	On average, 71% of funded activities were implemented in three districts (see Indicator 2.1 for detail)	77.4% - under the one plan, one budget and one report reform, there is increasing partner coordination at the district level in planning, implementation and monitoring of District Implementation plans.	UNJP, via DIP Tracker
	[LF INDICATOR] Proportion of pregnant women who have 4+ (four or more) antenatal care visits (UNJP vs non-UNJP districts)	"National: 35.7% (UW Districts: 33.1%) / Milestone not achieved; trajectory off course"	National: 29.3% (UNJP districts: 29.4%) Milestone not achieved; trajectory off course. / TOC/LF review underway to consider trajectories and milestones to 2028	National: 37.7% (UNJP districts: 23.6%) / Milestone not achieved, trajectory off course. / We will review this indicator in light of the MDHS data which shows an improvement since 2015.	DHIS2 2022 / MDHS 2024
Equity	Gender equity ratio of people accessing SLAs	This will be explored for future reports	To be explored for future reports, aligned with the new HSJF Results Framework	The tools so far do not disaggregate gender. This has been identified as part of SLA System capability enhancement.	MoH SLA Unit
	Gender equity ratio of people accessing UNJP training	Nearly 1:1 (442 Males:386 Females, 53% to 47%)	1:1, for instance, No. health workers mentored on QI is 1,262 (631 M ; 631 F)	2,015: 1197 (59%) M, 818 (41%) F	UNJP