## Annual Review Template

Title: Climate Adaptation Water and Energy Programme (CAWEP)
Programme Value £ (full life): £17,484,361.16		Review date: 10 February 2026
Programme Code : 300164	AMP start date: 10 November 2019	AMP end date: 30 September 2026

Summary of Programme Performance
Year	2021	2022	2023	2024	2025	2026
Overall Output Score	B	B	A	A	A	A+
Risk Rating	Major	Moderate	Moderate	Moderate	Major	Moderate

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300164
DevTracker Link to results framework:

A. SUMMARY AND OVERVIEW

A.1 Description of programme
The Foreign, Commonwealth & Development Office (FCDO) in Zimbabwe funds CAWEP, implemented by UNDP and UNICEF, to strengthen the resilience of vulnerable communities against climate shocks. The programme focuses on:

1. Climate-resilient water and renewable energy infrastructure to ensure reliable access to water for household and productive use, even during droughts and floods and affordable clean energy to sustain livelihoods.
2. Enhanced Early Warning Systems (EWS)[1] for timely access to weather and climate information, enabling communities to better anticipate and respond to climate risks.
  [1] Systems put in place to analyse and identify potential weather- and climate-related risks and hazards. All early warning systems aim to enable early action to save and protect lives, livelihoods, and assets of people at risk.
3. Technical assistance to government and non-state actors to integrate climate data into infrastructure planning and development.
4. Policy influence through evidence and learning to improve national climate adaptation and resilience strategies.
Reaching out to twenty districts[2], CAWEP was designed to benefit over 700,000 people with solar-powered, multi-use water and energy systems and reliable climate information. The programme has two main components which are described below:
[2] Buhera, Mutare rural, Makoni, Mutasa, Gweru, Zaka, Chiredzi, Gutu, Chikomba, Chipinge, Chimanimani, Nyanga, Binga, Insiza, Lupane, Bubi, Umguza, Nkayi, Chivi, Tsholotsho.

Component 1: Adaptive & Flexible Water and Energy Supply
UNICEF implemented this £2.5 million component between July 2021 and June 2022 to address emerging water and clean energy needs. It provided solar-powered, multi-use water supply systems in nine drought-affected districts to mitigate climate-related risks. This component is now closed.

Component 2: Climate Adaptation – Community Water & Renewable Energy Infrastructure and EWS
This is the main programme component, funded at £14.1 million from August 2022 to September 2026. Implemented by UNDP, this component focuses on climate-proofing[3] community water and energy systems and strengthening EWS in vulnerable districts. This review primarily assesses this component.
[3] Measures taken to prevent infrastructure from being vulnerable to potential long-term climate impacts. Under this project, this involves infrastructure improvements, solar pumping, and water-use efficient, irrigation technologies (drip, sprinkler systems)

A.2 Summary supporting narrative for the overall score in this review
This review rates CAWEP’s performance over the past year at A+, as the programme exceeded expectations on all the four outputs. Notable achievements include: (i) strong performance in delivering the integrated business development strategy, which is one of the most important pillars anchoring the sustainability of CAWEP’s interventions, (ii) contributing and influencing national policies that help to improve climate resilience in Zimbabwe; (iii) maintaining a 100% functionality of water and clean energy infrastructure installed in previous years, and (iv) strong programme influence and support helping to shape national policies on climate, renewable energy and business-led irrigation development in Zimbabwe. Preliminary analysis shows these achievements are also being delivered at good value for money across all the four outputs.

Another notable achievement is the SADC[4] regional recognition of CAWEP’s Hakwata green village project, which comprises of a 200-kilowatt minigrid. The Southern African Centre for Renewable Energy and Energy Efficiency (SACREEE) has identified the Hakwata project as a good example of an integrated, sustainable, and replicable renewable energy solution for rural communities and has requested the project to be showcased at the 2026 SADC Sustainable Energy Week to be held 23-27 February 2026.
[4] Southern African Development Community

A.3 Major lessons and recommendations for the year ahead
The following sections highlight key lessons learnt in the year under review and provide strategic recommendations to be taken forward in the remaining programme implementation period.

A.3.1 Key lessons learnt
Business‑oriented models improve sustainability:
CAWEP’s market‑driven enterprise approach for irrigation schemes offers stronger incentives, better financial discipline, and greater long‑term sustainability than traditional cooperative systems, which tend to limit agility, innovation, and investment. This is being observed across all CAWEP irrigation schemes, although additional support is needed to help them manage challenges that come with local entrepreneurial growth, such as high expectations to meet demand, maintaining quality of products and services and profit sharing.

Resilience is strongest when interventions are both integrated and logically sequenced:
Communities become more resilient when support is delivered as a coordinated and well‑timed package. Starting with basic financial skills and savings groups helps households prepare for bigger investments like irrigation and solar energy, leading to stronger ownership and lasting results.

Reinvestment shows real capacity‑building:
A clear sign of strong capacity‑building is when communities reinvest profits into strengthening their enterprise instead of prioritizing short‑term consumption. At Wanezi (Insiza) and Gororo (Chivi), irrigation groups demonstrated this by reinvesting earnings into equipment and assets that boosted production. In over a year of production, profits are being reinvested back into business.

A.3.2 Key Recommendations
Below are high level strategic recommendations. Other output related recommendations are provided in Section C.
- Finalise CAWEP’s sustainability exit strategy that includes critical issues such as transition to local ownership, resource mobilisation for continued management, roles and responsibilities of stakeholders, and managing and sustaining the revolving fund. (By 31 March 2026)
- Complete the programme endline survey by June 2026, to enable evidence based high level policy learning and influencing, including at the planned close out learning event before the programme closes in September 2026.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

B.1 Theory of Change Description
CAWEP aims to strengthen the resilience of Zimbabwean communities and public institutions to climate-related shocks such as droughts and floods. The programme’s theory of change assumes that if poor and vulnerable households gain sustainable access to climate-resilient, multi-use water and renewable energy infrastructure, and benefit from effective Early Warning Systems (EWS) through UK funding and strong partnerships, they will become more adaptive to the impacts of climate change. This increased adaptive capacity will, in turn, reduce vulnerability and enhance long-term resilience.

CAWEP continues to operate under this original logic. Findings from the 2025 Outcome Monitoring Survey (OMS) confirm that the programme is still aligned with its initial Theory of Change and delivering as designed. Consequently, there have been no changes to the outcome or impact indicators over the past year. Fig 1 below illustrates the programme’s ToC.
Fig 1: CAWEP Theory of Change (ToC)

B.1.2 Stakeholder and beneficiary engagement
CAWEP’s implementation approach this year has demonstrated a highly effective and well‑coordinated stakeholder engagement model operating at multiple levels of government and within communities. The Steering Committee (SC), which met four times during the year, provided a stable platform for senior government engagement on policy direction, strategic oversight, and cross‑sector alignment. This consistent high‑level interface ensured that implementation remained grounded in national priorities and benefitted from unified government leadership. At the sub‑national level, UNDP’s technical team worked closely with district technical departments, community structures, and contractors, fostering a collaborative, hands‑on environment for delivering water and energy infrastructure. This partnership approach accelerated implementation and ensured that technical solutions responded directly to community needs. Community engagement has been one of the programme’s strongest pillars. Throughout the year, CAWEP facilitated local planning meetings for resource mobilisation, business management, and operations and maintenance. These engagements empowered communities to take leadership roles in maintaining water works, organising labour contributions, and managing enterprise development. During the annual review, the programme’s effectiveness in beneficiary engagement was clearly visible. Communities exhibited maturity, strong confidence, high levels of ownership, and active participation, particularly through community‑based management structures such as Irrigation Management Committees and Energy Management Committees. Taken together, these achievements show that CAWEP’s model of multi‑level stakeholder coordination and deep community participation is not only functioning effectively but has been instrumental in meeting key milestones and strengthening long‑term sustainability across programme sites.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

B.1.3 Progress towards achieving Outcomes and Impact
This review shows that CAWEP has already achieved a significant part of desired outcomes and on track to deliver the desired impact. The table below show progress towards achieving the intended outcomes and desired impact.

Table 1: Key Outcomes Key Performance indicators
Outcome description	Success Indicators	Target	Achieved
Poor & vulnerable people become more adaptive to effects of climate change through sustainable access to long term climate resilient and multiple use water and renewable energy infrastructure	No. of people supported to better adapt to the effects of climate change through sustainable access to solar powered multiple use water systems, Renewable Energy and Early Warning Systems	700,000	2,861,000
	No. of people with improved access to clean energy as a result of set up/connected to solar micro/minigrids/Solar Home systems/Biogas Digestors/Solarised Social Institutions.	20,000	24,385
	Number of social institutions with improved access to clean energy as a result of set-up solar micro-mini grids, solar modules	82	92
	Percentage of businesses/ enterprises demonstrating sustainable growth as a result of access to solar powered multiple use water systems, Renewable	40%	87%
	Number of green jobs created or improved as a result of developed/rehabilitated multipurpose water and clean energy infrastructure	500	791
	Percentage of targeted land under irrigation	100%	94%

As shown above, CAWEP is delivering very strong results, significantly contributing to climate resilience among vulnerable communities, through a range of adaptation interventions. The programme reached 2,861,000 people with solar-powered water systems, renewable energy technologies and early warning systems, reaching over four times the target of 700,000. This is a significant programme contribution to the UK’s International Climate Finance (ICF) key performance indicator on people supported to adapt to effects of climate change. Access to clean energy also surpassed expectations, with 24,385 people now benefiting against an expectation of 20,000, while 92 social institutions are now solarised compared to the planned 82. This is improving essential services across communities. Additionally, 87% of supported enterprises are demonstrating sustainable growth, more than doubling the 40% target and underscoring CAWEP’s strong contribution to climate‑smart economic development and resilience through a range of adaptation interventions. This progress is reflected in the creation of additional 291 new green jobs across project sites, as well as the ability of the Gororo (Chivi district) and Wanezi (Insiza district) irrigation schemes to secure loan facilities from AFC and Virl Microfinance Institutions to procure farming equipment, demonstrating evidence of expanding asset bases. These schemes have also begun purchasing insurance policies to protect CAWEP funded water supply and energy infrastructure from natural disasters, equipment failure, and theft, ensuring long‑term service continuity. At this stage, 94% of CAWEP’s targeted area is now under irrigation. Through CAWEP support, 105 hectares are now under irrigation and productive, against a baseline of 0%. This is a remarkable achievement, despite the 112-hectare target not being reached yet.

In addition to these outcomes, that were set at design stage, CAWEP has also realised unintended positive impacts which include: (i) the Hakwata mini‑grid unexpectedly attracted NetOne cellular company to install a permanent mobile base station powered by the solar system. This significantly improved telecommunications and internet access for Hakwata and surrounding areas, supporting education and local entrepreneurship; (ii) the construction of the dam in Wanezi led to the building of a bridge, which now provides year‑round access to schools, clinics and markets, and (iii) private sector buyers like Whitney Paprika gained from the stable contract‑farming partnerships with CAWEP irrigation schemes, securing consistent, lower‑cost chilli supplies. This strengthened the chilli value chain and improved overall profitability.

Given the programme is going in its final year, an endline evaluation is planned to fully assess the programme impact in detail and make recommendations for the future.

B.1.4 Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
Based on (i) results delivered such as over 100% over achievement on all outcome indicators, except one on area under irrigation, (ii) realized positive unintended outcomes mentioned above, (iii) strong evidence that the programme is being delivered at good value for money and (iv) overall positive stakeholder feedback and high programme performance rating, CAWEP should continue for the remaining seven months, focusing on putting in place measures that will help with sustaining achieved outcomes and ensuring the impact continues to be realized beyond the programme. Continuing CAWEP provides a critical opportunity to test and lay the foundations for future climate and nature work that aligns with the UK and Zimbabwe strategic priorities. In the coming months, the programme will advance three priority areas that are central to FCDO’s and Zimbabwe’s emerging climate and nature agenda:

- AI‑enabled Early Warning Systems (EWS): CAWEP will support the design and testing of advanced forecasting and analytics tools that integrate scientific data with Indigenous Knowledge Systems, improving the accuracy and reach of community‑level early warning information.
- Nature‑Based Solutions (NbS) Strategy: The programme will work with the Government of Zimbabwe to develop and operationalize a national NbS framework, identifying practical adaptation pathways and demonstrating how nature‑based interventions can reduce climate risks at scale.
- Piloting net‑metering in irrigation schemes: CAWEP will pilot net‑metering models within existing solar‑powered irrigation schemes to improve energy efficiency, lower tariffs, and enhance the financial sustainability of community‑managed systems.
By continuing the programme, FCDO can build on existing momentum while generating the evidence, models, and partnerships needed to shape the next generation of climate and nature investments in Zimbabwe.

## C. DETAILED OUTPUT SCORING

Output Title	Developed climate resilient multiple use water and energy infrastructure
Output number:		1	Output Score:	A+
Impact weighting (%):		40	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 No. of community multipurpose water & clean energy infrastructure developed/rehabilitated with special technical designs and features that respond to climate risks. Disaggregated by type (i) Solar Piped Water Systems (PWS) (i) mini/micro grids, (iii) small dams (iv) Irrigation systems/networks, Biogas digesters	200	236
1.2 Proportion of functional water and renewable energy infrastructure	90%	97.5%
1.3 Proportion of water and renewable energy infrastructure with a community management structure and business model for maintenance	90%	100%

C.1 Briefly describe the output’s activities and provide supporting narrative for the score.
All three key indicators have significantly exceeded expectations at this stage, earning the programme an A+ output rating in this review. This outstanding performance is driven by efficient resource utilisation, deployment of highly skilled technical teams, proactive stakeholder engagement, and rigorous monitoring systems. These factors enabled the programme to achieve cost savings and identify opportunities for additional multi-use water and clean energy infrastructure beyond the original plan. A good example of this is on prioritising raising the Wanezi Dam spillway, increasing flood control capacity and enhancing the dam’s storage capacity from 1.4 million cubic meter to 1.85 million cubic metres. This increases water availability. This targeted investment delivered a highly cost‑effective outcome, substantially improving water availability and reliable supply for the Wanezi community, while maximising the impact of the resources allocated.

At the time of review, 97% of established infrastructure was fully operational compared to the expected 90%. This was certified by the compliance team comprising of ZINWA[5], DOI[6] Agritex, RDC[7], IMC[8], Water Point Committees. This performance is attributed to robust quality assurance protocols, timely maintenance interventions, and strong community ownership mechanisms. Furthermore, an assessment of infrastructure installed over a year ago confirmed a 100% functionality rate, demonstrating the effectiveness of sustainability measures such as capacity building for local management committees and integration of preventive maintenance schedules. This implies that the programme’s sustainability strategy is working well; however, continued investment in technical backstopping and spare parts supply chains will be critical to maintain this performance.
[5] Zimbabwe National Water Authority
[6] Governrmnt of Zimbabwe’s Department of Irrigation
[7] Rural District Council
[8] Irrigation Management Committee

All community water and energy facilities under CAWEP have functional, well-structured management systems supported by viable business models, which are successfully mobilising financial resources for operations and maintenance. The programme had targeted 90% functionality with business models in place at this stage but achieved 100%. Integrating income-generating components into community management systems has created economic incentives that strengthen community cohesion and ensure long-term infrastructure sustainability.

To expand household and enterprise access to affordable clean energy and stimulate rural economic activity, CAWEP is being innovative and launched a private‑sector led solar mini-grid development pilot project at two sites at Zamuchiye (Chipinge District), and Fombe (Nyanga District). The initiative aims to create a scalable and sustainable framework for private‑sector–driven mini‑grid development, supported by policy and financial de‑risking instruments.

C.1.1 Challenges
There were no major challenges experienced in delivering this output during the year. This was expected as a significant amount of works were completed in the previous year.

C.1.2 Describe any changes to this output during the past year, and any planned changes as a result of this review.
There were no major changes to this output besides increasing the dam spillway height by 1.2 metre and accelerating the private sector led mini grid component as explained above. No changes are recommended as a result of this review.

C.1.3 Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

C.1.3.1 Recommendations from the previous AR
Below is progress in implementing recommendations made in the previous review.

Recommendation	Progress
Recommendation 1: Speed up the completion of the outstanding irrigation schemes in Gororo and Wanezi. The mid-term evaluation identifies this as a potential threat to building resilience.	Completed: Gororo Irrigation scheme compliance testing conducted and passed as satisfactory.
Recommendation 2: Strengthen capacity of ZINWA and community operators to operate the system in Binga.(April 2025, UNDP)	In progress: Refresher Operation & Maintenance training conducted by the contractor. Performance will continue to be assessed in the coming months. Any capacity gaps identified will be addressed before the project ends in September.

C.1.3.2 Lessons learnt
No new key lesson learnt under this output.

C.1.3.3 Recommendations for the year ahead
With only seven months remaining, CAWEP should prioritise actions that maintain functionality. secure the sustainability of high‑performing infrastructure and consolidate the programme’s proven delivery model.

Output Title	Established/resuscitated community governance structures are effective in managing installed infrastructure.
Output number:		2	Output Score:	A+
Impact weighting (%):		30	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 No. of governance structures trained to operate, manage, and maintain installed infrastructure are operational. Disaggregated by community/ districts referred to as Asset Management Committees (AMCs)	10	16
2.2 % of people in community governance structures who are women	70%	88%
2.3 % of representative community governance structures engage effectively with both community and external stakeholders, including maintenance service providers.	85%	100%
2.4 % of the households that pay for water and/or power use/maintenance.	70%	93%
2.5 % of targeted communities with a functional income generation/Business model to finance operation and maintenance	90%	100%
2.1.1 No. of women & youth-led enterprises established as a result of technical and business skills training. Disaggregated by (i)Type of training, (ii) Sex, (iii) Age, iv) Type of business	40	102
2.1.2 % of women-led enterprises accessing credit from financial institutions Disaggregated by (i) sex, (ii) Type of business	50%	79.5%
2.1.3 % of youth-led enterprises accessing credit from financial institutions Disaggregated by (i) sex, (ii) Type of business	30%	19%
2.1.4 No. of loans disbursed from the Revolving Loan Fund (disaggregated by gender)	90	358
2.1.5 Total annual value of loans disbursed to women and youth-led enterprises through the Revolving Loan Fund	$120,000	$174,350
2.1.6 Percentage of Portfolio at Risk (PAR)	5%	5%

C.2 Briefly describe the output’s activities and provide supporting narrative for the score.
Following the previous review where this output received a B rating for moderately not meeting expectations, strong progress has been achieved across all indicators except one, justifying the A+ rating awarded in this review. This is because of strong performances across both standard and high‑weight indicators that are most critical to programme sustainability and community resilience building. Below is a summary of performance in these key areas.

(i) Governance Structures:
Governance capacity has strengthened significantly, with 16 Asset Management Committees fully operational, well above the milestone of 10. Women’s representation in these structures has reached 88%, exceeding the expected 70% and reinforcing gender inclusivity. Governance structures also achieved full, 100% engagement with communities and external stakeholders, including the private sector, reflecting a clear increase in confidence to engage beyond the anticipated 85%.

(ii) Cost Recovery and Maintenance:
Cost recovery and maintenance systems are performing strongly. A total of 93% of households are paying for water and/or power use and maintenance, surpassing the target of 70% and ensuring sustainability. Both water maintenance and power maintenance achieved complete compliance, showing strong community ownership of installed infrastructure.

(iii) Income Generation and Business Models:
All targeted communities now have functional income‑generating or business models in place, achieving 100% coverage against an expectation of 90%. This secures long-term financing for the operation and maintenance of infrastructure assets. The performance of the community village savings and lending schemes continues to demonstrate strong growth and resilience. Since the programme’s inception, cumulative savings have reached US$ 444,704 (£326,554) and ZAR 2,031,975[9] (£92,929) reflecting a steadily expanding culture of financial discipline and collective investment.
[9] The Hakwata community in Chipinge use the South African Rands (ZAR), hence savings in ZAR

(iv) Women & Youth Enterprise Development:
Enterprise development has exceeded projections, with 102 women and youth enterprises established compared to the milestone of 40. Financial inclusion indicators are strong, as 79.5% of women-led enterprises accessed credit from financial institutions, surpassing the expected 50%. The Revolving Loan Fund also performed very well, disbursing 358 loans in total compared to the target of 90, with a combined value of US$174,350 against an annual projection of US$120,000. The Portfolio at Risk remains stable at 5%, exactly as envisaged at design stage, indicating sound financial management and prudent lending practices.

Despite these extensive achievements, youth access to credit remains at 19%, below the intended 30%. Tailored financial products and targeted capacity-building efforts are being rolled out to address these constraints.

C.2.1 Challenges
The main challenge the review identified is the low access to credit facilities by youth led enterprises.

C.2.2 Describe any changes to this output during the past year, and any planned changes as a result of this review.
No significant changes were made to this output in the year.

C.2.3 Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

C.2.3.1 Recommendations from the previous AR
Below is a table that shows progress towards implementing recommendations from the previous review on this output.

Recommendation	Progress
Recommendation 1: Finalise the procurement of the revolving fund manager and the fund management modalities (March 2025, UNDP)	Completed – VIRL micro finance was contracted in April 2025. The revolving fund facility is now fully operational and performing well.
Recommendation 2: Test and strengthen the capacity of community-based management structures and youth enterprises on financial management, leadership and conflict resolution as the programme gets into the final year. (Quarterly until August 2025, UNDP)	In progress- Capacity assessment continued in the year. Close monitoring reveals internal conflicts, cultural issues and interference of traditional leaders as main operational issues the management structures encounter on a regular basis. Continuous backstopping and capacity building is being provided by the programme.
Recommendation 3: Fully implement market linkage trainings, ensuring communities are better equipped to engage, analyse, and respond to the market to get the best out of their produce. (June 2025, UNDP)	In progress- CAWEP is empowering beneficiaries with business management skills across all districts, specifically targeting those trained in vocational skills, irrigation scheme committees, and village savings and lending groups. The focus is on developing business plans, managing cash flow, developing budgets, and developing marketing strategies. The programme is also facilitating partnerships between farmers and potential buyers such as Montgomery Food Processors, who are also exposing farmers to other farmers from more established and successful schemes.

C.2.3.2 Lessons learnt
A key lesson is that the underperformance in youth access to credit shows that inclusion cannot be assumed, it must be intentionally designed with tailored financial products and dedicated capacity-building.

C.2.3.3 Recommendations for the year ahead
The following recommendations are made under this output:
- As the programme comes to an end, put a plan in place with carefully thought options for managing the Revolving loan facility beyond the programme implementation period. (June 2026)
- Explore support mechanisms that improve credit access for youth led enterprises. (April 2026)

Output Title	Enhanced Early Warning Systems (EWS), helping vulnerable communities to better anticipate, plan and respond to negative impacts of climate change and extreme weather events
Output number:		3	Output Score:	A+
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 No. of districts/communities that receive EWS strengthening support from CAWEP.	17	17
3.2 No. of people that regularly (monthly) receive and understand weather & climate information	544,130	2,453,736

C.3 Briefly describe the output’s activities and provide supporting narrative for the score.
This output was largely achieved between 2024-2025 and focus this year was on ensuring the results achieved were sustained and contributing to the intended outcome of improved climate adaptation capacity as a result of improved access to reliable weather and climate information. This review shows all the sixteen districts with Automated Weather Stations (AWS) and strengthened Early Warning System (EWS) through CAWEP are still functional while the number of people that regularly receive and understand weather & climate information has significantly increased. This is due to the programme’s extensive engagement and use of local radio stations. These radio stations had an extensive reach of over 2.5 million people.

During the year under review, Zimbabwe experienced persistent rainfall and widespread flooding. CAWEP support proved critical in strengthening national early warning systems. Key institutions such as the Meteorological Services Department (MSD), the Zimbabwe National Water Authority (ZINWA) and the Agriculture and Rural Development Advisory Services (ARDAS) were able to fully access, interpret and operationalise data from automated weather stations, hydrological gauges and other early warning platforms. For example, on 30 December 2025, the MSD generated timely, high‑resolution forecasts and advisories based on enhanced EWS data. ARDAS used this information to guide farmers on crop and livestock management, adjust planting calendars and support local disaster‑preparedness measures. ZINWA integrated seasonal forecasts and real‑time hydrological data into catchment‑level decision‑making, enabling the agency to issue accurate river‑level updates and flood alerts. These alerts triggered rapid community and district responses, reducing potential loss of life, crops and infrastructure.

Overall, the strengthened early warning systems made possible through CAWEP directly improved forecast accuracy, advisory quality and emergency response coordination, demonstrating clear, measurable impact during a high‑risk rainfall season. In view of this, the review rates the output performance at A+, achieving above expectations.

C.3.1 Challenges
No major challenges were identified in delivering this output.

C.3.2 Describe any changes to this output during the past year, and any planned changes as a result of this review
There were no changes in delivering or manging this output in this year.

C.3.3 Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

C.3.3.1 Recommendations from the Previous Annual Review
The table below shows progress on implementing the recommendation made on this output in the last Annual Review.

Recommendation	Progress
Recommendation 1: Increased use of radio platforms and in vernacular languages to reach out to more people.	In progress: More national, regional and community radio stations continued to be engaged to increase coverage on climate and weather information. This has helped the programme to exceed its target on helping people to better adapt to climate shocks. Latest community radio stations to be engaged are Twasumbuka in Binga and Zvomuganga in Manicaland.

C.3.3.2 Recommendations for the year ahead
This review makes the following recommendations:

Ahead of the endline evaluation, strengthen community feedback loops that facilitate regular collection of feedback on the usefulness, accuracy and timing of advisories. This will help ensuring the information remains relevant and locally grounded and provides a mechanism for continuous improvement of forecast products.

Pilot the AI‑enabled Early Warning Systems (EWS) that enable the designing of advanced forecasting and analytic tools that integrate scientific data with Indigenous Knowledge Systems, improving the accuracy and reach of community‑level early warning information.

Output Title	Improved National Climate adaptation policies/Strategies/learning material supported/developed
Output number:		4	Output Score:	A
Impact weighting (%):		10	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 No. of policies or strategies developed/supported as a result of programme influence. Disaggregated by Type e.g., specific policy, strategy, learning paper, operational manuals	5 [10]	9[11]
4.2 No. of policy briefs developed using evidence generated by the programme to influence upscaling or changes to different approached to climate adaptation/resilience	3	4[12]
[10] National Adaptation Plan (NAP), Piped Water Scheme Protocol, Energy Efficiency Policy, water policy, National Clean Cooking Strategy/Framework)
[11] NAP- Approved by Government and launched NEEP- Approved by Cabinet NCCS- Approved by Ministry of Energy National Insurance Strategy for Rural Water Supply Infrastructure in Zimbabwe- Drafted Climate Change Management Bill- Supported stakeholder consultations. Learning Papers-4
[12] NEEP, National Clean Cooking Strategy, Drafts: 1-Promoting the implementation of climate compatible development in Zimbabwe, 2-Climate proofing climate change adaptation projects in Zimbabwe

C.4 Briefly describe the output’s activities and provide supporting narrative for the score.
During the review period, performance exceeded expectations across all policy‑influence indicators, delivering nine major policy products against planned five at this stage. With CAWEP support, an additional policy brief was developed in the year, bringing the total to four against three expected. In view of this performance, the review rates the output performance at A+, moderately exceeding expectations. The programme continues to achieve substantial policy influencing. Two policy briefs on (i) Promoting the implementation of climate compatible development in Zimbabwe and (ii) Climate proofing projects in Zimbabwe were drafted. Although yet to be finalised, these products keep CAWEP on track to deliver the intended objective of achieving evidence-based policy influencing. The government recognises CAWEP technical and financial support in shaping the national policy framework.

In addition to government approval and launch of the National Adaptation Plan (NAP) and National Energy Efficiency Policy (NEEP) last year, CAWEP managed to secure endorsement of the National Clean Cooking Strategy. CAWEP strong technical support continues to be recognised in the year under review, following visible technical and financial contributions to the drafting of the Climate Change Management Bill and the development of high-quality learning papers on (i) A systematic review of benefits of adaptation projects (ii) A review of the community resilience and (iii) Mitigation co-benefits analysis of adaptation projects. These are now under review and will be completed in the coming year. The CAWEP supported National Clean Cooking Strategy, and the Hakwata Green Village Model provided key inputs into Zimbabwe’s National Energy Compact[13] launched during the year. All this is helping to strengthen evidence‑based decision‑making and influencing climate‑resilience policy reforms at national and local level. The scale, quality, and strategic importance of these achievements reflect exceptional technical leadership, high‑level government engagement, and consistent over‑performance relative to programme targets.
[13] A strategic framework, aligned with SDG7, committing to universal, reliable, affordable, and sustainable energy access by 2030, heavily relying on private sector investment, renewable energy (solar/wind), and infrastructure upgrades to boost generation, address shortfalls, and promote clean cooking solutions, requiring significant funding for implementation.

C.4.1 Describe any changes to this output during the past year, and any planned changes as a result of this review.
There were no changes on this output in the year under review.

C.4.1 Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

C.4.2.1 Recommendations from the Previous Annual Review
The table below provide an update on recommendations made in the previous Annual Review on this output.

Recommendation	Progress
Recommendation 1: Make strategic recommendations on how government can use lessons learnt from CAWEP to implement approved policies, ensuring there is no implementation gap when CAWEP ends.(September 2025, UNDP)	In progress- Significant progress has been made on this, including engaging the Government relevant Permanent Secretaries on policy uptake on CAWEP best practices. In addition, three learning papers[14] and two Policy briefs[15] have now been developed. These are based on CAWEP’ s operation research.
Recommendation 2: Finalise the National Insurance Strategy for Rural water supply and start to mobilise communities under CAWEP to consider getting insurance policies.(May 2025, UNDP)	In progress – The final draft is still being reviewed by the Ministry of by the Ministry of Lands, Agriculture, Fisheries, Water and Rural Development., Agriculture, Fisheries, Water and Rural Development.
[14] (i) A systematic review of benefits of adaptation projects- A case study of the CAWEP project in Zimbabwe, (ii) A review of the community resilience for the CAWEP project target communities in Zimbabwe and (iii) co-benefits analysis of adaptation projects- A case study of the CAWEP project in Zimbabwe
[15] (i) Policy Brief 1- Promoting the implementation of climate compatible development in Zimbabwe and (ii) Policy Brief 2- Climate proofing climate change adaptation projects in Zimbabwe

C.4.2.2 Lessons Learnt
Policy influencing or support is more effective if backed by research and evidence which CAWEP has successfully done.
C.4.2.2 Recommendations for the year ahead
- Finalise the learning papers and policy briefs for adoption by Government of Zimbabwe.
- Continue to engage the Ministry of Lands, Agriculture, Fisheries, Water and Rural Development on finalising the National Insurance Strategy for Rural water supply.

## D: VALUE FOR MONEY

D.1 Key cost drivers and performance
The main programme cost drivers for the year under review were construction of climate proofed irrigation infrastructure at Gororo and Wanezi irrigation sites which accounted for 26% of the annual budget. Borehole drilling and community water distribution connections and setting up of the revolving loan facility were other key cost drivers. The programme continued to use the competitive procurement bidding system for all contracts to secure the most advantageous combination of quality and price. This led to reductions in costs on several major purchases leading to savings on different budget lines. The programme has been granted a six month no cost extension to absorb these savings to complete critical close‑out activities and pilot high‑impact, scalable climate adaptation innovations.

D.2 Value for Money (VfM) performance compared to the original VfM proposition in the business case
The programme continues to track VfM metrics under the different categories on Economy, Efficiency, Effectiveness and Equity. The programme has VfM performance indicators which this review assessed against baseline indicators. Overall, the programme is making good progress in achieving positive metrics on VfM. Please see detailed VfM assessment below.

D.2.1 Economy:
UNDP competitive bidding practice ensured the goods and services were bought at the right price and not beyond what the market offered. Savings were made in the process. For example, the contract for supply and installation of diamond mesh fencing for Gororo irrigation in Chivi was budgeted at US$77,240.00 but the issued order was for US$ 59,942 thereby making a saving of 22%. Supply and delivery of Sesame and Sunflower seeds were budgeted for US$24,100.00, but the order value was US$12,257.22, making over 50% in savings. One of the main drivers is use of previous reliable suppliers. This was the case in procuring electrical equipment for Fombe and Zamuchiya mini grids under the private sector led pilot project.

D.2.2 Efficiency:
Efficiency is being achieved through minimizing cost of reaching a beneficiary. Through measures such as UNDP’s Direct Implementation Modality[16] (DIM), community participation and use of government expertise, the programme cost per beneficiary is currently at £14 against the expected £52 from the feasibility study. CAWEP strong alignment with Government of Zimbabwe ministries, Rural District Councils and relevant stakeholders prevents overlapping activities in the same wards or facilities ensuring each partner complements CAWEP investments, increasing efficiency. Partnerships with government extension services (e.g., AGRITEX, Ministry of Women Affairs, Community, Small and Medium Enterprises Development) reduce training and mobilisation costs and increase efficiency.
[16] Modality whereby UNDP takes on the role of Implementing Partner.

D.2.3 Effectiveness:
The main intended outcome of CAWEP is that poor and vulnerable households are better able to adapt to effects of climate change through sustainable access to multiple water and clean energy supply infrastructure to enable productive, household, and institutional use. This review shows that the programme is on course to deliver the expected outputs and outcomes. Key achievements made in the year include completion of the Wanezi dam, Gororo and Wanezi irrigations systems and rolling out of the revolving loans to trained project applicants so they can start income generating projects. These outputs together with relevant training in governance, business management, skills training and cross-cutting issues like gender equity are leading to positive outcome indicators, demonstrating programme effectiveness. However, to sustain all this, emphasis is being placed on strengthening governance and group cohesion systems.

D.2.4 Equity:
The review observes that CAWEP has remained true to its core intention as an equity‑driven programme that prioritises Zimbabwe’s most climate‑vulnerable and poorest districts such as Binga, Chipinge, Chivi, and Insiza, directing resources to communities facing acute water scarcity, recurring severe droughts, and limited coping mechanisms. CAWEP continues to expand sustainable access to water, clean energy, and climate information, while ensuring inclusive representation of women, youth, people with disabilities, and other marginalised groups in Irrigation and Energy Management Committees and other interventions. The programme is strengthening community voice and equitable governance, evidenced by rising confidence among community members, particularly women to lead committees and engage external actors, including private‑sector markets. CAWEP also championed the development of a transparent, pro‑poor national solar mini‑grid tariff model through a multi‑stakeholder negotiation process, ensuring clean energy remains affordable and aligned with the SDG principle of leaving no one behind. This model is now being incorporated into the national mini‑grid policy framework.

D.3 Assessment of whether the programme continues to represent value for money
Based on the above analysis CAWEP still represents good value for money. Overall cost-effectiveness was maintained through continuous programme monitoring, quality assurance assessments and pro-active risk management ensuring that outcomes are achieved at optimal cost.

E: RISK

Overview of risk management
Risks are reviewed monthly during progress meetings between FCDO and UNDP. In‑depth discussions are held quarterly before updating the risk register. UNDP escalates to FCDO any risks whose likelihood or rating is increasing and require timely action. In the year, the programme’s overall residual risk rating has remained moderate. A refresher Due Diligence Assessment of UNDP was carried in December 2025, and the draft report highlights that the partner’s internal control systems, policies and procedures are well placed to monitor, detect and mitigate risks to our programme. The table below provides an update on key risks that were anticipated during the year.

Risk category and appetite	Risk description, update, and mitigation measures.
Safeguarding- cautious	Description- Risk arising from failure to establish and maintain strong safeguards to prevent harm to beneficiaries of CAWEP, staff and the communities where we work or the environment leading to ethical violations and reputational damage. Includes possibility of drowning in the newly constructed Wanezi dam and land degradation at sites where construction has taken place. / Update- FCDO & UNDP have both been closely monitoring environmental and Sexual Exploitation, Abuse and Harassment (SEAH) in the last year. No new cases were reported. / Mitigations- / UNDP ensured contractors, employees and subcontractors adhere to the signed code of conduct on Sexual Exploitation and Abuse (SEA), stepped up awareness activities in communities and schools on identification and reporting of related SEA issues. Contractors implemented action plans from environmental impact assessments to ensure restoration works post construction activities.
Policy and program delivery- receptive	Description-risk arising when supporting policy work through CAWEP due to weakness in influence, engagement and limitation in evidence and this may undermine FCDO impact. / Update-This risk has not materialised. We continue to monitor it closely. / Mitigations- CAWEP is developing learning papers and knowledge products to provide evidence for policy and decision making. Also, CAWEP works in collaboration with the relevant government departments to develop the policies. This increases ownership of the document and commitment to its operationalisation.
Financial and fiduciary- cautious	Description-Risk of poor asset management leading to theft and vandalism and risk of contractors being unable to meet delivery timelines because of cashflow problems- this can lead to sub-standard equipment being supplied leading to weak VFM and delivery failures. / Update -No theft of assets has been reported in past year. / Mitigation- Use of community-based guards, security fencing, insurance and community engagement setting up grievance handling platforms have been mitigating factors against asset the / UNDP and relevant government technical departments conduct compliance monitoring and certification of works to ensure quality workmanship. FCDO also receive monthly progress reports on the same.
Reputational- cautious	Description- Programme activities could potentially involve practices that fail to comply with national and/or international labour or safety & health standards, e.g. child and forced labour during constructions. / Update- there is no evidence of the risk materialising during the year. / Mitigation- Continuous monitoring of project implementation, sensitising community on the prohibition of child labour and employing knowledgeable SHE officers at sites.
Strategy and context- receptive	Description- Political uncertainty in Zimbabwe in the form of civilian demonstrations resulting in violent responses from the law enforcement officers adversely slowing programme implementation. Economic instability causing rising inflation and exchange rate volatility. / Update-the socio-economic context of Zimbabwe has been relatively stable over the year, both FCDO and partners continue to actively monitor the situation. / Mitigation- Work with the politics, governance and economics team to regularly monitor the political and economic situation and engage senior government officials including providing regular updates and undertaking joint field trips.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

F.1 Programme Overview
The total programme value of the business case is £17,484,361.16 funding the delivery of three different components including the pre-implementation feasibility study. This review focused on the Community water & renewable energy infrastructure & Early Warning Systems (EWS) component being implemented directly by UNDP working closely with government departments to ensure ownership and sustainability. The contribution agreement between UNDP and FCDO has a total value of £14,100,000 and all has now been fully disbursed to UNDP.

F.1.1 Financial Management
Programme funds are transferred to UNDP. FCDO receives quarterly financial reports for review and approval. A review of these reports show that UNDP has been spending within the set limits and timeframes, adhering to the proposed forecasts. In the year, £801,366 was disbursed to UNDP as set out in the contribution agreement. The expenditure rate by December 2025 was at 88%. All payment documents were reviewed by FCDO ensuring completeness and adherence to FCDO financial management policies. Whilst doing a full overview of their finances.

UNDP had the CAWEP project audited in June 2025 covering the period January- December 2024 with a total expenditure value of US$ 5,093,000. The report highlighted an unmodified opinion showing that controls were generally established and functioning well. The main components covered by the audit were on governance, development activities and operations.

F1.2 Asset monitoring and control
UNDP purchased some assets for use at the inception of CAWEP. These include laptops, computers, office furniture and two vehicles to facilitate field monitoring. An updated asset register of these items is shared with FCDO every six months. No asset losses were reported.

F1.3 Governance and Accountability
The programme steering committee is the apex body for CAWEP. It is co-chaired by FCDO and the Ministry of Environment, Climate and Wildlife. It meets every quarter to deliberate on strategic and policy issues affecting the programme. In the year under review, four steering committee meetings were held. These have been very useful platforms to lobby for high level policy decisions. In the year under review the steering committee was instrumental in roping in high level office bearers for crucial decision making. The steering committee also acted as a watch dog reviewing and querying the progress and activities implemented by the Programme Management Unit (PMU) which is led by UNDP, this was a useful challenge ensuring compliance, value for money and sustainability.

F1.4 Programme Branding
UNDP is fully aware of the FCDO branding requirements. Programme areas visited during the year showed well labelled signage with UK International Development branding at completed sites such as Mlibizi and Hakwata and Gororo. Branding at Wanezi irrigation field is available, but yet to be erected at the dam site. FCDO will follow up with UNDP to ensure appropriate branding is put up after all the works have been completed.

F1.5 FCDO performance
FCDO interacted well with implementing partner UNDP as well as other stakeholders who are important to CAWEP. FCDO held 11 monthly meetings with UNDP to ensure proactive review of progress, challenges and risks together. An open communication window is also available in the form of emails, calls and other ad-hoc checks both from and to the partner. FCDO also actively reviewed the submission from UNDP on exchange rate gains and facilitated a no cost extension to ensure completeness of critical close‑out activities.

G: MONITORING, EVIDENCE AND LEARNING

G.1 Monitoring and Evaluation
Over the past year, CAWEP implemented a structured and proactive monitoring and oversight framework to ensure effective delivery, high-quality outputs, and strong accountability across all components, hence the impressive performance. Regular joint monitoring missions were conducted involving UNDP, Government counterparts, and implementing partners. These missions enabled real-time assessment of progress against targets, early identification of challenges, and the provision of on‑site technical support to strengthen implementation quality. FCDO programme team also had quarterly monitoring visits to Wanezi (Insiza district), Gororo (Chivi district) and Mlibizi (Binga district).

Routine project tracking was complemented by systematic reviews of contractor performance and compliance. This included evaluating adherence to contractual obligations, quality of works delivered, timeliness, environmental and social safeguards compliance, and alignment with technical specifications. Technical monitoring visits helped to provide technical support, particularly on climate‑resilient infrastructure, community‑based adaptation approaches, and safeguards enabling prompt implementation of corrective actions. Examples of this include collective analysis of the flood threat posed by original old Wanezi dam emergency spillway on the newly constructed pump house. This resulted in its closure and relocation to an appropriate site. In Binga, monitoring also enabled an early detection of operational issues requiring coordinated action. Inadequate technical capacity among extension officers at irrigation schemes was identified on chilli and sugar beans harvesting and post harvesting management which could result in losses. A multistakeholder meeting convened by the District Development Coordinator (DDC) resolved the issue by strengthening capacity building and deploying more qualified expertise to the Mlibizi irrigation scheme.

No evaluation was conducted in the year, but the endline evaluation will be conducted in the coming year.

G.2 Evidence and Learning
Throughout the year, CAWEP has maintained a strong learning focus, consolidating evidence that is already strengthening Zimbabwe’s resilience‑building policies. The programme has consolidated insights from implementation into learning papers now under review, each providing clear analysis of how CAWEP approaches are helping communities adapt to climate impacts.

Climate proofing has been central to this learning agenda. Evidence from interventions such as the construction of the climate‑proofed Wanezi Dam, engineered to withstand a 1‑in‑200‑year flood event demonstrates how resilient water infrastructure can reduce community vulnerability. CAWEP has also embedded climate‑risk screening and mitigation measures across all project activities, ensuring that water, energy, and community systems are designed to withstand future climate extremes.

These learning outputs present early, practice‑based results and highlight the conditions needed to scale climate‑proofing approaches nationally. Collectively, they are informing policy dialogue and contributing to stronger, climate‑responsive policies in Zimbabwe.

Date of last narrative financial report	30 Jan 2026	Date of last audited annual statement	25 September 2025