## Logical Framework
ORGANISATION NAME | University of Manchester
PROJECT NAME | African Cities Research Programme
IMPACT | Impact Indicator 1 |  | Baseline | 2021-12-31 | 2022-12-31 | 2023-12-31 | 2024-12-31 | 2025-12-31 | 2026-12-31 | Target (31-Dec-27) | Legacy | Assumptions | Notes:
More prosperous cities and reduced poverty for some groups through research-driven policy and programming with positive impacts on service delivery, economic development, poverty reduction, and the nutrition, health, wellbeing and environments of low-income people living in cities. | Case studies of the uptake of ACRC approaches in policy and programming in ACRC cities (cumulative). | Planned | 0 | 0 | 0 | 0 | 2 | 3 (cumulative) | 4 (cumulative) | 5 (cumulative) | Examples of urban reforms in the ACRC cities that secure urban prosperity and reduce urban poverty while responding to the climate emergency | ACRC positive impacts are not cancelled out by negative impacts over which ACRC has limited control, eg. reduced reputation of FCDO due to withdrawal of funds from other projects, war, climate change, pandemics, adoption by elites of dysfunctional policies in other areas, etc. The potential tension between economic growth and poverty reduction related to ACRC objectives, with the additional demand to address the climate emergency, is resolved i.e. that some routes to economic growth exacerbate inequalities and make poverty reduction more difficult. That poverty reduction efforts recognise the diverse needs of disadvantaged groups and go beyond those groups that are relatively easy to reach. | The studies provide substantive detail on the uptake of ACRC approaches and reflect the result of the sustained engagement and highlight the emerging benefits to low-income people living in cities (please refer to the case study template). They are intended to track the approach beyond immediate project work; for example, it might be take up of the coalition approach, the hybrid informal-formal approach and the integrated systems approach. Additionally, it might also be an extension of the specific project beyond the confines of the project. There are multiple parts of ACRC work that may be taken up. These including: the CoS/PS approach; approaches to addressing specific PCPs; and the work with city coalitions and ToC. ACRC's innovative research may be taken up by national governments, local governments, and other state agencies such as development authorities. The work may also be taken up by FCDO and other development partners. It is to be expected that agencies adopt the approaches and modify them to be more effective, developing their ownership over their policy and programming innovations. This process of amending the approaches will be captured in the case study approach, hence the indicator chosen for impact monitoring. Progress towards these indicators will be captured annually in ACRC's reports to FCDO. Brief updates will be provided to case studies from previous years.
|  | Achieved |  | 0 | 0 |  | Moderately not met. 2 case studies have been provided but one of these does not so far involve uptake of ACRP approaches. | Met; 1 new (Harare - policy and practice shift on informality).
Source
Impact tracking. Annual Reports. Case Studies. Official documents.
| Impact Indicator 2 |  | Baseline | 2021-12-31 | 2022-12-31 | 2023-12-31 | 2024-12-31 | 2025-12-31 | Target (30 Sept 26)
Planned
Achieved
Source
| Impact Indicator 2 |  | Baseline | 2021-12-31 | 2022-12-31 | 2023-12-31 | 2024-12-31 | 2025-12-31 | 2026-12-31 | Target (31-Dec-27) | Legacy |  | Similar to Impact Indicator 1, there are multiple parts of ACRC that may be taken up and captured in the case study approach. This indicator focuses on the uptake of ACRC approaches in other cities within the country where ACRC research has taken place (the Foundation Phase cities), cities in other countries where ACRC research has not taken place, development partners and international organisations using ACRC approaches for multi-city programmes. ACRC to submit 1 example in 2026 with the potential to develop this example further for 2027, in addition to adding 2 new case studies (for a cumulative total of 3 in 2027)
| Case studies of uptake of ACRC approaches beyond research cities (cumulative) - e.g. other cities within the country, cities in another country, international organisations | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 (cumulative) | Examples of ACRC work including specific reforms and approaches that nurture reform that are being taken up by organisations and agencies beyond the ACRC cities.
|  | Achieved |  | 0 | 0
|  |  | Source | [8 empty] | Risk rating:
|  |  | Impact tracking. Annual reports. Case studies. Official documents. | [8 empty] | Moderate
INTERMEDIATE IMPACT | Intermediate impact Indicator 1 |  | Baseline | 2021-12-31 | 2022-12-31 | 2023-12-31 | 2024-12-31 | 2025-12-31 | 2026-12-31 | Target (31-Dec-27) | Legacy | Assumptions | Notes:
Learning contribution from African Cities | Studies (cumulative) of significant learning identified covering 1 or more of the following areas such as: - ACRC's Theory of Change - Local leadership (broadly conceived) - Urban politics - System strengthening - Domains - Cross-cutting themes (municipal finance, climate, gender and migration) Research: - Research practice; the incorporation of action research; and locally led research design - Methodological and epistemological learning (community knowledge) - Processes for uptake | Planned | [6 empty] | 2 | 5 (cumulative) | 7 | Common learnings can be drawn from different action research projects and can collectively apply to specific thematic areas. Academics within the ACRC can work constructively with AR leads and other relevant staff to maximise the learning for project level activities. ACRC is building on established relationships however this process of synthesis is tricky in part because a decentralized process has resulted in different disciplinary backgrounds, interests and focus. Academics can work constructively with others involved in ACRC. These learning outputs are likely to be led by academics. ACRC is aware that project staff often find this process at best extractive and at worst inaccurate. | ACRC will prepare notes on high level learning that is intended for academic publication. This may include theoretical papers as well as policy orientated contributions. The papers themselves may not be complete. The focus of these notes is high-level learning which is of relevance to those interested in urban programming, urban politics and urban development in general. Lessons of relevance to less specialist FCDO staff will be communicated through other means. These learnings provide detailed analysis to enable ACRC to contribute to ongoing academic and policy and programming debates. The learnings will allow for teams to show work that is contextually informed, and drawing from experiences beyond a single project. The ACRC team may select something innovative and paradigm shifting where relevant because of its significance; this might be less advanced because it's intrinsically more difficult. The template for logframe reporting will include - 1 to 2 pages: Who is learning; what are they learning; how are they learning; how is the learning shared; why is this important (for ACRC's impact) Each example will note where these are: a) conceptual impact (changing ways of thinking etc); b) instrumental impact (influencing policy and practice etc); c networks and connectivity impact (e.g., building and strengthening networks etc); and/or d) capacity building impact (building researchers' capacity to strengthen research uptake etc). ACRC will identify the most substantive knowledge for a range of relevant audiences. ACRC will incorporate migration within relevant targets, milestones, and output-level figures so that migration deliverables are explicitly captured without restructuring the logframe around migration. There are no pre-defined milestones/targets per theme, but these are being tracked for learning and interest.
Achieved
|  |  | Source | [8 empty] | Risk rating:
|  |  | Impact tracking. Annual reports. Meeting and interview notes. Academic publications. | [8 empty] | Moderate
Outcome | Outcome Indicator 1 |  | Baseline | 2021-12-31 | 2022-12-31 | 2023-12-31 | 2024-12-31 | 2025-12-31 | 2026-12-31 | Target (31-Dec-27) | Legacy | Assumptions | Notes:
|  | Planned | Consortium knowledge on agencies pressing for reforms (be they national or local governments, FCDO or other bilateral development partners, multi-lateral organizations or civil society agencies) in research cities that have struggled to achieve success. | 0 | 0 | 5 | 10 | 15 | Final target to be agreed with FCDO by Dec 23 |  | Body of open access, high quality research findings helps to catalyse multiple developments of ACRP's research and uptake work. ACRP findings in use in new and existing programmes - and available for future work - in addressing PCPs. |  | Success will be reflected in level of productive engagement, evidence of uptake of ACRP thinking, and an engagement by those with responsibilities for urban projects and programming with our research reports and other documentation. Evidence will include records of meetings, requests for ACRC inputs, etc. We recognise that some government interest may require confidentiality and we will seek to provide documentation in these cases. This outcome focuses on the instances of engagement and usages of ACRC research products and the result of the uptake related to action research/research projects.
Robust new knowledge and evidence on African ‘cities of systems’, political settlements and urban development domains leads to development of, and investment in, more effective economic development and poverty reduction policies and programmes in African cities, by FCDO, its partners and other development agencies including national and local government and civil society. | Number of uses of ACRC's research approach and products in policy and planning in African cities (cumulative) | Planned | Consortium knowledge on agencies pressing for reforms (be they national or local governments, FCDO or other bilateral development partners, multi-lateral organizations or civil society agencies) in research cities that have struggled to achieve success. | 0 | 0 | 5 cumulative | 10 cumulative | 15 cumulative | 20 cumulative | 25 cumulative | Body of open access, high quality research findings helps to catalyse multiple future developments of ACRC's research approaches (and specifically the conceptual framework) and outcomes including uptake work. ACRC findings related to elite commitment, state capability, citizen mobilisation and reform coalitions in use in new and existing programmes - and available for future work - in addressing PCPs. Greater appreciation of the significance of community knowledge to programme outcomes and citizen mobilisation with journal paper publications in 2027 and 2028. Revisiting of conceptual framework through a working paper by Dec 2027. Take up of ACRC's work on decentralised project delivery shared through a journal paper publication in 2028. | For all Outcomes: New external crises (such as war, climate change, etc) do not undermine success Innovative projects can be achieved even if they challenge elites Availability of funds and willingness to fund new approaches on a larger scale Continuing interest in urban programming on the part of national governments, city governments and international agencies. Recognition that ACRC approach with political settlements and city of systems analysis is required. Assume that FCDO is functioning as a bilateral development assistance agency ie. with funds and developing programes for which ACRC findings are relevant. | This outcome focuses on the instances of engagement and usages of ACRC research projects and the result of the uptake related to action research/research projects. Where there is an update to previously reported examples, this will be captured in a separate annex.
|  | Achieved |  | The main form of tracking will be a quarterly uptake reporting questionnaire for city and domain leads to compile, which will provide an initial overview. Follow up interviews with staff, and external stakeholders will be used to deepen and corroborate anecdotal evidence. The Consortium will also track online and digital mentions, a broad set of Google alerts and citation data | Monitoring mechanisms explained last year. The ACRC team were delighted by the interest from the National University of Science and Technology in Namibia. Next year (2023) will be an important year, as city reports will enable the programme team to receive real-time feedback from city uptake meetings and it will be possible to monitor downloads and other indicators from the city reports | The programme has already had influence on policy and programming particularly at the local authority level, but also, in some cases, national governments including from officials with responsibility for policy and planning (Accra, Freetown). The cases for this indicator (see Annex 1 for further details) come from Accra ((1) informal settlement upgrading), Freetown ((1) housing), Harare ((2) informal economic development and housing), Lilongwe ((3) informal settlement upgrading and community inclusion in planning) and Nairobi ((2) housing and economic development). The influence of the ACRC reflects the relevance of the findings and the willingness of leading city-based researchers from academic departments, professional agencies and community organisations to engage with the ACRC. ACRC research has been well received within ACRC cities, and the established quality of the local research teams together with city-based uptake specialists has helped to facilitate access to high level officials and political elites. | 11 cumulative (2 this year): Accra - Accra Metropolitan Assembly (AMA) approach to waste management; Mogadishu - research used by Danwadaag Durable Solutions Consortium on programme design to improve quality of housing for IDPs | Met; 15 cumulative (4 new in 2025). Accra - waste management and composting; Harare - Project Management Committee (PMC); Lilongwe - national informal settlement upgrading strategy; Nairobi - sanitation (Mukuru)
|  |  | Source | [8 empty] | Risk rating
|  |  | Impact tracking. Annual reports. Partner reports. City lead reports. Google scholar and webanalytics. | [8 empty] | Major
| Outcome Indicator 2 |  | Baseline | 2021-12-31 | 2022-12-31 | 2023-12-31 | 2024-12-31 | 2025-12-31 | 2026-12-31 | Target (31-Dec-27) | Legacy | Assumptions: | Notes:
| Cumulative number of Reform Coalitions with enhanced capacity to contribute towards ACRP instigated urban reform | Planned | Awareness of work of reform coalitions across ACRC partners | 0 | 0 | 3 reform Coalitions (cumulative) taking part in capacity and capability strengthening programme | 6 reform coalitions (cumulative) taking part in capacity and capability strengthening activities | 9 reform coalitions (cumulative) with enhanced capacities and capabilities providing significant support for action research and research projects to address PCPs. | 12 reform coalitions (cumulative) in ACRC with enhanced capacities and capabilities providing significant support for research and action research projects to address PCPs. | 13 reform coalitions (cumulative) in ACRC with enhanced capacities and capabilities providing significant support for research and action research projects to address PCPs (to be reviewed in late 2026) | An understanding of how reform coalitions can contribute to catalysing urban reforms and keeping the reform process on track. This understanding will be supported by a book chapter synthesising experiences across the ACRC, and a second chapter exemplifying the work of one reform coalition in an ACRc city. Book to be prepared by the end of 2027. | Existing reform coalitions engage with ACRC. Interested reforms participate in ACRC activities to strengthen reform coalitions. Those involve in reform coalitions participate in research to assess the success of coalition activities. | Reform coalitions are defined as an informal or formal group or alliance of stakeholders that makes a deliberate, concerted effort to address urban challenges and nurture reform. The group/alliance should involve a wide, diverse range of stakeholders with an interest in the relevant urban development challenge.
|  | Achieved |  | The Consortium has undertaken initial research and thinking to refine its understanding of the role and definition of reform coalitions in urban change, which was presented to the Regional Studies Association Area. A journal article is currently being drafted. There were over 30 high level meetings during the Inception Phase with senior stakeholders working on urban reform, particularly amongst international organisations, existing urban networks and research initiatives. Work in cities to identify and build relations with reform coalitions is underway. | The ACRC team's work in cities has a complex engagement with local reform coalitions. The team is working closely with SLURC (Freetown) and UAL (Kampala) to enable their long experience of formal collaboration with diverse stakeholders, including local authorities, to be a part of ACRC. The team have identified coalitions in cities and domains of interest to ensure that the uptake work includes these groups. Progression to the implementation phase will enable the team to advance this outcome. | 3 reform coalitions have taken part in capability development activities supported wholly or partially through the work of the ACRP. (1) In Kampala the Urban Action Lab, a multi-actor knowledge based platform, is bringing together Makerere University academics, community groups and state officials to develop policies and programmes. ACRP has worked with multiple team members to incorporate a politically nuanced analysis into their urban focused contributions. through enhanced skills in political analysis). (2) In Lagos, the Nigerian Federation for the Urban Poor (a reform coalition of community groups active in informal settlements) engaged in ACRP Foundation Phase research and advanced their skills to generate, validate and access evidence. participants have used this evidence to strengthen their capacity to demand state accountability and to identify solutions for improved housing for low-income residents. Community activists had the opportunity demonstrated their new capabilities when they interacted with legislators to discuss how to provide affordable housing for the urban poor at an ACRC dissemination workshop on Community Infrastructure Projects and the Lagos State Development Plan 2052. (3) In Lilongwe, The National Slum Upgrading Programme (NSUP), which supports the delivery of new low-cost housing (greenfield), home improvements (in-situ upgrading), provision of basic services, infrastructure and livelihood opportunities in Lilongwe, has been strengthened by an informal coalition between the Ministry of Lands (and Department of Urban Development), Lilongwe City Council (LCC), Centre for Community Organisation and Development (CCODE) and the Malawi Homeless Peoples Federation (MHPF). Informed by the approaches and knowledge obtained though participation in several ACRC workshops (particularly on the political settlements approach which helped the coalition conduct a more rigorous stakeholder mapping which identified different stakeholder interests and points of friction), the coalition is involved in the piloting of the programme. | 6 cumulative (3 this year) | Met; 9 cumulative (3 new this year). Nairobi - improving tenure security in Mathare; Freetown - addressing kush use in Freetown; Nairobi - reform coalition for refugee integration
Source
Measurement of capacity of reform coalitions. Project documents. Individual city uptake strategies. Annual reports.
| Outcome Indicator 3 |  | Baseline | 2021-12-31 | 2022-12-31 | 2023-12-31 | 2024-12-31 | 2025-12-31 | 2026-12-31 | Target (31-Dec-27) | Legacy | Assumptions: | Notes:
| Cumulative number of cities where there are examples of significant ACRC contributions towards citizen engagement in ACRC efforts to secure urban reform | Planned | Agreed approach to identifying relevant groups of mobilized citizens (in domain studies and PS studies) together with analysis of their interests and measure of their potential strength. | 3 citizen groups relevant to ACRC domains involved in uptake activities in the first set of 7 cities. | 3 citizen groups (six in total) relevant to ACRC domains involved in uptake activities in the second set of 6 cities. | 3 citizen groups taking part in ACRC action research projects to address PCPs | 5 more citizen groups (cumulative since 2023) taking part in ACRC action research projects to address PCPs | 11 citizen groups (cumulative since 2023) taking part in ACRC action research projects to address PCPs | 14 citizen groups (cumulative since 2023) taking part in ACRC action research projects to address PCPs | 15 citizen groups (cumulative since 2023) taking part in ACRC action research projects to address PCPs (to be reviewed in late 2026) | Citizens effectively engaged in urban reform, influenced by understanding of ACRC work. These and other citizen groups better understand the potential of working with academics and professionals to secure such reform. Reflective article on the role of mobilised citizens in urban reform. This understanding will be supported by a book chapter synthesising experiences across the ACRC, and a second chapter exemplifying the work of citizen mobilization in an ACRC action-research project. Book to be prepared by end of 2027. Additional material will contribute to an understanding of the potential significance of community knowledge in urban reform (journal publication prepared in 2027). Documentation of enhanced ways of working between academics and communities will also be set out in a blog and podcast by end of 2027. | Assume it can be demonstrated to mobilized citizens that ACRC activities are relevant to their needs and interests. Assume that activities successfully draw in relevant mobilized citizens to contribute to Foundation Phase research and Implementation Phase action research and uptake. Assume that uptake activities demonstrate the added potential of ACRC approaches to mobilized citizens. | Engaged citizens are groups of organized residents that come together to address their needs and interests in relation to an identifiable urban development challenge. This can be low-income informal residents (SDI and others); and/or low-income informal workers; and/or higher income residents (Harare Concerned Residents etc.) and/or higher income formal workers (eg. Trade unions). The work engages with a range of mobilized citizens in the Implementation Phase including trade associations, street trader groups, residents' associations, ratepayers associations, youth groups, women's groups, community health volunteers, etc.
|  | Achieved |  | Work is underway to identify relevant citizen groups in each of the first set of cities. For example, in Accra, early engagement has included the SDI Ghana Homeless Peoples Federation, as well as links to citizen groups such as the railway squatters’ association, youth in slums association, Ghana informal traders’ association, and informal waste pickers groups. As the city research and uptake work advances, city teams will identify those groups with agendas that are aligned to the African Cities research programme. |  | Three citizen groups have been involved in the preparation of the pilots for PCPs (see Annex 3). In Harare, members of the Zimbabwe Homeless People’s Federation have used their previous expertise in organizing traders and workers in markets to support the planning of Glen View 8 market upgrading. In Mogadishu, informal settlement managers with an established commitment to better managed camps have been involved in plans to enhance tenure security; and community groups in central city areas have also contributed to plans. In Nairobi, two established citizen networks have been involved in planning for a project in Mathare, a large informal neighbourhood. | 8 cumulative (5 this year) | Moderately exceeded; 12 cumulative (4 new this year). Harare - engagement between the market traders and the city; Lagos - women-led water and sanitation committees; Maiduguri - formation of community; Mogadishu - access to justice;
|  |  | Source | [8 empty] | Risk rating:
|  |  | Project documents. Annual reports. Impact tracking. | [8 empty] | Major
| Outcome Indicator 4 |  | Baseline | 2021-12-31 | 2022-12-31 | 2023-12-31 | 2024-12-31 | 2025-12-31 | 2026-12-31 | Target (31-Dec-27) | Legacy | Assumptions: | Notes:
| Progress towards securing elite commitment (including both political and business elites) to ACRC approaches to addressing PCPs and securing reform. | Planned |  | Methodology to identify significant elites for ACRC and metrics of commitment for specific elite groups (eg. national political elites, city political level elites, business elites, profession-related elites) identified and then applied in remaining years of the programme. | To be agreed in 21-22 logframe review. (See Annex 1 of 2022 Annual Report which proposes future metrics) | tbc | 2-page report on the testing of the methodology to measure elite commitment together with information on the results | Improved elite commitment in each city versus 2024 levels (as demonstrated through reporting against the methodology, see notes) | Continued improvement through established measurement process in the dimensions of elite commitment in each action research project (building on previous year, as demonstrated through reporting against the methodology agreed in the Annual Report/Review for 2022) | Continued improvement through established measurement process in the dimensions of elite commitment in each action research project (building on previous year, as demonstrated through reporting against the methodology agreed in the Annual Report/Review for 2022) | Members of relevant elites supportive of ACRC approaches. Evidence of the efficacy of urban reforms for elites. This understanding will be supported by a book chapter synthesising experiences across the ACRC, and a second chapter exemplifying the work of elite commitment “journey” in one action research project in one ACRC city. Book to be prepared by the end of 2027. Testimonials from government, private sector & community actors about the value of co-produced hybrid infrastructure solutions to be acquired by June 2027. | Assume that at least some elites will engage with the research, projects and programmes of ACRC. Assume that this engagement will result in an interest in ACRC and that the programme is able to avoid being co-opted such that urban reform is not achieved. | The definition of elite from the Effective States and Inclusive Development (ESID) political settlements work: ‘Elites are those individuals that occupy high-ranking positions, whether de facto or de jure, in those societal and governmental organisations with sufficient power that, acting singly or with others, might plausibly, by their action or inaction, make a significant difference to the maintenance, evolution or destruction of the political settlement, for example high-level party leaders, high-level administrators, high-ranking military officials, captains of industry, major financiers, powerful labour leaders, popular or well-connected religious leaders, major publishers, high-ranking diplomats from influential foreign countries, etc’ ACRC measures elite commitment through 4 dimensions: (i) financial, (ii) discursive, (iii) practical and (iv) legal. Each of these dimensions are considered in determining the level of elite commitment in each action research project within a city. Continued improvement means that the aggregated level of elite commitment (based on the cumulative action research projects) improves overall. ACRC will demonstrate this by giving scores to each project and aggregating these scores. ACRC recognises that some projects may stay the same in level of elite commitment or move backwards, but continued improvement requires that such a shift is fully compensated by other projects moving forward. ACRC uses an ordinal scale, hence the categories are not strictly additive, and does not assume that projects are equal in significance.
|  | Achieved |  | City uptake leads are all tasked with an initial stakeholder mapping of all relevant stakeholders, particularly in relation to the domains that are being studied in their location. This initial mapping will be combined with the political settlements mapping and analysis work (particularly drawing upon Brinkerhoff’s five indicators of political commitment ) to provide a comprehensive picture towards the end of the foundation phase for each city. | Annex 1 of 2022 Annural Report proposes future metrics | A metric for measuring elite commitment and engagement was developed last and has been trialled this year, with engagement being described according to type (discursive, legal, financial, or practical) and by strength (strong, moderate, or incipient (weak)). In 2023, engagement across the mostly practical in each of the 12 cities and either moderate or weak. Nevertheless, there have been many examples of substantive practical” engagement (see Annex 4 for more details). This has primarily been with political elites with business elites being less substantively involved. | Met. | Met.
|  |  | Source | [8 empty] | Risk rating:
|  |  | Scan of key stakeholders/audiences policy releases | [8 empty] | Moderate
| Outcome Indicator 5 |  | Baseline | 2021-12-31 | 2022-12-31 | 2023-12-31 | 2024-12-31 | 2025-12-31 | 2026-12-31 | Target (31-Dec-27) | Legacy | Assumptions: | Notes:
|  | Planned |  | Identification of capacity and capability metrics for government staff and politicians identified and then applied in remaining years of programme. | To be agreed in 21-22 logframe review | tbc | tbc | tbc | tbc |  | Capacitated local government and national government staff. Capacities politicians. Awareness of new learning approaches suitable for reform. Engagement of relevant training agencies (professional institutions, academic departments) in new approaches to urban reform and new approaches to capacity and capability development. |  | We will engage multiple local government and national government officials from street level bureaucrats upwards. We will identify relevant capacity and capability needs including those that are technical, relational and analytical (politics, etc.). We will pay attention to the different needs required in different contexts due to alternative historical and cultural realities. We will seek to develop cadres of officials able to respond effectively as political opportunities introduce reforms which need to be taken into policy, programming and practice. There may be generic capabilities such as setting up stronger accountability processes for state service provision and for improving the ability of lower level officials to work collaboratively with low income residents.
| Progress towards building the capacities and capabilities of national and local government staff and politicians at all levels relevant to ACRP approaches to addressing PCPs and securing reforms. | Planned |  | Identification of capacity and capability metrics for government staff and politicians identified and then applied in remaining years of programme. | To be agreed in 21-22 logframe review. (See Annex 2 of 2022 Annual Report which proposes future metrics) | tbc | 2-page report on the testing of the methodology to measure capacity and capability strengthening together with information on the results | Improved national and/or local government capacity and capability in each city versus 2024 levels (as demonstrated through reporting against the methodology, see notes) | Continued improvement through established measurement process in the dimensions of national and/or local government capacity and capability in each action research project (building on previous year, as demonstrated through reporting against the methodology agreed in the Annual Report/Review for 2022) | Continued improvement through established measurement process in the dimensions of national and/or local government capacity and capability in each action research project (building on previous year, as demonstrated through reporting against the methodology agreed in the Annual Report/Review for 2022) | Capacitated local government and national government staff. Awareness of new learning approaches suitable for reform. Engagement of relevant training agencies (professional institutions, academic departments) in new approaches to urban reform and new approaches to capacity and capability development. This understanding will be supported by a book chapter synthesising experiences across the ACRC, and a second chapter exemplifying the work of one action research project in building state capabilities. Book to be prepared by the end of 2027. | Engagement at all levels of government as required for both city studies and action research and research activities to address PCPs. For city studies ACRC assumes that there will be an interest in using ACRC's methdology within local and national government agencies. For activities to addressing PCPs ACRC assume that there will be an interest from multiple officials and politicians in ACRC's innovative approaches. ACRC assumes there will be some interest from academic departments and professional institutions in replicating training activities. | Enhanced capability and capacity are distinct from elite commitment. This refers to the ability of government (at different levels) to respond and carry out urban reform when political commitment is in place. For example, the government may be committed to water reforms, and convinced that there is a need to coproduce water delivery with local informal providers. That requires officials at all levels of the water utility have the competence to design and operate hybrid systems, it requires internal coordination to identify failings in any one part of the system being reluctant to implement a coproduced process, and it requires the relational capacity in street level bureaucrats to have constructive relations with informal providers. ACRC measures enhanced state capacity through 3 dimensions: (i) state resources and competency, (ii) internal coordination and (iii) relational capacity. Each of these dimensions are considered in determining the level of elite commitment in each action research project within a city. Continued improvement means that the aggregated level of enhanced state capacity (based on the cumulative action research projects) improves overall. ACRC will demonsrate this by giving scores to each project and aggregating these scores. ACRC recognises that some projects may stay the same in level of elite commitment or move backwards, but continued improvement requires that such a shift is fully compensated by other projects moving forward. ACRC uses an ordinal scale, hence the categories are not stricktly additive, and does not assume that projects are equal in significance.
|  | Achieved |  | Work towards this Outcome will build on the city studies, which are underway. | Annex 2 of 2022 Annural Report proposes future metrics | 3 | Met. | Met.
|  |  | Source | [8 empty] | Risk rating:
|  |  | Project documents | [8 empty] | Moderate
INPUTS (£) | (£) |  | Govt (£) | Other (£) | Total (£) | SHARE (%)
INPUTS (HR) | (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | 2021-12-31 | 2022-12-31 | 2023-12-31 | 2024-12-31 | 2025-12-31 | 2026-12-31 | Target (31-Dec-27) | Legacy | Assumption | Notes:
Robust new knowledge and evidence on African ‘cities of systems’, domains and political settlements documented with lessons effectively communicated. | Produce and refine African Cities conceptual framework and methodology, sharing this knowledge with relevant audiences through appropriately-designed diverse knowledge products | Planned | zero | An over-arching analytical framework developed and published. A Methodology for undertaking research using the analytical framework developed. | Analysis undertaken of robustness of framework and methodology in first set of 7 city studies, revisions made as necessary. | Analysis undertaken of robustness of framework and methodology in full set of city studies and guidance note provided on future research | Case study on use of framework in 2 cities | Evidence provided that the CF is locally owned and locally operationalised in the Implementation Cities | Additional case study on evidence of uptake of ACRC framework ideas in a city programme or policy | 1 academic paper on the uptake of the conceptual framework submitted and one working paper orientated to government and non-governmental audience (to reach a wide professional audience, information about the working paper will be disseminated through urban newsletters and blogs) | ACRC methodology and framework incorporated into relevant teaching programmes at UG and PG level leading to capacitated professionals. PhD projects employing ACRC concepts and findings. Reforms are effective as pioneer reforms, and trigger further project invetsments in new areas. Elaboration of the participation of academics included in the chapter on reform coalitions. | Partner institutions remain stable and key partner individuals do not move. Recession and cuts do not affect sources of research funding including FCDO research commitments. Academic journals and universities continue to have an interest in ACRC and urban reform. Foreign currency fluctuations do not reduce value of research resources. | This indicator is concerned with the development and utilisation of ACRC's conceptual framework. In the Foundation Phase, this indicator was contributed to by the city synthesis reports; in the Implementation Phase, the case studies are expected to come through from the five selected cities that are implementing action research projects.
|  | Achieved |  | Met Overarching analytical framework published on ACRP website, September 2021. Methodology for using the framework agreed December 2022 | Not met: The first 7 city studies are not yet completed due to delays in budget certainty and the slowdown through the pandemic. They will all be completing in the next 3 months and it is anticipated that this analysis will be completed by the second quarter of 2023. | Met; the ACRC's City Synthesis Reports all attempted to show how national and city-level politics, urban systems, and particular configurations of actors, agencies, ideas and practices have shaped development in various domains, while its Cross-City Domain Reports sought to aggregate and analyse the work of the domain teams across cities. | Met. See Annex 3 of Annual Review for full case studies on the use of the conceptual framework in Accra and Mogadishu. | Met.
|  | Source/Data collection model | [9 empty] | Risk Rating:
|  | Quarterly reports to FCDO of online reach. Quarterly reports to R4D on outputs. ACRC Annual Reports. Case studies. | [9 empty] | Minor
| Output Indicator 1.2 |  | Baseline | 2021-12-31 | 2022-12-31 | 2023-12-31 | 2024-12-31 | 2025-12-31 | 2026-12-31 | Target (31-Dec-27) | Legacy | Assumption | Notes:
| Production and dissemination of high quality, peer-reviewed and relevant research products by ACRC. | Planned | zero | 13 city scoping studies published. Review on urban political analysis published. ACRC Framework paper externally reviewed and published. | Working papers on 7 city studies (set 1) and associated domain studies drafted and available on ACRC website. | Working papers on all city studies and cross-city domain studies drafted and available on ACRC website. | Publish all city studies, all domain reports, three cross-cutting reports plus summaries of each report as briefs | 10 working papers, 15 journal papers, 1 book and 10 book chapters accepted for publication and placed in the public domain. Metrics on citations, reviews, downloads provided where available. | 45 working papers and research reports (cumulative), 30 peer reviewed publications (cumulative) and annotated bibliography/literature published on migration in African cities. Citation and influence of work evident in the international academic and policy literature. | 50 working papers and research reports (cumulative), 35 peer reviewed publications (cumulative) and 6 research reports on migration in African cities (to be reviewed in late 2026) | Body of literature widely available and catalysing new scholarship on the political economy of African cities | Highly motived ACRC staff and contractors deliver work to the quality required. Swift and timely publication to agreed timelines including review process being completed. | Numbers of outputs difficult to predict upfront. This will be reviewed at each annual review. Target numbers for each year are tenative and will be revised and agreed with FCDO at relevant times. Summary/synthesis chapters of books (such as introductions and conclusions) will be counted towards the milestone target, provided that they put forth substantive content (this will be determined on a case-by-case basis by ACRC). These chapters will be counted as one book chapter towards the milestone target (ie. in books containing both an introduction and a conclusion, the introduction and conclusion would be counted as one book chapter, not two)
|  | Achieved |  | Met 13 Scoping studies published on ACRP website in 2021. Analytical literature review published November 2021 and annotated bibliography published in December 2021. | Not met: The first 7 city reports are not yet completed due to delays in budget certainty and the slowdown through the pandemic. They will all be completed in the next three months and it is anticipated that these reports will be published on the website by the second quarter of 2023. Domain leads are confident that the city domain research reports will enable this research to advance the field. | Not met: the ACRC team is currently working with city and domain leads to complete the work. The reasons for the delays are (i) the city leads took longer than expected in bringing together the diverse contributions across the research team in ways that integrated the findings, (ii) the process of finding reviews able to take on this work took longer than anticipated in some cases, and (iii) many reviewers have not maintained their commitment to return a timely review. For the cross-city domain reports, there is a similar reason for delays as for city working papers, i.e. securing the reviewers who are best placed and waiting for their reviews, and that a small number of city domain research reports have been delayed leading to domain leads not being able to complete the report. | Substantially not met. By December 2024, 7 of 12 city reports, 6 of 8 domain reports, and no crosscutting reports had been published. All published reports were summarised as briefs. | Moderately not met. 15 working papers; 8 journal papers; 2 book proposals accepted; and 1 book chapter.
|  | Source/Data collection model | [9 empty] | Risk rating
|  | Quarterly reports to R4D on outputs. ACRC Annual Reports. Google Scholar. Impact monitoring. | [9 empty] | Minor
| Output Indicator 1.3 |  | Baseline | 2021-12-31 | 2022-12-31 | 2023-12-31 | 2024-12-31 | 2025-12-31 | 2026-12-31 | Target (31-Dec-27) | Legacy | Assumption | Notes:
| Production of policy briefs, blogs, video blogs and novel means of communication that share new knowledge beyond academia and professionals. | Planned | ACRC uptake and communication strategy and plan | Website established and effective communication modalities identified and designed | All key communication channels (including website, social media, video and podcast) established and widely engaged with. | 1 case study of novel communication used to share knowledge. | 20% increase on key web metrics from 2023: Web users: 38k Web page views: 103k Working paper downloads: 500 LinkedIn subscribers: 1250 E-news subscribers: 825 | Maintain key web metrics from 2024: Web users: 43k Web page views: 80k Working paper downloads: 2500 LinkedIn followers: 3400 E-news subscribers: 1000 | 10% increase on average of key web metrics from 2024: Web users: 47k Web page views: 88k Working paper downloads: 2,750 LinkedIn followers: 3740 E-news subscribers: 1100 | 20% increase on average of key web metrics from 2024: Web users: 51.6K Web page views: 96k Working paper downloads: 3000 LinkedIn followers: 4080 E-news subscribers: 1200 | Repository of authoritative knowledge on African cities available open access and read by a wide range of different stakeholders. | Interest in ACRC among a wider audience both within and beyond ACRC cities. All relevant groups able to access internet and other means by which ACRC work is disseminated. | ACRC will encourage Consortium members and others involved with ACRC to be involved in producing content. Infographics will be used to reach out to non-academics, and other non-specialists. From 2026, the average increase is determined by aggregating the % change in each of the 5 key web metrics and dividing the sum by 5.
|  | Achieved |  | Met ACRC website launched in April 2021. Blogs, newsletters and twitter accounts established | Exceeded: Strategic and consistent communications activity across ACRC’s digital channels has yielded strong results over the past year, with more than 86,000 website views and 29,300 visitors in 2022. 64 blog posts were published – an average of five per month – which is more than double the number shared in 2021. Reach and engagement were strong on both primary social media channels, with followers surpassing 3,400 on Twitter and 1,000 on LinkedIn The African Cities podcast was launched in March and is showing promise, with 1,039 downloads for the 11 episodes released so far, across 68 countries. Building on scene-setting mini campaigns from 2021, online activity in 2022 aimed to provide greater clarity and deeper insights into ACRC’s research approach and theory of change. On the website, more interactive “about” and “connect” pages and a new “research” page were introduced, along with refined website navigation and new content for urban development domains and crosscutting themes. Significant media engagement throughout the year demonstrated the effectiveness of profile-raising activities to date, with requests for comment from The Economist, AFP, Financial Times and BBC World Service, along with coverage from The Conversation Africa and Deutsche Welle. | Met: Novel communication used to share knowledge on exploring urban reform coalitions. Urban reform coalitions are a key component of the ACRC theory of change and the approach to uptake more widely. They can create a way for collaboration between researchers, communities, NGOs, city elites and state agencies, enabling them to drive forward potentially contentious issues of policy and implementation around urban reform. While the concept of reform coalitions is well established, particularly within civil society, there are aspects of its application to urban reform processes that the programme has been keen to explore and highlight. It is also distinctive to the overall approach of ACRC and therefore a key idea the team has wanted to engage people around. At the same time, as there isn’t a singular, settled understanding of urban reform coalitions – and because it is part of a hypothesis that is being tested (within the ToC) – the concept is one where feedback was needed to catalyse further insights around, rather than definitively promoting as a settled conclusion and recommendation for others to adopt. The main aim was to drive engagement and conversations around the potential of urban reform coalitions, and in particular the role of knowledge, in creating substantive change. | Moderately exceeded. Web users: 43,500 (38% increase) Web page views: 80,016 (7% decrease) Working paper downloads: 2509 (505% increase) LinkedIn followers: 3435 (231% increase) E-news subscribers 1082 (58% increase) | Met. Web users: 46k Web page views: 81k Working paper downloads: 3252 LinkedIn followers: 5,182 E-news subscribers: 1,037
|  | Source/Data collection model | [9 empty] | RISK RATING
|  | Quarterly reports to FCDO of online reach. Quarterly reports to R4D on outputs. ACRC Annual Reports. Stakeholder surveys. | [9 empty] | Minor
| Output Indicator 1.4 |  | Baseline | 2021-12-31 | 2022-12-31 | 2023-12-31 | 2024-12-31 | 2025-12-31 | 2026-12-31 | Target (31-Dec-27) | Legacy | Assumption | Notes:
| Steps taken to build a database of projects and programmes relevant to ACRC | Planned | 0 | Specification developed. Database structure built and guidance on data collection developed. | Database populated by city study researchers. | Expanded database used by ACRC researchers. | Expanded database used by 1000 users / 2500 page views | 2000 users 3500 page views 8 case studies | Database completed for cases not initiated by ACRC projects 10% increase on key web metrics from 2025: 4753 users and 8989 page views 10 case studies of external initiatives published in 2026. 2 cases from ACRC projects added to the database. | 20% increase on key web metrics from 2025: 5185 users and 9806 page views 16 cases from ACRC projects added to the database. | Database of projects and programmes on Afican cities. | That a balance is achieved between simplicity and complexity in the design of the database. That a strong set of projects and programmes is secured across the 13 cities. That the information of the database will be of assistance in the development of approaches to addressing PCPs. This assumption will be tested. | The database launched in 2024 with the majority of case studies focusing on urban reform initiatives of interest to but not initiated by ACRC. With action research projects maturing in the Implementation Phase, the database in 2026 will focus on documenting cases primarly from ACRC's action research proejcts.
|  | Achieved |  | Marginally Not Met Specification developed, agreed within consortium and prototype expected to be piloted January 2022 | Met: The database has been built and populated with its first case studies. More case studies are in draft form and ready to be peer-reviewed before being uploaded, and a further list of case studies to pursue has been developed. Budget uncertainty meant that it was not possible to recruit the RA associated with this work until the end of 2022. It is anticipated that the RA will be in post within the first quarter of 2023 and this will further catalyse the database work. | Met: Within ACRC, researchers have been actively engaged with the database of urban reform. An internal version of the database interface / website was launched at the consortium wide meeting in May, and the team subsequently received 39 additional suggestions for additional case studies. So far around over 30 different ACRC researchers from across the consortium either are, or have been involved in authoring, co-authoring or contributing information. At the current time four case studies have been finalised, six are being externally reviewed, with 14 currently being drafted and an additional 8 ready to be worked on. Final case studies are around 2000–3500 words long. In December a peer review process for case studies was agreed and began to be implemented. This is especially important for two reasons: firstly because the focus is on recent (past 10 years) or ongoing initiatives, for which there are not always huge quantities of written resources available to draw on; and secondly to ensure a focus on documenting lessons and that the discussion is framed by the ACRC's ToC. | Substantially exceeded. Expanded database used by 1,974 users/ 3,623 page views. | Substantially exceeded. 4,321 users 8,172 page views 8 case studies
|  | Source/Data collection model | [9 empty] | RISK RATING
|  | ACRC Annual Reports. Feedback from colleagues. | [9 empty] | Minor
| Output indicator 1.5 |  | Baseline | 2021-12-31 | 2022-12-31 | 2023-12-31 | 2024-12-31 | 2025-12-31 | 2026-12-31 | Target (31-Dec-27) | Legacy | Assumption | Notes:
| Steps taken to ensure the co-production of knowledge is achieved | Planned | Strong commitment and experience in consortium on how to co-produce different forms of knowledge and to share capacity in this regard. | At least 50% of city scoping studies created through co-operation of authors in both the north and south. ACRC plan to coproduce (and decolonise) knowledge going forward in place. | At least 50% of city studies (both the first and second set) prepared through coproduction of authors in both the north and south. | At least 50% of action research and research projects to address PCPs designed through coproduction of researchers in both the north and south. | 100% of all action research projects led by the global South | 80% of peer-reviewed publications published in 2025 with global South authorship (sole authorship or co-led); 50% of peer-reviewed publications submited from writing workshop participants | 80% of peer-reviewed publications published in 2026 with global South authorship (sole authorship and co-led) 80% of published migration papers include global South authorship | 80% of peer-reviewed publications published in 2027 with global South authorship (sole authorship and co-led) 80% of published migration papers include global South authorship | Contribution to enhanced processes to coproduce research and decolonise knowledge demonstrated (in the context of urban reform). | Diverse skills, disciplines and experiences across the consortium can work together to coproduce the knowledge required. Success in bringing together community, professional and academic knowledge. Also in bringing together critical social theory with urban disciplines such as planning, engineering and architecture. | There is considerable experience across the consortium both in the substantive tasks, city study related research and approaches to addressing PCPs, and to coproducing knowledge. However, all consortium partners need to advance practice for this to be successful. The challenge is particularly to find ways to incorporate academics and non-academics as well as those in the global North and South. In 2025, measurement across aggregate of action research and research projects. (By project not by value of project).
|  | Achieved |  | Marginally Exceeded 50% (12 of 24) authors or co-authors of the city scoping studies were from the global south. Strategy to decolonise knowledge agreed and is being translated into various practical planning documents amongst both research and uptake teams. | This is being monitored carefully for all city studies. The programme is on track to exceed this indicator. For city synthesis reports, 71.5% of Set 1 city reports are being authored solely by researchers in the global South (43%) or co-produced by authors in the South and North (28.5%). In Set 2 cities, all city reports are expected to either be prepared by Southern researchers or co-produced by Southern and Northern researchers. A full breakdown of all city studies from the foundation phase will be provided in next year’s annual report, once all studies have been completed. | Met; 52 of the 60 PCP and PCP solutions have 100% African authorship. | Met. All approved Action Research projects are 100% led by researchers and organisations in the global South. | Met. 85% of peer-reviewed publications with global South authorship. 31% of peer-reviewed publications submitted from writing workshop participants.
|  | Source/Data collection model | [9 empty] | RISK RATING
|  | Annual reports. Plans for Theme 3 Action research. Theme 2 city plans. Evaluations. | [9 empty] | Moderate
IMPACT WEIGHTING (%)
50%
RISK RATING
INPUTS (£) | (£) |  | Govt (£) | Other (£) | Total (£) | SHARE (%)
INPUTS (HR) | (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | 2021-12-31 | 2022-12-31 | 2023-12-31 | 2024-12-31 | 2025-12-31 | 2026-12-31 | Target (31-Dec-27) | Legacy | Assumptions | Notes:
Productive relationships with reform coalitions, relevant groups of elites and local and national government officials operationalised. | Progress towards operationalizing productive relationships with existing and newly established Reform Coalitions such that they are committed to ACRC evidence-informed ways of working. Cumulative number of examples between reform coalitions and others involved in ACRC activities in which the value-added by reform coalitions can be identified. | Planned | Knowledge and experience embedded in Consortium, FCDO and CAG. | Raised awareness of ACRP thinking amongst members of reform coalitions in first set of seven city studies as evidenced through engagement with ACRP uptake. | Raised awareness of ACRC thinking amongst members of reform coalitions in the city studies as evidenced through engagement with ACRC uptake. Analysis of contribution by reform coalitions to urban reform in all city studies completed. | 5 examples of collaboration between reform coalitions and others (e.g. Elites) which have contributed to ACRC activities. | 10 examples (cumulative from 2024) of collaboration between reform coalitions and others involved in ACRC activities in which the value-added by reform coalitions can be identified. | 15 examples (cumulative from 2024) of collaboration between reform coalitions and others involved in ACRC activities in which the value-added by reform coalitions can be identified. | 20 examples (cumulative from 2024) of collaboration between reform coalitions and others involved in ACRC activities in which the value-added by reform coalitions can be identified. | 22 examples (cumulative from 2024) of collaboration between reform coalitions and others involved in ACRC activities in which the value-added by reform coalitions can be identified (to be reviewed in late 2026) | Improved understanding of the contribution of reform coalitions and other alliances to urban reform processes. Greater support for the activities of reform coalitions. More effective members of reform coalitions. | Reform coalitions are able to hold together with common purpose and be effective in their efforts. Reform coalitions agree to initial engagement with ACRC. Mobilized and organized citizens engage with reform coalitions and are able to catalyse a change in elites’ wn understanding of their interests. Mobilized and organized citizens do not disengage from the political process, and/or pursue violent means to address their needs and interests. Elites choose not to respond to reform processes with increased violence and/or manipulation of citizen expectations | ACRC Theory of Change indicates that effectve reform coalitions are essential if intractable complex problems are to be effectively addressed. At the same time, it is recognised that reform coalitions need to work - explicitly and/or implicitly - with mobilized citizens to secure reforms that are costly to elites. Therefore, there is a need to work in ways that enable the required assumptions to be secured. Engagement includes meetings, briefings, discussion panels linking coalitions with elites.
|  | Achieved |  | Milestone moderately not met This work has been delayed owing to COVID 19 and the need to restructure the programme to manage budget cuts, but the programme is well placed to catch up. Uptake plans being written, which will include activities to make contact with reform coalitions. City researchers have many of these contacts already, so there will be some awareness amongst reform coalitions of the consortium's thinking. Good progress is being made in Accra, Freetown and Harare. Beyond the cities themselves, good contacts have been made with a range of international organisations. | Marginally not met. With respect to raised awareness of ACRP thinking: in Accra, the team has been discussing with staff at UN-Habitat with a plan to relaunch the Housing and Urban Development Network (HUDNET) as a reform coalition able to advance initiatives in housing and urban development. Other meetings have been with the CSO SDG11 group and Coalition of NGOs in Water and Sanitation. In Freetown, the Sierra Leone Urban Research Centre focused one of its City Learning Platforms in December 2022 on translating research into practice, sharing preliminary results from the ACRP research. The City Learning Platforms have been developed by SLURC to enable multiple stakeholders to come together to discuss experiences and ways in which they can collaboratively identify solutions for the upgrading of informal settlements in the city of Freetown. In Harare, the Urban Informality Forum held a session in September 2022 focused on land and tenure security, at which the ACRP team presented their work. The session was organised at the University of Zimbabwe and drew in a wide range of relevant stakeholders, including residents’ associations, City of Harare officials, banking sector, NGOs, informal settlement representatives, community researchers and government officials. The Forum is co-convened by Dialogue on Shelter, Development Governance Institute, University of Zimbabwe, and Shelter and Homage Trust. A follow up meeting with Forum participants took place in December, and a further engagement has been scheduled for March 2023. In Nairobi, ACRC is linking up regularly with the Mathare Special Planning Area Research Collective (MSPARC) to discuss community priorities, including issues of safety and security, affordable housing and delivery of basic services. MSPARC is building on the experiences of the Special Planning Area in Mukuru, and includes Muungano Wa Wanavijiji, Mathare Social Justice Center, Ghetto Foundation, Mathare Roots and NUVONI-International Centre for Frugal Innovation. In the second set of cities, relevant reform coalitions have been identified and initial discussions have taken place, with further engagements planned as the research findings emerge. A paper analysing the contribution of reform coalitions to urban reform will be completed by the end of 2023. This will draw on all city studies. | Exceeded; 7 examples of reform coalitions. 1. Accra - Engagement with Local Government Network (LOGnet) and the National Urban Forum-Technical Working Group on Urban to rationalise for reforms in housing and service delivery , 2. Harare - Urban Informality Forum engaging strongly with the ACRP's research and evidence, and has been very supportive of work to advance the informal economic sector policy for the city of Harare and to ensure more effective state support for the informal economic sector. 3. Kampala - Longstanding relationships that the Urban Action Lab have developed with a mltitude of state agencies since it was founded in 2000 have added to the credibility of ACRP, and the City of Systems team (some of whom work within the Urban Action Lab) have been asked to engage with the Kampala Capital City Authority officials to advance Kampala's climate action plan. 4. Lagos - the Centre for Housing and Sustainable Deevelopment at the University of Lagos has helped the ACRC team to build relations with the state governor and officials in the state government who are tasked with taking forward the Lagos State Development Plan. 5. Lagos - Work in Lagos by ACRP has also catalysed the formation of a new coalition, the Pro-Poor Media for Development Network, which is being supported by journalists working with leading news outlets including the Premier Times Nigeria. 6. Maiduguri - The Network of Civil Society Organisations in Borno (NECSOB), an umbrella coalition of civil society organisations in Borno State which has been recognised by the state government that has been in the forefront of citizen-driven development (often interfacing between government, development organisations and affected communities), has made a substantive contribution to ACRP's uptake activities. 7. Nairobi - Mathare Special Planning Area Research Collective (M-SPARC), a coalition established to advance the development of the informal neighbourhood of Mathare, has helped to situate the work of the ACRP with the Nairobi Rivers Commission | Met. 5 examples of collaboration (12 cumulative) | Moderately exceeded. 16 (4 new). Accra - informal waste operators; Kampala - KCCA in food loss and waste; Nairobi - reform coalitions on refugee integration; strategy; Nairobi - Ngong River
|  | Source | [9 empty] | RISK RATING
|  | City as system studies. Domain studies. ACRC database. Annual reports. Feedback from coalitions. Publications | [9 empty] | Major
| Output Indicator 2.2 |  | Baseline | 2021-12-31 | 2022-12-31 | 2023-12-31 | 2024-12-31 | 2025-12-31 | 2026-12-31 | Target (31-Dec-27) | Legacy | Assumptions | Notes:
| Steps taken to ensure effective engagement with political elites to build support for urban reform. Steps are also taken to engage with the business elite. | Planned | Political analysis research at cities and domain levels and the definition and identification of political elites. Political analysis research at cities and domain levels and definition and identification of business elite. | Members of business and political elites in first set of 7 cities participate in ACRP uptake activities. | Members of business and political elites in second set of cities participate in ACRP uptake activities. | 1 example of political or business elites engagement (resource contribution, brokering, in kind contribution etc.) with ACRP activities. | Political or business elite actively engaged (e.g. resource contribution, brokering, in kind contribution etc.) in 5 ACRP action research and research projects. [Active engagement to be defined in project specific plans.] | Political or business elite actively engaged (e.g. resource contribution, brokering, in kind contribution etc.) in 10 (cumulative from 2024) ACRP action research and research projects | Political or business elite actively engaged (e.g. resource contribution, brokering, in kind contribution etc.) in 15 (cumulative from 2024) ACRP action research and research projects | Political or business elite actively engaged (e.g. resource contribution, brokering, in kind contribution etc.) in 17 (cumulative from 2024) ACRP action research and research projects (to be reviewed in late 2026) | Improved understanding among academic community as to how to engage business and political elites in urban reform. Improved awareness among elites of the benefits of urban reform. | It is assumed that relevant individuals will engage in ACRC processes if appropriate opportunities are created. It is also assumed that any opposition encountered from these groups can be managed. It is assumed that active engagement will lead to commitment. | This indicator focuses on the steps taken to engage political and/or business elite. Business and political elites are included in this output indicator in recognition that they may be significant individuals who are not comfortable working within reform coaltions but who are, nonetheless, important to securing urban reform and the achievement of ACRC objectives. ACRC programme staff will reach out to reform coalitions that include business and political elites. The team will also engage them directly as required.
|  | Achieved |  | Milestone not met, but on course for completion This work has been delayed owing to COVID 19, but plans are in place to catch up. Relevant political elites have been engaged in some cities (eg Lilongwe, Harare and Accra). Plans to engage political and business elites are being included in the uptake workplans for other cities. | Met: Information is included from the first set of cities, as delays to programme activities meant that the ACRC team was unable to report this fully last year. In Accra, close engagement with the national government led revision of urban policy and with the Ministry of Local Government, Decentralization and Rural Development (particularly the technical working group on urban who requested a briefing). In Freetown, close engagement with municipal authorities who have participated in meetings, also with the Mayor’s Delivery Unit and Transform Freetown, Development Planning Office, engineering department and the city councillors’ unit. The team have also engaged with a range of other state agencies, including Ministry of Land, Housing and Country Planning, Sierra Leone Housing Corporation, Directorate of Food and Nutrition, Ministry of Health and Sanitation, National Disaster Management Agency, Ministry of Western Region, National Youth Commission and Nation Youth Service. In Harare, close engagement with Harare City Council and the Ministry of Local Government (including follow up meetings with the Mayor at his request), with business associations such as Zimbabwe National Chamber of Commerce and the Confederation of Zimbabwe Industries and with private sector elites, such as City Park Holdings. Also engagement with the Permanent Secretary for Devolution and Provincial Affairs who invited the ACRC team to participate in meetings related to Harare. In Lilongwe, close engagement with the Lilongwe City Council, including a briefing to their Finance Committee, also a presentation to the National Planning Commission. Findings have been presented to and discussed with community governance structures in Kaliyeka, Mtsiriza, Senti and Mgona.In Maiduguri, close engagement with departments within the Government of Borno State including State Security Services, Commissioner of Police, Urban Planning and Development Board, State Agency for Youth Empowerment and Social Support Operations, and the State Agency for the Coordination of Humanitarian Affairs and Crises Response. Engagement has also included the Permanent Secretary at the Ministry of Poverty Alleviation. In Mogadishu, engagement with the Benaadir Regional Authority including discussions with the Planning and Environment Department and Head of Land, also with Mogadishu District Commissioners. In Nairobi, close engagement with multiple departments of the Nairobi City County Government. With respect to the second set of cities, in Dar es Salaam, this has included a wide range of local government leaders at multiple levels. For example, the chairman from Karakata settlement, Kipawa ward in Ilala city council, has taken part in meetings, as have sub-ward leaders from Mjimpya in vMnyamani ward. Executive officers from the ward level have also taken part in meetings. Local councillors from the city council level and town planners have also taken part in uptake meetings to benefit fully from the research findings. In Kampala, initial briefings for the Kampala Capital City Authority (KCCA) have been completed with councillors and the budget and planning committee to introduce them to the research. | Exceeded; 2 examples in the reporting period. 1. In Maiduguri, a pilot project will work with the state government, the district government and customoary leaders to extend the work of land titling into informal neighbourhoods and raise the percentage of persons with statutory rights of occupancy and enable informal land-owners to benefit from the additional security. NECSOB (see output indicator 1.2) will assist with mobilising communities through a wider range of activities. The Borno State Geographic Information Systems (BOGIS) is the most important state agency for this work, and the agency is commitmed and willing to enter a MoU with ACRP to implement the project. Additionally, support for the pilot project has also been gained via verbal consent from the traditional rulers and from the leaders of the district governments. 2. In Harare, support has been secured for the pilot project which mobilises entrepreneurs and informal works in Glen View 8; in particular, support from both the City of Harare and relevant ministries for the pilot project to upgrade Glen View 8 is linked to their understanding of the wider significance of the project for policy and programming towards the informal economy. The pilot project team have secured agreement from local councillors, political party representatives, city technocrats, local representation from relevant government ministries and public bodies, development agencies and the Glen View Home Industries Associations in addition to a range of enterprise groups and other civil society agencies. The City of Hrare technocrats have agreed to take part in the Multi-Stakeholder Working Group (MSWG) to support the improvement process. | Met. 5 examples of collaboration | Met. 10 (5 new). Accra - urban property tax workshop and government commitment to decentralisation; Lagos - multi-level government support and cross-city learning exchange; Harare - new markets policy and GV8FC; Nairobi - integration into the Ngong River master plan; Nairobi - support from NCCG to promote integration
|  | Source | [9 empty] | RISK RATING
|  | Theory of change. Annual reports. Evaluation. Publications | [9 empty] | Moderate
| Output Indicator 2.3 |  | Baseline | 2021-12-31 | 2022-12-31 | 2023-12-31 | 2024-12-31 | 2025-12-31 | 2026-12-31 | Target (31-Dec-27) | Legacy | Assumptions | Notes:
| Progress towards building and strengthening the capacities and capabilities within both the Consortium and its partners, and more widely in Reform Coalitions and local and national government. | Planned | Capacity strengthening needs assessment. Emphasis on sharing of experience and expertise within the Consortium. This will also be mapped to provide a baseline assessment of relevant resources. | Capacity strengthening plan for city studies developed, agreed and implemented in relevant period with an emphasis on capacity sharing between Consortium members. | Consortium staff and non-consortium research and uptake partners to have their capacities enhanced. | Capacity strengthening plan for action research and research related to PCPs developed and agreed. | 3 case studies of capability development programmes for professionals and communities involved in city studies, and/or action research and research work produced. | 6 case studies (cumulative from 2024) of capability development programmes for professionals and communities involved in city studies, and/or action research and research work produced. | 9 case studies (cumulative from 2024) of capability development programmes for professionals and communities involved in city studies, and/or action research and research work produced. |  | Higher capacity individuals and organisations working on urban reform. Capacity and capability needs for more effective urban reform identified. | Interest in capacity building within and beyond the consortium. Early identification of capacity sharing and strengthening related to action research and research needs for addressing PCPs is possible. | ACRC will develop a range of capacity sharing and strengthening activities within the consortium and beyond the consortium for foundation phase studies, action research projects and uptake. These will involve considerable learning about both urban development processes and approaches and political economy analysis and political processes. The reporting of Output indicator 2.3 will end in 2026 to reflect the decrease in budget and activity of capability/capacity development programmes.
|  | Achieved |  | Milestone not met, but on course for completion. Capacity Strengthening Plan has been delayed, owing to delays in recruiting staff, but a range of capacity strengthening activities have been undertaken around the development of overarching frameworks and documents. A capacity survey has been undertaken with Consortium members to ensure that the Plan is strongly informed by their priorities. | Met: ACRC has continued to engage in capacity sharing activities at multiple levels, including peer-to-peer learning within cities, across cities within work strands (PS, systems, domain, uptake, safeguarding etc) and within the broader conceptual framework of the programme. For example, in Accra, the team organised five neighbourhood capacity building workshops for over 150 participants drawn from different stakeholder groups to share ACRC’s conceptual framework and learn from community experiences. Efforts have also been made to enhance local capabilities. In Lagos, for example, the team benefited from a master class in political economy from Dr Damilola Agbalajobi offered early in the research process. We developed a programme of activities to develop broader research and research-related skills, such as how to communicate research findings and how to get published. These sessions were attended by 132 people from across ACRP. Uptake partners in the Set 1 cities have been engaged in diverse ways, through one to one meetings, domain-focused discussions and large-scale uptake events. This has provided an opportunity for the ACRC’s conceptual framework to be introduced and the comprehensive information about the city presented. | Met: a three-phase plan has been developed, which aims to be responsive to the participatory nature of action research. As participation can be measured along a continuum from passive to active participatory research with possible forms in between, there is no blueprint of action research which makes it important for any team to define it in a way that achieves the intended outcomes of the research. Each city team will have to gauge whether a particular phase is a worthwhile exercise to do or if there is ample experience and expertise, focus can then be on monitoring progress of key progress markers. ACRC also places considerable emphasis on the incorporation of local residents and the development of community knowledge; therefore, ACRC has a plan to enhance the development of community knowledge and build the capabilities of both community and non-community researchers to achieve this goal. | Met. 3 case studies of capability development programmes produced. | Met. 6 (3 new). Hybrid academic writing and mentoring programme; strengthening the advocacy skills and legal knowledge of informal settlers to participate in the tenure process in Mogadishu; online training series with Spring Collaboration
IMPACT WEIGHTING (%) |  | Source | [9 empty] | RISK RATING
40% |  | Annual reports. Survey of stakeholders. | [9 empty] | Moderate
INPUTS (£) | (£) |  | Govt (£) | Other (£) | Total (£) | SHARE (%)
INPUTS (HR) | (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | 2021-12-31 | 2022-12-31 | 2023-12-31 | 2024-12-31 | 2025-12-31 | 2026-12-31 | Target (31-Dec-27) | Legacy | Assumption | Notes:
Action research projects and research projects incorporating African Cities Research Consortium approach being implemented. | Steps toward building a suite of Action Research projects that demonstrate substantively novel approaches using examples of policies, programmes and practices that address priority complex problems (PCPs) and secure urban reform and which are gender relevant with approaches that address the economic development needs of women and girls, and which take account of gender specific vulnerabilities in efforts to secure poverty reduction. | Planned |  |  | Round 1 Priority Complex Problems identified as well as approaches and processes to address them. | Round 1 of PCPs projects underway; identified number of households that will benefit from specified improvements in either poverty reduction and/or economic prosperity and/or reduction in climate related risk. Method to measure gendered impacts within and beyond the household in place. | For all PCP projects underway: number of households identified that will benefit from specified improvements in poverty reduction and/or economic prosperity and/or reduction in climate related risk. Data are disaggregated by gender. | For all PCPs: number of households identified that are benefitting from specified improvements in poverty reduction and/or economic prosperity and/or reduction in climate related risk. Data are disaggregated by gender; gendered impacts within and beyond the household will be measured. | For all PCPs: increased number of households identified as benefitting from specified improvements in poverty reduction and/or economic prosperity and/or reduction in climate related risk. Data are disaggregated by gender; gendered impacts within and beyond the household will be measured. | For all PCPs: increased number of households identified as benefitting from specified improvements in poverty reduction and/or economic prosperity and/or reduction in climate related risk. Data are disaggregated by gender; gendered impacts within and beyond the household will be measured. | Effective urban reforms underway that build on approaches used in action research projects, with gendered aspects identified. | An interest in urban programming and projects exists at both the national and transnational level i.e. including and reaching beyond FCDO. Multi-sectoral political informed approaches will succeed and will not be delayed by political challenges and/or operational and technical issues. Technical aspects improved through systems analysis and ability to catalyse urban reform through effective coalition interventions and inspire elites to change direction is demonstrated. | There are two types of projects under this indicator: 1) Action research projects which reflect a suite of new projects that demonstrate substantively novel approaches to urban reform 2) Action research projects linked to existing programmes, policies and practices
|  | Achieved |  | NA | The PCP identification process was delayed by the ongoing budget uncertainty. The PCP Panel has been formed and met initially in December. Unfortunately, budget confirmation for the next two years was only confirmed after the panel first met. A further meeting to finalise the process to identify PCPs that are planned to be piloted was held in early January. Potential projects to address PCPs are now being assessed with the next meeting planned for February 2023. This will likely be a two-stage process with a revise and resubmit phase. The first round of pilot projects to address PCPs will therefore be identified by March 2023. | For this output the example of Harare, one of the pilot projects, is used. The project is to upgrade an informal furniture market (see Annex 12 above). Verified figures on the number of traders at Glen View 8 are unavailable. Obtaining accurate figures is exacerbated by various factors. In part the exponential growth of the complex has experienced since it was first established in 2000. Numbers increased in 2005, after Operation Murambatsvina, when enterprises that were demolished across the city were relocated at Glenview 8. Another key factor why figures fluctuation is due to frequent fires which have become a yearly occurrence. In addition, access to and ability to retain a market stall is linked to the power and control wielded by space barons who charge fees. The number of businesses operating at any time is also includes ancillary traders, such as food vendors, that have set up in and around the market. In addition, during Covid traders spread to the surrounding neighbourhood, acquiring rented spaces in back yards of neighbouring households. There is no consensus on actual numbers, as the following figures illustrate. According to a 2012 study by the International Journal of Marketing and Technology the city council allocated 1,920 small and medium enterprises stalls. A survey in 2022 estimated that the industrial complex houses over 500 informal economy enterprises that specialise in the production and selling of furniture, with over 1,500 men and women are either directly or indirectly employed at the complex.9 In the absence of reliable figures, the starting point of the action research will be a participatory mapping and profiling exercise which will cover the totality of the market and the existing stock of facilities and services and will verify the formal and informal boundaries of the trading area. The inventory of existing facilities and services will inform the type of improvement interventions that will form part of a participatory prioritization process to identify which improvements to the infrastructure, that will enhance the economic activity and quality of working conditions, will be implemented. Although the traders are primarily men, women do have a significant presence in the market complex. The detailed mapping and profiling information will establish a baseline and disaggregated data set on female and male traders, including gendered data on the space barons and representation in traders’ associations. As part of the mobilization, the Zimbabwe Homeless People’s Federation will support women and youth-led saving groups at the Complex targeting women and youths who are involved at the different production stages of the furniture businesses including the supportive economic activities. The Federation has an initial target of 100 women organised in savings groups. The savings groups focus will also include households in the immediate surroundings of the Complex who are, in many respects, linked to the furniture businesses. The action research in Maiduguri will augment the land administration and registration process which is being undertaken by the Borno State Geographical Information System (BOGIS) in collaboration with the local government councils and traditional rulers. A digitisation of land and buildings is underway, and the programme of land registration, which enjoys strong support from the Governor, is being extended to incorporate customary land titles into the land registry database. According to BOGIS data, an initial round of data capture related to a total of 102,858 properties surveyed, 10,109 have customary certificates of occupancy, and 4,126 have only local sales agreements. Land registration through customary means has enjoyed legitimacy for centuries however those holding customary title are exposed to various risks including abuses of power by local land vendors, forged and flawed documents as well as land grabbing linked to political interests. Low-income households, particularly low-income women are at greatest risk of experiencing these abuses. In many instances low-income people have lost their lands to powerful groups. Land conflicts are common, the courts are inundated with cases, and weakness in the justice system result in insecurity for the most vulnerable, fuelling distortions in the land economy. Upgrading the land registration system to include customary title holders aims to curb the practices of the powerful groups as well as recognize customary titles as legitimate and record these transparently in the land registration system. The ACRC action research project will contribute to the process working with the groups that are certificate holders and through legal and technical advisory services, enable the resolution of cases, and the transition to statutory titles. This group have been selected since these local agreements are those that are at greatest risk. It is expected that 1,000 titles will be issued benefitting 1,000 households. Low-income women have historically faced gendered challenges in acquiring land. The ACRC project will include the processing of titles for women; the first trail aims to benefit 100 women living in the most marginalised communities. The aim of the trial is to document a process which can be replicated. The project will carry out an awareness raising process to enhance the capabilities of local leaders, the custodians of the land, on the merits and benefits of titling. The action research will engage the leaders, clarifying their role as well as the role of local government in the new registration system, bringing together the key state and civil society actors and customary leaders to enhance the land reform coalition. Reporting on the number of titles will include a socio-economic profile of the households that obtain titles; the learning will also document what are the co-benefits of the holding title, (in addition to security). | Met. For all action research projects, number of beneficiary households identified. In almost all cases, gender disaggregated data is available. | Met. The programme has identified beneficiaries across 5 categories of early benefits, with partial gender disaggregation where feasible.
|  | Source | [9 empty] | RISK RATING
|  | Annual reports. Case studies. Action research project evaluations. | [9 empty] | Moderate
| Output Indicator 3.2 |  | Baseline | 2021-12-31 | 2022-12-31 | 2023-12-31 | 2024-12-31 | 2025-12-31 | 2026-12-31 | Target (31-Dec-27) | Legacy | Assumption | Notes:
| Evidence based learning generated on existing urban reform efforts (not initiated by or directly supported by ACRC) | Planned | ACRC Conceptual Framework and Theory of change. Consortium knowledge on previous failed attempts at urban reform. |  |  | 3 existing projects identified for study by ACRC (for their consistency with the conceptual framework and Theory of Change) and permission for research secured by project "owners". Research plan for the study of 3 projects drafted and agreed within ACRC andwith project "owners". Further 4 projects identified for study by ACRC and permission for research secured from project "owners". | Research plan for the study of second 4 projects drafted and agreed within ACRC and with project "owners". | Report on the results from at least 2 research projects available. Dissemination plan for results also agreed |  |  | Repository of documented experience and learning from addressing PCPs in urban reform. | Assume that projects and programmes will be identified that demonstrate substantively novel approaches consistent with the research findings from Theme 2, that can be usefully researched to understand better the successes and challenges of such approaches. This might include those that have used a similar methodology to analyse projects and identify implementation options. Or those with overlapping operational approaches. Assume that the agencies involved in such projects and programmes will be open to ACRC researching their work. Assume that research will continue even if there are sensitive findings. | This output is focused on research projects; these are intended to produce and disseminate learning by ACRC on the effective implementation of existing projects that address priority complex problems and secure urban reform. These projects were not implemented by ACRC partners but are similar to those that ACRC might have designed. Research projects starting from 2023 will be identified and implemented, with detailed plans on how the results will be shared. Reporting on this output ended in 2025 because the research reports are being captured in Output 1.2
|  | Achieved |  | NA |  | The proposed action research project aims at improving the health and nutrition conditions of children in urban informal settlements specifically those in private informal primary schools not currently targeted by the existing county programmes. Since the pilot project was proposed late in 2022, there has been much more widespread recognition of the need for improved school feeding. The Government of Kenya at both at the national and County levels are cognizant of the food insecurity and nutrition problem faced by some vulnerable urban populations including children. The Governor of Nairobi County has therefore launched a school feeding programme dubbed Dishi na County for public primary schools and early child development (ECD) centres in Nairobi County targeting mostly informal settlements and /or low-income urban areas. Three established programmes will be studied both to provide the evidence to inform approaches to inclusive school feeding in Nairobi and encourage such approaches to be more inclusive and specifically to reach out to informal schools in informal neighbourhoods. These programmes are the following: The Dishi na County school feeding programme targets to feed at least 250,000 children through 10 centralized kitchens serving several public primary schools and ECD centres in select Nairobi sub-counties. It is essential to include this programme due to its significance for the governor. It forms a significance benchmark against which other projects can be evaluated by the county government. Food4Education has also been selected. It is being implemented in some public primary schools in Nairobi and its environs, Mombasa and Kisumu. It has been selected because it informed the design of the Dishi na County School feeding programme. It was also influential to the researchers in the first phase of ACRC i.e. during the identification of the priority complex problem (PCP). It’s also been selected to learn from due to its longevity and because its already being scaled up in other Counties (Mombasa and Kisumu) i.e. it has achieved both material improvements in the quality of life and health of school children, and has moved school feeding up the political agenda. Research staff have already engaged with this project in the Foundation Phase domain research (health, well-being and nutrition domain). Food Banking Kenya is the third project selected. It is also being implemented in Nairobi. The model works with select supermarkets and informal schools. It collects all the short shelf-life groceries that are still edible and re-distributes them to school for feeding of the immediate use in feeding of the school children. This model has been selected to learn how school feeding programmes can leverage on SMEs for improved environmental sustainability and reduced food waste. Finally, four informal schools within Viwandani and Mathare that are offering food to their students will be studied to understand the school-produced food model. Research plans have been drawn up by the project team and are in the process of being finalised by ACRC. Once they have been signed off by ACRC, they will be shared with the projects and programmes that will be studied, and MoUs will be signed. | Met. Two sets of research projects are under way which will investigate 5 case studies. Research plans are in place. | Moderately exceeded. 4 research outputs are described with dissemination approaches.
|  | Source | [9 empty] | RISK RATING
|  | Research reports. Annual reports. ACRC evaluations | [9 empty] | Moderate
IMPACT WEIGHTING (%)
10%
INPUTS (£) | (£) |  | Govt (£) | Other (£) | Total (£) | SHARE (%)
INPUTS (HR) | (FTEs)
| Output Indicator 4.2 |  | Baseline - 2018 | Milestone 1 | Milestone 2 | Target - 2021 | [5 empty] | Assumptions
Planned
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 4.3 |  | Baseline - 2018 | Milestone 1 | Milestone 2 | Target - 2021
Planned
Achieved
Source
INPUTS (£) | (£) |  | Govt (£) | Other (£) | Total (£) | SHARE (%)
INPUTS (HR) | (FTEs)
RISK RATING
OUTPUT 5 | Output Indicator 5.1 |  | Baseline - 2018 | Milestone 1 | Milestone 2 | Target - 2021
Planned
Achieved
Source
| Output Indicator 5.2 |  | Baseline - 2018 | Milestone 1 | Milestone 2 | Target - 2021 | [5 empty] | Assumption
Planned
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 5.3 |  | Baseline - 2018 | Milestone 1 | Milestone 2 | Target - 2021
Planned
Achieved
Source
INPUTS (£) | (£) |  | Govt (£) | Other (£) | Total (£) | SHARE (%)
INPUTS (HR) | (FTEs)
RISK RATING
OUTPUT 6 | Output Indicator 6.1 |  | Baseline - 2018 | Milestone 1 | Milestone 2 | Target - 2021
Planned
Achieved
Source
| Output Indicator 6.2 |  | Baseline - 2018 | Milestone 1 | Milestone 2 | Target - 2021 | [5 empty] | Assumptions
Planned
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 6.3 |  | Baseline - 2018 | Milestone 1 | Milestone 2 | Target - 2021
Planned
Achieved
Source
INPUTS (£) | (£) |  | Govt (£) | Other (£) | Total (£) | SHARE (%)
INPUTS (HR) | (FTEs)
RISK RATING

## Collection Models
Outcome indicator 1 – first due by Dec 23 (5 examples needed then)
Number of uses of ACRP's research approach and products in policy and planning in African cities (cumulative)
Unsure if this is within ACRC Cities, or beyond?
Current main source of city reporting is through quarterly uptake reports via Uptake Team. Rosebella lliaising thoroughly with city teams. Establish who she liaises with to ensure we get the furthest reach with partners in cities e.g. not just Uptake? Follow up with Rosebella
DM : Carrying on in Cities going forward to implementaiton phase. Uptake via Chris and Martin - agree a process for information capruting via Uptake Reporting, how to ensure nothing is missed, things are followed up on
Outcome indicator 2 - first due by Dec 23 (3 examples needed then)
Cumulative number of Reform Coalitions with enhanced capacity to contribute towards ACRP instigated urban reform
MEL Tracker noting progress on the identification of RCs at City level via Uptake quarterly reporting. Measurement of RCs' baseline capacity and capacity after programme/associated outcomes has not been started?
DM: Via PCP projects' City Managers, Comms & Uptake
Outcome indicator 3 – due Dec 23 - Three citizen groups taking part in ACRP action research projects to address PCPs
Cumulative number of cities where there are examples of significant ACRP contributions towards citizen engagement in ACRP efforts to secure urban reform.
MEL Tracker noting progress on citizen groups for current cities via Uptake quarterly reporting. Reporting method to be reviewed for Implementation phase - how will citizen group involvement be measured in new projects?
DM: Comms & Uptake to agree how to capture this. Need a process to follow up on quarterly reports each quarter so we have numbers/examples at year end for reporting
Outcome indicator 4
Progress towards securing elite commitment (including both political and business elites) to ACRP approaches to addressing PCPs and securing reform.
Review Annex 1 of 2022 Annural Report for future metrics proposals
MEL Tracker noting progress onpolitical and business elites via Uptake quarterly reporting
Research Group agenda for October: Integrate into PCP pilots
Outcome Indicator 5
Progress towards building the capacities and capabilities of national and local government staff and politicians at all levels relevant to ACRP approaches to addressing PCPs and securing reforms.
Review Annex 2 of 2022 Annural Report for future metrics proposals
MEL Tracker noting progress on city capacity strenghtening via Uptake quarterly reporting (?) Double check with Rosebella or via saved reports - look on MS Teams
Research Group agenda for October: Integrate into PCP pilots
OUTPUT 1
Overall: Robust new knowledge and evidence on African ‘cities of systems’, domains and political settlements documented with lessons effectively communicated.
Output Indicator 1.1 – due to report Dec 23 (analysis of robustness of framework from all cities)
Extent of effective utilisation of the African Cities conceptual framework and methodology.
Follow up with Seth/Sam/Diana as to how this will be covered. Reports synthesis from Set 1 cities? WP or academic paper? Indicator definition - what will this Indicator cover in particular?
Flag for next RG - indicator for CF 1.1 Output. Taking stock of CF in implementation phcase. Shuaib & Tim responsible for CF going forward
Output Indicator 1.2 – due to report Dec 23 (working papers from all cities + domains on website)
Production and dissemination of high quality, peer-reviewed and relevant research products by ACRP.
Set One Cities WPs to add to ACRC Website once ready - these are ongoing as of June 2023. Review completion via SMT Leads. Set 2 ready and on website by Dec 2023?
DM: Ongoing. Ensure review at RG at quarterly intervals for 1.1 and 1.2
Output Indicator 1.3 – due to report Dec 23 (One case study of novel communication used to share knowledge. )
Production of policy briefs, blogs, video blogs and novel means of communication that share new knowledge beyond academia and professionals.
One case study of novel communication used to share knowledge. Restructure of website to incorporate PCP work undertaken. Discuss with Chris and Hannah whether they think this is still on track or needs pushing back/ amending
DM: Novel comms- Foundation phase - Chris and Martin flag what to do , we can prep content
Output Indicator 1.4 – due to report in Dec 22 (database completed by city study researchers)
Steps taken to build a database of projects and programmes relevant to ACRC
Underway: Project is ongoing. Has timeline been extended? 2023 Goal: Expanded database used by ACRP researchers?
DM: Overseen by RG. Kate & Selam replacement report at RG in October. Also liaise with Chris re: outputs
Output 1.5 – due to report in Dec 23 (At least 50% of action research and research projects to address PCPs designed through coproduction of researchers in both the north and south. )
Steps taken to ensure the co-production of knowledge is achieved
Underway - monitoring of co-production via PCP Panel? Who is monitoring Action Research projects - Beth ?
DM: Monitoring process - PCPs. Do around contracting process. Who is involved in designing the PCPs? Global North and Global South.
OUTPUT 2
Overall: Productive relationships with reform coalitions, relevant groups of elites and local and national government officials operationalised.
Output Indicator 2.1 – due to report Dec 23 (Five examples of collaboration between reform coalitions and others (e.g. Elites) which have contributed to ACRP activities.)
Progress towards operationalizing productive relationships with existing and newly established Reform Coalitions such that they are committed to ACRC evidence-informed ways of working.
MEL Tracker noting progress on RCs via Uptake quarterly reporting. Are we on track from Set 1 cities? Set 2 to add more
DM: For RG: Stocktake in October. 5 project started by December. 4 pilots plus 1 more. Or a platform e.g. SLURC?
Output 2.2 – due by Dec 23 (One example of political or business elites engagement (resource contribution, brokering, in kind contribution etc.) with ACRP activities.)
Steps taken to ensure effective engagement with political elites to build support for urban reform.
Steps are also taken to engage with the business elite.
MEL Tracker noting progress onpolitical and business elites via Uptake quarterly reporting
For PCP Committee: poss Harare? DM speak to Irene and Beth. DM speak to Irene re: 2024 2.2 number of engagements
Output 2.3 – due to report in Dec 23 (Capacity strengthening plan for action research and research related to PCPs developed and agreed)
Progress towards building and strengthening the capacities and capabilities within the Consortium and more widely in Reform Coalitions and local and national government.
MEL Tracker noting progress on city capacity strengthtening so far via Uptake quarterly reporting. To do: plan how this learning can feed into AR and PCP activities, and how capacity is measured for the new projects
DM: Cities may run late. Each PCP will have own CS plan. These need collating / keeping track of together. DM speak to Irene.
OUTPUT 3
Action research projects and research projects incorporating African Cities Research Consortium approach being implemented.
Output Indicator 3.1 – Due by Dec 23 (Specific targeted areas for PCPs: poverty reduction/climate change/gendered impact)
Steps toward building a suite of new projects that demonstrate substantively novel approaches using examples of policies, programmes and practices that address priority complex problems (PCPs) and secure urban reform and which are gender relevant with approaches that address the economic development needs of women and girls, and which account of gender specific vulnerabilities in efforts to secure poverty reduction.
PCP Measurement - taken from PCP Outline proposals and/or project development? Measurements built in from the start for gendered impact?
DM: Pick up as we move forward with PCPs. Pick up with review point for 2.2
Output Indicator 3.2 – due Dec 23 (completed design of action research additions to augment ongoing programmes [round 1])
Steps taken to contribute effective substantively novel action research additions to existing programmes, policies and practices that address PCPs to increase their likelihood of success in improving household wellbeing
AR Reports overdue? Follow up with Beth C-B? Also AR workshops, general progress
DM: Pick up as we move forward with PCPs. Pick up with review point for 2.2
Output Indicator 3.3 – due Dec 22 (3 existing projects identified for study by ACRC (for their consistency with our CF and ToC) and permission for research secured by project "owners").
Steps toward the production and dissemination of relevant and accessible learning by ACRC on the effective implementation of existing projects that address priority complex problems (PCPs) and secure urban reform.
· How measured: Unclear – who would be analysing this and how?
Liaise with SMT - have these 3 projects been chosen? Are these projects from the first phase that will feed learning into Implementation phase via use of CF/ToC in PCPs?
DM: Study existing projects? Future SMT on City Selection - after that. September

## Definitions
Term | Relates to | Definition | Potential Indicators
Reform Coalitions | Outcome indicator 1.2 | An informal or formal group or alliance of stakeholders that makes a deliberate, concerted effort to address urban challenges and nurture reform. The group/alliance should involve a wide, diverse range of stakeholders with an interest in the relevant urban development challenge. | Needs data on (a) numbers of coalitions (with an indication if we have stimulated new coalitions) and (b) capacity. We will assess coalitional capacity with respect to knowledge, skills, relationships, and finances. Indicators of enhanced knowledge might include the production, circulation and absorption of ACRP knowledge products, eg city studies, domain studies, approaches to addressing PCP studies, by and across different members of the coalition. Enhanced analytical skills might be indicated by use of the ACRC’s diagnostic framework or other ACRP methods; enhanced communications skills by ACRP brokered uptake and outreach activities; enhanced political skills by the ability to recognise and take advantage of windows of political opportunity. Enhanced relationships might be indicated by expanded membership of the coalition, evidence of a growing network, etc. Enhanced finances might be indicated by the coalition receiving funding either from ACRP, internal sources, or external stakeholders. Some of these indicators, eg number of studies shared, number of outreach activities undertaken can be counted; others, eg political skills and enhanced relationships are better captured through case-studies.
Citizen Engagement | Outcome indicator 1.3 | Engaged citizens – groups of organized residents that come together to address their needs and interests in relation to an identifiable urban development challenge. [This can be low-income informal residents (SDI and others); and/or low-income informal workers (some WIEGO members such as Streetnet and others); and/or higher income residents (Harare Concerned Residents etc.) and/or higher income formal workers (eg. Trade unions).] | We will assess citizen engagement with respect to citizens’ collective organisation and participation in urban reform efforts of interest to ACRP. Collective organisation might be indicated by community or membership meetings; the creation of new groups or associations; by advocacy activities, direct action, ‘rude accountability’, or self-help efforts, all around approaches to addressing PCPs that have been identified by ACRP, and where there is evidence of ACRP catalysing or contributing to these efforts, for example through conducting action research in the community and disseminating knowledge products therein, through brokering connections between the community and reform coalitions, etc. Participation might be indicated by community attendance in invited spaces such as council meetings, planning meetings, academic or professional forums, to discuss approaches to PCPs identified by ACRP. Some of these indicators can be quantified, eg number of new associations formed, but the link to ACRP will in most cases need to be traced through case-studies and community testimony.
Elite commitment | Outcome indicator 1.4 | Definition of elite commitment from ESID political settlements work: ‘Elites are those individuals that occupy high-ranking positions, whether de facto or de jure, in those societal and governmental organisations with sufficient power that, acting singly or with others, might plausibly, by their action or inaction, make a significant difference to the maintenance, evolution or destruction of the political settlement, for example high-level party leaders, high-level administrators, high-ranking military officials, captains of industry, major financiers, powerful labour leaders, popular or well-connected religious leaders, major publishers, high-ranking diplomats from influential foreign countries, etc’ | Elite commitment can be evidenced through one or more of the four indicators outlined in our measurement note (discursive, legal, financial and practical), and refers to those individuals that occupy high-ranking positions (whether de facto or de jure) in those societal and governmental organisations with sufficient power that make a significant difference to the maintenance, evolution or destruction of the political settlement. Their involvement can make or break a process, and therefore securing their buy-in is a major enabling factor in urban reform.
Enhanced capacity and capacity | Outcome indicator 1.5 |  | Enhanced capability and capacity are distinct from elite commitment. This refers to the ability of government (at different levels) to respond and carry out urban reform when political commitment is in place. For example, the government may be committed to water reforms, and convinced that there is a need to coproduce water delivery with local informal providers. That requires officials at all levels of the water utility have the competence to design and operate hybrid systems, it requires internal coordination to identify failings in any one part of the system being reluctant to implement a coproduced process, and it requires the relational capacity in street level bureaucrats to have constructive relations with informal providers.

## Risk
Risk rating definitions | Minor | Moderate | Major | Severe
| This is an issue / risk that could have a minor effect on the achievement of one or many of the Department's strategic objectives, or could have a minor effect on the effectiveness or efficiency of the Department's activities or processes | This is an issue / risk that could have a moderate effect on the achievement of one or many of the Department's strategic objectives, or could have a moderate effect on the effectiveness or efficiency of the Department's activities or processes | This is an issue / risk that could have a major effect on the achievement of one or many of the Department's strategic objectives, or could have a major effect on the effectiveness or efficiency of the Department's activities or processes | This is an issue / risk that could severely affect the achievement of one or many of the Department's strategic objectives, or could severely affect the effectiveness or efficiency of the Department's activities or processes

## notes
1.1 | research papers
quality
conceptual framework
analytical guidance
coproducing
project analysy
no database
relationships | s/h engagement
| reform coalitions | new | triggered by us have life of own
|  | existing | learning new skills
projects

## Activities Log
OUTPUT 1 | ACTIVITY 1.1 | Milestone 1 March 31st 2018 | Milestone 2 - September 2018 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Risks | Monitoring Officer
| ACTIVITY 1.2 | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 |  | Monitoring Officer
| ACTIVITY 1.3 | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 |  | Monitoring Officer
OUTPUT 2 | ACTIVITY 2.1 | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Risks | Monitoring Officer
| ACTIVITY 2.2 | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 |  | Monitoring Officer
| ACTIVITY 2.3 | Milestone 1 | Milestone 2 | Milestone 3 | 4 | Milestone 5 | Milestone 6 |  | Monitoring Officer
OUTPUT 3 | ACTIVITY 3.1 | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Risks | Monitoring Officer
| ACTIVITY 3.2 | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 |  | Monitoring Officer
| ACTIVITY 3.3 | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 |  | Monitoring Officer
| Activity 3.4 | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 |  | Monitoring Officer
OUTPUT 4 | ACTIVITY 4.1 | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Risks | Monitoring Officer
| ACTIVITY 4.2 | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 |  | Monitoring Officer
| ACTIVITY 4.3 | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 |  | Monitoring Officer
OUTPUT 5 | Activity 4.4 | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Risks | Monitoring Officer
| Activity 4.5 | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 |  | Monitoring Officer
| ACTIVITY 5.3 | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 |  | Monitoring Officer
OUTPUT 6 | ACTIVITY 6.1 | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Risks | Monitoring Officer
| ACTIVITY 6.2 | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 |  | Monitoring Officer
| ACTIVITY 6.3 | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 |  | Monitoring Officer