Programme Completion Review

Title: Transparency and Accountability for Inclusive Development (TAcID)
Final Programme Spend £ (full life): £ 7,589,050	Review Date: 30/06/2025
Programme Code: [AMP ID#] 300210	Start Date: 01/03/2018	End Date: 31/03/2025

Summary of Programme Performance
Year	2018	2019	2020	2021	2022	2023	2024
Programme Score	A	A	A	A+	A	A	A
Residual Risk Exposure Rating	Moderate	Moderate	Major	Major	Major	Major	Major

DevTracker Link to Business Case (and any addendum):	https://devtracker.dfid.gov.uk/projects/GB-GOV-1-300210/documents
DevTracker Links to all logframes used during programme lifetime:	https://iati.dfid.gov.uk/iati_documents/24594664.xlsx

A. Summary and Overview

Description of the programme and what it has achieved
The Transparency and Accountability for Inclusive Development (TAcID) programme sought to increase government transparency, accountability and responsiveness to demands from citizens, including through better allocation of resources to priority areas and greater participation and inclusion in the country’s governance. The programme had two pillars. Pillar 1 was called POTENCIAR (‘strengthening’ in Portuguese) and its activities addressed governance problems that were undermining the quality of basic health services, particularly maternal and child health services, with a focus in the province of Nampula – the country’s most populous province. POTENCIAR was delivered by a consortium of national and international organisations led by Chemonics through a local programme team.2 Pillar 2 focused on raising awareness and building momentum on anti-corruption and governance reforms, and it was led by the Centre for Public Integrity (CIP)3, the Mozambican chapter of the NGO Transparency International. CIP delivered this work through research, investigative journalism and evidence-based advocacy.
[note] For details on the work of POTENCIAR, see their website: Our Mission - Programa POTENCIAR
[note] For details, see Mozambique - Transparency.org
Both pillars delivered their activities while adapting to a very challenging operating context. TACID’s flexible approach was particularly suitable for a fluid context where partners worked through the COVID-19 pandemic (2020/21), two electoral cycles in Mozambique (2018/19 and 2023/24), HMG organisational changes and reduced ODA programme budgets.
POTENCIAR’s collaborative approach, which championed ‘working with’ local and national partners, instead of partners ‘working for’ them, piloted cost-effective initiatives that led to greater inclusion, efficiency and effectiveness of basic health services while demonstrating new ways of working that, if implemented at scale, could have a positive impact in the quality of health services across the country. These efforts included (for a full list of results, see annex 6):
- Provision and rolling out of leadership and management training to all district health directors in the province of Nampula, and to all health centre directors in two districts of the province (Nampula and Monapo), which received positive feedback from beneficiaries, service users, and authorities, who recommended the training should be replicated across the country;
- Rolling out of peer learning and sharing of best practices between district health services, which helped embed the idea of ‘local solutions to local problems’ and promoted cost-effective responses to service delivery constraints;
- Strengthening of health committees and the establishment of local grievance redress mechanisms (GRM) platforms for users, which helped address issues of poor staff performance and mistrust and improved the relationship between users and service providers.
- Spearheading and supporting a national campaign against obstetric violence –pioneering work on this area led to the drafting of the country’s first bill against obstetric violence and its submission to Parliament.
CIP, in turn, strengthened its position as the country’s leading civil society organization on anti-corruption, transparency and integrity issues. Since 2019, CIP’s investigative journalism and evidence-based advocacy contributed to at least 23 policy and institutional changes, including on (for details, see annex 5):
- Improvements to the country’s penal code;
- Changes to the female prison system to better protect inmates from sexual abuse;
- Changes to procedures for the attribution of nationality/citizenship to foreigners;
- Improvements to the country’s management of its natural resources through a new legal framework.
Major lessons learned, evidence generated and recommendations
LESSON#1: Unpredictability of funding (ODA) presents a major challenge to innovative programme delivery and working effectively with local organisations. Budget reductions negatively impacted on POTENCIAR’s and CIP’s ability to meet the original ambitions of the programme.
LESSON#2: Be bold and ambitious on programme objectives but ensure these are proportionate to the scale/size of investment envelope – and if cuts affect investment, downscale ambitions. The programme’s financial resources were limited, and hence its original goals probably unrealistic from the onset – even more so when budget cuts drove a focus on a proving and an area. Programme teams could have downsized outcome and impact objectives earlier in the programme delivery cycle.
LESSON#3: Achieving scale and replicating locally led achievements needs time and strong linkages to larger investors/investments and broader policy-dialogue. POTENCIAR’s impact and policy influence could have benefited from stronger linkages with World Bank, Global Fund and Ministry of Health from the start of the programme. FCDO and partners need to agree early on joint advocacy strategies.
LESSON#4: Avoid jargon and communicate clearly about the impact and results of the programme – not the process/methodology. POTENCIAR’s efforts on so-called multi-stakeholder initiatives drew on an agreed methodology to drive change – and most of its comms and reports focused on the methodology and process, which were rather jargon-laden, not its results, which quite practical, real-life stories of change.
LESSON#5: Collaboration across government, civil society and other partners can work and deliver results – but fostering a common agenda is critical. POTENCIAR’s work demonstrated the potential of collaborative approaches to address collective action problems (mistrust, lack of coordination) and help improve service delivery. Results underlined that, once issues of common concern are jointly identified and agreed on, government institutions, civil society organisations, private sector actors and development partners can work together to design and implement cost-effective local solutions.
LESSON#6: Resources do not drive change on their own – but they remain important, particularly in contexts of extreme financial scarcity. Lack of resources is not the only, and sometimes not the main, constraint to improvements across basic service delivery, transparency and accountability – and both CIP and POTENCIAR showcased that change can happen with limited resources. However, both civil society and governments, particularly local governments, often need some additional support to drive governance and service delivery improvements – without that, civil society organisations can barely operate, as they do not have their own sources of revenue, and service providers struggle to scale up new practices and change behaviours, particularly in a context where public resources remain highly centralised.
LESSON#7: The political context shapes what is possible. POTENCIAR’s outcomes were deeply influenced by factors beyond its control — from centralised budgeting and incoherent decentralised governance structures to weak infrastructures and the country’s fragile political situation. Election cycles opened and closed spaces for action. Programmes must understand and adapt to the political economy and structural realities they operate in.
LESSON#8: Effective partnerships build legitimacy through trust and local relevance. POTENCIAR’s credibility came from being low-profile, non-partisan, and rooted in partnerships. The programme’s role as a trusted, neutral intermediary was vital in facilitating collaboration, driving innovation and helping reforms, especially when the programme supported the generation and use of appropriate evidence.
LESSON#9: Inclusion and recognition drive local ownership. POTENCIAR’s partners were motivated by shared goals around maternal and child health but also training and recognition fo their work (e.g. t-shirts, certificates, invitation to policy events). Inclusion and recognition fostered stronger engagement and sustainability of local accountability efforts.
LESSON#10: Framing matters for mobilising support and action. Reframing complex or sensitive issues — e.g. moving from addressing “obstetric violence” to efforts for “humanisation”, which is a common theme within the health sector - helped build broader support and shared ownership. Positive framing can unlock engagement and depoliticise contentious issues.
LESSON#11: Invest in existing local accountability actors and structures instead of creating new/parallel structures. Local oversight bodies, such as health user committees and provincial inspectorates, often lacked resources rather than commitment to carry out their work. Small investments on their work and stronger links with community actors helped them deliver on their priorities and ensured sustainability of efforts. Supporting and connecting existing accountability structures, instead of creating new ones, enabled them to function more effectively.
LESSON#12: Advocacy campaigns can contribute to change – but evidence, political context, popular support, and partnerships matter. CIP carried out several advocacy campaigns, but only some of them led to tangible results (for details, see annex 5). This was the case with the hidden loans, whose campaign gained momentum with the change of government and joint pressure from international partners; and the investigation around sexual abuse in the female prison of Ndavela, which was very well evidenced,made the national news and then got significant traction with the government. Also, CIP’s efforts to showcase best-practices from mining companies led to greater transparency across the sector, illustratrating that positive incentives and partnerships can also drive improvements in policies and behaviours.
RECOMMENDATION#1: Mainstream inclusion: Ensure governance programmes are inclusive and participatory, engaging a broad range of stakeholders, including marginalised communities and grassroots organisations, to enhance the legitimacy, ownership and sustainability of these initiatives.
RECOMMENDATION#3: Support incremental changes: Recognise the value of small, incremental changes in governance practices. For example, supporting initiatives that promote knowledge sharing and peer learning can drive meaningful progress in governance and accountability.
RECOMMENDATION#4: Activate flexible funding mechanisms: Donors should develop innovative funding mechanisms and models that allow for programme adjustments based on real-time monitoring and learning. These should allow budget flexibility and give managing agents scope to be responsive and proactive in supporting partners to overcome barriers to change.
How this report was conducted
This review was led by TACID’s Senior Responsible Owner/SRO, with the support of the programme officer. The review team, which also led previous annual reviews of the programme, assessed reports and talked to beneficiaries, implementing partners and other stakeholders at national level. The team also carried out a field visit to Nampula, including Monapo district, where we met and discussed with government authorities, programme partners, beneficiaries, and local communities. Finally, other BHC Maputo staff provided inputs and quality-assured the document: Health Adviser; Economics Adviser (VfM); Team Leader, Political, Governance and Comms/PGC team (quality assurance).
Actions following approval of this report
Most of the final steps for closing the programme have already been completed.
- All payments have been made. There are no unspent funds to recover.
- Final audited statements have been received.
- All programme assets have been properly disposed of, with no major issues found during checks.
- Once approved, the PCR will be published on DevTracker.
- CIP’s purchase order has been closed. POTENCIAR’s will be closed by the end of June.

## B: Theory of Change and Outcome Assessment (1-2 pages)

	Starting point	Final result (spend)
Budget	Up to £ 10 mln	£ 7,589,050
Timeframe	1st April 2018 – 31st March 2024	01st March 2018 – 31st March 2025
Outcomes	Increased government transparency, accountability and responsiveness to citizen demands, including through better allocation of resources and more inclusive planning and decision-making processes.	International indices, surveys and indicators suggest small improvements in human development, but limited progress on anti-corruption, transparency and accountability. / Programme reports documented several cases of success on anti-corruption, accountability and service delivery, which are often not captured through international indices/surveys.

Overall assessment of programme outcomes, sustainability and VfM
At impact level, programme results were mixed. On human development, Mozambique’s Human Development Index increased gradually since the start of the programme – though the country’s ranking has barely changed from the bottom of the world’s 10 least developed countries. Meanwhile, perceptions of corruption, as measured through Transparency International’s Corruption Perception Index (CPI), fluctuated at the margins over the period, returning to the baseline score by the end of the programme.
[note] For details, see: Specific country data | Human Development Reports
[note] CIP is the national chapter of Transparency International (TI). The corruption perceptions index (CPI), however, is compiled independently by TI’s HQ – the local chapter is only consulted in the process. CPI’s index assesses countries’ integrity from 1 – totally corrupt to 100 – zero corruption.
[note] For details, see: Corruption Perceptions Index 2024 - Transparency.org
Human Development Index
	2023	2022	2021	2020	2019	2018	2017 / (Baseline)
HDI score	0.493	0.490	0.478	0.477	0.475	0.469	0.461
Rank	182						183
	0.462 / (Target)

Corruption Perceptions Index
	2024	2023	2022	2021	2020	2019	2018	2017 / (Baseline)
CPI score	25/100	25/100	26/100	26/100	25/100	26/100	23/100	25/100
Rank	146	145	142	147	149	146	158	153
	33/100; / 145/180 / (Target)

At outcome level, results were also mixed. For high-level governance indicators, which were drawn from Mo Ibrahim’s Index of Africa Governance, results were disappointing – with very little improvements in citizens’ perceptions of the government’s work on anti-corruption, accountability and service delivery. On more specific indicators, which were drawn from partner reports, results were more promising – with both CIP and POTENCIAR contributing to important changes in their respective areas of work. CIP documented at least 23 cases where its work led to policy, legal or institutional changes (for details, see annex 5). POTENCIAR also documented 18 instances where the programme’s work led to significant changes (for details, see annex 6).
Both pillars of the programme carried out external evaluations in 2023. POTENCIAR’s evaluation recognised the impact and results of its approach, particularly on driving low-cost interventions that improved health sector governance and led to more inclusive and effective health services where implemented. However, it also acknowledged that replicating and scaling up these approaches was likely to demand additional resources, which, even if minimal, would be challenging for cash-constrained local governments. CIP’s external evaluation recognised the impact of their work on anti-corruption; however, it also stressed the need for the organisation to consider different approaches to address complex governance and corruption problems that do not always respond to traditional advocacy. Both partners took on board these recommendations – POTENCIAR changed its ways of working for the remainder of the programme, while CIP introduced changes to its approaches for the new Strategic Plan (2024-2034).
Both CIP and POTENCIAR placed great emphasis on the sustainability of their approaches and results. During the final year, POTENCIAR worked closely with government partners to enable them to take ownership of, and to anchor, improvements in their internal plans and processes. Ongoing interest by the international community’s Health Partners Group (HPG) in POTENCIAR’s cross-sectoral approach can further enhance the programme's achievements and value for money. As for CIP, legal reforms, policy and structural changes are locked in and will outlive the programme. And the organisation will continue its work with funding from other partners – though will likely reduce the scope of its work if no further funding from the FCDO is available.
On TACID’s Value for Money/VfM, the programme delivered significant returns to the UK’s investment. POTENCIAR’s approach of fostering partnerships across society to design and implement local, cost-effective solutions to concrete problems is particularly suited to a moment where internal and external funding sources are scarce. Health authorities in Nampula, which were badly hit by cuts to foreign aid, can already pivot to some of POTENCIAR’s approaches to mitigate the impact of those funding cuts. And these approaches can be replicated across the country without significant costs to governments and civil society. CIP’s work, in turn, not only uncovered serious malpractice, wrongdoing and abuse of office, which will surely have a deterrent effect across society and reduce waste of public resources, but also contributed to policy and institutional reforms that will increase government revenue collection, particularly from the extractive industries.
Detailed progress on outcomes is summarised in the below table:

Outcomes	Indicator	Targets / (24/25)	Results	Progress
Main outcome / Increased government transparency, accountability and responsiveness to citizen demands, including through better allocation of resources and more inclusive planning and decision-making processes.	Perceived improvements in state performance on anti-corruption and service delivery efforts (POTENCIAR+CIP)	Accountability: 60.5 / A/C: 51.5.	Acc: 53.9. / A/C: 34.3.	NOT MET. On indicators about perceptions of improvements on accountability and anti-corruption, the programme did not meet its targets.
		Health: 62. / Education: 59. / SP: 57	Health: 50.2. / Education: 65.2. / SP: 39.1.	NOT MET. On indicators about perceptions of improvements on service delivery, the programme only met its target for education, which, in the end, was not the programme’s area of work – for health, the programme was far from the target.
	Number of cases and degree of policy, legal and institutional changes achieved through evidence-based advocacy led by CIP.	14 cases	23 cases	EXCEEDED. Over the programme period, CIP’s advocacy, investigative journalism and awareness raising activities contributed to important policy, legal and institutional changes in the country. For details, see annex 5.
Intermediate outcomes / Collaboration: ‘Improved collaboration and coordination amongst key actors at provincial or district level enhances ways of working and the efficient/effective use of resources available for inclusive, humanised health service delivery’	Number of significant changes (SCs) in collaboration between key actors at provincial or district level that enhances ways of working and the efficient/effective use of resources available for inclusive, humanised health service delivery to which POTENCIAR has made a distinct contribution	4 SCs	5 SCs	EXCEEDED. In total, POTENCIAR contributed to 5 significant changes and 1 partial significant change. There were 4 significant changes during Years 1-3; and 1 significant and one partial change during Year 4. For details, see annex 6.
Empowerment: ‘Empowered health service providers at district or facility level and community users hold each other accountable and benefit from provision of humanised health services’	Number of significant changes in accountable or humanised health services resulting from empowered users, providers or district level staff to which POTENCIAR has made an important contribution	4 SCs	3 SCs	PARTIALLY MET. In total, POTENCIAR contributed to 3 significant changes and 1 partial change. There were 3 significant changes in years 1-3, and a partial change during Year 4. For details, see annex 6.
Influencing national policy and practice: ‘subnational policy and advocacy initiatives contribute to reformed laws and/or policies, as well as cross-sectoral practices towards humanised and accountable health and other service areas’	Number of significant changes in humanised or accountable health care policy (new policy or implementation of existing policy) to which POTENCIAR has made a significant contribution	3 SCs	6 SCs	EXCEEDED. POTENCIAR contributed to 6 significant changes in total — 3 significant changes in years 1-3, and 3 during Year 4. For details, see annex 6.
`Reformed laws, policies or practices towards increased collaborative or humanised service delivery and accountable governance	Number of significant changes in collaborative or humanised service delivery and accountable governance that sustain elements of the POTENCIAR vision and approach	3 SCs	4SCs	EXCEEDED. POTENCIAR supported 4 significant changes in its extension year. For details, see annex 6.
[note] Moh Ibrahim Index of African Governance, Transparency and Accountability - Public Perceptions on Accountability and A/C, and Perceptions on health, education and social protection.. For details: Ibrahim Index of African Governance (IIAG) Data Portal | Mo Ibrahim Foundation
[note] This indicator assesses the extent to which citizens feel that the head of the executive does not ignore parliament, as well as the extent to which citizens feel that officials who commit crimes are punished.
[note] This indicator assesses the extent to which citizens feel that the head of the executive, members of parliament and the police are not involved in corruption, the extent to which citizens feel that they do not need to bribe government officials in exchange of administrative services, as well as citizens' satisfaction with how the government is doing at fighting government corruption.
[note] This indicator assesses the extent to which citizens are satisfied with how the government is doing at improving basic health services and at providing water and sanitation services, as well as citizens' perceptions of how easy it is to obtain the medical care they need.
[note] For POTENCIAR’s monitoring framework, ‘significant change` means: ‘new capacities, opportunities, or motivations in actors contributing to increased transparency, accountability, and responsiveness within health service delivery.’ The programme reported on significant changes to which POTENCIAR was assessed to have made a contribution.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.
The Business Case proposed a Theory of Change (ToC) that evolved to respond to analytical findings, shifts in the context and programme learning, though there were no changes to impact and outcome statements (for details, see annexes 1/4). TACID’s pillars delivered on different aspects of the theory of change – POTENCIAR explored the space(s) for greater ‘collaboration’ and ‘partnership’ between government and citizens, while CIP focused its work on unpacking citizen’s demands/grievances through research and investigative journalism and seeking accountability for these demands/grievances through ‘advocacy’ and ‘critical engagement’. In practice, after the inception period, POTENCIAR took a narrower approach to its work, focusing its activities in the health sector, on issues related to maternal and child health, and working in the province of Nampula. POTENCIAR’s initiatives were called ‘Pro-Accountability Initiatives’/PAIs, which ranged from improving the work of health training institutes to rolling out grievance redress mechanisms. After an external evaluation in 2023, POTENCIAR shifted from Pro-Accountability Initiatives (PAIs) towards the promotion of ‘Humanised Healthcare’, with a focus on three areas: Collaboration, Empowerment and Policy Influencing. This change took onboard most of the work that had been done through the PAIs but reframed the approach. For CIP, the organisation retained its focus on research, advocacy and policy engagement throughout implementation – though the external evaluation led to changes to CIP’s new Strategic Plan (2024/2034).
In line with the Theory of Change, TACID’s results framework also evolved over the years. POTENCIAR added intermediate outcomes to better capture the results of their work. These intermediate results initially focused on measuring the impact of the programme at district, provincial, national and international level, and later changed to capture the results of the three new workstreams: collaboration, empowerment and policy influencing.
At output level, indicators changed to respond to changes in approach and focus throughout implementation – particularly for POTENCIAR. As already discussed, POTENCIAR initially piloted multi-stakeholder initiatives to address health governance challenges – the Pro-Accountability Initiatives (PAIs). POTENCIAR’s five PAIs focused on: PAI 1: Improvement of grievance redress mechanisms related to maternal services in health units; PAI 2: Joint working between health authorities, non-governmental organisations (NGOs), community-based organisations (CBOs), and community radio stations involved in the provision of maternal health services; PAI 3: Improvement in the quality of education of health professionals and supervision provided to health training institutes; PAI 4: Cross-sector health/social protection; PAI 5: Inter-sectoral platform to share good practice on grievance redress mechanisms. After the 2023 external evaluation, these multiple efforts were streamlined into a ‘Humanized Service Delivery’ approach – with three workstreams around ‘collaboration’, ‘empowerment’ and ‘influencing’. This approach was implemented until the of the programme.
For the one-year extension period, POTENCIAR’s focus was to ensure the ownership of their approach and programme results by local partners – and this is reflected in the ‘Detailed Output Analysis’ section below. For previous output indicators, our assessment of performance and progress towards their milestones and targets was captured through annual reviews from 2018 to 2024. For this Project Completion Review/PCR, the team only looked into progress on outputs for the programme’s extension year – April/24 to March/25.

## C: Detailed Output Assessment

Output Number and Title		Evidence and resources for strengthening institutional capacities to deliver humanised services consolidated and disseminated (POTENCIAR)
Output Score		A
Impact weighting (%)		25%	Impact weighting revised since last AR?	N/A

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
Number of training and management support resources introduced to key stakeholders.	New Indicator for year 4 (extension year)		3	MET. 5 / Four resources were handed over to Nampula’s Health Provincial Directorate and one to non-state actors.

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.
This assessment covers activities and results of the extension period – April/24 to March/25. Progress on previous outputs (2018/2024) was assessed through annual reviews, as per information above (Section B).
Output indicator 1.1 assesses the results of POTENCIAR’s efforts to document its approaches and then anchor them into local and national processes – driving ownership and sustainability. During the review period, POTENCIAR exceeded its target and concluded the handover of four management resources to Nampula’s Health Provincial Directorate, and one to provincial non-state partners:
1. A ‘humanisation’ checklist for the Provincial Directorate’s health inspections. POTENCIAR developed the checklist to be used as an attachment to the official inspection guidelines for the health sector. The checklist was finalised following reviews by the Health Directorate Inspection and Health Directorate Humanisation units, as well as by the General Health Inspection gency at national level (IGAP).
2. A flow chart of the grievance redress mechanisms processes at health facility level. The flow chart is expected to facilitate registration and follow-up on grievances at the health facility level. To ensure relevance and utility, the tool was co-created with the Provincial Health Directorate staff who provided several rounds of feedback on drafts following a mapping of existing materials
3. Training manual on leadership and humanisation. Nampula’s Provincial Health Directorate led the drafting of the training manual for the humanisation of district health providers and is currently expanding the document to add two further modules on financial management and human resources (HR) before it is finalised for roll out at scale.
4. Guidelines for the future organisation and consolidation of cross-sectoral planning processes at district, provincial and national levels.
5. GESI guidelines for non-state partners. These were developed to support replica training of the guidelines.
Lessons learned through this output, and recommendations for future programming
See summary above (Section A).

Output Number and Title	Influence evidence-based public policy and programme planning through collaboration on humanised service delivery and accountable governance (POTENCIAR)
Output Score	A
Impact weighting (%)	25%		Impact weighting revised since last AR?	N/A

Output Indicator		Starting Target	Final Logframe Target	Final Result Achieved
Diversity of groups whose concerns are incorporated into advocacy and/or collaborative activities		New Indicator for year 4 / (extension year)	2.50 / (out of 4)	MET / Average of diversity and inclusion scores: 3 / Average diversity: 3.1 / Average inclusion: 2.9
For advocacy: Number of POTENCIAR initiatives with meaningful engagements by policymakers and practitioners (with POTENCIAR evidence and learning on humanised service delivery and accountable governance)		New Indicator for year 4 / (extension year)	4	MET / 5 initiatives.
Bill against obstetric violence submitted to parliamentary committee		New Indicator for year 4 / (extension year)	Bill submitted	MET
[note] Measures average quality of advocacy and collaboration using a 1-4 scoring tool according to criteria a) Are a wide variety of actors engaged in collaborative and advocacy initiatives (i.e., Civil society, government, private sector etc.) particularly with the presence of state actors at all levels? b) Do the collaborative and advocacy initiatives include marginalized voices, and address aspects of the issue/problem which are most important to marginalized groups (determined through civic engagement activities, ethnographic research, third-party research)? Data is gathered thorught beneficiary feedback and interviews.

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.
This assessment covers activities and results of the extension period – April/24 to March/25. Progress on previous outputs (2018/2024) was assessed through previous annual reviews, as per information above (Section B).
Output indicator 2.1 assesses the diversity and inclusion of local voices into POTENCIAR’s work – looking into five of its latest initiatives:
1) Citizen manifestos for electoral process. The collection of citizens’ views on healthcare issues to include in party manifestos and debates took place in 9 districts. At least 38% of focus group discussions included a suggestion from a participant from a marginalised group, and 56% of manifesto focus groups were conducted in very rural districts.
2) Provincial seminar on ‘Health’s Holistic Vision’. This conference on multisectoral approaches to health, organised by the Health Provincial Directorate, included representatives from diverse organisations. Participants evaluated the diversity of groups as relatively high (3.3/4) but noted that inclusion was less good (2.3/4), with little representation of district-level or community organisations and district-level administrators.
3) Workshop with the Superior Institute of Health Sciences (ISCISA) and the National Directorate of Training of Health Professionals (DNFPS) on the adoption of deontological and ethics modules in national training curricula. Some participants felt that more vulnerable voices could be better represented, and evaluations scored the diversity of participants as 3.5 and inclusion 2.5.
4) Draft law against obstetric violence. 18/21 partners responding to an assessment of the HumanizaMoz campaign provided an average score of 2.9 out of 4.
5) Grievance Redress Mechanism Platform. In a partner assessment during Year 4/Quarter 3, participants rated diversity as good but again remarked on the challenges of meaningful inclusion.
Output indicator 2.2 assesses POTENCIAR’s efforts to consolidate and disseminate its work/results on humanised service delivery with policymakers and practitioners. The programme reported 5 such initiatives:
1. Experience sharing for improving health training curricula. The Health Training Institute (ICS) shared their learning and positioning on the importance of deontological modules in curricula for students with ISCISA and National Department for Training of Health Professionals (DNFPS) of the Ministry of Health (MISAU). The DNFPS welcomed their position and MISAU acknowledged a separate letter of recommendation. More follow-ups will be needed to advance this agenda
2. Elections’ Health Citizens Manifesto. This was drafted based on evidence of citizens’ priorities, some of which had been influenced by their engagement with the POTENCIAR programme. The citizens were supported to participate in a debate where political candidates engaged with their recommendations. The process provided a rare opportunity for some of the citizens’ representatives to engage directly with politicians.
3. Multi-stakeholder consultations on the cross-sectoral grievance redress mechanisms/GRM platform. This built on previous POTENCIAR research and learning on the role that GRMs play in improving health services. All parties agreed that the platform was relevant and should be hosted by a national NGO, with some external oversight. This group decided that the health component would be integrated within an existing education GRM managed by the Mozambican NGO CESC.
4. Training of district partners on Gender, Equality and Social Inclusion (GESI). This involved NGO partners and health practitioners engaging in ways that should institutionalise more gender aware and inclusive practice in the health sector.
5. Holistic Vision Conference organised by the Nampula’s Provincial Health Directorate. The event was well attended by government officials, academics, and some policymakers. It created a space for discussion and engagement on the importance of a cross-sectoral approach to health system designs in line with existing government policy and POTENCIAR’s previous advocacy. Following the conference, POTENCIAR supported the Provincial Health Directorate in taking forward its recommendations.
Output indicator 2.3 assesses the results of POTENCIAR’s work on the bill to prevent and address cases of obstetric violence. On this, the programme reported that the HumanizaMoz campaign presented the Bill to Parliament, which is an important milestone in the campaign for the approval of the law.
Lessons learned through this output, and recommendations for future programming
See summary above (Section A).
Output Number and Title	POTENCIAR evidence and learning contribute to discussions with partners on how to sustain the programme’s approach to humanised service delivery and accountable governance (POTENCIAR)
Output Score	A
Impact weighting (%)	20%		Impact weighting revised since last AR?

Output Indicator		Starting Target	Final Logframe Target	Final Result Achieved
Number of quality evidence products generated by POTENCIAR of its contribution to humanised service delivery and accountable governance		New Indicator for year 4 / (extension year)	3 products with quality score of 2.5 or more	MET. / Number of products: 4. / Quality: Score of 3.
Number of products documenting or communicating the POTENCIAR governance model		New Indicator for year 4 / (extension year)	3	MET. / 5 products.
For the sustainability and/or uptake of the POTENCIAR approach: Number of partners with whom POTENCIAR have had meaningful engagements on evidence and learning on humanised service delivery and accountable governance		New Indicator for year 4 / (extension year)	2	MET / 2 partners
[note] Measures average quality of evidence in terms of the following criteria: voice and inclusion, appropriateness, triangulation, contribution, and transparency. Measurement made with reference to a scoring tool where 1-4 scoring tool where 1 is low quality and 4 excellent quality. See MREAL strategy for details of the scoring tool.

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.
This assessment covers activities and results of the extension period – April/24 to March/25. Progress on previous outputs (2018/2024) was assessed through previous annual reviews, as per information above (Section B).
Output indicator 3.1 assesses POTENCIAR’s work to disseminate lessons from the programme’s implementation, ensuring that other partners, national and international stakeholders draw on its experience to further support improvements to health services. POTENCIAR completed and disseminated four studies in the review period:
1. A Political Economy Analysis (PEA) on collaboration in the health sector in Nampula province, which scored 3.1 for quality. The PEA examined how brokering and convening approaches can shift power dynamics and foster collaboration amidst challenging political and economic contexts. Through six detailed case studies, it illustrated how incremental trust-building efforts can establish new ways of working that improve governance and service delivery, even in resource-constrained environments. The report included details of factors that help and hinder collaboration, along with implications for different actors. These informed a policy brief.
2. The baseline and endline studies to assess the impact of the Training of Trainers for Health Directors, which scored 2.9 out of 4 and 3 out of 4 for inclusion and quality respectively. The endline report found that those trained by directors (replica training) exhibited more inclusive attitudes.
3. A study conducted by the Academic Association of Nutrition and Food Security (ANSA) assessed safeguarding mechanisms against sexual exploitation and abuse and sexual harassment (SEAH) within a sample of four of the eight districts covered by the UNFPA Family Planning project, which is a FCDO-funded programme. This report scored 3.6 out of 4 on the quality assessment.
4. A desk-based study of the Grievance Redress Mechanisms Platform was not scored, as the scoring tool which focuses on criteria such as voice and inclusion was not appropriate for the methodology.
Output indicator 3.2 assesses POTENCIAR’s efforts to document its ways of working and approach. POTENCIAR produced 5 products:
1. A note on the advocacy trajectory of POTENCIAR. This product discusses POTENCIAR’s approach to supporting the HumanizaMoz Campaign, from conceptualisation to operationalisation
2. A note on POTENCIAR’s citizen engagement and empowerment approach. This product is a personal reflection by a staff member on the approach.
3. A video documenting the POTENCIAR collaborative model. This product includes partners’ reflections on the POTENCIAR approach, its achievements as well as the programme’s legacy.
4. A policy brief on collaborative practices for development partners.
5. A policy brief on collaborative practices for policymakers in Mozambique.
Output indicator 3.3 focuses mainly on engagements that sought to sustain support for initiatives that are part of the approach established by POTENCIAR.
1. USAID/LOGOS programme. Members of the LOGOS programme engaged positively with findings and frameworks from the Study on Collaboration and PEA. POTENCIAR had anticipated this would lead to continued discussions and engagement before the USAID stop work order.
2. BHC and members of the Health Partners Group provided helpful critical feedback on the PEA Collaboration study. These partners included Canada cooperation and aid (CA), GIZ, Government of Flanders, UNICEF, World Bank Global Fund, Path, N’weti, and Village Reach, among others.
Lessons learned through this output, and recommendations for future programming
See summary above (Section A).
Output Number and Title	Increase public debate on transparency, accountability and corruption with greater scope and visibility (CIP)
Output Score	A
Impact weighting (%)	30%		Impact weighting revised since last AR?	Yes, from 25% to 30%

Output Indicator		Starting Target	Final Logframe Target	Final Result Achieved
4.1 Uptake of CIP reports by media, civil society and other stakeholders as measured by: / A. # of times CIP’s work is disseminated through mainstream media (newspapers, TV, radio) / B. Number of visitors to CIP’s website; / C. Number of social media followers (Facebook, Twitter e WhatsApp) / D. Quality of reports (as per beneficiary feedback, between 0-10). / E. Number of engagements on social media (Facebook)		N/A	TV: 80. / Radio: 40. Newspaper: 60. / 150.000; / FB: 50,000; / Linkedin: 32,000; WhatsApp: 32,000; / 8 / 200,000	EXCEEDED / TV: 51. / Radio: 331. / Newspapers: 60. / 505.072 / FB: 76,000; / Linkedin: 41,996; / WhatsApp: 32,000. / 9 / 1,200,000
4.2 Number of times government officials and private sector actors respond to advocacy work		90 / (cumulative from 2019)	90 / (cumulative from 2019)	180 / (30 in 2024)
[note] Milestones were agreed with CIP at the start of the review period – for example, early in 2024 for that year. No end of programme target was agreed on as CIP’s work and the implementation of their Strategic Plan continues beyond the lifetime of this programme.
[note] When this is not explicitly noted, data/targets refer to information from 2024 only, and are not cumulative of all implementation years.
[note] CIP puts together a media clipping, which illustrates how their work has been referenced in the media; however, it doesn’t give evidence of all instances.
[note] CIP’s beneficiary feedback survey asked 33 key informants about the quality of CIP’s work – 90% said they were happy or very happy with the work.

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.
Throughout our partnership with CIP, the organisation delivered high-quality and high impact work with an even greater effort on public outreach through social media. CIP’s publications are reaching a wide audience through different channels, including a new podcast, the CIPCAST, whose episodes have reached thousands of people across the country. Feedback gathered by the organisation highlighted the quality and relevance of its work. As proposed in the programme’s theory of change, CIP’s investigative journalism, advocacy campaigns, policy research and partnerships have contributed to government and private sector responsiveness and engagement with civil society. In 2024, CIP documented at least 30 instances where there was a response/follow-up from public authorities and private sector to their work. Since 2019, there were around 180 instances of government and private sector response. Below, some examples of this work in 2024:
CIP’s advocacy	Government/Private sector response
CIP published the 4th report of its Extractive Sector Transparency Index	Kenmare started publishing on its website the financial reports, the reports of tax payments made to the government, sustainability plans, updated environmental reports and the project development plan. / SASOL has requested that the CIP be part of the design of the Local Development Agreement (ADL) for the next five years (2025 to 2029)
CIP investigated and published an article on mining in the district of Búzi, Sofala Province	The Provincial Assembly of Sofala requested the signing of a memorandum of understanding with CIP, which was signed on July 2024
Advocacy for the approval of a national sovereign fund law	As a result of CIP's advocacy work on the sovereign wealth fund, CIP was invited by the Minister of Finance to be part of the discussion group on the regulation of the Sovereign Wealth Fund Law. And Parliament included civil society in the legislation as part of the governance structure of the sovereign wealth fund.
Advocacy on public procurement	CIP is part of the review team of the decree on public procurement, at the invitation of the Ministry of Finance.
Investigative journalism on public procurement	CIP investigated and exposed the case of Zohra Limited, which in about 4 years invoiced at least £4 million in contracts with public entities in the city of Tete. Now the company's CEO has been arrested, being under suspicion of money laundering.
Advocacy on anti-corruption	At the request of the Assembly of the Republic (AR), CIP provided comments to the Draft Law for the Revision of the Public Probity Law.
Advocacy on public-private partnerships	DP World, the largest shareholder of MPDC, the concession company for the operation of the port of Maputo, invited CIP to participate in the process of carrying out environmental studies as part of the expansion of the area of the port of Maputo.
Investigative journalism on environmental crimes committed by the Haiyu mining company in Nampula.	The Ministry of Environment began engaging with the CIP through invitations to participate in national meetings on environmental issues and a roundtable on carbon credits.
[note] Most papers are available on CIP’s website: Pagina inicial - CIP - Centro de Integridade Pública (cipmoz.org)

Lessons learned through this output, and recommendations for future programming
See summary above (Section A).
D: Value for Money
VfM performance compared to the original VfM proposition in the business case
The original value for money proposition in the business case was that by combining social accountability and advocacy on anticorruption, transparency and accountability, TAcID would achieve a set of benefits associated with both approaches. Expected benefits included: improving the quality of services by strengthening provider capacity; enabling citizen engagement with providers; reducing leakages of drugs and other materials and misuse of public goods; better behaviour of public officials; increases in use of services; reporting and redress of corruption practices; prevention of corruption/mismanagement through exposure/deterrence; recovery of misappropriated goods/resources.
Regular assessments throughout programme implementation concluded that the programme delivered good value for money.
CIP did not develop specific VfM metrics, but its positive impact in the country far exceeded our investment, with several cases of corruption and human rights abuses exposed, addressed and under investigation by authorities. CIP is also fully staffed by Mozambicans, which reduces its costs (economy). Staff are effective through high quality work, as evidenced by beneficiary feedback (efficiency). And their advocacy delivers results and support governance reform processes (effectiveness): with legal, regulatory and institutional changes and cost-saving measures.
POTENCIAR developed detailed VfM metrics, as per below assessment. The programme met or exceeded all its outputs and contributed to its outcomes with the approved investment. And it has delivered on its value proposition with a good performance on effectiveness.
Economy: VfM performance in this category was good. Throughout implementation, POTENCIAR’s measured its performance on economy indicators based on the cost-ratio of short-term and long-term technical assistance; of administrative to programme expenditure; and of national to international consultants. Throughout the period, programme costs averaged 2/3 of programme expenditure; more than 90% of consultants were national; and more than 2/3 of consultants were long-term consultants.
VfM Economy indicators, Years 1/4
Cost ratio administrative to programme expenditure	Inception	Year 1	Year 2	Year 3	Year 4	Average
Administrative expenditure	35%	23%	34%	34%	35%	32%
Programme expenditure	65%	77%	66%	66%	65%	68%
Cost ratio national to international consultants
National consultants	90%	88%	96%	92%	98%	93%
International consultants	10%	12%	4%	8%	2%	7%
Cost ratio short-term to full-time technical assistance
Short-term technical assistance	75%	18%	28%	24%	17%	32%
Full-time technical assistance	25%	82%	72%	76%	83%	68%

Efficiency: POTENCIAR performed well on criteria for judging the efficiency of adaptive programmes. For years 1-3, POTENCIAR recorded several examples of efficiency as commonly defined in adaptive programmes, and as documented in previous annual reviews. For year 4, POTENCIAR measured efficiency in delivery in its use of resources to achieve outputs with a different set of criteria:
Criteria	Progress
a) Less than 50% of resources (level of effort/LOE) for research products is resourced externally	In the final quarter of year 4 (Jan/March 2025), externally sourced LOEs for research products were 26%. POTENCIAR anticipates the average remained below 50%.
b) Other development partners and governments contribute to funding to POTENCIAR events	For the Holistic Vision conference in Nampula, POTENCIAR provided 55% of the budget of £40k. The rest of the budget was covered by 10 other partners, primarily NGOs, but also a couple of private companies. The Nampula Health Provincial Directorate contributed with human resources.
c) Resources are saved by using events/platforms coordinated by others to reach a wider audience	1) The collaboration with CSO-network PLASOC on the elaboration and dissemination of the electoral ‘citizens’ manifestos’ meant that PLASOC turned POTENCIAR’s Nampula focused-initiative into a national effort, with data collection and dissemination in 10 provinces of the country (all but Cabo Delgado).
d) Resources are leveraged through existing relationships and mechanisms established during Phase 1 to reach a wider audience or to organise/implement activities more quickly, or so that they are better quality, or so that they cost less (savings).	1) The implementation of the citizens’ manifestos in Nampula was quicker and reached more districts due to previous partnerships at provincial and district level. 2) POTENCIAR reengaged with the General Inspection of Health to support the elaboration and dissemination of a support tool for a humanised focus on health inspections.
e) Increased effective resource use through adaptation based on learning.	1) Based on the learning from the external evaluation, POTENCIAR streamlined the consortium and increased the participation of local partners

On effectiveness, the 2023 external evaluation rated POTENCIAR’s effectiveness as high. For the extension year, POTENCIAR measured effectiveness (including sustainability and equity) in its use of resources through different criteria:
Criteria	Progress
A) Partners invest in taking on the national grievance redress (GRM) platform, with the potential to benefit many citizens.	USAID-funded LOGOS co-invested in the establishment of the national GRM platform (75% of £10k) earlier in 2024. The National General Inspectorate (IGAP) committed to supporting the implementation of this platform, while the Health National Inspectorate will provide oversight, and LOGOS committed to provide continued investment in through CESC.
B) Partners commit to using POTENCIAR’s learning and evidence to take on its role and replicate the collaborative and empowering approach, ideally sustaining Health Provincial Directorate inspection visits.	Partners in Monapo district continued to work closely together through coordination on the WhatsApp group initiated by POTENCIAR. Nampula Provincial Health Directorate committed to advancing cross-sectoral planning guidelines.
C) Ministry of Health’s adoption of an improved focus on ethics and deontology modules within the health education curriculum (important for equity) is approved and funded with potential to benefit citizens	The Health Training Institute of Nampula showed commitment to implementing the module with their own budget and managed to do so in 2024. While this is not as significant as our original ambition – national level adoption – it is strong indication of the value placed on the module and its effectiveness
D) Citizens’ manifestos feature in political debate prior to the elections.	Citizen manifestos were part of the Nampula provincial debate just before the election and all candidates signed up to support them.
E) Partners take on leading the work for the approval of the Bill of Law against Obstetric Violence (OV)	CESC has funding and committed to continuing to support initiatives to advance the passing of the Bill of Law against Obstetric Violence.
F) Ministry of Health commits to continuing with POTENCIAR modules for humanised training of service providers.	The training module on humanisation for service providers was approved at provincial level in Nampula. The Health Provincial Directorate is integrating additional modules, for example on finances, before final approval and submission to the Ministry of Health.

Equity: Performance on equity was good. Throughout programme implementation, the service users who benefitted most from improvements were women and children, many of whom were very poor. The scaling up of training for health co-management committees should result in better relationships between providers, communities and users, and lead to reduced demands for illicit fees to 17of 20 very rural health facilities in Monapo and Nampula districts, which could have considerable economic as well as health impacts for very poor households. For year 4, POTENCIAR achieved equity in delivery when people from marginalised groups and remote communities participated in processes to influence electoral citizen manifestos and other advocacy and influencing activities.
E: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.
TAcID’s risk rating remained major for the past five years of programme implementation – within the programme’s and the office’s risk appetite. Throughout, the programme faced some risks that remained constant, while new risks emerged in recent years. Historical risks included: 1) The conflict in Cabo Delgado and its spread across Northern Mozambique, which added challenges to POTENCIAR’s operation in Nampula; 2) Tensions around programme coordination and alignment with the country’s agenda for decentralisation, which brought challenges to collaborative approaches at provincial level; 3) The reliance of Nampula health authorities on funding from international NGOs and resource-based partnerships – which meant that POTENCIAR’s low-cost approach faced resistance from some people at provincial level; 4) Competition for resources among community-based organisations (CBOs), which made local level collaboration more difficult; 5) Increasing backlash against/harassment of critical NGOs and their personnel – which was a significant risk to CIP’s work. In the final years, some new risks emerged: 1) Recurrent doctors’ strikes, which had a negative impact on the health sector; 2) The country’s electoral cycle, with municipal (2023) and general (2024) elections, which affected the space for policy reform and decision-making at local and national level, the operations of public services, and increased the risk of elections-related violent and unrest.
FCDO and partners monitored and mitigated these risks regularly. FCDO kept an up-to-date programme risk register, and both CIP and POTENCIAR maintained detailed risk registers. For POTENCIAR, effective risk management was part of our Key Performance Indicators/KPIs. We also followed up with CIP on the recommendations from their due diligence assessment.
F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation
Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency
Partnership Performance
The programme operated through two delivery channels: an inputs-based and payment-by-results (PbR) contract with Chemonics (POTENCIAR), and an accountable grant with the Centre for Public Integrity (CIP). Despite external shocks such as COVID-19 and budget reductions, programme partners performed well, demonstrating resilience, adaptability, and strong focus on delivery.
Chemonics (POTENCIAR) received an SSRM rating of 80% for the final review period (Oct 2024 – Mar 2025), reflecting strong responsiveness, adaptive leadership, and quality delivery. Throughout programme implementation, Chemonics fulfilled or exceeded most contractual Key Performance Indicators (KPIs) linked to technical outputs, stakeholder engagement, and MEL. However, early-stage weaknesses in risk identification and escalation were flagged by both FCDO and the 2023 SSRM review.
REDACTED
REDACTED
REDACTED
Commercial and Financial Performance
REDACTED
FCDO provided consistent oversight throughout the programme. Both Chemonics and CIP updated risks and delivery chain maps regularly, and annual spot checks were conducted on assets. Chemonics maintained strong internal controls, while CIP improved its asset register and audit compliance over time.
However, due diligence on downstream partners remained a weak area for CIP. Despite early identification of this gap in the 2018 Enhanced Due Diligence Assessment, full compliance was not achieved, and two downstream partner reviews out of three were completed during the programme. Virtual asset spot checks replaced field verifications during the COVID-19 period.
Open Book Accounting (OBA) - which allows full visibility of how budgets are spent - was implemented by Chemonics, but enforcement was delayed. Forecast challenges, staff transitions, and system upgrades slowed the early rollout. CIP was not contractually required to follow OBA, but FCDO encouraged greater financial transparency across both pillars. While CIP improved its financial reporting overtime, they did not consistently provide the detailed budget breakdowns needed to fully align with OBA principles. As a result, FCDO could not easily compare costs or assess value for money across the two delivery channels, and a joint value for money (VfM) framework for both pillars was never finalised, despite being proposed in the business case.
Programme-level approach to monitoring and evaluation
Both partners submitted regular narrative and financial reports, and by the end of the programme these were generally aligned with FCDO requirements. However, there were some challenges at the start. For POTENCIAR, the Monitoring, Research, Evaluation, Accountability and Learning (MREAL) framework was revised post-evaluation to include outcome mapping and better disaggregated data. CIP adopted simpler beneficiary feedback tools. Both were responsive to feedback from FCDO and other donors (in the case of CIP) and in the final year, both partners delivered strong results.
Lessons and Recommendations
- Earlier enforcement of due diligence standards and OBA across all partners would have strengthened financial oversight.
- Having one clear system to measure value for money across the whole programme would have made it easier to compare results and learn what worked.
- Despite good progress, downstream partner risk management and inclusion frameworks (especially for gender and disability) could have been more robust.
- FCDO could strengthen early risk escalation mechanisms and provide clearer guidance on safeguarding and fraud response.
Date of last narrative financial report	30 April 2025	Date of last audited annual statement	30 April 2025

Annex 1 – TACID’s Theory of Change, as per Business Case

Super Impact
Poverty, inequality and instability reduced
Improved service delivery and reduced corruption

Impact

Improved human development outcomes and reduced corruption

Increased government transparency, accountability and responsiveness to civic pressures, including through better allocation of resources and more participatory planning and decision-making processes

Outcomes

Mozambican citizens (women, marginalised groups, youth) are aware of their rights and entitlements to basic services
Effective, evidence-based advocacy initiatives around transparency and anti-corruption, with a focus on mobilising ‘drivers of change ’(youth)

Provincial and national ‘strategies’/coalitions for change, linking up local engagement and higher-level advocacy and involving state and non-state actors, are developed and implemented
Mozambican citizens (women, marginalised groups, youth) engage with service providers and government officials at facility and district for: (1) monitoring of service provision; (2) monitoring of budget execution/public works (3) planning and budgeting processes

Outputs

Innovative approaches and tools for civic engagement and accountability are piloted and, if successful, scaled up

National/
Provincial partners will:
a) Use evidence to support local and national level advocacy for better service delivery; governance reforms; increased transparency and accountability.
HMG officials will:
a) Use national and international platforms to further advocacy efforts on these issues;
b) Provide leadership on these issues in the international community;
c) Speak up against attempts to clamp down criticism;

Local grantees/
Mediators will:
a) Facilitate dialogue between state and non-state actors;
b) Strengthen platforms for engagement at the facility level;
c) Engage local influential actors to put pressure on providers.
d) Engage with local governments

DFID implementing partners will either:
a) Select, fund and provide capacity to local actors, including civil society and public officials, to implement civic engagement tools to deal with governance bottlenecks in service delivery; or
b) Carry out themselves research and information gathering on governance issues.
DFID implementing partners will:
a) Carry out awareness-raising and mobilisations campaigns to inform citizens and public officials about their rights and duties, paying particular attention to the needs of marginalised groups.
DFID implementing partners will:
a) Design and propose innovative solutions to civic engagement, piloting them, and when successful, scaling them up
Activities/
Inputs

Annex 2, TACID’s Theory of Change, as per revisions, 2020/2023

Annex 3 – TACID’s Theory of Change, as per revisions, 2023/2025

Annex 4 – POTENCIAR’s delivery model, 2023/2025