## ICTD Annual Review

Title: ICTD – Tax and Development: Equity, Efficiency and Accountable Governance
Programme Value £ (full life): £13,300,000.00		Review date: 30 June 2025
Programme Code: 300211-101	AMP start date: 01/10/2018	AMP end date: 31/03/2027

Summary of Programme Performance
Year	2019	2020	2021	2022	2023	2024	2025
Overall Output Score	A	A	A+	A	A+	A+	A+
Risk Rating	Minor	Minor	Minor	Minor	Minor	Minor	Minor

DevTracker Link to Business Case:	All published documents
DevTracker Link to results framework:

A. SUMMARY AND OVERVIEW

Description of programme

The International Centre for Tax and Development (ICTD) funds research to help make tax systems more equitable, efficient, and conducive to promoting economic development and strengthening governance and accountability. It is an independent tax research network run from the Institute of Development Studies at the University of Sussex in Brighton and the University of Toronto. The ICTD was established in 2010 to provide evidence on how best to strengthen taxation reform in developing countries. This FCDO support is via an Accountable Grant for the ICTD to deepen its research in Africa and develop key relationships in South Asia to initiate research there.

The expected Impact of the FCDO-funded programme is: improved developing country tax systems that support pro-poor economic growth, advance equity for poor people, increase revenue, and improve accountability.

The expected Outcome is that: high quality evidence is accessed by governments of developing countries and other stakeholders including FCDO and other donors, multilaterals, and civil society organisations, who then modify their practices, policies, or programmes.

The ICTD research is structured around three themes:

1. National tax policy and administration: comprising tax administration and compliance (including the role of digital technologies); tax and governance; tax, welfare and inequality; gender and tax; and international taxation.
2. Sub-national and informal taxation: research on the realities of sub-national and informal taxation; and analysing links between central and local government.
3. Strengthening civil society capacity on tax: (i) better understanding the role that civil society can play in supporting accountable and effective taxation, (ii) producing research in conjunction with civil society partners, and (iii) disseminating research within civil society and advocacy networks to increase the impact of our research.

The ICTD also works to strengthen the capacity of policymakers, developing country researchers, and civil society to co-produce tax research, understand tax issues and evidence, and improve policies, and to engage with those partners to translate research into concrete impact.

ICTD’s current funding is outlined in the table below:
Table 1: ICTD Funding

Amount	Funder	Dates
£13.3m	FCDO	Oct. 2018 – March 2027
US$2,249,886 (£1,704,148)	Bill & Melinda Gates Foundation (Gates Foundation)	Nov. 2022 – Oct. 2025
$3,120,000 USD / (£2,338,908)	Gates Foundation (Phase 2 focus on DPI and tax)	Oct 2024 - Sept 2027
NOK 57,248,330 (£4,280,329)	Norwegian Agency for Development Cooperation (Norad)	Dec. 2021 – Nov. 2026
US$8,381,675 (£6,488,115)	French Ministry of Economy, Norad, and Gates Foundation are active funders for LoGRI (GIZ funding is complete)	Sept. 2021 - Dec. 2027

Summary supporting narrative for the overall score in this review

This year ICTD has continued to deliver high quality research, engage across HMG and with core partners in Africa and Asia, and invest in knowledge sharing and capacity building.

Highlights include:

ICTD research and technical input informed VAT legislative reform in Senegal increasing revenue by £2.5 million in half a year. ICTD’s support to the Directorate General of Taxes and Domains in updating and implementing the Finance Act 2023 led to reforms that increased VAT revenue in the second half of 2024, with an additional 1.905 billion CFA (c. £2.5 million) raised from digital services provided from abroad.

Long term capacity building improving the Rwanda Revenue Authority (RRA) research team’s influence and impact within revenue authorities. ICTD built RRA research team’s capacity on methodologies, analytical tools, and in conducting experimental research over ten years. As a result, the research function is more prominent and influential within the tax administration, having tripled in size, and with studies leading to practical changes in policy and administration. For example, the Government of Rwanda’s recently announced increase in taxes on gambling was credited to the RRA research team’s review of gaming tax law and recommended revisions.[1]
[1] Rwanda Implements Significant Gambling Tax Raise | iGamingToday.com - News, insights and Slots review

ICTD engagement informs changes to administrative practices in Nigeria’s Federal Inland Revenue Service (FIRS). ICTD engagement and partner workshops inform the expansion of FIRS’s research function, and the development of a policy to guide tax research and establish a framework for evidence-based decision making that enhances the efficiency, effectiveness, and equity of the tax system.

ICTD’s work with Rwanda Revenue Authority (RRA) to reduce compliance costs and confusion for taxpayers led to improved voluntary compliance and increased revenue. A cost-benefit analysis based on ICTD’s research showed a 1:12 return on investment, with every US $1 spent generating US $12 in additional revenue over six years. The intervention led to a 54% increase in tax payable, starting from a low baseline involving newly registered taxpayers. In the first two years it is estimated that US $16 extra revenue per taxpayer was collected, increasing to an extra US $302 per taxpayer in years three to six, with new taxpayers encouraged to declare. See the VfM section of this report for further details.

Increased engagement and support to FCDO’s Public Finance and Tax Department (PFTD). Newly implemented six-monthly meetings between ICTD and PFTD have led to greater coordination and identified topics for PFTD’s community of practice, which ICTD subsequently ran for FCDO. ICTD also helped develop a learning journey on taxing the wealthy, advising on the design and delivery drawing on existing ICTD research; and a Best Buy paper for Public Financial Management (PFM) and Tax, preparing a tailored literature review, mapping and analysis of the effectiveness and cost-effectiveness of tax reforms and interventions.

High-level policy engagements and evidence-based contributions influencing global tax debates. On gender, ICTD launched the Community of Practice for Gender and Tax, collaborating with the Centre for Sustainable Development and including members from the World Bank, the IMF, OECD, the African Tax Administration Forum (ATAF), Oxfam, and UNDP. On informality, ICTD collaborated with ATAF in the organisation of their African Tax Research Network (ATRN) 9th Annual Congress, held in Botswana in September, featuring ICTD presentations and a dedicated event on informality with engagement from 25 revenue officials. On international taxation, following last year’s vote supporting the establishment of the UN Framework Convention on International Tax Cooperation, ICTD co-organised several workshops with attendance from UN country representatives and secretariat staff, civil society, and academics. ICTD produced several policy briefs for the G20/T20 on inclusive digital transformation, informality, and a fairer global tax architecture. Later in 2024, ICTD began engaging with the Financing for Development process, this will be scaled up in 2025.

ICTD developed a four-year strategy setting key objectives on research, operations, communications and engagement, alongside an implementation roadmap. The document was developed by the ICTD’s Centre Management Team in close consultation with team members from the research, programme, and communications teams. Feedback was sought at an all-team retreat in November 2024 and following this, the strategy document will be finalised in early 2025.

Strong record of publication and ICTD citations, with good policy follow up. ICTD published ten peer-reviewed journal articles and book/chapters this year, and cumulatively across years has now reached over 16,000 citations of ICTD publications. ICTD was mentioned in the media 46 times, all meeting or exceeding targets.

Major lessons and recommendations for the year ahead

Lessons:

Lesson 1: FCDO central policy analysis has been able to benefit from ICTD’s expertise. ICTD prepared a tailored literature review, mapping and analysis focused on tax interventions. The assessment of evidence, technical insights and rigour were valued by the leading policy team was able to feed into the full literature review and evidence mapping report now in turn being used to prepare the PFM and Tax Best Buy report. The flexibility of ICTD in supporting this work was highly valued by tax colleagues and RED.

Lesson 2: Adapting approaches to content sharing on social media will continue to be important in the current online environment. Changes outside programme control have made it necessary to constantly adapt approaches to research dissemination. This has impacted some programme KPIs. The programme will continually need to invest in trialling and adapting approaches to improve engagement, including through Facebook boosting, Google Ads, reviewing its presence on Twitter, and exploring other social media platforms, such as BlueSky.

Lesson 3: Changes to selection process for ICTD’s Research in Tax and Development course. ICTD’s Research in Tax and Development course remains successful, as demonstrated by the record 885 applications received this year. This reflects the course’s reputation and the demand for training in this field. The surge in applications also presented challenges in the selection process. To better identify candidates with a clear understanding of tax and development issues and a genuine interest in the course, ICTD introduced an additional application exercise to help address the rise in AI-generated applications. Insights from this year’s course led to adjustments, including to the schedule to allow participants more time to refine and develop their projects, thereby enhancing the quality of course outcomes. Additionally, the decision to give mentors a greater role in the selection process for the 2024/25 cohort has proved beneficial, with a more engaged set of participants.

Lesson 4: ICTD explores new models for working with countries in South Asia. Scoping work in South Asia suggested that there are research opportunities and possibilities for engagement with revenue authorities, but that the model needs to be tailored to overcome the lack of institutionalised research collaboration at national and regional levels. A cornerstone of ICTD’s existing agreements with revenue authorities in Africa is that they will collaborate and share data to published as working papers. The regional body, ATAF, played a role in showing the benefits of research based on administrative data which helped overcome concerns in other administrations. In Asia, no regional coordination exists of this kind, so collaboration has been ad hoc and requiring lengthy negotiations to setup projects. While studies have been conducted in India and Pakistan, they have not evolved into the structured, longer-term collaboration that has been possible in Africa; in some contexts the approach will need to be adapted significantly due to local concerns, for example for the Inland Revenue Department in Nepal.

Recommendations for the year ahead:

Recommendation 1: Diversifying Funding: last year’s annual review included a recommendation on forward planning which recommended ICTD develop a three-year financial plan considering FCDO funding for ICTD ends in 2027. Since then, global aid funding uncertainty has increased, and the UK has confirmed a reduction of aid contributions to 0.3% of GNI. This makes diversifying funding even more essential for ICTD’s sustainability. ICTD’s financial plan was submitted in April 2025 but does not clearly articulate how additional funding will be generated. Review and update this, outlining steps for implementing the plan (ICTD, by November 2025).

Recommendation 2: Value for Money: last year the annual review asked ICTD to strengthen outcome assessment and collect cost data to ensure outcome case studies feed into an assessment of VfM. Demonstrating value for money is even more important given limited ODA funds overall. While work has been done to collect cost data to feed into VfM calculations, ICTD should include cost/savings data in outcome stories wherever possible, so we are able to say, e.g., ‘due to X investment by ICTD, Government Y saved ££/generated ££ additional tax revenue.’ [ICTD, by January 2026]

Recommendation 3: Produce synthesis papers on topical issues and use these outputs to engage with key actors and in key fora. Making research accessible to policy makers and stakeholders is essential for research uptake. Synthesising research supports this goal and helps ensure broader reach. Produce six synthesis papers over the course of the year, with a proportion of themes agreed after consultation with FCDO programme team by Q2, and the remainder produced flexibly, depending on opportunities that emerge over the year. [ICTD, by January 2026]

Recommendation 4: Identify key policy engagement opportunities throughout the year and time publications and communication to maximise impact. Develop a list of major events and key debates taking place (e.g., the Financing for Development Conference, the UN Tax Convention, the G20, etc.) and draft a publication and communication plan to maximise these opportunities to showcase new and existing research and engage in key debates. [ICTD, by September 2025]

Recommendation 5: Logframe review. ICTD and FCDO to ensure an annual logframe update at least six months before the end of the review period (i.e. by end June which is six months in advance of the December milestones). In 2025, the logframe was updated in February 2025 for the December 2025 milestones, but to note also this recommendation for future years. Given the maturity of ICTD as a research programme, for the coming year review logframe milestones to ensure they are sufficiently ambitious, while remaining realistic. As part of FCDO and ICTD’s annual logframe discussion and review, consider removing counting web sessions from the logframe as they no longer serve as the best measure of online engagement. Instead identify another metric that may more usefully track engagement with content. [ICTD and FCDO, by September 2025]

Recommendation 6: Gender balance of capacity building activities: The ICTD should consider how to ensure a balance of women and men in its capacity building activities beyond its Teaching and Learning (‘Research on Tax and Development’) course. While most participants on that course are women, the same is not true for ICTD’s Research within Tax Administration workshop and for informal mentoring by ICTD staff. ICTD should encourage women working in revenue authorities to access the same mentoring and capacity building opportunities as their male colleagues and should seek out ways to encourage greater uptake by women.

Recommendation 7: Reporting. As per the model for FCDO Annual Reviews, ICTD’s reporting to FCDO should fit the template guidance and aim for no more than 20-25 pages excluding annexes (our final document needs to be less than 30 pages excluding annexes), building on steers and guidelines which will be provided by FCDO.

Recommendation 8: ICTD’s future work. Looking ahead, ICTD should lay the foundations for work on tax, debt, and governance; tax and protests; and on environmental taxation in line with FCDO priorities and interests. While retaining flexibility to adapt will be useful in this uncertain funding period, work can be done to allow for quick scale up in these areas once funding is clarified.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The programme’s overall Theory of Change (ToC) and South Asia ToC are shown below. The Review Team and the ICTD agree that these are still valid, the assumptions underlying these ToCs remain true, and the evidence produced, when disseminated to engaged policy makers and other stakeholders, is leading to clear impacts on the policy decisions of governments.

The South Asia ToC was updated during the previous reporting period to reflect collaboration with the Mahbub ul Haq Research Centre. The overall Theory of Change continues to be focused on developing key relationships in the region, alongside projects of specific strategic opportunity, as network-building in South Asia was temporarily disrupted due to budget cuts during the Covid-19 pandemic.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Details of progress at Outcome and Impact levels are shown in Table 2 below and the narrative that follows.
Table 2: Impact and Outcome milestones and progress in January 2024-Dec 2024

Impacts and outcomes	Milestone	Progress
Impact: Improved developing country tax systems that support pro-poor economic growth, advance equity for poor people, increase revenue, and improve accountability.
Impact indicator: Number of Impact Stories describing how ICTD research, capacity building, and policy engagement activities have contributed to increased efficiency in revenue administration, increased tax collection, enhanced equity in tax systems, or strengthened accountability.	1	1 – met expectation
Outcome: High quality evidence is accessed by governments of developing countries and other stakeholders including DFID and other donors, multilaterals, & civil society organisations, who then modify their practices, policies or programmes.
Outcome Indicator 1: Changes to tax policy or administrative practices are made or seriously debated on the basis of evidence from ICTD research, which increase equity, effectiveness or accountability.	2	2 – met expectation
Outcome Indicator 2: Number of high-level policy documents and reports in the last year (by international financial institutions, intergovernmental organisations, international NGOs, aid agencies, etc.) that cite ICTD research.	28	31 – moderately exceeded expectation

Impact Story: ICTD research and technical input informed VAT legislative reform in Senegal, increasing VAT revenue and administrative efficiency.

Senegal’s VAT code did not allow for taxation of digital services by foreign providers without a local presence, meaning an increasingly important part of the economy was outside the VAT net and there were tax inequalities between service providers depending on whether they had a local affiliate (e.g., Canal+ did, but Netflix did not so was not taxed). OECD guidelines recommended VAT be levied in the country of the end user, however differences remained between these guidelines and Senegal’s Finance Act 2023. The Directorate General of Taxes and Domains (DGID) was tasked with implementing this Finance Act and DGID asked ICTD to conduct background research into the practices of other African countries and provide recommendations. ICTD offered recommendations based on interviews and reviews of VAT guidance in other countries and the OECD approach; later ICTD provided comment on the draft Ministerial Decree, which would articulate implementation details. Some of ICTD’s recommendations were implemented in the first Decree, while others were adopted later in the Finance Act 2024, and two further Decrees.

ICTD’s recommendation to relax the Finance Act 2023 requirement that foreign digital platforms must appoint a tax representative in Senegal was adopted in a revision of the law made thorough the Finance Act 2024 and became operational in July 2024. This led to increased VAT revenue in the second half of 2024, with an additional 1.905 billion CFA Franc (c. £2.5 million) raised from digital services provided from abroad. ICTD recommendations also improved efficiency for both the tax administration and businesses (through reduced compliance costs) thanks to simplified registration, declaration, and payment processes. Foreign service providers could now file returns every quarter using a simplified online registration and filing interface, enabling remote registration without requiring a local fiscal representative, supporting increased VAT revenue overall. This also improved horizonal equity by ensuring that online streaming services such as Netflix were within the VAT net alongside domestic services, such as Canal+. A working paper on these insights and best practices is due for publication during 2025.

Outcome Indicator 1, Story 1: 10-year collaboration between ICTD and the Rwanda Revenue Authority (RRA) contributes to significant growth of research department and greater impact of research on policy.

2025 marks a decade of collaboration between ICTD and the RRA. Sustained engagement that has built research capacity and profile within the RRA has led to greater, longer lasting policy impact. In 2015, the RRA had three full time staff members and were constrained in their capacity to formulate and conduct research to generate evidence in response to policy needs. Initially ICTD was invited to work with the RRA analyse administrative data from Rwanda and conduct academic and policy relevant studies. From 2018 onward, the RRA requested a comprehensive plan for building capacity within the RRA. ICTD developed a year-long course on research methods and taxation reserved for RRA and Uganda Revenue Authority staff. From 2021 onward, the RRA invited ICTD’s current executive director (then research director) to serve as research adviser to the RRA, to further develop capacity, strengthen quality of outputs, and support implementation of research findings. ICTD’s RRA research adviser led a capacity assessment of RRA’s research function and made recommendations for improvement, several were incorporated into the new organisational model being developed at the same time.

As a result of this collaboration, the RRA has more than tripled in size, now employing 10 researchers. The expansion of the research team concluded in this reporting year. After nearly a decade of collaboration, the research function is more prominent and plays a strategic role within the tax administration. Research is recognised as key to decision making within the RRA, and recommendations from research papers are tracked and fed into the RRA’s action plan. Several studies have led to practical changes in policy and administrative functions, improving administrative efficiency (e.g., a nil filing study resulted in the deregistration of at least 40,000 tax payers – reported at the last AR [2]), equity[3] and improvements in revenue collection (see VFM story on taxpayer education from this year, with the programme leading to a 29% increase in the number of taxpayers submitting declarations).[4] An interview with RRA’s former Commissioner for Planning and Statistics credited ICTD with improving the research team’s standing and influence within the revenue authority. For example, the Government of Rwanda’s increase in taxes on gambling, announced in February 2025, was also attributed to the research team’s review and recommendations.[5] RRA interviewee claimed this was only possible due to the capacity that had been built over time with the support of ICTD.
[2] Active Ghosts: Nil-filing in Rwanda
[3] The VAT in practice: equity, enforcement, and complexity
[4] Teach to comply? Evidence from a taxpayer education program in Rwanda
[5] Rwanda Implements Significant Gambling Tax Raise | iGamingToday.com - News, insights and Slots review

Outcome Indicator 1, Story 2: ICTD engagement and partner workshop informs changes to administrative practices in Nigeria’s Federal Inland Revenue Service (FIRS) and evidence-based policy recommendations.

Nigeria, Africa’s second largest economy, has one of the world’s lowest tax-to-GDP ratios. Tax reform has been spearheaded by the Executive Chairman for the FIRS; however, a key constraint has been the availability of context-specific evidence on what does/not work within the existing tax system. Since 2017, ICTD has collaborated with FIRS supporting development of tax research capacity and use of evidence in policy making through establishing the Nigerian Tax Research Network (NTRN), which provided opportunity for high-level engagement with policy makers. FIRS staff also received training through ICTD’s Tax and Development Research Course. A partner workshop in 2023, involving staff from eight African revenue administrations, including FIRS Head of Research and Statistics Department and Head of Research Division, and discussed successful strategies for shaping policymaker views and decisions for greater impact.

The Head of Research and Statistics Department described being influenced by the insights gained and strategies discussed. After the workshop, the Department Head initiated changes to strengthen the quality of research output from FIRS: she headhunted senior researchers, reached out to revenue authorities in Africa to understand and compare experiences in research priorities and gaps; invested in FIRS research capacity; and initiated an open call for external research papers to publish a FIRS journal of tax studies. Alongside, ICTD engaged with the research department offering advice on specific policy recommendations and conducted research in conjunction with FIRS employees, strengthening FIRS research quality and team capacity. This engagement led to FIRS research department developing a policy to guide tax research and establish a framework for evidence-based decision making; alongside five policy briefs with recommendations for reform across five revenue collection areas, drawing on ICTD research. These are being reviewed by FIRS management.

Outcome Indicator 2: Number of high-level policy documents and reports in the last year (by international financial institutions, intergovernmental organisations, international NGOs, aid agencies, etc.) that cite ICTD research.

This outcome moderately exceeded expectations during this reporting period. The ICTD’s work was cited in 31 high level policy documents and reports by numerous international agencies. Some of these reports cite multiple ICTD publications, which points to the influence on ICTD’s wider body of work in policy documents by international organisations.

Highlights include:
- The OCED’s Revenue Statistics in Africa 2024 (five ICTD publications citated),
- UNDP’s Human Development Report 2023-2024 (eight ICTD publications cited)
- The World Bank book ‘Levelling the Playing Field: Addressing Structural Inequalities to Accelerate Poverty Reduction in Africa’ (seven ICTD publications cited).
- The UN Women’s World survey on the role of women in development 2024: harnessing social protection for gender equality, resilience and transformation cites ICTD arguments from the ICTD working paper on engendering taxation and policy brief published in same year. These citations were picked up again in the UN Secretary General’s report on the survey later in 2024.
- The World Bank’s Knowledge Note on Unpacking Tax Compliance from a Gender Perspective also cites both these recent papers as well as earlier ICTD work on both tax and compliance and gender and tax.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Overall ICTD is a very successful investment with significant networking and capability impacts and a strong track record publishing work in high quality journals. ICTD has established itself as the leading institution for tax research in developing countries. Interviews highlighted ICTD’s strength in turning academic research into practically actionable recommendations for policy makers; as well as supporting research functions within revenue authorities to become more influential and effective within their institutions. This has been instrumental in this research programme achieving real-world impact.

In the context of reduced aid funding worldwide and increased costs of debt servicing due to global financial turbulence, governments in developing countries will have to raise more domestic revenue to maintain administrative costs. This will likely lead to increased demand for ICTD’s expertise as governments increasingly recognise the need for increased self-reliance and more predictable sources of funding. ICTD remains a high-return investment for FCDO and should be continued.

Progress on recommendations from the previous Annual Review

The previous Annual Review recommendations were as follows (with updates under each recommendation):
1. Engagement with Posts. The ICTD should continue to support FCDO posts knowledge of ICTD research in or related to that country (a-b are repeated and updated from the 2023 Annual Review):
  1. when presenting ICTD research to FCDO posts, the ICTD researchers and representatives should provide background on the research activities being funded by Research and Evidence Directorate so that posts are fully aware and are encouraged to engage proactively (Action: the ICTD, on-going);
  2. the ICTD should provide Development Directors, at posts where the ICTD has been actively engaged, with a list of ICTD research conducted related to their country after the Annual Review (Action: the ICTD, by end July 2024); and
  3. Building on a and b, ICTD should respond rapidly, constructively, and independently (without intervention from the programme PRO) to requests for support from FCDO posts and policy desks (Action: the ICTD, to be assessed by FCDO in Dec 2024 and May 2025)
Met, with work ongoing.
1. ICTD provided background on FCDO-funded research in-country when visiting FCDO posts this year, for example during visits to Rwanda, Uganda, Sierra Leone, and Ghana.
2. This was completed and reports were sent on Sierra Leone, Rwanda, Pakistan, Ethiopia, Uganda and Ghana.
3. Interviews suggested ICTD responded rapidly and constructively to requests for support from posts and policy desk.

ICTD-FCDO review and learning. (repeated and updated from the 2023 Annual Review) The ICTD and FCDO focal points on tax and development should meet at least after every Annual Review and ideally 6-months later to share key emerging messages from the Tax and Development programme to feed into planning processes in FCDO posts (Action: the ICTD and FCDO focal points, by end Sept. 2024 and end March 2025)

Met. Meetings between ICTD’s Giulia Mascagni and PFTD’s Angela Bellmooney took place on 4th September 2024 and 21 March 2025. FCDO reported that these catch ups were valuable to highlight ICTD and FCDO priorities for the next 6m and identify overlaps that could be leveraged for policy development. As a result of these conversations, they have jointly identified topics for PFTD’s community of practice that ICTD have subsequently run for FCDO.

Theory of Change. The Theory of Change should be updated to show reference to FCDO not DFID (Action: FCDO, by July 2024)

Met. Theory of Change has been updated.

Logframe. The output indicators and weightings should be reviewed including considering: moving output indicator 1.3 from output 1 to output 2; reducing the weighting of output 1 and increasing the weighting of output 2; and widening output 2 to include policy engagement and research uptake. ‘To improve policies’ should be removed from output 3, and in 3.1 and 3.2 assessment of research quality and lead authorship should be considered (narrative or numbers) in future. (Action: ICTD and FCDO, by Nov 2024)

Partially met. The new output indicators and weightings have been revised as follows and the total number of citations (output indicator 1.3) has been moved to output 2:
- Output 1 – 35% (Outputs 1.1 & 1.2)
- Output 2 – 30% (Outputs 2.1, 2.2, 2.3, 2.4 & 2.5)
- Output 3 – 25% (Outputs 3.1, 3.2 & 3.3)
- Output 4 – 10% (Outputs 4.1 & 4.2)

The logframe updates for 2024 were not completed until February 2025 due to being combined with the logframe for the No Cost Extension. This meant it was beyond the timeframe assessed by this Annual Review and edits could not be used for 2025 milestones. ICTD and FCDO should both be ensuring an annual logframe update at least six months before the end of the review period (i.e. end June given the December milestones), but FCDO recognises some confusion may have been caused by staff vacancies in RED.

Value for Money. Building on the good progress to date on VFM, ICTD should strengthen outcome assessment and routinely collect cost data to ensure the case studies clearly feed into an assessment of VfM. (Action: ICTD by Apr 2025)

Met, with work ongoing. ICTD has improved their value for money assessments, however demonstrating value for money is even more important given limited ODA funds overall. This recommendation should be considered ongoing for the coming year.

Reporting quality. The ICTD should ensure that it continues to enhance (high quality, fact-checked and proof-read) annual and other reports to FCDO. (Action: the ICTD by next quarterly report and Annual Report 2025).

Met. The ICTD has quality assured a high standard annual report for FCDO – it was high quality, fact-checked and proof-read. Nevertheless, it required redrafting to fit FCDO’s needs for the Annual Review publication. Future reporting should be more specific and concise (using the model of the current review) and FCDO will consider providing extra guidance to support this in future. See recommendation 7 for the upcoming year.

Forward planning. Given the FCDO AG ends in March 2025, with the possibility of an extension to March 2027, the ICTD should prepare a short-medium term (3 year) financial plan (Action: ICTD, by Dec 2024)

Not met. ICTD submitted a three-year financial plan in April 2025 in time for the extended deadline (after the reporting period for this Annual Review), however it did not include substantial detail on fundraising plans and therefore missed important forward-planning requirements. ICTD has since informed FCDO that some of the operational planning exists in internal ICTD documents. FCDO seeks further follow up as part of improved communication between FCDO and ICTD on forward planning and funding and as we seek to prioritise ICTD’s sustainability. ICTD and FCDO are already discussing a way forward.

## C. DETAILED OUTPUT SCORING

Output Title	New Research Produced: Production of high-quality & policy-relevant tax research, mainly in FCDO priority countries in Africa and South Asia
Output number:		1	Output Score:	A+
Impact weighting (%):		40%	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of ICTD own publications and translations produced (Working Papers, Other) (Research in Briefs, Policy Briefs and African Tax Administration Papers (ATAPs)). / Weighting: / Working Papers 80% / Other 20%	Working Papers: 16 / Briefs and Other: 16	Substantially exceeded. / Working Papers: 25 / Briefs and Other: 37
1.2 Total number of peer-reviewed journal articles and book/chapters published.	10	Met. 10
1.3 Total cumulative number of citations of ICTD publications.	11,313	Moderately exceeded. 16,307

Supporting narrative for the score.

ICTD made strong progress this year, exceeding milestones against two indicators on this output, the number of ICTD publications produced and the number of citations of ICTD publications, and meeting the indicator for the number of peer-reviewed journal articles and book/chapters published. Overall, this output moderately exceeds expectations.

Output Indicator 1.1: Number of ICTD own publications and translations produced significantly exceeded expectations for this year. During the reporting period ICTD published 25 Working Papers and 37 publications in the ‘Briefs and Other’ category (30 Research in Brief publications, four African Tax Administration Papers [ATAPs], and three Policy Briefs). During the reporting period ICTD undertook targeted effort to complete papers that had taken a long time to get to publication, which supported these considerable numbers. A list of publications can be found in Annex 2.

Output Indicator 1.2: Total number of peer-reviewed journal articles and book chapters published met expectation for this year. The ICTD achieved the logframe target of 10 peer-reviewed publications, publishing nine journal articles and one book chapter. A list of peer-reviewed journal articles and book/chapters published can be found in Annex 2. Notable journal articles include: Sub-national property tax reform and tax bargaining: Lessons from a quasi-randomized reform program in Sierra Leone (Prichard, W., Jibao, S. and Orgeira Pillai, N., 2024). This article follows ten years of work on property taxation in Sierra Leone and is one of two ICTD articles published in the prestigious journal World Development this year; alongside The taxed informal economy: Fiscal burdens and inequality in Accra, World Development (Anyidoho, N. A.; Gallien, M.; Rogan, M. and van den Boogaard, V., 2024), also published in the World Development journal. The ICTD article Does the Value-Added Tax Add Value? Lessons Using Administrative Data from a Diverse Set of Countries (Brockmeyer, A., Mascagni, G., Nair, V., Mazhar, W. and Almunia, M., 2024) was also published in a well-regarded economic outlet, the Journal of Economic Perspectives. These are indications of the quality of ICTD research and their contribution to the academic field.

Output Indicator 1.3: Total cumulative number of citations of ICTD publications exceeds expectations this year. ICTD significantly exceeded the target for the total cumulative number of citations of publications, with 16,307 citations. This citation rate reflects the relevance of ICTD research and growing recognition of ICTD's contributions. Citations were included in several noteworthy publications, including by the Asian Development Bank, Atlantic Council and European Institute of Security Studies, and in a range of IMF, ODI, OECD, and UN papers.

Any changes to this output during the past year, and any planned changes as a result of this review.

No changes were made to this output or the wider logframe during the reporting period.

Lessons learned this year and recommendations for the year ahead See front.

Output Title	Policy engagement: new research, learning and recommendations reach and engage decision makers to increase their understanding and use of evidence to improve tax policy.
Output number:		2	Output Score:	A+
Impact weighting (%):		25%	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
2.1 * Number of high-level policy meetings or conferences at which ICTD team members participate present or speak at / * Total number of academic meetings or conferences attended / * Total number of civil society engagements	Policy: 36 / Academic: 25 / Civil society: 16	Moderately exceeded. / Policy: 39 Academic: 27 Civil society: 17 / (See Annex 3 for more details)
2.2 Total mentions of ICTD work in the media	40	Moderately exceeded. / 46
2.3 Number of collaborations with FCDO staff or advisers to support their tax programme that require (a) less than half a day of staff time (1/2 day -) and (b) more than half a day (1/2 day +).	a) 9 b) 6	Moderately exceeded. / a) 12 / b) 8 / (Listed in Annex 1)
2.4 In the last year: / * Total number of website sessions / * Total number of Facebook followers / * Total number of X (Twitter) followers	Website: 170,000 / Facebook: 7,500 / Twitter: 9,000	Moderately not met. / Website: 137,280 / Facebook: 6,990 / Twitter: 9,100

Supporting narrative for the score

The ICTD continues to demonstrate a good level of policy engagement, moderately exceeding all but one logframe target, and overall this output is moderately exceeded.

ICTD team members participated in a range of high-level policy meetings and conferences; mentions of the ICTD's work in the media have exceeded logframe milestones; as did collaborations with FCDO staff or advisers on tax programmes. FCDO colleagues in the Public Finance and Tax Department (PFTD) highlighted the positive and constructive engagement they have had with ICTD, and appreciated ICTD’s accessibility and responsiveness to FCDO asks; and commented on the ability of ICTD to effectively turn academic findings into practical policy recommendations for partners, increasing the impact of the research.

Social media sessions and followers (2.4) did not meet all targets in part to changes made by Google Analytics and challenges faced in boosting content on Facebook (more detail below). Full detail on ICTD’s policy engagement work is presented in Annex 3.

Output 2.1: High-Level Policy, Academic and Civil Society Engagement moderately exceeds logframe milestones. ICTD engaged with key stakeholders including revenue authorities, government officials and representatives, tax practitioners and experts, multilateral institutions, civil society organisations, and researchers. Examples include:
- ICTD Research Fellows Max Gallien and Vanessa van den Boogaard held a webinar for the German International Cooperation Society (GIZ) where they presented the Mass Tax Registration Policy Brief and discussed related research. Approximately 40 people attended including from country offices.
- ICTD Research Director Martin Hearson presented a summary of ICTD’s work on the Inclusive Framework and UN Tax Convention to an academic audience at the LSE event Making Global Tax Governance Fit for the 21st Century. Martin also co-organised the conference Reimagining Global Tax Governance at Saïd Business School in Oxford and chaired a panel through the invitation of Andrew Debalen from the World Bank.
- ICTD Executive Director Giulia Mascagni gave a virtual presentation at a closed meeting with a group of 18 Chief Economists of governments across Africa on options to mobilise more revenue fairly – with particular focus on ICTD’s work on tax targets, digitisation, and taxing the wealthy) as examples of reforms that increase both revenue and equity.

Output Indicator 2.2: Media Coverage of ICTD’s Work exceeds expectations this year. The ICTD and its research featured in the media 46 times in the past year, with three peaks in coverage: during ICTD’s conference in Ghana in February; following the tax protests in Kenya in July; and finally, during ICTD’s conference in Rwanda in December. Highlights include:
- Research Fellow Wilson Prichard’s interview with CBC News in June on the #RejectFinanceBill protests in Kenya. The video explainer gained more than 900,000 views on the outlet’s YouTube channel, which has more than 3.82 million subscribers.
- Related to the same news event, external authors Eric Magale and Mario Schmidt authored a piece for The Conversation, referring to their then-forthcoming ICTD research (ICTD Working Paper 211, Tax Awareness and Fiscal Workarounds in Contemporary Kenya: Reactions Towards New Taxation Laws, and the Need to Renew the Social Contract). The piece was syndicated to other news outlets, including by local media in Nigeria and Uganda, and led to a media inquiry by The Economist, resulting in an article featuring an interview with the ICTD’s Executive Director Giulia Mascagni.
- For more on ICTD’s media coverage, see this page on their website.

Output Indicator 2.3: Collaborations with FCDO staff or advisers to support their tax programme exceeds expectations this year. The ICTD exceeded Logframe targets for number of collaborations with FCDO staff or advisers to support their tax programme, with 12 instances of support requiring less than half a day and eight instances requiring more than half a day. Engagements took place at various levels, including through the FCDO Public Finance and Tax Department (PFTD), Community of Practice (CoP), bilateral engagement with members of the PFTD team at central office and in at post.

Examples include the following and more detail can be found in Annex 1:
- ICTD undertook a literature review, analysis, and synthesis of evidence relating to the effectiveness and cost-effectiveness of Public Finance Management and Tax reforms/interventions, to inform the development of a Best Buy paper for Public Financial Management (PFM) and Tax for PTFD.
- Supporting PFTD to design a learning journey on taxing the wealthy, advising on the design and delivery of the journey and going forward contributing to workshop discussions and providing technical input on written outputs.
- Contributing to an FCDO retreat for public finance and tax advisors from the East African region.
Advising FCDO Sierra Leone on their new "Expertise to Support Economic Reform in Sierra Leone Programme".

Output Indicator 2.4: Website sessions and social media followers does not meet expectations, apart from Twitter/X followers which slightly exceeded expectations. During the reporting period the ICTD website accumulated 137,280 sessions or visits, missing the target of 170,000 for this year. However, this was a 43.2% increase on last year’s numbers, as were the 253,286 page views (up by 47.3%), and the 83,768 new users (up by 40.9%). Failure to meet the logframe targets is partly due to changes made by Google Analytics which altered how web sessions are defined and collected, leading to lower session counts (even if user engagement remained consistent). This means figures reported before 2023 are not comparable with figures reported since the changes took place. There has also been reduced organic traffic attributable Google’s AI generative being rolled out (in May 2024). ICTD is monitoring these changes but expect further volatility. Because of this, we recommend that web sessions are no longer used as a KPI in the Logframe for the contract extension as these figures may become less useful, with the team identifying another metric that may more usefully track engagement with content.

On social media:
- ICTD saw a small increase in its Facebook follower count from last year (+50), reaching a total of 6,990, which does not meet the target of 7,500. Ongoing decline in organic reach and engagement on the platform continued to present a challenge. Facebook initially blocked ICTD’s ability to ‘boost’ posts until late 2024, and posts are occasionally blocked for being ‘political’, both presenting further challenge this year. Despite this, ICTD have improved their visibility on the platform, having accumulated a page and post reach of more than 53,990 (up by 187% on last year).
- ICTD’s X followers have slightly exceeded the target for this year, with the centre’s followers increasing over the year to a total of 9,100 in December 2024, however this is in the context of steadily declining global user numbers on X. While ICTD has continued to disseminate research and participate in broader debates on tax and development, the team are exploring alternative platforms.
- ICTD has a growing platform on LinkedIn, with 11,035 followers (up by almost 38% on last year), with an average engagement rate of 6.11%; high compared to industry benchmarks of 2.1-2.4%.
- The ICTD has continued publishing its monthly newsletter, which has a total of 3,761 subscribers, with an average Open Rate of 27.6% and Click Rate of 6.1% (above the industry average).

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes were made to this output during the reporting period. See Output 1 section on output changes for progress on last year’s AR recommendation relating to the logframe and changes going forward.

Lessons learned this year and recommendations for the year ahead – see front.

Output Title	Capacity Building: Improved capacity of policy makers, developing country researchers & civil society to co-produce tax research and understand tax issues and evidence and to improve policies.
Output number:		3	Output Score:	A+
Impact weighting (%):		25%	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of (a) ICTD own publications and (b) peer-reviewed journal articles, book chapters or books authored or co-authored by Southern researchers.	ICTD publications: 16 / Journal articles: 2	Substantially exceeded. ICTD publications: 22 working papers / Journal Articles: 8 / (See Annex 2 for more detail)
3.2 Number of joint research projects carried out with Revenue Authorities or other government agencies any point in the year.	9	Moderately exceeded. 11
3.3 Number of people from developing countries who participate in ICTD research capacity building activities, disaggregated by gender.	Participants: 50 / Women: 23 / Men: 27	Moderately exceeded. Total participants: 73 / Women: 25 / Men: 48

Supporting narrative for the score

ICTD has substantially exceeded targets for one indicator, and moderately exceeded its targets for two indicators. Overall, we judge this to have moderately exceeded expectations for this output. Interviews demonstrated the value revenue authorities place on this sustained capacity building and the impact it is having within institutions. For example, in the Rwanda revenue authority, ICTD’s support to their research team, building capacity on research methodologies, analytical tools, and in conducting experimental research was credited with improving the research team’s standing within the authority and internal management increasingly listening to its recommendations. The Government of Rwanda’s recently announced increase in taxes on gambling was reportedly a result of the revenue authority’s research team who undertook research on the issue and recommended revising gaming tax law. The review team’s interview with a representative from the RRA claimed this would not have been possible without the increased team capacity built over time with the support of ICTD.

Output Indicator 3.1: Number of (a) ICTD own publications and (b) peer-reviewed journal articles, book chapters or books authored or co-authored by Southern researchers exceeds targets for this year. ICTD exceeded the logframe target for this indicator, producing 22 ICTD working papers, and eight journal articles authored solely or jointly by Southern researchers (against targets of 16 and two respectively). Highlights include: Tatiana Falcão on environment taxation where she presented a multilateral carbon tax treaty; Jalia Kangave and Solomon Rukundo on Does Having More Women in Parliament Result in More Gender-Sensitive Tax Policies? A Case Study of Uganda’s Parliament in parliament in Uganda; Bishal Chalise on double taxation avoidance agreements (which he then presented at the 80th Annual Congress of the International Institute of Public Finance and to the Ministry of Finance in Nepal); and a paper by Karishma Banga on trade rules was released ahead of the WTO 13th Ministerial Conference and was followed by a blog, which led to Pakistan's Ambassador to the WTO asking how they should approach the negotiations, invitations to speak and further collaborations. A full list can be found in Annex 2.

Output Indicator 3.2: Number of joint research projects carried out with Revenue Authorities (Revenue Authorities) or other government agencies any point in the year exceeds expectations for this year. ICTD carried out 11 joint research projects with Revenue Authorities or other government agencies, surpassing the target of nine. ICTD’s collaboration with Revenue Authorities on new research and provided pathways for uptake and impact. Highlights include:
- Ghana Revenue authority stamp tax project: Assessing costs and revenue collected through a simplified tax regime.
- Tax Officials project / The interpersonal side of tax compliance: interactions between taxpayers and tax officials in Rwanda: Investigating officials’ attitudes to enforcement and tax collection, and their views and motivations, with implications for taxpayer compliance.
- Tax compliance costs and digital technologies in Uganda: A National Taxpayer Survey: Measuring compliance costs across tax types in Uganda through a large-scale taxpayer survey, with comparisons to taxes paid across firms, tax types, and the industrial sector; and the role of digitalisation in alleviating or exacerbating compliance challenges.

Output Indicator 3.3: Number of people from developing countries who participate in ICTD research capacity building activities exceed expectations for this year. While the overall target was exceeded, and the number of women participating in the training met the target for this year, the proportion of women participating in capacity building activities overall reduced. The gender balance for teaching activities where selection is controlled by ICTD remains very good overall; however, there are other types of engagement where programme has little control over participant selection and the gender balance reflects the dominance of men in research departments. Research capacity building activities this year included:
- Research in Tax and Development course: in the reporting period the 23/24 course ended and the 24/25 course began. Twenty-five participants were selected for the 23/24 cohort (13 women, 12 men) from 15 different countries. The 24/25 cohort began in December 2024, with 26 students (14 women, 12 men) from 19 different countries including, Mongolia, Dominican Republic, and many Sub-Saharan African nations. A total of 885 applications were received, which was the highest since its expansion beyond revenue authorities, reflecting the courses growing reputation.
- Research within Tax Administration Workshop: ICTD brought together research departments of Revenue Authorities from different countries for a two-day workshop in December 2024 in Kigali, Rwanda. The goal was to provide an opportunity for learning amongst researchers from revenue administrations and with ICTD staff. This was followed by a conference that focused on digital tax administration.
- Mentorship: Beyond the formal capacity building programme, ICTD Research Fellows have undertaken additional mentorship activities with researchers from the global South. Those being mentored by ICTD were overwhelmingly men. ICTD should encourage women working in revenue authorities are able to access the same mentoring opportunities as their male colleagues.
- PhD scholarships: two students are counted against the logframe target this year, having started their PhDs during the reporting period. Overall, one new sponsored PhD student from Africa, and one ICTD-linked PhD student from France joined the nine existing funded PhD students in the UK (eight from the Global South), and two ICTD-linked PhD students at the University of Toronto (one from the global South).
Building Networks: to support network building the ICTD funded and took part in the 2nd RRA Research Day February 2024; co-hosted 10th EPRN Annual Research Conference June 2024; and organised a research study visit for a delegation of three staff and four students from the Kenya School of Revenue Administration (KESRA) to the Institute of Development Studies June 2024. Expanding early career researchers’ access to these networks has been a core part of ICTD’s Teaching and Learning course strategy.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes were made to this output during the reporting period. See Output 1 section on output changes for progress on last year’s AR recommendation relating to the logframe and changes going forward.

Lessons learned this year and recommendations for the year ahead – see front.

Output Title	South Asia Research: Develop a significant tax research programme in South Asia.
Output number:		4	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
4.1 Number of new research projects initiated	2	Met. 2
4.2 Number of initiatives taken to develop new research partnerships	1	Met. 1
4.3 ICTD publications produced dealing with issues in South Asia	3	Met. 3

Supporting narrative for the score

ICTD met all targets against this logframe outputs over the reporting period. ICTD maintains a modest portfolio of projects in South Asia. Opportunities for deepening research networks and expanding influence have been moderate but important, with a particular focus on various research opportunities and initiatives in Sri Lanka and Pakistan.

Output Indicator 4.1: Number of new research projects initiated met expectations. ICTD began two new projects in South Asia, meeting their logframe target. New projects include:
- ‘India in International Tax Negotiations’, a largely interview-based project to study India's objectives and strategies in international tax negotiations since 2008, working with a local co-author, Suranjali Tandon of the National Institute for Public Finance Policy (NIPFP). This is the first time ICTD have worked with NIPFP on research.
- Research conducted by Ahsan Zia Farooqui, one of ICTD’s PHD cohort, on revenue mobilisation and compliance with subnational tax in the context of weak state capacity in Pakistan, specifically property tax collection in Lahore. The findings will offer insights into the behavioural drivers of tax compliance in Low and Middle-Income Countries and provide evidence for improving tax policy, enhancing revenue mobilisation, and supporting sustainable economic growth in developing countries. It is an extension of ongoing ICTD and LoGRI work in Pakistan, which investigates citizens’ preferences for progressive property taxation and is part of an ongoing collaboration with the Excise and Taxation department and Lahore University of Management Sciences (LUMS).

Output indicator 4.2: Number of initiatives taken to develop new research partnerships met expectations this year. ICTD developed one new partnership in Sri Lanka. Mick Moore is working in collaboration with think tank Verité Research to address critical issues in the region's tax systems. Moore authored an op-ed which was published in the Daily Mirror, Colombo in September, outlining why an existing proposal for a wealth tax (Imputed Rental Income Tax) should be rejected. This was published two days before the presidential election, and contacts in the new government disclosed that they had already decided to reject the proposal. The next steps will include Moore producing a policy brief on property valuation making the case for a new property taxation system in Sri Lanka using simplified valuation.

Output Indicator 4.3: ICTD publications dealing with issues in South Asia met expectations for this year. ICTD has published three working papers covering issues in South Asia:
- Gupta, B.; Velayudhan, T.; Dhawan, P. and Garg, A. (2024) Why Don’t Firms File Tax Returns on Time? Evidence from the Indian GST, ICTD Working Paper 207, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.086
- Chalise, B. (2024) Do Double Taxation Avoidance Agreements Attract Foreign Direct Investment The Case of Nepal, ICTD Working Paper 205, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.076
- Mahajan, A.; Mittal, S.; Reich, O. and Barwahwala, T. (2024) Using Machine Learning to Catch Bogus Firms, ICTD Working Paper 196, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.050

Alongside the below journal articles, counted under Output 1.2:
- Brockmeyer, A., Mascagni, G., Nair, V., Mazhar, W. and Almunia, M. (2024) "Does the Value-Added Tax Add Value? Lessons Using Administrative Data from a Diverse Set of Countries." Journal of Economic Perspectives, 38 (1): 107-32. DOI: 10.1257/jep.38.1.107
- Gallien, M., Javed, U. and van den Boogaard, V. (2024) “Zakat, Non-state Welfare Provision and Redistribution in Times of Crisis: Evidence from the Covid-19 Pandemic”, Studies in Comparative International Development. https://doi.org/10.1007/s12116-024-09447-x

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes were made to this output during the reporting period. See Output 1 section on output changes for progress on last year’s AR recommendation relating to the logframe and changes going forward.

Lessons learned this year and recommendations for the year ahead – see front.

## D: VALUE FOR MONEY

Key cost drivers and performance

VfM performance compared to the original VfM proposition in the business case

The ICTD developed and reported on indicators to strengthen the VfM assessment based on recommendations from an earlier Annual Review. These have been used for reporting this year and calculations were done using data from Q4 of the 2023/24 financial year and Q1, Q2 and Q3 from the 2024/25 financial year.

Economy

For ICTD, economy is achieving the lowest cost for their inputs for maximum output and this year they have again continued with the hybrid teaching model. The hybrid model has the same content as the in-person course, but just one in-person meeting as opposed to three, realising a cost reduction for the teaching and learning programme of £103,368. The hybrid model necessitated a teaching and learning portal which contains lectures, literature reviews and case studies, which students have found useful. The reduction in face time has been balanced with increased effort to connect students via WhatsApp groups.

The ICTD has leveraged partnerships to promote its work on tax and informality, achieving wider dissemination at reduced costs. These include a five-year partnership with Women in Informal Employment: Globalising and Organising (WIEGO) for research programme in Accra, sharing financial responsibility and resources; co-hosting seminars and producing joint policy papers to expand ICTD’s audience without additional investment; collaborating on working with partners, enabling ICTD to publish ten working papers at no cost; and organising a plenary session at the African Tax Research Network (ATRN) Annual Congress, hosting interactive sessions, and disseminating their work at a fraction of the cost of hosting a similar event independently.

Efficiency

The ICTD benefits from an experienced and efficient programme team with exceptionally low turnover and has adaptive programme management approaches that have enabled efficient and effective processes to ensure high quality outputs of research.

ICTD has developed significant expertise in collaborative research with partners, enabling it to achieve excellent value for money. Throughout the year, the ICTD has co-hosted events and worked with partners to minimize their overall costs. Examples include partnering with the Danish Institute for International Studies (DIIS) and the Centre on Armed Groups (CDG) where papers for an event in Switzerland meant ICTD only had to cover travel costs for researchers; to a partnership with the United Nations University – World Institute for Development Economics Research to fund an assistant based at the Uganda Revenue Authority’s (URA) Data Lab in Kampala, saving on staff time and travel costs by avoiding the need to travel to Uganda for administrative data.

Equity

In the ICTD research programme, equity is a central theme, with a focus on advancing equity for poor people as a key impact goal. Additionally, the programme emphasises global Southern and women’s participation as important indicators of value for money in achieving equity. ICTD calculate the proportion of women’s participation in the Teaching & Learning course at 64%, the proportion of working paper authors/co-authors who are women at 56%, the proportion of working paper authors/co-authors from the Global South at 88%, and 36% of all the Southern authors are women. Of the ICTD the proportion of women permanent research staff is 45%.

Effectiveness

The Theory of Change for ICTD aims to influence policy and practice by improving developing country tax systems to support pro-poor economic growth, advance equity for poor people, increase revenue, and improve accountability. Citations are a key indicator of the programme’s impact, with the ‘cost per incidence of research use or per citation’ serving as a measure of effectiveness. The ICTD has calculated the investment cost per incidence or citation use to be £463.94 and is lower than the previous year. However, this metric should be interpreted carefully, considering the value of who is using or citing the evidence.

Cost-Effectiveness

ICTD research and technical input informed VAT legislative reform in Senegal, increasing VAT revenue and administrative efficiency. Senegal’s VAT code did not allow for taxation of digital services by foreign providers without a local presence. ICTD offered recommendations based on interviews and reviews of VAT guidance in other countries and the OECD approach; later ICTD provided comment on the draft Ministerial Decree, which would articulate implementation details. Some of ICTD’s recommendations were implemented in the first Decree, while others were adopted later in the Finance Act 2024, and two further Decrees. ICTD’s recommendation to relax the Finance Act 2023 requirement that foreign digital platforms must appoint a tax representative in Senegal was adopted in a revision of the law made thorough the Finance Act 2024 and became operational in July 2024. This led to increased VAT revenue in the second half of 2024, with an additional 1.905 billion CFA Franc (c. £2.5 million) raised from digital services provided from abroad.

ICTD’s work with Rwanda Revenue Authority (RRA) to reduce compliance costs and confusion for taxpayers led to improved voluntary compliance and increased revenue. A cost-benefit analysis based on ICTD’s research showed a 1:12 return on investment, with every US $1 spent generating US $12 in additional revenue over six years. The intervention led to a 54% increase in tax payable, starting from a low baseline involving newly registered taxpayers. For the first two years it is estimated that US $16 additional revenue per taxpayer was collected. As new taxpayers were encouraged to declare, this is expected to increase to an additional US $302 per taxpayer in years three to six.

The Tax Treaties Explorer is free online tool that shows the details of about 3,000 tax treaties. It was originally launched by the ITCD in 2016 and updated in 2021 and 2023 with support from several funders. The 2023 update cost £20,648. There were no major changes made in 2024, and ongoing maintenance or updates are expected to be relatively low cost. The tool was still widely used and had nearly 5,000 unique visits from 147 countries and helped with research and policy work. People also kept requesting data, showing it is still useful. In 2024, the ICTD used the Tax Treaties Explorer to support treaty analysis in Nepal, Rwanda, and Mozambique. The tool enabled quick, high-quality insights with minimal staff time, saving 156 working hours (equivalent to £21,193 of senior researcher time). It supported research, government projects and policy discussion across all three countries and it is anticipated that annual savings could increase even further from those generated in 2024.

Assessment of whether the programme continues to represent value for money

The ICTD’s work aims to support increased revenue mobilisation and improve tax systems for greater equity, fairness, trust, and accountability. Quantifying impacts can be challenging due to the mix of measurable and non-measurable goals, the indirect and widespread effects of research, and difficulties in accurately attributing long-term outcomes. As such, the ICTD reports cost-effectiveness through VfM stories that combine quantitative and qualitative evidence to illustrate evidence of the VfM generated by the programme, covering different types of impact such as revenue impacts, tax system quality, research influence, efficiency, and engagement.

Analysis of the programme over the last year indicates that the programme continues to deliver strong value for money. It has successfully met its output targets and achieved good outcomes and impacts, partly through effective cost-saving measures.

E: RISK

The overall risk rating for the programme remains at Minor for the reporting period. All potential risks and mitigation actions are effectively managed through discussions between ICTD and FCDO, which help to adequately assess the severity of each risk and monitor progress of mitigation actions. The residual risks continue to remain within the cautious risk appetite. Risk ratings and key risks are summarised below.

Strategy & Context	Policy & Programme Delivery	Public Service & Delivery Operations	Financial & Fiduciary	Safeguarding	People	Reputa-tional	Overall
Moderate	Moderate	Minor	Minor	Moderate	Minor	Minor	Minor

Strategy and Context (moderate)

Global aid spending has changed dramatically since the last annual review with huge reductions in USAID spending. This is alongside broader financial turbulence linked to US implemented trade tariffs. The impact of these changes is still being realised. The changing security situations and the potential for conflict in the areas where the ICTD operates pose risks to researchers and the programme. To mitigate these risks, the ICTD collaborates with local partners in recipient countries. These partners understand the local contexts and associated risks, taking proactive measures and corrective actions as needed. Unless focussing on taxation and insecurity/conflict, the ICTD avoids more insecure areas. As of February 2024, fewer projects were being undertaken in fragile and conflict affected states.

Policy & Programme Delivery (moderate)

The key risk to programme delivery is that research outputs may not be of sufficient quality. To mitigate this, the ICTD has a robust selection and monitoring process to ensure high-quality research and outputs. New partnerships will be considered if the risk increases. The ICTD invests in local researchers and has a strong social media and web-based presence to publicise research calls for proposals.

The UK Government’s announcement of plans to reduce ODA to 0.3% GNI by 2027/28 has led to uncertainty about the funding available for research and development programming during this Spending Review.  The grant to ICTD currently runs until March 2027. FCDO and ICTD discuss finances as part of their regular financial meetings.

The ICTD programme team is well-balanced to manage changes, including staff turnover, without impacting the delivery and overall capacity. Although the ICTD has limited networks in South Asia for research, they continue to develop these.

Public Service and Delivery Operations (minor)
The programme monitors the risk that policy makers may not use the evidence provided. To address this, the ICTD has strong policy engagement strategies and maintains contacts with local policymakers to promote the research. Interest in taxation is growing across Africa, with governments recognising it as an important funding source. This wider interest helps mitigate the risk, and a similar outcome is expected as the work in South Asia expands.

Finance and Fiduciary (minor)

A key risk to the programme is uncertainty and reduced funding. Diversified sources of funding have enabled the ICTD to continue and FCDO has this year signed a no-cost extension to the programme until 31/3/2027.

The ICTD continues to monitor risks such as the misuse or appropriation of FCDO funds. Various financial policies are in place to mitigate these risks. A due diligence exercise confirms that the ICTD’s financial policies and procedures ensure transparency, business continuity, and appropriateness throughout the supply chain, with anti-fraud policies passed to downstream partners.

Safeguarding (moderate)

The safeguarding risks in the ICTD programme are moderate, as it is mainly with senior tax officials in other government institutions and international agencies. The FCDO emphasises the importance of recognising power inequalities among researchers and between researchers and policymakers, which affects safeguarding risk. The risk rating remains at moderate and remains stable and well mitigated by the ICTD. The ICTD implements various duty of care policies, including immediate response procedures for natural disasters or civil disturbances, and requires assurances from sub-contractors/grantees. Ethical reviews and project risk assessments are conducted before research starts, and data protection policies are in place. A risk register is completed for newly approved projects to detail and monitor safeguarding risks.

People (minor)

Analysis at the IDS is in place to mitigate risks for researchers operating in high-risk environments. The ICTD collaborates with local partners who understand the local landscape, security, and health risks, enhancing mitigation efforts. Risk management approaches developed during the Covid-19 Pandemic, such as remote working policies and improved fieldwork planning, continue to be implemented to further project colleagues and partners from global crises.

Reputational (minor)

The primary reputational risk identified is negative media coverage of FCDO funded tax research interventions. Close collaboration with FCDO helps to identify potential reputational risks early in the research process, allowing for timely corrective action.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Funding to ICTD is via an Accountable Grant Arrangement. The programme started in 2018 with an original end date of March 2023 and in 2023 it was extended to 31 March 2025 in. As a result of reductions in funding in earlier years, and following consultation between FCDO and ICTD in 2024, a time only extension was agreed to March 2027, at which point we assess the full amount of the agreed grant will have been disbursed.

Following the departure of the programme PRO, meetings between FCDO and ICTD had reduced earlier in the year but were resumed and there has been regular extensive engagement over the year on consultation of the programme and future work. A time only extension was agreed, with an AG amendment signed in 2024, following submission of a comprehensive proposal by ICTD. As part of the recommendations from last year, ICTD has submitted a three-year financial plan setting out its intended plans for diversification of funding. ICTD and FCDO have also completed a review of the logframe, which was agreed and updated in February 2025.

Key cost drivers are research input costs, knowledge dissemination and learning, and management costs.

2024/25 Quarterly Payments against original Forecasts
	Q1	Q2	Q3	Q4	Total
Forecast[6]	£352,027	£451,948	£606,590	£589,432	£1,999,997
Actual	£352,027	£415,080	£584,425	£648,467	£1,999,999
[6] The forecast figures are those provided early in the financial year, at the end of quarter 1.

The ICTD submits quarterly reporting with a detailed narrative of activities and spend each quarter and updates forecasts based on expenditure. Payments are made in arrears quarterly and based on the last reporting, the ICTD estimates full spend against the allocation of £2m for FY24/25. The forecast figures shown are those provided at the start of the year, and these are updated with quarterly reporting.

There are no programme assets and programme information up to 31 March 2025 was last updated to IATI on 29 May 2025.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

The ICTD uses various methods to ensure consistency and robustness. It has a detailed approval process with multiple review stages, including by a Research Advisory Group (RAG) of thematic experts. During fieldwork, gate reviews[7] are integrated into the contracting and sub-granting processes. These reviews help assess project quality and progress, allowing for timely feedback and adjustments to keep projects on track. In addition, ongoing monitoring is facilitated through regular engagement with colleagues and key partners along with regular meetings and in-country meetings with partner organisations. The ICTD also has regular stocktakes with the FCDO’s programme team where progress, including budgets/forecasts, risks and outputs, are discussed so action can be taken appropriately and timely.
[7] A Gate Review is a control point that determines whether a project can proceed to the next stage or phase. It is a formal project management step that confirms the project team completed the required processes and tasks, and that the project is worth continuing. Stakeholders review the project deliverables, milestones and risks and decide to approve or terminate the project.

This Annual Review was conducted in April jointly by a Governance Adviser and the Deputy Programme Manager (DPM) leading on ICTD, both from the Politics, Conflict and Humanitarian team (PCH), Research and Evidence Directorate (RED). This was a desk-based review of key documents, including the ICTD’s Annual Report. The evidence provided in the ICTD Annual Report was fact checked and triangulated with scheduled interviews with some key stakeholders such as the Rwanda Revenue Authority (RRA), the Uganda Federal Income Revenue Services (FIRs), HM Revenue & Customs (HMRC) as well as feedback from FCDO policy desks and post overseas. Internet searches were also completed for documentation mentioned in the ICTD report (publications, external journals, and publications of international institutions). e.g., the World Bank, the IMF, UN Habitat, UN General Assembly – Report of the Secretary General, and others, and international and national newspapers, and engagements such as seminars and conferences.

Evidence

ICTD has advanced its research and engagement across its key themes, overcoming challenges and capitalising on new opportunities to drive impact. The programme has in many areas exceeded the milestones set out under the grant from FCDO. The programme has continued to have success in publishing high quality cutting-edge research on gender and tax, informality, international tax and taxing the wealthy, with publications in prestigious journals such as World Development and the Journal of Economic Perspectives.

In the past year the ICTD has scaled up efforts to engage with key actors in the thematic areas of this grant and contribute to evidence-based insights to global debates. In collaboration with the Centre for Sustainable Development at the Brookings Institution they launched the Community of Practice for Gender and Tax and on informality, worked with the Africa Tax Administration Form (ATAF) in the organisation of their African Tax Network (ATRN) Annual Conference held in Botswana. The ICTD has also developed a four-year strategy that sets key objectives on research, operations, and communications and engagement, as well as a roadmap to achieve them.

Learning

The ICTD engages with FCDO policy teams, including the FCDO Public Finance and Tax Department (PFTD) and the Community of Practice (CoP) on Public Finance, and posts overseas to disseminate research findings and policy recommendations. This year FCDO funded research was shared with Rwanda, Uganda, Sierra Leone, Ghana, Pakistan, and Ethiopia.

Date of last narrative financial report	6/3/25	Date of last audited annual statement	31/3/24

ANNEXES
## ANNEX 1: FCDO support collaborations with FCDO staff or advisers to support their tax programme

Month	Details of Support
January 2024	Wilson Prichard, Mick Moore and Giulia Mascagni led a community of practice webinar for FCDO PFTD on “Leveraging research programs to strengthen country level support: lessons from ICT the experience”. / (1/2 day -)
February 2024	Martin Hearson and other team members spoke to the BHC staff while in Accra - a talk given at the embassy at Eileen Rafferty’s request. / (1/2 day -)
February 2024	Wilson Prichard travelled to Rwanda to present at an FCDO retreat for their public finance and tax advisors from the East African region. He presented on “integrating political economy analysis into (tax) reform”. Sessions involved all PTFD advisors from the region. He also had a couple of separate discussions with Antonia Strachey, from PFTD, in the lead up to the event and to help share ideas about design. While in Rwanda, Wilson also had a separate extended meeting with the tax advisor in the FCDO Rwanda office, Zephy Muhirwa, during which they discussed FCDO’s overall strategy for supporting property tax reform in Rwanda, and Wilson offered advice on their programming. (1/2 day +)
March 2024	Wilson Prichard and Giulia Mascagni met with Angela Bellmooney and Rajesh Kishan from FCDO PTFD to discuss ICTD’s experiences working in partnership with ATAF and offer advice on their programming. (1/2 day -)
March 2024	Wilson Prichard met with Mark Dray and Israel Fekade from the FCDO office in Ethiopia, where they serve as economic advisors focusing on public finance and tax. They discussed possible options for FCDO support to property tax reform, and the general dynamics of those reform efforts. (1/2 day -)
March 2024	Martin Hearson led a session at this academic workshop in Oxford on UN GA Resolution 78/230 on the Promotion of Inclusive and Effective International Tax Cooperation at the United Nations. Frederik Heitmuller and Mbakiso Magwape also participated. It was a discussion bringing together academics and several key policy stakeholders. FCDO and HMT were there for the whole workshop. There was also a follow up workshop in July where Imraan from FCDO mentioned he would be interested in speaking with ICTD more often on international tax issues. (1/2 day +)
April 2024	Wilson Prichard gave presentations to FCDO Community of Practice on April 17, 2024 “Change that lasts: Principles of Program Design for Property Tax Reform” (1/2 day +)
May 2024 (and previous months)	Between September 2023 and May 2024, Giulia Mascagni met several times with Samantha Miller from HMRC and FCDO, while she was an advisor at the RRA. Samantha was supporting the RRA leadership in the process of institutional transformation while Giulia was leading a project investigating institutional culture amongst tax officials, and how it affects compliance. They met several times to make sure the research insights would feed into and support Samantha’s role, while the presence of an FCDO advisor at RRA was essential to open new connections with the HR department who was anchoring the cultural transformation process and used ICTD’s research in that context. (1/2 day +)
May 2024	Vanessa van den Boogaard and Giovanni Occhiali met with the FCDO in Sierra Leone (Kate O'Loughlin, Eileen Rafferty) to advise on their new "Expertise to Support Economic Reform in Sierra Leone Programme", which is currently proposed to include a strong focus on local government taxation (diagnostic studies), engagement between traditional authorities and local councils, and expansion of the tax net through BMS. The programme is being managed by ASI and is worth 2 million GBP over 1.5 years. (1/2 day -)
May 2024	Wilson Prichard was contacted by the FCDO India Office for support related to thinking about potential property tax reform priorities, including meeting with Abhirup Dasgupta, Head Economic Cooperation, Hirawati Gokhali, Senior Advisor, and Dom O’Connell on May 7th. Has also involved repeated email exchange, sharing of a wide range of materials and discussion of potential future collaborative steps. (1/2 day -)
June 2024	Martin Hearson and Awa Diouf gave a presentation to the FCDO Community of Practice on DIGITAX Component 1 (1/2 day -)
June 2024	Vanessa van den Boogaard and Max Gallien met with Dr Antonia Strachey, East Africa Regional Tax Advisor at the Public Finance and Tax Department at the FCDO. She had reached out because of an interest in the ICTD's work on taxation and conflict and armed group taxation. We discussed a wide variety of the ICTD's work in this area and agreed to stay in touch on the topic going forward, with a potential dedicated community of practice or roundtable session. We spoke about the topic both with a particular focus on East Africa and more global insights, including plans for future work in this area, and pitching these themes more effectively to a PFM audience. / (1/2 day -)
June 2024	Vanessa van den Boogaard and Giovanni Occhiali, met with Charles Denton, leading the HMRC's capacity building programme in Sierra Leone. Discussed key challenges + needs of NRA/ MRP specifically, shared our work with the NRA, planned to continue engaging as things progress on both sides. (1/2 day -)
July 2024	Wilson Prichard had a bilateral meeting with Antonia Strachey, Advisor at FCDO Rwanda, about possible property tax reform programs, rental income tax reform and possible collaboration with the Rwanda Revenue Authority. (1/2 day -)
September 2024	Martin Hearson co- organised the Reimagining Global Tax Governance https://oxfordtax.sbs.ox.ac.uk/event/reimagining-global-tax-governance-conference at Oxford University, including chairing a panel of political scientists. One of his contributions was to ensure a broader participation from the global South as commentators on papers. As well as the academics listed on the agenda, the event was attended by some policy actors, in particular Imran Hokam-Dahd from FCDO, some Treasury people and Dimitrij Konsewitch from GIZ. (1/2 day +)
October 2024	Max Gallien met with Miljan Sladoje & Alistair Lobo to discuss ICTD positioning, research and policy interests in relation to tax & debt more broadly as well as the FFD process. one topic of discussion was tax targets / 'what can countries raise' issue. We shared our policy brief on this and how we are developing that work. (1/2 day -)
November 2024 and December 2024	Martin Hearson, Fabrizio Santoro and Florian Dierich undertook a tailored literature review, analysis and synthesis of evidence relating to the effectiveness and cost-effectiveness of Public Finance Management and Tax reforms/interventions - to inform the development of a Best Buy paper for Public Financial Management (PFM) and Tax. This comprised numerous days of work from the core team of three plus a half day each from a number of associated fellows (1/2 day +)
December 2024	Max Gallien and Giovanni Occhiali attended the ATAF Annual Meeting in Kigali as delegates as well as acting as panellists. Giovanni presented on a panel on EOI, Max presented on a side event panel on taxing informal economies, which also launched an ICTD-ATAF joint policy brief. Both events were very well attended. Throughout the event, we met with a variety of partners and revenue authorities, and ICTD was visible as an organisation at the event, which included around 500 guests in total, including a range of CGs and RA staff from all ATAF members. Aside from these conversations, we also had meetings with our FCDO colleagues with some planned next steps: / - with Angela Bellmooney on setting up a learning journey on taxing HNWIs / - with Antonia Strachey on presenting an overview of our work with the URA early next year to the Kampala BHC as they are thinking of potentially ramping up their DRM work in the country (1/2 day +)
December 2024	Awa Diouf participated in a meeting on December 18th, 2024, with representatives from FCDO, IISD, TaxDev, and ICTD to discuss how to collectively provide feedback on the updated PCT Tax Incentives Toolkit. This consultation, requested by PCT partners (IMF, OECD, UN, and WBG), aims to refine high-level principles guiding policymakers on tax incentives, particularly for developing countries. The meeting's objective was to agree on a collaborative approach to give feedback. After discussions, it was decided that organisations would submit individual feedback, complemented by a joint cover letter to demonstrate coordination. ICTD expressed interest in contributing, particularly by leveraging our practical insights from Africa.
December 2024	Co-hosted by the International Centre for Tax and Development (ICTD) and the Rwanda Revenue Authority (RRA), our conference– themed ‘Towards a Digital Tax Administration: Lessons learnt and directions for reform’ – featured a selection of panels that tackled in-depth issues critical to the digitalisation agenda. These ranged from data management and governance to public infrastructure, to inclusion. During the conference Giulia Mascagni had dinner with Antonia Strachey. James Murdoch, Fabrizio Santoro and Giulia Mascagni also had a meeting at the High Commission to present ICTD's work in Rwanda and discuss future directions in tax research and FCDO priorities in the region. FCDO attended the conference itself and contributed as panellists.

## ANNEX 2: List of Publications

#	Publication	Title	Date	Authors: Southern/ Northern/ Both
Working Papers
1	WP179	Msiska, T. and Thawe, M. (2024) Resolving Tax Disputes: Market Vendors and Local Councils in Malawi, ICTD Working Paper 179, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.002	Jan 24	Southern
2	WP180	Yimam, S,; Lidetu, K. and Belete, T. (2024) E-tax System Adoption and Tax Compliance in Ethiopia: Large and Medium Taxpayers’ Experience, ICTD Working Paper 180, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.003	Jan 24	Southern
3	WP181	Banga, K. and Beyleveld, A. (2024) Are Trade Rules Undermining Taxation of the Digital Economy in Africa?, ICTD Working Paper 181, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.007	Feb 24	Both
4	WP182	Henn, S.J.; Marchais, G.; Mastaki Mugaruka, C.; Sánchez de la Sierra, R. (2024) Indirect Rule: Armed Groups and Customary Chiefs in Eastern DRC, ICTD Working Paper 182, DOI: 10.19088/ICTD.2024.011	Feb 24	Both
5	WP185	Grieco, K. (2024) Can Rural Property Tax Generate Revenue? A Simple Accounting Exercise in Sierra Leone, ICTD Working Paper 185, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.010	Mar 24	Northern
6	WP186	Joshi, A.; Kangave, J. and van den Boogaard, V. (2024) Engendering Taxation: a Research and Policy Agenda, ICTD Working Paper 186, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.017	Mar 24	Both
7	WP 187	Falcão, Tatiana (2024) A Climate Treaty for the Global Taxation of Carbon, ICTD Working Paper 187, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.022	Apr 24	Southern
8	WP188	Occhiali, G.; Kangave, J. and Khan, H.A. (2024) Taxing High Net Worth Individuals in Nigeria: Preliminary Insights and the Case of Borno State, ICTD Working Paper 188, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.024	Apr 24	Both
9	WP 190	Grieco, K. (2024) Building Fiscal Capacity with Traditional Political Institutions: Experimental and Qualitative Evidence from Sierra Leone, ICTD Working Paper 190, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.028	May 24	Northern
10	WP 191	Wampler, B.; Touchton, M. and Kiprono, T. (2024) Building Trust and Tax Morale in Kenya’s Counties: An Evaluation of Participatory Budgeting, ICTD Working Paper 191, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.049	Jul 24	Southern
11	WP 193	Bergeron, A.; Kabue Ngindu, E.; Tourek, G. and L. Weigel, J. (2024) 'Does Collecting Taxes Erode the Accountability of Informal Leaders? Evidence from the DRC', ICTD Working Paper 193, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.046	Jun 24	Both
12	WP 195	Anyidoho, N.A.; Gallien, M.; Rogan, M. and van den Boogaard, V. (2024) The Price of Simplicity: Skewed and Regressive Taxation in Accra’s Informal Sector, ICTD Working Paper 195 Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.044	Jun 24	Both
13	WP 196	Mahajan, A.; Mittal, S.; Reich, O. and Barwahwala, T. (2024) Using Machine Learning to Catch Bogus Firms, ICTD Working Paper 196, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.050	Jun 24	Both
14	WP 197	Ahrenshop, M. (2024) 'Tax Earmarking and Political Participation: Theory and Evidence from Ghana', ICTD Working Paper 197, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.051	Jun 24	Northern
15	WP 198	Yimam, S.; Arega, T. and Occhiali, G. (2024) Evaluating Ethiopia’s Environmental Strategy: Does it Support Green Growth?, ICTD Working Paper 198, Brighton Institute of Development Studies, DOI: 10.19088/ICTD.2024.053	Jun 24	Both
16	WP 199	Kangave, J. and Rukundo, S. (2024) 'Does Having More Women in Parliament Result in More Gender-Sensitive Tax Policies? A Case Study of Uganda’s Parliament', ICTD Working Paper 199, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.055	Jun 24	Southern
17	WP 200	Traore, R.J. (2024) La politique d’harmonisation fiscale au sein de l’Union Économique et Monétaire Ouest Africaine : analyse et perspectives, Document de travail de l’ICTD 200, Brighton: Institute of Development Studies, DOI : 10.19088/ICTD.2024.058	Jul 24	Southern
18	WP 204	Lees, A. and Mascagni, G. with Yimam, S.; Gebretsadik, G. and Ndajiwo M. (2024) Research Within Tax Administration: from Monitoring Revenue to Influencing Policy, ICTD Working Paper 204, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.066	Jul 24	Both
19	WP 205	Chalise, B. (2024) Do Double Taxation Avoidance Agreements Attract Foreign Direct Investment The Case of Nepal, ICTD Working Paper 205, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.076	Aug 24	Southern
20	WP 206	Occhiali, G. and Okello, O. (2024) Taxation of Fisheries in Kenya: Neither Improving Management nor Raising Revenue?, ICTD Working Paper 206, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.084	Aug 24	Both
21	WP 207	Gupta, B.; Velayudhan, T.; Dhawan, P. and Garg, A. (2024) Why Don’t Firms File Tax Returns on Time? Evidence from the Indian GST, ICTD Working Paper 207, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.086	Sept 24	Southern
22	WP 208	Manwaring, P. and Regan, T. (2024) Public Disclosure and Tax Compliance: Evidence from Uganda, ICTD Working Paper 208, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.063	Sept 24	Both
23	WP 210	Edeh, H.C. (2024) The Effect of the Liberian Government’s Taxation Policies on Poverty and Inequality, ICTD Working Paper 210, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.102	Oct 24	Southern
24	WP 212	Kuhn, K.; Cadzow, L.; Heitmüller, F.; Hearson, M. and Randriamanalina, T. (2024) The International Tax Regime Complex: Understanding Change in Global Tax Governance, ICTD Working Paper 212, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.105	Oct 24	Both
25	WP214	Haberly, D. (2024) ‘A New Map of World FDI: Estimating Sources and Pathways of Offshore Investment in Major Developed and Developing Economies, ICTD Working Paper 214	Dec 24	Northern

African Tax Administration Papers
1	ATAP 34	Groening, E.; Moore, M.; Mukama, D. and Waiswa, R. (2024) 'Pathways into the Tax Net: Better Ways to Register African Taxpayers', ICTD African Tax Administration Paper 34, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.029	May 24	Both
2	ATAP 36	Mayega, J.; Waiswa, R. and Nabuyondo, J. (2024) How Clean is Customs Data? Data Management in Uganda Revenue Authority, ICTD African Tax Administration Paper 36, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.082	Aug 24	Southern
3	ATAP 37	Nyirakamana, C.; van den Boogaard, V. and Ahmed W. (2024) Land and Property Taxation to Finance Urban Development in Somaliland: Challenges and Prospects for Reform, ICTD African Tax Administration Paper 37, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.083	Aug 24	Both
4	ATAP 38	Sulu, N. and Moore, M. (2024) Improving Revenue Collection in Malawi. Tax Collectors’ Perspectives, ICTD African Tax Administration Paper 38, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.108	Oct 24	Both

Policy Briefs
1	PB5	Grown, C. and Mascagni, G. (2024) Towards Gender Equality in Tax and Fiscal Systems: Moving beyond the Implicit-Explicit Bias Framework, ICTD Policy Brief No. 5, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.015	Mar 24	Northern
2	PB6	Gallien, M., Lees, A., and Mascagni, G. (2024) ‘Getting Targets Right: How Much Revenue can Lower-Income Countries Raise?,’ ICTD Policy Brief 6, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.016	Mar 24	Northern
3	PB 9	Tilahun, N. and Yihdego, A. G. (2024) Unsuccessful Implementation of the OECD Transfer Pricing Guidelines in Low-Income Countries: The Case of Ethiopia, ICTD Policy Brief 9, Brighton: Institute of Development Studies DOI: 10.19088/ICTD.2024.033	May 24	Both

Research in Briefs
1	RIB 103	Are Trade Rules Undermining Taxation of the Digital Economy in Africa?	Mar 24	Southern
2	RIB 106	East, S. (2024) Is Transparency Enough? An Examination of the Effect of the Extractive Industry Initiative (EITI) on Accountability, Corruption and Trust in Zambia, ICTD Research in Brief 106, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.020	Apr 24	Northern
3	RIB 107	Archibong, B.; Moerenhout, T. and Osabuohien, E. (2024) Protests, Fiscal Redistribution, and Government Responses: Evidence from Nigeria, ICTD Research in Brief 107, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.025	Apr 24	Both
4	RIB 108	Thakur, S. (2024) Not-So-Freeway: Informal Highway Taxation and Armed Groups in North-East India, ICTD Research in Brief 108, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.027	May 24	Southern
5	RIB 109	Groening, E.; Moore, M.; Mukama, D. and Waiswa, R. (2024) Pathways Into the Tax Net: Better Ways to Register African Taxpayers, ICTD Research in Brief 109, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.031	May 24	Both
6	RIB 110	Joshi, A.; Kangave, J. and van den Boogaard, V. (2024) Engendering Taxation: A Research and Policy Agenda, ICTD Research in Brief 110, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.03	May 24	Both
7	RIB 113	Yimam, S.; Asmare, F. and Moore, M. (2024) Does Competition from the Informal Sector Reduce Tax Compliance in the Formal Sector? Evidence from Ethiopia, ICTD Research in Brief 113, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.037	May 24	Both
8	RIB 115	Asmare, F.; Yimam, S. and Semreab, E. (2024) Presumptive Taxation and Equity: Evidence from the Ethiopian Informal Sector, ICTD Research in Brief 115, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.041	May 24	Southern
9	RIB 117	Yimam, S. and Mekonnen, Y. (2024) Women in Ethiopian Tax Administration: Evidence on Representation and Performance, ICTD Research in Brief 117, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.041	Jun 24	Southern
10	RIB 119	Ahrenshop, M. (2024) Tax Earmarking and Political Participation: Theory and Evidence from Ghana, ICTD Research in Brief 119, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.052	Jun 24	Northern
11	RIB 120	Yimam, S.; Arega, T. and Occhiali, G. (2024) Evaluating Ethiopia’s Environmental Strategy: Does it Support Green Growth?, ICTD Research in Brief 120, Brighton Institute of Development Studies, DOI: 10.19088/ICTD.2024.054	Jun 24	Both
12	RIB 126	Yimam, S.; Lidetu, K. and Belete, T. (2024) E-tax System Adoption and Tax Compliance in Ethiopia: Large and Medium Taxpayers’ Experience, ICTD Research in Brief 126, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.067	Jul 24	Southern
13	RIB 127	Gupta, B.; Velayudhan, T.; Dhawan, P. and Garg, A. (2024) Why Don’t Firms File Tax Returns on Time? Evidence from the Indian GST, ICTD Research in Brief 127, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.085	Jul 24	Southern
14	RIB 128	Wampler, B.; Touchton, M. and Kiprono, T. (2024) Building Trust and Tax Morale in Kenya’s Counties: An Evaluation of Participatory Budgeting, ICTD Research in Brief 128, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.097	Jul 24	Southern
15	RIB 129	Msiska, T. and Thawe, M. (2024) Resolving Tax Disputes: Market Vendors and Local Councils in Malawi, ICTD Research in Brief 129, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.072	Jul 24	Southern
16	RIB 130	Falcão, T. (2024) A Climate Treaty for the Global Taxation of Carbon, ICTD Research in Brief 130, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.073	Jul 24	Southern
17	RIB 131	Grieco, K. (2024) Building Fiscal Capacity with Traditional Political Institutions: Experimental and Qualitative Evidence from Sierra Leone, ICTD Research in Brief 131, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.074	Jul 24	Northern
18	RIB 132	Occhiali, G.; Kangave, J. and Khan, H. A. (2024) Taxing High Net Worth Individuals in Nigeria: Preliminary Insights and the Case of Borno State, ICTD Research in Brief 132, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.075	Jul 24	Both
19	RIB 133	Chalise, B. (2024) Do Double Taxation Avoidance Agreements Attract Foreign Direct Investment? The Case of Nepal, ICTD Research in Brief 133, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.077	Jul 24	Southern
20	RIB 134	Occhiali , G.; Falade, M. and Quak, E.-j. (2024) Missing the Forest for the Trees: Ekiti State’s Quest for Forestry Revenue and its Impact on Forest Management, ICTD Research in Brief 134, Brighton: Institute of Development Studies, DOI: 10.19088/ ICTD.2024.078	Jul 24	Both
21	RIB 135	Occhiali, G. and Quak, E.-j. (2024) Implementation Obstacles and Political Appeal of Environmental Taxes in Sub-Saharan Africa: Reflections from Selected Countries, ICTD Research in Brief 135, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.079	Jul 24	Northern
22	RIB 136	Bergeron, A.; Ngindu, E.K.; Tourek, G. and Weigel, J.L. (2024) Does Collecting Taxes Erode the Accountability of Informal Leaders Evidence from the DRC, ICTD Research in Brief 136, Brighton: Institute of Development Studies, DOI 10.19088/ICTD.2024.087	Sept 24	Both
23	RIB 137	Manwaring, P. and Regan, T. (2024) Public Disclosure and Tax Compliance: Evidence from Uganda, ICTD Research in Brief 137, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.088	Sept 24	Northern
24	RIB 138	Gallien, M.; Occhiali, G.; Ross, H. and Quak, E. (2024) An Overlooked Market: Loose Cigarettes, Informal Vendors, and Their Implications for Tobacco Taxation, ICTD Research in Brief 138, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.095	Sept 24	Northern
25	RIB 139	Kangave, J.; Occhiali, G.; Kamara, I. and Quak, E. (2024) How Might the National Revenue Authority of Sierra Leone Enhance Revenue Collection by Taxing High Net Worth Individuals?, ICTD Research in Brief 139, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.096	Sept 24	Northern
26	RIB 140	Anyidoho, N.A.; Gallien, M.; Rogan, M. and van den Boogaard, V. (2024) The Price of Simplicity: Skewed and Regressive Taxation in Accra’s Informal Sector, ICTD Research in Brief 140, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.098	Oct 24	Both
27	RIB 142	Bergeron, A.; Fournier, A.; Kabeya, J.K.; Tourek, G. and Weigel, J.L. (2024) Using Machine Learning to Create a Property Tax Roll: Evidence from the City of Kanaga, D.R. Congo, ICTD Research in Brief 142, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.101	Oct 24	Both
28	RIB 143	Edeh, H.C. with Scarpini, C. (2024) The Effect of the Liberian Government’s Taxation Policies on Poverty and Inequality, ICTD Research in Brief 143, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.103	Oct 24	Both
29	RIB 145	Kangave, J. and Rukundo, S. (2024) Does Having More Women in Parliament Result in More Gender-Sensitive Tax Policies? A Case Study of Uganda’s Parliament, ICTD Research in Brief 145, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.106	Nov 24	Southern
		French publications
30	RIB94	Gallien, M.; Javed, U . et van den Boogaard, V. (2023) Entre Dieu, le peuple et l’État : les conceptions citoyennes de la Zakat, ICTD Résumé de recherche numéro 94, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2024.019	Sept 24	Both
31	RIB97	Bandula-Irwin, T.; Gallien, M.; Jackson, A.; van den Boogaard, V. et Weigand, F. (2023) Beyond Greed: Why Armed Groups Tax, ICTD Résumé de recherche numéro 97, Brighton: Institute of Development Studies, DOI: 10.19088/ICTD.2023.044	Sept 24	Northern

Journal Articles / Book chapters
1	JA 88	Mascagni, G., Santoro, F. & Mukama, D. Teach to comply? (2024) Evidence from a taxpayer education program in Rwanda. Int Tax Public Finance. https://doi.org/10.1007/s10797-023-09809-6	Jan 24	Both
2	JA89	Brockmeyer, A., Mascagni, G., Nair, V., Mazhar, W. and Almunia, M. (2024) Does the Value-Added Tax Add Value? Lessons Using Administrative Data from a Diverse Set of Countries. Journal of Economic Perspectives, 38 (1): 107-32. DOI: 10.1257/jep.38.1.107	Feb 24	Both
3	JA 90	Mbakiso Magwape, 'Article: Agenda Setting and Decision Making under the OECD/G20 IF and the WTO – Developing Countries and Reform', (2024), 52, Intertax, Issue 4, pp. 270-293, https://doi.org/10.54648/taxi2024033	Apr 24	Southern
4	JA 91	Shehaj, P., & Zagler, M. (2024). Asymmetric Double Tax Treaties: Relief Method and Tax Sparing for Foreign Direct Investment in Developing Countries. Public Finance Review, 0(0). https://doi.org/10.1177/10911421241247241	May 24	Both
5	JA 92	Occhiali, G. (2024) 'Obstacles and appeal of environmental taxation: Insights from sub-Saharan Africa', Environmental Development, 51: 101037	Oct 24	Northern
6	JA 93	Prichard, W., Jibao, S. and Orgeira Pillai, N. (2024) Sub-national property tax reform and tax bargaining: Lessons from a quasi-randomized reform program in Sierra Leone, World Development, Volume 185.	Oct 24	Northern
7	JA 94	Gallien, M., Javed, U. & van den Boogaard, V. Zakat, Non-state Welfare Provision and Redistribution in Times of Crisis: Evidence from the Covid-19 Pandemic. St Comp Int Dev (2024). https://doi.org/10.1007/s12116-024-09447-x	Oct 24	Both
8	JA 95	Anyidoho, N. A.; Gallien, M.; Rogan, M. and van den Boogaard, V. (2024) The taxed informal economy: Fiscal burdens and inequality in Accra, World Development, 187, DOI: 10.1016/j.worlddev.2024.106879.	Dec 24	Both
9	JA	Influence of Domestic Constituencies in the Implementation of International Tax Standards and Legitimacy of Global Tax Governance / Juliana Cubillos González, Frederik Heitmüller Intertax Volume 52, Issue 3 (2024) pp. 207 – 225 / https://doi.org/10.54648/taxi2024027	Mar 24	Both
1	BC21	OECD (2024), Development Co-operation Report 2024: Tackling Poverty and Inequalities through the Green Transition, OECD Publishing, Paris, https://doi.org/10.1787/357b63f7-en.	Jul 24	Northern

## ANNEX 3: High-level external engagement 2024 (most recent listed first)

Date	Engagement	Type
Dec-24	On 18th of December, Awa Diouf participated in a consultation meeting along with representatives from FCDO, the International Institute for Sustainable Development, and TaxDev, on how to collectively provide feedback on the Tax Incentives Toolkit of the Platform for Collaboration on Tax (PCT), as requested by PCT partners (IMF, OECD, UN, and the World Bank Group). ICTD expressed interest in contributing by leveraging its practical insights based on work in Africa.	Policy
Dec-24	Fabrizio Santoro held a half-day training session on research methodology with the Rwanda Revenue Authority (RRA) research team upon their request.	Academic
Dec-24	Frederik Heitmuller presented at a meeting organised by Centro Para Democracia e Direitos Humanos (a Mozambique-based civil society organisation) and SOMO (a Dutch civil society organisation). The meeting was a part of a series that aims to elaborate on a tax treaty policy for Mozambique. Frederik focused on the motives behind entering into, terminating, and renegotiating tax treaties, drawing significant interest from attendees, which included members of tax administration, Ministry of Finance, and other relevant institutions (i.e. Ministry of Commerce, Customs Administrations).	Civil Society
Dec-24	Kigali, Rwanda: A team from ICTD – Giulia Mascagni, Martin Hearson, Giovanni Occhiali, Max Gallien, and Daisy Ogembo – met with members of the Kenya Revenue Authority (KRA) and the Kenya School of Revenue Administration (KESRA) to discuss several ongoing projects and engagements and the possibility of executing a pilot engagement. Immediate next steps agreed include potential collaboration on an event on informality and taxation, and on the work on taxing high net worth individuals with ATAF.	Policy
Dec-24	Kigali, Rwanda: Giulia Mascagni held two meetings with the Commissioner General and Deputy Commissioner General of the Rwanda Revenue Authority (RRA) at the sidelines of ICTD’s conference. The meetings centred on touching base on the existing collaboration between ICTD and RRA 10 years on, as well as key insights and recommendations from an ICTD project on tax officials, and how ICTD can further contribute to RRA’s plans and priorities in the coming years.	Policy
Dec-24	Jalia Kangave represented ICTD at an event hosted by RELX to launch the publication of consolidated tax laws of Ethiopia. It was attended by the Deputy Head of Mission of Ethiopia’s Embassy, a representative of FCDO, and RELX staff, among others.	Policy
Dec-24	The World Bank team in the Sahel Region reached out to Fabrizio Santoro after going through the ICTD study on e-tax in Burkina Faso to explore potential collaboration and learning opportunities for all countries in the region. Fabrizio presented learnings from the DIGITAX Research Programme, while his external co-authors for the paper, Jule Kaini Tinta and Mouhamed Zerbo, shared insights specific to Burkina Faso.	Policy
Dec-24	Marco Carreras and Fabrizio Santoro had an online introductory call, as part of ICTD’s work on tax and digitalisation, with Dr Caetano Penna, Director of the Brazil-based Centre for Strategic Studies and Management (CGEE), to discuss common research interests and possible collaboration.	Academic
Dec-24	Fabrizio Santoro presented at a virtual panel, entitled ‘Digital Public Infrastructure meets tax digitalisation – what can we learn?’ co-hosted by ICTD and the World Bank.	Academic
Dec-24	Through the invitation of Andrew Debalen from the World Bank, Giulia Mascagni gave a virtual presentation on tax reform – with particular focus on our work on tax targets, digitisation, and taxing the wealthy (including property taxes) as examples of reforms to increase revenue and equity – at a closed meeting with a group of 18 Chief Economists of governments across Africa.	Policy
Dec-24	Kigali, Rwanda: Max Gallien and Giovanni Occhiali presented on two panels during the Annual Meeting of the African Tax Administration Forum (ATAF) – Gio presented on Exchange of Information (EOI) for tax purposes, and Max on a side-event panel on taxing informal economies (with ar. During Max’s panel, ICTD and ATAF launched a joint-policy brief on the topic. Both panels had significant attendance, with around 300 for the EOI session, and 100 for the one on informal taxation.	Policy
Dec-24	During the above event, Max Gallien and Giovanni Occhiali also met with FCDO colleagues, specifically Angela Bellmooney to discuss setting up a learning journey on taxing high net worth individuals, and Antonia Strachey to discuss presenting an overview of ICTD work with the Uganda Revenue Authority in early 2025 to the Kampala British High Commission.	Policy
Dec-24	Nepal: Martin Hearson had several engagements during his trip to Nepal: He met with British Ambassador, Rob Fenn, to brief the latter on his research project funded by the UK Department for Business and Trade, exploring the prospects for a UK-Nepal tax treaty. During the meeting, Martin also gave an introduction of ICTD.	Policy
Dec 24	In Nepal, Martin Hearson also met with Mehdi Rizvi, a GIZ representative in Nepal who leads its tax work, to discuss a common interest in focusing on digitalisation.	Policy
Dec-24	Martin and external author Bishal Chalise presented their work on tax treaties, including on double taxation avoidance agreements, at the Ministry of Finance in Nepal, with the joint secretaries and revenue secretary in attendance, among others.	Policy
Nov-24	Martin Hearson met with the deputy director of the Inclusive Financial Systems department of the Gates Foundation to discuss a study they are doing on regulations affecting digital financial services in nine countries (Bangladesh, Ethiopia, India, Indonesia, Kenya, Nigeria, Pakistan, Tanzania, and Uganda), for which one component is tax. Martin provided insights on tax policies, particularly surrounding mobile money in African countries.	Civil Society
Nov-24	Martin Hearson had an online call with Iyabo Masha, director of the G24, to discuss potential interface of their work with ICTD. This includes engagement with the G20 process and that of the Fourth Financing for Development Conference, and new areas of focus for the G24, including taxing the wealthy and climate finance taxes.	Policy
Nov-24	Johannesburg, South Africa: Fabrizio Santoro spoke at a panel on digital public infrastructure (DPI), providing a tax perspective, at the International Conference on Public Finance in the Digital Era, hosted by ODI and the Collaborative Africa Budget Reform Initiative (CABRI).	Academic
Nov-24	Fabrizio Santoro and Seid Yimam discussed a potential partnership with the Ethiopian Economics Association on digital integration for tax.	Academic
Nov-24	Giovanni Occhiali, Wilson Prichard and Jalia Kangave presented various pieces of work related to property and rental income taxation to the Benue Internal Revenue Services and the Benue State Attorney general to foster future collaboration	Policy
Nov-24	Giovanni Occhiali delivered a seminar on data and analytica needs for a successful implementation of environmental taxes in lower income countries to the Addis Tax Initiative	Policy
Oct-24	Vanessa van den Boogaard presented at the Governance and Local Development (GLD) annual meeting in October 2024 on "Traditional authorities and local revenue collection in Sierra Leone"	Academic
Oct-24	Giovanni Occhiali was invited by Tax Justice Network Africa to deliver the seminar on "Environmental taxation in Africa: Are they effective in curbing environmental damage?" for their CSO learning event on the connection between climate and tax justice. Over 30 different participants from TJNA or from various organisations were in attendance.	Civil Society
Oct-24	IDS members seminar: Digital Public Infrastructure and Taxation: Lessons Learned and Ways Forward This seminar aimed at spurring a discussion around the potential of digital public infrastructure (DPI) to strengthen governments in low-income countries, with a focus on Africa. DPI, consisting of three pillars - digital ID, digital payments and data exchange systems -, has emerged as a revolutionising game-changer for the digital transformation of governments and societies. The DPI concept builds on open-source, interoperable and scalable pillars – akin to Lego blocks – which can be assembled and combined to create inclusive, resilient and adaptable digital solutions. Speakers: Fabrizio Santoro, IDS, Caroline Khene, IDS and Celeste Scarpini, IDS. Chair: Martin Hearson, IDS	Academic
Oct-24	Max Gallien attended a range of plenary and Civil Society Policy Forum events on taxation and had a set of side meetings at the WB/IMF Annual Meetings. This was not related to a particular project, but some meetings were particularly relevant to WB-ICTD collaborations on presumptive taxes and on some of the potential future work on tax and debt.	Civil Society
Oct-24	Awa Diouf attended the 2024 CATA Technical Conference, themed "Reshaping Tax Administration in a Dynamic Landscape," in Mauritius from October 21–25, 2024. Awa moderated Session 3: Countering Tax Non-Compliance from Digital Operators. This session focused on safeguarding VAT revenue amidst growing digital transactions and explored country-specific strategies for tracing and recovering VAT from online platforms. As well as moderating Awa participated in a working session on the “Effectiveness of the Automatic Exchange of Information (AEOI) in Combating Tax Evasion”.	policy
Oct-24	Martin Hearson presented a summary of ICTD’s work on the Inclusive Framework and UN tax convention to an academic audience at the LSE event Making Global Tax Governance Fit for the 21st Century. It was attended by Lakshmi Naryanan from the Indian High Commission, and Peter Hurst now working for UNDP.	Academic
Oct-24	Max Gallien met with Miljan Sladoje (IGC) & Alistair Lobo (FCDO) to discuss ICTD positioning, research and policy interests in relation to tax & debt more broadly as well as the FFD process.	Policy
Oct-24	Wilson Prichard attended a closed-door event hosted by the African Mayoral Leadership Initiative (AMALI). The AMALI program annually recruits a group of 10-15 high profile and ambitious mayors across Africa, who then participate in a two-year strategic leadership and strategic support program designed to support them in delivering their reform agendas. Will was recruited to the program to act as the lead resource person and mentor. In attendance were the Mayors/Governors of: Kenya (Nairobi and Kajiado), Namibia (Windhoek), Zimbabwe (Bulawayo), Zambia (Chongwe, Mansa and Ndola), Ethiopia (Harar), and Sierra Leone (Freetown). Below are some key engagements from this trip:	Policy
Oct-24	Nairobi, Kenya: Wilson Prichard had an in-depth discussion with the Governor, as well as his director of finance, about potential directions for property tax reform in Nairobi, with an agreement to continue those discussions and explore potential reform collaboration. The central focus of the discussion was strengthening property mapping and valuation.	Policy
Oct-24	Windhoek, Namibia: Wilson Prichard had an in-depth discussion with the mayor, and her head of external partnerships, about the functioning of their property tax system and possible international lessons, focusing heavily on enforcement. Agreed to have a follow-up call with her technical team.	Policy
Oct-24	Bulawayo, Zimbabwe: Wilson Prichard had an in-depth discussion with the mayor about limitations of his existing system, and possible reform models, focused on incorporating simplified valuation of buildings into their system which focused exclusively on land. Agreed to the outlines of a collaboration in supporting Bulawayo in planning reform, with agreement for follow-up.	Policy
Oct-24	Chongwe, Zambia: Wilson Prichard had an in-depth discussion with the mayor about limitations of his existing system, and possible reform models, focused on strengthening mapping and valuation and improving taxation on customary land. Agreed to continue discussion about strategies for the later, and the mayor agreed to join a LoGRI/UN-HABITAT webinar in early November.	Policy
Oct-24	Mansa, Zambia: Wilson Prichard had an in-depth discussion with the mayor about limitations of his existing system, and possible reform models, focused on strengthening mapping and valuation and improving taxation on customary land. Agreed to continue discussion about strategies for the later.	Policy
Oct-24	Freetown, Sierra Leone: LoGRI has previously supported a comprehensive reform of the property tax system in Sierra Leone, and we took this opportunity to discuss key issues and strategies for achieving long term sustainability of the reform.	Policy
Sept-24	In late August we received an invitation to present our work on taxation of HNWIs in a GIZ closed seminar, but unfortunately no one from our team could make the proposed date, which had already been fixed. We did have a conversation with the seminar organiser to give them an overview of our work on the topic as well as discussing other upcoming work. Giovanni Occhiali met with Florian Schatz and Sezer Yilmaz, both from GIZ Good Governance Program.	Policy
Sept-24	Giulia Mascagni presented at a workshop titled ‘Providing Incentives for Tax Compliance through Tax Audit Design: Insights for Germany and Italy’. Despite the title, the workshop was a more general one focused on mostly economic studies of tax compliance from across the world. The event provided many useful connections with prominent economists working in this field (with a bias for those based in Europe/US) including Monica Singhal, Gabriel Zucman, Zareh Asatryan, Nadja Dwenger and Luca Salvadori (who also works with RRA in Rwanda) and others.	Academic
Sept-24	Giovanni Occhiali met with Jacob Iormbagah (T&L alumnus and co-supervised by Vanessa van den Boogaard for his PhD) and representatives from Benue Internal Revenue Services and other state actors, to discuss potential ICTD work on rental income taxation in Benue State	Policy
Sept-24	Mick Moore was approached by Natasha Fernandes, Producer of the BBC World Service Programme 'More of Less', about a possible item they might run in response to a listener comment about the very small numbers of people who seem to pay taxes in Uganda. Mick briefed Natasha extensively on (a) different tax concepts (b) the interpretation of Uganda tax statistics and (c) the broader implications for equity. Mick also put her in contact with Ronald Waiswa of the URA for data and as a possible interviewee. We don’t know if they will run with this item.	Civil Society
Sept-24	On the 12th of September, Fabrizio Santoro and Celeste Scarpini met online with GIZ Zambia to discuss ZRA's plan to improve its taxpayer registration strategy. ZRA wished to collaborate with ICTD to frame this new registration strategy.	Policy
Sept-24	Vanessa van den Boogaard had a series of engagements with IMF Governance and Anti-Corruption Division of the Legal Department at the IMF, feeding into a political economy of corruption analysis in Sierra Leone	Policy
Sept-24	Martin Hearson co-organised a conference titled ‘Reimagining Global Tax Governance’ at Saïd Business School in Oxford and chaired a panel.	Academic
Sept-24	Martin Hearson co-organised the IPE in flux: IPEG annual workshop in Edinburgh, as a convenor of the group. Martin presented on the project “Mobile Capital: Capturing Rent from Digital Financial Services in Africa” and chaired another panel discussion.	Academic
Sept-24	Frederik Heitmuller attended a call organized by Arvinn Gadgil from the UNDP Global Policy Centre for Governance on the Addis preparatory meeting for next year's Financing for Development Conference. There were around 50 participants in the call, mainly civil society, some government.	Civil Society
Sept-24	ATRN Annual Congress in Botswana - Vanessa van den Boogaard, Max Gallien, Giovanni Occhiali, and ICTD grantee Najibullah Nor Isak (Director of Revenue at Somalia MoF and former T&L course participant) all presented papers from their work with the ICTD. For example: "Taxing informal economies: Changing the conversation" (plenary session);"Rethinking taxation of informal economies in Africa" (interactive session); "The taxed informal economy: Fiscal burdens and inequality in Accra"; "The political economy of taxation in Somalia: Historical legacies, informal institutions, and political settlements"	Academic
Sept-24	ICTD colleagues ran a tax and informality plenary session which significantly increased the visibility of the ICTD’s work in this area. ICTD colleagues also hosted a tax and informality interactive session, which was highly popular.	Policy
Sept-24	Multiple in-person meetings with ICTD grantee Najibullah Nor Isak. Meetings included coaching on his ATRN presentation (ICTD working paper in progress) and on the first draft and directions for revisions of his tax competition paper.	Academic
Sept-24	Meetings with NRA (Sheku Kamara) about ongoing and future research in Sierra Leone, as well as potential mentorship/ supervision of students at Njala University (by Giovanni Occhiali and Vanessa). New connections made with e.g. ZRA, OBR (Burundi), FIRS, LRA.	Academic
Sept-24	Meeting with the KESRA CG and Raymond Nzali GIZ Tanzania Rep expressing keen interest on ICTD's informality work.	Policy
Sept-24	IBP is putting together a short course/capacity building series focused on tax transparency and engagement. Vanessa van den Boogaard engaged with them on the content of one of the sessions, which Vanessa wrote the video script for. Vanessa recorded part of the video focused on informality and taxation, and Jalia Kangave recorded the part on gender and tax. This was a significant civil society engagement and has the potential to have impact through dissemination of our work on informality and gender.	Civil Society
Aug-24	Mick Moore is a Member of the Club de Madrid (Annual Policy Dialogue) 2024 Working Group on International Tax Cooperation. The first meeting took place on 26 August attended by 20 participants, including one former Prime Minister (Belgium) and President (Lithuania) and 18 expert members of the Working Group, including Pascal St Amans and Jose Antonio Ocampo (Chair). It was a general discussion of the shape of the report. Mick emphasised the need to be strategic and focus on a small number of issues that the group might push forward and circulated relevant ICTD policy publications on taxing the wealthy and environmental taxes.	Civil Society
Aug-24	Max Gallien and Vanessa van den Boogaard attended ECPR in Dublin. Max organised and chaired a session on the Politics of Development, and Vanessa co-chaired (with Christian von Haldenwang of IDOS) a session on the Political Economy of Taxation in lower income countries. In this session, we presented our work on taxation in the informal sector in Accra (WP 195). ICTD grantee Abel Gwaindepi also presented his work in progress on taxation in the informal sector in Zimbabwe.	Academic
Aug-24	Giulia Mascagni was invited to the ATAF Heads of Tax Administration Masterclass and gave the opening presentation for session 6, "The importance of integration: shared benefits" which also included comments from Ms. Regina Chinamasa, Commissioner General, Zimbabwe Revenue Authority and Ms Varsha Singh, Commissioner General, Seychelles Revenue Authority.	Policy
Aug-24	Fabrizio Santoro presented research findings from his work on taxing the wealthy in Uganda, at the IIPF Annual Conference in Prague	Academic
Aug-24	Frederik Heitmuller attended the Second Session of the UN Ad-Hoc Committee to draft Terms of Reference for a UN Framework Convention on Tax.	Policy
Jul-24	Mbakiso Magwape presented a lecture at the University of Cape Town on the Future of Tax policy in Africa.	Academic
Jul-24	Vanessa van den Boogaard and Max Gallien hosted a series of panels at DSA on "Non-state social welfare and public goods provision: Development, inequality, and redistribution beyond the state". They presented their work on zakat, as well as work that Vanessa is doing with Giulia and Nicolas on informal taxation in Sierra Leone and Rwanda.	Academic
Jul-24	Mbakiso Magwape presented at the TJNA Workshop "Reforming the International Tax Regime: Lessons from the International Trade Regime", on lessons from trade (S&DT and plurilateralism) for tax, particularly as a panellist in UN negotiations.	Civil Society
Jul-24	Adrienne Lees had an update meeting with Tina Kaidu at the URA. They discussed progress on various projects, going through the list in the URA Quarterly Research Report from July 2024. They also agreed on a way to incorporate policy impact stories whenever we send the report. Tina also requested a dissemination meeting online, to have Celeste et al and Mick et al present their respective papers, both on inter-institutional data-sharing and registration matters.	Policy
Jul-24	Adrienne Lees met Moses Ogwapus, the former commissioner for tax policy URA (now commissioner for financial services) at the Ministry of Finance. Adrienne shared with him insights into ICTD’s recent work on tax targets, and he offered some ideas and stories from his experience.	Policy
Jul-24	Fabrizio Santoro led an internal workshop to RRA research team (10 staff, including 4 interns), facilitated by Annabel (ODI). The workshop was about practical suggestions on how to do research, and more specifically discussing issues and challenges with ongoing projects. It comes at a time when RRA research team agreed on research project for this coming year, so much of the discussion was preliminary around research not started yet. The session was very interactive as all participants had questions on their projects.	Academic
Jul-24	Martin Hearson was a speaker or moderator for several sessions at the UN Framework Tax Convention Roundtable	Academic
Jul-24	Frederik Heitmuller attended the Oxford-Potsdam Follow Up Workshop on the UN GA Resolution 78/230—The Promotion of Inclusive and Effective International Tax Cooperation—at the United Nations.	Policy
Jul-24	Fabrizio Santoro and Colette Nyirakamana met with Seth Kwizera from EPRN in Kigali at the University of Rwanda. They presented ICTD’s work in more detail and discussed whether training activities or assistance with funding proposals might be possible. They redirected him to the T&L material but will look at what specific sessions might be possible to deliver.	Academic
Jul-24	Sripriya Srivatsa, Giulia Mascagni, Jalia Kangave, and Vanessa van den Boogaard attended the Annual Conference of the International Association of Feminist Economists in Rome. Collectively they participated in 2 panels and 1 roundtable organised with colleagues from IDS, World Bank, WIEGO, and Cambridge, among many new colleagues as well. Examples of presentations: ‘Gender and taxation in the informal sector in Accra’, ‘Moving beyond sex-disaggregated data’: ‘Research and policy for gender and tax’.	Academic
Jul-24	Martin Hearson spoke on a panel at a meeting of around 50 people from UK-based NGOs, organised by BOND, Cafod and Christian Aid.	Civil Society
Jul-24	Mbakiso Magwape gave a lecture at the University of Cape Town on "The Future of Tax policy in Africa".	Academic
Jul-24	Mbakiso Magwape spoke on a panel at the Tax Justice Network Africa event "Reforming the International Tax Regime: Lessons from International Trade."	Civil Society
Jun-24	Martin Hearson taught on the Oxford University Law Department's Master’s in Taxation. Around 40 students were present, most of them professionals from business and civil society, with a significant proportion from lower-income countries	Academic
Jun-24	Martin Hearson attended the Society for the Advancement of Socioeconomics conference 2024 with Mary Abounabhan and Florence Dafe. They presented their work in progress paper "Mobile Capital: Capturing rent from digital financial services in Africa" now retitled "Platform Disempowerment: African governments and the taxation of digital financial services”.	Academic
June-24	In collaboration with the Economic Policy Research Network Rwanda (EPRN), ICTD sponsored the 10th EPRN Annual Economic Research Conference on boosting economic resilience to economic shocks. Giulia Mascagni was invited to give opening remarks and there were two sessions in which ICTD researchers Fabrizio Santoro and Colette Nyirakamana presented on taxing the wealthy and property taxes, while Mbakiso Magwape joined a policy panel with IMF, RRA, and MinEcoFin representatives. The session received significant audience feedback on issues like revenue forecasts, social unrest, and tax progressivity. In a follow up meeting, Fabrizio and colleagues detailed their research and discussed future collaborations with EPRN, underscoring the importance of their work in informing Rwandan tax policy and fostering continued partnership.	Academic
Jun-24	Giulia Mascagni, Max Gallien and Mick Moore presented their research at the NOPSA conference, titled: The politics of fiscal capacity: Domestic and international challenges to effective taxation NOPSA, Bergen	Academic
Jun-24	Giulia Mascagni gave the opening presentation in the side event on Gender and Tax at the 2024 ATI General Assembly. Giulia’s presentation used an ICTD Policy Brief on the biases framework as a starting point and discussed the new approach the paper proposes in the context of an application to tax expenditures, which was the main focus of the event.	Policy
Jun-24	Last year SOMO and partners were working on a project based around DTAs in Mozambique. Martin Hearson and partners published three reports on the findings that Mozambique is losing out on large amounts of potential tax revenue through its DTAs with Mauritius and the UAE. Martin met with the CDD and the Mozambican Ministry of Justice, who are setting up a working group to review the country’s DTAs and come up with recommendations, potentially redesigning these DTAs.	Civil Society
Jun-24	TAXUD (Benedetta Guerzoni, Ana Xavier, Scoppio Maria Elena) invited Giulia Mascagni and Caren Grown to present their policy brief on gender at the EC, in a series of Tax Talks they are organising as part of the diversity month at the EC. We brought in Michelle Harding from the OECD to provide a perspective from higher income countries. 51 participants showed up, mostly from TAXUD but also other directorates of the EC including RTD, JRC, BUDG, EMPL, REGIO, MOVE, and others.	Policy
Jun-24	"Constructing tax justice - honouring the contributions of Sol Picciotto" journal special issue webinar co-organised with University of Nairobi	Academic
Jun-24	Martin Hearson Chaired the Panel "Emerging Powers and Economies" at the British International Studies Association annual conference in Birmingham.	Academic
May-24	Martin Hearson renewed contact with Marilou Uy, formerly the Director of the G24 secretariat. She is now at Boston College but still exceptionally well connected. She was particularly interested in environmental taxes in the context of the Global Solidarity Levies Task Force of which she is a member (emerging from the Macron and Ruto-led summit in 2023). Martin sent Marilou ICTD working papers on shipping taxation and the UN work.	Policy
May-24	Giulia Mascagni presented cross-country VAT research at the UNU-WIDER Development Conference 2024, attracting interest from FCDO, the British High Commissioner to Mozambique, the Zambia Revenue Authority (ZRA), and the Uganda Revenue Authority (URA). Following her presentation, Allen Nassanga, Assistant Commissioner for Research and Innovation at the URA, discussed challenges with the President’s Office about VAT issues highlighted in the paper. Giulia shared the paper and a Uganda-specific note with URA, planning a future presentation to senior management. Allen Nassanga noted URA’s frequent use of ICTD research for decision-making, indicating significant impacts and potential for further collaboration. Giulia also engaged with key stakeholders in development economics, focusing on tax programmes. The conference included representatives from FCDO and Norad, as well as from organisations such as the World Bank, The African Economic Research Consortium (AERC), OECD, UN agencies, and tax researchers from UNU-WIDER, URA, ZRA, and the South Africa National Treasury.	Academic
May-24	Giovanni Occhiali and Frederik Kalyango (URA staff) presented the preliminary results of their ongoing study “What impacts do tax agents have on taxpayer compliance in Uganda? Evidence from eTax.” to various URA staff members. In addition, they met with Tina Kaidu and Nicholas Musoke from the URA research and innovation division, Simon Muyuga (Manager Compliance Risk Management, DTD), Jim Kagolo (Supervisor LTO compliance division, DTD), Natal (Board Affairs and Alternative Dispute Resolution Mechanism), Jackson Akampurira and Aisha Kabeja.	Policy
May-24	Frederik Heitmuller has been involved in steering and providing feedback on a research project on the impact of tax treaties on tax revenues generated from services supplied across borders. It focusses specifically on Colombia, Kenya, Brazil, Argentina, and Nigeria. The research was commissioned by the Independent Commission for the Reform of International Corporate Taxation (ICRICT) and conducted by Faith Amaro under the supervision of Sol Picciotto.	Civil Society
May-24	Fabrizio Santoro presented research findings from the paper “Technology Evolution and Tax Compliance: Evidence from Rwanda” at the inaugural International Conference on Tax for Growth, which was co-hosted by Tanzania Revenue Authority, the International Growth Centre (IGC), and Research on Poverty Alleviation Programme Limited (REPOA). The aim of the conference was to bring together world-leading researchers and policymakers to discuss questions relating to enhancing domestic resource mobilisation and strengthening tax systems in sub-Saharan Africa.	Academic
Apr-24	Vanessa van den Boogaard presented at the ‘Roadblocks and revenues: New geographies of taxation in conflict’ workshop in Montreux.	Academic
Apr-24	Martin Hearson observed four days of the First Session of Ad Hoc Committee meetings at the UN Headquarters in New York. The goal was to develop the draft TOR for a UN Framework Convention on International Tax Cooperation. Although he did not speak formally, Martin engaged extensively with delegates and observers during breaks, with his presence particularly appreciated by African participants. These informal discussions allowed him to build relationships, understand diverse perspectives, and support African delegates' positions, highlighting the importance of informal engagement in influencing international policy discussions.	Policy
Apr-24	Mbakiso Magwape met with Kasem Zotkaj at the Past & Future of Global Tax Justice Conference and continued a discussion on developing a "Tax and Sustainability" early careers informal workshop, linked with tax justice, which seeks to address equitable development (including and particularly the Global South). They solidified areas of interest and seek to start online with research proposals and collaborate to grow possibly into seminars.	Academic
Apr-24	Wilson Prichard was invited to lead a session on “Strategic Leadership to Strengthen Revenue Systems” at the annual Harvard Ministerial Leadership Forum welcoming finance and economic planning ministers from Africa, the Caribbean, and Latin America. The goal of the session – and the forum in general – was to provide a setting for Ministers to reflect on their key priorities, and to develop strategies for translating those priorities into action in their unique contexts. During the session, Will argued that strengthening revenue systems is not merely a technical problem, but an adaptive problem which depends on understanding complex systems and navigating diverse constraints on reform.	Policy
Apr-24	ICTD hosted a webinar called ‘Getting Targets Right – How much tax can low-income countries raise?’ with a panel of researchers and practitioners to discuss whether optimistic tax targets are helpful or hurtful and how to make them better. Panellists included Doris Akol (IMF), Bernard Baimwera (KESRA), Kyle McNabb (ODI), Modeste Fatoing Mopa (IMF), Amina Ebrahim (UNU-WIDER). The event was moderated by ICTD Research Director Giulia Mascagni, with ICTD Researchers Max Gallien and Adrienne Lees presenting work. 360 people registered for the conference, with 136 people joining the live event.	Civil Society
Mar-24	Martin Hearson was referred to Maida Kayekesi, an inspector at Zambia Revenue Authority and member of the steering group of the Inclusive Framework, by Ben Dickinson of the OECD secretariat. Maidah wants to write a research paper studying ATAF's role supporting African countries on international tax, in particular around assessing the impact of Pillar Two. The aim seems to be to explore the barriers to a level playing field that still exist for African countries at the IF.
Mar-24	Mbakiso Magwape met with visiting Professor Yan Xu, Scientia Associate Professor of Tax Law in the Business School at the University of New South Wales (UNSW) and Adjunct Associate Profession in the Faculty of Law at the University of Hong Kong regarding potential collaborative work, with the potential mention of environmental taxation. Mbakiso informed her of the research areas that ICTD is involved in. They also met again two weeks later at an SMU/Edinburgh ESG and Tax conference.	Academic
Mar-24	Mary Abounabhan had a follow up meeting with a GIZ member to discuss how to go about improving the tax registry in Ghana. They met at a seminar held by Max Gallien and Vanessa van den Boogaard. GIZ has plans to improve the quality of the tax registry mentioning specifically that the goals are to make the registry more efficient and to be revenue oriented. GIZ is still in very early stages of their project but keen on further collaboration and questions about specific tax auditing methodologies that are risk profile based and others that could help them design an intervention that leads to equitable results.	Policy
Mar-24	Vannessa van den Boogaard gave a lecture on "Informal labour taxes in Sierra Leone." University of Makeni, March 2024.	Academic
Mar-24	Martin Hearson led a session at an Academic Workshop in Oxford on UN GA Resolution 78/230 on the Promotion of Inclusive and Effective International Tax Cooperation at the United Nations. Frederik Heitmuller and Mbakiso Magwape also participated. It was a discussion bringing together academics and several key policy stakeholders (list below) convened by Philip Baker, a KC.	Academic
Mar-24	Following the approval of UN Resolution 78/235 on Promotion of Inclusive and Effective International Tax Cooperation at the United Nations, an Ad hoc Intergovernmental Committee was set up that will elaborate terms of reference for the drafting of a multilateral “Framework Convention” on tax matters. Prior to the first substantive session of the Ad-Hoc Committee, a call for input was issued by the Committee to which the ICTD International Tax team responded. In the submission, Martin Hearson, Frederik Heitmuller and Mbakiso Magwape highlighted which shortcomings we have identified in the current set up of global tax governance in our research and commented on various issues that arise going forward.	policy
Mar-24	Giovanni Occhiali attended a virtual roundtable discussion exploring the different policy approaches to carbon taxes taken by the United States and Europe and their global implications for Africa, hosted by Jericho on behalf of KPMG International.	Civil Society
Mar-24	Following an introduction from Doris Akol, Giovanni Occhiali and Giulia Mascagni met with 3 MoF Uganda staff to discuss ICTD work on taxation of HNWIs, and potential future synergies given a growing interest on the topic from the IMF side.	Policy
Mar-24	Giulia was invited to give a seminar at the Centre of Development Studies of the University of Cambridge. The talk was titled Taxation and Inequality: the under-rated role of tax administration" and it relied heavily on several ICTD research projects including the nuding experiment in Rwanda, the nil filers project, taxpayer education, as well as the targets policy brief.	Academic
Mar-24	Wilson Prichard and Giulia Mascagni met with Angela Bellmooney and Rajesh Kishan to offer advice on their work with ATAF.	Policy
Mar-24	Wilson Prichard presented to the Local Public Sector Alliance on his paper “Getting Good Enough Tax Governance: Simplified Strategies for Reforming African Property Tax Systems”	Policy
Mar-24	Wilson Prichard attended a two-day workshop with about 50 representatives from the government of Ethiopia, Ministry of Finance, Ministry of Urban Development, and regional and municipal governments, focused on property tax reform efforts. The workshop was organised by a consultancy firm, VNG international, who had led a pilot property tax reform in Sidama, Ethiopia. Will was invited as the lead international expert to give a keynote address on international experiences of property tax reform and key principles to guide reform efforts in Ethiopia.	Policy
Feb-24	Wilson Prichard met with Ernest Karasira who leads the property tax reform program for the Rwanda Revenue Authority on Feb 29th in Kigali to discuss their ongoing reform program, key questions and priorities, and potential support that could be provided by LoGRI/ICTD. After that they developed a concept note for collaboration and remained in touch. They then met again along with Denis Mukama on July 2 in Kigali to further develop possible models for collaboration, and ideas for the reform program, related to both property taxation and rental income taxation.
Feb-24	Giovanni Occhiali was invited to attend a 3-day closed meeting with officials from the National Revenue Authority and the Ministry of Finance of Sierra Leone to finalise the country’s Medium Term Revenue Strategy.	Policy
Feb-24	Martin Hearson discussed with Alex Cobham of TJN on UNCAC and the possibility of a UN convention on unitary taxation, and what could be ICTD's role in research or input. Complexities with OECD countries’ buy-in and Norway-led financial transparency convention put many CSOs off the idea of a UN convention.	Civil Society
Feb-24	Sripriya Srivatsa presented at the UNDP Global Dialogue on Public Finance and Tax for Gender Equality. It brought together over 40 member countries who are receiving support from the Tax for SDGs and ‘Equanomics’ initiatives. Attendees included officials from revenue authorities, ministries of finance, members from civil society and IFIs as well as researchers working on gender and public finance. The discussions centred around how fiscal planning can contribute to improving gender equality. ICTD were invited to participate on a panel titled, "Gender inequality in Public Finance and Tax systems", moderated by Caren Grown. Co-panellists were Lekha Chakraborty from National Institute of Public Finance and Ceren Ozer from the World Bank.	Policy
Feb-24	The RRA and the ICTD co-hosted the 2nd RRA Research Day which focused on the pivotal role of technology in improving tax administration. The 2nd RRA Research Day brought together esteemed personalities from relevant institutions to discuss Rwanda’s leading innovations in digitalisation and the implications for tax policies and systems across Africa.	Academic
Feb-24	ICTD Research Fellows Max Gallien and Vanessa van den Boogaard held a webinar for GIZ wherein they presented the Registration Policy Brief and discussed related research. Approximately 40 people attended including from country offices in Ghana, Zimbabwe, Tanzania, Pakistan, Morocco and Kosovo, amongst others. There was engaging discussion after the presentation.	Policy
Feb-24	The ICTD co-convened a two-day workshop with the Ghana Revenue Authority (GRA) in Accra. The workshop’s primary purpose was to explore how mobile money taxes could be designed in an effective and equitable way based on discussion centred around research and real-life experiences. Dr Charles Addae, GRA’s Deputy Commissioner of Strategy, Research, Policy and Programmes said that ‘The research findings and recommendations have been very useful in shaping Ghana’s e-levy since it was first implemented in May 2022. The event garnered significant media attention, particularly around the controversial e-levy. Media coverage of the event included outlets who report in the widely spoken Twi language in an effort to engage and involve the local community by making the discussion and information of the conference more accessible. While in Accra, the ICTD researchers were also invited to present DIGITAX research at the British High Commission (BHC).	Policy
Feb 24	IDS Members Seminar: Taxing mobile money in Africa: the good, the bad and the ugly (Martin Hearson, Awa Diouf).	Academic
Jan-24	The Addis Tax Initiative secretariat staff at GIZ reached out to Martin Hearson to get his thoughts on the UN Convention process. They will hold a side event on the subject at the UN FFD Forum in April and were thinking about how to structure it.	Policy
Jan-24	Mbakiso Magwape coordinated activities, with substantial input from Martin Hearson, Frederik Heitmuller and Suranjali Tandon (National Institute of Public Finance and Policy – NIPFP), on the writing of a policy brief submitted to the in response to a call by the Brazilian convenors of the T20 think tank network. The policy brief feeds into the G20 negotiations this year, with the submission made under the heading A Fairer Global Tax Architecture. The work streamlines with research activities that the ICTD programme has been involved with, particularly focusing on political and legal areas that require intervention or reform.	Civil Society
Jan-24	Jalia Kangave was a commentator and panellist at an internal symposium to conclude the current phase of the IMF’s Fiscal Affairs Department’s work on gender and fiscal policies. The symposium built on an internal workshop that was held in September 2022, which Jalia and Vanessa van den Boogaard attended and where IMF staff presented preliminary findings on their work on gender and fiscal policies. Various IMF staff presented the findings of the work that they have been doing in the past two years, with commentary being provided by external participants. Jalia was a commentator on the chapter on Gender and Revenue Administration and was also a panellist for the closing round table. IMF is planning on publishing a book on "Fiscal Policies and Institutions for Gender Equality” based on the various presentations that were made in the two days of the symposium.	Policy
Jan-24	ICTD work was referenced in a number of presentations and also mentioned by colleagues at the World Bank (Ceren Ozer), Brookings Institute (Caren Grown) and the Gates Foundation (Peter Hurst). Peter Hurst wrote Jalia an email after the symposium saying that for his presentation (which was mainly on reflections about important issues on gender and tax), he relied heavily on the literature review that Anu Joshi, Vanessa and Jalia wrote, which he accessed through the ICTD Learning Portal.	Policy
Jan-24	Kaja Guttormsgaard from Tax Justice Norway reached out to Frederik Heitmuller to get advice on understanding a reply from Norway’s Ministry of Finance to a question raised by a Norwegian parliamentary group, regarding Norway’s policy towards the OECD’s subject-to-tax rule. Frederik included some explanation why the reply of the Norwegian MoF was generally correct but suggested a few issues that the parliamentary group could follow-up on, among others: - the fact that next to the OECD’s STTR, an alternative provision has been developed by the UN Tax Committee. - to conduct more research on several industries, such as the shipping industry, to find out whether they benefit from low tax rates	Civil Society
Jan-24	Frederik Heitmuller followed up on earlier engagements with the Rwanda Revenue Authority and the Rwandan MINECOFIN on advising on Rwanda’s tax treaty policy and met with RRA’s research department to discuss a potential collaborative research project This would attempt to quantify tax revenue foregone through the tax treaties Rwanda has concluded and aims to conclude in the future.	Policy
Jan-24	Max Gallien and Vanessa van den Boogaard met with the local WIEGO advocacy team in Ghana to discuss how their research can feed into local advocacy strategies	Civil Society
Jan-24	IDS Fellow Karishma Banga alongside Alexander Beyleveld published a paper on international trade rules and the taxation of the digital economy with a view to contributing to the debates taking place ahead of the February WTO Ministerial. The paper generated significant engagement and discussion on social media, including between a Professor at New York University’s Law School, a senior Financial Times journalist and an Ambassador to the OECD and UNESCO. Karishma published a blog on the vexed question of Custom Duties for Electronic Transmissions (CDETs) and was interviewed by Tax Notes International, following an ICTD/IDS press notice around her work.	Policy