## Annual Review – Tax and Economic Governance

Title: Tax and Economic Governance (TEG)
Programme Value £ (full life): 20,000,000		Review date:
Programme Code: 300212	AMP start date: 20/08/2018	AMP end date: 30/06/2026

Summary of Programme Performance
Year	2019	2020	2021	2022	2023	2024 (June)	2024 (Dec. Light-touch)	2025 (PCR)
Overall Output Score	A	A	A	A	A	A	A
Risk Rating	Major	Major	Major	Major	Major	Major	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/40109555.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0004657.xlsx

A. SUMMARY AND OVERVIEW

Description of programme
FCDO’s Tax and Economic Governance (TEG) programme contributes to more inclusive economic growth by strengthening Government of Mozambique’s (GoM) revenue collection, public investment and debt management, and medium to long term fiscal planning. Fundamentally, the programme is about strengthening how taxes are raised by government and how public spending is managed to support economic stability and growth that is distributed fairly across society. The programme achieves this through provision of technical assistance (short- and long-term experts, training and capacity building) and purchase of goods and services for government as required (equipment, software and travel for trainings and field activities).

Support is justified by two main challenges. First, there is evidence that the sharp drop in economic growth since 2016 and the spike in public debt, both resulting in reversal of poverty reduction gains, were largely caused by inefficiencies in public management (in particular, public investment and debt management) as well as by external shocks (climate, Covid-19, conflict). Second, the extractives sector (in particular Liquefied Natural Gas (LNG)) presents both enormous opportunities but also significant challenges to economic governance. Mozambique needs to avoid the ‘resource curse’ which some analysts argue is already unfolding, with imbalances in the economy and a pattern of growth that doesn’t sufficiently benefit the poor. These are long term challenges and opportunities to which TEG seeks to respond through a combination of targeted technical support, investment in reforms and high-level policy dialogue aimed at strengthening macro-economic stability, and inclusive and more resilient growth.

The programme is made up of 3 components:
[note] The component numbers below don’t correspond exactly to the output numbers in the logframe.
1. Tax Reform for Inclusive Development (TEDI), £12m (50% FCDO and 50% Sida): Technical Assistance (TA) and investment in reforms to strengthen revenue administration and policy. This component is delivered through a contracted service provider (Cowater International) and benefits both the Ministry of Finance (MoF) and Mozambique Revenue Authority (MRA). TEDI activities support outputs 1 and 3 of the logframe.
[note] Sida (Swedish International Development Cooperation Agency) formally joined the TEDI programme in July 2022. The contract amendment with Cowater signed in December 2022 reflected the increase in funds to £12m.
2. Governance for Inclusive Growth (GEDI), £7m: Technical assistance to MEF, and policy analysis, implemented through a World Bank-Executed Trust Fund initiated under this programme. GEDI focuses on three main areas: strengthening analysis and planning for inclusive growth; strengthening public investment management; and strengthening debt and fiscal risks management. GEDI activities support outputs 2 and 3 of the logframe.
3. Monitoring, diagnostic and evidence (M&D), £1m: The component is directly managed by the FCDO TEG team to commission activities providing cross-cutting support to the programme objectives, providing flexibility for analysis and punctual support to emerging opportunities. For instance, under this component TEG commissioned the mid-term review of the programme, is supporting Mozambique’s efforts to strengthen Anti-Money Laundering/Counter Terrorism Financing (AML/CTF) to exit the Financial Action Task Force (FATF) grey-list and is supporting the FCDO’s Inclusive Growth Diagnostic for Mozambique.
[note] FATF grey-listed Mozambique because of inadequate systems for AML/CTF. Grey-listing can lead to increased transaction costs for businesses and can be a deterrent to new investments, if quick and credible action is not taken by GoM. TEG is funding a national consultant to support the GoM structure responsible for planning, monitoring and reporting of Mozambique´s FATF and ESAAMLG related actions.

Summary supporting narrative for the overall score in this review
This light-touch Annual Review (AR) covers July-December 2024, aligning the programme with the government’s January-December fiscal year, as recommended in the August 2024 AR. Although planned for end-March 2025, the AR is only being completed in August due to the late approval and publication of the 2025 state budget in May 2025. The budget is key to report on some AR results.
While the performance assessment is based on outputs and outcome milestones for December 2024, the AR reflects on lessons for the future based on progresses and challenges until July 2025. Milestones were adapted to account for significant challenges caused by the elections campaign and post-election disruptions that constrained engagement.
The overall score for this annual review is A, and all outputs scored A.
Despite challenges, three key results were achieved within the reporting period, along with important lessons as the project enters its final year:
TEDI submitted a tax policy diagnostic and reform roadmap to GoM. The objective is to gradually shift away from the current ad-hoc approach to tax policy – often influenced by lobbying pressures – towards a more strategic, evidence-based framework. This new approach aims to better balance key goals: revenue mobilization, equity, efficiency, and business facilitation.

There is clear evidence that government is following the tax diagnostic and road map: First, In July, the Council of Ministers approved Mozambique’s first-ever medium-term National Revenue Mobilisation Strategy (2025–2027), developed with TEDI’s support and informed by the aforementioned analysis. The strategy and underlying analysis is expected to guide discussions on tax reform under a potential new programme with the IMF. Additionally, thanks to TEDI’s efforts – being the sole provider of external capacity-building support to the Ministry of Finance’s tax policy function over the past four years – the Government of Mozambique formalised the tax policy mandate within the newly established Fiscal Studies Department. This marks a critical step in ending the problematic practice of the tax administration authority informally leading tax policy formulation.

Under the M&D component, a TEG-funded advisor continued to support GoM’s swift adoption of AML/CTF reforms progressing 11 of 12 FATF actions from Partly Compliant to Compliant during the review period. A site assessment is scheduled for September 2025, aiming for grey list removal at the October FATF Plenary.

The Fiscal Risks Report 2025 (published August 2024) was expanded to include risks stemming from Public and Private Partnerships (PPP) and subnational entities, representing an important improvement to the overall understanding of fiscal risks.

Major lessons learnt and recommendations for the year ahead:
Lesson 1: An opportunistic, adaptable, patient and politically savvy “nudge” approach is a more effective method to deliver politically complex reforms – a strict demand driven or payment by results approach is unlikely to have been able to achieve the same level of results.
Despite the programme’s strong use of political economy analysis tools, grasping the true incentives for deep reforms – and knowing how to influence them – remains a challenging and uncertain task. Factors such as optimism bias and information asymmetry between implementers, counterparts, and FCDO further complicate reform efforts. Attempting to mitigate these risks through strict demand-led, “fail-fast,” or payment-by-results strategies could have missed the significant tax policy achievements realized later in the programme.
While some of the impact at outcome level results are unlikely to be achieved (e.g. more inclusive growth, improved service delivery, improved taxpayers risk management) the results achieved (additional tax revenues, leveraged budget support, better quality of data and analysis for policy formulation) demonstrate that TEG remains a good to excellent investment (see Value for Money section). These results are a testimony of success of the TEG approach: building technical capacity and fostering relationships that create incentives for reform, while remaining agile in seizing opportunities as they arise.
Recommendation 1: While TEG’s ‘patient’ approach is proving effective overall, nine months from the project end, the implementers and FCDO should now strongly prioritise activities that will be able to evidence outcome results by the end of the project and strengthen outcome level-reporting. This should be a key element of the exit strategy.

Lesson 2: Supporting politically complex and uncertain reforms presents challenges for long-term financial forecasting. Principally due to the delay caused by the political transition, all three TEG components are at high risk of underspending by the current programme’s end date. (see financial section).
Recommendation 2: TEG implementers and FCDO should consider pursuing a programme extension. This extension would: a) Increase impact by building on the strong relationships TEG has now formed with the new administration, despite the challenges of a complex political transition and delays. b) Support continuity in key areas like economic management and Public Financial Management (PFM), ensuring progress is not lost while the future office portfolio is still being developed. c) Enable innovation by testing new delivery models at a larger scale – such as expanding the use of embedded advisers within the Government of Mozambique.

List of major recommendations
Recommendation	Owner/Date
1. TEG should strongly prioritise activities that will be able to evidence outcome results by the end of the project. / TEG should also prioritize strengthening outcome-level reporting in the next period (e.g. additional revenue collected with TEDI support) to ensure robust data is available for the project completion report.	Cowater, WB, backed up by FCDO TEG team (including TIG team leader as appropriate). By March 26.
2. TEG should explore the space for an extension, and as the office is planning its future portfolio, it is important to explore innovative ways to use this pot of funds, together with the M&D component, to prepare for the future.	FCDO TEG team and Cowater. / Seek no-cost extension by end of September 2025.
3. Develop a strategy to ensure that the disruption in the usage of the Public Investment Management system (allegedly caused by the post-elections turmoil) is restored from the next state budget 2026.	WB. By November when the state budget will be submitted for parliament approval.
4. TEDI to continue to monitor the relationship with MRA in response to past tensions.	Cowater. If difficulties resurface, consider escalations to Minister of Finance and FCDO senior leadership.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
At the impact level, the programme aims to foster ‘Improvements in inclusive growth and wider access to services that have been held back by inefficiencies in resource management and taxation’. This goal is supported by the outcome of ‘Strengthened Government of Mozambique capacity and processes demonstrated through improved revenue administration and more effective and transparent management of public resources.’ The programme’s outputs focus on enhancing revenue mobilisation capacity (including audit and extractives), reforming economic management (public investment management, fiscal risks and debt management) and providing policy analysis and evidence on inclusive growth.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
Progress during the six-month review period has been limited, largely due to the electoral cycle and post-election disruptions. Despite this, TEG remains broadly on track to meet most of its outcome-level targets. However, there is a concerning trend of the Public Investment Management (PIM) system being bypassed in some cases during preparations for the 2025 budget. This appears linked to increased pressure on the Government to fast-track project approvals in a context of delays caused by elections and post-elections disruptions. GoM considers this setback to be restricted to the 2025 budget cycle. While outcome 3 was also not met, progress in first half of 2025 has been fast and the outcome target remains on track. For now, the outcome confidence rating remains at Green/Amber.

Progress toward TEG’s long-term goals of inclusive growth and better public service access is slower than expected due to a challenging context. While TEG is achieving key outcomes – like boosting public revenue, improving financial transparency, and supporting policy dialogue – it operates in a strained fiscal environment. External shocks (conflict, climate events, COVID-19) and setbacks in wage bill reform have worsened public spending pressures, limiting funds for service delivery.

Outcome Progress Assessment
Indicators (*)	Milestones for this review	Target (2026)	Progress
1. Evidence of direct revenue-generating activities as a result of TEDI programme activities (e.g., audit, extractives, tax policy)	Evidence of 1 revenue-generating activity: MRA monitoring visits to extractive companies (Zambezia and Maputo).	Evidence of 2 direct revenue-generating activities as a result of TEDI programme activities in the year (£ where possible) – non-cumulative target.	Met. Monitoring visits to Zambezia and Maputo completed. Revenue impact not yet estimated.
2. % of new projects (and % of investment budget) funded through the budget or through state-owned enterprises selected through the public investment system.	100% of new projects included in the state budget 2025 have been selected through the public investment management system.	100% of new projects funded through the budget have been selected through the public investment management system.	Not met. GoM bypassed the PIM system for a series of projects. Exact percentage to be determined.
3. Share of majority state-owned enterprises (SOEs) included in the Government of Mozambique's debt database	15 percent of Central Government domestic debt reconciled and migrated into Meridian	75% of SOEs included in the GoM's central database (Meridian). SOE debt records centralized through a shared application between central government and the institute for state participation in enterprises.	Not met. The preparation for migration was nearly completed (see output 2 for more details) but the transfer of data only started in the first quarter of 2025.
4. Evidence of national strategies, policies and budgets (including tax policies) adopted that draw on policy analysis and are consistent with inclusive growth and fiscal sustainability.	None	TEDI: 2 analysis informing national strategies/policies/legislation. GEDI: Fiscal risks analysis informing MTFF and budget documents and debt strategy.	None expected.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
TEG remains a good value for money programme and with an important role in the overall BHC Maputo portfolio. Over the duration of the programme, TEG has directly contributed to the mobilization of over £60 million of additional revenues and created some of the core conditions for the approval of £600 million of multilateral budget support. Under the review period, despite the electoral disruptions, the programme was able to keep basic engagement with counterparts and to position itself to seize reform opportunities under the new GoM, in particular under the tax policy workstream. This investment has not yet been fully leveraged, strengthening the case for a programme extension to deliver greater Value for Money (VfM).

TEG plays an important role in delivering progress against the ‘sustainable and inclusive prosperity’ goal of the FCDO country business plan, as well as supporting the broader foundations for all other goals of the country plan in a range of ways. This includes:
- Supporting Goal 1 (‘peace and stability’) by enabling stronger public finances for more inclusive and equitably distributed public services and public investments to weaken the underlying drivers of conflict.
- Supporting Goal 2 (‘improving service delivery’), by increasing the revenue collected and how it is invested.
- Contributing to Goal 3 (‘strengthening climate resilience’) by supporting improved revenue generation and climate smart investment.
- Supporting Goal 5 (‘strengthening inclusive governance and democracy’) by improving fiscal information quality and transparency, critical to foster more inclusive participation in the public debate of governance.

## C. DETAILED OUTPUT SCORING

Output Title	The MRA’s capacity is increasingly strengthened to improve performance in the functions of audit to taxpayers and taxation of extractive industries.
Output number:		1	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this AR	Progress
1.1 Improved capacity of the audit function - measured by: a) no. sectors where specialised audit trainings have been delivered to MRA staff (formal and/or on-the-job); and b) no. audits in specific sectors conducted (initiated, underway or completed) by trained staff.	N/A	Awaiting restart of tax audit support
1.2 Improved extractives industries taxation unit measured by: a) No. of transfer pricing capacity building activities delivered (formal and on-the-job) b) No. of pieces of transfer pricing analysis conducted (started/completed).	a) One capacity building activities and/or trainings conducted on topic of Transfer Pricing (TP) Analysis / b) None for the period	OI 1.2 Exceeded. / a) Exceeded. Two capacity building activities conducted on TP analysis, namely: KPMG TP training held in Maputo and OCED TP workshop in South Africa.
1.3 Number of materials on GESI designed or disseminated with TEG assistance delivered to MRA and/or MEF, with % trainees/beneficiaries reporting improved understanding/awareness of GESI as a result of TEDI capacity building activities (disaggregated by sex).	i) Delivery of taxpayer education/comms material covering 2 topics (1 leaflet on simplified VAT and 1 leaflet on simplified Personal Income Tax); / ii) ≥75% male/female trainees reporting improved GESI understanding/awareness as applied to domestic revenue mobilisation.	OI 1.3 Partially Met. / i) Met. Two products delivered: 1 leaflet on simplified VAT and 1 leaflet on simplified PIT (ISPC) / ii) Not met. 50% of participants (all male) self-reported their GESI knowledge had adequately improved following the training.

Briefly describe the output’s activities and provide supporting narrative for the score.
The output scored A despite one of three the results not being achieved (one was exceeded and the other partially met, averaging met for the whole output). The percentage of trainees reporting improved knowledge of GESI is based on a too small sample of 6 beneficiaries of a training session of which half self-reported improved knowledge. Self-assessment can be quite subjective and for the next period, the logframe will add pre and post-tests to assess learning results. TEDI continues to support training on Transfer Pricing (TP), and the first TP analysis is expected for 2025.

Support to the audit function (Output Indicator 1.1) remained on hold during the review period, pending ongoing discussions about its resumption. Activities resumed in the second quarter of 2025, with a scaled down ambition. The current objective is to develop risk profiles for eight sectors by the end of the project, aiming to embed risk-informed practices into audit operations. This represents a revision to the original ambition of overhauling the entire taxpayer risk management system, which included designing processes, developing software, organizing databases, drafting guidelines, and delivering on-the-job training. Despite the scaled-down scope, the development of sector-specific risk profiles provides a solid foundation for continued reform by the Mozambique Revenue Authority (MRA) in broader risk management functions. These efforts may be sustained by possible IMF technical assistance, whose recent diagnostic – conducted to inform the resumption of its technical assistance to MRA – identified risk management as a priority area.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
No changes during the period. Planned change to the indicator that assesses improved GESI knowledge.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead

Recommendations from previous Annual Review	Owner	Progress
TEDI should periodically revisit the conditions for (re)engaging the support to tax audit and be prepared to maintain the pause, stop or resume support, depending on how the MRA responds to the minimum requirements presented by TEDI. In parallel, TEDI should continue discussions about relocating part of the TEDI resources currently allocated to the tax audit work to a new workstream on management of administrative revenue data (or other relevant opportunities).	FCDO, Cowater.	Discussions held during the review period and activities are gradually resuming in 2025.
5. Revisit the relevance of TEDI logistics support to tax education, communications and registry activities from the perspectives of GESI, VfM and risk management.	FCDO, Cowater. Ongoing, reflection and decision to be completed by November.	Discussion held and logistics support to communications campaigns are currently on hold. Support to logistics will have to be assessed against clear results indicators.

Output Title	Strengthened Government of Mozambique systems, policies, and reforms for economic management, focussed on PIM, fiscal risks, and debt management.
Output number:		2	Output Score:	A
Impact weighting (%):		40%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Debt management and fiscal risks Instruments and analysis (including for SOEs) produced for use in fiscal planning activities.	- Migration of the external debt from CS-DRMS to Meridian database completed and migration of domestic debt initiated. / - Fiscal risks report 2025 issued on time	Met. / - Migration of the external debt from CS-DRMS to Meridian completed and process to migrate domestic debt initiated. / - Fiscal Risks report for 2025 published in August 2024 as scheduled.
2.2 New or strengthened instruments, and capacity building activities delivered for improved PIM	None	None expected.

Briefly describe the output’s activities and provide supporting narrative for the score. The output scored A and remains on track to hit end programme targets. The Fiscal Risks Report 2025 was issued on time and importantly expanded to include risks stemming from Public and Private Partnerships (PPP) and subnational entities. Preparatory work to migrate domestic debt data to the new Meridian debt database was initiated – e.g. validation of domestic debt data and creation of the interface between Meridian with Central Bank and Stock Exchange databases.

Describe any changes to this output during the past year, and any planned changes as a result of this review. No changes during the year nor planned for the year ahead.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead

Recommendations from previous Annual Review	Owner	Progress
6.1 As the WB GEDI team is gradually rebuilt, discuss a realistic level of ambition for its work (PIM in particular) and define more appropriate milestones and targets.	WB, FCDO. To start in August and to be completed by January. This should align with the planning period for the definition of annual milestones with GoM counterparts.	Ambition level revised down to remove the target of establishing a centre of excellence on PIM at a local university which was deemed unrealistic. Nevertheless, the performance of the PIM indicator unexpectedly worsened with the by-passing of the PIM system by the new GoM during production of the 2025 budget (see outcome indicator 3).
6.2 Ensure quantifiable milestones have the quantity defined in the logframe – this was not done for two GEDI output indicators (2.2 and 3.2) in the current AR logframe.	Logframe revision to be completed by January.	Completed.

Recommendations for the year ahead	Owner
3. Develop a strategy to ensure that the normal usage of the PIM system is restored from the next state budget 2026.	WB, FCDO

Output Title	Processes/tools are more efficient and supported by timely and relevant policy analysis and evidence conducted that feed into fiscal planning and national debate and contributes to government policies and stakeholder partnerships and positions on inclusive growth.
Output number:		3	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Streamlined and/or more efficient processes and/or tools put in place with TEG support	TEDI Development and training of an Excel-based tool to facilitate the application of the Extractive sector Resources Rent Tax (IRRM).	Met. IRRM tool designed, discussed and submitted to the Extractive Industries Taxation Unit (EITU).
3.2 Number of discrete pieces of analysis, policy notes or technical assistance reports with a focus on tax policy inclusive growth and natural resource management completed and disseminated, with GESI considerations, and aligned where possible with timing and relevance for national planning processes.	3 for TEDI (non-inclusive of GESI considerations)	Exceeded. / 8 (2 of which with GESI considerations).

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 3 scored A, with 3.1 met and 3.2 exceeded. TEDI production of discrete pieces of analysis is very responsive to GoM ad-hoc demand and the number of requests in the period is inherently uncertain. Because of that, milestone tends to be conservative, and as such, it makes more sense to score A the output rather than A+. TEDI supported the implementation of Mozambique’s Resource Rent Tax (IRRM), introduced to capture excess profits in the mining sector. Although the tax was enacted in 2016, it has not been effectively applied. To address this, TEDI developed a detailed Excel-based IRRM model and conducted a workshop, before final submission to EITU. Further training on the tool is planned for provincial officials.

Describe any changes to this output during the past year, and any planned changes as a result of this review. No changes made during the last year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Recommendations from previous year	Progress
Ensure that the debate about major reforms (e.g. establishment of a fiscal council in Mozambique; introduction of a MTBF) is broadened beyond the direct counterparts of GEDI.	This debate has not been initiated due to the electoral disruptions to normal activities and urgent pressures from the ministerial restructuring splitting Ministries of Finance and Planning.
Over the next year, the TEG team should explore the links between the FRA, PER and the institutional review of GoM in support of broader work on system strengthening.	TEG commissioned a PFM system mapping for Mozambique to help explore opportunities for future work on central systems strengthening with greater impact on service delivery. This analysis has been delayed and currently expected to be completed by September 2025.

## D: VALUE FOR MONEY (1 page)

Key cost drivers and performance
The ranking of spending shares for TEG (all 3 components aggregated) is: Staff costs (consultants, programme management staff) having absorbed 57% of the annual spend; Project expenses (25%); Procurement fund (12%); Management fees and profit (6%). These shares have been relatively stable throughout the programme duration (except for the first year of TEDI due to limited use of the procurement fund) with no particular budget line driving major variations in programme costs.

Spending category	Share of total spend (Jul24-Jun25)
Staff costs	57%
Project expenses (e.g. office exp, travel)	25%
Procurement fund	12%
Management fees and profits	6%
Total	100%

 VfM performance compared to the original VfM proposition in the business case

TEG’s VfM performance is good, as detailed below.

Economy and Efficiency
For TEDI, fee rate thresholds are defined by the FCDO International Multi-Disciplinary (IMDP) framework. Under this framework senior consultant rates are capped at 10%-15% lower than rates for some similar contracts. In addition to these capped fees, Cowater offered discounts on the fee rates charged to FCDO resulting in total discounts of over £26,000 during the 6 months review period. Together with savings generated from negotiated prices with suppliers and use of GoM meeting facilities instead of renting hotel rooms for workshops, total savings ascended to over £38,000.

The WB GEDI Trust Fund (TF) information remains insufficient to scrutinize VfM more thoroughly (e.g. it does not specify what technical expertise if being funded for what activities). The VfM of the GEDI component continues to be underpinned at economy level by World Bank’s robust procurement processes and institutional capacity. Combined with achievement of output level results it suggests good VfM at efficiency level.

Effectiveness
The outcome level performance worsened in the period which impacts on the overall VfM effectiveness. However, a large part of the deterioration was due to elections and post-elections disruptions, and we expect an improvement in the next period.
The sharp reduction in extractive sector revenue during the review period (-57% when compared to same period of previous year), due to elections disruptions and other operational challenges for some companies, suggests that any revenue gains from TEDI supported activities was limited. However, two key results achieved during this period hold significant potential for future revenue generation: i) the development and delivery of tools and training to implement the IRRM, aimed at taxing super-profits in the extractive sector; and ii) the revision of the Fiscal Benefits Code to reduce redundant tax incentives.
The period also saw a temporary reversal in the enforcement of the PIM system, which is critical for ensuring efficient and effective public investment. While this setback is concerning, it appears to be limited to the 2025 state budget cycle. The programme will continue to monitor developments closely and support efforts to resume full implementation of the PIM system.

Equity
The inclusion of GESI considerations in the Tax system diagnostic and roadmap for reforms should help ensure that upcoming discussions on tax reforms for fiscal sustainability are informed by GESI sensitivities. For next year, TEDI will conduct an End-line survey to assess more comprehensively the impact of its GESI work that has been focused on tax policy analysis and communications.

Assessment of whether the programme continues to represent value for money
TEG continues to demonstrate value for money. To date, the programme has directly contributed to additional tax revenues estimated at approximately three times the total cost of the programme. Moreover, it has played a key role in supporting positive assessments by the IMF and World Bank, which contributed to disbursements of budget support valued at over ten times the size of the programme.

It is important to note that the current revenue estimates likely understate the actual gains due to measurement and reporting limitations. They also exclude future revenue benefits expected from the strengthened instruments and processes introduced by TEDI.

E: RISK [½ to 1 page]

Overview of risk management

TEG remains a Major risk programme. During the period, Context and Delivery risks related to elections and inauguration of a new GoM have largely materialised. The elections period and post-elections instability increased security risks and directly impacted execution of project activities. Leadership and structural changes within MoF and MRA led to reduced engagement. While the situation is gradually stabilising, context and delivery risks remain classified as Major. Looking ahead to the final eight months of the programme, risk management efforts should prioritise the following:
- MoF Transition: One of TEG’s key counterparts at MoF is transitioning to a newly established department that is not yet operational. This shift has reduced engagement from the outgoing department and poses a risk of delayed activity from a slow start by the new department. To mitigate this, TEG has proactively engaged with both the Minister of Finance and the Secretary of State for Budget and Treasury to encourage a swift operationalisation of the new department and to position TEG for rapid collaboration once it is functional.
- Financial risks: As the programme approaches its end-date, the risk of financial underspend increases. The current opportunities to accelerate or scale up activities are insufficient to absorb the remaining budget within the existing timeframe. TEG should explore the possibility of a no-cost extension, which could allow for new areas of intervention and help bridge the programme to future BHC initiatives in economic governance.
Fiduciary risk remains moderate. All funds are managed by Cowater and the World Bank, both of which have robust financial and procurement systems in place. Safeguarding risks are minor and well mitigated, with both implementing partners maintaining strong policies and systems aligned with FCDO standards. In January 2025, FCDO has updated the portfolio and project-level due diligence assessment of the World Bank, including a review of its safeguarding frameworks

A detailed programme risk matrix is updated on a quarterly basis throughout the year. Risks are updated by the Programme Officer and Senior Responsible Owner/Programme Responsible Owner, based on discussions with delivery partners and government. The following is a summary of pre- and post-mitigation risk status of the 12 risks identified in the risk matrix. There are no risks outside the mission risk appetite.

Summary of risks pre-mitigation
Severe	Major	Moderate	Minor
4	4	4	1
Summary of risks post-mitigation
Severe	Major	Moderate	Minor
0	1	5	7

Update on Partnership Principles

Both the technical assistance and the support to GoM investment components of the programme are designed to not use GoM financial systems. A fiduciary risk assessment was produced in 2023 under the M&D component of the project. It found that fiduciary risks had reduced in most areas but remained high. This confirms that our current approach remains valid.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The TEG Programme has a total approved budget of £20 million, of which £14 million are FCDO Funds and £6M Sida funds. Since the start of the Programme (GEDI in December 2018, TEDI in January 2020 and the Monitoring and Evidence component in July 2018), FCDO has disbursed a total of £16.3 million (£12.2M from FCDO Funds and £4.1M from Sida Funds). Across the 3 components, £6.5 million has been channelled to the World Bank, £9.6M to Cowater, and £0.2 million to various under the M&D component.

Financial execution is behind schedule. Nine months before the end-date of the project, TEG has a balance of £3.6 million. The balances per component are: TEDI (£2.3 million of which, £0.5 million from FCDO and £1.8 million from Sida); GEDI (£0.5 million) and M&D (£0.8 million). By the current programme end-date, the underspend is likely to be between £1.0-£1.5 million

A quarterly Performance Assessment Framework (PAF) is in place to assess and help improve Cowater’s performance, and to inform payment by results (up to 25% of fees are withheld until satisfactory performance is confirmed). The PAF KPIs (Key Performance Indicators) assess the quality and timeliness of agreed reporting, implementation of deliverables and accuracy of monthly financial forecasting. Cowater has consistently met all KPIs and maintained a positive approach to feedback and adjustments requested such as responding swiftly to requests for earlier submission of reports, forecasts or invoices. Cowater has strong financial and administrative systems in place.

Regarding audits and asset monitoring and control, the World Bank provides a Single Audit report annually. For the reporting period the report will be available in September 2025. For TEDI, an Audit Report should be submitted by end of June every year but due to ongoing challenges with auditors in Mozambique, Cowater have experienced delays each year with the TEDI Audit. The Audit for 2024 is ongoing and the report is expected to be completed by end August 2025.

TEDI maintains an updated asset registry, which is shared and reviewed by FCDO quarterly. The review of TEDI’s assets procedures and controls sufficiency is part of the annual audit objectives, thus a spot-check was not conducted and the relevant information will be submitted with the audit report. No assets were purchased through the GEDI component. The team at FCDO are in regular contact with government counterparts, particularly in relation to the TEDI component, to ensure the programme is demand-led and that any potential barriers to implementation can be overcome.

Date of last narrative financial report	WB Economic Governance component – GEDI annual report (February 2025) / Tax Component - TEDI Financial Report (January 2025)	Date of last audited annual statement	September 2024 / Ongoing

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring and Evaluation
TEG monitoring of progress is done through regular meetings, written reports and emails and ad-hoc conversations. The regular planning and monitoring meetings are: i) the TEDI Steering Committee (expanded to include GEDI) meet twice a year with participation from FCDO (senior and technical level), MRA and MEF directors, Cowater, WB, Sida and IMF. The SC chair has been the same since its creation, having changed its position in GoM in 2025 from MEF Permanent Secretary to advisor of the minister of finance; ii) FCDO and Cowater meet monthly for a regular catch-up on TEDI (an email with updated progress is submitted before every meeting); iii) FCDO meets with the WB every two-months. Going forward, it would be useful if TEDI could join the annual planning meetings between WB and GEDI counterparts.

Regarding written reports: i) Cowater submits progress reports quarterly and annually, and Cowater performance is assessed quarterly; ii) the WB submits a 6-months report and another for the year; iii) the Tony Blair Institute submits progress reports every six-months. The TEG team maintains a good professional and cordial relationship with implementers and with some of the GoM counterparts. As such, informal phone calls/WhatsApp messages are often used to discuss emerging issues.

Evidence
Access to data to measure outcome level results remains a significant challenge. TEDI has been working with counterparts to strengthen the monitoring and reporting of results, but improvements are still marginal. TEDI should prioritize strengthening outcome-level reporting in the next period to ensure robust data is available for the project completion report.

Learning
Both the WB and Cowater have specific sections in their regular reports to identify lessons learned. Cowater includes a specific section to report on how it will act on new learning and in the following period reports on actual actions taken and any new learning from those. These reports are extensively discussed during the regular engagements with FCDO. In September 2023, TEG completed its mid-term revenue that provided valuable lessons and recommendations that are being followed and monitored by implementers and FCDO.

A key learning exercise planned for next year is the GESI end-line survey to deepen the understanding of the outcome/impact TEDI GESI related work. To note that the planned GESI mid-line survey was dropped due to elections related disruptions.