## Annual Review

Title: Tax and Economic Governance (TEG)
Programme Value £ (full life): 20,000,000		Review date: March 2026
Programme Code: 300212	AMP start date: 20/08/2018	AMP end date: 31/12/2026

Summary of Programme Performance
Year	2019	2020	2021	2022	2023	2024	2024 (Jul-Dec. Light-touch)	2025
Overall Output Score	A	A	A	A	A	A	A	A
Overall programme risk rating	Major	Major	Major	Major	Major	Major	Major	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/40109555.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0006906.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

The Tax and Economic Governance (TEG) Programme is a £20 million, eight year initiative supporting Mozambique to strengthen domestic revenue mobilisation, improve economic management, and foster national dialogue on inclusive growth and natural‑resource revenue governance. Its overarching goal is to enhance fiscal sustainability and promote the transparent, effective use of public resources for inclusive growth. The programme initial timeframe was 6 years with a budget of £16.5 millions of UK funds only, and both were increased during implementation. The programme is made up of 3 components:[1]
[1] Sida formally joined the TEDI component in July 2022 allowing for a time and costed extension of the project.

1. Tax Reform for Inclusive Development (TEDI), £12m, of which £6million from FCDO and £6million from the Swedish International Cooperation Agency (Sida). Provides Technical Assistance (TA) and in-kind support to strengthen tax administration and policy. This component is delivered through a contracted service provider (Cowater International) and supports both the Ministry of Finance (MF) and Mozambican Revenue Authority (MRA). TEDI support outputs 1 and 3 of the logframe.

2. Governance for Inclusive Growth (GEDI), £7m: Providing TA to MEF, and policy analysis, implemented through a World Bank-Executed Trust Fund initiated under this programme. GEDI focuses on three main areas: strengthening analysis and planning for inclusive growth; strengthening public investment management; and strengthening debt and fiscal risks management. GEDI activities support outputs 2 and 3 of the logframe.

3. Monitoring, diagnostic and evidence (M&D), £1m: The component is directly managed by the FCDO TEG team to commission activities providing cross-cutting support to the programme objectives, providing flexibility for analysis and punctual support to emerging opportunities. For instance, under this component TEG commissioned the mid-term review of the programme, is supporting Mozambique’s efforts to strengthen Anti-Money Laundering/Counter Terrorism Financing (AML/CTF) to exit the Financial Action Task Force (FATF) grey-list (achieved in the period under review) and is supporting the FCDO’s Inclusive Growth agenda.

At end-2025, TEG was no cost-extended to December 2026 allowing the programme to consolidate institutional reforms and to bridge the gap with the future portfolio.
Summary supporting narrative for the overall score in this review January 2025 – December 2025

During the review period, TEG maintained strong engagement and results across several areas, despite a challenging context marked by macro fiscal fragility, political uncertainty and constrained institutional capacity. FCDO supported this through robust policy engagement with GoM counterparts, strong and collaborative oversight of implementers, and close coordination with other partners.

The programme scored an ‘A’ overall, with all three outputs individually also scoring ‘A’. Performance against output‑level indicators was strong with several indicators met or exceeded with exception of Gender Equality and Social Inclusion (GESI) indicators that were slightly missed. TEDI delivered the planned technical assistance and capacity‑building activities and generated substantial gains in protecting the tax base – through strengthened audits and extractives valuation identifying significant potential liabilities. GEDI delivered the expected system‑strengthening outputs, including timely and expanded fiscal‑risk reporting, further improvements to the Medium‑Term Fiscal Framework (MTFF), and completion of climate‑sensitive public‑investment management tools.

The outputs are contributing to outcome level gains, particularly in revenue mobilization, and improved processes and contents for the Medium‑Term Fiscal Framework (MTFF), debt management, and fiscal-risk analysis. However, TEG did not meet its outcome level ambition for Public Investment Management (PIM) reflecting the increasingly challenging contextual conditions and government actions beyond the programme’s control.

Headline results:

Over £220 million of additional revenue (mobilised and potential) from TEDI’s tax administration support: Audits in the extractive sector identified £165.6 million in potential additional liabilities; the introduction of international reference pricing increased declared mineral export prices from 62% to 84%, generating an estimated £52.3 million in additional potential revenues; targeted enforcement notices to tax debtors contributed to £2.39 million of additional payments completed.

Institutional development for tax policy reform: TEDI contributed directly to the creation of Mozambique’s first dedicated tax‑policy directorate by building the Ministry of Finance’s analytical capacity over several years. TEDI’s tax‑policy diagnostics and reform roadmap informed the Government’s medium‑term National Revenue Strategy, and several officials trained under TEDI are now part of the new directorate. This represents a significant institutional step toward in establishing a permanent, evidence‑driven tax‑policy function within government.

Strengthened macro-fiscal management tools: With continued GEDI support to the MTFF process, the MF prepared and published the MTFF (2026–2028) using improved modelling and better integration of macroeconomic and debt data. The national debt‑management system was fully institutionalised for external debt and around 75% of domestic debt was migrated into the meridian system, following GEDI’s work on data validation, system configuration and coordination with the central bank and stock exchange. [2] GEDI produced the analytical foundations for the Fiscal Risk Report 2025, enabling its timely release with expanded coverage of pensions, climate risks and state‑owned enterprises. For public investment management, GEDI supported the development and update of key tools for project appraisal – including a revised climate‑sensitive framework and a new assessment tool for public–private partnerships. However, PIM has the biggest gap between output progress and outcomes, as only 7% of public investments in the budget were assessed under the PIM system, compared with a 100% ambition.
[2] The Meridian system is a modern debt data storage system that improves consistency and credibility of debt data.

Improvements in financial integrity: Programme funding enabled a fulltime national adviser to support implementation of Mozambique’s FATF action plan on AML/CTF, helping secure the country’s removal from the grey list in October 2025. This contribution strengthened monitoring and interagency coordination, reducing financial sector risks and supporting investor confidence. UK support focused on the urgency to exit the FATF grey list and avoid the related economic costs. For the remainder of TEG, the focus will be on 2 aspects: i) to fund TBI delivered capacity building to ensure GoM is able to perform all coordination and reporting on its own; and ii) to co-fund together with Swiss Development Cooperation (SDC) a project to support financial transparency and assets recovery to further incentivise responsible investments and reduce revenue leakages.
Major lessons and recommendations for the year ahead

Lessons:
Experience in 2025 confirmed that reform progress continues to depend on addressing political economy constraints, strengthening institutional ownership, and improving data flows across government. PIM is a telling example – the system was largely bypassed during the 2026 budget process, demonstrating that technical reforms alone are not sufficient without clear roles, disciplined cross departmental coordination, supported by a legal framework and high-level endorsement.

Durable results come from strengthening core systems – such as valuation tools, debt management platforms, project appraisal frameworks, and fiscal planning procedures – rather than relying on one-off training. These gains also require comprehensive, well sequenced and often long-term interventions. For example, increased and fairer revenue collection from audits depends not only on better quality of audits, but also on stronger taxpayer risk management systems and more effective post-audit litigation processes, such as the Fiscal Court. Coordination with other partners will be increasingly important to ensure support is delivered at the right scale and with sufficient coherence.

Strong monitoring and reporting must be built into delivery from the outset: when data flows are weak or delayed, even strong results cannot be fully evidenced. This underlines the importance of early agreement on expectations and data‑sharing with GoM counterparts, though in practice incentives for transparent and timely data provision can be deeply entrenched in political-economy dynamics and challenging to shift in a sustained manner.
Recommendations for 2026

As the programme enters its final phase, the focus should be on actions that are achievable and have the greatest likelihood of sustaining results beyond closure. These recommendations set out the priority actions required in the final months of TEG to consolidate results, ensure orderly closure, and maintain the durability of key reforms.

Recommendation (SMART Action)	Responsibility	Completion Date
1. Complete the TEDI outcome harvesting analysis and GESI end-line survey and produce respective short findings summaries to inform the FCDO Project Completion Report.	TEDI (lead), / FCDO (review and integration into PCR)	September 2026
2. Finalise audit cases initiated under TEDI ensuring taxpayer comments are addressed and provide guidance for follow-up steps to support revenue recovery after TEG closure.	TEDI (delivery), / FCDO (oversight)	September 2026
3. Review the legal and institutional framework to ensure compliance with the requirement that only e-MIP[3] approved projects are included in the state budget.	GEDI (technical assistance), FCDO (help broker agreement with counterparts)	December 2026
4. Produce at least two policy briefs that support government discussions and public debate on tax or fiscal issues.	TEDI (tax briefs), / GEDI (fiscal briefs), / FCDO (oversight)	TEDI: September 2026 / GEDI: Dec. 2026
5. Document and hand over all core tools and related guidance in consolidated packages for continued use by MEF and MRA to support post-TEG continuity. Handover to FCDO of all non-confidential analysis produced under the programme.	TEDI (valuation, audit, GESI tools and processes and various tax policy analysis), GEDI (MTFF, debt, fiscal risks and PIM tools and processes and various analysis reports), FCDO (handover oversight)	TEDI: September 2026 / GEDI: December 2026
6. Align remaining deliverables with the UK–Mozambique Growth Pact and consolidate lessons for future programming. Prepare a short handover note mapping final outputs to Growth Pact priorities (based on guidance provided by FCDO) and document lessons from existing demand side pilots (e.g. CSO, media or academic engagement) to inform the design of future UK support.	FCDO (lead), / TEDI (technical input), GEDI (technical input)	TEDI: September 2026 / GEDI: December 2026
7. Extend financial transparency support to ensure greater sustainability of reforms and processes and provide support to and assets recovery project jointly with SDC.	International Centre for Assets Recovery – ICAR (lead for assets recovery); / TBI (lead for AML/CTF overall coordination and sustainability); / SDC and FCDO (oversight and brokers).	December 2026
8. Update the logframe targets following last programme no-cost extension.	TEDI and GEDI (propose new targets). / FCDO (validate the new targets and review the logframe).	April 2026
[3] Electronic Mozambique Investment Platform

For a list of major recommendations from the previous annual review, and their status, please refer to ANNEX: List of Major recommendations (from last AR Aug 2025).

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

TEG’s Theory of Change (ToC) sets its outcome-level ambition as ‘Strengthened Government of Mozambique capacity and processes demonstrated through improved revenue administration and more effective and transparent management of public resources’. This ambition is largely being met – though unevenly – across TEG’s intervention areas, and the ToC remains broadly valid up to the outcome level.

At the impact level, the ToC aspires to contribute to ‘Improvements in inclusive growth and wider access to services’. Achieving this by TEG’s closure is unlikely, given the far more challenging-than-anticipated political economy barriers to reform and the influence of external shocks (e.g. climate, COVID-19, and international conflicts). While the impact ambition is unfeasible by the programme’s endline, TEG has established important technical foundations to drive impact even if protracted.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

In 2025, TEG remained broadly on track to achieve its intended outcomes, with notable overperformance in areas where institutional tools and embedded advisory support effectively drove behavioural change (see table below). Although ambitions for tax policy reform were not achieved—partly due to a constructive ministerial restructuring that formally integrated tax policy into an MF department but slowed progress during its lengthy establishment—revenue related outcomes exceeded expectations overall. Extractives audits and strengthened valuation practices generated significant potential revenue gains, while enforcement actions translated into realised collections. These results demonstrate that TEDI’s support is directly enhancing taxpayer compliance and safeguarding the tax base.

PIM challenges affected progress towards Outcome 2 (PIM screened new‑ projects). Despite major technical achievements under GEDI – such as updated climate sensitive PIM guidance and strengthened appraisal tools – only 5 projects (7%) included in the Budget FY2026 followed the required e-MIP process. This reflects limited institutional discipline rather than technical shortcomings, including disruptions from institutional fragmentation following ministerial restructuring. Planned actions for 2026 include (i) strengthening the legal and institutional framework for PIM; ii) formalising a DNPED[4]–DNO[5] gatekeeping mechanism; (iii) improving interoperability between eMIP and MPO[6] systems; and (iv) using the 2027 budget cycle to enforce compliance and test strengthened processes.
[4] National Directorate of Economic and Development Planning
[5] National Budget Directorate
[6] Planning and Budgeting Module (within the Government’s budgeting system)

Progress toward strengthened debt and fiscal risk management remained strong. The Meridian system is institutionalised for external debt, with domestic debt migration reaching approximately 75%, meaning that government now has a more complete, reliable and centralised record of its debt, which improves forecasting, reduces errors and strengthens fiscal decision-making. Although this progress coincided with a deterioration in the public debt sustainability assessment, improved data reliability and coverage will be essential for the forthcoming debt restructuring process. The MTFF continues to be used routinely and has improved in methodological rigour and credibility. This means that Government budgeting should become more realistic, because forecasts are based on better data and clearer assumptions. Planned actions for 2026 include completing domestic debt migration, integrating Meridian with e-SISTAFE[7], and broadening fiscal risk coverage (especially on SOEs and climate risks). Completing these actions will give government a clearer, more complete view of its liabilities and risks, improving planning and reducing the chance of fiscal shocks.
[7] State Financial Administration System

Overall, the programme remains broadly on track to deliver the outcome level results within its final months, including recovering the small underperformance in 2025 of domestic debt migration to Meridian. The PIM outcome is more uncertain but still possible. The priority for the remaining months is therefore to consolidate gains, ensure responsible closure, and leave the systems supported by the programme in a sustainable, usable state for government to build on.

Outcome Progress Assessment
Indicators (*)	Milestones for this review	Target (2026)	Progress
1. Evidence of direct revenue-generating activities as a result of TEDI programme activities (e.g., audit, extractives, tax policy)	Evidence of 3 direct revenue-generating activities as a result of TEDI programme activities (£ where possible) / 1. Tax policy measures (e.g. approval of Fiscal Benefits Code and/or rationalisation of VAT exemptions). / 2. Monitoring Visits to Extractive Industries (EI) companies / 3. Bloomberg database.	Evidence of 2 direct revenue-generating activities as a result of TEDI programme activities in the year (£ where possible) – non-cumulative target.	Exceeded / Four revenue‑linked actions were delivered: / 1. Monitoring and inspection visits to EI taxpayers produced immediate compliance follow‑up. / 2. The international reference‑pricing system (Bloomberg) increased declared mineral export prices, generating an estimated £52.3 million in potential additional revenues. / 3. EI audits identified £165.6 million in potential additional liabilities. / 4. Enforcement notices issued with programme support resulted in £2.39 million in voluntary payments.
2. % of new projects (and % of investment budget) funded through the budget or through SOEs selected through the PIM system.	100% of new projects funded through the budget have been selected through the public investment management system.	100% of new projects funded through the budget have been selected through the PIM system.	Not Achieved / Share of new projects selected via e-MIP in state budget 2026: 7% (5 projects).
3. Share of majority State-Owned Enterprises (SOEs) included in the Government of Mozambique's debt database	80 percent of domestic debt migrated into Meridian.	80% of SOEs included in Meridian. SOE debt records centralized through a shared application between central GoM and the institute for state participation in enterprises.	Nearly Achieved (75% vs 80% target) / ≈75% migration by end‑2025 (all Treasury Bonds uploaded; Treasury Bills ongoing manually) targeted to surpass 80% early‑2026.
4. Evidence of national strategies, policies and budgets (including tax policies) adopted that draw on policy analysis and are consistent with inclusive growth and fiscal sustainability.	TEDI: 1 analysis informing the revision of the VAT code. GEDI: Fiscal risks analysis informing MTFF and budget documents and debt strategy	TEDI: 2 analysis informing national strategies/policies/legislation. GEDI: Fiscal risks analysis informing MTFF and budget documents and debt strategy.	Achieved. / TEDI analysis informed: the National Revenue Strategy that was approved by the council of ministers; The SWF[8] investment policy revision and LNG fiscal regime work. GEDI fiscal risk analysis underpinned MTFF 2026-28 and State budget 2026.
[8] Sovereign Wealth Fund

Confidence statement: Green/Amber. The programme continues to demonstrate credible progress toward its outcome‑level objectives. However, confidence is moderated by areas where results remain partially achieved and by persisting challenges in data-sharing for results monitoring. To note that following the no-cost extension of TEG formally completed in March 2026, the end-programme logframe targets will be reviewed in April 2026.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

TEG is scheduled to close in December 2026 and continuation of the programme through the final months remains justified. The programme continues to demonstrate strong value for money, having generated fiscal gains far exceeding its cost and embedded improvements in core systems that will strengthen government performance beyond the programme’s lifespan. Within the wider FCDO portfolio, TEG underpins key objectives on economic stability, inclusive growth and governance, and provides analysis that supports broader donor engagement, including IMF and World Bank operations. Given Mozambique’s acute fiscal pressures and the ongoing need for credible tax policy, debt transparency and macro fiscal management, completing the programme to its planned end date allows for responsible closure, consolidation of institutional gains, and a structured handover to future UK engagement.

## C. DETAILED OUTPUT SCORING

Output Title	The MRA’s capacity is increasingly strengthened to improve performance in the functions of audit to taxpayers and taxation of extractive industries.
Output number:		1	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestones (s) for this AR	Progress
1.1 Improved capacity of the audit function - measured by: a) no. sectors where specialised audit trainings have been delivered to MRA staff (formal and/or on-the-job); and b) no. audits in specific sectors conducted (initiated, underway or completed) by trained staff;	a) Phase 3 of specialised audit training delivered for 2 sectors (banking & telecoms); and Compliance Risk Management (CRM) workshop delivered across same sectors. b) 3 audits in Banking Sector and 1 audit in telecoms sector initiated in the year with trained staff working on it.	Achieved / a) Achieved. Phase 3 of Training delivered for banking & telecoms; Compliance Risk Management (CRM) workshop delivered across same sectors in all 3 regions of Moz. / b) Achieved. Total of 4 audits (2 for banking and 2 for telecoms sector) initiated with trained staff working on them.
1.2 Improved extractives industries taxation unit measured by: a) No. of capacity building activities delivered (formal and/or on-the-job) b) No. of pieces of Transfer Pricing (TP) analysis conducted (started/completed).	a) 6 capacity building activity and/or trainings conducted / (of which 3 contain TP elements) / b) one TP analysis commenced on one Oil & Gas or Mining company	Exceeded / a) Achieved. Seven CB activities conducted of which 2 have TP elements. / b) Exceeded. 4 / TP analysis initiated on 3 mining companies and 1 O&G company.
1.3 Number of materials on GESI designed or disseminated with TEG assistance delivered to MRA and/or MEF, with % trainees/beneficiaries reporting improved understanding/awareness of GESI as a result of TEDI capacity building activities (disaggregated by sex).	a) Delivery of taxpayer education/comms material covering 6 topics. / b) ≥75% male/female trainees reporting improved GESI understanding/awareness as applied to domestic revenue mobilisation; and post-test scores to improve by average of ≥20% compared to pre-test scores.	Partially Achieved / a) Partially Achieved. 3 materials covering 3 topics. / b) Partially Achieved. Pre-and Post-test results from Do No Harm training showed average score on knowledge test increase from 64% average before training to 80% post-training.

Briefly describe the output’s activities and provide supporting narrative for the score.

Delivery under Output 1 was strong in 2025, with the programme meeting or exceeding four of the six milestones. The most strategically important and value for money areas – strengthening audit capability and improving extractives taxation – performed above expectations, with trained teams applying new methods and initiating live cases, and the extractives unit undertaking its first internally led transfer pricing analyses. These achievements reflect a shift from training to practical, operational uptake, which is central to the theory of change.

Performance on GESI was mixed, but the minor deviations from milestones did not materially affect the output’s overall achievement. Although the measured learning improvement from pre to post training reached 16% against a 20% target, participant satisfaction remained strong (80% versus a 75% target). The shortfall in communication products reflects a deliberate reduction in ambition – made after the logframe review deadline – as part of the no cost extension discussions, rather than an implementation gap.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes made. A logframe revision is planned following the programme no-cost extension.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

The previous AR (August 2025) did not include any recommendations for this output. Given the short time left, the next period should be used to close this area of work responsibly, ensuring initiated audits (see recommendation 2) are completed and that key methods and tools introduced by the programme are clearly explained, documented, and passed on to the tax authority (see recommendation 5).

Output Title	Strengthened Government of Mozambique systems, policies, and reforms for economic management, focussed on PIM, fiscal risks, and debt management.
Output number:		2	Output Score:	A
Impact weighting (%):		40%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Debt management and fiscal risks Instruments and analysis (including for SOEs) produced for use in fiscal planning activities.	2 new fiscal risks instruments: Enhanced analysis on pensions and on climate risks- Fiscal risks report 2025 issued on time.	Achieved / - Pension fiscal risk instrument: PROST‑based pension sustainability analysis conducted and technical note on pension‑related fiscal risks prepared. / - Climate‑related fiscal‑risk instrument delivered, including modelling methodology and integration of climate risks into the Fiscal Risk Report 2025, supported by training for MoF staff. / - Fiscal Risk Report 2025 issued on time and publicly disseminated.
2.2 New or strengthened instruments, and capacity building activities delivered for improved PIM	2: Climate-smart PIM and PPP risk assessment	Achieved / - Climate-smart PIM instrument delivered: Climate risk screening review completed; updated Climate-Sensitive PIM Framework prepared; dissemination workshop delivered. / - PPP risk assessment instrument delivered: Review of PPP risk management practices and development of a PPP readiness assessment tool and report.

Briefly describe the output’s activities and provide supporting narrative for the score.

Delivery under Output 2 remained strong, with all milestones met and key system strengthening instruments completed. GEDI delivered two major fiscal risk products - pension sustainability analysis based on a Pension Reform Options Simulation Toolkit (PROST), and new climate risk modelling – and issued the Fiscal Risk Report 2025 on schedule. Progress on debt management continued, with external debt fully institutionalised in the national system and around 75% of domestic debt migrated, improving transparency and forecasting. Public investment tools were also strengthened through an updated climate sensitive project appraisal framework and a new PPP readiness and risk assessment tool, both validated with government counterparts. Although the outcome level indicator on PIM usage was not achieved due to institutional noncompliance during the 2025 budget process, the underlying technical foundations for future improvement were significantly reinforced.

Against the indicators, fiscal risk instruments were completed and incorporated into reporting as planned, and both climate smart PIM and PPP tools were delivered in full. Overall, Output 2 reflects strong progress in strengthening the Government’s core economic management systems. GEDI delivered the tools needed for improved fiscal risk analysis, debt management and investment appraisal, and the Ministry of Finance has begun to apply several of these—most visibly through the use of enhanced modelling in the MTFF, the integration of climate and pension risks in the Fiscal Risk Report 2025, and the continued use of the national debt management system. While some tools, such as the updated PIM framework, are still in early stages of uptake, the technical foundations for longer-term institutional consolidation are now in place. Remaining weaknesses are linked to institutional discipline rather than technical gaps, justifying an A score.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes made. A logframe revision is planned following the programme no-cost extension.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation from last AR	Status	Evidence
1. Develop a strategy to ensure that the normal usage of the PIM system is restored from the next state budget 2026.	Partially Addressed (strategy developed; not yet implemented due to 2025 budget conditions)	The strategy was developed: all its technical, procedural and institutional components appear in the 2025 GEDI report. / Its implementation, however, continues unsatisfactory due to limited enforcement of the system.

Recommendation for 2026:
Given the limited time remaining, the focus for 2026 should be to continue with the implementation of the strategy to ensure adequate use of the public investment system rather than attempting full restoration. Priorities include completing and implementing the recommendations from a diagnostic of the legal and institutional framework, updating project appraisal tools, strengthening coordination between planning, project screening and budgeting processes.

Support in the remaining months should centre on responsible closure, making sure the systems strengthened during the programme are left in a usable state, and that government counterparts are positioned to take the reforms forward after the programme ends.

Output Title	Processes/tools are more efficient and supported by timely and relevant policy analysis and evidence conducted that feed into fiscal planning and national debate and contributes to government policies and stakeholder partnerships and positions on inclusive growth.
Output number:		3	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Streamlined and/or more efficient processes and/or tools put in place with TEG support	TEDI: i) Bloomberg database; ii) IRRM[9] taxpayer form Guidelines; iii) Risk criteria framework. / GEDI: Capacity successfully built, demonstrated by Ministry of Finance producing credible MTFF on a regular basis.	Achieved / TEDI: All 3 milestone products delivered. / GEDI: MF produces improved and timely MTFF, demonstrating that TEG‑supported tools, processes, and capacity‑building have strengthened and streamlined macro‑fiscal planning.
3.2 Number of discrete pieces of analysis, policy notes or technical assistance reports with a focus on tax policy inclusive growth and natural resource management completed and disseminated, with GESI considerations, and aligned where possible with timing and relevance for national planning processes.	TEDI: 5 of which at least 2 inclusive of GESI considerations / GEDI: 4 notes: Fiscal Council Notes, SOE note, Tax Policy Note, and Growth and Jobs Diagnostics (slide deck)	Achieved / TEDI produced 9 analyses, exceeding the volume target. / Only 1 included GESI considerations (VAT exemptions incidence analysis), below the required 2. / GEDI delivered all four items in the required domains
[9] Imposto sobre a Renda de Recursos Minerais - Resource Rent Tax

Briefly describe the output’s activities and provide supporting narrative for the score.

Delivery under Output 3 remained strong, with all planned tools completed and taken up by government counterparts. The mineral reference pricing database is now operational and used routinely; the resource rent tax form guidelines were finalised; and a sector wide risk criteria framework was developed to strengthen audit case selection. The MF continued to produce credible medium-term fiscal frameworks, demonstrating improved analytical capacity and consistent use of programme supported tools. TEDI produced nine policy notes, and GEDI delivered four analytical products informing fiscal rules development, state-owned enterprise risk assessments, tax and trade policy, and inclusive growth diagnostics, meeting or exceeding the required targets apart from the GESI proportion. Overall, all milestones were achieved or exceeded except for slight underachievement on GESI analyses. Tools were delivered and embedded across valuation, audit and macro fiscal processes as planned, and the quality and integration of these outputs justify an A score.

While not included in the logframe milestones, it is important to note that TEG funded the mapping of public financial management systems completed in November 2025 – later than planned – to help inform options for future UK support.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes made. A logframe revision is planned following the programme no-cost extension.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

The previous AR (August 2025) did not include any recommendations for this output. Given the limited time remaining, the focus should be on responsibly closing this output rather than starting new reforms and completing the GESI end-line survey to assess changes in awareness and inclusion relative to baseline and provide short findings summary for use in FCDO’s project completion report (see recommendation 1). This means ensuring that the key analytical tools and policy products developed under the programme are properly documented, shared with the relevant government teams, and positioned to be used after the programme ends (see recommendation 5).

## D: VALUE FOR MONEY

Key cost drivers and performance

Spending Category	TEDI (£)	GEDI (£)	TBI and Fiscus (£)	Combined (£)	% of Total
Staff Costs	1,401,553	183,925	38,760	1,624,238	57.0%
Project Expenses	927,603	191,452	0	1,119,055	39.2%
Management. Fees & Profit	72,555	32,415	3,640	108,610	3.8%
TOTAL	2,401,712	407,792	42,400	2,837,503	100%

The programme maintained strong financial control in 2025, with total expenditure of £2.84m. All components remained within FCDO’s 5% monthly forecast variance tolerance throughout the year. However, relative to the forecast at the start of the year, TEG revised spending downward to reflect counterparts’ absorption capacity constraints. This underspend, combined with flexible and adaptive planning to support TEG’s transition into the new UK portfolio, underpinned the approval of a nine‑month programme extension, from March to December 2026.

Staff costs (57% of total spend) continued to be the programme’s main cost driver, as expected for a technical assistance programme, reflecting the high and relatively inflexible market rates required for specialised audit, extractives, macro‑fiscal and debt‑management expertise. These inputs are essential for delivery, have few viable lower‑cost substitutes, and therefore represent the most structurally difficult cost category to reduce without undermining results.

Project expenses (39% of total spend), includes the TEDI procurement fund (£341k) to provide in-kind support (e.g. equipment and software) to GoM counterparts, were driven by renewed in person missions, workshops, and reflected broader market inflation in travel, accommodation and logistics rather than supplier‑driven price increases. Contracted rates remained within agreed ceilings, and procurement processes ensured that input costs were controlled despite rising market prices.

Management fees and profits (4% of total spend) remained broadly consistent with the agreements with implementing partners, with WB and TBI charging 15% and 13% of personnel costs, respectively. While Cowater’s net profit and margins in 2025 reached 3%, exceeding the 1.4% rate for the whole contract, Cowater’s cumulative net profit and margins from project start up to December 2025 remains below 1% of total cumulative spend.

Overall, combined TEDI–GEDI-TBI spending reflects well-coordinated planning and focused delivery. Combined financing enabled expanded analytical work, strengthened modelling and reporting systems, and targeted capacity building across MEF, MRA and other institutions. The programme delivered strong value for money while effectively supporting partners to manage rising macro fiscal‑ pressures and advance priority reforms.

VfM performance relative to the original business case

Economy and Efficiency: The programme maintained strong cost discipline throughout the year. The most tangible economy gains came from practical delivery adjustments – most notably relocating workshops and training to government or programme premises, which saved £13,426 without affecting quality. Although overall mission activity increased, efficiencies were generated by reducing travel per output through greater use of local and regional experts, combined missions and remote follow-up, alongside tight financial forecasting that kept variance low across components.

Programme efficiency was further strengthened by deliberately reallocating resources toward higher yield activities: TEDI’s focus on extractives valuation, transfer pricing reviews and targeted audit support generated significantly greater potential fiscal returns for the same level of expenditure, while joint missions and on-the-job support models reduced the cost per output. Together, these choices ensured that resources were used effectively and increased the value delivered for each pound spent.

Effectiveness: The programme delivered strong effectiveness results in 2025, particularly in revenue mobilisation and macro fiscal management. Under the tax component, potential and realised additional revenue mobilisation reached a total of £220 million. The exit from FATF grey list can help protect or mobilise additional investments which would further contribute for public revenue collection. These results demonstrate that targeted technical assistance can translate into concrete fiscal effects helping smooth the fiscal pressures. Effectiveness was also reinforced through system level improvements delivered by the governance component as evidenced by the consistent production of timely and improved MTFF, fiscal risk analysis, and national debt reports. These results reflect strong progress in consolidating core economic management systems that underpin long-term fiscal stability.

Equity: Gender and inclusion considerations were integrated into delivery where relevant. TEDI supported the development of simplified taxpayer information materials with gender‑sensitive messaging, and training activities showed strong participation (above 50%) by women. Learning outcomes also improved indicating stronger awareness of how tax measures and communication practices can affect different groups. While performance against GESI milestones during the year was mixed, the progress was solid progress and aligned with more realistic and strategic ambition (see output 3).

Overall assessment of VfM: The programme continues to demonstrate strong value for money, combining disciplined cost management with targeted interventions and adaptive allocations that generate measurable fiscal benefits and strengthen core government systems, aligned with the programme ToC. TEDI’s focus on high yield activities – such as extractives valuation, audit follow-up and transfer pricing work – was able to identify additional revenue opportunities far greater than the cost of delivery. At the same time, GEDI reinforced foundational tools and systems to support fiscal planning and sustainability. The removal of Mozambique from FATF grey-list can help mobilise additional investments and public revenues. Together, TEG components remain cost-effective investments for FCDO and Sida, with benefits that will continue to accrue beyond the programme’s closure.

E: RISK

Overview of risk management

The programme operated in a complex and volatile political economy context throughout 2025, requiring a comprehensive and adaptive risk management approach. Risks were monitored through quarterly reviews, leadership consultations, political economy analysis, and sustained engagement with counterparts and other development partners. During the year, the programme tracked 11 risks spanning political, economic, institutional, operational, fiduciary, and reputational dimensions.

Despite this challenging environment – marked by increased security constraints and political pressures, capacity weaknesses, and coordination challenges – no severe risks materialised into delivery failure. This was largely due to the programme’s flexible work‑planning, targeted redeployment of resources, strengthened dialogue with government institutions, and increased reliance on embedded advisers. For example, when institutional traction temporarily weakened around the broader audit‑reform agenda, the programme proactively scaled down engagement and redirected effort towards areas with stronger ownership – such as extractives valuation, transfer‑pricing work and targeted enforcement – which allowed delivery to continue and protected overall output performance, before scaling back up the work on audits.

Risk Trajectories and Mitigation

The political transition period brought unrest, shifting priorities, and increased resistance around sensitive fiscal reforms, which narrowed the space for high‑profile policy change, such as Fiscal Benefits reform or VAT code reform. To mitigate this, the programme adjusted its portfolio (see above) allowing delivery to continue even as political uncertainty persisted. The space for politically difficult policy changes remains constrained but TEG work has created the foundations to quickly seize opportunities when they emerge.

Security risks affected monitoring visits and audit missions in extractive regions due to unrest and protests. The programme mitigated these risks through close coordination with GoM counterparts. sequencing field visits carefully and using remote analysis where necessary.

Institutional and operational risks remained high but stabilising. The creation of a new Directorate for Fiscal and Financial Analysis was an important step toward institutionalising tax policy, though progress was slowed by staffing constraints and weak data‑sharing practices. The programme responded with targeted technical engagement, high‑level briefings, efforts to maintain cross‑institutional dialogue, and (temporarily) adjusting focus between areas.

Fiduciary risks remained minor given the funds are managed by implementers with robust financial and safeguarding systems and FCDO’s strong oversight including through external audits.

Overall, risk exposure remained high but manageable. Pre‑mitigation ratings included 3 severe and 3 major risks, while post‑mitigation ratings reduced these to 0 severe and 1 major, demonstrating the effectiveness of the programme’s adaptive mitigation strategies.

Summary of risks pre-mitigation
Severe	Major	Moderate	Minor
3	3	4	1
Summary of risks post-mitigation
Severe	Major	Moderate	Minor
0	1	4	6

Update on Partnership Principles [1/2 page]

We are not required to report against the Partnership principles under this project. Support is channelled through parallel systems, with no direct financial transfers to government. The 2023 fiduciary risk assessment validated this approach which will remain until programme closure.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Delivery performance continued to be a strong aspect of the programme. A quarterly Performance Assessment Framework (PAF) is in place to evaluate and support improvements in Cowater’s performance, and to inform payment‑by‑results, under which up to 25% of fees are withheld until satisfactory performance is confirmed. The PAF KPIs assess the quality and timeliness of agreed reporting, implementation of deliverables, and accuracy of monthly financial forecasting. Cowater has consistently met all KPIs and maintained a positive, solutions‑oriented approach to feedback, responding promptly to requests for earlier submission of reports, forecasts, or invoices. Cowater also maintains strong financial and administrative systems.

The FCDO TEG team holds regular monthly meetings with the WB GEDI and Cowater TEDI teams, during which risks, progress against outputs, finances, and other relevant themes are discussed. Separately, the FCDO TEG team conducts fortnightly internal cluster meetings to ensure compliance, follow up on AR recommendations, update risks and the Delivery Plan, and track other processes such as contract and agreement amendments.

Regarding audits, the World Bank provides an annual Single Audit Report. For the reporting period, the report for GEDI was made available in September 2025. For TEDI, the Audit process is planned to start mid-April 2026 and will cover the reporting period (Jan-Dec 2025). This delay is due to the contract time extension which took longer than we expected. The last Audit report was finalised in October 2025, with a significant delay and an unqualified opinion was issued. We have initiated discussions with the Partner to ensure the Jan-Dec 2025 Audit process runs smoothly and timely.

TEDI maintains an updated asset registry, which is shared with and reviewed by FCDO on a quarterly basis. A detailed review of TEDI’s asset management procedures and control systems is included within the annual audit objectives, and results will be submitted alongside the audit report. No assets were purchased under the GEDI component.

Commercial performance remained strong, supported by disciplined procurement and consistent application of IMDP and contractual requirements. Competitive tenders, negotiated rates, and framework agreements contributed to reduced input costs, while partnerships with institutions such as ATAF, INAMI, and National Petroleum Institute (INP) minimised logistical duplication and facilitated cost‑sharing for technical missions. These approaches enhanced value for money by reinforcing the link between technical quality and operational efficiency.

Financial performance in 2025 was steady, predictable, and aligned with implementation intensity.

Component	Total / Budget (£)	Budget / Jan–Dec / 2025 (£)	Execution Jan–Dec / 2025 (£)	Cumulat. spend 2019-25 (£)	Exec. Jan-Dec 2025 (%)	Cumul. Execut. (%)
300212-101 (TEDI)	12,000,000	2,887,496	2,376,996	10,566,708	82%	88%
300212-102 (GEDI)	7,000,000	1,000,000	500,000	6,500,000	50%	93%
300212-103 (M&D)	1,000,000	42,400	42,400	208,875	100%	21%

Under the TEDI component, from January to December 2025, total expenditure reached 82% of the annual plan and FCDO completed full utilisation of its £6 million total budget. Expenditure was delivered through timely submission of invoices covering regular monthly claims and PbR instalments, reflecting a consistent pattern throughout the year. The underspend and remaining balance (from Sida funds plus a £120k top-up by FCDO) provide headroom for the approved extension from March to September 2026 and aligns with the programme’s adaptive resource planning.

Under the GEDI component, £1 million was forecast and £500k disbursed for the reporting period. During the drafting phase of this report, a final disbursement was made, completing full disbursement of the programme’s £7 million budget to be spent in the extended period up to December 2026.

The M&D component continues to underspend. For the reporting period, £42.4k was forecast and fully spent; however, as of December 2025, the component retains a balance of £791k (from a total budget of £1 million), of which £200k is committed and £591k remains uncommitted (see section On the M&D Underspend below).

The TEG Programme has an approved total budget of £20 million, comprising £14 million in FCDO funds and £5.87 million in Sida funds. Since the start of the programme (GEDI in December 2018, TEDI in January 2020, and the Monitoring and Evidence component in July 2018), FCDO has disbursed a total of £17,775,583 (£13,208,875.31 from FCDO funds and £4,566,708 from Sida funds).

Overall, financial management demonstrated strong forecasting accuracy and compliance with budget ceilings. Monthly variances remained low, the procurement fund was deployed for high‑impact technical interventions, and disbursement patterns aligned with delivery rhythms across all components. This ensured the programme remained financially robust while responsive to contextual shifts.

#### On the M&D Underspend

The M&D component continues to underspend, with £42.4k spent in the reporting period and an uncommitted balance of £591k as of December 2025, alongside around £200k already committed to ongoing work on illicit finance and asset recovery under the International Centre for Asset Recovery (ICAR) strand of the future public‑financial‑management agenda. This balance reflects an intentional decision to maintain flexibility as the programme enters its final phase rather than a delay in delivery.

Given the transition from TEG to a new UK–Mozambique portfolio framed by the Inclusive Growth Compact, the remaining M&D funds are expected to support continuity of engagement, particularly by providing early analytical, diagnostic and initial delivery capacity for the forthcoming Public Financial Management strategy (within the existing approved budget structure). This approach helps ensure that priority economic‑governance work can continue smoothly after TEDI closes in September 2026 and GEDI in December 2026, avoiding a capability gap and preserving reform momentum. Final decisions on the allocation of the uncommitted balance will be taken during 2026, with forecasts updated accordingly to reflect emerging needs.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring
Monitoring during the review period combined quarterly missions, regular reporting from TEDI and GEDI, and simple on-the-job logs used in audit support. These were complemented by government publications such as the national debt report, the Fiscal Risk Report 2025 and the Medium-term Fiscal Framework, which helped verify system level progress. Monitoring also captured disaggregated information where available – for example, on gender participation in training – supporting the programme’s commitment to Leave No One Behind. Beyond gender, further disaggregation was limited due to gaps in administrative data, though efforts were made to capture available information where possible. Overall, monitoring confirmed strong performance in revenue and macro fiscal areas, while highlighting continued bottlenecks in public investment management and data sharing.

Evidence
Evidence quality improved in valuation, audit and fiscal risk areas during 2025, supported by reference pricing tools, audit logs and better debt data following migration into the national debt management system. These improvements strengthened the reliability of reporting and helped quantify several outcome level results. However, gaps persist in administrative data – particularly Realtime revenue figures and public investment information – and routine data sharing remains inconsistent. These limitations affected the completeness of some indicators and will require continued attention as the programme closes. Plans to improve access through the national financial management authority and the development of a future macro fiscal and PFM data repository are intended to reduce these gaps over time.

Learning
Learning over the past year came from quarterly monitoring missions, regular reporting from TEDI and GEDI, and ongoing discussions with government counterparts. These processes helped identify where programme tools were being used effectively and where institutional or political economy constraints were limiting progress. Three key lessons emerged. 1) First, practical tools embedded in government systems – such as valuation methods, debt management processes and project appraisal frameworks – deliver more sustained results than one-off training (see lesson 2 in section A). 2) Second, reforms that require coordination across ministries are vulnerable during periods of restructuring, as seen in public investment management (lesson 1 in section A). 3) Third, revenue gains depend on completing the full audit cycle, which is why remaining support will focus on closing a small number of high value cases (Lesson 2 in section A). The programme’s learning aim for the final months is to ensure that these tools, methods and insights are fully documented and handed over, so government counterparts - and future UK engagement - can carry the work forward after TEG ends.

Date of last narrative financial report	TEDI – 26/01/2026 / GEDI – 12/02/2026	Date of last audited annual statement	TEDI – 19/09/2025 / GEDI – 16/10/2025

# ANNEX: List of Major recommendations (from last AR Aug 2025)

Recommendation	Owner/Date	Status March 2026
1. TEG should strongly prioritise activities that will be able to evidence outcome results by the end of the project. / TEG should also prioritize strengthening outcome-level reporting in the next period (e.g. additional revenue collected with TEDI support) to ensure robust data is available for the project completion report.	Cowater, WB, backed up by FCDO TEG team (including TIG team leader as appropriate). By March 26.	Addressed / The programme demonstrably shifted to outcome evidencing in 2025. The task for 2026 is to close the loop—i.e., track cash collections post assessment and embed routine publication where feasible (e.g., audited recovery figures).
2. TEG should explore the space for an extension, and as the office is planning its future portfolio, it is important to explore innovative ways to use this pot of funds, together with the M&D component, to prepare for the future.	FCDO TEG team and Cowater. / Seek no-cost extension by end of September 2025.	Addressed / The extension path and forward-looking pilots were put in place in 2025, meeting the recommendation’s intent to prepare for a next phase offer.
3. Develop a strategy to ensure that the disruption in the usage of the Public Investment Management system (allegedly caused by the post-elections turmoil) is restored from the next state budget 2026.	WB. By November when the state budget will be submitted for parliament approval.	Partially addressed / Budget for 2025 was delayed and only approved in April 2025. It basically was unchanged from late 2024. Therefore, no opportunities existed to implement the strategy. / The strategy and tooling for restoration however remain are in place; 2026 budget execution must now be used as a compliance test‑bed, with transparent score‑cards and hard gating on e‑MIP IDs to move this from “partial” towards “achieved”.
4. TEDI to continue to monitor the relationship with MRA in response to past tensions.	Cowater. If difficulties resurface, consider escalations to Minister of Finance and FCDO senior leadership.	Addressed / The recommendation was followed via monitoring, early course correction, and formal channels. The reports do not indicate a need for ministerial level escalation in 2025; if 2026 shows renewed slippage (e.g., audit case closure stalls), escalation pathways remain available.