Programme Completion Review

Title: Support to Ethiopia General Education Quality Improvement Programme for Equity (GEQIP-E)
Final Programme Spend £ (full life):£108.8 million	Review Date:	January 2025
Programme Code: 300236	Start Date: April 2018	End Date: January 2025

Summary of Programme Performance

Year	Apr’19	Aug’2019	Nov’20	Nov’21	Nov’22	Nov’23	Jan 2025
Programme Score	A	A	A	A+	A	A	A
Residual / Exposure Rating	Moderate	Major	Major	Major	Major	Major	Major

DevTracker Link to Business Case (and any addendum):	GEQIP E Business Case / devtracker.fcdo.gov.uk/programme/GB-GOV-1-300236/d
DevTracker Links to all logframes used during programme lifetime:	Most recent Logframe / devtracker.fcdo.gov.uk/programme/GB-GOV-1-300236/documents

Abbreviations
ALP: Accelerated Learning Programme / AMP::Aid Management Platform / AR: Annual Review / BDD: Business Delivery Department / CCA: Continuous Classroom Assessment / CPD::ContinuousProfessional Development / CSSF: Conflict, Stability and Security Fund / D4D: Data for Delivery / DDA: Due Diligence Assessment / DLR: Disbursement Linked Result / EDT: Education Development Trust / EGRA: Early Grade Reading Assessment / CSSF: Conflict, Stability and Security Fund / D4D: Data for Delivery / DDA: Due Diligence Assessment / DLR: Disbursement Linked Result / EDT: Education Development Trust / EGRA: Early Grade Reading Assessment / ESDP VI: Education Sector Development Plan VI / ESS: Ethiopian Statistics Services / HCDT: Humanitarian and Conflict Development Team	IDA: International Development Association / IERCs: Inclusive Education Resource Centres / IFR: Interim Financial Report / LMIC: Low and Middle-Income Country / MDTF: Multi Donor Trust Fund / M&E: Monitoring and Evaluation / MoE: Ministry of Education / MoF: Ministry of Finance / NSLT: National School Leadership Training / OCR: Outcome Confidence Rating / PAD: Programme Appraisal Document / PCR: Programme Completion Review / PF: Prosperity Fund / P4R: Programme for Results / PrOF: Programme Operating Framework / PRO: Programme Responsible Owner / REB: Regional Education Bureau / SAHE: Safeguarding Against Harmful Effects / SIP: School Improvement Plans / SRO: Senior Responsible Owner / TARGET: Technical Assistance to Reinforce GEQIP-E in Ethiopia / TPLF: Tigrayan People Liberation Front / TREE: Transforming Education in Ethiopia / VfM: Value for Money

Summary and Overview (1-2 pages)

Description of the programme and what it has achieved [1/2 page]
The GEQIP-E was the third iteration of a package of reforms to enhance quality, access, and efficiency of education in Ethiopia. The programme provided critical support to Ethiopia’s Education Sector Development Plan, ESDP VI (2020- 2025). The Programme comprised two components 1) Financial Aid (FA) via a Multi Donor Trust Fund (MDTF) Programme for Results (P4R) run by the World Bank (including funds from the UK, Norway, Finland, UNICEF and Global Partnership for Education (GPE)) and 2) Technical Assistance (TA) - to Reinforce GEQIP-E in Ethiopia (TARGET), entirely funded by the FCDO. The original timeframe for FCDO’s Business Case was 2017 – 2022.
The intended impact of the programme was to improve learning for all (Quality and Equity) and Increase Efficiency of the Education system to develop the human capital needed for Ethiopia's transition to a Lower Middle-income country (LMIC) status. The programme had five outcomes:
- Improved learning outcomes
- Improved teaching practice and leadership
- Increased participation of disadvantaged learners in education
- Increased efficiency and performance of the Education System
- Improved sustainability of Education Financing
The GEQIP-E was designed in a very different context to the one Ethiopia has faced since 2020. The Covid-19 pandemic, severe climate events and the conflict within Ethiopia, has had detrimental effects for the delivery of government business across sectors, with education significantly affected. Certain regions within the country (primarily Oromiya and Amhara) can now be considered emergency contexts due to conflict. Although a peace agreement with Tigrayan People Liberation Front (TPLF) was signed in 2023, the region remains unstable and in need of substantial assistance to recover from three years of conflict.
Partly because of these shocks, GEQIP-E has been extended twice. A no cost extension was approved in 2021 to catch up on lost time due to school closures during the COVID-19 pandemic. The programme was extended again in 2023 to allow sufficient time to disburse outstanding Payment for Results (P4R) payment for already achieved Disbursement Linked Indicators, to catch up on interventions delayed due to conflict, Covid 19 etc., and to allow time to design a follow-on programme. The final end date was January 2025. Even though the programme was extended, the endline targets for the Financial Aid remained largely unchanged from 2023. As a result, programme support for school grants ceased after 2022.
The World Bank will close their project in April 2025. Our funding trhrough the MDTF has already been fully disbursed and accounted for. The World Bank rated the programme as moderately satisfactory (equivalent to FCDO overall meeting expectations) in its June 2024 Aide Memoire. This reflected challenges due to the prolonged conflict in certain regions, which was delaying some Program activities, especially those related to classroom construction and enhancing school access in refugee-hosting areas, specifically in the Amhara region. These issues have been addressed and GEQIP-E is now closed. The final report on the project’s performance is expected later in 2025. The project received additional funding from IDA to support refugee education. GPE also provided additional financing to scale up Inclusive Education Resource Centres (IERCs).
The World Bank executed its fund management duties satisfactorily including facilitating biannual and a Mid Term Review Mission, and quarterly steering committee meetings. An action plan that included measures to improve programme performance measures (fiduciary, financial management, staffing) was designed, executed, and monitored on regular basis.
FCDO’s TA contract with Education Development Trust (EDT) was also extended in 2023 with an additional £1.3 million up to March 2024. This enabled EDT to scale-up interventions from previous years’ activities and respond in conflict affected areas. The focus was primarily on delivering additional activities under three of the programme’s outputs:
- Output 3: Improved skills and competencies of School Leaders and Teachers
- Output 5: Improved systems and capacity for planning, policy formulation and reform (Improved system of data collection, analysis, teacher preparation, delivering programs) established
- Output 6: Sector Financing and Programme Management/ Monitoring of GEQIP E programme strengthened.
Payments to Education Development Trust (EDT) were based on contracts, with disbursements linked to timely submission and satisfactory performance against key performance indicators respectively. The programme team had regularly risk discussions with EDT to update the delivery chain risk mapping. There was a regular asset register, and proper asset disposal processes undertake as per the FCDO asset disposal guideline.
Despite a challenging operating environment, overall GEQIP-E is judged to have met expectations. It has performed well against most of its outcome targets (see section B below) and has contributed to progress the desired impact of improving learning for all and system efficiency. Table 1 below summarises progress against the output targets where the programme has met or exceeded expectations:
Table 1: Summary of GEQIP-E output performance
Output	Targets (end of project)	Achievement
1 Improved performance and accountability of schools and communities	1.1 85.5% of schools rewarded on basis of performance on timely basis / 1.2 68% of schools received school grants by 30 Dec. 2022 / 1.3 Online textbook distribution and inventory management system piloted in 2022. / 1.4 75% of schools display their report cards	Overall: Moderately exceeded / 1.1 Moderately exceeded:91% / 1.2 Substantially exceeded: 91% but only in emerging regions / 1.3 Met expectations / 1.4 Moderately exceeded: 83.8%
2 Quality Enhancement and Assurance Programme (QEAP) for pre-primary education to improve children's readiness for learning put in place	2.1 35% of Level 1 of 0-classes in phase 1 schools upgraded to higher level.	Overall: Substantially exceeded: / 2.1 67.4% upgraded from Level 1 and there is evidence from the comprehensive exit evaluation of GEQIP-E that the investment in early years is having beneficial a beneficial impact on reading skills in grade 1.
3 Improved skills and competencies of School Leaders and Teachers	3.1 4700 school leaders & supervisors (at least 30% female) trained and received certificates . / 3.2 TARGET's NSLT training and accreditation Model adopted by the MoE and partners Universities / 3.3 School leadership continuous Professional Development (CPD)programme rolled out in full scale to reach 9000 schools and 125,000 school leaders and teachers. / 3.4 90% of phase 1 schools visited by cluster supervisors and key teachers at least three times a year for school based continuous teacher professional development. / 3.5 All [the mother-tongue,] Maths and Science teacher in the 18,000 schools received training through cluster supervisors and key teachers	Overall: Met expectations / 3.1 Met expectations – 4,656 trained (2024) / 3.2This indicator was dropped in 2023 as accreditation was deemed out of scope of the programme / 3.3 Moderately not met: 7,978 schools reached with school leadership training / 3.4 Met expecations : 96% target schools were visited three times by key teachers and cluster supervisors. / 3.5 Met expectations : 94% of the targeted maths and science teachers received training through cluster supervisors and key teachers
4. Reduced barriers for disadvantaged learners to progress in education and improve career opportunities	4.1 70% of schools develop and implement gender sensitive SIPs with community participation in GEQIP E and TA target schools / 4.2 70% of schools delivering life skills training and clubs operating in line with girl's club guidelines in GEQIP E Target Schools (Primary schools with grade 5 and higher in Afar, Beneshangul Gumuz and Somali) and TA target schools / 4.3 800 Inclusive Education Resource Centers (IERCs) Equipped with inclusvie Education Resources and adequately trained staff and operating	Overall: Met expectations / 4.1 Met expectation: 72.4% of the schools are functioning according to the guideline. / 4.2 Met Expectations: 73.4% schools with functional gender clubs / 4.3 Substantially exceeded: 1400 IERCs established (600 of them are through the GPE Additional Financing)
5. Improved systems and capacity for planning, policy formulation and reform (Improved system of data collection, analysis, teacher preparation, delivering programs) established	5.1 EGRA report of raw student test scores available by 30 June 2023 / 5.2 Demand driven research/ data collection (12 in number) conducted. / 5.3 Data for delivery systems established and utilised / 5.4 GEQIP E outcome led planning and implementation processes embedded across the MoE and REBs. / 5.5 Conflict affected areas received support on Adapted Curriculum and Accelerated Learning Programme (ALP) planning and implementation	Overall: met expectations / 5.1 Met expectations: EGRA 2023 available / 5.2 Moderately exceeded: 14 in total / 5.3 Met expectations / 5.4 Moderately not met: 85% of REB respondents reported improvements in outcome based planning / 5.6 Met expectations: All targeted REBS (Afar, Amhara and Tigray) had ALP plans and 75% had received training
6. Sector Financing and Programme Management/ Monitoring of GEQIP E programme strengthened.	6.1 Education Financing Strategy validated and implementation agreed / 6.2 GEQIP E successor programme informed by lessons and best practices of TARGET / 6.3 Lessons and best practices of TARGET shared with stakeholders / 6.4 An Endline review of TARGET completed	Overall: Met expectations / 6.1 Met expectations - finalised in 2023 / 6.2 Met expectations: UK’s new education programme – TREE – designed and approved in late 2024 / 6.3 Met expectations: Lessons learned disseminated / 6.4 Met expectations: Endline submitted in April 2024

Major lessons learned, evidence generated and recommendations [1/2 page]
The findings and recommendations for the FCDO-Ethiopia education team are summarised in the table below. These are being fed into design and implementation of FCDO’s new education programme – Transforming Education in Ethiopia (TREE):
Table 2: Summary of findings and recommendations
No	Issue	Findings and recommendations
1	Financing	As noted in the 2023 Annual Review, the Multi Donor Trust Fund has helped to crowd funding into the sector. . However, overall funding to the education sector has been constrained by the fiscal situation in Ethiopia. In the next phase of its programming FCDO should continue to advocate for sufficient funding to general education from i) domestic resources -in terms of an increase in the share of the education budget allocated to general education and ii) from IDA where we are asking whether the remaining $350 million of funding to ETOL can be allocated from IDA21.
2	Partner coordination	While the MDTF was effective at bringing donors together, there is a recognition that the operating environment in Ethiopia means that there is a need for more flexible delivery options. Consequently, the GPE sector grant is now being implemented by UNICEF. FCDO should support MoE to strengthen its coordination of partners and funding streams to avoid duplication of effort.
3	Conflict and crises	Conflict and crises have had a major impact on GEQIP-E programme delivery. Over 8.8 million children are out of school primarily due to conflict induced emergencies and climate-related shocks and only around 10% of these children are currently accessing Education in Emergency (EiE) services. FCDO should keep the balance of investments in the TREE programme under review by i) working with the World Bank and GoE to mainstream the response to conflict and crises into ETOL and ii) including a focus on the response to conflict and crisis in the next phase of our Technical Assistance programme
4	Learning levels	Despite substantial progress in expanding access to education, significant challenges persist in achieving quality learning outcomes. The 2023 National Learning Assessment shows that at grade 4, students were able to answer correctly approximately 31 percent of the questions in English and 44 percent in Maths, with male students slightly outperforming female students. FCDO should continue to prioritise evidence-based approaches to improving foundational learning in the next phase of its programming
5	Strengthened accountability	GEQIP-E has had a positive impact on improving the efficiency with which inputs to schools such as textbooks and school grants are used through publishing school improvement plans in schools and improving how the distribution of textbooks is monitored at regional level. FCDO should continue to support strengthened accountability mechanisms, such as strengthening community engagement in schools and improving systems for monitoring the distribution textbooks and other key inputs down to school level to improve the efficient use of inputs into the system and help maximise value for money.
6	School inputs	School grants are critical to the operation of schools but are a core recurrent cost which should be funded from government own resources. FCDO should sustain funding for targeted interventions that provide additional support to schools recovering from conflict and crises, support refugee inclusion in the education system, or narrow the gap in achievement between emerging and other regions.
7	School leadership	School leadership and CPD have been identified as a critical system building block in the new World Bank programme – Ethiopia Education Transformation Operation for Learning (ETOL) and in the Ethiopia Education Transformation Plan. FCDO should leverage the learning from its programming to support government to roll out of high-quality school leadership training and continuous professional development for teachers nationally
8	Equity	Support for girls and disability are two areas that are resource intensive. There is a risk of having too many indicators related to equity that the programme thinly spreads resources, which will increase reach but possible reduce sustainable impact. FCDO should clearly target its equity focused interventions and maximise scarce resources by working cross sectorally where feasible.
9	Data and planning	While there are positive developments in data processing and planning, ongoing challenges need continued focus. There is significant variation in the capacity and needs in different regions. The emerging regions and those affected by conflict need adaptation. Future UK support should build on the data and delivery support it has provided to date and facilitate scale up in the most underserved regions.
10	Evaluation	The TARGET endline evaluation notes the lack of baseline studies which complicated efforts to measure the impact of interventions at school level. Provision for the generation of baseline studies should be a precondition for any programme to be approved by the MoE. FCDO should ensure that the M&E supplier for TREE is contracted as soon as practical after the Technical Assistance supplier to put in place baseline studies.
11	VfM	There was a lack of quantitative information on vfm performance in GEQIP E. FCDO should establish a vfm baseline for the new programme and ensure that key vfm metrics are tracked,

 How this report was conducted [1 paragraph]
This PCR scores the programme’s lifetime performance based on triangulated evidence extracted from a broad range of sources, including a thorough review of previous Annual Reviews (with the 2023 Annual Review providing important endline information for some targets), Ministry of Education (MoE) GEQIP-E programme 2023/24 annual implementation report, the TARGET Endline Evaluation, TARGET quarterly progress reports, TARGET Verification Report (January 2024), the GEQIP-E Comprehensive Exit Evaluation (July 2024), World Bank Aide Memoire (issued June 2024), The Exit Evaluation collected GEQIP-E programme performance data collected against impact, outcome, and output indicators from all regions in Ethiopia. The review was led by a Senior Education Adviser who has just joined the programme so was well-placed to provide an independent view.

Actions following approval of this report [1-2 paragraphs]
GEQIP-E programme has been implemented according to the PrOF rule 29. The TA has undertaken an inventory of all assets and physical asset though out the life of the programme. The programme team conducted physical asset spot checks during the programme implementation. An asset disposal recommendation was submitted and approved by the Development Programme during programme closure. The decision included maintaining high value assets, particularly vehicles to use for the successor TA programme. The lead implementing partner, EDT, also returned cost of damaged assets to central contingency budget.
An independent audit focused on the TA component was conducted 22nd Jan 2024 – 30th April 2024, Ineligible expenditures just over £2,000 identified by the audit were refunded to FCDO in October 2024. Furthermore, World Bank Interim Financial Reports (IFR), independent audit and verification reports were continuously reviewed to determine whether funds channelled through the MDTF were utilised for intended purpose. The programme team has gathered all the necessary information from WB and TA to confirm that no funds are owed and no further transactions will be required.

## B: Theory of Change and Outcome Assessment (1-2 pages)

	Starting point	Final result
Budget	£110,000,000.00	£108,744,87.00
Timeframe	July 2018 – July 2022	July 2018 – January 2025
Outcomes	1) Improved learning outcomes / Target: 25% of students in Grade 2 can read at functional fluency level in phase 1 (FA) and TA target schools / Target: % of students in Grade 8 who perform at basic proficiency level or above in English (55%) and Maths (58%) in phase 1 (FA) and TA target schools / Improved teaching practice and leadership / Target: Aggregate inspection scores of in quality of teaching, lesson planning, teaching methods, assessment, and inclusion in phase 1 (FA) and TA target schools (70%) / Increased participation of disadvantaged learners in Education / 3.1 Target: Girls to boys enrolment ratio in Grade 8 in Afar, Somali and B.G Regions (71%) / Target: 49,000 children with disabilities enrolled in cluster schools benefiting from services resourced and staffed Inclusive Education Resource Centres (IERCs). / Target: Increased Gross Enrolment Ratio (Gr. 1-8) in Afar, Somali and Beneshangul Regions (96%) / Improved efficiency and performance of the education system / Target: Grade 1 to Grade 2 Progression rate (the number of Grade 2 enrolees to the number of Grade 1 enrolees (80%) / Target: School Inspection level of Phase 1 (FA) and TA Target Schools (least performing regions and woredas including in emerging regions) – 15% (primary) and 8% (secondary) / Target: Effective implementation of delivery plans and realization of targets set for delivery program in the 9 regions and 2 city administrations[1]. / Improved financial sustainability of the education system / Target: Government budget allocation for education recurrent expenditure (£225 million) / Target: Increased spending on general education (43%)	1.1 Not achieved: Overall the percentage of students at functional level in grade 2 stands at 18.3% in 2023. / 1.2 Achieved: Phase 1 schools have achieved an average 85% (88% male and 84% female) for English and 72% 74% male and 69% female) for Maths. / 2.1 Achieved: - A composite score of teachers in Grade 7 & 8 Mathematics, English and Mother Tongue stands at 70.29% / 3.1 Achieved: - 71.9% / 3.2 Achieved: - 91,012 student enrolled / 3.3 Not achieved: Good progress in Beneshangul Gumuz, (115.9%), but rates remain low in Afar and Somali regions, with 69.0% and 83.9% respectively). / 4.1 Achieved: 88% in 2023 although the latest data (Nov. 2024), shows a downward trend, standing at (78.7%). / 4.2 Achieved – 12.6% primary and 7.2% secondary / 4.3 Achieved: All TARGET supported regions have outcome-based delivery plans, instil delivery routine and a system to monitor delivery of results (the D4D system). / 5.1 and 5.2 No data : - We do not get a breakdown of general education spending at regional level. The Federal budget mainly captures secondary education. In 2024/25 the federal budget for general education increased by 43% from 56 billion birr to 80 billion birr.
[1] Tigray is replaced by Sidama region in this milestone and it measures changes in all regions except Tigray).

Overall assessment of programme outcomes, sustainability and VfM

As noted above the programme was extended twice by a total of more than two years. These were no cost extensions to manage slow disbursement largely because of Covid-19, and the conflicts in Tigray, Amhara and Oromia. Despite these operational challenges, the outcomes remained unchanged and as summarised above have been achieved.

The impact of the programme was measured by a combination of completion rates and student performance in National Learning Assessments. Progress against the impact indicators is summarised in table 3 below. There has been relatively satisfactory progress with respect to completion rates in primary schools, but overall learning outcomes have declined slightly (although most recent available data is for 2023). However, note the upward trend in GEQIP-E Phase 1 schools from a 2022 assessment which is encouraging. There is also some evidence that the investment in pre-primary education (O classes) may be beginning to have an impact on children’s early grade reading skills.

Table 3: Progress against impact indicators
Impact: Improved Learning for all (Quality and Equity) and Increased Efficiency of the Education system
Indicator	2017/18 Baseline	TARGET	Achieved (2023/24)
Completion rates in primary education (Grade 4, 8) / Aggregated scores of Grades 4, 8, 10 and 12 NLA examination results	Grade 4: 53% (54%M, 53%F), Grade 8: 54% (56%M, 52%F), / Grade 4: 58% (58%M, 58%F) Grade 8: 61% (61%M, 61%F	Grade 4: 58% (58M, 58%F) / Grade 8: 61% (61%M. 61%F)	Completion rates – Grade 6 / Female – 67.1% / Male – 67.9% / Completion rates – grade 8 / Female – 61.8% / Male – 58.8% / No data available for grade 4. Following the education system reform, grade 6 has become a point of measurement.
	Grade 4 - 44.74% (46.27%M, 43.24%F); / Grade 8 - 41.14%; / Grade. 10 - 40.64% (42.68%M, 38.35%F); / Grade. 12 - 45.52% (49.13%M, 40.53%F)	Grade 4- 43.71% (45.12M%, 42.14%F) Grade 8- 41.17% (43.08%M, 39.12%F); Grade 10 - 50% (50%M, 50%F); Grade 12 - 55% (55%M, 55%F)	Grade 4- 39.7 (40.1M, 38.00F) / Grade 8- 36.2 (37.5M, 34.8F). / No data for grade 10& 12

The picture on programme sustainability is mixed with some evidence from the comprehensive evaluation that the programme has built capacity in the system to deliver. For example, different regions have allocated and expanded budgets to run programmes for early years education (known as O-class) and continued to run other activities even in the absence of school grants in 2024. Others were less optimistic however, that requisite skills had been built. Stakeholders suggested several sustainability strategies for future programming, including anchoring donor support more firmly in Ethiopia’s Education Transformation Program (EETP) and developing a domestic resource mobilization strategy to generate more sustainable income and resources.
Overall, despite numerous challenges in the operating environment, the programme delivered good value for money. It contributed to improved education for 27 million children enrolled in public primary and secondary schools (including ‘0’ class) with a specific focus on the most marginalised, including children with disabilities. FCDO’s financing helped to support GoE to improve access and learning for over one million children at an average per capita cost of £120 over the life of the programme (equivalent to approximately £30/beneficiary/annum). By pooling funds with other donors, the programme helped to better coordinate and target support. There are four major threats to vfm for general education support going forward which will need to be carefully managed (see recommendations):
- Learning levels remain stubbornly low which risks undermining the overall cost effectiveness of UK education investments
- Government funding to general education has not increased as a proportion of overall education spending which could potentially affect the impact of donor efforts to support the Ministry of education to improve quality and access
- There is some fragmentation of donor funding to the sector which risks creating duplication and inefficiencies
- Conflict continues to affect the flow of funds through government to some regions which means that our funding does not reach some of the most marginalised.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators. [1/2 – 1 page]
The Theory of Change (ToC) remained valid, despite the changing context. Some changes were made in 2023 to reflect the changing context (see 2023 AR) but impact and outcomes remained unchanged. Overall, many of these changes have been in response to dynamics outside of the control of the programme (predominantly the lasting impact of Covid-19, the conflict and its effect on implementation of planned activities). While the assumptions from the ToC have also remained relevant, disparity between regions as regards equity of outputs and outcomes is noticeable. No explicit conflict assessment, or assumptions of political stability, were included to underpin the original ToC; as the FCDO in Ethiopia moves into programme design for its next bilateral education intervention, the inclusion of conflict analysis based on evidence will be important.

Figure 1: GEQIP_E ToC

## C: Detailed Output Assessment [aim for max. 1 page per output. Repeat for each output]

Output Number and Title	Output 1: Improving performance and accountability of schools and communities
Output Score	A+
Impact weighting (%)	30%		Impact weighting revised since last AR?	No

Output Indicator		Starting Target	Final Logframe Target	Final Result Achieved
1.1 Financial awards to best performing schools disbursed on timely basis (by 31st of March every year) for schools improving on G1/G2 enrolment and G5 Survival rates		85.5%	85.5%	Moderately exceeded: / 92.04% received PBSA before March 31st, 2022.
1.2 Timely availability of school grants including in emerging regions to improve learning conditions in line with SIP standards		68% of schools receive grants by 30 Dec. 2021	A) 68% of schools in emerging regions received school grants by 30 Dec. 2022 / B) At least 68% of schools in all regions received grants and utilized effectively (in line with school grant guidelines) through out project implementation time line.	Overall: moderately exceeded / A) Substantially exceeded: 93.7% of schools in emerging regions received SG by 30 Dec 2023 / B) Met expectations: National school grant distribution ceased in 2022 – 2023 Annual Review reports the target was achieved
1.3 Percentage of Woreda Centers and schools receiving textbooks including the emerging regions		Online textbook distribution and inventory management system piloted in 2022.	Online textbook distribution and inventory management system piloted in 2023.	Met Expectations (although a year later than originally planned)
1.4 % of school report cards publicly displayed in PTA/PSTA and community meetings in the phase 1 (FA) and TA target schools		75% of schools display their report cards	75% of schools display their report cards	Moderately exceeded: 78.6% of schools publicly display school report cards

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score. [1/2 page]

Output 1.1 Financial awards to best performing schools There were delays in implementation at the outset of the programme, but these were subsequently ironed out. The GEQIP-E comprehensive evaluation reports that this indicator was fully achieved at over 90%. The comprehensive evaluation of GEQIP-E further concludes that performance-based payments along with public display of school report cards (see below) made a significant contribution to improve the internal efficacy result area in sampled schools across the country. The payments were discontinued after 2022 because of lack of available funds in the programme.

Output 1,2 Timely availability of school grants, including in emerging regions Performance against this output has consistently exceeded expectations showing the importance the government attaches to school grants as a means to fund operational costs and improve learning conditions. Results from a survey conducted as part of the comprehensive evaluation of GEQIP-E suggest that school grants had positive benefits on teacher professional development but views were mixed on whether they have helped to support children with special needs. It was agreed with MoE to provide additional school grant financing to refugee hosting primary and secondary schools. All the Disbursement Linked Results related to this support were reported to have been achieved by March 2024 in the June 2024 verification report to the World Bank.

Output 1.3 % of woreda centres receiving textbooks including in emerging regions. The indicator was changed in 2022 to focus on woredas having an online textbook and inventory management system. This was to ensure efficient distribution of textbooks to schools as well as on utilization of textbooks in the teaching learning process. The World Bank GEQIP-E Aide Memoire (June 2024) reports that the Disbursement Linked Result (DLR) to pilot an online textbook distribution and inventory management system piloted by June 30, 2023 was fully achieved. Textbook availability has reportedly improved over the life of the programme from a baseline of 58% to over 70%. The increase is higher for rural areas, where the share of Grade 1 children with access to textbooks increased by 18 percentage points, from 64% to 82%, compared to an increase of 4 percentage points, from 83% to 87% for urban Grade 1 student. This is extremely encouraging.

Output 1.4 % of school report cards publicly displayed: To ensure transparency of how school grants are being spent, each school is required to display a School Report Card (SRC), in a visible location to the public. Overall, against a target of 75%, the results of aggregated data from the regions (reported in MoE’s 2023/24 Annual GEQIP-E report), gives a performance of 78.6 % of all schools in Ethiopia, school report cards (SRCs) displayed in PTA/PSTA and community meetings in the phase 1 supported schools.

Figure 2: The number of Sampled Schools that Displayed School Report Card (SRC) In Five Progressive Years (2019-2023)

Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]

School grants are critical to the operation of schools but are a core recurrent cost which should be funded from government own resources. FCDO should only fund school grants for targeted interventions such as to provide additional support to schools recovering from conflict and crises, promote interventions to advance gender equality, leverage resources to support refugee inclusion in the education system, or narrow the gap in achievement between emerging and other regions.

GEQIP-E has had a positive impact on improving the efficiency with which inputs to schools such as textbooks and school grants are used through publishing school improvement plans in schools and improving how the distribution of textbooks is monitored at regional level. FCDO should continue to support strengthened accountability mechanisms to improve the efficient use of school inputs.
While the MDTF was effective at bringing donors together, there is a recognition that the operating environment in Ethiopia means that there is a need for more flexible delivery options. Consequently, the GPE sector grant is now being implemented by UNICEF. FCDO should support MoE to strengthen its coordination of partners and funding streams to avoid duplication of effort and strengthen accountability and the programme funded senior education advisor role working together with the lead education advisor will among others help to make this happen.

Output Number and Title	Output 2: Quality Enhancement and Assurance Programme (QEAP) for pre-primary education to improve children's readiness for learning put in place
Output Score	A++
Impact weighting (%)	10%		Impact weighting revised since last AR?	No

Output Indicator		Starting Target	Final Logframe Target	Final Result Achieved
2.1 National standards for 0 class school inspection developed and implemented in phase 1 schools		35% of Level 1 of 0-classes in phase 1 schools upgraded to higher level.	35% of Level 1 of 0-classes in phase 1 schools upgraded to higher level.	Substantially exceeded / 67.36% schools upgraded from level 1 to level 2 (this is to be further confirmed)
2.2 Quality Enhancement packages developed and ToT completed, inspection framework for 0 class developed and approved			This indicator was dropped in 2021.	NA

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score. [1/2 page]
2.1 National Standards for 0 class[2] inspection: This indicator has consistently exceeded expectations. The upgrading of O-classes from Level 1 to Level 2 was achieved. The GEQIP-E Theory of change proposes that provision of incentives for: enhancing the quality of O-Classes strengthening school-based monitoring of student progression through the primary grades; and outreach to parents and communities on the importance of age-appropriate enrolment and regular attendance in the early grades will improve Grade 2 to Grade 1 enrolment ratio; and Grade 5 survival rates. The Comprehensive evaluation reports that the provision of better-quality O-classes had a positive impact on the Grade 2 to Grade 1 enrolment ratio. There was also qualitative evidence from the survey of teachers and headteachers that O-classes have contributed to improved early literacy.
[2] Refers to pre-primary education provision in formal schools
2.2 Training of O-class teachers This indicator was reported on in the 2020 Annual Review. Intervention related to this output are one off and cannot be rolled over to subsequent years hence dropped from the programme logframe. This coincided with a shift in emphasis from providing inputs to a greater focus on enhancing the quality of provision through the inspection process. However, due to the Covid-19 pandemic Training of Trainers was substantially offtrack.
Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]
There is evidence that the O-class programme has had positive impacts both on over-enrolment to grade 1 and on the development of early literacy skills[3]. Given that O-classes have only been established in around 50% of primary schools, and the continued challenges with improving foundational reading levels, FCDO should continue to work with MoE to scale up the provision of quality early years education in Ethiopia.
[3] DLR 5b.4 was improved child development and learning as measured by the percentage of O-class students which correctly respond to MELQO pre literacy test items. Performance was 51.4% in 2023/24 compared to 44% in 2021/22 – a 7% improvement against a target of 5%.

Output Number and Title	Output 3: Improved skills and competencies of School Leaders and Teachers
Output Score	A
Impact weighting (%)	30%		Impact weighting revised since last AR?	No

Output Indicator		Starting Target	Final Logframe Target	Final Result Achieved
3.1 Support establishment of sustainable school leadership reform through re-designing and creating accreditation systems for the pre-service education leadership training.		A) 4700 school leader & supervisors (at least 30% female) trained and received certificates . / B) TARGET's NSLT training and accreditation Model adopted by the MoE and partners Universities	A) 4700 school leader & supervisors (at least 30% female) trained and received certificates . / B) TARGET's NSLT training and accreditation Model adopted by the MoE and partners Universities	Met expectations / 4,636 school leaders trained / Met expectations / Agreed that adoption by GoE out of scope
3,2 Inservice (CPD based) School Leadership programme focusing on poor performing schools (complementing related efforts of GoE) designed and implemented.		Programme rolled out in full scale to reach 9000 schools and 125,000 school leaders and teachers.	Programme rolled out in full scale to reach 9000 schools and 125,000 school leaders and teachers.	Moderately not met expectations / Rolled out to 7,978 schools
3.3 A new school based Continuous Professional Development (CPD) programme for Mother Tongue, Maths and Science Teachers validated and implemented.		A) 90% of phase 1 schools visited by cluster supervisors and key teachers at least three times a year for school based continuous teacher professional development. / B) All the Mother tongue, Maths and Science teacher in the 18,000 schools received training through cluster supervisors and key teachers	A) 90% of phase 1 schools visited by cluster supervisors and key teachers at least three times a year for school based continuous teacher professional development. / B) All the Mother tongue, Maths and Science teacher in the 18,000 schools received training through cluster supervisors and key teachers	Met expectations / A) Moderately exceeded: 96% / B) Moderately not met:16,861 (94% of target)

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score. [1/2 page]
3.1 Support sustainable school leadership reform: This output was delivered by our TA (TARGET) programme provider, EDT, in partnership with MoE. The TA was procured in 2019 so the focus in 2018 was working with the Ministry to prepare the ground for the programme. Targets have mostly been met or exceeded for the school leadership reform efforts since the provider started work. It has successfully moved from piloting to scaling over the life of the programme. As of 2024, 4,655 school leaders had been trained under the programme. The TARGET verification report notes that TARGET was not in a position to make unilateral decisions regarding the accreditation and subsequent scale-up or institutionalisation of national school leadership training. Its role has been to demonstrate that this innovation is effective for Ethiopia and to foster an understanding that accreditation is essential. The Ministry has not yet adopted the model, possibly because of scepticism among educational officials, and a general weariness in the education sector due to numerous reforms proposed and partially implemented over recent decades. However, school leadership has become part of the new nationwide programme, EETP and planned to be upscaled through other donors and GoE’s own funding. EDT’s evaluation also revealed the MoE already invested a 10million ETB (GBP153,800) and doubled the initially planned number of trainees from 1,500 to 3,000. This was due to the NSLT pilot demonstrated impressive results.
3.2 Inservice (CPD based) School Leadership programme focusing on poor performing schools. The major objectives were to improve the performance of 9000 low-performing schools from the existing levels at least one level up as per the inspection standard categorisation of the MoE. SL-CPD model for poorly performing schools was designed and the requirement was for the redesigned model be piloted to reach 9000 schools. The programme started with 700 schools, and following successful completion of the pilot, it scaled up to 7,278 schools all over the country, bringing the overall number of schools to the 7,978, performed a bit lower that the target. TARGET also successfully delivered the scale-up of the National School Leadership Training (NSLT), with training over the last year of reporting focusing on delivering face-to-face training on the first three modules of the four-module programme and the peer and self-learning component of the training.
3.3 New school based Continuing Professional Development programme: the focus was on improving student learning outcomes, with a focus on early grade reading and instruction of mother tongue, English and mathematics for grade 7&8. The support system is being anchored by subject-specific key teachers and supervisors, and headteachers who provide regular support and guidance to classroom teachers. According to the Continuous Classroom Assessment (CCA) approach, provision of Trainer Of Trainers instruction for key teachers and cluster supervisors is then followed by training for specific subject teachers. The GEQIP-E Comprehensive evaluation reports that 96% of phase 1 schools were visited at least three times by cluster supervisors and key teachers. It also reports that 16,861 schools were reached with cascade training (94% of the target of 18,000).

Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]
School leadership and CPD have been identified as a critical system building block in the new World Bank programme – Ethiopia Education Transformation Operation for Learning (ETOL). FCDO should leverage the learning from its programming to support government to roll out of high-quality school leadership training and continuous professional development for teachers nationally

Output Number and Title	Output 4: Reduced barriers for disadvantaged learners to progress in education and improve career opportunities
Output Score	A
Impact weighting (%)	10%		Impact weighting revised since last AR?	No

Output Indicator		Starting Target	Final Logframe Target	Final Result Achieved
4.1 Development and implementation of gender sensitive SIPs with community participation in GEQIP E and TA target schools		70% of schools integrate gender in SIP.	70% of schools integrate gender in SIP.	Met expectations / 2,255 (72.4%) of the target have functional gender clubs
4.2 % of schools delivering life skills training and clubs operating in line with girl's club guidelines in GEQIP E Target Schools (Primary schools with grade 5 and higher in Afar, Beneshangul Gumuz and Somali) and TA target schools		70% of schools delivering life skills training and club	70%	Met expectations / 72.4% of the 2,255 grade 5 to schools conducted life skills training through gender club leaders
4.3 Number of Inclusive Education Resource Centers (IERCs) Equipped with inclusive Education Resources and adequately trained staff and operating		800 Inclusive Education Resource Centres (IERCs)	800	Substantially exceeded / 1400 IERCs established with 600 of them through GPE additional financing

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score. [1/2 page]
4.1 Development and implementation of gender sensitive SIPs School Improvement Plans are intended to guide schools on how to spend their school grants. Gender sensitivity in these plans is designed to promote greater equity in terms of access and learning. In 2019, the school improvement framework was revised to promote gender equity issues in school improvement planning (enhance girls educational access and learning). This has helped schools to analyse and compare their own progress and challenges to effectively implement gender mainstreaming in teaching and learning. The target has been slightly exceeded. However, an FCDO supported research report shows lack of resources to fully implement gender sensitive school improvement plans and sufficiently tackle factors hindering their educational access and learning.
4.2 Percentage of schools delivering life skills training and clubs Clubs are primarily intended to create safe spaces for girls in Grades 5-8, which is the stage where girls are most likely to drop out of school. The World Bank’s June 2024 Aide Memoire reports that 72.4% (2,225 out of 3,073) of primary schools in Afar-75.8%, Somali-70.5% and Benishangul-Gumuz-73.4% have functioning Girls’ Clubs. Furthermore, the GEQIP-E comprehensive evaluation found that the majority of the sample of gender clubs visited in Afar, Benishangul-Gumuz and Somali Regions were operational according to the improved gender clubs guidelines. Specifically, Afar and Somali Regions showed 100% operational clubs, and Benishangul-Gumuz Region had a high operational rate with 92.31% clubs operational. However, study reports show lack of human and financial resources is one of the factors hindering the full functions of the gender clubs.
4.3 Number of Inclusive Education Resource Centres (IERCs) According to the World Bank’s June 2024 Aide Memoire 1,400 Inclusive Education Resource Centres (IERCs) have been established and receiving support. Such IERCs play a crucial role in providing specialized support services, learning materials and assessment facilities for Children with Special Needs. The enrolment number has reached 148,528 exceeding the target of 49,000. Most participants surveyed as part of the GEQIP-E comprehensive evaluation believed that the established/strengthened IERCs contributed a lot for a significant increase in the number of students with special needs. This also led to a sustained result, where regions have taken over and continued them. According to the Development Partners' observations, the government is assuming responsibility for the IERCs and striving to enhance effectiveness. There is also a positive indication that the government intends to provide better support for children with special needs, particularly those with disabilities.

Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]
IERCs are one of the successful interventions of GEQIP E. The MoE has now leveraged more finance from GPE to scale up this intervention and establish 600 more IERCS in Ethiopia. A key aspect of the overall agenda that will need to be addressed urgently is to design a capacity building programme that will equip both the communities and teachers with the skills for teaching children with special educational needs and ensure children with disabilities (including new entrants) access adaptive technology constantly to sustain their retention, learning as well as optimum utilisation of already established systems and services.
Support for girls and disability are two areas that are resource intensive. There is a risk of having so many indicators related to equity that the programme thinly spreads resources, which will increase reach but possibly reduce sustainable impact. FCDO future programmes need to be explicit in the intention around focus on and the impact we want to have. This needs to correlate to the resources available within the programme. There is also a need for cross-sectoral engagement and advocating senior officials beyond the Ministry of Education, including the Ministry of Labor and Social Affairs and Ministry of Women and Children alike to ensure their commitment to allocate the necessary resources, provide expertise and promote gender mainstreaming and disability inclusion in all programmes.

Output Number and Title		Output 5 - Improved systems and capacity for planning, policy formulation and reform (Improved system of data collection, analysis, teacher preparation, delivering programs) established
Output Score		A
Impact weighting (%)		10%	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Log frame Target	Final Result Achieved
5.1 Timely Availability of Educational Information	A) EGRA report of raw student test scores available by 30 June 2023 / B) Demand driven research/ data collection (3 in number) conducted.		A) EGRA report of raw student test scores available by 30 June 2023 / B) Demand driven research/ data collection (12 in number) conducted. / C) Data for delivery systems established and utilised	Met expectations / A) Met expectations: EGRA 2023 already completed / B Moderately exceeded:14 in total / C Met expectations
5.2 Designing and implementing delivery plans.	All regions implemented delivery programme and improved education sector performance.		A) GEQIP E outcome led planning and implementation processes embedded across the MoE and REBs. / B) Conflict affected areas received support on Adapted Curriculum and Accelerated Learning Programme (ALP) planning and implementation	Met expectations / A) Moderately not met / 85% of REB respondents reported improvements in outcome based planning / B) Met expectations / All targeted REBS (Afar, Amhara and Tigray) had ALP plans and 75% had received training

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score. [1/2 page]

Timely Availability of Educational Information Performance against has met expectations. Since the start of the programme, MoE has conducted two National Learning Assessments (in 2019 and 2022) and two Early Grade Reading Assessments (2021 and 2023). School capacity to report data through the Education Management Information System has also been built. The number of demand driven research products has consistently exceeded expectations with fourteen demand-led research products developed and disseminated since 2019[4]. The data for delivery (D4D) indicator was added in 2023. The TARGET endline evaluation notes that the D4D system stands out for improving school level real-time data collection and utilisation to support decision making. Recent engagement with a school benefited from this
[4] i)"Students' exam cheating in middle and secondary level schools in Ethiopia," (ii)"Implementation of moral education in Ethiopian Schools(iii) Enablers, Barriers, and the Way Forward,"(iv) "comprehensive gender analysis of the General Education Quality Improvement Program for Equity (Ethiopia), (v)Community Attendance Team (CAT) Intervention to return Learner to School; (vi) The Effectiveness of Covid 19 School Reopening Responses to Re-Enroll and retain children and improve learning; (vii) The Effects of war on teaching and learning process in Northern Ethiopia; (viii) returning Vulnerable back to school; (xi)Assessment of Inclusiveness and School Accessibility to students with special educational needs; (xi) a study on re-thinking the development of teachers, school leaders and educational professionals; (xii) evaluation of school feeding programme, (xiii) study on teachers demand and supply; (xiv) survey and analysis of the existing situation of the education sector in terms of students learning outcome and enrolments;

Designing and implementing delivery plans. Support for delivery planning in the Ministry and regions was introduced in 2021. The original intention was to introduce a deliverology approach with a ‘Delivery Unit established in the MoE and accountability structures to be developed in the PM’s office. However, in the event this provided to be politically unfeasible. Instead, the focus has been on strengthening outcome reporting within GEQIP-E. At baseline, all eleven regions developed plans but more work was needed to focus these on outcomes rather than outputs and inputs. The TARGET Endline evaluation found that 85% of respondents from the REBs reflected that the current regional delivery plans reflect outcome-based performance. The change was mainly attributed to TARGET’s intervention. The TARGET Endline Evaluation notes that the programme adapted its implementation strategy for implementation in conflict-affected areas. For instance, training of teacher sessions for the school leadership training programme were conducted in Tigray and Amhara regions, adapting to the local circumstances.

Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]

While there are positive developments in data processing and planning, ongoing challenges need continued focus. There is significant variation in the capacity and the extent to which such systems are utilised by different regions and schools. Future UK support should build on the data and delivery support it has provided, ensure continued and optimum utilisation of already established systems, and facilitate scale up in the most underserved regions.

The TARGET endline evaluation notes the lack of baseline studies which complicated efforts to measure the impact of interventions at school level. Provision for the generation of baseline studies should be a precondition for any programme to be approved by the MoE. This will also help in defining the technical assistance that will be provided to schools and identify the potential gaps in resourcing.

Output Number and Title		Output 6: Sector Financing and Programme Management/ Monitoring of GEQIP E programme strengthened.
Output Score		A
Impact weighting (%)		10%	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
Public Private Partnership Study undertaken	Education Financing Strategy validated and implementation agreed		Education Financing Strategy validated and implementation agreed	Met expectations / Strategy was approved in 2023
Funding arrangements, Quality Programme Management systems and stakeholder engagement established.	An Endline review of TARGET completed		A) GEQIP E successor programme informed by lessons and best practices of TARGET / B) Lessons and best practices of TARGET shared with stakeholders / C) An Endline review of TARGET completed	Overall: Met expectations / A) Met expectations: GEQIP-E successor programme –TREE – approved / B) Met expectations Lessons learned document produced and disseminated / C Did not Met expectations: Endline review of TARGET submitted April 2024 but the quality of evaluation does not meet FCDO’s standard

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score. [1/2 page]
6.1 Education financing strategy As reported in the 2023 Annual Review, the Education Financing Strategy was validated, and key findings disseminated in 2023. The GoE continued to allocate 22 percent of public expenditure to education, which is above the Sub-Saharan average of 17 percent and overall acceptable level. However, the subsector allocation favours higher education, with an estimated 40 percent allocated to this sector. target was achieved. General education does not receive sufficient finance to deliver nationally on basic inputs such as school grants and textbooks which are the building blocks of improved quality
6.2 Funding arrangements, Quality Programme Management systems and stakeholder engagement established. Two additional targets were added to this indicator in 2023. The first was the design of a successor programme to GEQIP-E which has been achieved. The Business Case for TREE was approved in 2024. The Bank’s programme, ETOL, though which our financial aid will flow, was approved in February 2025. The TARGET endline report was received in April 2024. It provides an independent assessment of the performance of the TA component of the programme. Overall, the evaluation finds that TARGET was well aligned with Ethiopia's educational policies and showed adaptability when faced with challenges, including the Coronavirus Disease 2019 (COVID-19) pandemic and insecurity in various regions. Lessons generated from the endline evaluation were captured and shared with stakeholder.
Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]
As noted in the 2023 Annual Review, the Multi Donor Trust Fund has performed well as a coordinating mechanism to oversee and manage the GEQIP-E programme and to crowd funding into the sector. Lessons learned have been fed into the design of the new FCDO funded programme – Transforming Education in Ethiopia (TREE). However, domestic and donor funding to general education is insufficient In the next phase of its programming FCDO should continue to advocate for sufficient funding to general education from i) domestic resources - in terms of an increase in the share of the education budget allocated to general education and ii) from IDA where we are asking whether the remaining $350 million of funding to ETOL can be allocated from IDA21.
Complementary support to FA through the MDTF via a Technical Assistance programme was very effective under GEQIP-E despite multiple shocks. The FCDO TA programme endline evaluation shows significant improvement in leadership competency, inclusiveness, use of evidence and data for education planning and decision making registered because of the TA support. This has contributed to increased enrolment ratios, gender and disability inclusion particularly on educational participation and academic achievement of children with disabilities. FCDO should ensure strong alignment between the proposed TA under TREE and UK’s other education-related investments.

D: Value for Money [½ - 1 page]

 VfM performance compared to the original VfM proposition in the business case
The provision of PforR financial aid, and the technical assistance to enhance delivery and school leadership were essential components in enhancing delivery and strengthening the Ethiopian Education system. Table 4 below summarises the main vfm conclusions related to both the financial aid and TA components of the programme. VfM metrics were not regularly tracked over the life of the programme so the PCR has drawn on evidence from narrative reporting and a vfm assessment of the programme which was conducted in 2022,

Table 4: VfM analysis of the programme
VfM measure	Financial Aid	TA component (TARGET)
Economy	The GEQIP E programme used a Payment for Results (P4R) model incentivizing diverse results including at processes, output, and outcome level. These included the big cost drivers in the programme such as a set amount of 50ETB (£0.77) per capita grant (for Grade 1-4 students).,	Overall, the programme was delivered within the planned budget and has managed principal cost drivers, including training participant per diems and consultant fee rates, and venue hire. There was minimal budget variance signifying a robust adherence to the allocated budgets, exemplifying efficient budget management and financial control within the programme.
Efficiency	Most of the intermediate-level result indicators of GEQIP E related to efficiency, and they generally showed good performance. There have been some challenges with respect to low-budget execution and procurement delays due to its complexity and lack of procurement expertise in government.	The expertise acquired in the initial years contributed to more efficient methods in the later phases of the programme. These evolving trends underscore the programme's commitment to efficiency and a certain level of sustainability through the development of local capacity.
Effectiveness	Evidence shows that there was generally good progress at the outcome level but to date there has been no significant improvement in learning outcomes . Conflict and the COVID-19 pandemic have acted as brakes on progress in terms of improving children’s learning levels.	TARGET adjusted its operations in light of several contextual and external factors, including frequent ministerial changes in the MoE, conflict situations and the COVID-19 pandemic. Its strengths included embedded TA, regular stakeholder consultation, strong management processes, and frequent risk adjustment.
Equity	Equity was the major focus of GEQIP E. It included activities aimed at reducing barriers to schooling and learning amongst marginalized groups such as disadvantaged girls and children with disabilities. There was excellent progress on including children with disabilities, but challenges remain in closing the gender gap between the emerging and more developed regions, and reaching vulnerable children impacted by conflict and crises.	The programme undertook deliberate measures to promote gender equity, particularly by training women staff and leaders and supporting schools in emerging regions. Despite these efforts, the numbers indicate persistent underlying challenges. Conflicts and systemic barriers continue to impede the equitable distribution of educational resources and opportunities.

A VfM review of the programme conducted in 2022 concluded that investments in education in Ethiopia represent good VfM. GEQIP-E and TARGET both contained many elements that were well designed to address the most pressing issues of the Ethiopian education sector and spending per pupil is low relative to other recipient countries. The vfm rationale for investment presented in the Business Case of 2018 therefore still holds. Table 5 summarises the main vfm lessons learned and follow up actions by the education team.
Table 5: VfM lessons learned for the next phase of the programme
Recommendations and lessons	Action
Procurement practice of goods and services by MoE through the GEQIP E MDTF and in the education sector as a whole is poor and needs urgent attention.	Additional procurement support has been built into the ETOL programme by the World Bank and we will monitor closely.
Make VfM an explicit consideration in programme design of GEQIP-E and TARGET successors	The TREE Business Case includes a comprehensive set of indicative VfM metrics. A baseline will be established by the TREE TA at the end of the inception period.
Consider pro-poor weights for School Grants.	ETOL has a greater emphasis on investing in underserved communities, meaning woredas and districts with poor education provision, as well as girls, refugees and other disadvantaged groups (see overall recommendations).
Use leverage as biggest bilateral partner to advocate for more spending at lower levels of education, in particular pre-primary and primary.	UK will continue to advocate for a greater share of the education budget to general education (see overall recommendations) and the UK has influenced increased budget allocation for foundational learning and most disadvantaged learners through the ETOL design.
Continue to focus investments on pre-primary	Equitable access to early learning is a major focus of ETOL
FCDO has been the largest bilateral donor to Ethiopian education and has made a critical impact through the GEQIP programmes and other investments.	The design of TREE has learnt the lessons from the GEQIP E programmed delivered through FCDO’s FA and TA. TREE will continue to target the twin challenges of equitable access and learning in the context of ongoing crises in Ethiopia.
Review GEQIP-E’s P4R funding model before its next iteration.	Lessons have been learnt and built into ETOL. The programme complements the P4R component with investment lending which will provide strong technical assistance (TA) to ensure effective Program implementation.

E: Risk [½ - 2 pages]

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.
The original overall risk rating of the programme was Moderate. The programme risk rating in the annual reviews between 2019 and 2023 was increased to Major due to: 1) COVID-19 pandemic and related school closures, 2) escalating social unrest, and political challenges, and 3) issues with budget planning and execution. As a result, this programme continued holding a ‘major’ risk rating.
The FCDO held a comprehensive risk register for the GEQIP E programme which was maintained, monitored, and updated regularly. The programme risk register was updated quarterly by FCDO’s Education programme team and reviewed in detail by SRO, PRO &DPM. until the program end date i.e. January 2025.   Prior to the review of the Programme Risk register PM team holds RR review meetings with the TA suppliers and the information is used to feed into the Programme’s RR.  Risks were categorized under fiduciary, policy & programme delivery, strategy & context, and safeguarding.
The following risks were identified and closely monitored and managed throughout the life of the programme.
- Financial and fiduciary (cautions appetite):  Major Fiduciary risks during the lifetime of the programme were associated with delays in school grant transfers, weak reporting from schools, low budget utilization, weak internal audit functions, and weak procurement system, and staff turnover. ‘There were 11 fraudulent cased identified related to school grant. Nine cases colosed by the MoE Ethics and Anticorruption and the remaining two cases that went through legal procedures have been resolved, with the court ordering the school principal to repay the misused funds. The money was deducted from the principal's monthly salary and returned to the school's financial account.
- Strategy and context (Receptive risk appetite):  There were two major risks within the strategy and context category. The first major risk was Social and political unrest disrupt education service delivery, outbreak of conflict in various regions, drought and COVID-19. Besides, raising inflation on food and non-food item, has caused significant increase the cost of living and education material. GoE incurred significant costs responding to such challenges, which negatively compromised its ability to match agreed level of funds to the programme and ensure sustainability.
- Policy and programme delivery (Receptive risk appetite): Risks under this risk category included: a) ensuring vfm in programme in TA service delivery due to optimistic forecasts and delay in delivering milestones according to planned timeline and lack of understanding on FCDO commercial and financial. Requirements: b) capacity in implementing partner organizations negatively affecting the quality and implementation progress of the program; and b) ambitious changes expected within the MoE ways of working with the PforR modality and potential slippage of DLIs.
- Reputational (Cautious risk appetite):The risk associated under this category related with Programme on Financial Aid modality, delay on programme financial aid which could pose a reputational risk.
- Safeguarding (Cautious risk appetite) This Risk associated with policy/legal frameworks for environmental and social management and inconsistent implementation in all regions. This is related to lack of considering cultural appropriateness noted in pastoralist communities’ social values, culture, indigenous knowledge and social structures.
To mitigate the risks the programme used the Partnership Principles Assessment as the baseline condition for FCDO Financial Assistance support. FCDO together with other DPs including WB, and other teams across the Embassy was engaged in close and proactive monitoring to catch up with delays, minimize the impact and for collective influence. Besides, the programme liaises with GoE, Ministries and Regional Education Bureaus.
To ensure that the funds were utilized for the intended purpose, it adhered to programme Operational Manual (PoM), financing guidelines and verification protocols, which clarify the process and disbursement for PforR for the FA program. MoE ensured that reports from the regions came regularly and monitored the timely submission and measures to secure these program requirements such as withholding resources based on discussion with Ministry of Finance. Furthermore, the programme adhered to the PrOF rules, Public Financial Management (PFM) and ensures a robust Fiduciary Risk Assessment conducted by the WB and FCDO and mitigation measures implemented. The 2023/24 FRA rated moderate, which broadly reflects good international practice, adequate laws, regulation and guidance in place. Besides, the WB also had a strong oversight and monitoring of programme performance.
A Due Diligence Assessment and refresher were held before the programme reached an agreement with the TA provider. Technical Assistance was mobilised to complement the results outlined in the FA, to monitor and evaluate the programme implementation and to ensure Safeguarding Against Harmful Effects (SAHE). Additionally, the programme conducted robust monitoring of contract performance through reviewing periodic physical performance, financial and audit reports. Moreover, the programme has thoroughly followed the findings of external audit report submitted by Audit Service Corporation (ASC) and the WB follows the availability of plan of action and ensures corrective actions undertaken. Besides, there was a quarter review and update of Delivery chin and risk mapping exercise with partners.

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation [1 - 1 ½ pages]
Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency. [1 page]
Commercial management
The programme was implemented through two components: first was a share of the fund to GoE through the World Bank MDTF for PforR and the second is through contracted Technical Assistance and Monitoring and Evaluation (M&E).
The Financial Assistance component of the programme management and disbursement of funds is conducted in accordance with the Administrative Agreement entered between the UK and the World Bank MDTF. The day-to-day execution of the programme is guided by the Programme Operational Manual of GEQIP-E. The World Bank is executing its fund management duties satisfactorily including facilitating biannual and a Mid Term Review Mission, and quarterly steering committee meetings. An action plan that includes measures to improve programme performance measures (fiduciary, financial management, staffing) is designed, executed, and monitored on regular basis.
Payments to Education Development Trust (EDT) and M&E supplier Montrose were based on contracts, with disbursements linked to timely submission and satisfactory performance against key performance indicators respectively. The programme team had regularly risk discussions with EDT to update the delivery chain risk mapping. Besides, there was a regular asset register, and proper asset disposal processes undertake as per the FCDO asset disposal guideline. Based up on the PrOF Programme Asset Guideline. FCDO ensured the best value for money by retaining high value assets; namely five vehicles for GEQIP-E successor programme and ensured these assets were maintained in running order.
Some of the challenges that were addressed during the programme implementation period included limited engagement of Regional Education Bureaus in the planning and monitoring activities, ongoing armed conflict in some parts of target regions of the country particularly Amhara, a disconnection in monitoring at lower structural levels and issues with data processing and software of Education Management Information System (EMIS), accuracy in manual data collection and reporting in Data for Delivery (D4D), There was a delay in recruitment of TA staff members,
Financial management
 Table 6: Programme spend by component
Code	Component Description	Total programme budget (£)	Total spend against budget to date (£) (Jan 2025)	% spend against total budget	Remaining budget/ Budget not utilised as of Jan 31st 2025	% remaining budget/ Budget not utilised as of 30th Jan 2025.
300236-101	FA for the GEQIP-E	£90,m	£87.38m	97.1%	£2.61m	2.9%
300236-102	TA, research, innovation to GEQIP-E	£20.8m	£20.66m	99%	£135k	1%
300236-103	Programme Monitoring and independent verification/evaluation for GEQIP-E	£795k	£732k	92%	£62k	8%
	Total	£110m	£108.7m	99%	£1.2m	1%

Table 7: Budget disbursement per year per project
Project code	FY19	FY20	FY21	FY22	FY23	FY24	FY25	Total
300236-101	15,000,000.00	25,000,000.00		7,100,000.00	19,000,000.00	20,100,000.00	1,187,395.00	87,387,395.00
300236-102	-	2,290,451.72	3,301,136.45	5,185,831.67	3,836,017.16	6,043,752.54	7,224.24	20,664,413.78
300236-103	-	-	-	122,766.00	137,921.84	471,480.80		732,168.64
Total	15,000,000.00	27,290,451.72	3,301,136.45	12,408,597.67	22,973,939.00	26,615,233.34	1,194,619.24	108,783,977.42

The General Education Quality Improvement Programme for Equity (GEQIP-E) supported by the pooled resource through the WB- MDTF and has standard reporting mechanism which is the Interim Financial Report (IFR) produced by Ministry of Education (MoE) and yearly audit report that has been carried out by the Audit Services Corporation. The GEQIP-E financial aid disbursement for Government of Ethiopia (GoE) is guided by a Memorandum of Understanding (MoU) signed with the Ministry of Finance (MoF) and an Administrative Agreement signed with the World Bank.
Disbursement for the GEQIP-E FA through the WB-MDTF was based on conditions such as approval of the interim financial reports, verification of attainment of results for the disbursement of funds associated with disbursement-linked results (DLRs); planned and implemented during each year of the Program’s cycle audit findings and management response. According to the Program Appraisal Document (PAD), the attainment of DLIs/DLRs was agreed to be verified by an independent verification agency (IVA) starting from 2017/18. The Ethiopian Statistics Services (ESS) has been commissioned to serve as the IVA for the program. The utilisation of the transferred amount to date is £88,6m. Besides, the WB provide an oversight role for the fiduciary, social and environmental safeguard aspects of the programme. This oversight by the WB was provided for the entire programme period from 2017-2025.
For the TA supplier, payment was made based on demonstrated performance against the agreed key performance indicators, milestones and after securing approval from independent Monitoring and Progress Evaluation with Montrose International LLP and HCDT SRO and PRO approval. £125k of funding was deducted for unachieved milestones and £4k for damaged assets. The utilisation of the transferred amount to date is £20,6m. Reimbursement payments were made based on the actual financial expenditure report submitted and were verified by the programme team.
For independent Monitoring and Progress Evaluation, FCDO signed a contact with Montrose International LLP on August 2021 to provide advice, support and quality assurance to enrich EDT-TARGET M&E activities, verify TARGET’s activities and milestones and produce Midline and Endline Evaluation Repot. The supplier submitted all deliverables and based on the contract agreement a total of £649k plus late penalty payments were disbursed. Several factors contributed to the delay. This included the need to undertake a detailed scrutiny on Montrose’s transactions, delayed response by Montrose to clarify contested receipts and financial reports to make sure all expenditures, mainly reimbursables, were illegible and in line with the contract before making final payment.
Programme-level approach to monitoring and evaluation [1/2 page]
The main monitoring mechanism for the FA component of GEQIP E has been bi-annual joint implementation support missions, which were led by the Ministry of Education and the World Bank. The missions involved a steering committee meeting, progress reporting by the Ministry of Education, and in-depth issue-based discussion with relevant departments in the MoE and the Ministry of Finance ranging from specific technical components of the program to procurement and financial aspects. Such missions also involved school field visits to triangulate information acquired from the federal MoE and regions.
The achievements, challenges, recommendations and action plans were then captured in an Aide Memoire from such missions and helped to improve the quality of program implementation such as inform risk management plans. A process evaluation is carried out for the Financial Aid Programme and is expected to inform the detailed planning and implementation of a successor programme. A comprehensive exit evaluation of GEQIP-E was procured by the MoE independently (July 2024). The study found a generally positive picture but there is more work to do to improve foundational learning, ensure more children stay in primary school, and tackle regional gender disparities in the emerging regions,
Alongside this, FCDO’s centrally funded research programme – Research for Improving Systems in Education (RISE) - researched how national education reforms in Ethiopia, including GEQIP-E, have been working to improve learning. The team included the Institute of Educational Research at Addis Ababa University, the Policy Studies Institute (PSI), Ethiopia, and the REAL Centre at the University of Cambridge. The research generated a large body of evidence that can be found here. The findings of the research have fed into the design ETOL and GoE broader reform efforts.
The Technical assistance component of the business case included an independent M&E function. Two light touch midlines and an endline evaluation were undertaken during the time span of the program. The end line evaluation among others assessed the extent to which the TA component helped to deepen and accelerate the effective realization of the higher-level program outcomes and impact of the FA. The evaluation concluded that T the UK Government’s £20.8 million investment through TARGET has achieved its intended results. Commendable results include:
- Leadership: School leadership training reformed to become practice-oriented, with school leaders who passed through this training already demonstrating enhanced leadership competency.
- Systems and data: Established systems for improved availability and utilisation of real-time data to support long-term and day-to-day improvements.
- Gender equality: More women in educational leadership positions and foundations in place to sustain this.
- Equity: Improved learning and access to education for marginalised learners, including children with disabilities, rural girls, and other minority groups.
- Learning: Improved learning outcomes in target schools and low-performing crisis-affected schools.
- Sustainability: TARGET approach adopted by new nationwide education programme in Ethiopia and will be scaled-up.

Date of last narrative financial report	26 December 2024	Date of last audited annual statement	29 February 2024