## Annual Review Template
Title: Teacher Effectiveness and Equitable Access for Children (TEACH) in Zimbabwe
Programme Value £ (full life): £55,540,000		Review date: 26/10/25
Programme Code: 300252	AMP start date: 26/07/19	AMP end date: 31/12/26

Summary of Programme Performance
Year	2019/20	2020/21	2021/22	2022/23	2023/24	2024/25
Overall Output Score	B	A	A	A	A	A
Risk Rating	Major	Major	Major	Major	Moderate	Moderate

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-300252 Documents (fcdo.gov.uk)
DevTracker Link to results framework:	DevTracker Programme GB-GOV-1-300252 Documents (fcdo.gov.uk)

## A. SUMMARY AND OVERVIEW
Description of programme
The Teacher Effectiveness and Equitable Access for Children in Zimbabwe (TEACH[1]) programme (Jul. 2019 to Dec. 2026) has a total budget of £55.54m. This annual review covers the period Sep. 2024- Aug 2025.
[1] All abbreviations are spelt out fully or footnoted upon first use. A complete list is found in Annex A
Its impact and outcome statements are as follows:
Impact Statement: Contribute to a positive shift in the trajectory of learning outcomes in Zimbabwe: leaving no one behind.
Outcome Statement: Strengthened and more sustainable national education system that is improving the quality of teaching and equitable access for all.
TEACH has operated in a challenging environment. The year in review began during a severe drought that impacted the food security of 50% of the population. The 2024-25 rainy season was good, but food insecurity persisted into early 2025, negatively impacting attendance and enrolment of disadvantaged pupils. Zimbabwe’s projected population of school going age (4 to 18) is 5,898,724, yet the actual 2024 school population is 4,735,506 (50.2% girls), suggesting that over a million children may be out of school.
Economic challenges persist. The annual rate of inflation remained high at 95.8% in the local ZiG currency[1]. However, $US denominated prices remained stable with an estimated annual inflation rate of 3.2%[2]. The education sector budget has risen from 13.7% of the national budget in 2024 to 16.9% in 2025[3]. This remains below the 20% target set in the Kenyatta Declaration, which Zimbabwe has signed. Education was allocated 46.6 billion ZiG out of a total budget of 282.6 billion ZiG (3.4% of GDP). Most of the budget continues to be spent on wages (82% in 2025). This limits spending on infrastructure, teaching resources and recurrent costs. Up to date information about budget disbursement is not available, however Ministry of Primary and Secondary Education (MoPSE) has reported that only 31% of the annual budget had been received in the first 6 months of 2025[2]. The government’s own Basic Education Assistance Module (BEAM) for the payment of fees for orphans and vulnerable children (OVCs) has remained inactive for the past two years.
[1] Zimbabwe Inflation Rate
[2] Zimbabwe's Inflation Surge in Local Currency, USD Enters Deflation: Comparative Analysis with SADC Peers
[3] UNICEF Biannual Report July 2024-Dec 2025.
[2] Presentation to Education Coordination Group 17/08/2025
MoPSE has moved ahead with implementation of the new Heritage Based Curriculum (HBC) in 2025 by organising training at subnational level, however, shortages persist in availability of print copies of new syllabuses and other updated materials.
Government of Zimbabwe (GoZ) has introduced a new (PVO) Private Voluntary Organisation Act of 2025 necessitating additional compliance requirements for TEACH implementing partners operating as Non-governmental Organisation (NGOs) .
About changes to UK ODA
- At this time of profound global change, the UK has taken the difficult decision to gradually reduce the UK’s Official Development Assistance (ODA) to the equivalent of 0.3% of Gross National Income (GNI) by 2027.
- The UK remains fully committed to playing a globally significant role in humanitarian aid and development. The transition to spending 0.3% of GNI on ODA will require significant shifts, including establishing long-term partnerships based on mutual interests and respect.
Reductions in ODA necessitated only minor adjustments to TEACH logframe targets during this reporting period, but will necessitate significant adjustments to workplans and the logframe for the next annual reporting period.
Summary supporting narrative for the overall score in this review
The TEACH programme scores ‘A’ in the 2025 AR indicating that, overall, it is meeting expectation.
This score summarises the following rating for each of the four active outputs:
- Output 1: Equitable access to schools for marginalised girls and boys, including Children with Disabilities (CWDs) = B (30% weighting)
- Output 2: Increased capacity of teachers and administrators for quality teaching and learning = A+ (40 % weighting)
- Output 3: Education system strengthened = A (10% weighting)
- Output 4: Supporting Adolescent Girls’ Education (SAGE) = A+ (20% weighting)
Key achievements for the year in review include:
- The training of 350 inspectors in reformed inspection methodology and 72,372 teachers in improved classroom methodologies.
- Training and delivery of materials for teaching Social and Emotional Learning (SEL) to 3,284 ECD teachers.
- The delivery of Accelerated Teaching and Learning (ATL) to 5,657 out-of-school girls, over 90% of whom demonstrated improved literacy and numeracy skills.
The most significant challenge met was:
The under-delivery of school improvement grants (SIGS) to only 738 schools compared to the target of 791
Achievements and challenges are discussed fully in Section C below.
The four outputs were delivered through six financial components [3].
[3] The geographical distribution of each component by district is summarised in Annex D
- 101: Equitable Access implemented by UNICEF (Outputs 1 & 2)
- 102: Teacher Professional Development (TPD) implemented by Education Development Trust (EDT) (Outputs 2 & 3)
- 103: Monitoring, supervision, technical assistance, and evaluation - managed by FCDO (Crosscutting)
- 105: Solarisation of schools – implemented by UNICEF (Output 1)
- 403: Supporting Adolescent Girls Education (SAGE) – implemented by Plan International Output 4)
- 404: Social and Emotional learning (SEL) pilot at pre-primary level implemented by Think Equal (Output 2)
Major lessons and recommendations for the year ahead
Lesson	Recommendation
Output 1: Equitable Access
Negative trends are noted in (ii) gender equity in primary enrolment and enrolment of children with disabilities (CWDs).	MoPSE and TEACH partners to seek reasons for these trends and adjust programming to respond. (by Mar 2026).
Disbursal of School Improvement Grants (SIG) did not meet expectation with 43 FCDO-funded schools failing to receive in time.	Reasons for SIG payment failure to be investigated and rectified (by Dec 2025).
Zimbabwe remains without a School Financing Policy as TEACH enters its final year of providing SIG to disadvantaged schools.	TEACH partners to work with MoPSE and GoZ to advocate for cabinet adoption and implementation (by Dec 2025).
Certification of solar installation in six Phase 1 schools remains outstanding and progress in Phase 2 is behind planned timeframes.	UNICEF to complete outstanding certification and expedite Phase 2 in line with original timeframes, while implementing relevant lessons learnt and recommendations (by Aug 2026).
Theft and vandalism of solar installations remains a concern. There has been limited engagement from MoPSE. .	UNICEF and MOPSE to continue risk mitigation activities (e.g. community mobilisation, physical security, district monitoring) with engagement from MoPSE to increase sustainability.
Output 2: Increased capacity to teachers and administrators for quality teaching and learning
A decrease was noted in Gr. 3 Zimbabwe Early Learning Assessment (ZELA) Literacy results from 78% in 2024 to 74.94% in 2025.	Seek and address reasons for the decline. TPD to maintain focus on foundational learning and remediation (by Mar 2026).
Use of Learning Passport remains low and its potential for sharing materials has yet to be realised. This may be reflective of a low level of general ICT skills among educators and officials.	TEACH to maintain advocacy with MoPSE and teachers to increase use of Learning Passport. Future programmes to consider strategies to strengthen ICT skills educators (by Jun 2026).
Uptake of e-inspection and other use of data in decision making is inhibited by lack of ICT equipment at Provincial and District levels.	MoPSE and FCDO to invest in MoPSE ICT infrastructure (subject to availability of funds) (by Aug 2026).
Development of the GEDSI[4] and Safeguarding strategy is not fully aligned with the Gender Analysis and Audit (funded by GPE) resulting in possible inconsistency or duplication of effort.	MoPSE, TEACH and GPE partners to align GEDSI and safeguarding strategy implementation with the Gender Analysis and Audit, and collaborate to ensure recommendations are implemented. (By Mar 2026).
Implementation of SEL heightens teachers’ awareness of the emotional wellbeing of pupils and reveals previously unrecognised difficulties.	MoPSE and Think Equal to adapt programmes to equip teachers to respond to issues of safeguarding and wellbeing and to refer cases where appropriate.
Funding is no longer available for an external evaluation of the SEL Pilot, yet valuable lessons still need to be captured.	Think Equal to strengthen internal evaluation of SEL pilot to ensure lessons are documented. FCDO to make resources available if possible (by Jun 2026).
Output 3: Education system strengthened
The TPD Working Group has made specific recommendations for the improved alignment to pre- and inservice teacher education.	MoPSE and partners to ensure: (i) Participation of teachers’ colleges in in-service training, (ii) more ministerial collaboration at provincial level, and (iii) co-development of materials (by Mar 2026).
TEACH-supported research on blended learning has revealed a critical lack of relevant IT skills among teachers.	MoPSE and EDT to collaborate in designing a structured training plan for teachers on blended learning and ICT integration.
Output 4: Supporting Adolescent Girls’ Education (SAGE)
SAGE significantly exceeded milestones for learning outcomes, suggesting targets could be more ambitious.	SAGE to review and update Output and Value for Money (VfM) indicator targets to increase level of ambition for end of the project (by Dec 2026).
There is significant unmet demand from communities for Non-Formal Education (NFE) for boys. Indicators suggest boys now face significant challenges compared to girls.	SAGE to pilot providing access to the TVET to a cohort of adolescent boys. (by Mar 2026).
Plan International has successfully supported MoPSE to develop a costed draft NFE Policy.	MoPSE and Plan International to support submission and adoption by GoZ. (by Mar 2026).
A comprehensive review of SAGE NFE materials has not yet been conducted to ensure full alignment with HBC.	Plan and MoPSE to review NFE materials to ensure full alignment with HBC (by Mar 2026).
[4] Gender Equity, Disability and Social Inclusion

Project performance in addressing recommendations from the 2024 AR is summarised in full in Section C, under the relevant Output.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
The Theory of Change (ToC) presented in the logframe, may be stated in words as follows:
If (Outputs) TEACH: (i) supports equitable access to schools for marginalised girls and boys including CWDs, (ii) Increases the capacity of teachers and administrators for quality teaching and learning, (iii) strengthens the education system and (iv) supports out-of-school adolescent girls to access basic education. And identified assumptions hold (see Annex C) -
Then (Outcome Statement) this will result in a strengthened and more sustainable national education system that is improving the quality of teaching and equitable access for all.
This will contribute to (Impact Statement) a positive shift in the trajectory of learning outcomes in Zimbabwe - leaving no one behind.
A diagram of the ToC is presented in Annex B. The logic of the ToC and wording of the impact and outcome statements have remained unchanged since the programme began in 2019. However, activities have evolved and adapted in light of unfolding events, lessons learnt, and challenges faced (e.g. financial crisis, Cyclone Idai and Covid 19).
Since 2023, adaptations have also been made to rationally reallocate activities between TEACH and three Global Partnership for Education (GPE) programmes (i) System Capacity Grant (SCG) - $3.3m: 2021-2025, (ii) System Transformation Grant (STG) - up to $24m, 2023-26 and (iii) the Girls’ Education Accelerator (GEA) - $12.4: 2023-2026. Implementation of TEACH and GPE are coordinated through the Education Partnerships Steering Committee (EPSC), which meets quarterly to ensure coordination and consistency with the wider ToC of the education sector in the MoPSE Education Sector Strategic Plan (2021-2025) (p72).
In Oct 2024 a Business Case Addendum approved a no-cost extension of TEACH for 9 months from 31st Mar 2026 to 31st Dec 2026. The following were also approved:
- An additional £2,400,000 committed to UNICEF for a second phase of solar electrification in 78 additional schools by Dec 2026.
- A new Accountable Grant Arrangement (AGA) with EDT to extend the TPD component from 1st Nov 2025 to 31st Mar 2026.
- A three month no-cost extension of the AGA with Think Equal from 31st Mar 2026 to 30th Jun 2026 to complete the delayed SEL pilot project.
In April 2025, further changes to the logframe were approved, based on: (i) recommendations in the 2024 Annual Review (AR) and (ii) updated information on beneficiary numbers. The following Impact Weightings were maintained: Output 1 = 30%; 2 = 40%; 3 = 10%; 4 = 20%.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
Outcome level:
Of five outcome indicators, two are on track and three are off-track.
Outcome Indicator	Target (programme end)	2024 Result (2023 data)	Milestone for 2025	2025 Result (2024 data)	Status
1. Proportion of P3 and satellite[5] School Improvement Grant (SIG) supported schools that have at least 75% retention rate up to grade 7 (Gr7)	50%	52%	50%	56%	On Track
2. Number of marginalised children provided access to functional schools (poorest primary/satellite)	240,318 learners	Total: (329,874(T) 162,855(F) 167,019(M)	265,951 learners (F 131,125)	225,654 (F: 112,334)	Off Track
3. Dropout rate for secondary school learners (by sex)	3.4% (forms 1-6) – changed to: F 4	T:13.2% (F:14.3%; M:12.0%)	14%	T: 11.9% (M:11.3% F:12.5%)	On Track
4. Percent children achieving at or above grade appropriate level of maths after completing Gr 2	T: 76% (M:74, F: 79)	T:70.1 (M:67.3%, F:72.7)	76% (M:74%, F:79%)	T: 72.5% (M:69.7% F: 75.1%)	Off Track
5. Percent children achieving at or above grade appropriate level of English after grade 2	81%	T:78% (M: 74.8%; F: 81.3%)	77.1% (M:76%, F:81%)	T 74.9% (M:70.7%, F78.9%)	Off Track
[5] ‘satellite’ schools are less developed schools not yet fully registered.

Outcome Indicator 1. The proportion of School Improvement Grant (SIG) supported schools achieving a 75% Grade 7 Retention Rate improved by 4% compared to 2023. This supports the assertion that SIGs have a positive influence on pupil enrolment and retention (On Track).
Outcome Indicator 2 represents the total number of pupils enrolled in schools benefiting from SIGs funded by TEACH. The milestone of 265,951 learners (F:131,125) was not met. Actual figure of 225,654 (F:112,334) is 40,297 below the milestone. Reasons for the under-delivery of SIGs are discussed under Indicator 1.1 below (Off Track).
Outcome Indicator 3. The secondary Form 4 drop-out rate has decreased from 13.2% in 2024 (2023 data) to 11.9% (M:11.3%; F12.5%) in 2025 (2024 data). Reasons for the improvement may relate to the combined impact of interventions, including SIG, under Output 1. The trend is surprising given stress created by the 2024 drought. (On Track).
Outcome Indicator 4. The percentage of primary Gr 3 pupils at grade level in mathematics in Zimbabwe Early Learning Assessment (ZELA) rose slightly from 70.1% in 2024 to 72.5% (M: 69.7%; F:75.1%) in 2025. However, this was below the milestone of 76%. It is concerning that girls now outperform boys by a margin of 5.4% (Off Track).
Outcome Indicator 5. The Percentage of primary Gr 3 pupils at grade level in English in ZELA decreased from 77.1% in 2024 to 74.9% (M:70.7%, F:78.9%) in 2025. While performance is below benchmark, the long-term trend remains positive (see graph). It is concerning that girls outperform boys by a margin of 8.2%. This decrease is not readily explicable, given the focus on foundational literacy and equity in TEACH. Reasons should be sought and addressed (Recommendation 1).
It remains feasible, that the TEACH programme will reach all its Outcome Targets by the end of the project in December 2026.
Impact level
Two out of three of the Impact Indictors are fully on track (see table below).
#	Impact Indicator	Target end programme	2024 Results (2023 data)	Milestone for 2025	2025 Results (2024 data)	Status
1	Examination pass rate at G7 (by sex)	47% with gender equity	T:45.1% (M:40.8%; F:49.3%)	47% (with gender equity)	T: 49.0 (44.0%M; 53.7%F)	Average On Track but males below target.
2	Examination Pass rate at Form 4 (by sex)	30% with equity	T:30.13% (M:29.4%; F:30.8%)	31% (with gender equity)	T: 33.2 (32.7%M; 33.5% F)	On Track
3	Gender Parity Index for Primary and Lower Secondary (F1-4) – Gross Enrolment Ratio (GER)	>0.95 – 1.05	Primary1:00 / Secondary: 1.04	>0.95 – 1.05	Primary: 1.03 / Secondary: 1.00	On Track

Impact Indicator 1. The primary Gr 7 Pass-rate improved by 3.9% from 45.1% in 2023 to 49.0% in 2024. However, the gap in performance by gender is widening, with girls outperforming boys by 9.7%. This should be investigated (Recommendation 1). The 2024 AR also noted that 138 (2%) out of 7,386 primary schools nationwide reported a zero percent pass rate. Encouragingly, this has declined although there are still 81 schools (1%) in 2025. (Average On Track, but males below target).
Impact Indicator 2. The secondary Form 4 pass-rate improved by 3.1% from 30.1% to 33.2%, with gender equity. The 2024 AR drew attention to the existence of 381 out of 3,131 secondary schools (12%) nationwide that reported a zero percent pass rate. New figures for 2024 pass rates are not yet publicly available (On Track).
Impact Indicator 3. The Gender Parity Index indicates near equity in enrolment at primary level (1.03) and parity in enrolment at secondary level (1.0) (On-Track).
These trends suggest that TEACH will reach its Impact Targets by the end of the project.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
TEACH is meeting expectations in delivering outputs, is making mixed progress in meeting milestones at outcome level and strong progress at impact level. TEACH continues to make a decisive contribution to stabilising and enhancing the Zimbabwean education system in a challenging environment. External evaluation and stakeholder feedback indicates that it is considered relevant to the current needs of the sector and is highly valued.
TEACH remains aligned with the policy emphasis of the new UK government in supporting human capital development[4] and is also well aligned to SDG 4 objectives. Activities also remain closely aligned with GoZ priorities summarised in the Education Sector Strategic Plan 2021-25. (ESSP).
[4] UK Government (2025) UK’s Modern Industrial Strategy.
TEACH has a ‘significant’ (5%) rating on the FCDO Disability Inclusion Marker, reflecting its contribution to UK reporting on commitments in the United Nations Convention on the Rights of Persons with Disabilities. Key activities in this category include additional SIG payments to schools and TPD in inclusive teaching methods. TEACH also has a ‘significant’ (5%) rating on the FCDO Gender Equality Marker reflecting its contribution to compliance with the UK Gender Equality Act. Key activities in this category include second chance education and vocational training of rout of school adolescent girls through SAGE and support for development of the national GEDSI Strategy.
Based on the analysis of outcome and outputs achieved, ToC and Value for Money (VfM) indicators, there is evidence that TEACH has provided good value for money. It is recommended that it should continue, with a reduced budget, and while implementing the recommendations of this report.
## C. DETAILED OUTPUT SCORING
Output Title	Equitable access to schools for marginalised girls and boys, including Children with disabilities (CWDs)
Output number:		1	Output Score:	B
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Percentage and number of schools that receive SIGs by end of first term each year	(791) 99%	(93%) (B)
1.2 Number of MOPSE, school, and community personnel reached to improve understanding and support from inclusive access to Early Childhood Development (ECD) and quality education of CWDs (Annual data)	8,000 additional (non-cumulative)	12,498 (M: 4,609; F:7889) (A++)
1.3. Number of people with improved access to clean energy as a result of International Climate Fund (ICF) projects	Initial stakeholder consultation, / contracting of installers completed, / Key stakeholder engagements completed., / community engagement activities initiated.	Initial stakeholder consultations done (Rural Electrification Authority - Ministry of Energy and Power Development, Local Government and Social Amenities (MoEPDLGSA). Community sensitisation meetings initiated by Apostolic Women’s Empowerment Trust (AWET) (B)
1.4. Number of institutions with improved access to clean energy as a result of ICF projects	Identification of schools; site assessments completed	Preliminary list of schools identified, site assessments complete, development of request for proposals in progress. (B)

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 1 comprises activities to enhance equitable access to schools for marginalised girls and boys (including CWDs). In 2024/25 there were four active indicators; three indicators, did not meet expectation and one significantly exceeded expectation. This output therefore scored “B” overall, also considering the relative value of investment in each indicator.
1.1: Percentage and number of schools that receive SIGs by end of first term each year (B)
The target of 99% of the 791 schools receiving SIG ‘Regular’ within the first term was not met. 738 (93%) successfully received SIG. Regular SIG is provided to rural primary (P3) and satellite primary schools with an annual income below $2,000. The value of each grant in 2025 was $1,500, with special schools (serving CwDs) receiving $2,000. Fieldwork confirmed the intended distribution. Grants were most-commonly used by schools to buy essential supplies (e.g. textbooks, stationery and furniture) and are credited by beneficiaries with maintaining basic school functionality, in a year when payment of fees remained very low (10%-20% reported in satellite schools). Funding of Regular SIG is divided between TEACH and GPE, with an additional 1,247 schools targeted through GPE support in 2025. GPE also funds other types of SIG. “SIG Complementary” assists satellite schools to meet requirements for full registration and “SIG WASH” assists schools with urgent water and sanitation needs.
The main challenge was the large volume of bank payment rejections. Despite several attempts to pay all schools, by May 2025, 53 targeted schools still had not submitted valid banking details and failed to benefit. UNICEF took the decision to cease attempts to pay in early May, to allow necessary time for other processes such as SIG verification, which could only commence, in a 10% sample, once payment ceased. This verification process is now ongoing. UNICEF report that the main reason for non-payment included the dormancy of $US bank accounts held by schools and administrative errors in the transcription of bank details. Rejections were experienced across a range of banks, but the highest rates were with AFC and ZB[6] both of which had launched a new banking system which resulted in changed account numbers. Reasons for non-payment must be understood and rectified in time for the next disbursement for 2026 (Recommendation 2).
[6] Agricultural Finance Corporation (AFC), Zimbabwe Banking Corporation (ZB)
In the last quarter of 2024, MoPSE organised SIG inductions across the country for school heads, deputies and School Development Committee (SDC) members. Training aimed to: (i) sensitize schools on objectives of SIG, (ii) get acknowledgements of receipt, (iii) sensitize schools on SIG utilization criteria, (iv) train schools on record keeping, (v) reinforce the importance of working with SDCs, (vi) disseminate findings from the 2024 SIG verification exercise. To strengthen management of SIG, UNICEF procured 4 new computers and 2 printers for the MoPSE Grants Management Team (GMT). UNICEF also provided refresher training on their Harmonized Approach to Cash Transfers (HACT) system for 72 officials (M: 47, F: 25) from all 10 provinces.
A SIG verification exercise for 2024 was again carried out by Deloitte, with a 10% sample of all schools receiving SIG from any source (289 schools). The resulting report[5] found that a majority of schools were able to adequately account for expenditure, with only one school failing to do so. Deloitte classified each school according to its risk of fraud. In 2024 their opinion was that 2 schools out of the total sample (0.7%) were rated as ‘High Risk, which is an improvement on the figure of 6 schools (2% in 2023).
[5] Deloitte (2024) SIG Full Verification Report
A number of issues were identified, resulting in recommendations across a range of risk factors: (i) school management and procedures, (ii) procurement and supplier management, (iii) financial management and control, (iv) expenditure and invoice management, (v) project implementation and monitoring, (vi) cash and bank management, and (vii) FACE[7] Form management. Recommendations for tightening controls have been shared with MoPSE, districts and individual schools, in a concise and digestible format.
[7] Funding Authorisation and Certificate of Expenditures (FACE)
Deloitte reported that, on average, SIG accounts for (14.3%) of total school income (compared to 8.6% in 2024) with levies accounting for 79.9% (72.2% in 2024), and the remainder from other sources. The increasing cost of bank charges (average $45.2 per school) has also eroded the value of grants.
Field visits undertaken during the ongoing TEACH External Evaluation confirmed that SIGs are effectively targeted to the most disadvantaged satellite and P3 schools, and found that:
- “SIGs have moderately improved functionality of P3 and (especially) satellite schools, with emerging evidence of improved pass and completion rates”
- “Each additional $1,000 in total SIG funding disbursed to schools in a district over the past three years was associated with an increase of 3.1 enrolled students” [6].
  [6] Athena (July 2025) TEACH Evaluation: Interim Finding Update
It must be emphasised that 2026 will be the last year when SIGs will be funded by TEACH (750 schools), after which support will cease. This increases the urgency and importance of GoZ adopting a sustainable School Financing Policy (SFP) (Recommendation 3).
1.2: Number of MOPSE (all levels), school, and community personnel reached to improve understanding and support from inclusive access to ECD and quality education of CWDs (A++)
This indicator refers to the number of participants reached through community engagement activities. The target for the reporting period was 8,000 and this was met and significantly exceeded as a total of 12,498 (7,889 F, 4,609 M) community members were reached. This total figure is the sum of the 3 component figures in italics below.
UNICEF supported parental engagement in early childhood education through coaching parents in the use of story books to improve literacy levels in infant classes in districts identified as having low literacy levels in the 2022 ZELA Results. Through this intervention 4,054 (M:1,145; F 2,909) community members were reached in this reporting period.
UNICEF is also supporting community engagement activities, in districts and schools that benefited from both Phases 1 and 2 of school solarisation. So far, 6,460 (M: 2,506; F: 3,954) community members in Phase 1 schools and 1,984 (M: 958; F: 1,026) in Phase 2 have been reached by this activity. Training aimed to increase parental support in monitoring learning outcomes with special attention to ECD and CWDs. These engagements also, and importantly, aimed to raise awareness among community members, district officials, and school-level stakeholders about their roles in safeguarding solar and other investments in schools against theft and vandalism.
UNICEF commissioned a report entitled “An Evaluative Review of the Integrated Primary and Secondary School Community Fairs through Outreach (2022 to 2024)[7]”, which found that “fairs were relevant and effective in gathering communities and offering services that enabled hitherto marginalized and discriminated categories of individuals to enrol in schools (p. vii)”. It also reports “a steady decline in the rate of drop out of girls due to teenage pregnancy”. The report finds that important barriers remain to the retention of disabled learners including lack of teacher training, material resources and adaptations. The report draws attention to a worrying recent decrease in the enrolment of children with functional difficulties (disabilities). The number of CWDs enrolled at primary level in 2024 was 49,459 (F: 45%) which is a steep decline from the figure of 76,693 (F: 46%) reported in EMIS 2023. FCDO Annual Review (AR) fieldwork also raised doubts about the sustainability of community fairs in the absence of project funding.
[7] UNICEF (2025) An Evaluative Review of the Integrated Primary and Secondary School Community Fairs through Outreach (2022 to 2024)”
1.3: Number of people with improved access to clean energy as a result of ICF projects (B)
1.4: Number of institutions with improved access to clean energy as a result of ICF projects (B)
In August 2024 FCDO approved a proposal from UNICEF to proceed with implementation of Phase 2 of school solarisation, targeting an additional 78 isolated rural schools in Midlands and Masvingo Provinces. Solarisation is a popular intervention with MoPSE and school communities and has attracted national media attention. Process milestones for 2025 were agreed for indicator 1.3 & 1.4, (see table above). In both cases progress has not fully met expectations. For Indicator 1.3, a critical expectation was that contracting of installers be complete, which has not happened. Stakeholder consultations were completed and an implementation committee constituted of key GoZ partners was established. For Indicator 1.4 the expectation was that identification of schools be complete. At the time of writing UNICEF has completed a detailed site inspection report for a long-list of 90 schools, which has yet to be reduced to the target number of 78. There is therefore concern that Phase 2 is behind schedule in relation to the timelines stated in the approved proposal (Recommendation 4).
As reported in the 2024 AR, Phase 1 of School Solarisation targeted 150 deep rural schools in 8 districts to provide electricity to the school administrative office, one classroom and teacher accommodation. Installations in all 150 schools were completed, but so far only 144 have received final certification. The remaining 6 still have issues to be addressed by the contractors before certification and payment of retention fees. Examples of these issues include placement of the battery box and louvres for aeration. It is noted that the issue of certification was also raised in the 2024 AR, indicating that it has taken over a year to resolve.
UNICEF continues to monitor schools affected by vandalism and theft, with all incidents documented as fraud cases. Currently, there are 10 active cases related to the 150 Phase 1 schools. These follow-ups are part of ongoing efforts to ensure accountability and protect infrastructure investments. Greater engagement in addressing this issue is also requested from MoPSE. Some additional security features were also procured and distributed to all solarized schools including alarms, padlocks and flood lights. Additionally, offline servers were distributed to each of the 150 Phase 1 schools. These devices are loaded with teaching and learning materials from Learning Passport, that would otherwise require internet access to use. Signage has also been installed in all solarized schools to provide visibility of UK support.
In November 2024, FCDO completed an external evaluation of the Phase 1 of Solarisation by Research Methods International (RMI)[8], using a mixed methods approach, based on fieldwork in a sample of 60 schools. The report focused on 4 dimensions of interest. (i) Implementation Process (ii) Relevance, Effectiveness and Sustainability (iii) Initial Impact (iv) Value for Money. It reached the overall conclusion that - “The Solar Systems in Schools (SSS) Project has proven that solar energy can enhance educational infrastructure in rural Zimbabwe, providing essential electricity and supporting broader community development”. See Section G and Annex E below for a fuller summary of findings.
Solar installation Zhokwe Primary School, Gwanda
[8] Research Methods International (2024) Evaluation of the Solar Systems in Schools Project in Zimbabwe.
Additional Activities
Through TEACH, UNICEF supported several additional activities not captured in the logframe including: (i) Training of 1,697 teachers (M: 626, F: 1,071) in Clinical Remediation to support pupils with foundational skill gaps, (ii) Support for the review of child safeguarding circulars by MoPSE. (iii) Cluster training of Guidance and Counselling teachers on these Safeguarding circulars.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
The following two changes to the logframe were made for Output 1 in April 2025:
- Output 1.1: Percentage and number of schools that receive SIGs by end of first term each year. 2025 milestone reduced from (830) 99% to (791) 99%” to reflect a reduced budget.
- Output 1.2: Number of MOPSE, school, and community personnel reached to improve understanding and support from inclusive access to ECD and quality education of CWDs. 2025 milestone reduced from 15,000 to 8,000 additional personnel to reflect reduced budget.
- Output 1.3: Number of people with improved access to clean energy as a result of ICF projects. The end date of this indicator was extended from June 2024 to December 2026 to reflect the Phase 2 extension of solarisation. Process milestones were agreed for the 2025 AR and a target of 24,180 beneficiaries by Dec 2026.
- Output 1.4: Number of institutions with improved access to clean energy as a result of ICF projects. This indicator was also extended from June 2024 to December 2026 with a process milestone agreed for 2025 AR and a target of 78 schools set by Dec 2026.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
The table below summarises responses to 2024 recommendations relevant to Output 1.
2024 Recommendation	Response
TEACH partners to investigate possible reasons for discrepancies by sex in key indicators, define challenges faced by boys and adjust workplans accordingly if possible (ongoing to June 2025).	No additional resources were available to pursue systematic research. However, the matter was discussed at the Steering Committee, where members expressed the opinion that previous donor support may have focused too much on supporting girls to the neglect of boys. Not Completed– Carry forward
UNICEF to work with MoPSE to ensure that key SIG verification recommendations are communicated with districts and schools and follow up on their implementation (by June 2025)	SIG reports have been shared with Ministry through the Grants Management Team – these include specific reports shared with individual schools. Met
UNICEF to expedite completion of certification ensuring that faults are rectified before approval of retention payment (by Oct 2024). FCDO to extend logframe indicators 1.3 & 1.4 for one year to track completion (by April 2025).	6 schools in Phase 1 have variations that still need to be certified. Logframe amendment completed Partially Completed – Carry forward
FCDO to procure evaluation of solarisation pilot and share findings (by Dec. 2025). UNICEF to document lessons and share in biannual reporting. Lessons to be incorporated in the design of ongoing and future solar investments.	FCDO procured an independent evaluation of Solar Phase 1 and has shared the report with government and partners. UNICEF documents and shares lessons in biannual reporting. Lessons are being incorporated into delivery of Solar Phase 2. Met

The following lessons and associated recommendations are made for the year ahead.
Lesson	2025 Recommendation
Negative trends are noted in gender equity in primary enrolment and enrolment of children with disabilities.	MoPSE and TEACH partners to seek reasons for these trends and (if possible) adjust programming to respond. (by Apr 2026)
Disbursal of SIG Regular did not meet expectation with 43 FCDO-funded schools not receiving in time.	Reasons for SIG payment failure to be investigated and rectified (by Dec 2025). Actions to include: (i) MoPSE to meet banks to stress need for pro-active communication of changes and request waiving of charges (ii) pre-validation of account details before transfer.
Zimbabwe remains without a School Financing Policy (SFP) as TEACH enters its final year of providing SIG to disadvantaged schools.	TEACH partners to work with MoPSE and GoZ to advocate for cabinet adoption and implementation of SFP (by Dec 2025).
Certification of solar installation in six Phase 1 schools remains outstanding and progress in Phase 2 is lagging behind planned timeframes.	UNICEF to complete outstanding certification for Phase 1 and expedite Phase 2 in line with originally proposed timeframes, and implement relevant lessons learnt (by Aug 2026).
Theft and vandalism of solar installations remains a matter of concern. There has been limited engagement from MoPSE in addressing the issue.	UNICEF and MOPSE to maintain risk mitigation activities (community mobilisation, investment in physical security, district monitoring) with greater engagement from MoPSE for sustainability.

Output Title	Increased capacity to teachers and administrators for quality teaching and learning
Output number:		2	Output Score:	A+
Impact weighting (%):		40%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1. Number of inspectors trained on e-inspection tools based on reformed inspection methodology (disaggregated by sex and disability)	305 inspectors (cumulative) participate in virtual reflection session on implementation progress of the revised inspection methodology	350 (114%) inspectors participated in virtual reflection sessions. (M: 249, F: 101, Disability: 5) / (A+)
2.4[8] Percentage and number of teachers and school heads trained in selected schools on improved pedagogy (including gender responsive and inclusive approaches)	90% of 74,558 which is 67,102 Teachers and heads. (disaggregated by sex and disability)	72,378 (97% of 74,558) teachers and heads (M:29,616; F:42,761; 5 with disability) reached through school-based reflection sessions. (A+)
2.5a Number of quality assurance visits done by inspectors and district officials during the reporting period facilitated by the provision of fuel	7,500 visits (non-cumulative):	8,050 visits (A+)
2.5b Percentage of schools inspected using the revised inspection methodology (Each year)	15% of the targeted 5,322 schools under TPD (=798 schools)	3,325 (62.5%) schools inspected (2,209 primary and 1,116 secondary). (A++)
2.7 Number of school leaders in selected schools trained on school leadership for learning (by sex and disability)	90% of 5322 (4790) school leaders coached and mentored to implement toolkit 1-3 through cluster and school-based sessions	5,698 (107%) school heads (F:1,614; M:4,084; Disability 152) participated in coaching sessions) (A+)
2.9. Number of Think Equal SEL Curriculum class sets (narrative picture books, lesson plans and pedagogical resources) printed, and delivered to target classes	2,815 ECD classrooms reached	3,284 classrooms reached (sets distributed) (A+)
2.10 Number of teachers trained to implement SEL in the classrooms using the TE curriculum	2,815 teachers trained to deliver the SEL programme in ECD classrooms	3,284 teachers trained to implement SEL. (F:3056; 228 M) (A+)
[8] Discontinuity in numbering of Output indicators reflects removal of previous logframe indicators and will serve as a reminder to also report on these in the Programme Completion Review (PCR).

Briefly describe the output’s activities and provide supporting narrative for the score
Output 2 focused on enhancing teaching quality and leadership through targeted professional development and systemic reforms. There were seven active indicators this year; one significantly exceeded expectations (A++), and six exceeded expectations (A+), therefore, this output scored “A+”. Output 2 combines activities implemented by three partners: EDT (2.1, 2.4, 2.5b, & 2.7), UNICEF (2.5a) and Think Equal (2.9 & 2.10).
2.1 Number of inspectors trained on e-inspection tools based on reformed inspection methodology (A+)
A total of 350 individual inspectors (M: 249; F: 101; 5 with disability) were trained through virtual reflection sessions on the Reformed Inspection Framework and e-inspection process, with strong buy-in and ownership from MoPSE head office and sub-national level. 100 Data Administrators (DAs) (70 male, 30 female) from all 72 districts were trained to manage and analyse e-inspection data (using the Kobo Collect platform). Training was delivered by the MoPSE core team of inspectors in partnership with EDT. 300 School Inspectors received refresher training on revised inspection methodology through virtual (Zoom) sessions. Topics were informed by inspection reports. 120 officials from 10 provinces also received onsite support to access inspection dashboards and share inspection reports with schools. Working Groups were established at provincial level to organise responsive capacity building for inspectors.

2.4 Percentage and number of teachers and school heads trained in selected schools on improved pedagogy (including gender responsive and inclusive approaches) (disaggregated by sex and disability) (A+)
72,378 teachers and heads (54,306 primary,18,072 secondary) participated in school-based reflection sessions (at least 3 sessions per term). This exceeded the milestone of 67,102. TPD sessions reflected on experience in applying new teaching methods. An FCDO field visit in Nyanga and Mutoko in month / year confirmed the functionality of school-based CPD in remote schools. A YouTube video describing TPD under TEACH may be accessed here.
Various TPD materials were provided during this period including on-boarding guidelines for new heads and teachers and coaching guides for System Leads. These materials are widely recognised by MoPSE as key resources supporting rollout of the Heritage-Based Curriculum. Literacy and numeracy materials are valued by teachers in supporting implementation of ‘diagnostic assessment’, which is an expectation of HBC that teachers find a challenging.
Learning Passport (hosted by UNICEF) continues to provide open online access to a wide range of materials, though research shows that only 307 teachers are making active use of it - particularly for literacy and numeracy courses. Challenges remain in ensuring access and full functionality of the platform. Advocacy and awareness efforts for Learning Passport should be maintained by MoPSE (see recommendations).
The Third Biannual Assessment Report[9] by EDT, measured progress in Output 2. It highlighted increased usage of TPD reference materials by teachers (from 47% to 93%). It also found that engagement with TEACH predicted higher pupil numeracy performance. Classroom observation over the life of the programme has seen the percentage of teachers rated in the ‘Embedding’ and ‘Proficient’ categories increase from 48% in 2023 to 80.8% in 2024. Educators using the TPD General Pedagogy series reported the following: (i) improved identification of non-readers using diagnostic tools. (ii) Effective use of catch-up materials, (iii) Use of adaptive methodologies and practical application of inclusive pedagogies. (iv) Challenging of gender stereotypes and use gender-neutral language and resources.
[9] 3rd Biannual Assessment Report.
With support from EDT, the MoPSE Human Resource Department established a Continuous Professional Development (CPD) Technical Working Group to coordinate and consolidate CPD activities and programmes nationwide. EDT was appointed as co-chair and with Terms of Reference (ToRs) approved by the Permanent Secretary (PS).
2.5a Number of quality assurance visits done by inspectors and district officials during the reporting period facilitated by the provision of fuel (A+)
UNICEF has administered provision of 95,836 litres of fuel to districts and provinces for monitoring. Records reflect that 8,050 visits were supported, which exceeded the target of 7,500. This support remains highly valued by districts and has allowed officials to visit and support remote and underperforming schools that would otherwise go unsupervised. There is a clear link between this indicator and the next one. AR field visits confirmed that a continued shortage of functional vehicles is hindering inspection and other essential district functions. Support for fuel provision will cease at the end of TEACH at which time MoPSE will need to find alternative funding from MoPSE operational budget or another funding stream.
2.5b Percentage of schools inspected using the revised inspection methodology (A++)
3,325 schools were inspected using the revised methodology, compared to a milestone of 798 schools. This significantly exceeded expectation. The e-inspection programme has made strong progress, with persuasive evidence of a step change in the frequency and qualify of school inspection. TEACH is credited with moving inspection beyond compliance, to focus on quality teaching and learning outcomes. Most provinces reported high coverage in areas such as curriculum implementation, compliance with regulations, and school improvement planning. 95.4% of the school heads reported taking action following inspection visits. Schools also reported delivering staff development workshops to address areas of weakness observed.
Heads report increased engagement in classroom monitoring and in taking action to enhance gender equity, pupil well-being, hygiene health and safety. This reflects a more inclusive view of educational quality. EDT has supported development and utilisation of visually appealing dashboard summaries to support use of data for decision making at all levels. Ministry values e-inspection as a key example of their implementation of the National ICT Policy which sets the expectation of improved service delivery through ‘e-governance’.
Despite progress, the school inspection system in Zimbabwe still faces challenges, including limited coverage due to capacity constraints, skills gap among provincial quality assurers, and inconsistent quality of inspection and reports. There are deficits in capacity to provide support on issues such as screening and remediation of special needs and the interpretation of operational circulars. There is also a significant shortage of ‘tools of the trade’ with a severe shortage of computers and vehicles at district level.
2.7 Number of school leaders in selected schools trained on school leadership for learning (A+)
5,698 (F:1614; M:4084) heads participated in coaching sessions supporting implementation of Leadership Toolkits 1-3 (attending at least one session per term). This exceeded the milestone of 4,790. Toolkit 1 focuses on Leadership of Quality Teaching; Toolkit 2 on Improving Quality through Community Engagement and Toolkit 3 on Preparing for Inspection.
The Third Biannual Assessment Report found the percentage of all school leaders, categorised as operating above the “developing stage”, had increased from 55% to 89% since baseline. Participants reported improvements in time management and task prioritisation. Examples included an increase focus on classroom practice, improved delegation of tasks and more time dedicated to remedial sessions with pupils. 94% of heads self-reported taking steps to improve inclusion: (i) improved infrastructure for accessibility (ii) improved special needs identification and support (iii) Community engagement and awareness. AR fieldwork also confirmed that TEACH is credited with a change in the role of the head teacher to a greater focus on instructional leadership.
The cluster structure, through which schools meet in groups of 8-10, has been important in bringing support to heads through peer coaching sessions. The third biannual assessment found that school leadership training at cluster level was strongly associated with improved understanding of school leadership concepts. However, this same study found variations in the quality of cluster activities and emphasised inefficiencies in effective dissemination (back at school) when only one or a few representatives attend events at cluster level.
Building on TEACH’s school leadership support, the MoPSE Human Resource Department engaged EDT to support development of the Zimbabwe School Leadership Competency Framework, which aims to: define the competencies, clarify roles and expectations and define pathways for professional growth.
Coordination between this output and the British Council’s instructional leadership programme has been maintained through regular communication.
Additional EDT Activities
In addition to activities summarised in the logframe indicators, EDT has also provided some additional responsive support to MoPSE. A good example is the technical assistance provided to the new MoPSE Gender Mainstreaming, Inclusivity and Wellness Department where EDT has supported development of a Safeguarding, Gender, Disability, and Social Inclusion (GEDSI) strategy (See recommendations).
2.9. Number of Think Equal SEL Curriculum class sets (picture books, lesson plans and pedagogical resources) printed, shipped and delivered to the target classes. (A+)
The Think Equal Social Emotional Learning (SEL) programme is a global education initiative designed to foster a more just, peaceful, and empathetic world by introducing SEL for well-being, psychosocial support, and social justice in early childhood education. The programme cultivates 25 essential social and emotional competencies through an evidence-based curriculum. It supports Early Childhood Development (ECD) teachers with practical tools to embed SEL into daily teaching, including 20 culturally diverse narrative picture books, structured lesson plans, and ready-to-use teaching resources. The programme aims to:
- Reduce negative behaviours such as stress, anger, aggression, and discrimination.
- Strengthen children’s emotional literacy, resilience goal-setting, critical thinking, perspective-taking and ability to self-regulate.
Foster prosocial attitudes through structured lessons in empathy, gender equality, self-esteem, peaceful conflict resolution, environmental stewardship and collaboration.
This year has seen a strong turn-around in the SEL component of TEACH (which scored ‘C’ in 2024). The 2024 AR reported significant delays. However, shortly after that report, MoPSE approved materials and granted access to ECD B Teachers in 18 districts. This breakthrough was achieved through protracted engagement of TEACH partners and FCDO with MoPSE officials (LEPS[9] and CDTS[10]).
[9] Learner Welfare, Psychological Services, and Special Needs Education (department)
[10] Curriculum Development and Technical Services
During 2024-25, implementation has proceeded rapidly with support from EDT and REPSSI[11]. MoPSE sees the initiative as well-aligned with HBC and central to its implementation in ECD. High level support was illustrated by Hon Minister Moyo making a publicised visit to an ECD classroom in Matabeleland South and an article about SEL published in the national press. A monitoring visit by the FCDO to 2 randomly selected rural schools in Nyanga found strong understanding and support of the initiative by parents, teachers and school leaders alike.
[11] Regional Psychosocial Support Initiatives
3,284 classrooms were provided with class sets of Think Equal SEL materials. This exceeded the revised milestone target of 2,815 ECD (A+). Materials are widely appreciated as being of high quality and engaging for pupils. They have been provided in English, as per MoPSE policy, however mediation of the materials into the mother tongue (which is the medium of instruction in ECD classrooms) has proved challenging for some teachers.
2.10 Number of teachers trained to implement SEL in the classrooms using the TE curriculum (A+)
3,284 ECD-B teachers were trained to implement SEL. This exceeded the revised milestone of 2,815, agreed in Apr 2025. Classroom observations in Nyanga by FCDO found strong initial implementation by teachers, who have been quick to grasp new teaching methods. Training has been delivered through the existing TPD cluster structures by master trainers identified by MoPSE from among their own staff. Feedback was received that some training took place in substandard venues and that the duration (1 day) was felt to be insufficient. However, teachers are now receiving monthly follow up visits by REPSSI which is providing support and feedback to embed implementation. The SEL project will continue to June 2026.
New classroom methodologies include the ‘mood-meter’, through which pupils express their mental state, and the ‘kindness garden’ through which prosocial behaviours are celebrated. Use of these methods is increasing interest in provision of psychosocial support by teachers to respond to psychological needs that these methods reveal (see Recommendations)
Partners are commended for their effort to embed SEL in existing MoPSE structures. Beyond the output targets, partners have augmented teacher training with a significant engagement with relevant MoPSE staff and significant efforts to engage parents in recipient schools. An additional 3,105 stakeholders were trained on SEL (see promotional video). Think Equal has completed a rigorous baseline survey against which the initial impact of the programme will be measured before June 2026 (see recommendations).
Describe any changes to this output during the past year, and any planned changes as a result of this review.
The following changes to the logframe were made with respect to Output 2.
Output 2.4: Number of educators trained in practical gender responsive and inclusive approaches to classroom teaching. This indicator was previously augmented by another similarly worded indicator 2.3b. “Percentage and number of teachers and school heads trained in selected schools on improved pedagogy”. The 2024 AR recommended that they be merged (without changing milestones and targets).
Output 2.9 Number of classrooms endowed with the Social and Emotional Learning (SEL) Think Equal curriculum. And. Output 2.10 Number of teachers trained to implement SEL in the classrooms using the TE curriculum. In Nov. 2023, when the AGA was signed, the estimated target number of classrooms and teachers was 4,350. The actual target number was subsequently reduced to 2,815, which was understood to be the total number of ECD-B classrooms in the three target Provinces.
The original contract between FCDO and EDT for delivery of TPD will expire 31st Oct 2025. Based on the momentum achieved and demand from MoPSE for continued support, FCDO has granted a 5-month cost-extension to EDT (through an AGA of £700,000) to: (i) Develop a national Foundational Learning Strategy. (ii) Enhanced implementation of the HBC. (iii) Expand district-led CPD systems to an additional 30 districts to achieve nationwide coverage. (iv) Refine school inspection processes to support data-driven decision making.
A three-month no-cost extension has also been approved the AGA with Think Equal (from 31st Mar to 30th June 2026, to allow completion of all planned activities, following a significantly delayed start in implementation.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
The 2024 AR recommendations for Output 2 were addressed as follows:
2024 Recommendation	Response
TEACH partners to work with MoPSE to understand reasons for low performance and implement plans to address it including strengthened support to remedial programmes for non-readers (by December 2024).	Ministry has acted to prioritise foundational learning. (i) LePS is standardising remediation test items to identify pupils with learning difficulties. (ii) THRASS[12] under GPE, and SEL under TEACH are supporting teachers to deliver lessons. (iii) National scale up of the School Readiness Initiative (SRI) aims to ensure pupils are supported be developmentally on track before grade 1. (iv) Early learning development standards support school based continuous assessment. Met – Maintain effort.
MoPSE and TEACH Partners to improve publicity for the existence and content of Learning Passport and provide support and training on its use to beneficiaries.	Advocacy strategy being finalized with MoPSE. A short You Tube video has been developed and shared with partners to assist in amplifying the platform. Partially Met – Carry forward
EDT to maintain effort to refine the e-inspection system and consider the request to develop an integrated Data Management System (DMS), with attention to the need to build MoPSE capacity to manage the system (by June 2025).	The DMS Technical Working Group (TWG) has been established and includes relevant departments in MoPSE. These provide tools for digitization of initiatives like Joint Monitoring Visits (JMV) and BEAM. The CPD TWG has also been formed, led by the Director of Education Services (DES) at provincial level, with responsibility for quality assuring inspection data. Data Administrators assigned to each district are responsible for data cleaning prior to analysis. Partially Met – Maintain effort
EDT to work with provinces and districts to support district performance review meetings to review data and inform service delivery decisions (by June 2025).	Provincial Working Groups provide sessions on data management, report writing, and feedback processes. These build inspectors' ability to support school leaders. The group fosters teamwork among district leads, while provinces monitor districts to ensure effective data use. Partially Met – Maintain effort
EDT to seek strategies to strengthen coaching and support of cluster chairpersons, including online options. And EDT to differentiate support to districts to increase focus on lowest performers (ongoing through 2024-25).	The CDP TWG analyses TPD performance data and targets underperforming districts for support. Some provinces form teams to assist underperforming districts. EDT and MoPSE, deliver CPD Online Webinars to share best practices and strategies. Met
EDT to increase its base of trained focal teachers (subject to budget). And advocate for continued localisation of teacher recruitment by districts. (by June 2025)	Through the CPD TWG, support is provided for the orientation of new school heads and teachers at both district and school levels, this responds to the high attrition rates observed. Support for the Human Resource Department (HRD) has started to develop a national onboarding guide. Met
TEACH partners to maintain regular engagement with related interventions to seek consistency and eliminate duplication of effort. (ongoing through year)	TEACH supported MoPSE to establish the CPD TWG at national and provincial levels to coordinate CPD activities. The TWG is also used to coordinate HBC implementation and support. EDT will continue supporting the CPD structure, with technical assistance - Met - Maintain effort.
Consolidate 2.3b and 2.4 into a single combined logframe indicator (maintaining the current milestone and target valued. (by March 2025)	Logframe amended. Met
TE/REPSSI to propose a revised way methodology and workplan for the SEL pilot (by December 2024).	SEL implementation (in 18 districts) started in Feb 2025 after securing clearance and approval from MoPSE. Met
[12] Teaching Handwriting, Reading and Spelling Skills

The following new lessons and associated recommendations are made for the year ahead.
Lesson	2025 Recommendation
A decrease was noted in P3 ZELA Literacy results from 78% in 2024 to 74.94% in 2025.	Reasons for decline to be sought and addressed. TEACH to maintain focus on foundational learning and remediation (by Mar 2026).
Usage of learning passport remains low and the potential of the platform in sharing materials has yet to be realised.	TEACH to maintain advocacy with MoPSE and teachers to increase use of Learning Passport. (by Jun 2026)
Uptake of e-inspection and other use of data in decision making is inhibited by lack of suitable ICT equipment and Provincial and District levels.	MoPSE and FCDO to invest in upgrading ICT infrastructure at provincial and district levels (subject to availability of funds) (by Aug 2026).
Development of the GEDSI and Safeguarding strategy is apparently not fully aligned with the Gender Analysis and Audit (funded by GPE) resulting in possible inconsistency or duplication of effort.	MoPSE, TEACH and GPE partners to align the two initiatives, and collaborate to ensure recommendations are implemented. (By Mar 2026)
Implementation of SEL classroom methodologies heighten teachers’ awareness of the emotional wellbeing of ECD pupils and reveal previously unrecognised difficulties	MoPSE and Think Equal to adapt programmes (to the extent possible with existing resources) to equip teachers to respond to issues of safeguarding and wellbeing and to refer cases where appropriate (by Mar 2026).
Funding is no longer available for an external evaluation of the SEL/Think Equal Pilot, yet valuable lessons still need to be captured.	Think Equal to strengthen internal evaluation of SEL pilot to ensure lessons are documented. FCDO to make resources available if possible (by Jun 2026)

Output Title	Education System Strengthened.
Output number:		3	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.4a Effective delivery of alignment of pre-service and in-service through the TPD Working Group	1. MoPSE shares the annual ZELA Report with the TPD Working Group / 2. MOPSE and MoHTEISTD[13] through the TPD Working group, meet quarterly to discuss pre and inservice TPD alignment.	Four quarterly meetings out of four (4) were done. The 2023 ZELA report was shared in 2024. The 2024 report was shared with the TPD Working Group members. (A)
3.5b Number of Research Studies Conducted with MoPSE Research and Innovation Department (RID)	One research study conducted/year on an agreed topic with MoPSE with MoPSE RID.	A Research study was conducted on the Extent of Uptake of Blended Teaching and Learning Models in Primary and Secondary Schools in Zimbabwe. Led by MoPSE RID, validation of the study findings with stakeholders done June 2025. (A)
[13] Ministry of Higher and Tertiary Education, Innovation, Science and Technology Development

Briefly describe the output’s activities and provide supporting narrative for the score
This output focuses on strengthening MOPSE’s systems. Five indicators, previously tracked under this output, were moved to GPE funding in 2023 and were removed from the logframe. The two remaining indicators met expectation (A). This output has therefore scored ‘A’.
3.4b Effective delivery of alignment of pre-service and in-service training through the TPD Working Group (A)
All expected activities supporting alignment of pre- and in-service teacher training were completed. The two ministries of education responsible for the human resources development, (MoPSE and MoHTEIST[14]) enhanced their collaboration through participation in the curriculum review and implementation of the HBC. Teacher Education Colleges were well represented during the HBC provincial rollout sessions. Collaboration and alignment were nurtured through the TPD Working Group which recommended the following: (i) Increased participation of teacher education colleges in in-service teacher training, (ii) more inter-ministerial collaboration at provincial level, (iii) co-development of teaching materials. However, the high turnover of working group members from MoHTEIST affected continuity.
[14] Ministry of Higher and Tertiary Education, Innovation, Science and Technology Development
Preservice student teachers on school practicum placements have benefited from school-based staff development through TEACH TPD. This ensures they graduate with the same skills as in-service teachers. TEACH TPD materials on general pedagogy, numeracy, and literacy were shared with teacher education colleges via flash drives and the learning passport.
3.5b Number of Research Studies Conducted with MoPSE RID (A)
The milestone target was to complete with one major research study in 2024-25 bringing the cumulative total to four. During the reporting period, a study entitled “Effectiveness of Blended Delivery Models in Primary and Secondary Schools in Zimbabwe: Impact on Teaching, Learning, and Continuous Professional Development of teachers[10]” This explored the implementation of IT-assisted learning in rural schools and was completed as collaboration between EDT and MoPSE Research and Innovation Department (RID)
[10] “Effectiveness of Blended Delivery Models in Primary and Secondary Schools in Zimbabwe: Impact on Teaching, Learning, and Continuous Professional Development of teachers”
Findings include:
- Face-to-face and WhatsApp were the most used and effective teaching methods. There is limited use of platforms like Akello Smart Learning and Learning Passport.
- Teachers value blended learning for allowing individualised support for pupils,
- Teachers also appreciated an improvement in access to downloaded learning resources.
- Blended strategies may partly mitigate the shortage of textbooks.
Use of blended methods has enhanced research skills in both pupils and teachers,
Recommendations include:
- MoPSE to prioritise awareness campaigns for parents on importance of blended learning.
- MoPSE to develop structured training plans for teachers on blended learning models and ICT integration.
- MoPSE to develop blended learning strategy to provide standards, goals, guidelines.
- MoPSE to strengthen partnerships with the private sector and development partners to mobilise resources for ICT equipment and infrastructure.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
The following amendments were made to the logframe in April 2024.
“National EMIS report for previous year published and distributed”. This indicator was removed from the logframe after the 2024 AR. Support for the activity transitioned to GPE.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
The 2024 AR recommendations for Output 2 were addressed as follows:
2024 Recommendation	Response
MoPSE to review critical path to production of EMIS and expedite publication the 2023 EMIS. MoPSE and UNICEF to expedite plans for 2023 ESPR and JSR as soon as EMIS is available.	EMIS 2023 and 2024 published. JSR is planned for 2025 year with the contracting process underway 2025 data will be out before the end of 2025. Met.
MOPSE, with support from UNICEF, to continue to advocate for the finalisation of the SFP. (Rolled over from 2023, by December 2024)	Partners maintained effort through GPE, ECG and EPSC. However, SFP still not complete. GPE Trigger payment for completion now extended to Dec 2025. Not Met - Carry forward.
EDT to investigate implementing school-based TPD to address pedagogic issues raised in the ECD research study (by June 2025)	The SEL component of TEACH supports school based TPD on pedagogic issues raised by the research study. EDT is supporting scale up of SRI and continuous assessment of ECD pupils. ECD teacher guides are planned to support TPD sessions, building on TEACH general pedagogy modules Met.

The following new lessons and associated recommendations are made for the year ahead.
Lesson	2025 Recommendation
The TPD Working Group has made specific recommendations for the improved alignment of pre-and-inservice teacher education.	MoPSE and TEACH partners to collaborate to ensure (i) Increased participation of teacher education colleges in in-service training, (ii) more ministerial collaboration at provincial level, and (iii) co-development of teaching materials. (iv) MoPSE to strengthen partnerships with private sector and partners to mobilise resources for ICT equipment and infrastructure (By June 2026)
TEACH-supported research on blended learning has revealed a critical lack of relevant IT skills among teachers.	MoPSE and TEACH partners to collaborate in designing a structured and costed training plan for teachers on blended learning and ICT integration (by Mar 2026).

Output Title	Supporting Adolescent Girls’ Education
Output number:		4	Output Score:	A+
Impact weighting (%):		20%	Weighting revised since last AR?	Yes (New output)

Indicator(s)	Milestone(s) for this review	Progress
4.1 % of girls in Accelerated Teaching and Learning (ATL) demonstrating improved literacy and numeracy skills	Literacy: 67% / Numeracy: 69%	Literacy MPA: 92,8%; EPA[15]: 99,3%, Numeracy MPA: 91,3%; EPA: 99,5% (A++)
4.2 Number of girls in Integrated Skills Outreach Programme trained on financial literacy skills	N=1883. That is 60% of the eligible adolescent girls	62% of 3,530 (2,189) learners trained and demonstrating financial literacy skills during assessments. (A)
4.3 Number of girls trained on Sexual and Reproductive Health and Rights (SRHR).	60% of Enrolled Learners	82% of the enrolled 5,423 learners have received SRHR education through the Champions of Girls Education. (A+)
[15] Mid-Term Programme Assessment (MPA); End-Term of Programme Assessment (EPA)

Briefly describe the output’s activities and provide supporting narrative for the score
The Supporting Adolescent Girls’ Education (SAGE) project, delivered by Plan International supports 5,657 out-of-school adolescent girls (and 1,418 boys), through community-based learning hubs in 11 districts in Harare, Matabeleland and Manicaland. Participants (aged 10-19) are drawn from several intersecting disadvantaged categories including: married girls, young mothers, Apostolic[16] girls, girls with disability, minority ethnic groups, girls who have never been to school and girls in labour. Project activities are categorised into 4 components:
[16] The Apostolic Church community sometimes has a low rate of female participation in education.
- Accelerated Teaching and Learning (ATL) - enhancing literacy and numeracy.
- Technical & Vocational Skills Training (TVET) develops practical skills for livelihoods.
- Champions of Girls’ Education (CoGE) empowers girls and boys with life skills.
- Safeguarding ensuring the protection and well-being of participants.
The number of participants in each component is as follows:
Programme Component	Girls	Boys	Total
Accelerated Teaching and Learning (ATL)	5,657	0	5,657
Integrated Skills Outreach Programme (ISOP)	3,104	0	3,104
Technical and Vocational Education & Training (TVET)	426	0	426
Champions of Girls Education	5,423	1,418	6,841

All girls start by attending ATL and then progress to other components. The figure of 5,657 enrolled in ATL exceeds the original target of 5,027. Girls then choose a transition pathway. Some girls attend ATL, CoGE, and then ISOP or TVET, while others (normally the younger) attended ATL, CoGE, and then return to school. CoGE is open to both boys and girls.
Output 4 has three indicators, of which, one significantly exceeded expectation (A++), one exceeded expectation (A+) and one met expectations (A), This resulted in an overall ‘A+’ score. SAGE (Phase 2) began in October 2023 and will run until March 2026. It is now entering its final stages with an emphasis on completing the workplan and promoting sustainability.
4.1 Percentage of girls in Accelerated Teaching and Learning (ATL) demonstrating improved literacy and numeracy skills (A++)
ATL provides a necessary foundation of literacy and numeracy, upon which other aspects of SAGE are built. Indicator 4.1 tracks improvement in literacy and numeracy skills of the 5,657 ATL participants. The 2025 milestone, set at the start of the project, for the percentage of learners demonstrating improvement on Plan assessment tools was 67% for Literacy and 69% for numeracy. This has been greatly exceeded, with 92.8% demonstrating literacy progress and 91.3% achieving numeracy progress in during Mid-Term Progress Assessments (MPA) for Cohort 2. End-Term Progress Assessments (EPA) for Cohort 1 revealed even stronger results, with 99.3% advancing in literacy and 99.5% in numeracy. Given this stronger-than-expected performance, it is recommended that SAGE increases its ambition for the project end target (currently Literacy: 70% and Numeracy: 72%)[17].
[17] Also see discussion of VfM indicators for quantitative description of test performance.
Plan identify the following factors as contributing to the strong performance of ATL: (i) Ongoing capacity building of Community Educators to enhance teaching effectiveness, (ii) Strategic simplification of learning modules to promote comprehension, (iii) The dedication and commitment of learners.
ATL implementation is supported through a range of complementary activities in including:
- Provision of essential stationery, modules, and session guides
- Administration of learner progress assessments
- Professional development of Community Educators (CEs) and NFE Mentors including session observations and communities of reflective practice sessions,
- Reflection meetings with school heads and NFE Mentors,
- Disability assessments and provision of assistive devices, large font modules for learners with low vision and follow-up monitoring,
4.2 Number of girls in Integrated Skills Outreach Programme (ISOP) trained on financial literacy skills (A)
ISOP and TVET are two SAGE youth economic empowerment initiatives. ISOP provides community-based training to 3,104 girls (aged 15 and over) across the following trades: hairdressing (1,047), baking (883), dressmaking (697), poultry (142), blacksmithing (58), bead making (45), upholstery (27), detergents (17), building (11), carpentry (7), welding (4) & fence making (3). This is delivered through local ‘Mastercrafts’ people who pass on skills through which it is possible to make a local livelihood. Mastercrafts are provided with training and support by Plan including on inclusive training methods. Popular options like hairdressing are perceived as combining good earning potential with low start-up costs. To support effective learning, all participants are provided with essential ISOP materials and equipment tailored to their respective trades. Maintaining regular attendance is frequently a challenge in ISOP due to competing family and income generation priorities.
TVET is delivered through a one-month residential training course at a vocational training college, followed by a 3-month industrial attachment (for girls aged 16-22). It provides training to 426 girls across the following trades (many stereotypically male dominated): welding (166), motor mechanics (96), carpentry (82), solar (39), building (31), electric (8), leatherwork (2), sheet metal (1), engineering (1). Popular options such as welding are viewed as having high earning potential. To foster inclusivity, the Christian Blind Mission (CBM) led disability-friendly modifications to both infrastructure and training delivery across the colleges. Colleges have also been required to improve their safeguarding protocols. Lessons from the first cohort of learners led to adaptations in the TVET programme including increased coverage of costs of participation.
An impressive 75% of learners have successfully secured work placements within their districts. These industrial attachments have been supervised by TVET college lecturers. 95% of these took place in informal workplaces, mirroring the broader economy.
Financial literacy training is also a core component of both ISOP and TVET streams of training. This includes skills such as savings, budgeting, accounting and entrepreneurship. Its completion has been set as indicator 4.2. The milestone of 60% of the target enrolment of 3,138 completing was set for 2025. Plan International reports that 62% of the 3,530 girls enrolled in ISOP and TVET have successfully completed and are able to demonstrate financial literacy skills. Indicator 4.2 therefore scores ‘A’.
’When I first walked into the workshop, all eyes were on me – the only girl. Some doubted I could handle the tools, the heat, or the heavy lifting. But TVET training didn't just teach me welding it forged my confidence now I am able to do what was previously regarded as “males only trade”. I hope to make a living through this support I received from Plan International”. (Chipo a 20-year-old girl on industrial attachment).
4.3 Number of girls trained on Sexual and Reproductive Health and Rights (SRHR). (A+)
5,432 girls have enrolled in Champion of Girls Education (CoGE) and 1,418 boys. 4,625 girls have completed at least 15 sessions. The programme consists of 25 session which aim to foster self-awareness, self-confidence, and knowledge of sexual and reproductive health rights (SRHR), while addressing harmful social norms and promoting equitable relationships. Training also includes advice on response and referral pathways. The 2025 milestone was that 60% of enrolled learners should have received SRHR education. This milestone has been exceeded with 82% of enrolled learners reported as participating (A+). During this year, SAGE partners have reviewed and simplified CoGE materials and translated them into three local languages (Shona, Ndebele and Kalanga). A total of 450 booklets were printed and distributed with positive feedback received from users.
SAGE has trained 250 peer leaders (M: 79, F: 181) to deliver CoGE training sessions through annual sessions. 71 guidance and counselling teachers were also trained. Training refreshed understanding of roles, strengthened SRHR content delivery, and helped identify community stakeholders including health workers for referral and support. Community engagement initiatives included 63 men’s clubs, 63 women’s clubs, and 63 intergenerational dialogues. During the year, SAGE partners conducted CoGE lesson observations, with supportive feedback across a range of criteria including learner participation and inclusion. The evaluation of quality of lessons delivered by Community facilitators fell into the following categories: Excellent: 15%, Good: 65% Average: 20%.
In addition to the girls, 1,418 boys have also participated separately in CoGE sessions. This involvement enables boys to challenge stereotypes and fosters the development of equitable and safe relationships. By engaging both girls and boys in SRHR education, the programme aims to promote healthy relationships and informed decision-making.
Additional Activities
In addition to activities captured in the logframe, SAGE has made significant additional achievements including the following:
- SAGE has provided technical and financial support to MoPSE to revise the national Non-Formal Education (NFE) Policy, providing a framework to strengthen the national NFE systems and enhance quality and equitable access. Supporting adoption of this policy is a key aim for the remaining period of SAGE up to Mar 2025 to ensure its lasting legacy.
- SAGE has engaged in advocacy for the adoption of costing for NFE learners in the School Finance Policy currently being developed by MoPSE.
- SAGE has collaborated with EDT to revise e-inspection manuals for use in NFE classrooms and to meet the MoPSE commitments for prevention of violence NFE
- SAGE has engaged with MoPSE M&E department to ensure that the annual school survey collects relevant and accurate information about NFE implementation.
- SAGE is developing a mobile app to support teachers to support children with disabilities.
- SAGE has supported 75 hubs in 11 districts with community engagement to enhance governance through Hub Development Committees.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
The 2024 AR recommendations for Output 4 were addressed as follows:
2024 Recommendation	Response
Plan to facilitate discussion at training sessions of strategies to facilitate attendance including adjusting time schedules and using other modalities such as door-to-door and small group sessions (used curing Covid) (by Dec. 2024)	Adjustments to meeting schedules made in 15 hubs. SAGE successfully lobbied for school feeding support in 17 hubs, leading to improved attendance. Migrant girls were supported with telephone-based learning. Small group sessions established in 7 Bulilima hubs where the safety of girls travelling to hubs was affected by wild elephants. Met.
Plan to strengthen training and support of Community Educators and Peer Educators to build capacity in differentiation and remediation with special attention to pupils with special needs. Plan to collaborate with EDT on remediation as it is a common theme in both interventions (by March 2025)	Plan enhanced capacity of volunteers to engaging learners with disabilities and adapt content to diverse learning levels. SAGE has conducted two Disability Inclusion trainings, attended by all volunteers. A mobile application is being developed, offering versatile teaching strategies for handling learners with disabilities. Met – Maintain effort
Plan to investigate and explain reasons for the low enrolment of Phase 1 beneficiaries in Phase 2 and focus on efficient delivery of ATL to ensure full uptake of ISOP & TVET places (by April 2025)	A response strategy was developed to address key barriers identified as reasons for the low TVET intake, including raising awareness among parents, support in obtaining Identity Documents, and decentralising training. As a result, enrolment increased. Met
Swap the numbering of Output indicators 4.1 and 4.2 in the next logframe iteration.	Logframe amendment completed. Met

The following new lessons and associated recommendations are made for the year ahead.
Lesson	2025 Recommendation
SAGE has significantly exceeded milestones for learning outcomes under ATL– suggesting that existing targets could be more ambitious.	Plan to review and update Output and VFM indicator targets to increase level of ambition for end of the project (by Dec 2026)
SAGE has experienced significant demand from communities to support NFE for boys. Key education indicators now suggest that boys are now be experiencing significant challenges compared to girls.	Plan International to pilot providing access to the SAGE TVET model to a cohort of adolescent boys. (by Mar 2026)
Plan International has successful supported MoPSE to develop a costed draft NFE Policy.	MoPSE and Plan International to support submission and adoption by GoZ. (by Mar 2026)
A comprehensive review of NFE materials has not yet been conducted to ensure full alignment with HBC.	SAGE and MoPSE to review NFE materials to ensure full alignment with HBC (by Mar 2026)

## D: VALUE FOR MONEY
Key cost drivers and performance
The overall Value for Money (VfM) proposition for TEACH in the Business Case was that improving access and quality of education, especially for girls and disadvantaged children, will deliver both social and economic benefits. VfM in TEACH is tracked for indicators of economy, efficiency, effectiveness, and equity. 17 VfM indicators were monitored during the 2024-25 review period, shared between implementing partners. 14 indicators are ‘On Track’, 2 are ‘Off Track’ and there is no new data for one.
VfM performance compared to the original VfM proposition in the business case
Economy (inputs of appropriate quality at the right price)
There are 4 economy indicators being tracked in the TEACH Logframe
- Average cost of a school visit. Through UNICEF, TEACH provides fuel to district officials to conduct school visits for inspections, monitoring, and supervision (Output 2.5a). In 2024-25, the average cost per visit was US$18.24, down from $25 reported in 2024 and significantly better than the 2025 milestone of $24.23. Fieldwork confirms that provision of fuel contributed to improved school supervision. The price of fuel remained stable and fell slightly, with diesel fluctuating between $1,50 and $1.63 per litre ($1.58 to $1.79 in 2023-4) and petrol between $1.54 to $1.60 per litre ($1.57 to $1.65 in 2024-5)[11]. (On track).
  [11] www.zera.co.zw
- Average cost of professional development per educator per cycle. TEACH TPD conducted training sessions at a cost of US$14.96 per educator per cycle which is a 25% reduction on the figure of US$20 reported in 2024. This also compares favourably with the milestone set of US $21. Cost controls have helped TEACH to exceed its target numbers for training. Use of mobile money helps manage fiduciary risk of reimbursing participants. (On Track)
Average cost of catch-up (T&L) materials. No materials purchased 2024-25. (No data).
Cost per percentage point improvement in average literacy and numeracy scores for adolescent out-of-school girls. Plan report a figure of £7,634. This is calculated as: (i) Total ATL component budget July 2024 to June 2025 (£207,653) – Divided by (ii) average increase in literacy and numeracy scores (27%). (On Track).
The US$ unit costs of economy indicators remained stable. TEACH also continues to protect the buying power of SIGs by ensuring schools use US$ ‘Nostro’ accounts to manage funds. In June 2024 the annual rate of inflation in US$ was 3.2% and decreasing, while local currency annual inflation rate of in ZiG remains very high at 95.8%. No incidence is noted where the price or quality of inputs has compromised delivery.
The Phase 1 investment of £1.8m in solarisation for 150 schools was delivered by UNICEF within budget (£12,000 per school). However, external evaluation noted some compromise in quality and length of warranty. UNICEF has proposed higher specification (at least 10 KVA) with enhanced security features leading to a significantly higher unit cost for Phase 2 installations (£31,000).
Efficiency (Converting inputs into outputs)
The overall Output score of ‘A+’ reported in this AR indicates that TEACH is meeting expectations in converting inputs into outputs. The following four efficiency indicators are being tracked, three of which are ‘On Track’.
% of teachers participating in professional development activities over the past two years. The % of teachers participating in cluster training was 84.6% (of 1,619 teachers), which slightly exceeds the figure of 83.2% recorded in 2024 and the milestone set of 72%. This reflects continued high demand for TPD and efficiency of the delivery model. (On Track)
- National EMIS report for previous year published and distributed. The milestone set was that the 2023 report should be available. Both 2023 and 2024 reports were received by FCDO during the reporting period (Aug 24 and Dec 24 respectively). Production of the 2025 report is reportedly behind schedule. While this output is now supported by GPE funding, it is still being tracked as an indicator of overall sector efficiency. (On Track)
- Form 4 Dropout Rates. This indicator relates to efficiency of the education system as a whole. The F4 dropout rate has improved from 13.2% (M:12.0%, F:14.3%;) in 2023 to T:11.9% (M:11.33% F:12.49% in 2024). This exceeds the target set of 14%. This VfM indicator also doubles as Outcome indicator 3 in the logframe (targets to be aligned in forthcoming logframe amendment). The improvement is surprising, given that much of 2024 coincided with a period of drought and economic hardship. (On Track)
- Number of Learners achieving the benchmark learning results (Grade 5 level of learning) with the available cost. (SAGE). The analysis of literacy and numeracy scores in the ATL programme reveals average performance of 60.1%. This figure averages the average literacy score of 40% and the average numeracy score of 51.5%. Out of 3,824 learners assessed, 2,300 achieved Grade 5 proficiency. The project is on course to achieve the 75% target by the End Progress Assessment. (On Track)
Effectiveness (are outputs having the intended outcomes?):
All five Effectiveness Indicators are On Track. However, Programme performance is mixed at the Outcome level of the logframe, with only two out of five indicators on track.
% of Grade 7 pass rate: There was a 4% improvement in G7 pass-rate from 45.1% in 2023 to 49.0% in 2024. However, a performance gap is opening up, with girls now significantly outperforming boys (M: 44.0%, F:53.7%), which warrants further investigation. (On Track)
- % of Form 4 pass rate: There has been a 3.0% improvement, with gender equity – from 30.1% (M:29.4%; F:30.8%) in 2023 to 33.2% (M: 32.7%; F 33.5% F) in 2024. (On Track)
- Percentage of P3 and Satellite regular SIG supported schools with at least 75% retention rate up to Gr 7. The 2024 figure of 56% exceeds the milestone set (55%) and continues and improving trend (On Track).
- % of Teachers above the 'Developing' stage of the teacher competency continuum. 81% of teachers observed are at or above ‘Developing’ Stage, compared to a target milestone of 55% and a baseline of 48%. Persuasive evidence is emerging of the positive influence of TEACH on teacher’s competence in classroom practice. (On Track).
- Improvement in the average literacy and numeracy scores for adolescents out-of-school girls. (SAGE). Across 3,824 girls assessed the Average Literacy Score was 49.6% and the Average Numeracy Score was 62.1%. These figures compare well with the baseline valued of 30.5% for Literacy and 26.6% for Numeracy. (On Track)
Equity (spending fairly)
Promoting equity in education remains central to TEACH. Equity indicators are on track.
- GPI Index for enrolment in Forms 1-4[18] - remains within the expected range of 0.95 to 1.05. with a figure of 1.00. (On Track).
  [18] Form 1-4 Gross Enrolment Ratio (GER) for girls divided by Form 1-4 GER for boys
- Number of marginalised children provided access to functional schools (P3/Satellite). This indicator measures the number of children enrolled in schools receiving SIG and also serves as Outcome Indicator 2. The milestone of 265,951 learners (F 131,125) was not met. The Actual figure of 225,654 (F: 112,334) is 40,297 less than the milestone. The reasons are discussed in more detail under Output indicator 1.1. (Off Track).
- Percentage and number of educators trained in practical gender responsive and inclusive approaches to classroom teaching (sex and disability). 72,278 (M:29,616; F:42,761;) (97% of targeted teachers) have been trained against a target of 67,102 (90%) (On Track).
Percentage average improvement of numeracy and literacy scores per each subgroup (SAGE). The following improvements were recorded for test scores of each sub-group of SAGE participants (On-Track).
Group	Literacy baseline	Numeracy baseline	Literacy 2025	Numeracy 2025
Married girls	23.9	21.2	52.9	34.6
Young mothers	18.9	19.7	52.9	34.2
Apostolic girls	18.6	19.1	49.9	32.7
Girls with Disabilities	20.0	20.3	44.5	28.5
Girls from ethnic minorities	18.8	20.6	42.3	27.2
Girls never been to school	21.1	22.7	35.6	24.4
Girls engaged in labour	23.3	23.7	41.1	27.9

Overall Cost Effectiveness (Overall Impact on UK Foreign Policy Objectives)
With strong performance in supporting equitable access to quality education, TEACH contributes to delivery of UK’s international development priorities of reducing poverty and contributing to SDG 4, while building human capital necessary for inclusive economic growth.
Assessment of whether the programme continues to represent value for money
Based on (i) the relatively strong performance of TEACH on indicators of education access and attainment, (ii) the continued relevance of the theory of theory of change, and (iii) Good performance on VfM indicators, there is clear evidence that the project represents Value for Money and should continue.

E: RISK
Overview of risk management
The overall programme risk rating is Moderate. This assessment is based on the continued robust performance across components in a challenging operating environment and reflects the net rating of most risks currently tracked. The programme is delivered within FCDO Zimbabwe’s risk appetite and in line with its funding policy. Risk appetite describes the extent of the risks that FCDO are willing to take to achieve objectives, across the range of risk categories. For TEACH risk appetite is as follows:
Category	Appetite
Policy and Programme Delivery	Receptive
People	Cautious
Safeguarding	Cautious
Financial and Fiduciary	Receptive
Strategy and Context	Receptive
Reputational	Cautious
Public Service and Delivery Operations	Minimal

Fourteen key risks are currently identified and actively managed through the FCDO Aid Management Platform (AMP), across all categories. They are reviewed at least quarterly and managed proactively and proportionately. All TEACH partners also maintain a more detailed joint risk register tracking risks that might impact implementation and results. This is updated quarterly by risk leads. Key risks are flagged and discussed in monthly meetings of the TEACH Implementation Committee. Risk is also a standing agenda item in monthly progress meetings between FCDO and each partner.
The management of safeguarding risks remains at the core of delivery, because partners regularly access school and NFE hubs. The safeguarding policies and procedures of all partners are monitored by FCDO and are robust, including measures such as the vetting of staff, regular training of staff, and reporting pathways. FCDO due diligence is up to date for all partners, with full refresh completed for EDT in 2025, prior to the signing of a new Accountable Grant Arrangement (AGA) to extend the end date of their work to March 2026.
Key programme risks and mitigation actions.
Over the lifespan of TEACH new risks have emerged while others have been removed from the register that are no longer relevant to the environment or stage in the project cycle. The following table summarises six selected key risks currently receiving significant attention.
Category	Risk.	Mitigating Actions
Strategy and Context	Private Voluntary Organisation Act of 2025 introduces additional compliance requirements for TEACH partners that creates an additional reporting workload and constrains efficient and flexible operations.	(i) Partner organisations prioritise registration with GoZ under the PVO Act. (ii) Partners proactively share experience and advice in navigating compliance processes. (iii) Partners ensure alignment of plans with policies and priorities of GoZ. (iv) Partners maintain current MoUs in districts where they operate. (Residual Risk Moderate)
Strategy and Context	GoZ underfunding of education and poor budget implementation constrains GoZ ability to sustain and scale up TEACH investments and impacts on access and learning outcomes. Non- adoption of SFP leads to loss of additional GPE resources.	(i) Work with MoPSE to build case for investment in GoZ budget process. (ii) Support SFP development and engagement with Parliamentary Portfolio Committee (PPC). (iii) Conduct annual sector budget analysis and use findings for advocacy. (iv) Maintain targeted support for SIG to protect basic functionality of the poorest schools. (Residual Risk Major)
People	Reduced FCDO funding and the approaching end date of TEACH leads to loss of key staff (FCDO and Partners). Resulting gaps in capacity negatively impact on institutional memory, efficiency and effectiveness in the closing stages of TEACH.	(i) Partners ensure rigorous documentation of roles for ease of handover. (ii) Partners identify pool of available short-term consultants to cover possible gaps. (iii) Partners explore providing incentives for completion of contractual term by staff. (iv) project management prioritises transparent communication and provides support to manage anxiety and maintain focus. (Residual Risk Moderate)
Safeguarding	Partners may not have mechanisms to prevent and respond on safeguarding concerns leading harm to children, compromised delivery and reputational damage.	(i) FCDO maintains rigorous due diligence of partners to ensure robust policy and practice. (ii) FCDO monitors implementation of policies including regular training and reporting pathways (iii) FCDO engages partners to share best practice on partner engagement days. (iv) Engage with MoPSE to build capacity and strengthen safeguarding risk management. (v) Work with school leaders and districts to strengthen school safety and monitoring safeguarding in school. (Residual Risk Moderate)
Financial and Fiduciary	Lack of financial capacity or fraudulent intent in beneficiary schools leads to misuse of SIG funds. The limited scope of audit (10% of schools) leads to under-detection of fraud	(i) SIG transferred directly from UNICEF to dedicated $US dollar school SIG accounts (ii) All Heads receive financial management training and manual (iii) Utilisation criteria shared annually for eligible expenditure (iv) All receiving schools have School Development Plan to guide expenditure - reviewed and approved by Districts. (v) 10% annual random sample of schools selected for external audit. (vi) UNICEF conducts additional rapid assessment of 50 schools. (vii) Findings from audit consolidated in a report annually shared back to Districts and schools. (viii) Use monitored during inspection JMVs (ix) Where fraud is detected, cases investigated, funds are recovered, and disciplinary actions taken. (residual risk Major)
Reputational	Theft, abuse or underutilisation of solar installations diminishes the programme impact leading to reputational damage for FCDO and its partners. These are high value assets in remote schools with limited security controls.	(i) Community engagement to foster ownership and clarify roles in security and maintenance. (ii) provide alarm pads, sirens and other security devises. (iii) Increased unit cost for Phase 2 improves inbuilt security. (iv) Contractors provide clear guidance to users in operating manual. (v) Districts and partners monitor use, (Residual Risk Moderate).

Update on Partnership Principles
The Partnership principles for FCDO Zimbabwe are regularly reviewed. There has been no change in our assessment of Zimbabwe’s performance against partnership principles since the last annual review. FCDO’s contribution to the TEACH programme remains in line with policy of no UK money used to directly fund the GoZ (no budget support or financial aid), with an exception, as agreed by Ministers, to allow the SIGs to be provided directly to schools.
F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
Summarise the performance of partners and FCDO, notably on commercial and financial issues.
FCDO actively manages programme delivery, commercial and financial management for all components. All implementing partners provide good quality financial forecasting and financial and narrative reports, which the FCDO team reviews closely. All partners have provided up-to-date mapping of their delivery chains, including downstream partners. The implementation of due diligence recommendations for newer partners (Plan and Think Equal) are monitored. The FCDO programme team have provided induction and refresher training to all partners, through partner days, to reinforce FCDO compliance requirements. FCDO holds monthly meetings with each partner organisation, to review progress in workplan implementation, finances and emerging risks. TEACH has an active Implementation Committee, in which all partners meet every six weeks, to review progress and improve coordination.
Two additional tiers of sector governance meet quarterly: (i) The Education Partnerships Steering Committee (EPSC) is chaired by the MOPSE Permanent Secretary (PS). Membership includes MoPSE senior management, implementing partners and donor partners across the Zimbabwean education sector. This committee ensures programmes are well coordinated in support of MoPSE priorities and the Education Sector Strategic Plan (ESSP). (ii) The Education Coordination Group (ECG) also meets quarterly, chaired by the Honourable Minister and provides a forum for development partners to engage with MoPSE on matters of education policy and strategy.
UNICEF: Improved Equitable Access and Solarisation (Components 101 and 105)
The partnership is governed by the Standard Administrative Arrangement, which was amended in Nov 2024, to make available an additional sum of £2.4m for Phase 2 solarisation and to extend the end date until Dec 2026. UNICEF provides FCDO with biannual narrative reports in accordance the centrally managed global Framework Arrangement. Monthly partnership meetings are held to review progress against the workplan and emerging risks. UNICEF continues to provide quarterly reports on a limited number of fraud cases arising from previous SIG verification exercises and vandalism or theft of solar installations.
Education Development Trust (EDT): Teach Professional Development (Component 102)
FCDO has a contract with EDT for the period 25th Aug 2021 to 31st Oct 2025. 10% of each payment is dependent upon Key Performance Indictors (KPIs), all of which were met during this year. EDT provide FCDO with a high standard of reporting. They have shown agility and responsiveness in refining implementation plans to incorporate evolving MoPSE priorities (e.g. HBC implementation). The regular monthly meetings are well planned, with a shared agenda, and minutes provided well in advance. In July 2025, FCDO approved a new AGA of £700,000 to extend EDT’s work by 5 months from Nov 2025 to Mar 2026, with additional activities including: (i) Development of a national foundational learning strategy (ii) Support for HBC implementation, (iii) Expansion of district-led CPD systems to an additional 30 districts to achieve nationwide coverage, (iv) Refinement of school inspection processes.
Plan International: Supporting Adolescent Girls Education (Component 403)
Plan has an AGA for £5,151,710 for the period Oct 2023 to Mar 2026. They have made strong progress during this reporting period. The Plan team maintain good relations with GoZ counterparts and other TEACH partners. Plan provides timely, well-considered narrative and financial reports. Monthly meetings are well planned, with an agenda shared in advance together with presentation that includes updates on action points from previous meetings.
Think Equal: Reducing Violence in Schools and Communities (Component 404)
This AGA for £1,500,000 supports SEL and ending violence in schools. It started in Nov 2023. The end date has been extended by three months from Mar 2026 to Jun 2026, to allow full implementation following a delayed start. This component has performed well during this reporting period, with Think Equal working in closely with EDT and REPSI. Think Equal have maintained good quality quarterly financial and narrative reporting.
Financial Management
The budgets for the current (25/26) and previous (24/25) financial years are below.
Component	Partner	Actual 24/25	Budget 25/26
300252-101	UNICEF	£1,799,088	£2,926,488
300252-105	UNICEF	£2,246164	£153836
300252-102 & 405	EDT	£2,676,935	£1,986,554
300252-103	Evaluation	£71,662	£295,000
300252-403	Plan International	£2,343,423	£1,753,802
300252-404	Think Equal	£202,575	£839,575
Total		£9,339,977	£7,955,255

Partners are responsible for day-to-day financial management by providing monthly reports to FCDO for review and approval. TEACH is generally spending as planned, with quarterly variances within the acceptable range of 5% against planned budget throughout the programme. When in-month slippages or overspend occurs, partners provide timely submissions with justification. Upon receipt of payment requests, the FCDO programme team analyses these to ensure compliance with programme delivery rules, and (for EDT) ensure KPIs have been met. Each partner has provided audited statements the dates of which are listed at the end of Section G below. UNICEF’s certified financial statements have also been received in good order.
Asset monitoring and control
At the closure of Girls’ Education Challenge (GEC), FCDO ensured that SAGE Phase 1 assets were returned to Plan for continued use in TEACH. Assets include laptops, vehicles and motorbikes. Plan inventory was submitted as part of its annual reporting in August 2025. An asset check was also conducted for EDT as part of the AR compliance checks. EDT has an asset inventory in place that was confirmed by programme team in August 2025. The register has a comprehensive record of items such as motorbikes, two vehicles, desks, chairs, laptops, mobile phones, tablets, monitors, solar unit among others. The assets are in good condition, well coded with serial numbers and labelled according to FCDO standards. The coding matches the record in the inventory. All items were accounted for.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]
Monitoring and Evaluation
During this annual review period FCDO has conducted four field monitoring visits to the following districts: Mutasa (2-days), Marondera (1 day) Chikomba (1-day), and Nyanga (2 days). All visits were undertaken jointly with senior MoPSE officials to facilitate joint reflection. The first two visits place in the context of the regular termly Joint Monitoring Visits (JMVs) in which, every school term, EPSC members visit randomly selected schools in all 10 Provinces using a jointly agreed monitoring instrument. These visits are followed up by a reflection and feedback meeting at MoPSE headquarters. JMV visits enable follow up on a wide range of topics of current concern e.g. HBC implementation, teacher retention, the prevalence of non-readers and the management of SIG.
This 2025 TEACH AR was conducted in-house by the FCDO education team (July-October 2025), led by the SRO. Terms of reference and a timeline were developed in June with stakeholder questionnaires and shared with MoPSE and partners. Fieldwork was conducted in Nyanga in July 2025. This district was chosen because it has a number of remote rural schools where solarisation and SEL are being implemented in the same schools. Both these components had been rated as underperforming (B or C) in the previous 2024 AR. Stakeholder feedback was sought across all active outputs, through a mixture of direct observation, interview and focus group discussion. Fieldwork was complemented with a series of conversations with MoPSE officials involved in implementation. The review was quality assured by the FCDO Zimbabwe Human Development and Inclusion Team leader before approval by the Development Director.
Evidence
EMIS 2024 was disseminated in December 2024 with preliminary data informing the 2024 Joint Sector Review meeting in Mutare in late November. EMIS 2024 has informed discussion in this AR Report. Matters of concern, already raised, include the apparent decline in enrolment of CwDs and the widening gender performance gap with girls now significantly out-performing boys across a number of key indicators of both enrolment and learning outcomes.
In the past year, EDT has continued to build the evidence base of TEACH through production of Biannual Assessment Reports (latest July 2024) which collates school monitoring data and quantifies improvements in observed teacher and head teacher competence (reported above).
EDT also supported the research study entitled “Effectiveness of Blended Delivery Models in Primary and Secondary Schools in Zimbabwe: Impact on Teaching, Learning, and Continuous Professional Development of teachers[12]”. Findings are summarised above under Output. 3.5b.
[12] “Effectiveness of Blended Delivery Models in Primary and Secondary Schools in Zimbabwe: Impact on Teaching, Learning, and Continuous Professional Development of teachers”
Learning
This 2025 AR identified 17 lessons for 2025 and makes associated recommendations for each one for the year ahead. Lessons from the TEACH programme have also been effectively fed into ongoing internal strategic planning within FCDO Zimbabwe. Logframe amendments completed during 2025 reinforced the necessity of disaggregation of data by gender, disability and location for all logframe indicators.
Two externally commissioned evaluations were ongoing during the 2024-25 AR period:
- The Evaluation of the Solar Systems in Schools Project in Zimbabwe[13] was completed Research Methods International (RMI) and approved in October 2024. Fieldwork was undertaken in a sample of 60 benefitting schools.
  [13] Research Methods International (2024), Evaluation of the Solar Systems in Schools Project in Zimbabwe.
- The Evaluation of the TEACH Programme in Zimbabwe was commissioned from Athena Infonomics through the FCDO Global Evaluation and Monitoring Framework Agreement (GEMFA) and is still ongoing at time of writing, but preliminary findings, based on fieldwork in a sample of 40 schools, are available.
The findings and recommendations of these two external evaluations conducted during 2024-5 are summarised below in Annex E and F and have fed into the recommendations of this AR. Both external evaluations employed OECD DAC[19] evaluation criteria: Relevance, Coherence, Effectiveness, Efficiency, Impact and Sustainability.
[19] Organisation for Economic Co-operation and Development's Development Assistance Committee
Date of last narrative financial report	UNICEF- 28 August 2025 / EDT –31 July 2025 / Think Equal- 4 August 2025 / Plan International- 30 July 2025	Date of last audited annual statement	EDT- 29 July 2024 / Think Equal – 3 October 2024 / UNICEF- 24 July 2025

Annex A: Abbreviations Used in this TEACH Annual Review
AMP	Aid Management Platform
AR	Annual Review
ATL	Accelerated Teaching and Learning
BEAM	Basic Education Assistance Module
CBM	Christian Blind Mission
CDTS	Curriculum Development and Technical Services
CE	Community Educators
CoGE	Champions of Girls’ Education
CWD	Children With Disabilities
DES	Director of Education Services
DSI	District Schools Inspector
ECD	Early Childhood Development
ECG	Education Coordination Group
EDT	Education Development Trust
EMIS	Education Management Information System
EPA	End of Programme Assessment
EPSC	Education Partnerships Steering Committee
ESPR	Education Sector Performance Report
ESSP	Education Sector Strategic Plan
FACE	Funding Authorisation and Certificate of Expenditures.
FCDO	Foreign Commonwealth and Development Office
GEDSI	Gender Equity, Disability and Social Inclusion
GEMFA	Global Evaluation and Monitoring Framework Agreement
GDP	Gross Domestic Product
GEC	Girls’ Education Challenge
GoZ	Government of Zimbabwe
GNI	Gross National Income
GPE	Global Partnership for Education
GPI	Gender Parity Index
HBC	Heritage Based Curriculum
HRD	Human Resource Department
ICF	International Climate Fund
ICT	Information and Communication Technology
IEP	Inclusive Education Policy
ISOP	Integrated Skills Outreach Programme
JMV	Joint Monitoring Visit
JSR	Joint Sector Review
KPI	Key Performance Indicator
KvA	Kilovolt amperes
LePS	Learner Welfare, Psychological Services, and Special Needs Education
MPA	Mid-Programme Assessment.
MoHTEISTD	Ministry of Higher and Tertiary Education, Innovation, Science and Technology Development
MoEPD	Ministry of Energy and Power Development
MoFEDIP	Ministry of Finance, Economic Development and Investment Promotion
MoICT	Ministry of Information and Communication Technology
MoPSE	Ministry of Primary and Secondary Education
MoWACSMED	Ministry of Women Affairs, Community, and Small and Medium Enterprise Development (MoWACSMED)
NFE	Non-Formal Education
ODA	Official Development Assistance.
OECD-DAC	Organisation for Economic Co-operation and Development's Development Assistance Committee
OOS	Out of School
PED	Provincial Education Director
PFM	Public Finance Management
PPC	Parliamentary Portfolio Committee
PVO	Private Voluntary Organisation
PwFD	Pupils with Functional Difficulties
REA	Rural Electrification Agency
REPSSI	Regional Psychosocial Support Initiatives
RID	Research and Innovation Department
RMI	Research Methods International
SAA	Standard Administrative Agreement
SAGE	Supporting Adolescent Girls Education
SCG	System Capacity Grant
SDC	School Development Committee
SEL	Social and Emotional Learning
SIG	School Improvement Grant
SPPRS	(Department of) Strategic Planning Policy Research and Statistics
SRHR	Sexual Reproductive Health and Rights
SRI	School Readiness Initiative
STG	System Transformation Grant
THRASS	Teaching Handwriting, Reading and Spelling Skills
TEACH	Teacher Effectiveness and Equitable Access for all Children Programme
TE	Think Equal
TEC	Teacher Education College
ToC	Theory of Change
ToT	Training of Trainers
TPD	Teacher Professional Development
TTC	Teacher Training College
TVET	Technical and Vocational Education and Training
TWG	Technical Working Group
UNICEF	United Nations Children’s Fund
VFM	Value for Money
ZELA	Zimbabwe Early Learning Assessment
ZiG	Zimbabwe Gold (currency)
ZimSEC	Zimbabwe Schools Examination Council
ZimSTAT	Zimbabwe National Statistics Agency

Annex B: TEACH Theory of Change

Annex C. TEACH Logframe Assumptions
Assumptions - Outcomes to Impact:
- Schools and teachers remain accessible most of the time, beneficiaries and stakeholders are able to engage with programme activities, attendance in TPD programmes is in sufficient numbers.
- Political goodwill and ability to initiate and sustain policy and structural reforms towards improving capacity to improve the quality of education.
- ECT works in close collaboration with UNICEF and GoZ and has access to the required data.
- Parents and guardians continue to be willing and able to send children to school and can afford fees
- School Financing Policy supports reduction of school fees for the poorest families
- Political and economic changes over the next 10 years do not prevent achievement of the impact
- Macro-economic environment normalises, and the wage bill provides sufficient salaries for teachers to be motivated to improve teaching and learning
- Teacher motivation increases with provision of effective professional development
- Changes to the ways of teaching (blended approach) will enable learning for all in different ways and different contexts
- Gender sensitive research and analysis will support transformation in the education sector on improving equitable access for all learners
Assumptions – Outputs to Outcomes:
Output 1: Equitable access to schools for marginalised girls and boys including CWDs
- SIGs support enrolment and learning outcomes for boys and girls
- There is appetite and demand in the Zimbabwean government to use evidence to improve learning outcomes
- Zimbabwe implements and monitors the commitments made in the Kenyatta Declaration on domestic financing and on policy reform.
- Solarisation in schools positively affects teachers’ motivation to remain in rural schools and presents opportunity to review digital learning school design
Output 2: Increased capacity to teachers and administrators for quality teaching and learning
- Schools and districts welcome better coordination and teacher professional development support and are interested in being involved in the TEACH programme
- Teachers, policymakers and communities are able to change behaviour and put their new skills and expertise into practice
- Continued acceptance of cluster centre model of delivery of teacher training
- School heads training supports schools at local level to function effectively – targeting female teachers with school head training will increase number of female heads in primary and secondary schools
- Training in safeguarding issues will increase practical action amongst key education stakeholders
- After inspection training, MoPSE will implement inspections using the revised inspection handbook and methodology.
- The Think Equal intervention successful passes through inception, is granted access to ECD classrooms and obtains permission from MOPSE for the use of materials in schools.
- Teachers are available to participate in the SEL training in targeted areas.
Output 3: Education System Strengthened
- There will be continued support and commitment by the Government of Zimbabwe to strengthening and improving the national education system, including the development and implementation of various social and education policies
- Better evidence will lead to better policymaking in the education sector
- School financing policy is approved for implementation and has political backing
- MoPSE and MoHTEISTD continue to collaborate on a joint strategic approach in overlapping area of teacher training policy and have the capacity to deliver effective teacher training
- Pre-service and in-service training is aligned around the compressed education curriculum, syllabus, new assessment frameworks and the catch-up strategy effective teacher training
- Pre-service and in-service training is aligned around the compressed Education curriculum, syllabus, new assessment frameworks and the catch-up strategy
- Reliable, usable evidence is produced by the programme and disseminated with findings and recommendations shared.
- Data and knowledge are improved, synthesised and communicated in an effective way.
Output 4: Supporting Adolescent Girls’ Education
- The data collected is consistent and comparable across participants and timeframes.
- Teaching methods are relatively consistent over the assessment period.
- The demographic characteristics of the participants remain relatively consistent.
- The data used to measure improvement in literacy and numeracy skills are assumed to be accurate and reliable.
- Community opinions on re-entry policy for pregnant girls can shift to ensure those girls stay in school and drop-outs decrease
- Girls have equal access to financial literacy programs and resources
- The educational content is sensitive to diverse cultural and social contexts, making it relatable to the highly marginalized girls.
- The girls' privacy and confidentiality are respected, creating an environment where they feel comfortable discussing SRHR topics.
- The educational environment is non-judgmental and safe, allowing girls to ask questions and seek clarification without fear of stigma.
- -The girls understand the purpose of SRHR assessment and are motivated to engage with it.
The parents or caregivers of the girls are supportive of their engagement with SRHR education and practices.
Annex D. List of Districts Benefiting from each TEACH Intervention
Province	District	UNICEF	Solar	EDT	Plan	Think Equal
Bulawayo	Bulawayo	No	No	No	Yes	No
Harare	Harare	no	No	No	Yes	No
Harare	Chitungwiza	no	No	No	No	No
Harare	Epworth	no	No	No	No	No
Manicaland	Buhera	Yes	Yes	Yes	No	Yes
Manicaland	Chimanimani	Yes	No	Yes	Yes	Yes
Manicaland	Chipinge	Yes	Yes	Yes	No	Yes
Manicaland	Makoni	Yes	No	Yes	No	Yes
Manicaland	Mutare	Yes	No	Yes	Yes	Yes
Manicaland	Mutasa	Yes	No	No	Yes	No
Manicaland	Nyanga	Yes	Yes	No	No	Yes
Mash Central	Bindura	Yes	No	No	No	No
Mash Central	Guruve	Yes	No	Yes	No	Yes
Mash Central	Mazowe	Yes	No	Yes	No	Yes
Mash Central	Mbire	Yes	No	Yes	No	Yes
Mash Central	Mount Darwin	Yes	No	Yes	No	Yes
Mash Central	Muzarabani	Yes	No	No	No	No
Mash Central	Rushinga	Yes	No	Yes	No	Yes
Mash Central	Shamva	Yes	No	No	No	No
Mash East	Chikomba	Yes	No	Yes	No	No
Mash East	Goromonzi	Yes	No	No	No	No
Mash East	Marondera	Yes	No	No	No	No
Mash East	Mudzi	Yes	No	Yes	No	No
Mash East	Murehwa	Yes	No	No	No	No
Mash East	Mutoko	Yes	No	Yes	Yes	No
Mash East	Seke	Yes	No	No	No	No
Mash East	UMP	Yes	No	Yes	No	No
Mash East	Wedza (Hwedza)	Yes	No	Yes	No	No
Mash West	Chegutu	Yes	No	Yes	No	No
Mash West	Hurungwe	Yes	No	Yes	No	No
Mash West	Kariba	Yes	No	Yes	No	No
Mash West	Makonde	Yes	No	Yes	No	No
Mash West	Mhondoro-Ngezi	Yes	No	No	No	No
Mash West	Sanyati	Yes	No	Yes	No	No
Mash West	Zvimba	Yes	No	No	No	No
Masvingo	Bikita	Yes	No	No	No	No
Masvingo	Chiredzi	Yes	No	No	No	No
Masvingo	Chivi	Yes	No	Yes	No	No
Masvingo	Gutu	Yes	No	Yes	No	No
Masvingo	Masvingo	Yes	No	No	No	No
Masvingo	Mwenezi	Yes	No	Yes	No	No
Masvingo	Zaka	Yes	No	Yes	No	No
Mat North	Binga	Yes	No	No	No	No
Mat North	Bubi	Yes	No	Yes	No	No
Mat North	Hwange	Yes	No	No	No	No
Mat North	Lupane	Yes	No	Yes	No	No
Mat North	Nkayi	Yes	No	Yes	No	No
Mat North	Tsholotsho	Yes	No	Yes	No	No
Mat North	Umguza	Yes	No	Yes	No	No
Mat South	Beitbridge	Yes	Yes	Yes	No	Yes
Mat South	Bulilima	Yes	No	Yes	Yes	Yes
Mat South	Gwanda	Yes	Yes	Yes	No	Yes
Mat South	Insiza	Yes	Yes	Yes	No	yes
Mat South	Mangwe	Yes	No	Yes	No	yes
Mat South	Matobo	Yes	Yes	Yes	No	Yes
Mat South	Umzingwane	Yes	No	Yes	No	Yes
Midlands	Chirumhanzu	Yes	No	No	No	No
Midlands	Gokwe North	Yes	No	Yes	No	No
Midlands	Gokwe South	Yes	No	Yes	No	No
Midlands	Gweru	Yes	No	No	No	No
Midlands	Kwekwe	Yes	No	Yes	No	No
Midlands	Mberengwa	Yes	No	Yes	No	No
Midlands	Shurugwi	Yes	No	Yes	No	No
Midlands	Zvishavane	Yes	No	No	No	No

Province	District	UNICEF	Solar	EDT	Plan	Think Equal
Bulawayo	Bulawayo	No	No	No	Yes	No
Harare	Harare	no	No	No	Yes	No
Harare	Chitungwiza	no	No	No	No	No
Harare	Epworth	no	No	No	No	No
Manicaland	Buhera	Yes	Yes	Yes	No	Yes
Manicaland	Chimanimani	Yes	No	Yes	Yes	Yes
Manicaland	Chipinge	Yes	Yes	Yes	No	Yes
Manicaland	Makoni	Yes	No	Yes	No	Yes
Manicaland	Mutare	Yes	No	Yes	Yes	Yes
Manicaland	Mutasa	Yes	No	No	Yes	No
Manicaland	Nyanga	Yes	Yes	No	No	Yes
Mash Central	Bindura	Yes	No	No	No	No
Mash Central	Guruve	Yes	No	Yes	No	Yes
Mash Central	Mazowe	Yes	No	Yes	No	Yes
Mash Central	Mbire	Yes	No	Yes	No	Yes
Mash Central	Mount Darwin	Yes	No	Yes	No	Yes
Mash Central	Muzarabani	Yes	No	No	No	No
Mash Central	Rushinga	Yes	No	Yes	No	Yes
Mash Central	Shamva	Yes	No	No	No	No
Mash East	Chikomba	Yes	No	Yes	No	No
Mash East	Goromonzi	Yes	No	No	No	No
Mash East	Marondera	Yes	No	No	No	No
Mash East	Mudzi	Yes	No	Yes	No	No
Mash East	Murehwa	Yes	No	No	No	No
Mash East	Mutoko	Yes	No	Yes	Yes	No
Mash East	Seke	Yes	No	No	No	No
Mash East	UMP	Yes	No	Yes	No	No
Mash East	Wedza (Hwedza)	Yes	No	Yes	No	No
Mash West	Chegutu	Yes	No	Yes	No	No
Mash West	Hurungwe	Yes	No	Yes	No	No
Mash West	Kariba	Yes	No	Yes	No	No
Mash West	Makonde	Yes	No	Yes	No	No
Mash West	Mhondoro-Ngezi	Yes	No	No	No	No
Mash West	Sanyati	Yes	No	Yes	No	No
Mash West	Zvimba	Yes	No	No	No	No
Masvingo	Bikita	Yes	No	No	No	No
Masvingo	Chiredzi	Yes	No	No	No	No
Masvingo	Chivi	Yes	No	Yes	No	No
Masvingo	Gutu	Yes	No	Yes	No	No
Masvingo	Masvingo	Yes	No	No	No	No
Masvingo	Mwenezi	Yes	No	Yes	No	No
Masvingo	Zaka	Yes	No	Yes	No	No
Mat North	Binga	Yes	No	No	No	No
Mat North	Bubi	Yes	No	Yes	No	No
Mat North	Hwange	Yes	No	No	No	No
Mat North	Lupane	Yes	No	Yes	No	No
Mat North	Nkayi	Yes	No	Yes	No	No
Mat North	Tsholotsho	Yes	No	Yes	No	No
Mat North	Umguza	Yes	No	Yes	No	No
Mat South	Beitbridge	Yes	Yes	Yes	No	Yes
Mat South	Bulilima	Yes	No	Yes	Yes	Yes
Mat South	Gwanda	Yes	Yes	Yes	No	Yes
Mat South	Insiza	Yes	Yes	Yes	No	yes
Mat South	Mangwe	Yes	No	Yes	No	yes
Mat South	Matobo	Yes	Yes	Yes	No	Yes
Mat South	Umzingwane	Yes	No	Yes	No	Yes
Midlands	Chirumhanzu	Yes	No	No	No	No
Midlands	Gokwe North	Yes	No	Yes	No	No
Midlands	Gokwe South	Yes	No	Yes	No	No
Midlands	Gweru	Yes	No	No	No	No
Midlands	Kwekwe	Yes	No	Yes	No	No
Midlands	Mberengwa	Yes	No	Yes	No	No
Midlands	Shurugwi	Yes	No	Yes	No	No
Midlands	Zvishavane	Yes	No	No	No	No

# Annex E: Evaluation of the Solar Systems in Schools Project in Zimbabwe (2024).
# Executive Summary
## Project Overview
The Solar Systems in Schools (SSS) Project, funded by the FCDO in Zimbabwe, is dedicated to improving energy access in rural schools across seven districts: Beitbridge, Buhera, Chipinge, Gwanda, Insiza, Matobo, and Nyanga. Its primary goal is to narrow the educational gap between rural and urban areas by providing reliable electricity for essential tools like ICT devices and lighting. This initiative aims to install solar systems in 150 schools, which will enhance the learning environment for around 66,000 students and 1,617 teachers by facilitating the use of educational technology. This evaluation focuses on assessing the project's implementation, relevance, effectiveness, sustainability, and overall value for money.
## Evaluation Objectives
The evaluation focuses on four main objectives:
1. Implementation Process: Assessing the efficiency and effectiveness of delivery.
2. Relevance, Effectiveness & Sustainability: Evaluating whether the solar systems were delivered as designed and if they met the intended needs.
3. Initial Impact on Teaching & Learning: Investigating early evidence of the project's impact on educational outcomes.
4. Value for Money: Analysing the economy, efficiency, and effectiveness of the project in delivering its intended results.
## Evaluation Methodology
The evaluation of the Solar Systems in Schools (SSS) Project employed a mixed-methods approach, combining qualitative and quantitative methodologies to assess the project's effectiveness, relevance, and sustainability. Data were collected through Key Informant Interviews (KIIs) with district officials, Focus Group Discussions (FGDs) with teachers and School Development Committees, and structured questionnaires distributed to teachers, students, and school heads. A multistage sampling strategy selected a representative sample of 60 schools from 150, covering seven districts to ensure socio-economic diversity and proper project implementation representation. The Cochrane formula determined a minimum sample of 382 learners for statistical reliability. Teachers and SDC members were considered for FGDs, 10 FGDs with teachers and 10 FGDs with the SDCs.
Data analysis utilized N-Vivo software for qualitative analysis, identifying themes through thematic coding, while SPSS facilitated quantitative analysis, summarizing data and testing for significant differences based on various factors. Quality assurance measures included regular checks for data completeness, pre-testing data collection instruments, and secure data management protocols. Ethical considerations were crucial, involving informed consent, confidentiality protections, safeguarding training for team members, and minimizing disruption to school activities. This comprehensive methodology aimed to provide a nuanced understanding of the project's impact on teaching and learning in schools.
## Key Findings
Implementation Process
- Stakeholder engagement was limited during the project planning phase, leading to insufficient needs assessment and community involvement.
- Rapid implementation without adequate stakeholder consultation led to gaps in project planning and execution (described below)
- Although installations generally proceeded without major disruptions, there were delays related to procurement issues and the late incorporation of key stakeholders.
Relevance, Effectiveness & Sustainability
- The installed solar systems met basic energy needs for lighting and charging devices. Although not envisaged in the design of the project, evidence from sampled schools shows that the energy generated has the potential to address other needs such as powering internet access and additional office appliances, such as audio-visual equipment, printers and photocopiers.
- Sustainability concerns were noted, particularly regarding maintenance and security against theft and vandalism.
- Initial sustainability plans were weak. The evaluation identified a need for ongoing stakeholder involvement for project sustainability.
Initial Impact on Teaching & Learning
- The availability of electricity facilitated improved learning experiences, increased teacher motivation, and community engagement. However, the full potential benefits were limited by insufficient ICT resources and lack of training on the optimal use of digital learning systems and platforms.
- Schools previously with no reliable and affordable energy source now have access to one. This has enabled after-hours learning and increased study time for learners. About 93% of school heads reported having observed some positive changes in the attainment of learning outcomes, attendance as well as positive changes in student engagement since the installation of the solar system
- Access to ICT gadgets has improved student learning experiences. About 4 in every 5 (80%) of school heads reported that their schools have some ICT gadgets (computers, tablets, phones and other devices purchased or used since solar system was installed). About 66% of the school heads reported that their teachers have access to a computer while about 44% of the head teachers reported that the learners also have access to a computer in their schools. Students were engaged in online learning, improving their understanding of concepts and performance in examinations. It was found that on average a school in solarisation option One had an average of 3 computers and 5 tablets/phones while a school in solarisation option Two had an average of 3 computers and 11 tablets/phones.
- Improved facilities and working conditions attracted and retained teachers in rural areas. This increased stability in staffing leading to better educational continuity. This is an encouraging and possibly one of the most tangible initial benefits of the project.
Value for Money
- The project demonstrated value for money regarding cost efficiency; however, the limited scope of solar systems and unmet expectations concerning their capabilities raised concerns about long-term effectiveness.
- The introduction of solar systems triggered complementary and entrepreneurial projects, such as nutrition gardens and fishponds. This strengthened community involvement and enhanced local food security, nutrition and school development and are exemplary practices in response to MoPSE’s emphasis on income-generating projects in schools.
## Recommendations
- Enhance Stakeholder Engagement: Future projects should prioritize early comprehensive stakeholder consultation to ensure needs are accurately assessed.
- Tailor System Designs: Customizing solar system designs based on specific school needs and local contexts will improve overall effectiveness.
- Strengthen Sustainability Measures: There is a need for further investment in securing the solar systems installed to ensure that these are not lost or damaged due to theft and vandalism. This investment could be directly by schools, but most realistically through various development partners, including FCDO, to ensure that these benefits are sustained in the long term. While some schools can afford security guards, most cannot sustain this cost in the long term.
- Expand Infrastructure Support: Integrating additional resources such as internet connectivity and solar-powered water supply systems will maximize educational benefits.
Conclusion
The SSS Project has proven that solar energy can enhance educational infrastructure in rural Zimbabwe, providing essential electricity and supporting broader community development. Continued engagement with stakeholders and tailored interventions will be crucial for scaling similar initiatives and improving educational equity across the nation.
Annex F
The Evaluation of the TEACH Programme in Zimbabwe by Athena Infonomics
Interim Findings Table
OECD-DAC Criteria	Evaluation Question (EQ)	Interim Findings
Impact	EQ1. To what extent has the TEACH programme contributed to changes in learning outcomes in Zimbabwe?	Mixed picture on learning outcomes, with positive trends (Form 4 pass rate; literacy) and contributions from TEACH interventions (SIGs, TPD, inspections, inclusive pedagogies) alongside uneven progress (Grade 7; numeracy). / Signals need for more targeted and intensive catch-up supporting areas with zero percent pass-rates, non-readers, and groups of under-performing boys, alongside guarantee of basic teaching resources (learner textbooks) in schools.
Impact	EQ2. To what extent has the TEACH programme contributed to changes in access to learning in Zimbabwe?	Highly mixed picture on changes in school enrolment (increase in PwFD[20]), dropout (high male dropout at secondary level) and retention (gains in TEACH schools), driven by a combination of external (e.g. COVID-19) and internal school factors (lack of infrastructure and qualified staff, GEDSI policy clarity), but mitigated in TEACH supported schools by various components. / Signals importance of supporting better Public Finance Management (PFM) of education budget (SFP and other TA), and regular disbursements to schools, BEAM payments, assistive devices etc.; implementation of Inclusive Education Policy (IEP).
Effectiveness	EQ3. To what extent has the TEACH programme affected the quality of teaching and school leadership?	Gender-balanced improvements in teacher competence, leadership and confidence from TPD, with real-life courses/ workshops and teacher networks most effective modalities, and adaptations to low-resource contexts and GEDSI. Results more pronounced where pre-existing skills-gaps (satellite schools, certain provinces) with variations in reach, take-up and continuity (governance gaps and cascade model), as well as confidence in ICT skills and special needs. / Points to need for more targeted TPD efforts geographically (alongside national CPD reforms), with components to strengthen sub-national delivery structures and ownership, and wider enabling environment around ICT and GEDSI (infrastructure + Teacher Training College instruction & personnel.
Effectiveness	EQ4. To what extent has the TEACH programme supported a more accountable learning environment?	TEACH has enhanced school inspections, shifting from compliance/ punitive focus to a technology enabled, data-driven supportive approach with enhanced GEDSI tools, although inspection coverage is uneven due to logistical and infrastructure challenges, and GEDSI lacks systemic integration. / Signals further need for emphasis on sub-national capacity building (PEDs, SDCs etc.) and funding for transport /fuel.
Effectiveness	EQ5. To what extent has the TEACH programme supported and promoted equitable access to Zimbabwe’s education system?	SIGs have moderately improved functionality of P3 and (especially) satellite schools, with emerging evidence of improved pass and completion rates where SIG+TPD+SAGE are layered, although with equity gaps (PwFD, GEDSI integration) and reduced SIG budget risking reversing gains. Community Engagement may bring positive short-term but limited longer-term gains without sustained improvements to school infrastructure (and teacher motivation/ retention). / Signals again need for sustainable financing solutions for schools (including inclusive education), and especially most vulnerable schools, alongside value of layering interventions.
Effectiveness & Sustainability	EQ6. To what extent has the TEACH programme supported and promoted a strengthened education system within Zimbabwe?	TEACH has played an important role in advancing specific education policies including the ELP, SFP, IEP, NFE, alongside generating new research outputs and enhancing education data collection through EMIS and ZELA (with some evidence of influence on policy and practice). Whilst this has strengthened the capacity for evidence-based planning within MoPSE, policy approvals remain slow, gaps in teacher CPD policy and cross-Ministry collaboration, and delays in (EMIS) feedback loops. / Signals need for streamlined/standardised processes for policy approvals, further strengthening of institutional capacity for data use& more intensive efforts on CPD and cross-Government working
Relevance	EQ7. What have been the most significant developments in the education context since TEACH began, and how well has TEACH responded?	TEACH provided a relevant systems-focussed, broad platform for partners to support implementation of Zimbabwe and FCDO’s education priorities, which proved responsive to policy shifts and external shocks (e.g. through blended learning + catch up & SEL + psychosocial support), and with aspects of GEDSI relevance embedded throughout. However, withdrawal from SIGs weakened foundation of equitable access component and holistic model. / Future TEACH programme to maintain upstream focus on system strengthening, including wider structural challenges around education financing/ disbursement, inclusive education - staffing, skills, and infrastructure, and teacher motivation/retention (alongside targeting most disadvantaged districts and schools with foundational, catchup support etc.).
Efficiency	Q8. To what extent have TEACH programme resources been used to promote Value for Money?	Pending Analysis
Coherence	EQ9. To what extent is the TEACH programme coherent across partners, externally and internally?	TEACH has contributed to a more structured and strategic education sector governance model, supporting policy alignment, co-design, co-implementation, with aligned logframes – including with MoPSE and GPE. Coherence was more variable at the sub-national level, and with scope for better coordinated and layered interventions. Cross-sector coordination on GEDSI remains more fragmented and weakly institutionalised. / Signals again need for attention at sub-national governance level, as well as embedding inclusive education focus and common strategy within national level governance.
[20] Pupils with Functional Difficulties