## Annual Review Template

Title: TradeMark Africa – Strategy 2 (Regional)
Programme Value £ (full life): £25,000,000		Review date: December 2025
Programme Code: 300257	AMP start date: July 2017	AMP end date: March 2026

Summary of Programme Performance
Year	2018/19	2019/20	2020/21	2021/22	2022/23	2023/24	2024/25
Overall Output Score	A	A	B	B	A	A	A
Risk Rating	Moderate	Moderate	Major	Major	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/24605596.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/44797714.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

TradeMark Africa (TMA), formerly TradeMark East Africa, is an aid-for-trade organisation that was established in 2010, with the aim of growing intra-African trade and increasing Africa’s share in global trade, while helping to make trade more pro-poor. Using its trade facilitation expertise, TMA focusses on reducing the cost and time of trading across borders through enhanced trade policy, better trade infrastructure, standards that work for businesses, greater use of digital innovations and a focus on creating trade access for vulnerable groups. Specifically, TMA is supporting two outcomes: reduced barriers to trade and improved business competitiveness. The business case period runs from 2017 to 2026, following a two-year extension in light of the implementation delays caused by the COVID-19 pandemic and subsequent budget adjustments. During this extension period, TMA has moved towards implementing its ‘Strategy 3’ (running from 2023-2030). Under this business case, FCDO continues to fund activities, outputs and outcomes which were present in Strategy 2 and are continuing to be delivered in Strategy 3.

TMA divides its work into country programmes and regional programmes, across its 14 countries of operation. This Annual Review (AR) covers regional funding, provided from FCDO Africa Programmes and Expertise Department (APEX). The funded activities are all in support of reduced barriers to trade (Outcome 1) and are inherently regional. Specifically, FCDO APEX funding under this programme supports three intermediate outcomes: improved sustainable efficiency and capacity of transport infrastructure; effective trade systems and procedures; and improved trade regulatory environment. Other ARs cover FCDO’s support for TMA in Kenya, Tanzania, Rwanda, Ethiopia, Somalia, Uganda, Malawi and to implement the African Continental Free Trade Area (AfCFTA).

The reduction in Official Development Assistance (ODA) has resulted in key changes to this programme. This Annual Review reflects that the programme has had to refocus resources and as a result, the findings of this Annual Review reflect on a programme in transition.

Summary supporting narrative for the overall score in this review

This annual review covers work conducted between April 2024 and March 2025. The timing of this review is aligned with TradeMark Africa’s internal annual review to enable this review to be based on the most up to date data. The activities undertaken during the year under review were largely a continuation of progress due to spending from the preceding year, targeting the next set of output milestones towards achievement of Outcome 1 within the Theory of Change.

The programme received no funding from FCDO in the FY. TMA continued some of the programme’s activities with funding from other donor partners. This review is carried out to track progress towards Outputs and Outcomes aligned with those activities funded by FCDO in prior years, and for which FCDO will consider funding in the subsequent year of the programme. Furthermore, maintaining oversight of TMA delivery of results against strategic outcomes is a key element of FCDO’s governance of TMA.

While the FCDO did not fund any programme activities during the FY, activities that represent a direct continuation of previously funded work have been assessed in this review and scored. The FCDO hopes to build on such activities in the following years. Activities that were stopped or moved to other programmes earlier in the programme life have not been scored.

The programme continues to be focussed specifically on two linked clusters of activities and outputs – (i) digital and ‘ICT for trade’ interventions, particularly related to the “Single Customs Territory” information sharing systems and “the Buyer-Seller Platform”; and (ii) support to East African Community (EAC) trade-enabling policy frameworks. Some workstreams undertaken in previous years were not continued in the regional programme as they were instead funded from FCDO country programmes (specifically, aspects of the DRC workstreams).

In the previous year, funding to the digital cluster made up approximately 70% of total FCDO expenditure for this programme, with the remainder allocated to the EAC cluster of workstreams. Results were weighted accordingly for the respective review. We have therefore retained these weights for this year’s review. The programme has been scored an A, indicating that it is meeting expectations on such Output and Outcome areas, while recognising that FCDO has not directly funded any activities this year.

FCDO continues to maintain an overarching relationship with TMA, particularly through our seat on the Board of Directors and Council of Donors, through our country programmes, and through continued central oversight of the wider funding relationship between the two organisations.

Key successes in the digital and ‘ICT for trade’ interventions included the launch and handover of the Single Customs Territory Centralised Platform (SCT-CP). The SCT-CP is now processing over 800,000 transactions. On the EAC workstream, successes included completing the design and agreement of a short-term package for the Nimule border post (South Sudan). This included a needs assessment with the EAC Secretariat and the architectural design for a prefabricated office.

Major lessons and recommendations for the year ahead

Detailed lessons and recommendations relevant to specific activity areas are set out against each output in Section C. This section summarises the key findings from across these lessons and recommendations.

Key lessons (this year)
- New systems introduced at partner institutions - such as digital platforms - deliver the greatest value when operational structures, ownership, and reporting routines are established in parallel with delivery of the technical solutions (hardware and software, etc).
- To secure sustained usage of new systems introduced at partner institutions, adoption should be followed by effective change management. This includes the introduction of simple Key Performance Indicators (KPIs). TMA should support this process by suggesting KPIs when new systems are handed over.

Key Recommendations for FY 25/26.
Strengthen the sustainability of new systems introduced into partner institutions by establishing regular reporting routines and assigning clear responsibilities to relevant staff at supported institutions. Additionally, provide periodic refresher training to reinforce capacity.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The Regional Programme’s theory of change holds that if region-wide rules, systems and institutions reduce barriers to trade; if interoperable digital infrastructure make procedures faster and more predictable; and if inclusion and safeguarding are built in, then cross-border trade within African regional economic communities will rise and contribute to inclusive prosperity. The programme therefore targets: i) Regional Economic Community (REC)-level policy, coordination and payment reforms; ii) regional digital public goods and standards that lower time and cost to trade; iii) regional enablers for quality, Sanitary and Phytosanitary (SPS) measures and market access; iv) an inclusion spine that strengthens participation by women and youth.

There were no year-on-year changes to Outcome or Impact indicators in this annual review period.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

No funding was provided to this programme this year. Moreover, the programme received numerous in-year budget reductions in previous years. This programme’s targets have thus been adjusted accordingly, compared to those anticipated at the beginning of the programme.

Overall, the programme is progressing well and delivering real benefits, especially where important reforms have been put in place and are being carried out. New laws and policies are helping to make trade easier and more efficient. For example, the East African Community (EAC) has adopted a new payments roadmap, which will make cross-border payments faster, safer, and less expensive.

Efforts to remove trade barriers are also moving forward. The EAC Regional Monitoring Committee (RMC) met twice this year to focus on solving key issues. Additionally, the Nimule-Elegu One-Stop Border Post is being operationalized though construction of prefabricated offices where the architectural designs were finalised. This will speed up border crossings.

The Single Customs Territory Centralised Platform (SCT-CP) - a new digital platform - is now in use, allowing customs and port authorities to share information instantly. This helps reduce paperwork and makes the process of moving goods more predictable. Work is also underway to introduce electronic certificates for plant imports and exports, making it easier for countries to move towards paperless systems.

Standards and SPS toolkits and targeted capacity support strengthened the conditions for lower compliance time and costs; thematic evaluations completed this year report such reductions across the wider portfolio.

Training and new tools have helped lower the time and costs needed to meet trade standards, and recent evaluations show these improvements are making a difference across the programme.

TMA has been in the process of undertaking a series of independent evaluations into intermediate outcomes achieved under Strategy 2, the majority of which were completed in 2025. Many of these provide robust evidence and learning relating to the activities underway in the regional programme under Strategy 3. An evaluation into the Standards and SPS activities, reported that activities “have had a positive impact on businesses, including micro, small, and medium-sized enterprises (MSMEs), contributing to job creation, gender equality, and environmental protection”[1]. Similarly, an evaluation on TMA’s transport infrastructure work found activities “successfully reduced transport times and costs, significantly improving trade efficiency and regional integration”[2]. These evaluations provide increased confidence that the continuation of activities in these areas has high potential for contributing to expected outcomes and impact. (for more information, see Section G below)
[1] Consultancy For Standards And Sanitary And Phytosanitary (SPS) Portfolio Evaluation – AENOR Conocimiento, February 2025
[2] Final Evaluation Report Sustainable and Efficient Transport Infrastructure Portfolio Evaluation, EDI Global, March 2025

Planned action in the year ahead.
Complete next-phase integrations and onboarding for the Single Customs Territory Centralised Platform and track usage and clearance-time differentials to evidence benefits.

Advance NPIECS/electronic-Phytosanitary (“ePhyto”) conformance and onboarding with early adopters (Zimbabwe first, with potential scale-up to Zambia/Malawi) and agree support arrangements with International Plant Protection Convention (IPPC)/Inter-African Phytosanitary Council of the African Union (AU-IAPSC) and National Plant Protection Organisation (NPPO).

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

We assess that the regional programme should continue. The theory of change remains valid and is being evidenced through system-level enablers now in place: the EAC Payments System Masterplan has been adopted by the Monetary Affairs Committee, the SCT-CP is operational for real-time data exchange among revenue and port authorities and the model NPIECS e-certification design is ready for onboarding. Inclusion and safeguarding practices have strengthened through the roll out of WITEI and other social/environmental measures.

Delivery has adapted to funding shocks through re-sequencing and portfolio reviews, protecting the linkage between outputs and outcomes. Independent evaluations report material reductions in time and cost to trade across relevant portfolios, supporting value for money from regional public goods whose benefits are shared across multiple countries. In the wider portfolio, the programme is supporting regional public goods and backbone systems (for example harmonised standards and regional digital platforms) that country and bilateral programmes then use and extend, aligning with Strategy 3 and TMA’s FY24/25 corporate priorities on results, systems and people productivity.

Continuation is recommended with light adjustments: secure pooled finance for paused regional public goods, for example such as those from activities that were formerly funded by USAID, lock in adoption plans for payments and NPIECS and maintain inclusion metrics in partner reporting so results remain transparent.

## C. DETAILED OUTPUT SCORING

Output Title	Cross-border information sharing framework operationalised
Output number:		EAC 1.3.1	Output Score:	A (Expectations met). Whilst no FCDO funding was allocated in FY24/25, TMA continued to demonstrate progress against this output area as part of the broader programme, utilising other donor funding.
Impact weighting (%):		70%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.3.1.a Progress towards operationalisation of TLIP	N/A	TLIP infrastructure was enhanced to support additional value chains, markets, and stakeholders.
1.3.1.b Progress towards operationalisation of the Single Customs Territory (SCT) information sharing platform (ISP)	N/A	The SCT-CP was launched and handed over to EAC. and the time-bound Blueprint towards a fully-fledged Customs Union was tabled and noted by EAC Council of Ministers
1.3.1.c Progress towards operationalisation of the bureaux of standards information sharing platform	N/A	None
1.3.1.d Progress towards operationalisation of the Food and Drug Authority Information Sharing Platform (FDA ISP)	N/A	The FDA ISP system operationalise with the support of TMA last year continues to be in use, facilitating exchange of information between relevant authorities.
1.3.1.e Progress towards operationalisation of the SPS information sharing platform	N/A	None

Briefly describe the output’s activities and provide supporting narrative for the score.

Despite no FCDO funding being allocated during the year under review, we have reviewed the extent to which prior year’s activities are performing as expected, as well as TMA’s output-level performance where funding was allocated from other donors for continuation of activities within the same area of work.

During the review period, TLIP Infrastructure enhancements included the initiation of strategic partnerships with Ghana and Zambia, with MOUs under review or at early discussion stages, and strengthened bilateral engagement with India and the UK, where agreements are progressing through final approval processes. Additionally, comprehensive process mapping was completed for several trade lanes, leading to the prioritisation of four value chains—pharmaceuticals, steel, motor vehicles, and vegetables—for immediate integration, in line with national trade priorities and the aim of streamlining customs and trade procedures.

Single Customs Territory Centralised Platform: The SCT-CP was launched and handed over and is now processing over 800,000 post-launch transactions (6.62m exchanges enabled overall), and the time-bound Blueprint towards a fully-fledged Customs Union was tabled and noted by EAC Council of Ministers. These achievements are integral to the same results chain and materially increase readiness for adoption and use

Operationalization of the EAC-Buyer Seller Platform (BSP): Phase 2 development was finalised, tested and operationalised. The platform was adopted by the Sectoral Committee on Investment for rollout; 652 businesses are registered. Final report and User Manual submitted to the EAC Secretary General on 25 April 2025 after addressing validation comments.

Country and sector work that supports the output: The Uganda Trade Policy review was validated; technical assistance was initiated on AfCFTA domestication.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No change to the output. No structural changes are proposed as a result of this review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation (from last AR)	Status (FY24/25)	Evidence / notes
Strengthen stakeholder-coordination mechanisms; develop clear engagement protocols to avoid internal/external validation delays.	Partially completed	TMA has maintained regular engagement with the EAC Partner States Coordination Committee and the Sectoral Committee on Investment, with the adoption of the Buyer-Seller Platform formally recorded in meeting minutes. However, there is currently no documented evidence of an established engagement protocol to guide these interactions
Foster cross-agency collaboration for trade facilitation; institutionalise regular cross-agency meetings.	Completed	The Regional Sub-Committee on Trade Facilitation convened successfully. The Single Customs Territory (SCT) Central Platform was launched and formally handed over, providing a robust mechanism for real-time data exchange between revenue authorities and port authorities, thereby enhancing transparency and efficiency in customs clearance processes. Furthermore, the Buyer-Seller Platform was adopted by the Sectoral Committee on Investment, paving the way for its regional rollout and alignment with broader trade facilitation objectives.

Key lessons (this year)
- New systems introduced at partner institutions - such as digital platforms - deliver the greatest value when operational structures, ownership, and reporting routines are established in parallel with delivery of the technical solutions (hardware and software, etc).
- To secure sustained usage of new systems introduced at partner institutions, adoption should be followed by effective change management. This includes the introduction of simple Key Performance Indicators (KPIs). TMA should support this process by suggesting KPIs when new systems are handed over.

Recommendations for FY 25/26.
1. Kick-off implementation: Establish a light-touch implementation support function within the EAC Secretariat, including a Project Management Officer (PMO) and progress tracker. Agree on two to three quick wins for FY 2025/26 for each policy instrument and assign clear leads and timelines.
2. Formalise commitments and resources: Conclude short Memoranda of Understanding (MoUs) to define roles, Technical Working Group (TWG) schedules, and points of contact. Include a sustainability note covering hosting and operating costs. Nominate data owners and set a reporting cadence for the Business Strategy Plan (BSP) and the Single Customs Territory Central Platform (SCT-CP).
3. Strengthen measurement and planning: Refine the output indicator to “policy instruments adopted or operationalised” and track three KPIs per instrument, for example:
  1. BSP: active buyers/sellers and successful matches
  2. SCT-CP: system uptime and monthly data exchanges
  3. Regional Investment Blueprint: Year-1 actions delivered versus plan
Manage Scope for AfCFTA Integration: If African Continental Free Trade Area (AfCFTA) domestication or national policy launches are to be included under this output next year, introduce a specific milestone only once funding and counterpart commitments are secured.

Output Title	One stop border post (OSBP)/integrated border management (IBM) instruments and frameworks developed and implemented; and WTO TFA measures identified and implemented
Output number:		EAC 1.4.1	Output Score:	A (Expectations met). Whilst no FCDO funding was allocated in FY24/25, TMA continued to demonstrate progress against this output area as part of the broader programme, utilising other donor funding.
Impact weighting (%):		0%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.4.1.a Progress towards implementation of OSBP/IBM instruments and frameworks	N/A	Improvements at select border posts included needs assessments and architectural designs being completed, deployment of ICT hardware, improved internet connectivity, and handover of the OSBP Performance Measurement Tool to the EAC.
1.4.1.b Progress towards implementation of priority measures /reforms in the regional trade facilitation action plan	N/A	None

Briefly describe the output’s activities and provide supporting narrative for the score.
 As above, we have reviewed the extent to which prior year’s activities are performing as expected, as well as TMA’s output-level performance where funding was allocated from other donors for continuation of activities within the same area of work.

This output streamlines corridor and border operations by aligning procedures, equipping priority posts and using practical tools for predictable crossings. During the year, the Nimule short-term package was defined, a needs assessment was completed in September 2024 with the EAC Secretariat and the architectural design for a prefabricated office was finalised to guide installation. At selected borders ICT kits were delivered (desktops, laptops and printers) at four posts (Lwakhakha KE/UG and Loitoktok/Tarakea KE/TZ), with internet supplied at Lwakhakha and sensitisation/training on the OSBP Performance Measurement Tool followed by handover to the EAC Secretariat.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes were made to this output.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

No recommendations were recorded for this output in the FY23/24 AR (no funding was allocated to Output 1.4 last year). This year focused on foundational fixes at priority borders and embedding simple operating tools.

Key lessons this year
- Infrastructure without coordinated operations underperforms. Nimule shows the need for approvals, staffing and harmonised processes alongside physical works.
- Short, targeted fixes (prefab, ICT, connectivity, tool uptake) can catalyse system change when ownership is clear.
- Early formalised stakeholder engagement is essential to avoid implementation delays.

Recommendations for FY 25/26.
1. Secure Government of Uganda and the Government of South Sudan approvals and site readiness for the Nimule prefab, then procure and install ICT and furnishings to operationalise joint working.
2. Translate EAC mission findings into time-bound border action plans: remove specific local constraints (e.g. the Isebania county barrier where still applicable), standardise Simplified Trade Regime (STR) practice, strengthen Joint Border/Border Management Committees (JBCs/BMCs) with named convenors and quarterly meetings, enforce joint verification, review agency footprints and scanning capacity and agree adjustments.
3. Institutionalise the One Stop Border Posts (OSBP) Performance Measurement Tool (PMT) via a simple quarterly reporting routine with a named officer at each supported OSBP, plus a light Training of Trainers (ToT) refresh at each OSBP that builds on the 250-stakeholder sensitisation.

Output Title	EAC trade enabling frameworks implemented
Output number:		EAC 1.4.3 a	Output Score:	A (Expectations met). Whilst no FCDO funding was allocated in FY24/25, TMA continued to demonstrate progress against this output area as part of the broader programme, utilising other donor funding.
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.4.3.a Progress towards implementation of the EAC trade enabling frameworks	N/A	1.TMA supported the EAC Secretariat to review the Simplified Trade Regime Common List , which led to products that are eligible to increase from 360 to 567. / The Simplified Trade Regime instruments were also translated into French and Kiswahili. / 2. TMA supported the EAC Secretariat with the development of the EAC Customs Bond, enabling traders use only one Bond while transiting across EAC

Briefly describe the output’s activities and provide supporting narrative for the score.

No material work was conducted on this output during this year. This reflects that no funding was provided (by the FCDO or other donors) towards this activity.

Last year, this programme supported the launch of EAC Customs Bond. During the year under review, use of the EAC Customs Bond has expanded, it is being piloted in Kenya and Uganda and is expected to be fully effective from January 2026. Further work was done following work last year which laid the groundwork for a Mutual Recognition Agreement between the EAC and India. This year saw the MRA approved for signing by EAC’s 47th Sectoral Council on Trade, Industry, Finance and Investment meeting. The EAC will now engage counterparts in India to begin preparations for the signing process, with signing expected from as early as 2026.

The Single Customs Territory (SCT) Information Sharing Platforms (ISP), rolled out to five countries last year has continued to be utilised. The platform has enabled real-time customs and port data exchange. Over 800,000 transactions have processed and 6.6 million exchanges have been enabled on the platform since its rollout.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes were made to this output.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation (from last AR)	Status (FY24/25)	Evidence / notes
Improve project planning to ensure realistic timelines, identify aspects which are contingent on external factors, and embed real-time monitoring processes	In progress	TMA, with support from other development partners, has held regular preparatory meetings with key stakeholders including EAC, ECOWAS, AfCFTA Secretariat, and relevant ministries. Quarterly and biannual meetings with the EAC Secretariat ensure projects are demand-driven and aligned with Council of Ministers decisions. Supported activities are incorporated into annual work plans, facilitating implementation and monitoring. Joint fact-finding missions with government representatives have helped identify and prioritise interventions at key border posts, improving project design and delivery. TMA’s participation in donor round tables has enhanced coordination and reduced duplication of funding.
Streamline procurement processes and improve donor coordination and reporting to support timely delivery	In progress	TMA has appointed a Commercial Delivery Manager to strengthen links between procurement, programme teams, and service providers. The CDM and Head of Procurement now participate in Peer Review Meetings to support programme design and delivery. Framework contracts have been established for 20 categories, onboarding over 200 service providers, which will streamline selection and contracting. Procurement policy improvements, including simplified single sourcing and negotiated procurement, have been introduced to increase efficiency. Automation is underway with the procurement of SAP Strategic Sourcing, expected to improve process turnaround time by 25% once fully implemented by June 2026.

.

Output Title	Mahagi One Stop Border Post (OSBP) Infrastructure developed and operationalised
Output number:		DR. 1.1.1	Output Score:	N/A - no funding or activities took place under the regional programme this year, as the activity had previously been shifted to a country programme
Impact weighting (%):		0%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
DR. 1.1.1.a Progress towards construction of Mahagi OSBP	N/A	N/A - no funding or activities took place under the regional programme this year, as the activity had previously been shifted to a country programme

Briefly describe the output’s activities and provide supporting narrative for the score.

No funding or activities took place under the regional programme this year, as the activity shifted to country programme

Describe any changes to this output during the past year, and any planned changes as a result of this review.

N/A

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

N/A

Output Title	DRC Customs Management System (CMS) upgraded
Output number:		DR 1.3.1	Output Score:	N/A - no funding or activities took place under the regional programme this year, as the activity had previously been shifted to a country programme
Impact weighting (%):		0%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
DR. 1.3.1 DRC Customs Management System (CMS) upgraded	N/A	N/A - no funding or activities took place under the regional programme this year, as the activity had previously been shifted to a country programme

Briefly describe the output’s activities and provide supporting narrative for the score.

No funding or activities took place under the regional programme this year, as the activity shifted to country programme

Describe any changes to this output during the past year, and any planned changes as a result of this review.

N/A

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

N/A
D: VALUE FOR MONEY

Key cost drivers and performance

Because FCDO did not allocate any funding to project workstreams, no project level VfM measurement is directly relevant.

Assessment of whether the programme continues to represent value for money

An independent assessment judged that TMA’s programmes represented good value for money overall. This assessment was based on projects funded by other donors achieving output targets and meeting expectations. Strong VfM evidence was observed. Results were delivered, despite funding shocks, by containing costs through co-funding and handing over the hosting of digital systems to partners, maintaining efficient delivery on core workstreams and remaining effective at scale on digital infrastructure and women’s trade access. Equity performance was also considered to be strong.

Based on this analysis we consider that there is sufficient evidence to assess that the programme is delivering acceptable VfM.

E: RISK

Overview of risk management

The overall risk score for the programme is Moderate. The risk appetites for each of FCDO’s seven risk categories (as noted below) were reviewed in June 2025 and remain appropriate when considered against residual risk levels.
Risk Appetite Category	Level
Strategy & Context	Receptive
Policy & Programme Delivery	Receptive
Safeguarding	Cautious
Public Service Delivery & Operations	Cautious
Financial & Fiduciary	Cautious
Reputational	Cautious
People	Cautious

Programme risks are identified, mitigated, reviewed and updated at different levels. The FCDO Programme management team reviews at least every three months. Some individual risks (e.g. reputational, fraud and safeguarding risks) are reviewed more frequently. The TMA Board takes an overarching view of risks to the TMA organisation, carefully considering risks that exceed TMA’s risk appetite and suggesting additional mitigation actions where appropriate. TMA delivery teams assess day to day programme risks as they relate to the implementation of programme activities. The FCDO programme management team discusses high level delivery risks with the implementing partner and other donors at Council meetings.
As there was no financial contribution to the programme in FY24/25, there were limited Financial and Fiduciary risks and Policy & Programme Delivery risks, in this reporting period. FCDO’s main risks identified were therefore organisational. TMA’s overall financial cashflow position and fund-raising continue to be Financial and Fiduciary risks for TMA. The cash-flow risk was reduced reflecting corrective action taken by TMA & FCDO to strengthen TMA’s cash position, although the withdrawal of some donor funding created additional pressure on the annual budget.

FCDO’s role as the legal member of TMA, and with an appointed board member, present potential reputational risks in the event of any negative reporting. The programme team ensures that these risks are mitigated through regular interaction and monitoring of the programme.

TMA monitors fraud risks through the Audit, Finance and Risk Committee of the board which meets quarterly. TMA management has strong fraud controls including the Incident Response Group (IRG) and a clear Fraud Response Plan which together provide active and systematic management of fraud risks.

TMA maintains a safeguarding risk register and a network of 26 risk champions across the organisation. Environmental and Social Impact Assessments are undertaken by qualified personnel, with findings integrated into project design and monitored by the Safeguarding and Project Risk Management team. Risks are reviewed quarterly and escalated to senior leadership. The IRG oversees incident response and reporting.

A thorough Due Diligence Assessment of TMA was recently completed by the FCDO programme team.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues

FCDO provided no financial contribution to the programme in FY24/25. No specific financial or narrative reporting was considered necessary.

FCDO currently acts as the sole “Legal Member” of TMA. As a Company Limited by Guarantee, TMA is required under Kenyan Law to have a minimum of one Legal Member (and a maximum of 50). FCDO continued to perform its role on the Board of Directors and the Council of Donors, which provide oversight and assurance that internal control systems are in place to deliver TMA’s objectives.

TMA provided their financial statements for the FY23/24 in December 2024 (which covered FCDO’s contributions that year). These were reviewed and agreed.

The APEX programme team continued to provide support and guidance to FCDO Posts which gave TMA funding in this reporting period under FCDO’s overarching Memorandum of Understanding. Regular meetings were arranged to share information and maintain consistency across the FCDO portfolio of national, regional and continental activities undertaken by TMA. These discussions included consideration of delivery and financial management risks.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

Given that FCDO provided no financial contribution this FY, this light touch Annual Review was a desk-based assessment undertaken by the APEX programme team based on information provided by the independent evaluators commissioned by TMA, TMA Board documents and other relevant evidence. A field visit to TMA’s headquarters in Nairobi was undertaken by the APEX programme management team in March 2025.

TMA have undertaken a comprehensive set of evaluations of their Strategy 2 activities. These included assessments of Trade Information Systems, Women in Trade, Export Capability & Public Private Dialogues, Standards and Sanitary and Phytosanitary measures and Sustainable and Efficient Transport Infrastructure. These evaluations aimed to assess the performance, impact and lessons learned from support provided by TMA under Strategy 2 (2017-2023). Relevant highlights from two of these are briefly summarised below.

Standards and Sanitary and Phytosanitary Portfolio Evaluation (February 2025) / This evaluation aimed to assess the performance and lessons learned from the support provided by TMA under Strategy 2 in the area of Standards and SPS measures, with a focus on the extent to which the portfolio under evaluation addressed the standards compliance as key barrier to trade in East Africa. / The TMA portfolio was aligned with political decisions at the continental, regional and national levels of the countries involved supporting economic integration in the region. Projects have had a positive impact on businesses, including micro, small, and medium-sized enterprises (MSMEs), contributing to job creation, gender equality, and environmental protection. Overall, the companies surveyed reported a median increase in sales, with some having increased much more the volume sold. Firms also indicated positive changes in the time needed for conformity assessment, with a reduction in the average time of about 44% (from 7 months in 2017 to 4 in 2023) as well as a reduction in the costs of over 50% in the median value. / The evaluation also noted that the projects have had a positive impact on social objectives, such as promoting women entrepreneurs and creating jobs - the overall median number of employees per business experienced an increase of over 24% from 2017 in the surveyed sample. It considered that the activities initiated by TMA’s S2 projects have a good chance of being sustained over time, thanks to businesses' motivation and governments' commitment to continuing economic integration.

Sustainable and Efficient Transport Infrastructure Portfolio Evaluation (March 2025) / An independent assessment of the Sustainable and Efficient Transport Infrastructure Portfolio implemented by TMA between 2017 and 2023 (TMA’s Strategy 2 period). The evaluation focused on four major projects making up the portfolio which was evaluated: the Goli/Mahagi One Stop Border Post (OSBP), the Nimule/Elegu OSBP, the Mombasa Roads project and the Hargeisa Bypass. The report evaluated the portfolio’s effectiveness, impact, efficiency, relevance, and sustainability, in line with TMA's goal to reduce barriers to trade and enhance business competitiveness across East Africa. / The evaluation assessed that the transport infrastructure portfolio has successfully reduced transport times and costs, significantly improving trade efficiency and regional integration during the Strategy 2 period. For example, at the Goli/Mahagi OSBP, the time taken to cross the border was reduced by 58%, while at the Nimule/Elegu OSBP crossing times were cut by 83%. Over the evaluation period, Mombasa Roads saw a 46% reduction in travel time, and the Hargeisa Bypass reduced travel times by 25%. These reductions in time were accompanied by significant cost savings. In Mombasa, transport and clearance costs decreased by 62%, while in Somaliland, the reduction was 40%. At the Goli OSBP, there was also a notable reduction in bribes and facilitation fees, with a reported 96% drop in these informal payments. The improvements in efficiency have had a positive impact on trade flows, market access, and the overall functioning of regional trade corridors.

Date of last narrative financial report	November 2025 (for the current/ongoing programme)	Date of last audited annual statement	4 December 2024