Programme Completion Review

Title: Somaliland Development Fund II (SDF2)
Final Programme Spend £ (full life): / £23.65 million (from £25 million)	Review Date:	30/06/2025
Programme Code: 300368	Start Date: / 04/2018	End Date: 30/06/2025

Summary of Programme Performance

Year	2018	2019	2020	2021	2022	2023	2024	2025
Programme Score	A	A	A	A	A	A	A	A
Residual Risk Exposure Rating	Moderate	Moderate	Major	Major	Moderate	Moderate	Major	Major

DevTracker Link to Business Case (and any addendum):	https://devtracker.dfid.gov.uk/projects/GB-GOV-1-300368
DevTracker Links to all logframes used during programme lifetime:	https://devtracker.dfid.gov.uk/projects/GB-GOV-1-300368

A. Summary and Overview

Description of the programme and what it has achieved

The Somaliland Development Fund (SDF) was first established in 2012 as a multi-donor programme to support sustainable infrastructure development in Somaliland. The SDF delivers investments that spur job creation and catalyse growth, while laying the foundation for longer-term development, leading to a more stable, peaceful, and resilient Somaliland. The programme is partially led by the Somaliland authorities (SLA). This helps build their capacity and strengthen public service delivery more broadly.

The Somaliland Development Fund Phase II (SDF2) was the second phase of the SDF, a £62.39M programme, with a final UK contribution totalling £23.65M (reduced from the £25M envisaged in the business case). SDF2 began in 2018 and was due to finish in March 2024, but was eventually extended to March 2025 to ensure the completion of two final projects. SDF2 was funded by the UK, Denmark, Netherlands, and Norway, and Mott MacDonald was competitively contracted as the Fund Manager. SDF2 was designed to build on the achievements of the first phase, but with more strategically prioritised sectors for investment aligned with the Somaliland National Development Plan (NDP), a shift from smaller projects, spread thinly, to larger more transformative projects, and a focus on addressing regional equity and Gender Equality and Social Inclusion (GESI). SDF2 also aimed to make greater use of SLA systems and rehabilitate existing infrastructure as well as deliver new projects, by way of encouraging a transfer of responsibility to SLA. A third phase of the SDF (SDF3) will be led by Denmark with assistance from the UK, Norway and the Netherlands, subject to available funding.

Operating context and achievements

During implementation, SDF2 faced various challenges and was exposed to several delivery risks. In the first quarter of 2020, COVID-19 lockdowns resulted in activities being either disrupted or halted. The subsequent reprioritisation of resources and activities of both the SLA and the UK, towards the COVID-19 response resulted in a reduction of interventions and geographical scope. Inflation followed, which led to a rise in the price of commodities required to implement activities, further reducing coverage. Somaliland also experienced drought in October 2020, following three seasons of consecutive below-average rainfall. The most severely affected regions were Sool, Sanaag and Togdheer, where huge numbers of livestock died. In 2022, the rains again were below average, with 800,000 people experiencing acute food shortages in January 2022. The final major event to impact SDF2 was the Las Anod conflict and anti-Somaliland protests which commenced in late 2022 in the capital of the Sool region. Whilst SDF2 was not implementing in the Sool region, the conflict did obstruct the movement of goods, people and businesses. It also led to a redirection of SLA’s spending towards stability. Over the last year of implementation, SDF2 continued to deliver in a challenging operational context with disruption of global supply chains impacting procurement processes and delivery of goods. The Houthi attacks to ships on the Red Sea during 2023 and 2024 led to a slight disruption and delay in electro-mechanic items required for the Boroma water supply. Another significant event which occurred during programme implementation was the issue surrounding Ethiopia and Somaliland Memorandum of Understanding, but this had no significant impact on the delivery of the programme.
[note] Rift Valley Institute, (2022), What are the causes of Somaliland’s drought crisis?
[note] FCDO, (2024), SDF2 Annual Review

Elections were held in November 2024, resulting in a change of administration. Despite the delays and heightened political tensions in the lead-up to the polls, the electoral process was largely peaceful, culminating in a smooth and credible transfer of power to a new administration, an important step forward for Somaliland’s democratic process. Since assuming office, the new administration has signalled a constructive and conciliatory approach. It has stated a clear commitment to resolving internal differences peacefully and strengthening unity. Its early engagement with development partners has also been constructive. However, Somaliland still faces key challenges. These include weak governance systems, complex clan dynamics, and ongoing concerns about fair distribution of resources. Somaliland’s relationship with Mogadishu remains strained.

Despite the challenges, SDF2 has consistently delivered against outputs, scoring an A in every year of implementation. Success has been due to the ability of the Fund Manager to deliver a strong performance, the programme’s ability to flex and adapt in the face of external challenges, and the ability of SDF2 to leverage other donor funding in the face of budget constraints (including FCDO’s). FCDO programme staff, including cross-cutting advisers and programme support, have also facilitated close coordination and ownership between the Secretariat, FCDO and other donors, resulting in effective and efficient delivery.

For this programme closure review, SDF2 scores an A overall with a range of scores across the five outputs from C to A+. It should also be noted that output 1 (10% weighting) measuring SLA capacity built, was not ambitious enough. There were no major concerns with the other output indicators. The logframe and targets have not changed significantly since the start of the programme. However, outputs 3.1 and 4.1 were amended to take account of the one-year extension to finalise the delivery of the roads and water projects. Outcome 1.4 was also added in the final year to account for the finalisation of the projects. The A overall is a fair rating for the delivery of outputs by a programme operating within a difficult context. Output results are summarised below:

Output	Score	Weighting
Output 1: Increased MDAs’ capacity in public resource management through planning and implementation of conflict sensitive, inclusive, economically sustainable, and resilience priority sectoral investments	A	10%
Output 2: Improved community level governance and management capacity through enhanced participation, inclusion, transparency and accountability	A	10%
Output 3: Improved economically strategic transport infrastructure is developed and maintained to promote inclusive economic growth	A+	30%
Output 4: Improved access to maintained WASH infrastructure and services in urban and rural areas to promote inclusive integrated social development	C	25%
Output 5: Improved productive and environmental management sectors enhancing incomes, food security and livelihoods, natural resources, watershed management and resilience	A+	25%

Major lessons learned, evidence generated and recommendations [1/2 page]

Lessons
- During SDF2 the involvement and influence (both direct and indirect) of key public figures in implementing agencies/ companies has sometimes shaped the execution and running of services. In some cases, such influence can have positive impacts such as helping to speed up progress, but on the other hand, it can lead to lack of transparency, accountability and rent-seeking behaviour.
- There is a trade-off between large projects which deliver tangible and well recognised infrastructure, and smaller projects with wider reach. The larger projects can increase the authorities’ visibility and help to build trust from the public. However, smaller investments can reach more people, mitigate elite capture and help with equitability of benefits.
- SDF has so far been too optimistic about the timeframes for SLA ownership. The SLA does not yet have the capacity and capability to manage the fund and often deprioritise their maintenance responsibilities. The lack of available local skills in key areas such as engineering, also creates challenges. The transition towards SLA ownership is therefore a long-term process that requires building more incentives, resources, willingness and transparency. It could be argued that as the citizen-state contract strengthens and revenue from services are realised, SLA incentives to take responsibility not only of delivery, but also of surrounding policy, legislation and ongoing maintenance, may increase. A major challenge has been effective governance and a functioning civil service, with the technical skills to manage large contracts. This brings about a reputational risk, in terms of asset maintenance and quality in the longer term.
- There is a need for tighter coordination of donor funded projects to maximise efficiency and effectiveness of interventions. For example, Kreditanstalt für Wiederaufbau (KfW) and Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) are currently implementing water infrastructure projects, but there has been limited interaction between them and the Fund Manager of SDF. Improved coordination will also enhance the oversight role of the Ministries, which is critical for ensuring greater government ownership, quality assurance, adherence to standards and long-term sustainability.
- There is a lack of clarity on the roles of ministries, including who should lead projects and how they should be coordinated. Whilst the National Development Plan (NDP) provides a roadmap for development and the President’s priorities, there is no method for tracking ministerial progress towards goals. The plan is also ambitious for a context with the size, capacity and issues faced by Somaliland.

Recommendations
- SDF3 should assess project activities for their ability to deliver equitable impacts and be more explicit about trade-offs for growth and inclusion, since these objectives may not always align. Where such trades-offs are necessary, SDF3 must seek other opportunities for inclusion e.g. partnering with universities to recruit female engineers for construction or providing more opportunities for qualified women to hold senior positions within the implementing teams or the fund manager. There should also be early and inclusive community engagement for projects and ensuring women are involved in the planning stages. Output and outcome indicators should also have targets for inclusion of different groups to incentivise action at the start of the projects.
- SDF 3 should make explicit it’s contribution towards building the citizen-state social contract, even if this might take longer than the programme lifetime. This would help guide the programme in implementation and identify relevant assumptions to be tested, such as whether citizens perceive SDF projects as being led by SLA, donor or private sector led. Delivery approaches can then be tweaked accordingly e.g. ensuring SLA only branding, direct ministry involvement in community consultation or identifying mechanisms to hold ministries to account for maintenance.
- Capacity building and organisational learning culture are required for transformative impacts, and these should be designed and comprehensively measured, with longer term views, even if SDF might be delivering over the medium term. This approach would result in more realistic target setting and more relevant indicators. SDF should retain the plan for the SLA taking over the fund in the future, but with well thought-out incremental targets which indicate more ownership over time.
- For all investments, the SLA should take a conditionality approach when setting up agreements with implementers, to ensure benefits reach end users, particularly for Public, Private Partnerships (PPP). This should include contractual agreements for water tariff reductions and reinvestment for maintenance where relevant. SDF3 should also consider this approach when designing agreements with the SLA, since signed paperwork has proven not to be sufficient.
  [note] A PPP law is now in draft waiting to be passed.
- SDF3 should consider a longer time horizon with regards to issues of climate and environment when selecting projects so that SDF investments have greater longevity for populations and sustainability this should include an assessment of the environmental impacts and the viability of the infrastructure under future climate change scenarios, it could also include management plans that look at the maintenance of the ecosystems that the infrastructure is based upon. For example, the borehole water projects have a limited lifespan, as there was insufficient analysis prior to the borehole drilling on what aquifer management and monitoring was required to maintain flows as demand on the network increased.

Performance of FCDO

FCDO ensured donor funds were spent as per the delegated agreement timelines and within approved project activities. Monitoring of projects was conducted by the programme team, and donor reports included annual financial and quarterly risk reports, annual audits, quarterly progress reviews, annual reviews, and final asset checks. During the programme, all payment requests from Mott were approved on time, ensuring contractors could implement at speed. The FCDO Senior Responsible Officer (SRO), Programme Responsible Officer (PRO) and programme team established and capitalized on the strong working relationship with development partners during implementation. As a result, FCDO successfully leveraged other donor funds during FCDO Official Development Assistance (ODA) cuts, meaning implementation could continue. FCDO was then able to increase its contribution in 2024-2025. The programme team was committed to ensuring long-term sustainability of SDF2 projects and thus ensured sustainability plans were handed over to the relevant institutions, although as discussed in the output narratives below, this was done with varying success.

Seven annual reviews were conducted during the life of the programme (2018 to 2024), all of which scored at least an A. The FCDO team facilitated timely implementation of annual review recommendations, contributing to enhanced quality of SDF2 outputs. FCDO held bi-monthly and monthly meetings with the fund manager, and quarterly meetings with development partners and the SLA, to facilitate effective information flow and effective tackling of challenges.

Performance of Mott MacDonald as Fund Manager

Despite the fragility and high risks in the programme’s operational context, the Fund Manager, Mott MacDonald, demonstrated the ability to deliver consistently. The Fund Manager held regular meetings to ensure partners were well-informed. FCDO received frequent updates on their programme progress discussions with relevant authorities. They also shared accurate budget forecasts and facilitated donor discussions on the budget, providing timely updates on variances and proactively providing management scenarios/options for these. However, the following areas of improvement have been identified for the Fund Manager - higher frequency of communication products and increased proactivity in seeking opportunities to reach a wider audience. As the rest of this review conveys, they also could have focussed more efforts on strategic thinking to ensure outcome level delivery.
During the last 6 months of the programme, Mott worked diligently to fully absorb the budget allocation from FCDO, delivering activities valued at approximately GBP 13.2M against the GBP 13.4 million that was budgeted. The quality of the infrastructure delivered was assessed as high, and the pace of delivery was generally good, with the team working through the month of Ramadan in March 2025 to ensure timely completion. With the programme ending by March 2025, Mott MacDonald put in place agreements to cover a defect liability period so that any defects arising after the project end date would be guaranteed servicing by each contractor. This guarantee period will end in March 2026.

How this report was conducted

This Programme Completion Review was led internally by FCDO staff. It draws on evidence provided by Mott MacDonald including the project final report, quarterly reports, International Climate Finance (ICF) report, and an end of programme value for money analysis. Previous FCDO Annual Reviews and findings from a Sustainability Review of FCDO’s Economic Development Programmes in Somaliland, delivered by FCDO’s third-party monitoring programme have also been used. After a desk review, interviews were conducted in Somaliland over the course of a week, with key stakeholders including the FCDO SDF2 team, relevant ministers and other Somaliland officials, development partners, and the Mott MacDonald implementing team.
[note] Tetra Tech International Development, Third Party Monitoring and Learning Somalia Monitoring Programme III (SMP III), (March 2025), Sustainability Review of FCDO’s Economic Development Programmes in Somaliland, Dissemination Activity Report

Actions following approval of this report

- Resolution of an outstanding payment issue relating to Chongqing Overseas Construction Corporation (COCC): SDF contracted COCC via contract number C101-117 to rehabilitate 12km of road from Sheikh to Laaleys town (50+500 – 82+000), along Burao – Berbera Road. COCC did not fully complete all the contracted works and in April 2024, Mott formally terminated the contract. Guided by the FCDO finance team in Nairobi, an accrual provision was made for the COCC debt in the 2024-25 Overseas Accounting Return (OAR) form and this liability will be discharged once the dispute has been cleared.
- Mott will share the final audit report covering the period Sept 2024 to March 2025. This report will inform fiduciary actions to be undertaken by SDF3 to enhance assurance once the programme is ready for kick-off.
- After the programme ended in March 2025, the FCDO Development Director approved the SDF2 asset disposal plan. Some assets were transferred to the relevant Ministries, Departments, and Agencies implementing projects to use for the sustainability of projects, while the remaining assets were handed over to Denmark for use in SDF3.
- Mott has shared relevant bank guarantees with FCDO, from the contractors for the liability period which caters for any defects that may arise from the projects. FCDO will engage the third-party monitoring (TPM) supplier Tetra Tech and their downstream partner Consilient to monitor projects.
- FCDO will disseminate this Annual Review to relevant stakeholders, both internal and external, ensuring they have access to learning from SDF2 to inform SDF3.

## B: Theory of Change and Outcome Assessment (1-2 pages)

	Starting point		Final result
Budget	GBP 25M		[ GPB 23,657,706.72?]
Timeframe	Jan 2018 – Dec 2022 as per the business case		April 2018 – Jun 2025 - actual implementation dates
Outcomes	1.1 - 0 / 1.2 – 14.6% / 1.3 – 43.5% / 1.4 – N/A	1.1 - 760,300 using services attributable to SDF2 / 1.2 - 22.6% citizens reporting improved service delivery / 1.3 - 30.7% citizens report projects are contributing positively to development / 1.4 - 78% reported improved capacity in project design & management

Overall assessment of programme outcomes, sustainability and VfM [1/2 – 1 page]

The programme has three interrelated outcomes: 1) improved and equitable service delivery to citizens 2) facilitated by SDF2 investments through 3) strengthened institutional capacity to prioritise, deliver, maintain and operationalise Somaliland's investments. It is assessed through four indicators:

Outcome indicator	Result	Rationale
1) Number of citizens using services attributable to SDF2 investments; disaggregated by sex, age, disability and region/area.	85% of the target / 760,300 persons out of a target of 886,300, using services attributable to SDF2 investments. / GESI analysis: / Gender: 40% female / Persons with disabilities: 10% / Age: 19-35 = 30.7%, 36-49 = 27%, 50-65 = 20.2%, 66+ = 22% / Region: Sanaag (1%), Awdal (17%), Maroodijeeh (40%), Saxil (6%) and Togdheer (36.9%).	Limited water connections in Hargeisa and Borama negatively impacted total reach.
2) % of citizens reporting improved service delivery as a result of SDF2 investments in their areas; disaggregated by sex, age, disability and region/area	64.6% of the target / 22.6% against a target of 35%. / Total HHs surveyed = 2,218 / GESI analysis: / Gender: 25.2% male, 21.6% female / Persons with disabilities: 27.1% / Region: Sanaag (43%), Awdal (39%), Maroodijeeh (22%), Saxil (19%) and Togdheer (3%). / Age: under 18 = 21.4%, youth = 20.8%, adults (36-49) = 27.5%, Adults (50-65) 18.2%, over 65 = 22.2%	The least progress was observed in Togdheer Region (livestock project), where the percentage of respondents reporting improved service delivery decreased from 7.7% to 3.4%. It is important to note that beneficiaries in the Togdheer region are mainly nomads, who are always on the move, and thus the surveys sometimes do not capture their perceptions accurately. / Survey results over time: / 2020 = (baseline) 14.6% / 2023 = 9.7% / 2024 = 23.5% / 2025 = 22.6%
3) % of citizens who perceive SDF2 projects are contributing positively to the development of their region; disaggregated by sex, age, disability and region/area	68% of the target / 30.7% against a target of 45.5% / 2020 = 43.5% / 2021/2 = N/A (Covid) / 2023 = 27.7% / 2024 = 36.5% / GESI analysis: / Gender: male HH = 30.8%, f HH= 30.6% / Person with disability in household: 34.1% / Region: Sanaag (58.9%), Awdal (49.8%), Maroodijeeh (27%), Saxil (29.9%) and Togdheer (8.1%). / Age: under 18 = 32.1%, youth = 29.2%, adults (36-49) = 35.3%, Adults (50-65) 25.6%, over 65 = 27.8%	The baseline was done in the backdrop of SDF 1 projects, including a flagship road project in Sahil with 82% positive sentiment. Therefore, the SDF target demonstrated an ambition to maintain satisfaction levels rather than increase them overall. / Despite 17m USD investment through SDF 1 & 2 on water, the city distribution expansion & intensification (the responsibility of Hargeisa Water Agency, the water utility in charge) has not been in tandem with the supply to enable households access piped water supply leading to a decrease in regional sentiment from 46.4% to 27.0%. / However, water trucking dependency in Borama and Hargeisa dropped from 41.1% in 2020 to 21.6% in 2025.
4) Level of capacity within Ministries, Departments and Agencies (MDAs) in the areas of project design and management, technical skills and knowledge, and operation and maintenance	104% of the target (78% out of the 75% target, n=50) reported improvement or strong improvement in project design and management / Total number of individuals surveyed = 64.	Strong results for capacity development by SDF, although mixed perspectives across the MDAs, possibly due to a lack of organisational clarity around project management leadership.

In the September 2021, the SDF Secretariat revised the logframe. Certain indicators were deemed no longer relevant, and milestones were revised due to delays caused by COVID-19 and budget changes factored in. The revised logframe was approved by December 2021. The main changes included a new outcome indicator 1.4 and revised milestones for the reporting period (May 2021-May 2022) to account for the additional results.

As described in the programme summary and overview, SDF2 was operating during a period of multiple shocks, including a currency crisis and high prices from July to December 2024. Even with that backdrop, 6% more people in SDF2 project areas reported increased incomes than those in non-project areas (impact level change). However, there was a real decrease overall due to the contextual challenges. There were minimal disparities between female and male-headed households (HH), and HH with a person(s) with disability. However, income increases for women were limited to the period where project activities were most active, since their participation was peripheral; they benefited most by selling refreshments to contractors. This was partly due to the lack of intentionality within the design of activities, but also because of the structure and culture of society. Men tend to be involved in economic activities that might benefit from infrastructure.
[note] CIDT, University of Wolverhampton, (March 2025), SDF II Fourth Survey

At the outcome level, SDF did not quite achieve the expected final logframe results, with some uncertainty about the sustainability and longer-term impacts. In total, 760,300 people reported using services attributable to SDF2 investments (outcome 1) which was just under the target of 886,300. For outcome indicator 2, attribution to SDF2 specific projects was somewhat difficult to ascertain, with a high proportion of respondents (24.9%) at baseline reporting improved services largely because of SDF 1 investments. As such, the proportion of positive responses dipped in 2023 as the immediate impact of SDF 1 investments wore off, before climbing again in 2024 once the effects of SDF2 investments were realised. Agriculture, fisheries and water services all experienced significant increases in people reporting improved services, whilst livestock experienced a decline. This was due to the ongoing challenges in the sector, including disease, high vulnerability to drought and limited access to veterinary services. In addition, beneficiaries in Togheer are nomadic and their movement may have affected survey results. Comparison with the non-project area data does provide some evidence that SDF2 projects had a net positive impact since survey results outside of SDF2 project areas showed a significant decrease in respondents reporting improved services.
[note] CIDT, University of Wolverhampton, (March 2025), SDF II Fourth Survey

In terms of SDF projects contributing positively to development, whilst reports were largely positive, there were mixed feelings about inclusivity. Evidence from the final survey suggested that certain sectors and communities felt underserved in development efforts and highlighted the importance of addressing regional inequalities in development planning. However, the Joint Steering Committee (JSC) (including development partners which decides on the investments) ensured an inclusive geographical equity distribution of projects such as Maydh Jetty and fisheries project in Sanaag regions, the Livestock Excellence Centre in Togdheer region, and Berbera-Sheikh-Burao road, but there were views that these investments were not always in areas most in need.
[note] Ibid pg. 48

On capacity building, Ministries, Departments and Agencies (MDAs) noted the challenges of bringing about institutional change with a realisation that capacity building at the individual level does not necessarily translate to organisation-wide shifts. Possible factors contributing to this include rigid staffing policies, bureaucratic hierarchies, and lack of project-based incentives. There were also few opportunities for trainees to put their learning into practice since many projects were outsourced, which also points to the lack of technical expertise and qualifications within ministries. Although interviews conducted through the programme closure review process supported these findings, the recent change of administration meant that few interviewees had knowledge of the capacity building initiatives which had taken place. However, all mentioned capacity building as a high priority for the new Somaliland administration.

Although not explicit within the SDF2 theory of change, delivery of services by the SLA is an important mechanism for building the citizen-state social contract. The visibility of the large projects implemented by SDF2, as well as the alignment with the SLA National Development Plans (NDPs) have been an important enabler for this. However, the branding of projects as SDF and the involvement of the private sector in the PPP mechanism for the Borama water infrastructure, has sometimes diminished the SLA’s visibility.
[note] The SLA did not make any contribution to SDF2, but the Ministry of Finance has requested that President consider this for SDF 3.

In terms of value for money (VfM), outcome level results were reasonable with valuable learning that can be applied to SDF3. However, VfM could be increased if monitoring (including annual review processes) took a deeper look at progress towards outcomes and encouraged the programme to pivot based on evidence. If there had been a deeper assessment of the potential for transformative impact within MDAs via capacity building, and a more concerted effort to test and track this, it may have increased outcome level results.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators. [1/2 – 1 page]

Figure 1 SDF2 theory of change
The theory of change for SDF2 was developed at the start of the programme. It has not changed since but has been tested throughout implementation. The expected impact of the SDF2 is to contribute to people being better off as a result of increased economic activity and increased revenue. Specifically, the Fund is expected to lead to the following three outcomes:
1. Improved and equitable service delivery to citizens facilitated by…
2. SDF investments (i.e. rehabilitated infrastructure) through…
3. Strengthened institutional capacity to prioritise, deliver, maintain, and operationalise Somaliland's investments.

The SDF2 ToC assumes that improved and equitable service delivery to citizens, enhanced SLA’s capacity to plan, maintain, and operate investments, and the development of accountable community-based management structures will lead to greater access to improved services and livelihoods, and enhance citizens' perception of SLA and its legitimacy. This is achieved through investments in strategic transport infrastructure, water, sanitation, and hygiene (WASH) infrastructure in urban areas, and improved productive sectors through natural resource management, integrated watershed management, and livelihood support in rural areas.
[note] The latter outcomes – enhancing citizen perception of SLA and its legitimacy are implied within the ToC diagram, but not explicit. See overall recommendations in the “Major lessons learned” section which explains how this should be dealt with in SDF3.

As described in the narrative above, there is some evidence that SDF2 achieved progress towards outcomes and impact, but there were assumptions that did not hold.

Impact:
- There were promising results with regards to people reporting increased income. However, there is evidence that the assumptions on equity of economic opportunities did not hold given that women reported mostly benefiting from the temporary workers employed for construction. Results also varied across sectors with most respondents reporting increased income working in agriculture (21%), followed by water (9%) and roads (7%), and lastly livestock (1%), although it is possible that figures could have been worse in the absence of SDF2 interventions given the drought.
  - Targets in future programmes need to consider the variances across sectors and GESI with regards to the impact of shocks and stresses. GESI considerations should have been explicit in the ToC so that they could drive the design of the programme and help set targets for specific groups.

Outcomes:
- On outcome 1, assumptions with regards to improved service delivery held, although there were disparities across sectors, groups and geographies.
- Findings suggest that although the capacity of civil servants initially increased, transformative and sustained change was not achieved. This was partly due to the organisational culture issues outlined above, but also because of the lack of technical skill within MDAs.
  - Capacity development in SDF 3 would be more effective with more SLA ownership and if an organisation-wide view was taken when designing activities. Institutional analysis, either led or co-led with officials would not only provide a thorough diagnostic of the gaps but would increase ownership of the process and results. The approach should also go beyond identifying individuals to train, to working on issues of organisational culture, values and behaviour, possibly delivering through teams or broader systems.
    [note] FCDO, 2025, Moving to Smart Technical Assistance
  - SDF should be more ambitious when measuring governance change and seek to understand transformative impact. A composite measure which looks across various criteria to understand the depth and breadth of change across MDAs, (possibly requiring evaluation resource), could be used, informed by e.g. the ICF KPI 15 methodology for transformational change, or organisational change assessments.
    [note] International Climate Finance KPI 15 Methodology Note: Extent to which ICF intervention is likely to lead to transformational change
- There were no direct indicators for outcomes 2 and 3 in the theory of change. Therefore, qualitative assessments were made through the annual review process. As covered by output 3, the planned infrastructure investments were delivered, largely on time and to budget. It was also part of the SDF agreements with officials that infrastructure would only be delivered if they agreed to budgeted operations and maintenance plans. However, lack of revenue, reprioritisation, and lack of qualified people to carry out maintenance (such as with the Maydh Jetty that was built through SDF 1) often meant there was no follow-through.
  - There are some signals that the authorities feel some commitment to the sustainability of SDF projects, since budgets are often at least initial put aside. SLA contribution to SDF 3, even if very small, might help to increase ownership and responsibility, but although this was mentioned as a possibility by officials, there is not yet any formal agreement.

Output level results have consistently been achieved throughout SDF, but there are still some challenges to achieving the depth of change envisaged at the outcome level. This is in part due to the challenging operating context, but also programme design, particularly on equity. The theory of change was also overly ambitious with regards to SLA capacity and capability. Results at the output and outcome level provide a relevant overview of SDF3 achievements.

Potential for transformative impact

The SDF2 programme does not include the ICF KPI for transformational change indicator within its logframe. SDF3 should consider including it, if the climate focus within the programme is significant enough, or if not, some similar methodology. Despite the lack of inclusion in the logframe, this Programme Closure Review provides useful evidence in assessing the potential for longer term, systemic change. The ICF KPI 15 methodology proposes that if there is evidence of several criteria being met, there is more chance of achieving transformational/ transformative change (i.e. change that triggers more change, particularly because incentives, motivations are triggered, leading to long-term behaviour change). The relevant criteria to SDF2 include political will and local ownership, capacity and capability increased, increased innovation, scalability and sustainability. Note that there is an additional criterion of “incentives” which is relevant for this assessment but was not included due to lack of evidence and analysis. This criterion also warrants inclusion in SDF3.
[note] To enable FCDO to report on the ICF 15 indicator, climate issues would have to be better integrated into all activities. Assessments of what extent the criteria were achieved would then have to be done through the lens of climate and environment considerations, as opposed to the broader analysis set out in this narrative.

- In terms of political will and ownership, there is evidence that SLA departments recognise its importance, but there is little follow-through with the implementation of maintenance plans. This is due to lack of revenue and competing interests and priorities.
- There were also challenges with implementing sustained and organisational level capacity building within the SLA. Capacity building activities could be more successful if the ambition of systemic organisational change was included in the design. However, SDF2 focussed largely on the delivery of training and mentoring of individuals with little focus on how this translates within organisational cultures. To increase the chances of success in SDF3, the programme must consider the political economy of capacity building initiatives such as hierarchy, team and departmental relationships, performance management and other relevant aspects, which impact the potential for results.
- SDF2 did successfully introduce innovation into the infrastructure such as solar panels which have led to reduced costs for water service delivery. This provides incentives for those responsible for delivery to implement or maintain such models in the future. However, more needs to be done on the aspects of groundwater availability, with a move towards dams to capture surface water. These would be costly to implement and there are no current plans underway to build dams.
- Scalability within the SDF context would mean more projects to meet more end-users, and more breadth across departments delivering. This is somewhat restricted to the size of the fund. SDF3 plans are already underway, but the importance of finding the right balance between large infrastructure projects which provide visibility for SLA, and breadth, is already being considered. Denmark have suggested that they intend to design SDF projects so that they fall between these two extremes.
- Finally, this review has covered sustainability both within Section B above and within the output narratives. There were mixed results on sustainability, with the potential for the water and livelihood projects to continue beyond the programme, but fewer positive indications regarding ongoing maintenance of the roads.

Overall, there is some evidence that SDF has the potential to be transformative, but incentives of political elites are not yet strong enough to ensure the ongoing sustainability of gains. Their capacity is still weak with little evidence that SDF2 activities have been able to deliver much impact in this area. A more intentional programme design, political economy analysis, analysis of systems and holistic approaches with regards to capacity building, will be required in SDF3 to meet more of these criteria. Note also that the ICF methodology also suggests that the longer SDF continues, and the more scale which is reached across departments and for end users of services, the more likely it is that transformative impact will be achieved. So far, scale has been quite limited particularly on the SLA side.
## C: Detailed Output Assessment [aim for max. 1 page per output. Repeat for each output]

Output Number and Title	Output 1: Increased MDAs’ capacity in public resource management through planning and implementation of conflict sensitive, inclusive, economically sustainable, and resilience priority sectoral investments
Output Score	A
Impact weighting (%)	10%		Impact weighting revised since last AR?	No

Output Indicator		Starting Target	Final Logframe Target	Final Result Achieved
1.1 Level of institutional knowledge in climate risk management focusing on Agriculture, Fisheries, Livestock and Water Supply sectors as a result of SDF2 investments / (ICF KPI 14) – Rating 0-6 (0: do not know, 6: fully knowledgeable)		5.0 as per rating scale / achieved by March 2024 / (SDF2 Logframe September 2021)	5 as per rating scale	A / 5.1 (13 respondents) / (2024 survey result. Note that the baseline assessment of 35 respondents score was 0)
1.2 Number of SDF2 supported MDA staff that demonstrate improved project design and implementation knowledge as a result of on the job and in-service training		85 / achieved by March 2024 / (SDF2 Logframe September 2021)	25% of all trainees report practicing and / implementing imparted skills in various / subjects	A++ / 78% (no = 141 participants, including 44 females)
1.3 Number of MDAs budgeting and spending on operation and maintenance in SDF2 supported sectors as per commitments made in the respective sustainability plans		5 out of 7 MDAs / achieved by March 2024 / (SDF2 Logframe September 2021)	7 out of 7 MDAs	B / 6 out of 7 MDAs
1.4 Number of SDF2 projects executed on time (and on budget (with 15% deviation); demonstrating improved planning and implementation		10 out of 10 projects / achieved by March 2024 / (SDF2 Logframe September 2021)	12 out of 12 projects	A / 100% no = 12 with an average deviation on budget of 2%, 8% and 15% and on time of 10%.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score. [1/2 page]

Output one tracks the capacity development of civil servants in 3 areas: project delivery and management; climate risk management; and technical skills (e.g. roads, water, GIS etc.). Results demonstrate good performance, with all targets being met. However, there is little evidence that this contributed to outcome level change (see outcome narrative above for more details, as well as the supporting narrative below).

Output indicators 1.1. and 1.2: On climate risk management, respondents were asked how confident they felt in applying the new skills and knowledge, with 87% responding positively. However, a relatively small number of individuals were involved in the practical application of knowledge, despite careful selection of participant selection. A similarly high proportion of respondents (78%) reported increased capacity in project performance, however, again there were few opportunities for trainees to put these skills into practice and little evidence that these led to broader institutional capacity gains. Although not an output level indicator, there was evidence of increased ability of contractors to write high-quality tenders in accordance with industry standards, a positive unintended outcome.
[note] Ibid pg. 55

Output 1.3: With regards to sustainability, MDAs were expected to provide budgets for operation and maintenance of SDF2 projects. Results were mixed for 3 of the ministries with some projects demonstrating good practice and others not. There was also evidence that sustainability planning (if not delivery) became more robust and transparent and that a small number of project management staff had increased capacity in this topic. In addition, 4 of the 5 MDAs had assumed costs for staffing and equipment, but three were challenges such as delays in signing a framework, agreeing legalities, disputes and gaps in community level structures which hindered progress.

Note also that during SDF1 and SDF2, there was collaboration with the Somaliland Civil Service Commission (CSI), which is an institution dedicated to public sector learning and capacity building. This included delivery of project management training to the project management teams. During SDF1, the CSI also provided understudies. Under SDF2, this relationship was taken further where the CSI provided expertise with the SDF Secretariat providing backstopping through CIDT.

Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]

Lessons
During the interviews the lack of technical expertise and reliance on contractors and international experts within ministries was a challenge to capacity building gains within SLA. The lack of opportunity for MDA staff to apply their knowledge, is probably also limited because projects require technical skills and qualifications which are not always available in Somaliland.

Recommendations
[note] Refer to the outcome level discussion (section B) for more information on learning and recommendations with regards to capacity building.
- SDF 3 should continue working with the Civil Service Commission to explore opportunities for broader change. This should include policy development and enforcement for recruitment, HR, and development of the civil service.
- To ensure a more systemic approach to conflict and inclusion, there should be an effort to include and measure these subjects in capacity development initiatives.

The UK holds a close and historic relationship with the SLA. The British Office Hargeisa will consult with the relevant ministries on the lessons learned from this review by sharing with the SDF secretariat and working through the implementing partner to ensure lessons are disseminated to relevant Somaliland stakeholders. These recommendations will be shared with Denmark who are leading the next iteration of the SDF.

Output Number and Title	Output 2: Improved community level governance and management capacity through enhanced participation, inclusion, transparency and accountability
Output Score	A
Impact weighting (%)	10%	Impact weighting revised since last AR?	No

Output Indicator	Starting Target	Final Logframe Target	Final Result Achieved
Number of inclusive community level structures put in place/reactivated; that are active in consultations during the entire project life cycle in adherence to programming principles (GESI, ESIA, Conflict Sensitive Programming, climate risk assessment)	45 community level structures / achieved by March 2024 / (SDF2 Logframe September 2021)	48 community level structures	49 community level structures / B / (102%) / 33% female against a target of 20%
Number of people actively involved in SDF2 Projects (Consultations, Planning, Implementing, Delivery & Management); disaggregated by sex, age, disability and region/area	5,000 people / achieved by March 2024 / (SDF2 Logframe September 2021)	5,500 people	A+ / 7087 people (129%) / GESI analysis: / Gender: 21% female, 79% male / Disability: 15% / Region: Sanaag (9%), Awdal (36%), Maroodijeeh (10%), Saxil (15%) and Togdheer (26.3%). / Age: 19-35 = 29.2%, 36-49 = 17.4%%, 50-65 = 25.6%, 66+ = 27.8%
Perception of elected community structures' members and beneficiaries on participation / accountability / transparency in SDF2 projects' implementation; disaggregated by sex, age, disability, and region/area – Rating 1-3 (1: poor, 2: good, 3: excellent)	2.5 / achieved by March 2024 / (SDF2 Logframe September 2021)	2.7	B / 2.1 (78%)

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score. [1/2 page]

Output 2 aimed to enhance governance and management capacity at the community level by promoting greater participation, inclusion, transparency, and accountability. The purpose was to strengthen long term operation and maintenance of infrastructure. To achieve this, community structures were established/ reactivated/ trained and actively engaged in consultations and activities throughout the project's lifecycle. Training included subjects such as leadership and organisational management, conflict and grievance management, financial literacy, and understanding of marginalisation and gender norms. Sector specific training was also provided e.g. crop production, fodder production, fish catch quality management, watershed management, and water point management. SDF2 also aimed to build SLA capacity for community engagement by appointing cross-cutting officers in sectoral ministries and providing training to technical officers.

The output targets omitted to set expectations for inclusion, although evidence from the Fund Manager suggest that this varied across community groups and more could have been done to address it. In some cases, women were integrated into existing Village Development Committees to address imbalances, and in others, separate groups for women were set up. Despite efforts by SDF2 to include women in community events, or training, women’s involvement was more symbolic than active. There was also little progress on integrating people with disabilities. There is some evidence to suggest that this is largely due to social norms, and the programme’s experience demonstrates that gender-transformative and inclusive attitudes and practices take time to embed. For example, male committee members often saw the role of women as providing insights on “women’s issues”.

The community-level structures were trained to actively support the implementation of the projects, for example in land acquisition, organising unskilled labour or mediating conflicts. Committees formed under agriculture and livestock, although seasonably driven, met frequently and played a critical role in the maintenance of water infrastructure. There was also evidence that community structures understood the limitations of external support and took responsibility for maintenance and community awareness raising. Their shared sense of responsibility led to collective action including pooling funds for repairs and improvements. Shaba, the private company responsible for the Borama Water project, reported that the water committee also played an important role in mitigating conflict when pastoralists and livestock entered the local area, destroying soil bunds.

The final indicator is a measure of 3 aspects of community involvement: participation, accountability, transparency and inclusion. A survey of 519 households found that 51% agreed that they were consulted and able to influence services. Accountability was the highest scoring component with 61% of households reporting that there were agreed terms of office and regular meetings to re-elect committee members. The transparency component fluctuated over time with mixed views, especially on the selection process for beneficiaries. Inclusion was the lowest scoring component, despite committees encouraging quotas for women and youth; 35% of respondents stated that project committee members were all men, and most committees only had one or two women. Where women were present, they did not always feel able to participate in practice. People with disabilities were also often excluded. Interviews with SLA staff and the Fund Manager suggest that inclusivity needs to be more deliberate with earlier and more inclusive community engagement. Consideration of GESI in the ToC would also help identify key points for inclusion.

Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]

Lessons
In rural areas, community management of infrastructure is often the best and most sustainable mechanism for provision of services, unlike big cities where you can achieve economies of scale. However, communities also require capacity building to be effective and ensure inclusion.

Recommendations
- SDF 3 should consider how to meaningfully and inclusively engage communities at the planning stage. SDF3 could also identify and consult with key stakeholders such as civil society, women’s rights or disability organisations as readily formed avenues for consultation. There should also be a shared vision amongst central and local government, community governance structures and the local community about the purpose of engagement and approaches to local ownership.
- SDF3 should consider undertaking formative research and analysis to understand stakeholders, their relationships, existing systems of participation, which groups are marginalised and how, local power dynamics and the way in which power is expressed. This should lead to more effective approaches for community engagement e.g. moving beyond a focus on formal processes and procedures, to building capacity on critical reflection and active participation, and ensuring that feedback loops with communities are prioritised.

As with all learning and recommendations in this report, the British Office Hargeisa will consult with the relevant ministries, SDF secretariat, implementing partners and Denmark to ensure dissemination to relevant stakeholders.

Output Number and Title		Output 3: Improved economically strategic transport infrastructure is developed and maintained to promote inclusive economic growth
Output Score		A+
Impact weighting (%)		30%	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
Aggregated SDF2 road service level – % change in travel time on roads rehabilitated with SDF2 support (INF_09.01)	21% reduction in / travel time (110 / minutes) as a / result of / completed 62km / of road and 4 / bridge decks on / Burao-Berbera / Road / achieved by March 2024 / (SDF2 Logframe September 2021)		21% reduction in travel time (110 minutes) as a result of completed 132km of road and 4 bridge decks on Burao-Berbera Road	A++ / 55% reduction in travel time from 279.2 to 125.1 minutes by 2025 (154.1 minutes)
Jetty capacity utilisation (INF_09.03) (Also related to indicator 5.3)	70% / achieved by March 2024 / (SDF2 Logframe September 2021)		70%	A / 64.8% (2024 survey) / 93% of the target achieved

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score. [1/2 page]

Strategic transport infrastructure investments initially focused on the rehabilitation of the Burao – Sheikh Road which included resurfacing of 62km of highway (completed in March 2024), improved drainage, rehabilitated bridges and installed traffic furniture. During the extension phase (from March 2024 to March 2025) another 78 km between Sheikh and Berbera was rehabilitated to bring the total length to 140 km. The road rehabilitation improves transport connectivity, enhances the movement of goods and services between Berbera and Burao, facilitates faster access to Berbera Port and connects the Eastern Somaliland hinterland, known as the livestock hub, to Berbera. Also included as a part of SDF2 transport infrastructure was the construction of a 165m Jetty in Maydh, Sanaag region completed in March 2022. The jetty was identified as one of the several ports and harbours identified for development the National Development Plan II (NDPII), to improve interconnectivity by sea between Berbera, the hinterland of Sanaag and parts of Toghdeer regions. The new jetty supports the fisheries and livestock value chain, as well as the export of other products and import of general goods.

In terms of sustainability, SDF2 provided equipment to the Ministry of Transport and Road Development for operations and maintenance. The Ministry reported that the quality of the road’s infrastructure is excellent and the provision of vehicles by the programme means they can continue to monitor the condition of the road. The roads are expected to last for 50 years minimum and have a guarantee until March 2026. However, whether SLA will provide ongoing budget for maintenance is still unclear, even though the Somaliland Roads Authority Agency is committed the operation and maintenance work and has already set-up a maintenance unit for the roads. There is also a lack of technical capability within the MDA for the upkeep of roads and bringing in international expertise is costly.

A survey conducted in 2024 of the Maydh Jetty suggested a significant increase in utilisation since the baseline, to 64.8%. However, this is also within the context of a drop in international trading from 72.2% to 58.1%. New fishing businesses (58.1%) and daily boat arrivals (74.3%) increased. The local community views the jetty as mixed-use infrastructure, since it has been constructed in a way that allows small ruminants (goats and sheep) to be transported to Berbera by sea to the export livestock pre-quarantine facility instead of by road. It is estimated that 8,0000 been exported through this port since inception.

Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]

Lessons
- Whilst ministries were positive about the impact of infrastructure and grateful to FCDO, it was felt that “soft infrastructure” was neglected during SDF2. This includes the systems, regulations and policies surrounding infrastructure for things like revenue collection, budgeting, and monitoring and evaluation. However, there were also there’s evidence that often policies and regulations have not been well implemented in the past. Ministry of Planning did sight that there was now a policy implementation plan, but time will tell whether this will be actioned. The SLA are cognisant of delays in implementing policies and regulations which catalyse transformative development. There are positive signs of an effort to establish a unit which would work across ministries to improve this.
- Bigger projects do not necessarily result in better projects, and it is the processes that influence the quality of infrastructure the most. The Ministry of Transport and Roads Development were complimentary about the ability of SDF to deliver quality compared to other donor projects, citing open competition for jobs, international expertise and close supervision by the Fund Manager and the SLA as enablers.

Recommendations
- As well as providing general capacity building projects, SDF 3 could investigate what opportunities there might be to build technical capability. This could include more formal partnerships with universities including work placements.
- Exit strategies should be well thought through. SDF 3 for example, could provide a specific component which assesses gaps which jeopardise the sustainability of infrastructure built in previous SDF programmes and work with the authorities to find workable solutions.

As with all learning and recommendations in this report, the British Office Hargeisa will consult with the relevant ministries, SDF secretariat, implementing partners and Denmark to ensure dissemination to relevant stakeholders.

Output Number and Title		Output 4: Improved access to maintained WASH infrastructure and services in urban and rural areas to promote inclusive integrated social development
Output Score		C
Impact weighting (%)		25%	Impact weighting revised since last AR?	Yes

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
Number of beneficiaries using safe and affordable drinking water for domestic use of an improved water source (Access is 200m for Urban) (WSH_06.01); disaggregated by sex, age, disability and region/area	133,000 / beneficiaries / using safe water / and affordable / water in Hargeisa / and Borama within 200m walking / distance / achieved by March 2024 / (SDF2 Logframe September 2021)		146,500 beneficiaries using safe water and affordable water in Hargeisa and Borama within 200m walking distance	C / 31.7% of the target achieved / 46,500 beneficiaries using safe water within 200m walking distance / GESI analysis: / Gender: 60% female, 40% male / Disability: 10% / Region: Awdal (30%), Maroodijeeh (70%)
% of households who report change in cost of potable water in Urban areas supported by SDF2	30% / achieved by March 2024 / (SDF2 Logframe September 2021)		50% (Borama and Hargeisa)	C / 47.3% of the target achieved / 14.2% of households reported a reduction in the cost of water

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score. [1/2 page]

This output tracked the progress of water supply infrastructure in Borama and Hargeisa. The Hargeisa Water Authority (HWA) is a fully public entity providing water to Hargeisa whilst Borama water is delivered through a PPP with a company called Shaba. Both are responsible for the distribution network to get water to households. The PPP arrangement is “Operate Only” where all assets developed by SDF belong to the central authorities, but Shaba is responsible for operations. The SDF2 activity included the drilling of boreholes, laying of transmission pipeline, as well as installation of other ancillary infrastructure such as solar panels, generators, pumps and tanks. The solar installations have significantly reduced reliance on diesel generators.

The first output indicator encompasses three metrics: accessibility, safety and affordability. The indicator significantly underachieved against the targets set for number of people accessing safe and affordable water in Hargeisa and Borama. Whilst an impressive 363,300 people reported access to water within 200m in total, the high cost reduced overall performance against this output target, with only 146,500 people accessing safe and affordable water. In Hargeisa, 36.3% of households reported a reduction in costs in 2023, but this dropped to only 9.3% in 2024, before increasing to 17.4% in 2025. In Borama, the proportion of households reporting more affordable water decreased from 31.6% in 2023, to 5.7% in 2024, before dropping again to 4% in 2025. The cost of water remains high in both cities, at $1.2 m3 in Hargeisa, and $1.5 in Borama. The water distribution network into residential areas by the water utility companies has been slow, hence not fully utilising the water produced by SDF investments. Surveys did indicate that water trucking dependency in project areas dropped from 41.1% in 2020 to 21.6% in 2025. In Borama, it decreased from 15.4% to 11.9%, and in Hargeisa from 48.1% to 25.2%. In terms on inclusion, in Borama, the development included pipeline connecting an Internally Displaced Persons camp. In Hargeisa, water kiosks service IDP areas and water carts and trucks distribute subsidised water.

Whilst HWA has manged to reinvest revenue to provide additional infrastructure (they were recently able to acquire a drill and have installed a new borehole), Shaba have not yet made any such progress. HWA have also attracted additional investment from donors, such as GIZ for lab testing and received a loan from Salama bank. It should be noted that the construction of infrastructure in Borama was only completed in March 2025, and reportedly, studies are still ongoing to understand the real cost per unit of water to inform tariff reductions and increase reach.

In terms of environmental sustainability, the water infrastructure projects require extraction of groundwater. Recharge has been assessed at both sites and is closely monitored. At both locations, there is an acknowledgement that in the long-term groundwater cannot be relied upon and so options for surface water collection (dams) are being investigated. HWA has already constructed a dam on the outskirts of Hargeisa ($3M-$5M investment made mostly from their revenue), and SDF carried out an assessment which located other potential dam sites. KfW is now leading a new more in-depth assessment to build on the SDF one. An assessment has also been carried out for Borama by Shaba, but funding has not yet been identified, and the requested budget was large at $25M.

Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]

Lessons
- PPP and public provision of services both have pros and cons. The PPP arrangement comes with investment from the private sector for the delivery of infrastructure and services. However, since the private sector is primarily driven by profit the benefits for end users are, at least in this example, are more limited. The water utility in Hargeisa operates as a semi-autonomous entity under the Ministry of Water, which provides a more structured and potentially more sustainable framework.
- One of the key challenges facing water provision by Shaba is the robustness of the PPP agreement. This is partly because Somaliland lacks an operational law or policy governing PPPs and the absence of a legal framework makes it difficult to ensure efficiency and sustainability. It is crucial that the finalization of the PPP law precedes any future investments under this model.

Recommendations
- The Ministry of Water should document their learning from the PPP in Borama, and public delivery in Hargeisa. This should include cost-benefit analysis, and list challenges and opportunities so that it can guide their approach in other locations. It should also set out the approach for the two scenarios for fair pricing i.e. 1) where there is competition to drive down prices, or 2) in situations where regulation is required. SDF 3 should consider whether support to this activity.
- More needs to be done to address the affordability of services provided by SDF investments. This could include prior agreements with implementing agencies and the private sector on how far tariffs should be reduced for end users and by when (see the section above on major lessons learned re. recommendation for a conditionality approach).
- There needs to be more coordination led by the central authorities for all infrastructure projects. There was a good example of coordination and layering of efforts from the KFW assessment, which built on the SDF dam assessment (see output 4). World Bank is also looking into a potential energy project in Borama which could present further such opportunities. The SLA should be responsible for holding at least a quarterly meeting to convene all donors working in Somaliland and encourage more coordination.

As with all learning and recommendations in this report, the British Office Hargeisa will consult with the relevant ministries, SDF secretariat, implementing partners and Denmark to ensure dissemination to relevant stakeholders.

Output Number and Title	Output 5: Improved productive and environmental management sectors enhancing incomes, food security and livelihoods, natural resources, watershed management and resilience
Output Score	A+
Impact weighting (%)	25%		Impact weighting revised since last AR?	Yes, up from 20%

Output Indicator		Starting Target	Final Logframe Target	Final Result Achieved
1. Change in hay yield per hectare in the irrigated fodder areas supported by SDF2		400 ha of land under irrigated fodder production resulting into a yield of 4 tonne/ha / achieved by March 2024 / (SDF2 Logframe September 2021)	400 ha of land under irrigated / fodder production resulting into / a yield of 4.5 tonne/ha	A++ / 200% / 800 hectares of land that averaged 4.62 tonnes per hectare
2. Change in agricultural production yield per hectare for beneficiaries directly benefiting and practicing SDF2 Agricultural interventions (PRO_02.02)		10,000 Hectares of land protected/rehabilitated/stabilised through construction of 489,500 metres of large soil bunds and 3,335 Hectares of treated land / planted with crops resulting into a yield of 0.8 tonnes/ha / achieved by March 2024 / (SDF2 Logframe September 2021)	10,000 Hectares of land / protected/rehabilitated/stabilised through construction of 489,500 metres of large soil bunds and 3,335 Hectares of treated land / planted with crops resulting into a yield of 0.8 tonnes/ha	A / 91% of the target / 100% of the target / 97.8% of the target / 9,111 hectares through construction of 490,038 metres of soil bunds resulting in 0.75 tonnes/ha
3. Change of fish harvested and cold stored from SDF2 supported project areas (PRO_02.04)		1,500 tonnes/year / achieved by March 2024 / (SDF2 Logframe September 2021)	1,500 tonnes/year	A+ / 111% of the target / 1,667 tonnes per year
4. Number of people with improved resilience as a result of SDF2 investments in productive and environmental management sectors; disaggregated by sex, age, disability and region/area (ICF KPI 4)		29,250 persons / achieved by March 2024 / (SDF2 Logframe September 2021)	29,250 persons	A++ / 257.8% of the target / 75,414 people with improved resilience / GESI analysis: / Gender: 60% female, 40% male / Disability: 10% / Region: Sanaag (0.5%), Awdal (70%), (15%) and Togdheer (29.5%). / Age: 19-35 = 30.8%, 36-49 = 27%, 50-65 = 20.2%, 66+ = 22%

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score. [1/2 page]

This output included 3 projects:
[note] An interview was conducted with the Ministry of Agriculture, but the Ministries of Livestock and Fisheries were unavailable.
- The livestock project delivered fodder production and facilitated the conversion of the Aroori livestock holding ground (LHG) to the Aroori Livestock Centre of Excellence (ALCE) in Togheer. The ALCE would implement the long-term vision of applied research, training, livestock disease surveillance, demonstration and extension services.
- The agriculture project aimed at improving production in the Durdur Ad Catchment through soil and water conservation activities (e.g. construction of bunds, dams and support for improved farming methods).
- The fisheries project in Sanaag built the capacity of fishing communities through co-operative societies, providing modern equipment, and building critical infrastructure to strengthen the value chain.

Output 5 moderately exceeded expectations overall. With regards to fodder production, the existing diversion system (weir) was rehabilitated resulting in approximately 800 hectares of land being irrigated against an expected 400 hectares. Eight hectares of demonstration farms were also established, helping to share best practices in fodder production, animal husbandry, feeding and storage. The ACLE now houses a group of young livestock and offer experts who conduct applied research and provide best practices on the health and wellbeing of livestock. Although livestock respondents were least likely to report household income increases, their physical capital stock either increased or remained the same even after the recent droughts.

On agriculture, the projects aimed to mitigate land degradation and increase crop yields through natural resource management, watershed management and introducing integrated soil and water conservation techniques. The initiatives focused on climate adaptation to assist agro-pastoralists in responding to climate change through sustainable land management strategies. There was an increase in the proportion of respondents reporting increased yields per ha, from 14% at baseline to 21% in 2025.

The fisheries project faced significant delays due to insecurity in the Eastern region which hindered the transport of equipment. Despite this, the activity delivered good results. The combined effects of the completion of the jetty, and the functioning ice making facility resulted in greater aggregation of fish, and the access of larger vessels transporting the fish from Maydh to factories in Berbera. The catch has also been increasing since the fishers fully put into use the fishing equipment and the cost of storage reduced as the ice making and cold storage facilities will run with power from installed solar system.

Initially the SDF2 business case did not include a focus on climate, but at the request of the Netherlands the International Climate Finance resilience indicator was included to ensure climate-related aspects were addressed. In 2020, due to FCDO budget reprioritisations, SDF2 had to reduce some activities, and ensure remaining ones would align with International Climate Finance objectives. As such activities in the agriculture and livestock sectors were adapted. The activities delivered led to reported improvements in the resilience of people involved, with 87.3% reporting improved resilience in 2025, up from just 17.3% in 2020. The combination of better resource management, innovative farming techniques, and effective preservation methods has empowered communities to withstand environmental and economic challenges more effectively.
[note] KPI 4 Methodology: Number of people whose resilience has been improved as a result of ICF (September 2019)

Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]

Lessons
- Early and continuous involvement of local communities greatly improved the ownership, implementation and maintenance of land management activities.
- Site selection seems to have prioritised technical requirements and scale (number of farmers in the area) as well a geographical spread. However, there was limited focus on assessing the potential for impacts on women and people with disabilities. (Previous recommendations include a GESI informed ToC).

Recommendations
- During interviews it became apparent that KFW are now delivering a similar agriculture project in another location, although approaches being applied are different. There is a need for more coordination of activities by the SLA to prevent any duplication of efforts and share learning. This would provide more standardisation across investments and provide the SLA with more ability to influence. (See also recommendations under output 4).
- In agriculture, SDF 3 should ensure integrated practices rather than partial interventions, even if it means investment is more focussed geographically. For example, a single location requires physical and biological soil and water conservation, irrigation, crop production, rehabilitation of roads, links to markets etc. This may not all fall to the responsibility of SDF 3, but increased coordination with donors and other relevant stakeholders would make interventions for effective.
- Community capacity building is critical for success, inclusion and sustainability. Establishment of proper community development centred governance structures would enable this (e.g., establishment of community watershed, crop production or water point management committees, women groups etc.). Adequate time at the planning stages could enable more purposeful community engagement.
- To do more on climate and environment, SDF 3 should focus on biodiversity conservation and provide quality, drought-resistant and/ or short cycle seeds for irrigated areas. The SDF3 business case does already have a very clear focus on climate change, so it is important that this is now implemented.

As with all learning and recommendations in this report, the British Office Hargeisa will consult with the relevant ministries, SDF secretariat, implementing partners and Denmark to ensure dissemination to relevant stakeholders.

D: Value for Money [½ - 1 page]

VfM performance compared to the original VfM proposition in the business case

The VfM proposition in the business case was that SDF2 would drive economy by purchasing inputs at benchmark rates (e.g. consultancy, car rental), efficiency by ensuring outputs were delivered within budget, effectiveness would be measured via outcome achievements and cost-benefit, and equity would be measured via disaggregation, ensuring that issues around geography, gender and clan were all considered during design and implementation. The business case also stated that first phase of SDF had performed above expectations with regards to economy and efficiency, but that decision-making processes could be made more robust by using cost-benefit analysis to drive cost-effectiveness. . SDF2 also produced a more developed framework to measure VfM.,
[note] FCDO, (2019), SDF2 Business Case, available on DevTracker
[note] Much of the analysis draws on that provided by: Mott MacDonald, (April 2025), SDF2 Value for Money Internal Assessment Report, not published.
[note] See annex 1 for more detail on VfM ratings used in the analysis.
With regards to economy, the overall costs of delivering major inputs across individual projects increased within acceptable margins of 15% deviation, except for the fisheries project, which had changes in scope of work. These cost increases can be attributed to post-COVID-19 disruptions in supply chains, global price hikes for input materials like bitumen and steel and longer shipping delivery lead times. Despite these challenges, several measures were taken to ensure costs remained within revised estimates e.g. through a payment-by-results approach. To optimize and ensure competitive bids, extensive technical planning through detailed engineering designs was conducted with clear specifications, mostly issued through open bidding to maximize free market competition. To support Somaliland national contractors, targeted advertising was done in local media to increase and encourage competition. As a result, Somaliland entities now make up over 70% of the service providers. A full analysis of costs with narrative is provided in the annexes. Overall economy is rated as good.
[note] 15% was the maximum acceptable range for deviations agreed by FCDO and Mott MacDonald for the VfM analysis measurement framework.
The efficiency analysis is divided into 4 parts: allocative, technical, relational and dynamic. Overall, efficiency is rated good.
1. Allocative efficiency: Cost-benefit analysis was used to decide on investments and final approval was given by the Joint Steering Committee after reviewing concept notes and project appraisal documents. However, the selection of projects followed a bottom-up planning process, with the SLA and Line Ministries prioritising projects within the NDP. This resulted in a less strategic approach, since alignment with the theory of change was not the focus, but it did facilitate more ownership by the SLA. The Hargeisa Water Agency Lasdhure project was designed to optimise the impact of the ongoing investments by the European Union, KfW as well as SDF1 investment.
2. Technical efficiency: The Programme Management Team managed day-to-day contract activities, with formal decisions approved by the Fund Manager. Resident Engineers were engaged to support technical on-site management, ensuring that over 95% of SDF2 contracts were implemented on budget and on time.
3. Relational efficiency: SDF2 required contracts to be signed by multiple parties, ensuring ownership of the process by all involved. While this sometimes resulted in delays in contract finalisation, it ensured comprehensive oversight. However, inclusion of beneficiaries in the project design stage should have been more intentional, particularly with a view to improving inclusivity.
4. Dynamic efficiency: SDF2’s design provided the fund the ability to deliver prioritised infrastructure projects, which once contracted, required little adaptivity. However, the projects under output 5, delivering infrastructure in the productive sectors did benefit from design flexibility. For example, the introduction of a water diversion weir under the livestock project provided adequate water for fodder production after the initial design proved insufficient for spate irrigation. Similarly, the agriculture project in Awdal region replaced sub-surface dams with solar-powered micro-irrigation projects targeted at youth, which have been well-received by the community.
Effectiveness (See section B on Theory of Change and Progress Towards Outcomes for a full assessment on effectiveness in terms of progress towards outcomes).	Outcomes were measured through the baseline and endline survey of final beneficiaries, and the capacity development survey within Ministries. To increase the chances of effective delivery and progress towards outcomes the Fund Manager implemented their own MEL systems and data collection processes, including feedback mechanisms and surveys. Their close working and use of TetraTech as FCDO’s third party monitor also helped to generate evidence and respond to learning. A lessons log, and Annual Review recommendations tracker were produced to ensure progress was made on learning. The Fund Manager also regularly assessed risks and potential mitigation measures. For example, in 2023, when the fighting in Laasanood was ongoing, development partners have formally signalled to the government that approval for additional funding for the SDF2 extension was increasingly difficult amongst ongoing conflict in Laasanood. Mott also built into contracts with contractors’ clauses that enable a cessation of work if the security situation requires.
Outcomes are often influenced by factors outside of the control of the programme. In the case of SDF2, outcome 1 was largely in control of the programme given it was a count of people utilising services delivered by SDF investments. However, in the case of water, SDF investments covered the main infrastructure, whilst the agency and companies were responsible for the network distribution to reach households. Although the operating context was challenging, particularly during the second half of implementation, SDF2 largely delivered outputs, albeit with some delays. As such, outcome 1 target was almost achieved with 760,300 citizens accessing services provided by SDF2 investments (cost per citizen is approximately £81). Outcome 2, citizen perception on improved service delivery, and outcome 3, citizen perception on development outcomes, were directly impacted by the broader contextual challenges, resulting in poorer performance against targets. The final indicator on capacity development of the MDAs was possibly the least in control of SDF, since the causal pathway relies on the capacity of individuals to take on new knowledge and a conducive broader organisational culture to embed that knowledge – the latter of which was not the case. As discussed in the progress towards outcome section, sustainability of outcome level changes are not guaranteed since the SLA has made little progress in demonstrating their ability to maintain infrastructure for the long term. Capacity building outcomes for the central authorities were also hindered by lack of opportunity for individuals to embed learning through practice.

In SDF3, full consideration of the relevant outcomes should be given at the start of the programme which capture the entirety of changes envisaged. Outcomes need to be measured as per the theory of change, for example an SLA commitment for ongoing maintenance, which while included in the theory of change diagram was not tracked during implementation. The broader state-building outcomes should also be explicit since they are integral to the theory of change and are the mechanism for achieving longer term, sustained transformative impact. The delivery of services by SLA builds trust in government, and this trust means support. SLA should therefore be incentivized not only to delivery infrastructure but to keep it maintained to build on this support and further increase trust. In this way, the true theory of change is not linear, but a circular self-enforcing loop. SDF3 should also consider measuring “(potential for) transformation” as an important outcome level indicator in its own right.

Overall, some outcome results came in below target, but with incremental progress throughout implementation. The Fund Manager also took proactive steps to ensure a robust MEL system and risk monitoring to inform programme decision. An assessment as per the scoring methodology provided by the Fund Manager would be that effectiveness scores adequate overall.

Equity looks at the inclusion of marginalised groups at all levels of the results chain, with higher level inclusive results achieving a higher score. Equity scores adequate overall. There were attempts ensure inclusion at the output level, with some positive results for impact level change for women and persons with disabilities. However, as mentioned in the narrative in section B (progress towards outcomes), there are indications that such benefits might be short lived, particularly for women. SDF2 also had to work within a context where female participation is institutionally low e.g. within MDAs SDF2 achieved 15% female participation, against a target of 20%. There were notable achievements in community level governance structures, with 33% being female against a target of 20%. However, the participation of persons with disabilities remained low. There were also concerns about the active engagement of women in practice. A final notable achievement was the increase to 44% of women having access to improved water compared to the baseline of 2.2 % (male access increased from 4.4% to 56.7%).

It should also be noted that both Mott MacDonald the Hargeisa Water Authority have made some progress in ensuring inclusivity of their immediate and contracted staff, which can help drive inclusive programming approaches. The Director of the Hargeisa Water Authority has taken deliberate action to employ staff based only on performance, ensuring overall effectiveness of the agency. This has included recruitment of graduates from universities (including women) to deliver infrastructure projects. However, women still face barriers, since facilities at construction locations are not always suitable.

E: Risk [½ - 2 pages]

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.

The overall risk rating for the SDF2 was Moderate for 2018-2019, Major for 2020-2021, and Moderate for 2022-2023. Nevertheless, in the last year of the programme, the risk rating was Major and influenced by the security matters in the Red Sea, election delays, the fighting in the east, and the MoU between Ethiopia and Somaliland. The SDF secretariat, donors and implementing partners mitigated the main risks by investing heavily in understanding through monthly and quarterly meetings the political context in Somaliland in relation to project design, delivery/implementation and regular donor-Somaliland engagements to consider the local environment and fragility. The SMP III provided the FCDO with timely, relevant feedback on the quality of partner-delivered activities, outputs, and outcomes (and/or signals of progress towards outcomes) by conducting verifications, learning, rapid research, capacity building and knowledge management. With the help of those activities, programme team and the fund manager used this feedback to drive programme adaptations and improvements to manage risks and learnt lessons about what does and does not work at the field area.

The quality of partner-delivered activities, outputs, and outcomes (and/or signals of progress towards outcomes) by conducting verifications, learning, rapid research, capacity building and knowledge management activities. With the help of those activities, FCDO programme team and the fund manager used this feedback to drive programme adaptations and improvements to manage risks and learnt lessons about what does and does not work at the field area. FCDO and the SMP III provided the FCDO with timely, relevant feedback on the quality of partner-delivered activities, outputs, and outcomes (and/or signals of progress towards outcomes) by conducting verifications, learning, rapid research, capacity building and knowledge management activities. With the help of those activities, FCDO programme team and the fund manager used this feedback to drive programme adaptations and improvements to manage risks and learnt lessons about what does and does not work at the field area. FCDO and the SDF secretariate ensured to monitor programme risks and updating quarterly risk registers which support the programme team to minimise most of the risks. There was no fraud cases identified during the programme implementation. FCDO quarterly updates the risk register in the Aid Management platform (AMP) and discusses this in a risk deep dive. The table below summarises the risk

Risk category	Description and Risk Mitigation Measures
Strategy and context	Overall rating: Major / The SDF faced several challenges in the external context throughout the implementation: / COVID-19: / COVID-19 had a major impact on all tiers of the SDF delivery chain. Upon the initial outbreak, movement of people was severely restricted and working from home became a default for quite some time. Following the initial wave, the economic impact was felt across the world and created challenges for Somaliland’s economy limiting SLA initial capacity to sustain any SDF investments. Repurposing of UK funds affected funding to SDF2 necessitating a review and reprioritisation of approved SDF2 projects. Competing demands for donor funds, SLA capacity, movement restrictions and supply chain disruption caused by the pandemic may mean that delivery was severely affected. / Delayed elections: / Following successful conduct of local government and parliamentary elections in 2021, tension remained around the presidential elections and political parties; these were finally held in 2024. The delay in elections resulted in intense dialogue between Government and Development Partners; the FM tried to maintain a neutral status. / Changes in MDAs leadership: / Changes in Somaliland ministers have taken place throughout the SDF implementation and often led to a slowing in decision-making whilst new ministers understand their role in the SDF governance arrangements. The FM has mitigated this risk by extensive discussions with the new ministers to support their understanding. / Drought: / Somaliland suffered from various droughts affecting large parts of the population facing crisis or emergency conditions. The drought also impacted projects, especially agriculture and livestock. / Security and conflict: / The evolving security situation in the east restricted access to proposed project locations, substantially slowing down project implementation (e.g. construction of the Maydh jetty) and project development (e.g. livestock and fisheries feasibility assessments). Also, a security incident in Borama led to temporary suspension of project activities. The risk was carefully managed through deployment of a full-time security officer and following an adaptive approach to planning and implementation. SDF Secretariat has also developed updated project specific conflict analyses of projects and ensured that recommendations were embedded into project designs for the projects designed. From the donors’ side, FCDO (including donor partners) have signalled to the government that approval for additional funding will be increasingly difficult amidst ongoing conflict in the east and donors reduced attendance of official government events. While also agreed with the FM to ensure risks are better embedded in their comms approach. / Tension on the Red Sea: / The tension on the Red Sea affected project delivery through disruptions in the supply chain. The FM Informing the suppliers to look for another market for the materials like Ethiopia and to consider other means of transportation for the material to Somaliland like air transport though it was expensive.
Policy & Programme Delivery	Overall rating: Major / SDF2 delivered a diverse portfolio of projects throughout Somaliland. Whereas the FM was appointed to maintain external control, the programme promotes government-led implementation; several MDAs delivering the SDF2 portfolio had already gained substantial experience under SDF1 and were able to conduct the day-to-day management of their projects. / MDAs were in turn supported by a wide range of implementing partners for delivery of services, supplies and works. The FM managed a robust procurement process for the competitive sourcing of these implementing partners and implemented strict contract management processes and performance-based payment system as part of contracting. For example, contracts were included a force majeure clause protecting the programme against non-delivery in the case of a gravely deteriorating security situation.
Public Service Delivery and Operations	Overall rating: Major / The FM demonstrated strong performance throughout the programme. The FM provided a wide range of managerial and technical skills and understanding of the political and operational challenges of the programme. Changes in core team members, at short notice was an operational risk. The FM mitigated this by implementing a strict health safety and security plans including journey management protocols for all travel outside Hargeisa and extensive training for all individual staff to ensure a safe and secure working environment. The FM established a staff retention mechanism in place with a recruitment procedure that verify staff performance prior to contracting and allow for rapid identification and mobilising of replacement staff. This established a roster of experts that can replace core staff as needed. They also set in place robust knowledge management system within SDF secretariat to manage store and share information generated.
Fiduciary and financial	Overall rating: Major / The implementation of the JSC-approved SDF operational guidelines, procurement manual, financial management and accounting manual, and other frameworks and manuals has been essential in managing fiduciary risks with all stakeholders in delivery of the programme. SDF strengthened government capacity by using country systems where possible but retained shadow financial and procurement systems through the external FM. The FM established strong procurement procedures and processes since the start of the programme, with active participation of MDAs. Despite this the programme has faced challenges with government understanding of the procurement requirements and processes. Potential fiduciary issues with procurement were clearly communicated by the FM to the JSC and remedied. Project budgets were on budget but did not flow through government systems. External audits were commissioned and to date no major issues have been raised. Exchange rate fluctuations were tracked by the FM on a continuous basis and presented in JSCs and quarterly progress reports. / The implementation of the JSC-approved SDF2 operational guidelines, procurement manual, financial management and accounting manual, and other frameworks and manuals has been essential in managing fiduciary risks within the programme.
Safeguarding	Overall rating: Moderate / Safeguarding risks remained prevalent throughout the programme, with heightened risk during full implementation. Projects were delivered in multiple sectors with varying levels of safeguarding risk. Somaliland is not progressive in the legislation protecting vulnerable adults and children’s rights as such data on safeguarding related issues is limited in Somaliland and so it is difficult to assess the magnitude of the problem. During the inception phase, the FM prepared an approach to safeguarding and all FM staff were trained on safeguarding. Standards are set out in bidding documents for implementing partners, and their bids are assessed accordingly. Due diligence of IPs includes an assessment of safeguarding related incidents with the organisation or its staff. All contract agreements included a clause that obligates IPs and it members to report safeguarding incidents through the reporting procedures of in the Safeguarding Plan. During implementation, additional training on safeguarding was organised for MDA and contractors. The FM also conducting a safeguarding lesson learnt knowledge sharing with the partners.
Reputational	Overall rating: Moderate / Reputational risk for SDF2 included perceived imbalances in regional and clan distribution of projects and fraud or deviation of programme funds. These risks have been managed through transparent allocation of funds across sectors, keeping regional balance in mind, and strong fiduciary management. Substantial work has been done during the development of the new projects to apply the SDF2 conflict sensitive programme framework to manage potential community tensions. / The reduction in UK funding affected the funding of projects. However, careful dialogue with Government and other Development Partners allowed seeking consensus on how to address the funding gaps; this helped the seamless implementation of projects with additional funding provided by the other SDF development partners. Fortunately, UK provided additional funding to cover its previous gap which resulted the completion of two major infrastructure projects for the last year of the programme.

Update on Partnership Principles
A set of Somaliland Development Principles, as agreed with the FCDO Somalia Network, supports implementation of Partnership Principles in Somaliland. The SDF2 is designed to work in close partnership with the SLA. All support for Somaliland authorities remains through a technical assistance approach so no funds are channelled through Somaliland accounts. The UK continues to track the SLA’s progress and commitment to the partnership principles in biannual updates to the Somaliland Partnership Principles Assessment: commitment to reducing poverty; respecting human rights; strengthening financial management; and strengthening domestic accountability.

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation [1 - 1 ½ pages]
Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.

Mott Performance

The fund manager has delivered a strong performance against the agreed set of Key Performance Indicators (KPI) throughout the programme duration. A robust work plan was developed by the fund manager which they used to monitor and evaluate activities through monthly technical, programme management level meetings, and quarterly joint steering committee meetings with the development partners and the government. FCDO programme management team evaluated performance of the fund manager against set of Key Performance Indicators (KPIs) on monthly basis while Mott has used the KPIs to track performance of the projects. The fund manager submitted to FCDO quarterly reports, KPIs progress updates, and financial reports and forecasts largely on time and within the required standards.

Mott demonstrated gold standard contract delivery; the fund manager’s performance has scored well, including at 93% in the last half of the final financial year against a set of KPI indicators assessed quarterly under a Cabinet Office initiative to get better value from FCDO contracted supply base and incentivise better supplier management. The FM has also ensured full capture of all programme assets on the asset register and conducted annual asset verification activities, from which reports were shared with FCDO. As the programme was ending in March 2025, the FM shared an up-to-date asset register for the programme to inform FCDO’s asset disposal process and decisions. FCDO used its third-party monitoring supplier Tetra-Tech to verify the assets which complemented the Mott asset report.

The fund manager implemented JSC-approved SDF operational guidelines, procurement manual, financial management and accounting manual, and other frameworks and manuals, these have been essential in managing fiduciary risks with all stakeholders in delivery of the programme. This system ensured the FM applied robust procurement processes for the competitive sourcing of implementing partners and implemented strict contract management processes and performance-based payment system to ensure quality as part of contracting. However, the need for the FM to actively share procurement information with participating MDAs to enhance transparency, including on timelines was identified during delivery.

Commercial and Financial issues: spending, audits

Since 2018, the UK has contributed £23.7m to the programme, aligning closely with the total programme budget of £25m. In the 2024/25 financial year, the programme demonstrated exceptional financial efficiency, with £13.26m of the £13.4m main budget allocation effectively utilized—achieving a 99% budget execution rate. To ensure timely and efficient disbursement, the programme team approved all fund manager (FM) payment requests promptly. The FM maintained robust financial oversight by providing updated quarterly forecasts and facilitating regular discussions with development partners to monitor progress and address variances. Additionally, the Senior Responsible Owner (SRO) and Programme Responsible Officer (PRO) held regular coordination meetings and shared updates with other donors, fostering alignment and consensus on programme spending.
At the end of each month, the fund manager submitted invoices accompanied by the completed activity reports from the contractor and the project manager’s (who is from the government) approval letters to FCDO programme team for review and approval. They payment are then director transferred to the contractor’s account by Crown Agents Bank. On quarterly basis, the TPM team conducted field verification activities where they monitored the actual completed activities, and they shared with FCDO any gaps they have identified from the field. The quarterly progress reports from Mott and quarterly verification reports from the TPM team supported the programme team to cross check the completed activities against the submitted invoices. The FCDO programme team had a monthly catch up with the fund manager about the progress status of the projects where we shared any gaps that were identified from the field. By the end of the programme, the total expenditure (including other donor partner funds) was GBP 61,369,817.33 million (Programme Fund – GBP 45,059,352.84 and Technical Assistance – GBP 16,310,464.49). This represents 99% of total programme value. During the eight years of the programme, 387 contracts were signed in which Somaliland entities were awarded 275 of the contracts (71% of total number of contracts) for a total value of USD 36,336,851 (or 67% of total programme expenditure).

AUDITS: The SDF2 programme had 7 financial audits since its start and was carried out by Baker Tilly. Key audit findings and recommendations reflected below were collaboratively tackled during delivery:
- Incorrect application of exchange rates: The auditor recommended that the fund manager should ensure that the correct OANDA rate is applied on all transactions incurred in foreign currency. Mott have strictly used the exchange rates indicated by Crown Agents Bank, as confirmed in their e-mail to FCDO dated 23rd of August 2024. Applying the OANDA rate would lead to deviations between what has been confirmed to FCDO and what would have been reported by us.
- Amount claimed inconsistent with actual expenditure incurred: The auditor recommended the management should ensure that adequate reviews of timesheets are done to ensure all the financial records are correct before invoicing FCDO. Mott realized that it was a mistake and indeed 21 days should have been invoiced. They have adjusted/ added in the December 2024 invoice.
- Procurement process: The auditor recommended that the set procurement procedures are applied consistently for all procurements to ensure an effective and efficient procurement process. Mott have implemented consistently procurement procedures using programme SOP that clearly marks the procedure to follow.
- Timesheet preparation, review and approval process: The auditor recommended to reduce the risk of days claimed not reflecting the actual tasks performed/undertaken by the consultants and TAs, timesheets should be prepared, reviewed, and approved at the month end. According to Mott, the findings were highlighted in last year’s audit report in December 2023. They have implemented the recommendations, and since then, only one timesheet has been found with the incorrect approval date. They agreed to continue to monitor this going forward and ensure that timesheets and invoices are signed according to the correct approval date.
- Failure to implement prior year recommendations: The auditor recommended management should ensure that all prior year audit recommendations are acted upon and relevant changes to the systems and controls are implemented where necessary. Mott reassured that recommendations following previous years’ audits are fully implemented. However, there will always remain a risk of human error as invoices need to be prepared manually.
- Variance between expert fees rate as per the invoices and rates used to invoice FCDO. Mott have invoiced FCDO the rates as per agreed Contract Amendment no. 5 dated 29th March 2024. They have observed that some rates incorrectly inserted into Contract Amendment no. 5, which are disadvantages to Mott MacDonald.
- Inconsistencies in supporting documents of internal payments. Mott ensured to monitor the supporting documents to ensure that the dates and Interim Payment Certificate (IPC) numbering align with the specific interim certificate payment being processed.

Mott has provided a comprehensive and satisfactory response to these issues, which has been shared with the FCDO.

Programme-level approach to monitoring and evaluation [1/2 page?]

FCDO conducted in-person monitoring throughout the programme, visiting Borama’s Shaba water public private partnership, Hargeisa Water Agency’s offices and pumping station, Dilla dams, Berbera Sheikh Road, and all implementing MDAs in Hargeisa. TPM partner Tetra Tech and their downstream partner Consilient conducted 56 verifications about SDF2 results throughout the programme implementation work since they began in May 2022. The TPM has also closely collaborated with Mott MEAL advisor for technical assistance and support any cross-cutting thematic reviews e.g. on log-frames across FCDO’s SMP3 programmes. Monitoring and evaluation at the ministry level was challenging and various requests were received during the interviews to simplify reporting requirements, since it overwhelmed the field teams.

A longitudinal study which covered both SDF1 and SDF2 was conducted, sub-contracted by Mott MacDonald (funded by the Danish). The objectives of the study were to:
1. Assess the long-term impact and sustainability of the SDF interventions since its inception.
2. Evaluate SDF’s strategic contribution to economic development, enhancing the state citizen relationship/social contract, equitable service delivery and capacity within MDAs, leveraging donor aid, government development prioritisation, and strategic application and planning of limited funds.
3. Evaluate the strengths, weaknesses, opportunities, and threats of the current SDF model in relation to the Somaliland political economy context.
4. Assess strategic investment decisions (sectoral and geographical) in achieving the objectives of the two phases of the SDF in relation to sectoral priorities for the past National Development Plans (NDP1 and 2) and the relevant development partners’ country programmes.

Unfortunately, the final report was not able to be remedied before the end of the programme. A more in-depth review carried out in SDF3, looking over the lifetime of the programme would be beneficial. All the results reported in this annual review therefore come from Mott MacDonald’s monitoring data for SDF2.

Learning

Mott was supported by the Centre for International Development and Training to conduct longitudinal/perception surveys. They conducted 4 perception surveys throughout the lifetime of the programme which measured achievements against intended outputs, outcomes, and impact. The FM also recruited an independent contractor to conduct longitudinal study of SDF since it started in 2012 which was requested by the previous government. The TetraTech TPM team also conducted a knowledge sharing and lesson learnt session of the programme where the FM also attended. With regards to sustainability, as recommended in this annual review, FCDO will ensure lesson learning from the SDF2 programme is shared with relevant stakeholders and to inform SDF3. Capacity building initiatives with the Fund Manager should also have long term impacts for individuals and Mott MacDonald should they go on to work on other programmes.

Date of last narrative financial report	March 2025	Date of last audited annual statement	Covering period September 2024 to March 2025. Not yet received, awaiting outstanding payment to COCC

ANNEXES:

Value for money assessment framework for SDF2

Performance standards for Economy:

Performance standards for Efficiency:

Performance standards for Effectiveness:

Performance standards for Equity:

Value for money: Economy analysis

Output	Narrative
Output 01: Increased MDA’s capacity in public resource management (All projects)	Overall cost of delivering output 1: / Actual: US$ 903,733 / Planned: US$ 940,400 / Variance: 7% / Savings of 7% were realised by partnering with Civil Service Institute and deploying national training experts resulting in 42% under expected budget for that activity. However, “other costs” including regulatory support, office and equipment came in 17% over budget.
Output 02: Improved community level governance (All projects)	Overall cost of delivering output 2: / Actual: US$ 757,035 / Planned: US$ 1,454,750 / Variance: 48% / The high variance was due to engaging community engagement specialists to support officers on each of the projects, rather than a third-party implementer. This significant cost-saving measure provided overall savings that were rechannelled within the same projects.
Output 03: Improved economically strategic infrastructure (Roads and Maydh jetty)	Overall cost of delivering output 3: / Actual: US$ 21,924,722 / Planned: US$ 22,306,715 / Variance: 2% / The construction projects were initially impacted by market conditions, particularly the fluctuating costs of bitumen, a major cost driver for roads after Covid -19. Despite these challenges, the projects stayed within the acceptable cost range,
Output 04: Improved access to WASH infrastructure and services (Well Field Collector, Borama I&II and Las Dhuure)	Overall cost of delivering output 4: / Actual: US$ 15,913,308 / Planned: US$ 17,262,421 / Variance: 8% / Large savings were made in the Borama project through effective resource management, with savings going towards studies in livestock, agriculture and water supply instead for possible SDF 3 funding. The Las Dhuure water project design review took longer than planned, but implementation proceeded smoothly.
Output 05: Improved productive and environmental managements sectors (Agriculture, Livestock and Fisheries)	Overall cost of delivering output 5: / Actual: US$ 7,636,666 / Planned: US$ 6,632,940 / Variance: -15% / Major savings were made (74%) upon the decision to rehabilitate the existing weir rather than build new infrastructure in the water project. This was balanced across the output with the fisheries project coming in at 42% above budget, with a broader scope, beyond inputs. These additional activities included maintenance of equipment and incorporating a diesel/solar hybrid power source to reduce the operation costs. There were also delays in delivery of equipment which negatively impacted efficiency, although the fisheries activity eventually caught up.