Programme Completion Review

Title: Supporting Inclusive Growth in Somalia (SIGS)
Final Programme Spend £ (full life): £38 Million	Review Date:	14 September 2024
Programme Code: 300370	Start Date: 21 August 2020	End Date: 31 December 2025

Summary of Programme Performance

Year	2021	2022	2023	2024	2025
Programme Score	A+	B	B	A	B
Residual Risk Exposure Rating	Major	Major	Moderate	Moderate	Minor

DevTracker Link to Business Case (and any addendum):	DevTracker Project GB-GOV-1-300370 Documents (fcdo.gov.uk)
DevTracker Links to all logframes used during programme lifetime:	DevTracker Project GB-GOV-1-300370 Documents (fcdo.gov.uk)

A. Summary and Overview (1-2 pages)

Description of the programme

The Supporting Inclusive Growth in Somalia (SIGS) programme, was originally envisaged to be a £38 million for the period 2020-2027 and was the United Kingdom's flagship initiative for economic development in Somalia. Due to FCDO budget re-prioritisation and the USAID funding cuts, the programme will now close in December 2025 having spent £13,481,048.35. The aim of SIGS was to support climate-resilient economic growth by addressing many of the barriers constraining micro, small, medium enterprise (MSME) growth, particularly lack of finance and limited access to productivity enhancing technology. SIGS was designed to be flexible and adaptive in that new components could be added, or existing components dropped or amended as evidence from the programme emerged. It was delivered through three main activities:

Strengthening MSMEs-led climate resilient growth. The UK co-funded the USAID managed Inclusive Resilience in Somalia (IRiS) programme, which takes a market systems approach to tackle the systemic constraints to private sector growth in high-value productive sectors in Somalia. IRiS focusses on livestock, fisheries and agriculture in the USAID priority focus area of South-West State, the coastal region of Jubaland and Banadir. The programme is implemented by a consortium led by DT Global. Due to lack of evidence of what works in Somalia, IRiS was designed as a truly adaptive programme, piloting initiatives in the early years and looking for evidence of what works so that scale could be achieved in the outer years.

1. Stimulating investment through Somalia’s financial sector: SIGS does this through two World Bank initiatives: Gargaara and the Financial Systems Initiative (FSI).
  1. Gargaara is an apex fund, established in 2019, to work through the Somali banking sector to address the very narrow set of financial products on offer and low risk taken by Financial Institutions (FIs).
  2. The FSI aims to improve the integrity of the financial sector in Somalia, such as compliance with anti-money laundering and counter-terrorism financing to enable and encourage international investment in Somalia.

Developing the evidence base on inclusive, sustainable, economic development in Somalia: Under the SIGS programme, a Foreign, Commonwealth and Development Office (FCDO) programme funded Monitoring, Evaluation and Learning (MEL) Advisor is embedded within the IRIS implementing partner to deliver evidence outputs. The Adviser overseas and manages all SIGS MEL activities ensuring coherence and consistency and acting as the focal point for MEL coordination across the programme.

With regards to attribution of results, note that whilst preferencing of budgets within the World Bank’s multi-donor trust fund is possible, they are non-binding (not earmarked). Given the complexity of the fund, it is not possible to attribute results and therefore all results delivered by Gargaara are reported in this review. FCDO can report attributable results delivered by the IRiS programme since only USAID and FCDO are contributing. For the programme lifetime, FCDO calculated the proportion of its entire funding of the IRiS project against the total annual funding budget provided by both USAID and FCDO. The total funds disbursed to IRiS was £12,858,811, with the UK contribution at £4,119,717.42, giving a UK attribution of 32%.

Operating context, progress and achievements

The SIGS programme operated in a challenging economic environment marked by structural weaknesses and market distortions. MSMEs dominate Somalia’s economy, but these businesses face significant challenges including high and multiple registration fees, weak regulatory frameworks, and markets dominated by a few large firms. Informality is widespread, which limits access to finance, job creation, productivity improvements, and participation in formal markets. Women-owned businesses are particularly disadvantaged due to barriers in mobility, access to collateral, and limited social networks.

Somalia’s banking sector has grown in recent years, with more deposits and increased credit to the private sector. However, financial inclusion remains very low. Banking penetration is limited, and available financial products are few. Risk aversion among banks restricts lending to informal businesses and productive sectors such as agriculture, livestock, and fisheries. Currently, less than 10% of Somali adults have a bank account, and only 4% of firms can access credit. Most businesses rely on self-financing for 92% of their working capital, compared to 78% in Sub-Saharan Africa. The sector is concentrated in a few banks linked to large conglomerates, which limits competition and innovation.

The SIGS programme was beset with challenges since the start of implementation. Project procurement of the IRiS programme took more time than originally envisaged. During the first years, FCDO budget reprioritisation, the political impasse caused by the postponed national election, climate-related shocks (including drought) and the global Covid-19 pandemic, all slowed progress.

With regards to IRiS since implementation began, it also emerged that a lack of vision, combined with the adoption of the adaptive approach (piloting/ testing and scaling) rather than having a set of defined activities, also contributed to confusion and a slow start within the implementing team, a lack of clear direction, and difficulty in identifying activities to deliver intended outcomes. At the same time there was pressure from USAID to deliver “quick wins” within the first year to demonstrate results, which took the focus away from programme thinking and design time, towards implementation. Due to these early performance issues, the DT Global team went through a change of leadership in December 2023, and a programme reset; reenforcing and embedding “market systems” as the preferred design and attempting to unify the team around a clearer vision, whilst still allowing for learning and adaptation.

With regards to the financial sector, Somalia saw improvements in recent years with bank deposits increased, indicating growing public trust, credit to the private sector has expanded, supporting business growth and more banks emerging, including new foreign entrants such as Turkey’s Ziraat Bank and Egypt’s Bank Misr, reflecting growing international confidence in Somalia’s economy.

The Central Bank and Financial Reporting Centre (FRC) - supported by the WB and other donors - have invested significant time and resources in strengthening various parts of the country’s Anti Money Laundering and Counter-Terrorism Financing (AML/CFT) architecture over the past two years in preparation for Somalia’s first regional Financial Action Task Force (FATF) mutual evaluation process, due in September 2024. However, this was postponed indefinitely on security grounds and resulted in Somalia only receiving a “technical compliance” review of the AML/CFT laws in place rather than a meaningful on-the-ground assessment of their effectiveness. This would have provided Somalia and international community with a reliable assessment of the effectiveness of its AML/CFT regime and a clear direction and roadmap on where it needs to improve. It would also have led to an influx of targeted TA from donors to support this. This was a significant setback for Somalia's efforts to rebuild its reputation with international investors, maintain momentum on AML/CFT reform and stem illicit financial flows.

FSI - through carrying out independent assessments of 6 Somali banks’ AML/CFT compliance and follow-on technical support to address these issues, as well as supporting the Central Bank on key areas of supervision - has helped to fill some of this gap. In the ongoing absence of a FATF assessment and the incentive it creates for governments to reform, ensuring that AML/CFT momentum is maintained will be critical to efforts to unlock international finance, counter Al Shabaab and support the public finances. FSI has demonstrated that framing the rationale for improving AML/CFT controls more ‘positively’, i.e. as economic and reward-based rather than around compliance imperatives and international standards, is more likely to shift incentives for change within the private sector especially.

The aim of the FSI was to pilot a new approach to supporting Somalia’s re-integration into the global financial system by facilitating international investment and supporting the development of correspondent banking relationships for Somali financial institutions. Specifically, it seeks to improve the integrity of the financial sector and ensure that high standards of corporate governance, risk management and compliance safeguarding against terrorist financing and illicit financial flows are met by participants in both the public and private sectors.

While suffering delays and challenges and noting FSI’s pilot nature, there has been sufficient progress made as well as supporting evidence seen to validate the project’s underlying assumptions and broad approach. Despite constraints on FSI's ability to engage more extensively with international banks and investors there have been encouraging early signs that FSI's activities are starting to bear fruit. Most tangibly this has been seen in the IFC's decision to move forward in providing trade finance guarantees to IBS Bank and Premier Bank. While not wholly attributable to these banks' involvement in FSI, the financial integrity assessments carried out by FSI formed a key part of IFC's due diligence on the two banks. More recently, FCDO at post has been supporting British International Investments (BII) in its plans to enter the Somalia market. This has consisted of providing contextual support on the political and security environment support as well as advising on market dynamics and potential areas for investment. While noting the need to protect commercial sensitivities around BII activity, BII’s interest in Somalia's financial sector comes on the back of sustained UK support to the sector both from FSI and Gargaara and provides further evidence of improving market conditions and has the potential to generate positive signalling to commercial investors and correspondent banks.

Gargaara was established to
- Improve access to finance for SMEs across Somalia, particularly those in the productive and underfunded sectors perceived as high-risk
- Build the capacity of financial institutions to effectively lend to businesses in the productive sector, by enhancing credit assessment, risk management, and lending frameworks.

Despite initial challenges in coordination and capacity, including slower decision-making in both WB and Somalia’s MOF, the Gargaara programme has made meaningful strides. While early expectations may have been ambitious, Gargaara spent its first three years building a strong foundation by onboarding private financial institutions (PFIs) capable of handling larger loans. Recognising the need to reach smaller and women-led businesses, Gargaara began onboarding micro-finance institutions (MFIs) in 2024. This strategic shift led to a rapid increase in disbursements and improved access to finance for underserved segments. Although data limitations make it difficult to fully assess impact, the expansion to MFIs marks a promising step toward greater financial inclusion.

Gargaara also successfully attracted US$20M additional funding from KfW (Germany), with an additional US$10 million expected which demonstrates growing confidence and the scalability of the Gargaara model. Gargaara has contributed to a cultural shift among banks, encouraging increased lending to productive sectors that were previously underserved, this shift has positive implications for job creation, local production, and economic diversification, early loan repayments have begun to flow back, with approximately US$11.4M in reflows collected to date indicates both financial viability and model sustainability going forward.

While Gargaara has reached a more matured stage, several forward-looking risks remain, institutionalisation of Gargaara is not yet complete, discussions between the WB, Gargaara and MOF are ongoing to determine Gargaara’s long-term institutionalisation, potential merger with Somalia Development and Reconstruction Bank (SDRB) is also under consideration. While this could be beneficial in the long term (with a fully functional SDRB), there is a risk if the merger is rushed before sufficient institutional capacity and oversight is built and since SDRB is fully under government control funds could be diverted to other uses.

Gargaara has evolved into a functional and impactful financing institution with a clear mandate to support SME growth in Somalia. It has overcome structural and institutional hurdles, attracted international investment, and helped reshape financial sector behaviour. However, its long-term sustainability hinges on careful decisions around its institutional future, governance, and funding independence.

Gargaara is now fully capitalised for SME lending, with approximately US$70 million in investment—US$50M from the World Bank’s MPF and US$20M from KfW. Gargaara is also part of the new WB SPRING project, with a specific support in the critical areas of Business Development Services (BDS) for PFIs and SME borrowers, risk-sharing mechanism to incentivise PFIs to lend more and to continue institutional support to strengthen governance and operations of Gargaara. FCDO should maintain continue engaging with the WB and Gargaara to:
Continue to expand lending to SMEs
Gargaara institutionalisation and to remains independent from full government control in the short term to safeguard resources and maintain programme integrity

FCDO also facilitated discussions between BII and Gargaara to establish a risk-sharing facility that will de-risk SME lending by PFIs, we are also engaging and coordinating donors (e.g. MPF contributors and KfW,) to align long-term strategies for SME finance in Somalia, advising the WB and MOF/FGS on the best pathway forward for institutionalisation, including safeguarding Gargaara’s mandate.

Output	Score	Weighting
MSMEs’ and producers, implement new, inclusive business models, benefitting from increased access to services (inc. finance), information and markets, increased linkages across the value chain, climate smart tech, improved practices	C	45%
Draft laws and regulations drafted / passed which provide a conducive environment for private sector growth	B	15%
Appropriate, accessible and affordable financial services, including payments, savings, credit and insurance provided (by a range of different providers) based on client needs, including consumer protection	A	30%
Improved risk profile or and greater familiarity with Somali banks, makes them a more attractive proposition to international banks/investors	A	10%

Major lessons learned, evidence generated and recommendations [1/2 page]

There are key lessons from SIGS that will inform design of future FCDO programming in this space.

An overarching point is that the private sector plays an important and outsized role in Somalia with a handful of private financial institutions (PFIs) dominating the economic and political landscape. Finding a way to work effectively and influence with these actors will be critical to future FCDO efforts to make progress on issues like the state’s ability to regulate private sector, tax business, or shape markets in the public interest.

1. Multilaterals like the WB, whilst playing a crucial role in Somalia laying the institutional capacity and state fundamentals, has limitations as a delivery partner given a highly technocratic and inflexible operational model and a mandate to work primarily through public sector partner,
2. Programmes with the right ‘reward’ based incentives, e.g. the carrot of correspondent bank relationships or DFI investment, can yield results and be an effective means to drive cooperation and engagement with private sector where a solely technical approach would struggle to.
3. Key decision-makers at the biggest PFIs have little interest in engaging with WB and prefer to deal directly with international government, from UK, EU and US in particular, who they see as a more credible partner, incl. better placed to support PFI’s efforts to improve their international reputation.
4. Somalia's isolation from the international financial system remains a fundamental constraint to its prospects for growth and stability. Without meaningful progress on the issue, moving money into/out of the country will remain costly and complex, deterring foreign investment, constraining cross-border trade and commerce, and undermining remittance flows. FSI has shown that it remains a high priority issue for the financial sector and private sector at large.
5. Adaptive programming is the chosen approach when dealing with complexity and where pathways are unclear as a result and/ or due to lack of evidence of what works.  This was a correct approach to attempt to deliver growth through the private sector in a context such as Somalia.  However, adaptive approaches require an organisational culture (implementing partner and donor) which prioritises and supports failure and learning, as well as success, is transparent, actively demonstrates openness to challenge and willingness to operate under risk and uncertainty. This proved very difficult to achieve within the set-up of IRiS due to multiple factors including lack of clear vision set by the donors, a bias towards demonstrating success by the implementers (possibly aggravated by the changes in staff and pushes for results in year 1), strong monitoring capacity but lack of evaluation (or prior adaptive experience) capacity within the implementing MEL team, and measures of success based on positive, sizable results.
6. An emphasis on innovation in the first years may have stifled the rollout of activities which have been known to work in similar contexts, such as working with cooperatives, VSLAs, increasing investment or scaling up business development services.
7. Reaching informal SMEs in Somalia is difficult, and they are disadvantaged in various ways such as high fees required for business registration, but then as a result lack of access to finance.  Access to relevant documentation and registration documents were identified as a major assumption in the original SIGS theory of change and this has not held.  SIGS could have focussed more on these structural issues, supporting MSMEs to gain relevant documentation and also work on the supply side to ensure there are relevant products (in the final months, IRiS did start pivoting towards working on the supply side) during implementation, and the World Bank has now incorporated a risk-sharing mechanism within it’s new SPRING project.
8. Support to MSMEs in the productive sector has the potential to enhance livelihoods, though it may not necessarily result in the creation of a significant number of jobs. In recognition of this, SIGS removed the jobs indicator from the logframe at an early stage. While improvements and diversification in livelihoods can be meaningful, the livestock and fisheries sectors faced considerable constraints that limited outreach. In contrast, the agricultural sector demonstrated more substantial results.
9. The monopolistic structure of the Somali private sector companies makes it challenging for smaller MSMEs to grow.  The structure provides a lot of power to these companies, who have vested interests in the status quo.

Key lessons from the SIGS programme will be directly used to inform and shape FCDO Somalia’s future programming, both in terms of what we work on and how we deliver. Primary recommendations include:

- Flexibility in delivery - FCDO needs to have the right decision-making mechanisms to ensure efficiency in use of resources, which means exiting or pivoting from activities as evidence emerges on effectiveness.  To achieve this, i) guiding principles and criteria to support decision-making through the programme cycle must be embedded in future programme design, and ii) strong consideration must be given to how greater operational flexibility can be achieved. This must include being far more clear-eyed about when and when not to work through IFIs like the WB, which was an overarching lesson from SIGS.
- UK must be an activist shareholder in the IFIs – the World Bank, IMF and to a less extent AfDB have large programming footprints in Somalia and strong working relationships with the authorities on technical issues which FCDO should aim to build upon and leverage.
- A clear approach to strategic engagement with the private sector must be embedded in design and delivery. Careful consideration must be given to how this can be optimally achieved but it should not rely on multilaterals. Any approach should see the UK take on a more deliberate and prominent role as partner with Somali counterparts by supporting engagement between public and private and with global institutions.
- “Unblocking” financial flows - needs to be a priority given its foundational importance to building a more financially self-reliant Somali state. Building on the trust and track record that the UK has built with public and private sector stakeholder on this issue will be key.
- The World Bank need to generate evidence and (hopefully) proof of concept with regards to the new risk sharing mechanism being implemented under the SPRING project to further test the assumption that informal businesses can formalise enough to reach services, including finance.
- Given the closure of SIGS, FCDO should focus on future proofing successes of Gargaara.  World Bank will be taking forward these successes in the SPRING project through which they will be providing business development services and trying to improve governance of Gargaara. FCDO must stay engaged.
- There needs to be mechanisms which challenge the status quo with regards to the few dominant companies who operate and hold power in Somalia.  The Somalia government needs to provide more support to the enabling environment, by establishing structures such as a Competition Authority.  FCDO should also consider whether to work with the government to support them in this.
- The commercial arrangements and agreements with USAID and World Bank gave FCDO limited power to make decisions or influence implementation.  Time taken to foster relationships, including regular engagements to understand progress mitigated some of this.  FCDO must not assume in business case design, that they will have much influence on programmes primarily delivered by other donors, and carefully weigh up the pros and cons of different funding models.
- The productive sector is the key to growth in Somalia, but there are many constraints, and FCDO now faces significant ODA reductions.  It is essential that FCDO only supports activities which have broad reach and provide the foundations for growth in the future.  This includes strengthening the enabling environment and supporting the creation of Competent Authorities, which provide essential regulatory and statutory frameworks for the productive sector. FCDO should also maintain active engagement to offer thought leadership to Somali authorities and collaborate with other development partners such as the World Bank and the EU who may have resources to invest in the sector
- FCDO should share learning from the closure of SIGS, and this Annual Review in relevant forums, including with the Private Sector Development (PSD) donor group by the beginning of 2026

Performance of FCDO
With regards to IRiS, the FCDO programme team remained engaged throughout implementation, regularly meeting with the implementing teams and USAID to ensure ongoing relationship building. However, not delivering bi-laterally gave rise to challenges with regards to FCDO influence. For example, there were limited opportunities for FCDO Senior Leadership to engage within the governance structure, and despite requests from FCDO to the partner, no steering committee was set up for IRiS. FCDO influence on World Bank components was similar, with regular engagements and opportunities to discuss challenges, but limited impact on the strategic direction.

Despite these limitations, FCDO performed well, including building relationships directly with the Gargaara team and banks to get further insights into progress and performance on the World Bank components. FCDO staff made regular visits to Somalia to maximise engagement with the implementing teams and other stakeholders.

FCDO has also demonstrated its unique ability to play a convening role with stakeholders in the sector. For example, FCDO initiated discussions between BII and Gargaara to explore setting up a risk-sharing facility that would support lending to SMEs, FCDO also facilitated the onboarding of larger banks within FSI, by convening a meeting with FCDO senior Leadership and the CEO of Dahabshil, eventually leading to the onboarding of this second largest bank in Somalia. There is also an ongoing discussion between FCDO and Salam Bank (the largest bank in Somalia) with the possibility of future onboarding to FSI. This is a result of the perception of trust and credibility of the UK by Somali partners.

Performance of partners
Components of the SIGS programme were led by the World Bank and USAID. FCDO contributed to the Multi-Partner Trust Fund of the World Bank and directly disbursed to USAID who had a bi-lateral agreement with DT Global to deliver IRiS. As such, this assessment covers both the principal donors and the implementing teams.

FCDO had a positive and collaborative relationship with the World Bank enabling close monitoring of progress and opportunities to provide a steer throughout implementation. Quarterly meetings were held with the World Bank team and progress reports were provided to FCDO on a quarterly and annual basis. However, the World Bank’s inflexible approach to engagement coupled with delays in contracting and delivery, led to a slow start and hampered implementation for both Gargaara and FSI. The relationship between FCDO and USAID was similarly collaborative with regular review meetings and timely reporting. USAID colleagues were open about the value they placed on the expertise of FCDO Advisers and programme staff and therefore proactively sought out FCDO views on critical issues related to programme design. The major performance flaws of USAID included a contractual arrangement (agreement) which gave USAID limited influence and oversight of the programme. It was designed this way to provide the necessary flexibility for an adaptive approach but instead led to lack of transparency and some of the challenges highlighted above with regards to lack of vision. Had the implementing partners demonstrated stronger performance, particularly with regards to the use of evidence and theory to interrogate and justify programme design decisions, this would have been less of an issue.

With regards to the implementing partners, there have been performance issues across all three. Gargaara’ s initial progress was much slower than anticipated, taking time to commence activities, become established, onboard financial institutions and disburse capital. In more recent years, disbursements have picked up with notable progress in their capacity and capability. However, there has been limited rigorous data and evidence produced by Gargaara to give a more comprehensive understanding of outcome level results. FSI progress was similarly slow, but largely due to bureaucratic issues of the World Bank. As described above in the Operating Context and Progress section, IRiS also had a slow start to activities, with pressure to deliver results in the first year, a change in management and a significant change in the overall programme approach (to MSR). These criticisms should be considered in the context of a hugely challenging operating context i.e. market systems which are beset with obstacles including a weak enabling environment, thin markets, climate impacts, lack of infrastructure, services and regulation to name a few. Therefore, questions about the validity of the market systems approach (as it was designed in IRiS) in Somalia are valid, particularly in terms of the ambition set out in the original business case.

Lessons from SIGS’s partnerships with the World Bank and USAID show both opportunities and challenges in delivery approaches.
- Delivering through others can bring scale and credibility, but also frustrations. The trade-off depends on programme nature, geography, and political economy.
  - World Bank works better with the government largely at the FGS level programmes, with less engagement with the Private sector. Key PFIs prefer to deal directly with the development partners (UK, EU and US etc) and they see as a more credible partner to support PFI’s efforts to improve their international reputation.
  - The World Bank projects largely depend on Project Management Units (PIUs) within FGS or FMS, often staffed by individuals recruited by line Ministries. These appointments are not always merit based, which negatively impacts programme delivery and performance.
  - Dependency Risk. If a lead donor shifts priorities, achievements can be lost (e.g., IRIS closure after USAID withdrawal).
  - Both World Bank and USAID processes were rigid and time consuming, limiting agility, limited FCDO to influence.
- Adaptive programming requires strong governance, clarity, and decision-making principles from the outset.

Delivery Options Analysis.
Through Others (Multilaterals & Bilateral Donors).
Strengths.
1. Credibility & Influence. Multilaterals have strong reputations and convening power, attracting other donors and government buy-in.
2. Shared Resources and Expertise. Leverages other donors’ financial resources, technical capacity, and networks.
3. Reduces duplication and transaction costs; strengthens diplomatic ties and donor harmonisation.
4. Economies of Scale. Large programmes can achieve significant reach.
Challenges.
- Slow Processes, bureaucratic procedures often delay implementation.
- It can limit visibility, UK branding and attribution may be diluted.
- Reduced Flexibility & Control, harder to adapt to changing contexts; limited UK influence.
- Dependency Risk. If lead donor changes priorities, UK influence diminishes

Direct Contracting Delivery Partner.
Strengths
1. Direct Control, greater influence over design, implementation, and reporting.
2. Flexibility, easier to adapt to changing contexts and innovate.
3. Clear Attribution, strong UK branding and visibility.
Challenges.
- Higher Management Burden. Requires strong oversight and contract management.
- Transaction Costs. Can be expensive compared to pooled approaches.

Ke recommendations for delivery options include.
- There is no one-size-fits-all approach. FCDO should adopt a strategy based on programme nature, political economy, and risk profile:
- Assess programme nature, beneficiaries and implementation geography, consider whether implementation will be at FGS, FMS level and weigh other stakeholders’ engagement like the civil society and the PFIs.
- Develop FCDO guidelines on delivery modes and risk assessment, include criteria for choosing delivery modes and risk mitigation strategies.
- FCDO should work with the World Bank and other development partners to improve PIUs recruitment processes, ensuring merit-based selection  to strengthen programme delivery

How this report was conducted

This programme closure review (PCR) was led internally by FCDO. Given the restructuring of USAID, and the closure of IRiS in March 2025, there have been no interviews related to the programme to inform this PCR. Interviews were held with the World Bank, Gargaara and FSI teams.

Actions following approval of this report
There are no follow up actions following approval of this report.

## B: Theory of Change and Outcome Assessment (1-2 pages)

	Starting point	Final result
Budget	£38m	[What was the final spend?] / £13,481,048.35
Timeframe	2020 - 2027	2020 - 2025
Outcomes	Refer to table below for the outcome statements, milestones and performance.

The theory of change for the programme remained the same for the final year. Although a theory of change workshop took place in November 2024, the decision was taken to remain with the previous version, given the early closure of the programme. This means that the assessment of performance is against the theory of change used in the 2024 Annual Review. The SIGS programme aims to catalyse growth in high value, sustainable sectors of Somalia to increase the resilience of market systems and ultimately of poor Somalis. It does this through:

- Easing access to finance for MSMEs - Gargaara provides loans to MSMEs working in the productive sector. Penetration rate for banking services in Somalia is low and MSMEs, particularly women-led and those in rural areas, struggle to access finance, which is a key constraint to growth.[1] In addition, the productive sector, which is vulnerable to weather and climatic conditions, is seen as high-risk by banks. Gargaara has been designed to fill this gap by providing financial products for MSMEs in the productive sector with a focus women-led MSMEs. Gargaara does this by accepting higher risk than existing banks, addressing the liquidity of Somali banks so that they can on-lend to MSMEs
  [1] World Bank, Country Private Sector Diagnostic, Creating Markets in Somalia [Somalia Country Private Sector Diagnostic (ifc.org)]
- Strengthening the financial system - FSI seeks to strengthen the integrity of the financial system so that Somali financial institutions, and in turn businesses, have access to greater and more flexible sources of capital (e.g. longer-term loans) and can transact more cheaply and efficiently internationally. The underlying rationale behind FSI’s theory of change is that Somalia’s isolation from the international financial system - due to high AML/CFT risks - undermines economic growth prospects as well as stability. The rationale behind FSI’s approach is that participating Somali financial institutions will be incentivised to increase transparency and improve the integrity of their AML/CFT systems by the prospect of an improved risk profile and improved access to foreign banks and investors.
- Supporting businesses to grow and diversify - IRiS works on the demand side of finance whilst offering a broader package of support to strengthen the private sector through a market systems development (MSD) approach. IRiS partnered with MSMEs in the productive sectors to address constraints to growth and build resilience, initially incentivising them with grants and technical assistance.

The theory of change remained largely consistent throughout implementation in terms of expected outcome and impact. Whilst activities changed in response to learning (particularly within the IRiS component), the overarching SIGS theory of change did not undergo any major revisions. Output wordings were simply tweaked to more accurately reflect the changes in activities. Assumptions remained valid, although new ones were added. In particular, the IRiS programme noted an emerging risk that given the structure of the productive sector, it was possible that activities could at least in the short term, further empower the few dominant and well-resourced firms, crowding out smaller businesses. There was also some evidence that benefits were skewed towards firms, rather than producers further down the value chain, due to profit incentives and power dynamics.

Overall assessment of programme outcomes, sustainability and VfM

Outcome statement	Outcome indicator	Result against target	Rationale
MSMEs and marginalised producers maintain, increase production & income in spite of shocks (inc. conflict and climate)	1: Value of annual sales of producers and firms	$2,514,296.68 / (530% of the target)	The over-achievement is both due to the quicker than expected ability to scale activities, the positive results aligned with the theory of change, but also an underestimation of the target.
	Number of jobs created	153 (12.3% of the target)	Figures are from IRiS (Gargaara has not yet been able to provide data on jobs). As described in the narrative, it emerged that the pathway towards resilience within IRiS was through improved/ diversified livelihoods rather than jobs. The intention was that in future years this indicator would be dropped. This didn’t materialise given the early closure of the programme.
Transformational change of markets and the financial system crowd in new actors and perpetuate more investment in the private sector[2]	GBP of additional private/ public finance leveraged to support climate resilience, disaggregated by type and origin of finance	IRiS $523,170 private finance (82%) / Gargaara: US$20M KFW (225%)	IRiS leveraged co-financing from the private sector to implement activities. / Gargaara attracted an initial US$20 million investment from Kreditanstalt für Wiederaufbau (KFW), a German state-owned investment bank in December 2023. Although there have been signals about additional investment from investors and donors, these have not yet materialised.
	Extent to which interventions are likely to lead to transformational change	Score: 3 against a target of 4[3]	The score remains the same as last year, with no additional evidence now available from IRiS and no substantial changes in the performance of Gargaara (which is also still providing limited evidence of outcomes).
[2] Transformational change is defined in the International Climate Finance (ICF) methodology as change which catalyses further change i.e. others are encouraged to replicate and scale-up activities in the long term - International Climate Finance KPI 15 Methodology Note: Extent to which ICF intervention is likely to lead to transformational change
[3] Scoring for transformational change: 1 Substantial evidence that suggests transformational change is unlikely or will not occur; 2 Partial evidence that suggests transformational change is unlikely; 3 Not enough evidence yet to assess, or the balance of evidence is inconclusive; 4 Partial evidence that suggests transformational change is likely; 5 Substantial evidence that suggests transformational change is likely or already occurring.

The impact indicator in the FCDO logframe was – number of households	whose resilience has been improved. There have been no changes to the results of this indicator since all results were reported from IRiS which has now closed without another household survey taking place. The total number of people with improved resilience because of IRiS interventions is 74,305.[4]
[4] Note that the ICF return for this ICF KPI reporting in 2025 was 14.6% of this i.e. 10,967.
Given the early closure of IRiS there have been no additional outcome level results to report in this programme closure review, beyond those reported in the 2024 Annual Review. World Bank have not to date provided outcome level evidence beyond the transformational change assessment. Although the World Bank and Gargaara have intentions to survey the onboarded PFI’s and MSMEs, this has not yet taken place. In terms of sustainability of outcomes already achieved, there has not been an opportunity to follow up with private sector actors and MSMEs to understand whether investments already delivered sustained outcomes, or what the impact might have been of the rapid closure. Capacity building efforts, and headway in linking MSMEs with finance institutions may have some longer impact results, given the dual track efforts of focussing on both the supply side through Gargaara which is ongoing, and the demand side through IRiS. There is anecdotal evidence that the perceptions of risk in the productive sector for financial institutions is beginning to reduce.

Follow up with SATG, the implementing team of the agricultural activities within IRiS was possible. One of the most significant milestones has been the establishment of the Somali Agricultural Regulatory and Inspection Services (SARIS) as an independent authority. Through IRiS support, key seed, agro-chemical, and plant protection laws were successfully passed by both Houses of Parliament and signed by the President on December 24, 2024. This achievement has provided SARIS with legitimacy, its own office, and the authority to regulate agricultural inputs. As a result, seed companies have formally registered with SARIS, and donors have begun channelling resources to strengthen this institutional framework.

SIGS was beset with challenges throughout its lifetime. Beyond the reason of early closure, outcome level change was modest compared to the original ambition set out in the business case due to the reasons summarised above in the operating context and performance of partners sections above. The IRiS programme did deliver impressive scale, particularly in the year before closure, reaching 33,812 unique participants who were able to access services delivered by the programme. This included technical inputs, finance, or capacity building to improve production. The original ambition in the business case was that the programme overall would deliver up to 20,000 new or retrained jobs. This was out of sync with the reality of working in the productive sector in Somalia, where most production happens at the household level, informally, with individuals growing crops with various intentions ranging from selling at market, to SMEs via aggregators for retail or trade, and subsistence. In 2024 the programme pivoted to reflect this by focussing on livelihoods rather than jobs.

With regards to GESI, IRiS had a particular focus on inclusion and tried to ensure equity of benefits by focussing activities on women’s access to finance and keeping track of who benefits. Disaggregated data is only available for their indicator which tracked total reach of activities. Of the total participants:
- 18,102 (54%) of people reached were women.
- 10, 265 (30%) were youth aged 15-29.

Gargaara also has a focus on gender inclusion, and results are provided within the relevant output reporting. In general, Gargaara has struggled to tackle issues of inclusion. For example, whilst the number of women businesses reached is impressive, the $ amount of loans to women has been very low, because these businesses tend to be micro or small enterprises that require smaller loan sizes. In addition, Gargaara disburses funds through banks and so reach is therefore reliant on where those banks operate – which is largely in cities. However, there are some areas such as Southwest, where several banks do exist, but reach is still very low.

SIGS also had the intention of leveraging $60,000,000 co-investment from the private sector and made slow progress in this area. Beyond the USD$20M investment provided by KFW, Gargaara has not tracked co-investment effects making it difficult to understand any outcomes. IRiS had leveraged only $5.2M.

With regards to increase incomes, again Gargaara did not provide any evidence from the MSMEs benefiting from loans so there is no data to report on this result area. IRiS tracked “increased sales for MSMEs and producers” which amounted to US$2.5M. The original SIGS business case suggested £30M increased incomes could be achieved by the end of the programme.

In summary the reasons for poor performance towards outcomes stem from a lack of vision set by the donors at the start of the programme, challenges in implementing a fully adaptive MEL to support the approach, and unrealistic ambitions set out in the business case. More opportunity for capitalising on local knowledge at business case stage, rather than relying on donor input, could have helped mitigate some of these challenges. It is also possibly that adaptive approaches require a much longer lead-in time to ensure the relevant scoping and political economy analysis can take place to inform programme design.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators. [1/2 – 1 page]

The SIGS theory of change posits that if the productive sectors are strengthened and diversified, and finance is more readily available for investment to spur this change, then the resilience of market systems, businesses and individuals will increase. In SIGS, this pathway is supported by the production of quality evidence which informs activities and allows for a more evidence-based enabling environment.

Under the context of the operational and programme design challenges outlined above, the logframe underwent significant changes throughout implementation, particularly with regards to the productive sector diversification outputs and expected outcomes delivered through the IRiS programme. These changes reflect the gradual emergence of a clearer vision for each of the target sectors and the re-alignment of activities with the Market Systems Resilience (MSR) approach.[5] Being an adaptive programme, outputs were also scaled, dropped or added as evidence emerged. Significant changes include:
[5] USAID Market Systems Resilience Framework – “considers how entire market systems can survive and recover in the face of shocks and stresses. The MSR lens can help humanitarian and development practitioners assess system resilience in order to not only address immediate needs but support sustainable, transformative system change.”

- In February 2023, FCDO moved the levels of indicators to reflect the theory of change: e.g. moving the International Climate Finance (ICF) resilience indicator to the impact level from the outcome and moving “jobs created” to the outcome level from the impact level (the latter was later replaced with an indicator measuring “change in incomes” to reflect results in livelihoods rather than job creation).
- Realigning indicators with that of the implementing team in February 2023: e.g. outcome 1 was changed from “income change of Micro, Small and Medium Enterprises (MSMEs)” to “sales turnover of MSMEs”.
- In February 2023, to respond to the shortage of data coming from Gargaara and encourage activities which focus on equity: removed the ambition to collect data on the “number of products and services available for MSMEs which also provide consumer protection”, to “number of Private Finance Institutions (PFIs) supported to develop new lending products for women”. This responded to the fact that consumer protection was thought to be too ambitious and that Gargaara was only collecting data on the latter indicator.
- To align with emerging evidence, in September 2023, the high-level outcome on Inclusive, resilient trade and growth in higher value, more sustainable sectors, was split into two outcomes. 1) about businesses resilience and profitability translating to jobs (livelihoods) and increased incomes 2) financial and market system transformation

A further revision to the theory of change diagram was made in December 2024, with the most significant proposed change being to remove the references to “jobs created” and instead focus on “livelihoods”. Whilst this resulted in logframe revisions, the changes were not implemented in practice because of the premature closure of the programme and lack of new results data since. The new theory of change diagram below reflects these recent changes and therefore represents the most up to date explanation of how SIGS was attempting to achieve results. The original theory of change from the SIGS business case can be found in Annex 1.

Overall, the output to outcome scores do provide an accurate reflection of the performance of the programme. However, the difference in performance across productive sectors is noteworthy, with progress in agriculture possibly due to the relatively simpler pathways towards change, as well as the deep knowledge and ability of the contracted partner to deliver. More time for implementation would have built more confidence in the outcome performance, particularly for Gargaara which has been able to increase disbursements quite significantly in the past 2 years, but must take steps to ensure sustainability of operations.
SIGS Theory of Change (updated November 2024)
## C: Detailed Output Assessment [aim for max. 1 page per output. Repeat for each output]

Output Number and Title	Output 1: MSMEs’ and producers, implement new, inclusive business models, benefitting from increased access to services (inc. finance), information and markets, increased linkages across the value chain, climate smart tech, improved practices
Output Score	C
Impact weighting (%)	45%		Impact weighting revised since last AR?	No

Output Indicator		Starting Target	Final Logframe Target	Final Result Achieved
Number of private sector enterprises with improved participation in the local economy		122	100 by 2027 / Relevant targets: / 50 by October 2024 / 66 by October 2025	C – Outputs substantially did not meet expectation (35% of the final logframe target) / 35 (as reported in October 2025 IRiS Annual Report)
% of recommendations implemented within IRiS activities to agreed deadlines from environmental risk assessments		N/A – was not included in the original logframe	80%	A – Outputs met expectation – but no new assessments against which this can be judged / 84% (105% of the logframe target as reported in September 2024 FCDO Annual Review)
Number of individuals in the agriculture and food system who have applied improved management practices or technologies		N/A not in the original logframe	101,586 / Relevant targets: / No target for 2024 / 77,826 by October 2025	C – Outputs substantially did not meet expectation (28.7% of the final logframe target) / 29,147 (as reported in October 2025 IRiS Annual Report)
Number of (IRiS) households benefiting from financial services provided through IRiS		5000	20,522 / Relevant targets: / No target for 2024 / 15,357 by 2025	C – Outputs substantially did not meet expectation (3.8% of the final logframe target / 775 (as reported in October 2025 IRiS Annual Report)

This output tracks progress of the IRiS programme which stopped prematurely, hence the lack of results against the intended logframe targets for the final year and overall C score. The output measured the success of onboarding SMEs to the IRiS programme in the form of a partnership arrangement. SMEs would be required to co-finance investments by IRiS for new equipment or infrastructure and receive capacity building. As a result, the intention was that their business would grow, requiring them to engage more producers (whose capacity they would develop through training and support), leading to higher revenue and profit. The co-financing arrangements were meant to incentivise initial investment, demonstrating proof of concept for new approaches (both by banks and by the MSMEs themselves) allowing MSMEs to further develop their business, perhaps seeking finance from banks in the future.

In total, IRiS had signed partnership agreements with 40 firms by the end of 2024, with 35 demonstrating improved participation in the local economy because of programme activities. In terms of numbers, these was good progress as at end of 2024 and demonstrated increasing progress of delivery. MSMEs showed some promise, with 29,147 individuals who were applying improved management practices in production as a result.

Whilst this trajectory showed some promise, there were some concerns around the businesses engaged at the firm level. Some evidence suggested that such firms were often funded by donor activity on a regular basis, and that many benefits were captured at that level rather than the individual producer level – who were the ultimate, marginalised target communities. Other issues included insecurity which hampered access, particularly for agricultural activities taking place in South-West Hirshabelle and Jubaland, which are the breadbasket regions of Somalia. Another persistent challenge has been the disconnect between agricultural programming and Somalia’s crop calendar. IRiS was also slow to design relevant activities and deliver in the livestock and fisheries sectors. Many such delays were due to bureaucratic delays in finalising concept notes and completing procurement processes, as well as issues in finding relevant entry points for activities.

Lessons learned through this output, and recommendations for future programming

- Lesson: When working with the private sector, interests ultimately are not aligned with FCDO’s or indeed that of other donors. SMEs are incentivised by profit, more than delivering benefits for vulnerable producers making it more difficult to deliver quality livelihood improvements at the producer level.
- Lesson: Linked to the above point, the development of the Somalia productive sector does not facilitate in any significant way, an increase in jobs. It does increase the opportunity for new entrants into the production of goods which provides livelihoods, but this is largely informal and unregulated. As a result, there is a risk of encouraging the exploitation of the most vulnerable by private sector firms. However, it should be noted that this was not always the case within IRiS, since some firms recognised the importance of social responsibility in principle, as well as a means of securing donor funds in the future.
- Lesson: There are ongoing and significant challenges in the seed sector. These include the absence of a structured seed improvement programme, lack of predictable rainfall, and the possible undoing of market linkages due to the abrupt closure of the programme. Strong institutional foundations, such as SARIS, are essential but require follow-through with implementation, enforcement, inspector training, and digital tools to ensure lasting impact.
- Recommendation: FCDO should remain engaged with the productive sector in Somalia, even if there is limited or no direct funding available. This would include the current SRO of SIGS continuing conversations with stakeholders where relationships already exist, such as SATG (implementing partner for IRiS agriculture) and the Somalia Agriculture Regulation and Inspection Service (SARIS).

Output Number and Title		Output 2: Draft laws and regulations drafted / passed which provide a conducive environment for private sector growth
Output Score		B
Impact weighting (%)		15%	Impact weighting revised since last AR?	Yes, down from 30%

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
Milestones achieved - of improved or new policies, standards and regulations prepared, revised and drafted	N/A not in the original logframe		2 policies signed into law	B – Outputs moderately did not meet expectation - SARIS Policy passed by parliament / (as reported in October 2025 IRiS Annual Report)

This output attempted to track the progress made in establishing a more conducive enabling environment for private sector growth. The programme found it challenging in the first years to identify areas that would support broader change through regulation. Some of the challenges IRiS faced included the complexity of working in a largely informal private sector, finding entry points that will not further disadvantage the most vulnerable, the multitude and complexity of obstacles within the productive sectors that limit private sector growth, and the need for political will and influence to get traction on some of these issues.

The agricultural sector in Somalia has arguably received a lot of attention and resource (beyond IRiS), which has accelerated both actual progress and thinking on how transformation might be achieved in the longer term. SATG was the lead in the IRiS consortium on agriculture, with a strong team and a clear vision on how the seed sector needed to adapt and develop in the face of climate change. SATG shared an internal paper with IRiS, setting out a detailed roadmap on how this would be achieved based on evidence and experience from other countries in the region.[6] This deep thinking accelerated progress. As such, IRiS enlisted a specialist consultancy service to facilitate the Somali Agriculture Regulatory Inspection Service (SARIS) integration into the law through the Somali parliamentary system. Evaluation, Learning, and Monitoring Initiative (ELMI) organised two public consultation meetings and the law were successfully passed through the Senate and House of Parliament and signed by the President in 2024.[7] The next steps would have been support from IRiS to ensure full implementation, but the programme ended just as talks began.
[6] The full paper is not published online, but a summary is available at: SATG, Enhancing Agricultural Resilience through Improving Farmer Access to Quality Seed of Improved Varieties - SATG | Somali Agriculture Technical Group
[7] Evaluation, Learning, and Monitoring Initiative (ELMI) was USAID’s internal evaluation function

By the end of the programme, IRiS had also provided technical assistance to support the establishment of a Competent Authority within the Ministry of Fisheries and Blue Economy, which would be responsible for developing and implementing compliance with fish quality standards, increasing opportunities for international trade and reducing wastage. Although this was not counted as progress as per the indicator, it was an important step in developing the sector.

Despite only achieving 1 law passed in parliament, which might suggest a C score, the progress that IRiS had begun to make in terms of setting out a clearer vision for the fisheries sector and taking tangible steps towards that, is reflected in the overall B. The IRiS programme went through various stages of change both in terms of implementation design and therefore MEL plans. The milestones for this indicator were never updated before the final Programme Completion Review (PCR), to reflect the entirety of the ambition set out for the enabling environment, which had become clearer within the final few months of the programme. For example, in the fisheries sector, the set-up of the Competent Authority was a huge step forward in terms of supporting a more formalised sector able to capitalise on the potential for export and international trade.

Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]

- Lesson: Strengthening the enabling environment does not stop with the passing of laws. It requires necessary skills, resources and political will as well as good analysis to understand potential implications, unintended consequences and impacts. FCDO and partners must move away from simply tracking the passing of laws to more comprehensively understanding the context and political economy at play. Measurement of success should take place within that understanding, perhaps with a more comprehensive composite indicator which tracks that which is within and outside of the programmes direct control. This would better assess the potential for success.
- Lesson: Feasibility and ambition were not well defined within the initial design of IRiS by donors. For example, the fisheries sector has such a complex, interconnected set of challenges, that it is hard to make progress by addressing some constraints while not addressing others. The market systems approach attempted to do this, but the resource constraints and feasibility of addressing all the challenges call into question whether this approach could have really worked in Somalia. Such challenges range from lack of regulatory environment, cold chain, energy, larger infrastructure such as jetties and roads, poor equipment provision and handling practices as well as lack of finance. A systems mapping approach to the design phase, with local inputs could have helped surface these issues and interconnections earlier, allowing IRiS to focus energy on key leverage points rather than spreading resource more thinly. That would have possibly included access to finance and possibly some incremental steps forward in the enabling environment. At the same time, and given the available resource, there is a question of whether Somalia was ready for the market systems approach within this sector.
Recommendation: FCDO should consider what, if any, support might be given to the productive sector in a new portfolio economic development programme for Somalia, given the reduction in ODA. With the smaller funding, we should consider where we might have the most transformative impact, by for example support to the enabling environment.

Output Number and Title		Output 3: Appropriate, accessible and affordable financial services, including payments, savings, credit and insurance provided (by a range of different providers) based on client needs, including consumer protection
Output Score		A
Impact weighting (%)		30%	Impact weighting revised since last AR?	Yes, up from 15%

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
Cumulative number and value of MSME loans disbursed from the Retail PFIs (disaggregated by % of loans to women)	$30M		$30M / 5500 loans / (12M and 2200 to women) / (Note July 2025 target: / 3900 loans / 22M)	B-Outputs moderately did not meet expectation (results as of Q3 2025) / $22,828,130 or 76.1% of the final target (100% of July target) / Women owned MSMEs share of total value: $2,800,000: or 12.3% of the target / 1735 loans disbursed or 31.5% of the final target / 741 loans to women owned MSMEs or 42.7% of the target
Amount of reflows received by Gargaara	N/A not in the original logframe		$8,012,686 / ($6,529,503 for 24-25)	A++ - as of Q2 2025 / $11.4M or 142% of the target

This output tracks disbursements from Gargaara, to give an indication of how accessible loans are. It also tracks reflows, which provide an insight into the potential sustainability of the institution since paid back loans can be lent out again. From 2020 Gargaara had a slow start to disbursements, with more rapid results in 2022, and a steady $4M disbursed each year since then. However, progress in the first half of 2025 was slow largely attributed to several PFIs reaching their financing limits and being unable to request additional funding. Whilst this approach ensures financial management and compliance, it temporarily slows disbursement rates. Given the early closure of SIGS, the final logframe targets were not met for indicator one. However, judging progress against this year’s target would have meant Gargaara achieved the milestone for amount disbursed. Gargaara also met the target for reaching the number of women-owned businesses with loans, but the total $ amount is much lower (12.3%) than that lent to male-owned businesses.

Gargaara has also struggled to increase access to finance for women. At the start, proportions of loans to women were negligeable, although this has increased with the onboarding of micro-finance institutions which have enabled faster disbursement of smaller loan amounts. Financing for female-owned businesses increased from $1.8 million in Q4 2024 to $2.8 million in Q2 2025. Whilst this falls short of the target of 40% disbursed to women, it is an improvement on previous years. It is questionable whether the initial 40% target was realistic given the complex societal gender dynamics in Somalia. However, Gargaara has also been slow to provide support to PFIs and MFIs in understanding the constraints and tailoring financial products to ensure more equitable access. Equally, geographically loan disbursements have been uneven, largely because there are a limited number of banks in some areas. Economic opportunities are also concentrated in the areas where people have businesses i.e. large urban areas as well as the additional cost associated operating/going to rural aeras.

Regional Loan Distribution (as per the 2025 Q2 report):
- Banadir received the most loans, with 53.6% of all disbursements.
- Puntland followed with 19.4%.
- Jubaland got 8.6%, Hirshabelle received 8.2%, and Southwest had 4.9%.
- Somaliland, Galmadug, and SSC Khatumo received very few loans and remain underserved.
Loan Types by Size:
- Microfinance (U$500 to US$5,000) had the highest number of loans (2,112), but a smaller total value of $5.3 million (just 17% of the total), showing it's aimed at small, grassroots businesses.
- Small window (U$5,000 to US$50,000) loans were fewer (345), but had the highest total value of $13.6 million (44.2%), meaning each loan was larger.
- Large window (U$50,00 to US$250,000) had only 64 loans, totaling $11.9 million (38.7%), indicating big investments in fewer, high-capital businesses.

On the second indicator, the reflow account now holds a significant balance, which is indicative of the ability of businesses to repay loans and provides proof of concept to banks who might consider the disbursement of finance to MSMEs in the future. However, delays in reinvestment planning, unclear criteria for allocation and lack of readiness among the finance institutions means that use of the revolving funds has been low so far.

Lessons learned through this output, and recommendations for future programming
- Lesson: Disaggregation of disbursements by gender have persistently demonstrated a major financing gap. This disparity underscores the structural challenges in access to finance for women, despite their significant participation in Somalia SMEs businesses.
- Lesson: Loan sizes indicate a balance between broad financial inclusion and concentrated investment in potentially high-growth firms. The high disbursement rate within the micro-finance window indicates accessibility to MSMEs, while the small and large windows channel resources to enterprises with higher capital requirements, potentially driving larger economic impacts.
- Lesson: The requirement for formal registration may unintentionally exclude a significant portion of informal SMEs. As Gargaara’s financing is currently limited to formally registered SMEs, many informal micro enterprises are unable to access these opportunities
- Recommendation: Gargaara should continue exploring ways to increase inclusion including gender, informal SMEs and geography. Delivering on original ambition to develop bespoke products for women and provide capacity building initiatives to PFIs on inclusion would be helpful. Expanding access to regions currently underserved could foster balanced national growth, reduce inequality. This could be done by partnering with other donors working in this space such as EU and SIDA and exploring new approaches such as agent models.
- Recommendation: FCDO must remain engaged with the World Bank, KFW as well as other donors who have a stake in Gargaara. The purpose being to ensure accountability with regards to funds already given and to take part in discussions regarding future institutionalisation and sustainability.
- Recommendation: Discussions have been initiated between BII and Gargaara on a risk-sharing facility. FCOD should continue to take forward these discussions to explore what might be possible. There have also been early discussions between BII and Premier on trade finance which FCDO should continue to facilitate.

Output Number and Title		Output 4: Improved risk profile or and greater familiarity with Somali banks, makes them a more attractive proposition to international banks/investors
Output Score		A
Impact weighting (%)		10%	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
Percentage improvement in assessment of quality and integrity of PFI systems by FSI stakeholders following TA and diagnostics	Please note: At the start of 2025 the programme team went through the process of revising the milestones and reporting requirements for FSI to transition from the operational milestones used for the first half of the project and towards more intermediate-level milestones, i.e. that sought to capture meaningful progress against the three Output level indicators. However, the decision taken in Q125 to close SIGS early meant that these changes were not enacted. / Thus, suitable reporting measures/milestones for output-level indicators were not set up so for the purpose of this PCR only existing milestones will be reported against.		Cumulative number of diagnostics completed of participating financial institutions and number of targeted TA missions successfully completed. / 8	Results expected by end of project in Q126 / 10 / Results as of Q325 / 4
Percentage change in participating international banks/investors reporting of understanding of Somalia financial sector investment climate and risks	As above		Cumulative instances of collaboration or resource sharing between local and international stakeholders, incl. knowledge exchanges or direct conversations held. / 11	Results expected by end of project in Q126 / 9 out of 11 / Results as of Q325 / 7
Perception of progress being made in development of correspondent banking relationships among all FSI stakeholders after TA work completed	As above		Direct conversations between participating PFIs and regional/international banks in relation to correspondent banking relationships / 8	Results expected by end of project in Q126 / 7 out of 8 / Results as of Q325 / 4

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score. [1/2 page] This output is delivered through the Financial Systems Initiative (FSI) – a UK, US and EU funded project delivered by the WB. The aim of FSI is to pilot a novel approach to supporting Somalia’s re-integration into the global financial system by addressing barriers to correspondent banking relationships and investor access. Through extensive market convening and technical assistance, FSI will build trust and cooperation between local and international financial sector stakeholders, while providing Somali banks with the support they need to meet key financial integrity standards.

Starting in mid-2022, FSI experienced delays in the first 12-18 months due to the slower than expected process of securing requisite buy-in and participation of Somali banks. It then suffered lengthy delays in the World Bank's procurement of 3rd party suppliers to provide the central technical component of the programme. In acknowledgment of these delays and the progress being made thereafter, FCDO agreed with the WB in May 2025 to extend the FSI project on a no-cost basis by 12 months (i.e. until May 2026) with the intent that this should allow FSI sufficient time to complete the core technical component of the project.

At time of writing (Oct '25), a first cohort of banks - Premier Bank, IBS Bank, Bushra Bank and MyBank - had received in-person independent assessments of their financial integrity and investor risk profile which included an action plan and recommendations on priority gaps. All four banks elected to receive follow-on technical support - via a separate 3rd party expert - to address key elements of the action plans. This work is expected to be completed by Spring 2026.
A second, smaller cohort - Dahabshiil Bank and Idman Community Bank - were due to complete independent assessments by end 2025. Both banks are eligible for follow-on TA provided it is completed by May 2026.

Directly assessing the quality and impact of the technical work is made difficult given its confidential nature and that banks have yet to complete the full process at time of writing. That said, feedback gathered from the first cohort of banks on the independent assessments – both from private FCDO conversations with two of the banks and in-depth feedback given by all 4 banks at FSI stakeholder events in 2025 - has been highly positive. This sense is further reinforced by the fact that several banks were sufficiently motivated to implement several of the reports' recommendations themselves using their own resources.

Under output 4.1 and 4.2

In addition to the technical side - and what sets FSI apart from most projects in the financial sector - is its stakeholder engagement element designed to foster direct relationships and improved understanding between Somali financial institutions and international investors and banks.

It must first be acknowledged that this side of the project – with its emphasis on changing banks’ behaviour towards AML/CFT compliance and the process of confidence and trust building between Somali banks and international banks/investors –comes with inherent challenges that are amplified in a context like Somalia.

That said, it is fair to say that this side of the project did not function as originally intended due in part to inflexibility in the WB delivery model. Due to constraints imposed on the WB hired consultant there was limited capacity to engage in the kind of flexible and opportunistic outreach to international stakeholders deemed a key part of the project’s delivery model in terms identifying and supporting would-be investors and correspondent banks.

Over the course of FSI, a series of stakeholder events - run by the WB - were held 3-4 times/year which were well attended and received, bringing together all 13 Somali banks with international banks, DFIs and investors. These events brought in expert speakers from organisations such as the Wolfsberg Group the Financial Action Task Force as well as facilitating knowledge exchange sessions and bilateral between DFIs/correspondent banks and Somali banks. Over the past two years, at FCDO's request, FSI has made more concerted efforts to raise the profile of the project. This has included staging events at WB Spring and annual meetings in Washington DC (2024 & 25) which pitched the project and its mission in front of a wider set of stakeholders, including US treasury and involved senior UK government representation.

Aside from these convening events, outreach to local and international stakeholders by FSI was limited. For example, WB outreach with Somali banks was done primarily through the Somali Bankers Association (SBA), with limited bilateral engagement, which slowed the building of trust, especially with the big two banks. Given that these two banks account for over fifty percent of the market, the participation of at least one of them was seen by the FCDO team as key to the credibility and impact of the project. As such, FCDO – in agreement with WB - led efforts to bring these banks on-board through extensive high-level engagement and influencing which involved the UK’s Ambassador to Somalia and FCDO’s Development Director for Somalia. These efforts led directly to the securing of Dahabshiil Bank’s participation in the project from mid-2024.

Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]

Lesson: The underlying rationale behind FSI’s theory of change, i.e. that Somalia’s isolation from the international financial system undermines economic growth prospects as well as stability, remains valid. While it is too early to say if the approach and assumptions behind it will deliver real progress against FSI’s ambitious objectives, the evidence to date – notably in the form of tangible interest from two DFIs in Somali banks– is encouraging.

Lesson: Establishing correspondent banking relationships remains a high priority issue for the financial sector and private sector at large, illustrated in the strong engagement seen at FSI’s stakeholder events; the Central Bank of Somalia (CBS)’s vocal support for the project (the Governor has repeatedly cited it as one of the country’s ‘most important projects’), and; seen in FCDO’s own interactions with the private sector. FCDO must ensure that the important trust and credibility it has established with private financial institutions on this issue are built upon.

Lesson: From a monitoring and evaluation perspective, greater consideration and creativity could have been given by the programme team on how to capture progress, particularly on the pathways to change between the more operational milestones and the outcome level indicators of the project.

Lesson: The process of building trust with Somali banks was hampered by (unavoidable) constraints in the security/operating environment which restricted in-person meetings. More avoidable in terms of future lessons were the constraints on local and international stakeholder engagement imposed by an inflexible WB delivery model.

Recommendation:

Recommendation: Work closely with WB team and central bank to ensure that steps are taken to validate and/or promote the progress made by participating banks' in FSI - including a final assessment of bank's progress against action plans - and ensure that steps are taken to harvest and disseminate lessons/data from this part of the project.

Recommendation: FCDO to initiate and carry forward discussions with WB on the future direction of AML/CFT support to the financial sector and how to build on FSI's progress. This should include open and frank discussions on how best to work with the private sector on compliance and enforcement and the optimal methods for doing this.

Recommendation: For any future activity in the space, more consideration and creativity will be needed at design stage on how progress will be measured and in identifying pathways to change, particularly with regards to the linkages between the technical work carried out and its influence on the perceptions and decision-making processes of foreign investors and banks.

D: Value for Money [½ - 1 page]

VfM performance compared to the original VfM proposition in the business case

As stated in the last Annual Review, the value for money metrics for SIGS in the business case measured the programme’s ability to meet outputs, outcomes, and impact. IRiS had developed its own framework that aligned with that original proposition. The overall VfM assessment for IRiS has not changed since the last Annual Review given programme closure. Whilst FCDO has worked closely with the World Bank to try and deliver value for money, the lack of data at the outcome level means measures of effectiveness are harder to make.

Economy
IRiS delivered poor value for money in terms of economy, with key cost-drivers being their non-budget activity at 60% and 39% only accounting for grants and activities on the ground. At the last annual learning event held in August 2024, USAID and FCDO highlighted this as a major concern and asked the IRiS implementing team to review it. Until the point of programme closure, the IRiS team had still not provided an updated budget for the following year’s activities.

Efficiency
Allocative efficiency: ITAD formed part of the IRiS consortium and had a role in generating research and evidence to inform programming. In the second year ITAD led a review of existing evidence across the target productive sectors, helping IRiS shape initial activities. Beyond the initial scoping work, ITAD did not deliver further outputs for IRiS. The challenges included a lack of research expertise on the ground, a data poor context, lack of vision in the first years that made it difficult to identify areas for further investigation and a lack of adaptive management and theory based evaluative thinking from the MEL team. ITAD was remote, working from the US, making it difficult for them to integrate and demonstrate additional value. The process for identifying IRiS activities started with a call from proposals from businesses looking for finance in terms of grants. This bottom-up approach had its merits in terms of being demand led, but resulted in a lack of strategic direction from IRiS with regards to who got selected. This delivered issues in terms of equity of impacts, and gave rise to the concerns around the programme reinforcing the existing dynamics within Somalia where just a few companies benefit, and others (without the technical capability or access) may be pushed out.

Technical efficiency: Gargaara, FSI and IRiS all experienced slow delivery of outputs in the first two years, leading to two consecutive B scores for SIGS in 2022 and 2023. 2024 was a turning point in the programme, with Gargaara disbursements increasing at more rapid rates given the successful onboarding of more financial institutions including MFIs, and IRiS activities in the agriculture sector, rapidly scaling. FSI also started gaining strong support and trust from local banks. However, output results in the fisheries and livestock sectors remained modest in IRiS. Notably they are also sectors with a much smaller proportion of disbursements through Gargaara compared to agriculture.

Relational efficiency: With IRiS, the FCDO and USAID have enjoyed a collaborative relationship. FCDO holds monthly meetings with USAID to discuss IRiS project implementation. There has also been a good working relationship between FCDO and the World Bank with regular monthly meetings being held to track progress with the implementation of Gargaara and FSI projects. In terms of downstream partners, the IRiS process of receiving grant applications from businesses meant that activities were informed using a bottom-up approach, however, as described already this also had drawbacks. The monitoring system within IRiS was effective, with opportunities for direct feedback from beneficiaries on at least an annual basis through surveys and focus groups. These findings helped to steer activities. However, more engagement of beneficiaries at the early stages of programme design would have delivered better results. The World Bank have a close relationship with the Gargaara team, providing administrative oversight, management supervision and capacity support. Gargaara is responsible for supporting and engaging with the PFIs and MFIs. Whilst they have conducted some outreach and training to the on-lending institutions, there has been no direct engagement with the end service users e.g. the businesses benefitting from loans.

Dynamic efficiency: With FCDO not being the main donor for any component of SIGS, it has had limited influence over process, which has often negatively impacted the ability of the programme to flex during implementation. In IRiS approval of project proposals were often delayed by bureaucratic processes in DT Global (the main consortium partner). Progress in FSI has also been hampered by the World Bank's inflexible engagement approach coupled with delays in contracting and delivering diagnostics for Somali banks. The World Bank have also been slow to convene consultations around the future sustainability plans for Gargaara, but now have a consultant to understand the options for institutionalisation and should be ready to share findings by the end of this year. Monitoring has been used to inform changes to interventions in IRiS, with annual surveys and ongoing analysis to understand challenges and opportunities. The lack of data from Gargaara beyond disbursements has meant the programme has focussed on scale more than quality, with little evidence of using data to adjust strategy.

Effectiveness: Outcome results across IRiS were not consistent across sectors. In the fisheries and livestock sectors, IRiS struggled to identify activities which would trigger change within market systems at scale. Feasibility of approaches was often an issue – with ideas ranging from jetty construction to solar fridges meeting significant obstacles in implementation. Despite this, outcome level changes were beginning to emerge, with 74,305 people reporting increased resilience, largely as a result of activities in the agriculture sector.

As mentioned already, Gargaara failed to report any outcome level evidence and therefore effectiveness is difficult to assess. Given the information available, there is some evidence that transformational change within the sector might be happening – with more loans now being disbursed to MSMEs in sectors that we know have historically been left out. However, it is difficult to ascertain attribution given the lack of data.

Equity: IRiS recorded a fair spread of its beneficiary outreach across all the intervention areas. Among the 33,122 project participants reached, 53% were women, 27% youth and 5% persons with disability. A total of 576 of the 665 project participants who accessed credit, were also women since the intervention specifically targeted women owned enterprises. Gargaara made some progress in terms of increasing reach to women, but this was mostly through the onboarding of MFIs, which disburse smaller loan amounts. Therefore, while the number of women businesses reached with loans significant increased, the total amount disbursed overall remained low at only 12.3%.

E: Risk [½ - 2 pages]

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance. [1/2 page]

The Supporting Inclusive Growth in Somalia (SIGS) programme was implemented over five years (2020 – 2025) in a complex, high-risk, and rapidly evolving environment. Initially assessed as carrying Major risk, the programme’s risk level declined to Moderate in 2023 and reached Minor by 2025, all while remaining within FCDO Somalia’s defined risk appetite. This positive risk trajectory was underpinned by strengthened partner capacity, improved political stability, enhanced communication and reporting, and robust monitoring systems.

Despite significant external shocks including the COVID-19 pandemic, geopolitical instability, and operational constraints in fragile and conflict-affected areas, SIGS consistently delivered results on time and under budget, demonstrating strong adaptive capacity and effective risk mitigation. Key risk drivers included:
- Funding shortfalls and donor budget adjustments
- Operational challenges in insecure and fragile contexts
- Capacity limitations among partners and beneficiaries
- Limited political incentives for reform
- Data quality concerns
- Exposure to fraud and corruption risks

FCDO and its implementing partners adopted a proactive, collaborative, and context-sensitive risk management approach. This included regular structured engagements (bi-monthly/monthly), continuous risk monitoring, adaptive programme design, and the use of informal channels to address emerging risks. Risk registers were actively maintained and updated, enabling timely course correction and safeguarding programme integrity. Listed below are the key risk categories and mitigation highlights:
- Strategy and Context: Political volatility, climate extremes, and macroeconomic shocks were addressed through adaptive design, strengthened remote monitoring, and political economy analysis.
- Policy and Programme Delivery: Delays in contracting and implementation were mitigated through early capacity assessments, streamlined protocols, and improved coordination platforms.
- Financial and Fiduciary: Despite budget cuts and aid pauses, no fraud was reported. Financial oversight was maintained through rigorous forecasting, scalable design, and transparent reporting.
- Safeguarding: No safeguarding incidents were reported. SEAH training, integrated risk assessments, and periodic audits ensured compliance and accountability.

Lessons Learned
- Partnerships & Assurance: Trust-based relationships with multilateral partners enabled flexible assurance mechanisms beyond formal agreements.
- Sustainability: Remains a key risk to long-term impact and VfM. Future programmes should embed sustainability from the outset, with clear exit strategies and local ownership models.

Update on Partnership Principles (delete this section if n/a) [1/2 page]

As FCDO does not provide direct development assistance to the Somali Governments, the Partnership Principles (PPs) were not applied to SIGS programme. The implementation of the SIGS however, sought to remain compliant with the British Embassy Partnership Principles assessment and guidance on working with government.

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency. [1 page]

The Supporting Inclusive Growth in Somalia (SIGS) programme was implemented through two core partners: the World Bank (WB) and USAID. This section summarises the implementation of SIGS, FCDO’s performance, and the contributions of its delivery partners.
Programme Implementation
WB initiatives, namely Gargaara (a Somalia apex fund) and the Financial Systems Initiative (FSI), aimed to stimulate investment through Somalia’s financial sector. Gargaara, registered with the Central Bank of Somalia, operates as a microfinance institution providing concessionary financing to commercial banks and micro-financial institutions. It targets productive sectors such as farming, livestock, fishery, and renewable energy. Gargaara is wholly funded by the World Bank through IDA and the Multi-Partner Fund (MPF), with KfW as an additional donor.
USAID’s initiatives co-funded by FCDO included GEEL (2020–2021), which supported businesses affected by the COVID-19 pandemic, and IRiS (2022–2025), which used a market systems approach to address constraints to private sector growth. IRiS was delivered by a consortium led by DT Global, partnering with Mercy Corps, Save the Children, SATG, and ITAD.
FCDO Performance
FCDO remained actively engaged throughout SIGS implementation, maintaining regular coordination with implementing partners and USAID. However, the absence of a bilateral delivery mechanism limited FCDO’s strategic influence, particularly in governance structures. Despite repeated requests, a steering committee for IRiS was not established, and FCDO’s influence over WB-led components remained limited.
Nonetheless, FCDO demonstrated strong performance in several areas:
- Direct engagement with Gargaara and financial institutions provided valuable implementation insights.
- Field presence was maintained through regular visits to Somalia.
- Convening power was leveraged to foster collaboration, including initiating discussions between BII and Gargaara, and facilitating onboarding of major Somali banks into the FSI programme.

Partner Performance
a) World Bank
- Quarterly engagements and reporting were consistent, but rigid engagement and delays in contracting slowed start-up of Gargaara and FSI.
- Gargaara’s local management board faced staffing and capacity gaps, delaying financial institution onboarding.
- Progress was made in enhancing governance and operational structures.
- Engagement with stakeholders attracted co-investment, including KfW’s investment in 2023.
- Data and evidence on outcomes remain limited.
b) USAID
- Partnership with USAID began in August 2020 to support Somalia’s COVID-19 response via GEEL.
- GEEL, implemented by DAI, achieved strong results including improved food security and job creation.
- FCDO contributed to IRiS design and evaluation, later implemented by DT Global and consortium partners.
- USAID valued FCDO’s technical input, but contractual structure limited oversight and strategic coherence.
- DT Global faced early challenges but improved delivery over time; suitability of market systems approach remains in question.
- Pause and Reflect sessions facilitated stakeholder collaboration and coordination.
- FCDO/USAID partnership encouraged IRiS collaboration with other FCDO programmes in the same geographic focal zone to build synergies and optimise results.
These performance issues must be viewed within the broader context of Somalia’s challenging operating environment, including weak infrastructure, limited regulation, and climate-related shocks. The ambition of the original SIGS business case may have underestimated these constraints.
Financial Performance

The SIGS programme was approved at £38 million over seven years (2020–27). By October 2025, £13.48 million (35%) had been spent. Programme delivery was significantly impacted by the COVID-19 pandemic, reductions in the UK’s Official Development Assistance (ODA) budget, and the US government’s pause on development aid, leading to early closure. Implementing partners demonstrated flexibility by revising budgets and adjusting planned activities in consultation with FCDO and participating donors to align with these constraints.

Below is a breakdown of SIGS spend against its original SIGS business case budget:

SIGS / Components	SIGS BC / Budget (£m)	Actual / Spend (£m)	Actual Spend Rate (%)
Programme design (300370-101)	£0.4m	£0.13	33%
GEEL ((300370-102)	£3.5m	£2m	57%
IRiS (300370-103)	£16.5m	£4.12	25%
Gargaara (300370-104)	£11.5m	£5.45m	47%
FSI (300370-105)	£3.5m	£1.38m	39%
Programme funded post (MEL) costs (300370-106)	£1.08m	£0.35m	32%
MEL Consultancy (300370-107)	£1.52m	£0.05m	3%
TOTAL	£38	£13.5m	36%

Programme-level approach to monitoring and evaluation

USAID had an internal monitoring, evaluation and learning provider, Evaluation, Learning, and Monitoring Initiative ELMI, which provided technical inputs into the monitoring and evaluation plan for IRiS. There was also a planned mid-term review underway by an external provider, but unfortunately this was not completed before the termination notice. Using the embedded FCDO Adviser resource a developmental evaluation approach had started, with one rapid analysis produced on the relevance of the market systems approach in Somalia. This produced some valuable insights – that the approach was relevant, but there were some constraints and risks emerging. Namely that support was going to MSMEs which were sometimes already well-resourced and supported, and that unequal power dynamics between producers and MSMEs could sometimes limit the benefits for the most marginalised. IRiS had begun to discuss strategies to mitigate against this, including changing the process by which MSMEs were selected for support.

Throughout implementation, the IRiS MEL team also produced regular reports to track progress and share learning. This included weekly updates, larger monthly reports and quarterly progress reports. A Pause and Reflect was also held once per year providing an opportunity for cross-sectoral learning and challenge to strategy.

With regards to the World Bank, programmes are provided with compliance and progress checks through their third-party monitor supplied by Abriynt. The reports have not yet been shared with FCDO. They also produce quarterly reports to update on progress and set priorities for the coming quarter.

FCDO provided a programme funded embedded adviser to the programme.  There was never any demand from the World Bank to use this resource for Gargaara as they felt the team needed to focus on implementation – the embedded MEL could have been a distraction.  USAID did support the MEL Adviser in IRiS but there were issues with defining a role that was distinct from the MEL Director role.  In the end the MEL Adviser tried to implement a developmental evaluation approach – working with the team to collate and analyse information in real-time and attempting to produce insights for adaptation.  However, since this was never a demand from the team, access to relevant meetings and tasks remained limited and therefore, there were limited opportunities to engage in a way that this type of evaluation approach requires.  Despite this the MEL Adviser managed to lead an evaluation on the relevance of the market systems approach in Somalia which did produce some useful insights and summarised evidence that could be used in the final Annual Pause and Reflect session.

Date of last narrative financial report	Gargaara Q4 Progress Report - 4th March 2025 / IRIS narrative report October 30, 2024	Date of last audited annual statement	IRiS Audit Report - February 2025

MSMEs are the principal mechanism through which inclusive, job-creating growth and by extension, competitive, well-functioning markets for poor people can be delivered. (Evidence: Transnational Capital in Somalia – The Blue Desert Strategy, 2019)