## SPFM Annual Review

Title: Strengthening Public Finance Management in Tanzania (SPFM)
Programme Value £ (full life): £20M FCDO funding, and £4.6M USAID funding		Review date: 20/05/2024
Programme Code : 300379	AMP start date: 20/02/ 2018	AMP end date: 31/03/ 2026

Summary of Programme Performance

Year	2019	2020	2021	2022	2023	2024	2025
Overall Output Score	B	A	A	A	A	A	A
Risk Rating	Major	Major	Major	Major	Moderate	Minor	Minor

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/24053414.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0006456.xlsx

## Key abbreviations:
BHC	British High Commission, Dar es Salaam	ODA	Official Development Assistance
CAG	Controller and Auditor General	PEFA	Public Expenditure and Financial Accountability
DPs	Development Partners	PFM	Public Financial Management
DPG PFM & Tax	Development partners group working on PFM & Tax	PFMRP VI	Public Financial Management Reforms Programme Phase six
FCDO	Foreign, Commonwealth & Development Office	PoRALG	Resident’s Office Regional Administration and Local government
FRA	Fiduciary Risk Assessment	REPOA	Research on Poverty Alleviation Programme Limited
GBP	Great Britain Pound	SPFM	Strengthening Public Financial Management Programme
GIF	Governance Innovation Fund	TRA	Tanzania Revenue Authority
GoT	Government of Tanzania	TZS	Tanzania Shillings
LGA	Local Government Authorities	VfM	Value for Money
MUSE	Mfumo wa Manunuzi Serikalini

## A: SUMMARY AND OVERVIEW

Description of programme
The Strengthening Public Financial Management (SPFM) in Tanzania is a Programme that started in 2018 with the aim of supporting Government of Tanzania (GoT) in reforming and strengthening public financial management. SPFM uses a partnership approach by primarily supporting government’s PFM reform programmes[1], through Financial Aid complemented by Technical Assistance to local and central government as well as accountable grants to non-state actors. The programme supports PFM reforms in mainland Tanzania and Zanzibar.
[1] Public Financial Management Reforms Programme (PFMRP) Phase V and VI
The SPFM programme has gone through a series of adaptations to match the ever-evolving context ranging from ODA cuts to changes in the political environment in Tanzania. Support for the period under review (April 2024-March 2025) was provided through Financial Aid to the Government of Tanzania and Zanzibar for supporting implementation of the PFM Reform Programme Phase VI (PFMRP VI) which is co funded by the World Bank; Technical Support for short term technical assistance to the President’s Office Regional Administration and Local Government (PORALG); and Fiduciary Risk Assessment (FRA). The team also used Programme funds to commission an audit of two accountable grants to British Council and Research on Poverty Alleviation (REPOA)[2] which ended last year.
[2] REPOA is an independent local think tank that engages in policy research and dialogues that promote socio-economic transformation for inclusive growth

Summary supporting narrative for the overall score in this review
This year, SPFM programme performance met expectation with an average score of “A” across outputs.

During the review exercise, development, upgrade and integration of a number of Public Financial Management (PFM) systems both at central and local level had been completed and a few systems were nearing completion. In addition, short and long-term trainings of different government officials both in mainland Tanzania and Zanzibar across different PFM components were successfully delivered. The programme also supported different PFM analysis. The objective of these reforms is to improve Tanzania’s PFM performance as laid out in the sixth Public Financial Management Reform Programme (PFMRP VI) which in return will accelerate Tanzania’s growth and service delivery to citizens. The following results recorded during the review period are worth highlighting:

- Tanzania Revenue Authority (TRA) increased active taxpayers from 1,705,000 to 1,851,324 which resulted in an increase in tax collection from TZS 3.465 trillion to TZS 3.587 trillion.
- For effective management of public debt, the Ministry of Finance conducted a debt sustainability analysis and reviewed the Medium-Term Debt Strategy. These assessments serve as a guiding framework for making informed borrowing decisions, ensuring a balance between gross financing needs and the capacity to repay debts both in the current and future periods
- The National e-Procurement System of Tanzania (NeST) was upgraded to include modules on e-contract and e-auction modules have been added, in addition suppliers can now lodge complains online. NeST is rolled out to all LGAs, improving competition and transparency of procurement in Tanzania.
- Drafting of the Medium-Term Revenue Strategy (MTRS) for the government of Tanzania was completed. The MTRS lays out government targets and strategies to raise domestic revenue mobilization in the medium term.

Major lessons and recommendations for the year ahead

The following recommendations will help the programme to generate results during its last year of implementation as well as considerations for future support in the new world of reducing ODA . Further detail on the rationale underpinning each recommendation can be found in the Detailed Output Scoring section.
All PFM systems (including software) under this output were developed internally as opposed to purchasing off-the-shelf software packages which are costly in the long run especially in cases where there is need to upgrade the system given the ever-emerging PFM needs. Off-the-shelf software packages also create dependency on technical skills from the supplier. A performance audit on cost effectiveness of Internally developed ICT systems conducted by CAG for FY 2023/24, noted that Outsourced systems were acquired at a relatively higher cost than in-house systems. The average cost for acquiring systems through outsourcing was TZS 1.3 billion Vs inhouse TZS 459.4 million.

Although it is ideal to develop such complex systems in-house, people with such skills are scarce and the demand for their skills is high especially in the private sector. There is therefore need for GoT to design retention policies for such critical skills. Moreover, with increasing cyber-attacks risks, GoT needs to put in place strong security measures to counter any potential attacks to the PFM systems it has heavily invested in.

Output one and its corresponding indicators and milestones are congested and cut across different priority areas and strategic objectives of the Public Finance Management Reform Programme (PFMRP VI), making it difficult to consistently track progress made against PFMRP VI on which the SPFM programme is anchored. We recommend the SPFM team to decongest the output, indicators and milestones for easy tracking of progress made against the PFMRP VI. For instance, all PFM systems development, upgrade and integration could come together under one indicator

The PFMRP VI secretariat is encouraged to adhere to the quarterly reporting frequency as per PFMRP VI operating manual which is in line with FCDO Programme Operating Framework (PROF) rules. This is especially important because it allows reviews to comprehensively capture progress made. It also helps the programme team to track progress on a quarterly basis and devise corrective measures early enough in case there is potential deviation from original plans.

Disbursements from FCDO should be made early enough to allow Government partners to start implementation early.

Government partners are encouraged to adopt result-based reporting because it helps readers to understand how PFMRP results are being achieved. Narrative reports should also capture challenges and lessons learned. This is particularly important for the programme team to come up with solutions to the challenges.

Fiduciary Risk Assessment (FRA): Monitor fiduciary risk mitigation measures on a regular basis. Most of the mitigation measures are part of the PFMRP VI which the SPFM programme and other Development Partners like the World Bank are already supporting.

Reprioritisation: BHC Tanzania needs to start engaging GoT on strategic PFMRP VI areas to support across different PFMRP VI priorities for the future. An interesting area to continue supporting is Local Government Revenue collection through property tax and rental income tax. With reducing ODA globally, property tax has the potential to boost Domestic Revenues to finance GoT development needs. The current policy of levying property tax on electricity bills not on property value can be improved to ensure property tax is based on the actual value of property. The International Centre for Tax (ICTD) and Local Government Revenue Initiative (LOGRI) are thinktanks working closely with FCDO Public Finance and Tax Department (PFTD) that have extensively researched and advised a number of African Countries on property tax. BHC Tanzania may want to engage these think tanks.

Coordination mechanisms need to be strengthened: Government officials reported transaction costs in dealing with multiple development partner demands as well as limited knowledge on what different DPs are supporting under the PFMRP VI programme. The Ministry of Finance needs to take a leading role in coordinating DPs who are supporting PFM and Tax reforms with support from UK as the co-chair of the Development Partners Group working on Public Financial Management and Tax (DPGM PFM & Tax).

Political and Governance Team role: The team especially the Governance cadre will need to play a more cross-office role e.g in conducting political economy analysis for teams delivering programmes in other sectors such as Education, Health, economic growth, social protection. The analytical work on budget, findings of the Controller and Auditor General, and other pieces the team has been leading across the office will continue to be of great importance to the office and to the DP community.

Leveraging Centrally Managed Programmes: With bilateral aid likely to reduce significantly, Centrally Managed Programmes will be an option to complement PFM work at post. For instance, the Public Finance Resource Centre is likely to have funds which can be used to finance PFM activities in posts

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The impact statement in the original business case is ‘public resources are allocated more strategically and used more efficiently and effectively to support service delivery’ and the outcome statement is ‘improved fiscal and tax policies, enhanced public capital spending and strengthened budget management and strengthened financial accountability and oversight’. These statements have not changed, and they remain relevant to the programme. Also, the revised assumptions in the business case addendum of 2023 continue to hold up.

SPFM outputs were revised in the business case addendum with an aim of aligning more to interventions that better link improvements of PFM to service delivery. The revised outputs are improved macroeconomic and macro-fiscal policy making, budget management, execution and scrutiny, and budget control and oversight; Improved Financial Accountability and Oversight and Audit; PFM systems and outcomes in Local Governments are improved; Improved research and analytical capacity on macroeconomics, PFM and business environment in Tanzania

Although the SPFM programme experienced budget cuts and financial aid pause in the early years, small budgets channelled through different delivery partners over the years i.e REPOA on macroeconomic research, British Council on scholarships and Palladium which delivered Governance Innovation Fund (GIF), all contributed to the SPFM programme outcomes and impact.

Whilst the SPFM programme logframe does not have metrics to measure the extent to which the programme is addressing the “leave no one behind” agenda i.e., age, sex, disability, geography, we judge that the programme is directly and indirectly contributing to the agenda. Effective Public Financial Management and increased revenues are enabling factors for improved service delivery to social sectors such as education, health, water and sanitation, etc, which significantly contribute to socio-economic wellbeing of people, especially women and girls and people with disabilities. One of the interventions during the review is supported to gender responsive budgeting which is expected to improve the way GoT plans and budgets for girls and women. Also, 40% of GoT civil servants who benefited from the master’s programme scholarship scheme were women and they have subsequently progressed in their respective careers. Furthermore, support for increasing own source revenues across Tanzania’s regions and local government authorities is expected to accelerate development in remote areas. The programme also supported the review of the guidelines for participation of Special Groups in Public Procurement in line with newly enacted Public Procurement Act (PPA), 2023 and PPR, 2024. The review was conducted to take into consideration the participation and engagement of special groups with respect to the National Supply Chain Management Policy of 2025 and Public Procurement Regulations of 2024.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
SPFM has been tracking progress on three main outcome indicators.
- Outcome indicator 1: There has been progress on the fiscal and tax policy making and accountability in Tanzania. These policies have been the basis for providing frameworks for Information Systems development and integration.
- Outcome indicator 2: Budget allocations on service delivery remain low despite relative to the current needs and ongoing population increase. For years, service delivery has been dependent on donor funding, but the government needs to improve allocation of budget to deliver services effectively.
- Outcome indicator 3: While the National Audit Office in Tanzania is the strongest in the region, government commitment to implement their audit recommendations remain relatively low, and in this reporting period in particular, it is lower than the previous year.

Below is a table summarising progress on outcome indicators.
Outcome	Outcome indicator	Milestone for this review	Progress
Improved fiscal and tax policies making and accountability in Tanzania	Positive changes in policies, acts, manuals, and guidelines on public finance management in line with PFM reforms in Tanzania and international standards	At least 2 acts revised in line with international standards	The public finance act was reviewed in this reporting period. / Efforts to reform public procurement legislative framework has started with the review of public procurement operational manual.
Improved budget credibility on service delivery - Higher public investment & budget out-turn	% of budget allocated and disbursed to service delivery sectors	% Budget allocated for FY 2024/25 / • Education 13.41% • Health 5.49% • Social security 5.28% • Water 1.73%	Budget implementation rate for FY 2024/25 / • Education 12.6% / • Health 5.3% / • Social security 5.28% / • Water 1.3%
Improved financial accountability and oversight	% of implementation of audit recommendations.	45%	Only 39% of all external audit recommendations were implemented for FY 2023/24 which is lower compared to 41% in FY 2022/23

Progress made across the outputs and previous years’ performance suggest that the SPFM programme is on track to contribute to expected outcomes. SPFM has contributed to ongoing country efforts to reform and strengthen PFM systems below are some key impact level indicators.
Despite a decrease in aid to the country, Tanzania has been surpassing its revenue collection target (2021/22 collection was 101%, 2022/23 was 101% and 2023/24 was 105%) as a result of domestic revenue and borrowing. Domestic revenue mobilisation potential in Tanzania is high with government working to reform tax administration and local government own source revenue framework and strategies. SPFM Supported the government in their efforts to improve property tax, and improvement of State-Owned Enterprise (SOE) management.

Source: Controller and Auditor General Reports FY 2023/24

There has been a significant improvement in the number of government institutions being audited with 95.5% getting unqualified audits. SPFM has been supporting the National Audit Office of Tanzania and the government to improve on their financial reporting which has improved the quality of financial reporting. More work still needs to be done on implementation of external audit recommendations which was low at a rate of 39% in 2023/24.

According to World Bank’s governance indicators there has been improvement on ‘governance effectiveness indicators’ in Tanzania since 2018. This includes Public Financial Management performance as reflected in the PEFA 2022. SPFM has continued to support PFM reforms in Tanzania through PFMRP VI. UK has been contributing through supporting improvement in the legal framework, policies, IT systems, human resource capacity, and oversight functions which has improved public financial management in Tanzania significantly.

According to the Assessment of Tanzania Public Procurement System (MAPS 2025), the institutional framework for public procurement in Tanzania is well established, an e-procurement system is in place, and the country public service recognises procurement as a profession by establishing a professional board covering both procurement and supplies professionals. SPFM has supported government efforts to develop and rollout NeST including to the local government. SPFM has also supported improvement in policies, manual and capacity of procurement practitioners in the government.
The next reporting year is the final programme year, SPFM should focus on reforms areas that have already started and are high priority to the government. The programme should also document lessons learned from this programme to be included in future support on this area.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

SPFM continues to demonstrate good VfM. A thorough VfM assessment was conducted in this reporting period, specifically rating then Economy, Effectiveness and Cost Effectiveness of the programme, which was considered ‘good’ and efficiency and equity, which is considered ‘moderate’. SPFM successfully concluded the evaluation of the scholarship programme with majority of beneficiaries recording transformative successes on their return to the Ministry of Finance where they have been able to lead strategic work that further enhances the sustainability of the programme. For examples, many scholars were involved in significant projects, such as the National Five-Year Development Plan, showcasing their contributions to national policymaking. Some scholars played key roles in preparing economic reports, securing concessional loans from international bodies like the IMF, and implementing the Tanzania COVID-19 Socio-economic Response and Recovery Plan (TCRP). In addition, an FRA was conducted for central and local systems in Tanzania Mainland and Zanzibar which has made us understand the fiduciary environment in Tanzania. The SPFM is positioned to mitigate majority of risks associated with providing financial aid in Tanzania in both Zanzibar and Tanzania for our service delivery and anti-corruption work. SPFM support to government reforms programmes has had direct effects on policies and practices of managing public funds allocated for service delivery for example our support to PoRALG and Regional Secretariat on developing local government own source revenue strategy framework and strategies and supporting training on property tax.

SPFM continues to be relevant and an important contribution of UK in strengthening government systems in Tanzania sustainably. SPFM should therefore be allowed to continue for the last year including to gather lessons for future engagements.

## C. DETAILED OUTPUT SCORING

Output Title	Improved macroeconomic and macro-fiscal policy making, budget management, execution and scrutiny, and budget control and oversight.
Output number:		1	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR.	Yes, the weighting has gone up.

Indicator(s)	Milestone(s) for this review	Progress
Improved macro-economic management (prudent fiscal, tax and debt policies) as a basis for a credible budget	Draft Medium Term Revenue Strategy completed.	Completed – Drafting of Medium-Term Revenue Strategy completed, tabled for management approval.
	Development and upgrade of 6 information Management systems completed	Partly completed / Phase one of Universal billing system completed. / Office of the Treasury Registrar Management Information System (OTRMIS) system upgrade completed, integration with other financial systems is ongoing. / Automation of Block Management System through mapping of taxpayers using Geospatial Information System (GIS) to capture physical addresses of taxpayers has completed. / Direct to Project Fund Management Information System (D-Fund MIS) upgrade is ongoing to be completed in June 2025. / Ministry of Natural Resources and Tourism Portal (MNRT) upgrade is ongoing and integration to at least 2 other government IT systems is ongoing. / Preparations for Zanzibar PFM IT system upgrade is completed.
	Taxpayer base upgraded	Completed: Tanzania Revenue Authority (TRA) increased the number of active taxpayers from 1,705,000 to 1,851,324.
Resources efficiently allocated on a medium-term basis in alignment with national priorities	M&E framework for the government on public resource management developed	Ongoing: The concept note for developing monitoring and evaluation e-system was prepared, but development is ongoing.
	Integration and upgrade of 3 information Management systems completed	CS Meridian integration with MUSE completed. / Centralized Budget Management System (CBMS) integrated to MUSE completed. / Internal contingent liability and monitoring system development ongoing:
	Gender responsive budget guidelines development completed.	Ongoing: Draft TOR were prepared and shared with DPs for comments and engagement of a consultant for undertaking the assignment
Budget executed as planned and timely and accurate reporting is available	Rollout of cash management modules to public corporations	Completed: Cash management module was rolled out to 271 institutions
	Public Asset Management Guidelines review completed	Ongoing: Draft of the Public Asset Management Guidelines, 2024 is being prepared.

Briefly describe the output’s activities and provide supporting narrative for the score.
Interventions under this output are largely aligned to Priority Area One of the Public Finance Management Reform Programme (PFMRP VI), i.e. Domestic Revenue Collection and external resources Management Improved and its corresponding strategic objectives. The following achievements were registered during the period under review:

By December 2024, Tanzania Revenue Authority (TRA) had increased active taxpayers from 1,705,000 to 1,851,324. This increase enabled TRA to collect tax revenue amounting to TZS 3.587 trillion which is 3% above the target of TZS 3.465. The percentage of taxpayers filling VAT returns and making payments on time has increased to 91.2% for large taxpayers and 94% for domestic revenue respectively. To enhance revenue collection, the Ministry of Finance (MoF) through Policy Analysis Division embarked on developing Universal Billing System with customizable forms and workflows to address the challenges posed by existence of stand-alone billing systems across public institutions.

Several systems were upgraded in this review period to improve planning, budgeting, execution, management and reporting of public finances. These systems included both the management of state-owned enterprises, ministries, departments and local governments. Examples of systems upgraded are: The United Republic of Tanzania Planning and Reporting System (Planrep); Office of Treasury Registrar Management Information System (OTRMIS) and PSC performance dashboard.

In the period under review, grant and loan data for FY 2024/25 was reconciled to improve government reporting and reduce audit discrepancies. Furthermore, an analysis on Official Development Assistance (ODA) flows from FY 2005/06 to 2023/24 was conducted to assess inflows, allocation, and effectiveness; and preparing monthly performance reports for grants and concessional loans. In addition, the D-Fund[3] Management Information System (D-Fund MIS) was reviewed and supported through the analysis of 1965 expenditure requests totalling 2,511.74 million shillings, ensuring compliance with financing agreements and improving fund disbursement for development projects. The review will be followed by a system upgrade.
[3] D-Fund refers to all development funds contributed by development partners.

On debt management, the Ministry of Finance conducted a Debt Sustainability Analysis (DSA) and reviewed the Medium-Term Debt Strategy. The assessment also serves as a guiding framework for making informed borrowing decisions, ensuring a balance between gross financing needs and the capacity to repay debts both in the current and future periods.

To improve macro-economic management, 15 technical staff from Zanzibar Planning Commission (ZPC) were trained on economic dynamic model and economic inflation forecasting model.

Implementation of most of the interventions under this output especially PFM systems (which normally take long) was completed although implementation of a few other interventions was still ongoing because implementation started in July 2024 instead of April 2024, the start of UK fiscal year, due to delays in disbursing funds to GoT.

Also, implementation progress made during January-February 2025 quarter was not reflected in this review as there was no progress report submitted by the partner.

Despite of the above challenges, we judge that this output is on track.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes were observed for this output.

This output and corresponding indicators and milestones are congested and cut across different priority areas and strategic objectives of the Public Finance Management Reform Programme (PFMRP VI), making it difficult to consistently track progress made against PFMRP VI on which the SPFM programme is anchored. We recommend decongesting the output, indicators and milestones to ease tracking of progress made against the PFMRP VI.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Last year, there were no activities implemented under this output due to the pausing of financial aid as a result of the reduction in the ODA budget. This output was therefore not reviewed.

Lessons and Recommendations

All PFM systems (including software) under this output were developed internally as opposed to purchasing off-the-shelf software packages which are costly in the long run especially in cases where there is need to upgrade the system given the ever-emerging PFM needs. Off-the-shelf software packages also create dependency on technical skills from the supplier. Although it is ideal to develop such complex systems in-house, people with such skills are scarce and the demand for their skills is high especially in the private sector. There is therefore need for GoT to design retention policies for such critical skills. Moreover, with increasing cyber-attacks, GoT needs to put in place strong security measures to counter any potential attacks to the PFM systems it has invested in. The Controller and Auditor General (CAG) conducted a performance audit on cost effective of internally developed government ICT systems[4] which identifies these issues and recommends appropriate measures for the government to undertake. We will work with the government to ensure effective implementation of the recommendations.
[4] https://www.nao.go.tz/uploads/Performance_Audit_Report_on_Cost-Effectiveness_of_Internally_Developed_Government_ICT_Systems.pdf

This output and corresponding indicators and milestones are congested and cut across different priority areas and strategic objectives of the Public Finance Management Reform Programme (PFMRP VI), making it difficult to consistently track progress made against PFMRP VI on which the SPFM programme is anchored. We recommend decongesting the output, indicators and milestones to ease tracking of progress made against the PFMRP VI.

Government Partners are encouraged to adhere to the quarterly reporting frequency. This will allow reviews to comprehensively capture progress made. It also helps the programme team to track progress on a quarterly basis and devise corrective measures early enough in case there is potential deviation from original plans.

Partners are encouraged to adopt result-based reporting because it helps readers to understand how PFMRP results are being achieved. Narrative reports should also capture challenges and lessons learned. This is particularly important for the programme team to come up with solutions to the challenges.

The output indicator in the logframe on “Parliamentary Budget Office (PBO) staff, Parliamentary Clerks and parliamentary committee members trained on PFM oversight topics” which was under output one has been moved to output two (“improved financial accountability and oversight and audit”) as it is more aligned to oversight and audit.

Output Title	Improved Financial Accountability and Oversight and Audit
Output number:		2	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	Yes, the weighting has gone up.

Indicator(s)	Milestone(s) for this review	Progress
Performance on SO4: % compliance level of Procuring Entities as required by Public Procurement Act and Regulation	NeST upgrade to include e-contract management, e-catalogue and e -auction modules completed:	Completed. NeST has been upgraded with e-contract and e-auction modules
	Special group participation in procurement functions assessment completed	Completed: The Guidelines for participation of Special Groups in Public Procurement in line with newly enacted Public Procurement Act (PPA), 2023 and PPR, 2024 were reviewed
	Assessment of sustainable supply chain practices in public sector assessment completed:	Ongoing: A consultant has been engaged to assess sustainable supply chain in Tanzania; this work is planned to be completed in June 2025.
	Appeals hearing process automation completed:	Completed: Appeals modules have been included in NeST. Rollout is underway in two of five zones.
Performance on SO5: % of Controller and Auditor General recommendations in central government fully implemented	Testing tools for Technical Audit Laboratory acquired:	Completed: Testing tools for technical audit laboratory were acquired.
	15 NAOT4 staff trained on reporting audits in result based in line with AFROSAI-E5 standards completed:	Completed: 15NAOT staff attended the AFROSAI-E training on Monitoring, Evaluation, Reporting, and Learning (MERL)
	Parliamentary Budget Office (PBO) staff, Parliamentary Clerks and parliamentary committee members trained on PFM oversight topics.	Completed:30 PBO staff and 40 Parliamentary Clerks and 50 committee members trained on: Fiscal and Monetary policies; Public Debt Management; performance of revenue collection systems in LGA

Briefly describe the output’s activities and provide supporting narrative for the score.
This output combines Priorities Four and Five of the PFMRP VI which are Procurement and asset management and Audit and oversight functions respectively.

Progress made in Procurement and asset management
To improve the public procurement management, the Public Procurement Regulatory Authority (PPRA) developed e-Contract Management module, the Lower-level module and an integration of NeST with MUSE for contract payment for all procurement categories. Development of these modules has facilitated completion of modules in NeST system and will enhance application of the NeST in contract management and the use of it at lower levels. In addition, the micro value and Local Purchase Order (LPO) payment modules in NeST were developed and tested and a mobile application for procurement by villages was also developed and operationalized.

The Guidelines for participation of Special Groups in Public Procurement in line with newly enacted Public Procurement Act (PPA), 2023 and PPR, 2024 were reviewed. The review took into consideration the participation and engagement of special groups with respect to the National Supply Chain Management Policy of 2025 and Public Procurement Regulations of 2024.

The National Supply Chain Management Policy of 2025 was also approved by the Government and is expected to guide the Supply Chain practices in the country.
Progress made in Audit and oversight functions

To comply with AFROSAI-E standards, the National Audit Office of Tanzania (NAOT) strengthened capacities of 9 staff on Monitoring, Evaluation, Reporting, and Learning (MERL) and 440 auditors were trained on new IPSAS 41 standards and International Financial Reporting Standards on Sustainability (IFRS S1 and S2).

The audit data Laboratory System (ADLS) was acquired and was successfully integrated with four (4) Systems (MUSE, GePG, TAUSI and HCMIS) while integration of other systems such as GoTHOMIS, RGS, GARI-ITS and PSSF Fund Management System were in progress. The audit data lab system is developed to ensure that auditors have fully access to the Government systems which facilitate auditing exercise.
We judge this output to be on track.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
No changes were observed for this output.

The output indicator in the logframe on “Parliamentary Budget Office (PBO) staff, Parliamentary Clerks and parliamentary committee members trained on PFM oversight topics” which was under output one has been moved to this output as it is more aligned to oversight and audit.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

This output like the previous output was not reviewed

Recommendations

One of the output indicators for this output is “Performance on “SO5 - % of CAG recommendations in central government fully implemented”. However, there is no milestone/target indicating the percentage of recommendations implemented. It would be good to add this milestone/indicator in the coming year. There are targets in PFMRP VI which can be used.

Output Title	PFM systems and outcomes in Local Governments are improved
Output number:		3	Output Score:	A
Impact weighting (%):		40%	Weighting revised since last AR?	Yes, the weighting has gone up.

Indicator(s)	Milestone(s) for this review	Progress
Performance on SO6: Improved progress in building sustainable PFM capacity in LGA[5]	TAUSI system upgrade to accommodate new revenue sources completed	Completed: Upgrading TAUSI system to accommodate new Revenue Sources of Billboards, Land Rent and Service Levy for local governments have been completed. / The Property tax module to accommodate valuation process is ongoing to be completed by end of May 2025.
	Valuation modal and valuation guidelines for LGA property tax collection completed	Completed: Valuation modal and guidelines for property tax has been completed, awaiting approval by PoRALG Management.
	Rollout Integrated Financial Tracking Management Information System (IFTMS) to 26 Regional Secretariats completed	Completed: IFTMIS was rolled out in all 26 Regional Secretariats targeting MMI, IA and ICTOs staff. The next target was LGA staff (IAs, ICTOs)
	Train regional financial management officers, accountants and treasurers on Final Accounts Preparations using MUSE and [6]FFARS completed	Completed: Training to Financial Management Officers and Accountants was conducted to all 184 LGAs in three zones i.e Mwanza, Morogoro and Mbeya
[5] Local Government Authority
[6] Facility Financial Accounting and Reporting System

Briefly describe the output’s activities and provide supporting narrative for the score.
This output is aligned to the first priority area of PFMRP VI which is improvement of Domestic Revenue and External Resources Management. The following progress has been made:

The Presidents’ Office Regional Administration and Local Government (PO-RALG) was developing a property tax valuation model and guideline which will be used in collection of property tax. In addition, an assessment on service levy payment from communication industry was being conducted in six (6) cities (Dodoma, Mwanza, Arusha, Tanga, Mbeya and Dar es Salaam). The assessment was meant to collect relevant information for proper decision-making in collecting service levy from telecommunication companies.

PO-RALG has rolled out an Integrated Financial Tracking Management Information system (IFTMIS) to 26 Regions. IFTMIS is used to track implementation of internal and external auditor recommendations and facilitates inspection to regions and local government authorities which is normally conducted by PO-RALG.

PO-RALG also strengthened capacities of 394 Financial Management Officers and accountants on new developments and upgrades in MUSE system from 184 LGAs. This training was meant to capacitate LGAs technical staff on the use of the upgraded modules in MUSE system.
We judge this output to be on track

Describe any changes to this output during the past year, and any planned changes as a result of this review.
No changes observed for this output

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Lesson and recommendations

Despite an increase in own source revenue collection from TZS 8.5 trillion in FY2022/23 to TZS 9.9 trillion in FY2023/24, local governments remain dependent on central government grants by 88%. The revenue potential on local government remains relatively high especially with the LGAs starting to collect property taxes. There is also an opportunity for the LGA to review the service levy. For the next reporting period, SPFM will continue working with PoRALG to ensure that proper systems and processes are put in place to enhance revenue collection in LGAs.

Source: FY 2023/24 CAG reports

Output Title	Improved research and analytical capacity on macroeconomics, PFM and business environment in Tanzania
Output number:		4	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	Yes, weighting has gone down

Indicator(s)	Milestone(s) for this review	Progress
British Council: 80% of students completing their course (cumulative)	Project audit report completed	Completed: The project audit report was completed in September 2024
	Project completion report completed	Completed. 100% of students who were awarded the scholarship completed and passed.
REPOA: Progress against completion of studies and dissemination	Project audit report completed	Completed. The audit report was completed and approved in November 2024
Number of technical assistances provided to PoRALG[7] and MoF to complement PFMRP VI activities.	Fiduciary Risk Assessment for Tanzania Mainland and Zanzibar Completed	Completed. The FRA for Mainland Tanzania and Zanzibar has been completed.
	At least 2 TA related activities provided to PoRALG	Completed: The programme supported 2 staff from PoRALG to attend a training on property Tax in South Africa
	At least 2 TA related activities provided to MoF	Not started
[7] President’s Office Regional Administration for Local Governments

Briefly describe the output’s activities and provide supporting narrative for the score.

This output aims at improving research and analytical capacity on macroeconomics, PFM, and business environment in Tanzania. Interventions under this output contribute directly and indirectly to PFMRP IV priorities. In this review period, focused on finalising audits for accountable grants to REPOA and British Council.

Short term technical assistance was provided to President Office Regional Administration and Local Government (PoRALG) to lead ongoing support on going reforms in property tax in Tanzania. The programme supported two staff from PoRALG to attend a training on property Tax in South Africa. These officials are expected to advise the GoT on polices that will help LGAs to efficiently and effectively collect property tax given enormous potential for collecting more of this type of tax in Tanzania.

Plans to support the Ministry of Finance with technical assistance to conduct mid-term review of the PFMRP IV and Gender PEFA did not materialise due to FCDO decision to pause new procurements following UK ODA cuts from 0.5% to 0.3% of UK Gross National Income (GNI).

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Last year’s review focused on the impact of research activities implemented under Governance Innovation Fund (GIF), which was a flexible fund to support opportunities identified by BHC for small, rapid interventions that can catalyse larger governance change and maximise UK influence in sectors that are key to the delivery of the BHC Tanzania Country Plan. All activities under GIF were fully implemented last year and last year’s review documented the impact.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress against last year’s recommendations

Conduct an impact assessment for the beneficiaries of the PFM scholarship by July 2024: This assessment was completed.

Complete programme financial audit for REPOA and British Council accountable grant by July 2024. The audit was completed.

Recommendations for next year

Reprioritisation: BHC Tanzania should start engaging GoT on strategic PFMRP IV areas to support in future years in different budget scenarios.

A possible area to continue supporting is Local Government Revenue collection through property tax and rental income tax. With reducing ODA globally, property tax has the potential to boost Domestic Revenues to finance GoT development needs. The current policy of levying property tax on electricity bills not on property value can be improved to ensure property tax is based on the actual value of property. The International Centre for Tax (ICTD) and Local Government Revenue Initiative (LOGRI) are thinktanks working closely with FCDO Public Finance and Tax Department (PFTD) centrally managed programme (CMP) which has extensively researched and advised a number of African Countries on property tax.

## D. VALUE FOR MONEY

VfM performance compared to the original VfM proposition in the business case

As per previous year annual review recommendation, this year we conducted a full VfM assessment of SPFM. This assessment takes stock of all progress made on VfM since the programme started. Below is a summary of key findings.

Economy. The SPFM programme demonstrated a good economy in its use of resources, particularly in the Governance Innovation Fund (GIF) component. GIF was implemented with a budget of £290,000, which was used to deliver four strategic projects. The use of local consultants and pro bono support from a programme director helped reduce costs. The programme also benefited from economies of scale by leveraging existing infrastructure from the implementing partner (Palladium), which reduced overhead costs.

Efficiency. GIF component demonstrated high efficiency, with all four projects completed on time and to a high standard. The use of an experienced implementing partner (Palladium) ensured that projects were delivered efficiently. While the programme has achieved significant milestones (e.g., improved local government revenue collection, adoption of IPSAS accrual-based accounting), there have been delays in procurement and implementation of technical assistance (TA) in some areas due to the 2021 ODA budget reductions. The Alternative Delivery Arrangement (ADA) was introduced to address some of these delays, but this added complexity to the delivery chain.

Effectiveness. The SPFM programme has made significant progress in achieving its intended outcomes, particularly in strengthening public financial management (PFM) at both central and local government levels. Key achievements include:
- Improved local government revenue collection: Local Government Authorities (LGAs) saw a 105% cumulative increase in Own Source Revenue (OSR) from 2016/17 to 2022/23.
- Adoption of IPSAS accrual-based accounting: This has improved financial reporting and accountability in public sector entities. Accrual-based accounting provides a comprehensive view of government finances and accrual reporting that ensures that expenditure of public funds is transparent, public officials are held accountable, and liabilities are recognized and planned for properly.
- Improved fiscal and tax policies: The programme contributed to the establishment of the Government Electronic Payment Gateway (GePG), which increased non-tax revenue from TZS 951 billion in 2017/18 to TZS 4,366 billion in 2021/22.
- However, the programme's effectiveness has been limited by external factors, such as the reduction in Official Development Assistance (ODA) and the impact of COVID-19, which forced the programme to scale down its ambition and refocus resources.
Equity. The programme has made progress in promoting equity, particularly through local government reforms and targeted interventions (e.g., GIF). However, the equity impact of central government reforms may seem to be limited, this is due to the time taken for these reforms to affect. The programme has made efforts to ensure equity in the distribution of gains, particularly through its support for central and local government reforms. The increase in LGA revenues has enabled the government to invest in public services, such as health and education, which benefit marginalized and rural communities.

Cost effectiveness. The programme has been cost-effective in delivering key outcomes, particularly in local government reforms and revenue collection. However, the cost-effectiveness of the programme has been constrained by implementation delays and external factors.

Recommendations. Strengthen monitoring and oversight: The programme team should continue to strengthen its monitoring and oversight mechanism particularly on periodic reporting on VfM, making sure it follows a programmatic framework that includes a strategy and a set of indicators. Leverage partnerships: The programme should continue to leverage partnerships with other development partners (e.g., World Bank, IMF) to maximize impact and ensure a coordinated approach to PFM reforms.

Assessment of whether the programme continues to represent value for money

The programme continues to demonstrate good VfM. It has managed to achieve significant milestones in improving PFM systems, increasing local government revenue, and enhancing fiscal transparency and accountability.

E: RISK

Overview of risk management

FCDO Tanzania manages a diverse portfolio with varying levels of risk tolerance. The organization articulates its risk appetite through a comprehensive portfolio risk register, which is reviewed monthly by the respective teams and quarterly by the ODA Management Board. Any significant changes are escalated to the appropriate level for timely intervention.

The overall risk rating for SPFM after implementing mitigation measures, is currently classified as 'minor.' This rating is primarily influenced by the use of government systems and other contextual risks. Throughout the year, the SPFM’s risk register has been diligently updated, tracking a total of ten risks. Of these, six risks have been successfully closed. These closures were largely due to the resolution of programme delays, which were initially caused by changes in programme staff, adherence to the MoU signing schedule, and timely disbursements. Additionally, the programme team, in collaboration with the secretariat, closely monitored the delivery of PORALG activities during the local government elections. The completion of audits for the British Council and REPOA has also mitigated reputational risks.

A detailed and updated programme risk register is maintained on the UK Government’s Aid Management Platform.

Below is a summary of the key risks:
	Risk Description	Risk Category	Residual Risk
1	Delays in implementing PFMRP VI programme activities due to fiduciary risk associated with use of ODA funds for unintended purposes.	Financial & Fiduciary	Moderate
2	Failure to deliver the outstanding consultancies to the government due to delays in procurement and contracting will impact our reputation and our ability to deliver SPFM effectively for the remaining programme period.	Policy & Programme Delivery	Minor
3	SPFM programme fails to create synergies with service delivery programmes on education, health, family planning, and PSSN making these programmes not to leverage on SPFM on PFM for service delivery.	Policy & Programme Delivery	Minor
4	The government attention towards PFM reforms agenda is reduced as we approach the upcoming general elections in October/November 2025, causing delays in implementation of programme activities	Strategy & Context	Minor

This structured approach ensures that risks are continuously monitored, assessed, and managed effectively, thereby enhancing the resilience and success of the UK’s initiatives in Tanzania.

Update on Partnership Principles (delete this section if n/a) [1/2 page]
In this reporting period, we have noted any concerns on our partnership arrangements with the Government of Tanzania. We continue to engage with the Government through financial aid and technical assistance to support the reform of public financial management in Tanzania.

Tanzania has invested, with donor support, significant time and energy in improving its financial management. There have been some successes in terms of revenue-raising, but further action needs to be taken to broaden the tax base and producing more realistic and transparent budgets.

The Government of Tanzania has designed and implemented major programmes to improve public financial management over the last 25 years, including with significant UK support. There have been notable successes – strengthened policies, IT systems, standards, and process on public finance management. The supreme audit office is well regarded in the region, and there have been improvements in domestic revenue mobilization and improved financial reporting in the local government. From 2022 to 2023 there was limited funding of the Government’s PFM reforms programme but as of July 2024 UK and the World Bank reengaged in the programme. The government continues to co-fund the PFMRP VI and sustains its reforms.

Fiduciary Risk Assessment (FRA)

In this reporting period, a full FRA was conducted that provided a baseline for BHC Dar es Salam. It was also in this reporting period that Shule Bora started providing financial aid which was disbursed in the second quarter of the government financial year.  An Annual Statement of Progress will be provided in the next annual review.

The 2024 FRA on Tanzania Mainland central and local systems reported seven main fiduciary risks for the education sector in Tanzania. Specifically, the fiduciary risks are associated with: (1) Weaknesses in the financial management practices expose the education sector; (2) Procurement arrangement and practices at MOEST and LGAs; (3) Weak internal controls and internal audit systems; (4) Unsatisfactory implementation of CAG recommendations should attract consequences to management; (5) Governance issues especially on transparency and accountability; (6) inadequate financial management capability especially at facility level; and (7) Corruption risks.

The FY 2023/24 Controller and Auditor General’s report confirms the fiduciary risks, however transparency and financial reporting in Tanzania has improved significantly with an average of 99.4% of all reports receiving unqualified financial audits. The trends in implementing CAG recommendations has worsen from 41% t0 39% compared to FY 2022/23. A Methodology for Assessing Procurement Systems (MAPS) assessment was also conducted in this reporting period, highlighting progress made so far on procurement systems in Tanzania, identifying issues,  and sets a road map for reforming procurement systems and practices in the future, The National e-Procurement Systeme of Tanzania (NeST) which is developed with Open Contracting Standards sets the country in a good trajectory to increase efficiency and effectiveness in procurement practices, and transparency.

For the next reporting period, The Strengthening Public Financial Management in Tanzania (SPFM) will be the main instrument for BHC to mitigate fiduciary risks associated with financial aid to the government of Tanzania. SPFM provides BHC with a platform to discuss and shape legal framework, policies, systems, and practices of PFM in Tanzania.  SPFM will play a key role in implementing the recommendations from the FRAs for other programmes providing financial aid to the government of Tanzania which are: Shule Bora Programme, Health Systems Strengthening Programme, PSSN and BSAAT.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

This review covers the first year of the two-year programme extension. This extension allowed the programme to spend GBP 6 million of the remaining programme budget between 24/25 and 25/26. Of this amount, GBP 5.5 million has been earmarked for direct financial support to the GoT. This allocation was formalized through a Memorandum of Understanding (MoU) signed by the Tanzanian Minister of Finance and the BHC Tanzania Development Director. For the current reporting period, GBP 3 million was disbursed to the Ministry of Finance.

The remaining GBP 0.5 million of the budget is designated for technical support to the Ministry of Finance (MoF), President’s Office – Regional Administration and Local Government (PORALG), and others, based on their needs and requirements. Further support was to the Development Partners Group Secretariat to strengthen development partner co-ordination in Tanzania to increase effectiveness of development assistance in supporting Tanzania’s national development goals.

For this reporting year, a portion of this has been utilized for a Fiduciary Risk Assessment (FRA). This assessment covered both the mainland and Zanzibar regions, focusing on enhancing transparency, accountability, and mitigating financial management risks within government programs. Additionally, efforts are currently underway to secure approval for further technical support for PORALG. This support is intended to bolster the capacity of local governments to manage their financial resources more effectively and sustainably.

Moreover, two outstanding audits for REPOA and British Council were completed during this reporting year. These audits have further strengthened the programme's oversight and accountability mechanisms, ensuring that the financial resources were utilized efficiently and effectively to achieve the intended outcomes.

During this reporting period, a decision was made by the SRO and approved by the BHC Tanzania Development Director to transfer of the remaining USAID funding from the SPFM Crown Agents Bank account to Wajibika Programme account. This change will effectively be carried out in the next review period.

Overall Performance Assessment
The GoT has shown continued commitment to financial reform and governance, aligning its objectives with the strategic goals of the FCDO. The disbursement of GBP 3 million in financial aid underscores the ongoing support for priority areas identified in previous discussions. This financial aid is crucial in maintaining the momentum of reforms and ensuring that the GoT can continue to improve its public resource management.

Performance of Partnerships
The partnership between the BHC and MoF has been notably productive. Regular meetings have been held with the leads of component implementing agencies within the MoF and PORALG to discuss the progress of various projects, address challenges, and explore opportunities. Furthermore, the UK team has engaged in missions to Dodoma and Zanzibar to facilitate these discussions and ensure that the support provided is effectively addressing the needs of the GoT.

In conclusion, the collaborative efforts between the FCDO and the GoT have been instrumental in advancing financial reforms and improving governance. The financial and technical support provided has been pivotal in enhancing the capacity of the GoT to manage public resources efficiently, ultimately contributing to better service delivery for the citizens of Tanzania.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and evidence.

During the review period, the SPFM team conducted extensive monitoring activities, including visits, reviews, and stakeholder engagement. These efforts were essential in tracking programme progress, identifying challenges, and informing strategic decisions, leading to comprehensive logical frame updates.

Furthermore, the SPFM team has been working closely with the PFMRP VI Secretariat to manage the programme, ensuring that activities align with the objectives and priorities of PFMRP VI. This collaboration has involved facilitating strategic high-level discussions on key PFM issues identified during technical working group meetings, which contributes to promoting a cohesive approach to PFM reform. Additionally, the team has reviewed programme operations, including reallocation of budgets within the same vote, to ensure efficient resource use and timely implementation of activities to achieve better outcomes for the programme.

As a result, GoT appreciates the UK's technical and financial support for PFM reforms and remains committed to these reforms in both mainland Tanzania and Zanzibar. Notably there is a strong focus on increasing domestic revenue collection through strategies such as the Medium-Term Revenue Strategy (MTRS) and local government revenue mobilization.

Additionally, the Lead Adviser has played a crucial secretarial role within the DPG PFM & Tax to ensure effective coordination and alignment of objectives. This role has involved successfully developing the mapping of DPs PFM and Tax support, leading in facilitating discussions between donors and Ministry of Finance officials during the Tanzania’s Medium Term Revenue Strategy, and the strategic analysis and presentation of the CAG report.

The structured approach to monitoring activities has ensured that the SPFM programme is effectively tracked and managed. The combination of monitoring visits, regular discussions, and stakeholder engagement has provided comprehensive insights into programme progress, enabling timely and informed decision-making.

The annual progress review evaluates the programme's achievements, risks, and management, summarizing the theory of change and assessing progress towards outcomes. It includes consultations, reviews previous recommendations, and provides new ones. Risk appetite is assessed, and FRA reports are reviewed. The methodology includes a desk review of key documents and meetings with stakeholders from the Government of Tanzania, development partners, and technical assistance providers, potentially involving visits to Dodoma and Zanzibar. The Annual Review Team, comprising 10% advisory support from the FCDO Governance cadre as the lead reviewer, which was complemented by, technical support and inputs from Programme Responsible Officer, Programme Manager, an Economist, and Finance Manager. The annual review was quality assured by a Results Advisor and a Senior Programme & Compliance Manager. The SRO provided quality assurance before submission to the Development Director for review.

Besides reviewing progress, the annual review is expected to offer recommendations for future UK engagement, which is currently in the design phase. Also provides suggestions on how to improve collaboration with other PFMRP VI development partners, such as the World Bank and the EU.

Learning

These lessons can help inform future activities and improve the overall management and effectiveness of the programme:
1. Effective Monitoring and Reporting: Regular and structured monitoring activities, including direct observations and formal reporting, are crucial for tracking progress, identifying challenges early, and ensuring transparency and accountability.
2. Stakeholder Engagement and Collaboration: Continuous engagement with stakeholders, including government officials, consultants, and development partners, enhances the alignment of project activities with national priorities and leverages collective insights for improved programme effectiveness.
3. Internal Capability Utilization: Utilizing internal technical and programme management capabilities has proven essential for the successful execution of the programme. This approach ensured that the team possesses the necessary expertise and familiarity with the programme's objectives, leading to more efficient decision-making and problem-solving.
4. Significant Impact of Scholarship Programme on Government Leadership and Expertise:
   The scholarship programme has demonstrated significant value and influence based on the follow-up survey evidence. This highlights the programme's significant impact on enhancing leadership and expertise within the government.
5. Coordination mechanisms need to be strengthened: Government officials reported transaction costs in dealing with multiple development partner demands as well as limited knowledge on what different DPs are supporting under the PFMRP IV programme. The Ministry of Finance needs to take a leading role in coordinating DPs who are supporting PFM and Tax reforms with support from FCDO as the co-chair of the PFM DPG.

	Date of last narrative financial report	Date of last audited annual statement
British Council	July 2024	September 2024
REPOA	Dec 2022	November 2024