Programme Completion Review

Title: LEAVE NO ONE BEHIND AS GHANA MOVES BEYOND AID
Final Programme Spend £ (full life): £27.627 million	Review Date:	April 2025
Programme Code: [AMP ID 300385]	Start Date: March 2019	End Date: / March 2025

Summary of Programme Performance

Year	2020	2021	2022	2023	2024	PCR 2025
Programme Score	A	A	A	B	A	A
Residual Risk Exposure Rating	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case (and any addendum):	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300385/documents
DevTracker Links to all logframes used during programme lifetime:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300385/documents

A. Summary and Overview

Programme Description
The ‘Leave No One Behind’ (LNOB) programme provided £27.627m, out of the £39.2m approved in the Business Case, over six years (2019-2025) to support the Government of Ghana (GoG) to strengthen its delivery of services to the poorest and most excluded. The LNOB programme worked through existing government structures, helping to ensure the sustainability of its interventions. Ghana’s social protection system is guided by the National Social Protection Strategy (NSPS) and includes a range of programmes such as: Livelihood Empowerment Against Poverty (LEAP), a flagship cash transfer programme for extremely poor households; the National Health Insurance Scheme (NHIS) which provides access to basic healthcare services, including exemptions for vulnerable groups; the Ghana School Feeding Programme (GSFP) which offers free meals to schoolchildren to improve nutrition and school attendance; Labour-Intensive Public Works (LIPW) which provides temporary employment for the poor through infrastructure projects, and Free School Uniforms, Capitation Grants, and Education Subsidies targeted at reducing barriers to education for poor children.
The LNOB programme made a significant contribution to strengthening Ghana’s social protection system, particularly in advancing mental health and disability inclusion. Its impact was evident across five key areas: policy influence, systems strengthening, evidence-based advocacy, capacity building, and stigma reduction.

 The programme contributed to four areas of change:

1. Improved policy, leadership, resources and governance systems that promote disability inclusion and mental health for all, as well as equal recognition and respect for human rights of the extreme poor and marginalised;
2. High quality integrated health and social protection systems are accessed and experienced by the extreme poor, the most marginalised, and persons with disabilities and mental health conditions;
3. Full, active participation and representation in society, and reduced stigma, discrimination, and human rights violations for the extreme poor and persons with disabilities and mental health conditions; and
4. Improved knowledge and evidence-based understanding of exclusion and what works to improve wellbeing, social and economic outcomes and rights.

The programme was implemented through three delivery mechanisms:
1. Cash transfers delivered through the World Bank Trust Fund (WBTF) – this component supported the Government of Ghana’s (GoG’s) ‘Livelihood Empowerment Against Poverty’ (LEAP) Programme of cash transfers from March 2019, ending formally in December 2023. FCDO funding ended early in 2022. Since the end of the agreement with the World Bank, an FCDO Centrally Managed Programme (CMP) ‘Social Protection Technical Assistance Advice and Resources Facility’ (STAAR) has provided Technical Assistance (TA) to the Ministry of Gender, Children and Social Protection (MoGCSP) to further strengthen gender and shock responsive social protection.
2. Mental Health and Disability support was delivered mainly through the Ghana Somubi Dwumadie programme (January 2020 – September 2024), led by Options Consultancy with partners including BasicNeeds-Ghana, Sightsavers, King’s College London, and Tropical Health. The programme helped the government expand quality integrated mental health services—especially at the primary and community levels. It also provided sub-grants to Civil Society Organisations (CSOs) and Disabled People’s Organisations (DPOs) for advocacy, inclusion, empowerment, recovery, and anti-stigma efforts.
3. The Synergy Fund, managed by the FCDO LNOB team, provided some results-based financial aid and supported complementary activities aimed at supporting synergies between social protection and disability inclusion. It provided technical assistance (TA) to the Government of Ghana for institutional strengthening of mental health services, supported research and evidence generation, and enabled rapid crisis response. Key interventions supported through the Synergy Fund included:
  [note] Business case definition of Synergy Fund: “DFID Ghana will retain some funds (a Synergy Fund) that will provide some results-based financial aid and support complementary activities aimed at supporting synergies between social protection and disability inclusion.”

- UNICEF (Dec 2019 – 2022): Strengthening integrated social services, including case management, referral, and reintegration pathways.
- Ministry of Health/Mental Health Authority (MoH/MHA) (Jan 2020-2024): Results-based, non-budget financial aid to enhance the integration and delivery of mental health services.
- WHO (Nov 2019 – Sept 2022): Implementation of the Quality Rights initiative to improve rights-based mental health care and separately, conducting a situational analysis of maternal mental health in Ghana to inform policy.
- Social Development Direct (SDD) October 2019 to February2020: Delivery of a scoping study on Disability and Gender inclusion to inform the Ghana Productive Safety Net Programme (GPSNP) and GoG with planning activities and interventions.
- UNICEF (Volta Flooding Response) February to June 2024: Support to mitigate risks of gender-based violence (GBV) and sexual exploitation, abuse, and harassment (SEAH) during the 2024 floods.
- World Food Programme (WFP) October 2024 to March 2025: Emergency support for Ghana’s dry spell to address food insecurity among vulnerable populations.

Overall, the Synergy Fund played a critical role in enabling cross-sectoral collaboration and responsive programming, reinforcing LNOB’s commitment to inclusive development and systems strengthening.

 Table 3: Assessment of Progress against LNOB Logframe Outputs

S/N	Output Description	Delivered By	Funding	Weighting	Score
1.	Stronger policy, leadership, resources and governance systems that respect the rights of people with disabilities, including people with mental health disabilities.	GSD	£1,700,000	15%	A
2.	Effective cash transfer payments and operational modalities, productive and financial inclusive skills and training delivered to extreme poor and vulnerable and marginalised households on a transparent, accountable and sustainable basis. (this component was primarily delivered by World Bank Trust Fund; funding was closed early in 2022. / Following the close of the WBTF component, the WFP delivered a Dry Spell project – with beneficiaries accessing cash grant/transfer	WBTF, UNICEF / WFP	£13,150,000	35%	A
3.	Scaled-up quality, integrated, disability inclusive community-based and recovery-oriented mental health and social services.	GSD, MoH/MHA, WHO	£5,050,000	10%	A+
4.	Reduction in negative and discriminatory attitudes, behaviours and norms against people with disabilities, including mental health disabilities.	GSD	£1,700,000	10%	A
5.	Evidence generated to inform policy, practice and enabling environment.	GSD	£3,400,000	20%	A
6.	Increased access to quality integrated Maternal Mental Health, inclusive of community-based healthcare and Community Health Planning and Services	WHO	£300,000	5%	A
7,	A strengthened sub-national social protection system (through strengthening individual capability) that can effectively identify, respond to and prevent social protection risks and address needs	UNICEF	£2,450,000	5%	A

Overall, the programme is assessed to have scored an ‘A’ with majority of outputs scoring ‘A’, and an A+.

Despite challenges such as Ghana’s economic crisis, rising inflation, COVID-19 impacts, and ODA cuts, the LNOB programme delivered strong results. In an overall sense, it contributed significantly to the way the Government of Ghana, at both national and local levels, delivers services for the poorest and most vulnerable populations.

Key achievements included:
- Provision of cash transfers to 343,343 households (1.6 million individuals) through the Livelihood Empowerment Against Poverty (LEAP) Programme. Through LNOB funding, 1.45 million LEAP beneficiaries, including 695,036 children and 131,915 people with disabilities received emergency cash transfer in April/May 2020, during the height of the COVID 19 pandemic. Uniquely, this payment also included a transport top-up, given the increased distances for collection of payments at local banks. Additionally, the LNOB programme enabled WFP to deliver a one-off cash transfer of US$60 to 14,211 vulnerable households—benefiting approximately 71,055 individuals affected by dry spells.
- Developing an investment case for mental health with the Mental Health Authority and partners. This has been widely used by government stakeholders and civil society organisations for information and advocacy purposes and cited by the media. Critical actions identified by the investment case, such as the establishment of the Review Tribunal, have been adopted, and mental health has been included under the National Health Insurance Scheme (NHIS) from 1 November 2024.
- Implementation of the Mental Health Act 846 through the launch of the Mental Health Policy and the establishment of the Mental Health Tribunal, along with the formation of Visiting Committees and other essential mental health structures.
- Integration of mental health considerations into the District Assembly Common Fund allocations for persons with disabilities.
- Development and deployment of Integrated Social Services (ISS) and the Social Welfare Information Management System (SWIMS) in 2022 to enhance access to social welfare services to the vulnerable. This system is currently operational in 170 districts (out of a total of 261) across all 16 regions in Ghana and was used in 2024 by the Department of Social Welfare to support victims of flooding in the Volta Region. The ISS has now been incorporated into the District Medium-Term Development Plans (DMTDPs) of Municipal, Metropolitan, and District Assemblies (MMDAs).
- An assessment of Ghana’s Social Protection Shock Response (SRSP) system laid the foundation for the development of a national SPSR Strategy by the MoGCSP. This is aimed at strengthening the resilience and responsiveness of social protection systems during crises.
- A range of research and implementation studies on disability, mental health and social protection - such as the District Mental Healthcare Plan Framework, District Assembly Common Fund (DACF) Disability Fund Guidelines, and the Mental Health Investment Case — proved instrumental in influencing policy and practice.
- Building the capacity of civil society organisations to advocate on critical national issues - particularly the campaign against witchcraft accusations - catalysed the formation of a committed coalition, which significantly contributed to the drafting and passage of the Anti-Witchcraft Accusation Bill (a private member’s Bill) by Parliament.
- Successfully supporting the GoG in transitioning to the electronic disbursement of LEAP funds, marking a pivotal shift from manual cash transfers. This digital transformation enhanced the efficiency, transparency, and timeliness of payments, reduced the risk of fund leakages, and improved the overall experience for beneficiaries. For the government, this shift not only streamlined administrative processes but also strengthened accountability and data management within the social protection system.

This PCR notes two opportunities which could be explored further in future advocacy and programming. The first is support for passage of the Disability Amendment Bill. The programme carried out several preparatory activities through the GSD component. These efforts included providing technical support to the Ghana Federation of the Disabled, which successfully advocated for the establishment of the National Council for Persons with Disabilities Board in November 2021. The programme also supported advocacy for the formation of a committee to advance the passage of the Disability Bill and the creation of a Disability Caucus in Parliament to review the draft Bill. Although the Bill was not passed before the programme concluded, its efforts have contributed to tangible progress. Encouragingly, the current government is in the process of finalising the amended Bill for submission to Parliament. FCDO will continue to monitor the progress of the bill towards its ultimate passage and implementation. Secondly, availability of psychotropic medicines in frontline health facilities remains a challenge. While the Mental Health Authority (MHA) secured a commitment from the Ministry of Health (MoH) to include mental health under the National Health Insurance Scheme (NHIS) and also include psychotropic drugs under framework contracting to procure them for psychiatric hospitals and regional medical stores, this did not lead to faster procurement or a more reliable supply. Some health facilities continued to face stockouts, as they relied on a mix of centrally and locally procured psychotropic medicines. These supply chain inefficiencies remain a significant barrier to consistent mental health service delivery. Resolving these supply chain issues will not only impact positively on mental health service delivery but also impact positively on the supply of other essential medicines within the Ministry of Health.
# Challenges, Mitigation Measures, and Lessons Learned
The LNOB programme faced some contextual and operational challenges:
COVID-19 Pandemic: The global COVID-19 pandemic in early 2020 caused significant disruptions to the programme. Implementation of workstreams was delayed, and original workplans had to be pivoted to respond to the pandemic. Staff recruitment and face-to-face stakeholder engagements were particularly affected, requiring a shift to remote modalities.

Political Transitions: Ghana's national election in 2020 resulted in a hung parliament and the dissolution of governing boards of public agencies. This slowed down engagement with government interlocutors and advocacy activities, as new officials had to be briefed and brought up to speed. This was further impacted by the protracted absence of the Minister for Gender, Children and Social Protection and delays in inaugurating the MHA Board. This created a significant vacuum in political and policy leadership.

LEAP Cash Transfer Delays: Internal system challenges within the Government of Ghana led to delays, of sometimes up to six months, in LEAP cash transfers. Additionally, the collapse of three Public Financial Institutions made it difficult for beneficiaries to access their funds. Furthermore, while Government subsequently announced significant increases to LEAP and School Feeding, price inflation eroded the real value of payments.

ODA Budget Cuts: Year-on-year reduction in Official Development Assistance (ODA) budget totalling about 30% of the originally approved budget, led to the cessation of some programme components and significant scaling-down of activities. This period coincided with economic uncertainties, including rapidly rising inflation, complicating longer-term financial planning.

Shifting FCDO Priorities: The introduction of the FCDO’s Women and Girls strategy prompted a strategic shift in LNOB, requiring the programme team to redesign activities. As a result, some planned interventions were delayed or adapted to better reflect the evolving strategic direction, particularly in areas related to gender equality and social inclusion in a more explicit way than in the original business case. Despite these adjustments, the programme maintained its core objectives and continued to deliver impactful results.

Stakeholder Priorities: The shift in approach - from direct service delivery and funding to a model focused on Technical Assistance (TA) provided by an independent supplier - required a period of adjustment for stakeholders who had previously prioritised tangible service delivery outcomes. Additionally, the supplier encountered challenges in fostering collaboration among programme partners, including multilateral organisations and government agencies, due in part to complex institutional dynamics and differing operational priorities

Inter-Ministerial Collaboration: Fostering effective cross-sectoral collaboration among Government of Ghana Ministries, Departments and Agencies (MDAs) presented some challenges. While mandates for social protection, mental health, disability and gender were clearly defined, overlapping responsibilities and differing institutional priorities occasionally made coordination complex and created some examples of delays, inefficiencies and limited results.

Mitigation Measures
The LNOB programme sought to limit the impact of internal and external challenges:
1. Adaptive Programming: Activities were refocused and reprogrammed to align with evolving contexts and FCDO priorities. Proactive financial scenario planning was used to minimise the impact of budget cuts. LNOB shifted significantly away from service delivery to systemic reforms in social protection and governance, to support GoG towards self-reliance and sustainability.
2. Remote Delivery: To mitigate the risks of COVID-19, the programme worked with partners to operationalise emergency cash transfers via mobile money. This ensured that new categories of vulnerable and excluded groups outside the programme were reached.
3. Responsible Exit and Strategic TA Delivery: FCDO’s exit from the World Bank Trust Fund (WBTF), though not initially planned, was executed responsibly to ensure service continuity. Through sustained engagement with the World Bank key programme components were able to continue without disruption. Further support was secured through a centrally managed UK TA programme to complement activities. This support strengthened national systems in alignment with the business case objectives, demonstrating FCDO’s commitment to sustainable impact and institutional resilience beyond direct funding.
4. Stakeholder Engagement: Regular updates and coordination with FCDO and implementing partners ensured alignment and buy-in. This was achieved through regular and ad hoc meetings, formal documentation, and official communications along with contract addendums.
5. Political Economy Analysis (PEA): Early-stage PEA provided valuable insights and supported LNOB’s capacity to understand power and institutional dynamics and to manage stakeholder expectations regarding the shift from direct service delivery to TA. The collective response to the COVID-19 crisis also provided opportunities for collaboration and joint-working within the sector.
6. Flexible and Agile Programming: The programme’s ability to pivot in response to COVID-19, political transitions, and shifting donor priorities was key to maintaining relevance and effectiveness. It used a range of delivery modalities – Trust Fund, UN Agency Partnerships, CMP partnerships, Commercial Contract and tools such as mobile money for emergency cash transfers. These were further complemented by the use of our internal technical expertise as well as our diplomatic and political influence. While this increased programme complexity, it demonstrated the importance of agile programming especially in crisis contexts.

Recommendations:
The following recommendations are intended to be forward looking and support the development of future business cases or other approaches to achieve related goals:

1. Given the rapid pivots required by LNOB, FCDO should clearly define what "flexible and adaptive programming" means in practice - especially under constrained funding like the 0.3% ODA context. Clear guidance would help partners respond quickly and consistently to emerging challenges while staying aligned with strategic goals
2. LNOB had a ‘laser focus’ within its reporting on the activities undertaken within agreed timelines; it would instead have been more useful to rebalance reporting towards impact and sustainability rather than inputs. FCDO may wish to strike a balance between the number of payment deliverables and the capacity of implementers to report on them in a timely way where payment by results model is applied, as this method of payment in particular drove the focus on short term results.
3. FCDO may consider using its levers to achieve greater political influencing and secure continued government buy-in and community ownership of programme interventions.
4. Embedded TA within government ministries proved useful in maintaining positive working relationships and influencing change for the GSD mental health component. FCDO could consider this approach where practical or applicable to drive and sustain system change particularly within GoG.
5. Successful pilots - such as the mental health review tribunal, regional MHVCs, and district mental healthcare plans - provided scalable models for strengthening mental health governance. In a constrained 0.3% ODA environment, FCDO can maximise impact by investing in light-touch, time-bound Technical Assistance (TA) over the next two years. This TA should focus on advocating for broader recognition of mental health conditions under the NHIS, addressing persistent psychotropic drug supply chain issues, and supporting anti-stigma efforts for persons with disabilities. Leveraging existing partnerships and systems, this approach balances sustainability with strategic exit planning, ensuring continued progress with limited resources.

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£39.2 million	£ 27.627 million (70% of Business Case budget)
Timeframe	March 2019 – March 2024	March 2019 – March 2025
Outcome	Extreme poor and marginalised, including women and men with disabilities and mental health conditions are increasingly able to exercise their rights and use high quality and integrated health and social protection systems, and participate in income generation activities	Extreme poor and marginalised, including women and men with disabilities and mental health conditions are increasingly able to exercise their rights and use high quality and integrated health and social protection systems, and participate in income generation activities

Overall assessment of programme outcomes, sustainability and VfM
The LNOB programme achieved multiple successes across outcome indicators, and most were met.

Outcome Indicator 1: % of LEAP beneficiaries who are identified as extremely poor according to targeting criteria (results disaggregated by gender and disability status).

LEAP cash transfers were assessed as having 'moderately met expectations,' largely due to internal financial system challenges within the Government of Ghana, compounded by the lingering effects of COVID-19 and the demands of parallel emergency cash transfer programmes. These factors led to delays in disbursement. However, despite these operational hurdles, the LEAP programme successfully reached 343,434 households (98% of target) and 1,641,321 individuals—exceeding its planned target by 10%. The World Bank’s Social Protection Public Expenditure Review (SP PER, Report Number: 181666) finds that 77 percent of LEAP programme beneficiaries were extremely poor (the poverty status of the rest could not be determined due to data discrepancies between the Ghana National Household Registry (GNHR) and LEAP), while 58.6% of beneficiaries were female and 17% had a disability. UNICEF Social Protection Budget Brief 2024 noted that LEAP has been successful at reducing poverty rates. It reduced multidimensional poverty rates among pre-school and school-aged children in beneficiary households by 10.5% and 1.3% respectively.

Outcome Indicator 2: Level of Government resource allocation and expenditure on mental health delivery and LEAP.

According to the World Bank, the Government of Ghana provided counterpart funding of US$140 million (as against overall US$83 million partner funding) towards the LEAP cash transfers program. In 2022 GoG allocation to Mental Health Authority was GHS 2.2m. This figure increased to GHs 4.1m in 2023 while budget allocation to LEAP was GHS 198m and saw an increase to GHS 395m in 2023. In 2024, allocation to LEAP increased to GHS 720m, an increase of 82%. These increases were facilitated by the Government’s political will towards social protection and represent a better-than-expected outcome for the programme. While these budgetary increases are a positive development, they still represent a relatively small share of the Government of Ghana’s total expenditure—amounting to just 0.23%of GDP in 2024. Although the LEAP and other social protection grant values were significantly increased from 2019 to 2024 to account for price inflation, actual LEAP payments have continued to suffer from irregular releases. Against a payment cycle of 8-9 weeks between payments, there have been up to 19-week gaps between cycles. These delays eroded the real value of the cash received by beneficiaries.

Outcome Indicator 3: % of people with mental health conditions with active NHIS membership (results disaggregated by gender and disability status).

The programme has raised awareness and commitment among government agencies, leading to improved institutional attitudes and increased investment in disability and mental health, including the inclusion of mental health services in the National Health Insurance Scheme. In 2022, 423,468 people with mental health conditions held active NHIS cards (M: 188,216 / F: 235,152). By 2023, this number rose by 116,740 (M: 51,469 / F: 65,271), reaching 540,208—an increase of 21.6%, exceeding the 20% target. While this represents significant progress, further validation is needed to accurately determine the total number of individuals with mental health conditions, in order to assess NHIS coverage as a proportion of the affected population.
Outcome Indicator 4: Extent of public awareness and sensitivity to mental health and disability in Ghana.

The results under this outcome were mixed. While deliberate efforts were made to enhance public awareness and sensitivity toward mental health and disability, overall public attitudes remained largely unchanged. A 2023 WHO-supported study found that attitudes toward people with mental health conditions in Ghana often fall short of human rights standards. Many respondents—including community members and some professionals—still supported coercive practices and believed that treatment decisions should be made by health workers or family members, rather than the individuals themselves. This highlights persistent stigma and a lack of understanding of mental health as a rights-based issue. The study found that people with personal experience of mental health conditions and services were often supportive of the use of seclusion, restraint, control, and involuntary treatments compared to other groups. This could be due to self-stigma, and the internalisation of the stigmatising attitudes and beliefs of people close to them as well as reflecting wider prevailing community attitudes.

Evidence generated through GSD grantees on the gender dynamics of witchcraft accusations contributed significantly to heightened calls for anti-witchcraft legislation and to halt discriminatory behaviour, which subsequently led to the passage of the Anti-Witchcraft Bill. Though the Bill failed to receive presidential assent before the change of government, it is hoped that stakeholders have inherent capacity to take it through Parliament again and secure the required Presidential approval. The work of GSD grantees also indicated (based on the Grants Evaluation) that persons with disability have experienced improved access to healthcare services, greater access to justice and enforcement of rights, are more likely to experience positive disability terminology, and report experiencing a reduction in stigma and discrimination in their communities.

Outcome Indicator 5: Number of GoG initiatives which consider mental health and disability in COVID-19 preparedness and response

During the peak of the COVID-19 pandemic, the LNOB programme supported the Government of Ghana in providing personal protective equipment (PPE) to staff across various health facilities as part of broader containment efforts. Although the support did not specifically target mental health or disability-related needs, it was anticipated that these measures contributed to reducing the overall impact of the pandemic on individuals with mental health conditions and disabilities. To strengthen staff capacity to consider mental health and disability inclusion in all their activities, 30 senior officials and 151 MMDAs integrated disability-inclusive actions into their annual plans. Through collaboration with the NDPC, MMDAs have also embedded Integrated Social Services (ISS) into their development plans, improving access to quality services for vulnerable children and enhancing data reporting practices.

Theory of Change

The LNOB programme aimed to contribute to improved services for the poorest and most excluded through support to the GoG. The theory of change (ToC) assumes that high-quality TA and financial aid (FA) if provided at the right time, with adequate buy-in, political will, and GoG ownership, would enable the Government to prioritise investment in services targeting Ghana’s extreme poor and most vulnerable. While the outcome and impact indicators have not changed during LNOB implementation, FCDO budget cuts and reprioritisation, and inadequate GoG budget allocation to the social sectors have resulted in adjustments to indicator targets over time to align realistically with the evolving context.

As a result of pivoting to respond to the COVID-19 pandemic in 2020, revisions were also made to the LNOB logframe and ToC. Revisions related to:
1. Conducting a Vulnerability and Exclusion (V&E) assessment to support the GoG’s V&E Strategy
2. New COVID-19 support through UNICEF and Options
3. Investment in LEAP emergency cash transfers. The most significant change was to the WBTF. This was to reallocate funds from Productive Financial Inclusion (PFI - £5m) and Ghana National Household Registry (GNHR £2.5m - half of the original allocation) towards emergency cash transfers. This allowed the temporary expansion of LEAP. However, in 2022 further ODA cuts and reprioritisation resulted in the early closure of the WBTF/Social Protection component of the programme. Nonetheless, LNOB remained active within social protection, focusing more on system strengthening and capacity building and using other levers for policy influencing.

Further revisions were made to the LNOB logframe and ToC in 2021 to reflect changes made to the LNOB programme as a result of ODA cuts and the need to adapt to contextual changes.

In 2022, as part of an overall programme review, FCDO convened LNOB implementing partners (IPs) to review the ToC and logframe. This assessment was critical, given the implications of ODA cuts to the programme and pauses which had delayed activities. In addition to that was the release of FCDO’s Women and Girls Strategy and associated budget ‘handrails’. The ToC was therefore stress-tested to examine whether existing assumptions remained valid. IPs concluded that they were confident that the ToC continued to reflect their best understanding of the causal pathways associated with the context and implementation activities. Despite these changes, the ToC remained valid throughout programme implementation.

This PCR could not directly measure the impact indicator – “percentage of people living below the poverty line” due to the absence of Ghana Living Standards Survey Round 8 (GLSS 8). While we await results from the GLSS 8, data from the 2024 Multidimensional Poverty Report released by GSS cluster indicates a total of 7.3 million persons, representing 24.3 % of household population were multidimensionally poor. Among these poor persons, 43.8 % experienced severe poverty through deprivations in several dimensions simultaneously. Compared to previous years (2011–2018) this indicates a decline in both the incidence and severity of multidimensional poverty across the country, with notable improvements in access to electricity, cooking fuel, and school attainment. For a more precise comparison, the upcoming results from GLSS 8 will be crucial, as they will offer updated insights into trends and regional disparities in poverty levels
[note] https://statsghana.gov.gh/gssmain/fileUpload/pressrelease/Multidimensional%20Poverty%20Ghana_Report.pdf

The following adjustments were made following the inclusion of the new Maternal Mental Health (MMH) component and a growing focus on increased social sectors financing, especially post-COVID:
A new impact indicator was added - “Percentage of Government’s expenditure on Social Protection as a percentage of GDP”.
As a percentage of gross domestic product (GDP), MOGCSP’s budget for 2024 is equivalent to 0.23% of GDP. This is an increase on the 0.17% of GDP allocated in 2023, and higher than in any year from 2019. Estimated total financing for social protection, which includes both contributory and non-contributory programmes in line with International Labour Organization (ILO) definitions, increased from 1.37% of GDP in 2023 to 1.67% of GDP in 2024. This is driven by the increase in LEAP and the NHIS The Ministry of Gender, Children, and Social Protection’s (MOGCSP) budget increased from GHS 1,487 million in 2023 to GHS 2,393 million in 2024. This was a 60.98% increase in nominal terms (i.e. at current market prices). Accounting for price inflation, the MOGCSP budget increased by 39.97% in real terms between 2023 and 2024.
A new assumption “There is sufficient research capacity and technical knowledge to conduct operational research and generate high quality evidence to inform government policies. Evidence generated by the Programme is relevant and addresses current needs of the most vulnerable”, was introduced due to the inclusion of the new MMH component.

Sustainability:
While some interventions have ceased with programme closure, and others remain visible in part, some LNOB interventions have been transformational and have introduced significant changes in GoG’s disability and mental health programming, stakeholder ways of working, and the attitudes and beliefs of Ghanaian citizens. Notable among these transformative outcomes are:

1. Formalisation of key structures and systems within government and traditional institutions – A Parliamentary Caucus on Disability remains within government structures and will continue to work with MoGCSP on the roadmap that will action GoG commitments made at the Global Disability Summit. Mental Health Review Tribunals activated by MHA in three regions provide learning sites for effective practices and will support the roll-out of the template for Tribunals in other Ghanaian regions. LNOB grantees supported the Anti-Witchcraft Bill in 2023. While it did not receive Presidential approval before the change of government, the broad range of stakeholders mobilised around the bill are prepared to take it through the parliamentary process again and get it enacted. Similarly, LNOB has supported the development of new sanction mechanisms and by-laws in communities and districts to address stigma and discrimination against people with disabilities and mental health conditions which have remained after the programme. These are expected to be scaled to other regions by the MHA. However, with the reduction of external financing from donors, it is unclear whether the GoG will be independently able to support the MHA and mental health interventions across the country. The PBA programme will fund until March 2026 and the programme will work with the MHA to ensure that interventions are sustainable. The PBA programme report will update progress in its annual report.
2. Organisational strengthening of CSOs, OPDs, women’s rights organisations (WROs), and self-help groups (SHGs) through targeted capacity-building initiatives across multiple thematic areas, aimed at enhancing their ability to apply best-practice, rights-based approaches in supporting persons with mental health conditions, while fostering a user-led approach to engaging duty-bearers.
3. These organisations can now be considered thought-leaders and role-models in this space and can sustain advocacy efforts. Training on improved monitoring, evaluation and learning (MEL) skills, donor reporting skills, and annual work planning enables key stakeholders to develop the confidence to apply for and receive future funding for their activities. At the community level, members of SHGs were supported to articulate funding/intervention priorities and have cultivated a sense of ownership and commitment for continuing engagement with district officials. A sustainable success story is LNOB’s facilitation of relationship building between SHGs and various officials of MMDAs, the NHIS, Department of Social Welfare and Community Development, and the Social Services subcommittee.
4. Attitudinal change in communities towards persons with disabilities and mental health conditions – LNOB has influenced behaviour change through sensitisation, training, incentivisation and persuasion. The programme has utilised the media and Social Behaviour Change (SBC) materials, including posters, jingles and language guides and helped community members to understand and appreciate people with disabilities, including mental health conditions. As a result, the programme registered a change in attitude and behaviour towards people with disabilities in pilot districts. While the results are currently limited to the pilot districts, the lessons learned from these interventions have the potential to inform and influence practices across the country. An interview conducted by Ghana News Agency with influencers at community level attested to changes in attitudes across multiple project communities. During this evaluation, stakeholders also confirmed positive changes, including reductions in name calling of people with disabilities or mental health conditions. This was as a result of the Positive Disability Terminology Guide that was established as a reference document. LNOB grantees, including VOICE Ghana, have helped to reinforce the commitments of relevant agencies and traditional leaders to address human rights abuses against people with disabilities. As a result, several communities have put in place sanctions mechanisms to address human rights abuses. There are indications that traditional and religious leaders will continue to project positive portrayals of people with disabilities or mental health conditions and to support them to take leadership roles in their respective communities.
5. Institutionalisation of Shock Response in Social Protection (SRSP) – With LNOB funding, UNICEF conducted a thorough assessment of Ghana’s SRSP system where the recommendations were widely disseminated. This assessment informed UNICEF’s approach to responding to the humanitarian crisis caused by flooding in the Volta Region in 2024. Similarly, the resulting recommendations have informed the development of a draft national shock response strategy by the MoGCSP. The SRSP strategy is aimed at strengthening the social protection system to function effectively during crises and support resilience across the lifecycle. This is especially timely given the growing impact of climate change, Ghana’s limited fiscal space, rising poverty risks, and potential spillover effects from the Sahel, which place additional strain on national resources.
6. Social Welfare Case Management & Referral Model - through LNOB, UNICEF implemented the Inter-sectoral Standard Operating Procedures (SOPs) for Child Protection and Family Welfare and the Case Management SOPs for Children in Need of Care and Protection in 160 out of the 261 districts (61% national coverage as of 2022), under the Integrated Social Services (ISS) initiative. Through ISS, an online digital case management system administered by MoGCSP to facilitate child protection and family welfare case management have become operational in 160 districts out of the 261 districts. Known as the Social Welfare Information Management System (SWIMS), it is implemented using Primero, an open-source software developed by UNICEF and adapted by the Government of Ghana to suit the local context and needs.

Value for Money:

The £27.627 million LNOB programme delivered strong value for money by achieving wide-reaching and sustainable outcomes for Ghana’s most marginalised groups, particularly persons with disabilities and mental health conditions. Despite facing significant challenges - including COVID-19, economic instability, and budget cuts - the programme reached over 1.6 million vulnerable people through LEAP cash transfers, supported emergency responses, and influenced major policy reforms such as the inclusion of mental health under the National Health Insurance Scheme and revisions to DACF guidelines. Its flexible, user-led approach enabled it to remain relevant and impactful in a shifting context.
LNOB also strengthened national systems and built the capacity of civil society and government institutions to sustain progress beyond the programme’s lifespan. Key investments in tools like the Social Welfare Information Management System (SWIMS), district mental health care plans, and inclusive policy frameworks have enhanced service delivery and accountability. The programme’s ability to adapt, deliver results, and catalyse systemic change confirms that the investment was not only justified but strategically transformative.
Although not a formal VFM assessment, it is instructive to consider that in 2025, Ghana is projected to spend around $1 billion annually on its National Health Insurance Scheme. As part of LNOB’s spend of £5-6million a year, it profoundly changed how Ghana’s health system views and deals with disability and mental health, including securing the inclusion of mental health within the NHIS system.

## C: Detailed Output Assessment

Output 1	Improved policy, leadership, resources and governance systems that recognise and respect the human rights of the extreme poor and marginalised, including all people with disabilities and mental health conditions
Output Score	A
Impact weighting (%)	15%	Impact weighting revised since last AR?	Yes

Output Indicator	Starting logframe target	Revised logframe target	Final logframe result	Final PCR Score
Indicator 1.1. / Extent to which intersectoral monitoring and accountability mechanisms strengthen GoG systems delivering mental health services and disability inclusion	Establishment of working group on Mental Health Review Tribunal (MHRT) / Inauguration of Mental Health Review Tribunal	This indicator was revised in Sept 2024 to support the scale-up of MHRT operations, incorporating lessons learned from pilot implementations / Document learning from Mental Health Review Tribunal including recommendations for scale up.	Lessons for Mental Health Review Tribunal (MHRT) documented resulting in development of a MHTR Manual	Outputs met expectation (A)
Original Indicator 1.2 / % of LEAP beneficiaries selected using Ghana National Household Registry (GNHR) data.	90% LEAP beneficiaries selected using GNHR data	Indicator Closed Sept 2022	78.5% LEAP beneficiaries selected using GNHR data	Output moderately did not meet expectation (B)
Indicator 1.3 / Level of implementation of Government's Vulnerability and Exclusion (V&E) Strategy	V&E assessment completed, and report validated, and recommendations inform MOGCSP's action plan	(Referenced as indicator 1.2 in logframe from Jan 2022)	Data collection for the V&E Assessment was carried out, analysis completed, and a dissemination workshop held.	Outputs met expectation (A)
Indicator 1.4 / Level of Technical Assistance to MoGCSP to strengthen social protection system and implement, map and coordinate COVID-19 activities and advocate for increased resources to contribute to the sustainability of the social protection sector.	a) 322,000 LEAP beneficiary households benefit from modified implementation and operations. / b) In COVID-19 response, front line workers are equipped to safely deliver critical child protection human rights, judicial and SGBV services to vulnerable groups. / c) analytical support provided to Social Protection Directorate on key Social Protection budget and financing issues. / d) CSO post payment monitoring to 32 LEAP communities in the wake of C19 to ensure transparency and accountability has commenced.	(Targets updated once all original milestones achieved). / Referenced as indicator 1.3 in logframe from Jan 2022) / a) Technical assistance provided to the provision of COVID-19 Relief Transfers to at least 120,000 vulnerable individuals. / b) Shock Responsive social protection assessment commissioned.	a) Technical assistance provided to 107,574 beneficiaries. / b) Shock Responsive social protection assessment complete.	Outputs met expectation (A)
Indicator 1.5 / Extent to which the Legislative Instrument (LI) of the Mental Health Act (846) and national mental health policy established and guide implementation of mental health services	Disability Amendment Bill LI is passed by Parliament and stakeholder dissemination commenced.	Indicator targets revised in Dec 2023 due to changing programme priorities. / (a) Review MHA 2019-2022 Strategic Plan and develop Strategic Plan for 2023 - 2026. / (b) Launch and dissemination of Mental Health terminologies in Akan booklet. / (c) Launch and dissemination of research agenda report. / (d) Availability of research report	a) MHA strategic plan completed / b) Mental health booklet in Akan disseminated / (c) Research agenda report launched and disseminated / (d) Report available	Outputs met expectation (A)

Overall output 1 scored A, reflecting a period of sustained high performance and delivery on all the planned activities, with all but one indicator scoring A. This output was scored A in all but one Annual Review.
The key deliverables from output 1 include establishment of Mental Health Review Tribunal (MHRT) and launch and dissemination of mental health research reports. The work on mental health policy and application was largely achieved despite contextual challenges from changes in Government leadership and a pause on work with the MHA.

Output 1.1 originally proposed the establishment of a working group on the Mental Health Review Tribunal (MHRT). However, during the programme, this indicator was revised with the view to supporting the scale-up of MHRT operations, through incorporating lessons learned from pilot implementations. Targets relating to this indicator were consistently achieved throughout the programme. LNOB provided technical assistance (TA) to the Mental Health Authority (MHA) to establish and operationalise the Mental Health Review Tribunal and Mental Health Visiting Committees (MHVCs), in line with the Mental Health Act (2012). These accountability mechanisms were piloted in five districts, marking the first time such human rights structures were implemented in Ghana.

Output 1.2 was originally intended to measure the percentage of LEAP beneficiaries selected using data from the Ghana National Household Registry (GNHR). However, funding to GNHR closed earlier than planned as part of the pivot to respond to COVID-19. Funds originally planned for GNHR were reallocated towards emergency cash transfers for the temporary expansion of LEAP. Despite this, the indicator achieved 78.5% of beneficiaries selected through GNHR data, against a target of 90%.

Output 1.3 aimed to conduct a comprehensive vulnerability and exclusion assessment, with the resulting recommendations intended to inform the MoGCSP’s action plan. The assessment was successfully completed, followed by a dissemination workshop. The final report has been validated and published. In addition, a programmatic response document - translating the assessment’s recommendations into actionable strategies - has been developed and formally approved by the MoGCSP.

Output 1.4 aimed to reach 322,000 LEAP beneficiary households through modified implementation and operations. It also sought to support frontline workers in the safe delivery of critical child protection, human rights, judicial, and SGBV services to vulnerable groups, alongside monitoring 32 LEAP communities in the wake of COVID-19 to ensure transparency and accountability. Following the successful delivery of these activities, the indicator was revised to focus on providing technical assistance for the COVID-19 Relief Transfers to at least 120,000 vulnerable individuals, and the development of a Shock Responsive Social Protection (SRSP) assessment report. The shock response assessment was successfully completed, and technical assistance was provided to 90% of the targeted beneficiaries.

Output 1.5 was designed to support the successful passage of the Disability Amendment Bill Legislative Instrument (LI) through Parliament. However, due to changes in funding and the evolving scope of the programme, the target was revised. The revised focus included: Reviewing the Mental Health Authority (MHA) 2019–2022 Strategic Plan and developing the 2023–2026 Strategic Plan; Launching and disseminating a booklet on Mental Health Terminologies in Akan; and launching and disseminating the Mental Health Research Agenda Report. All revised outputs were successfully delivered. The primary objective of the research publication was to establish a national mental health research agenda, build research capacity, and mobilize funding. This is expected to contribute significantly to improved evidence-based planning and decision-making in the mental health sector

Despite progress made under this output, transformational change may not be immediately realised. The Government continues to face significant challenges in sustainably resourcing and scaling inclusive social protection systems. These challenges stem from limited fiscal space, fragmentation of programmes across silos and multiple ministries, weak institutional capacity, and inadequate data systems. To help mitigate these constraints, one recommended measure is to establish an inter-ministerial coordination mechanism. This would facilitate better alignment of social protection initiatives, reduce duplication, and promote more efficient use of available resources.

Output 2	Effective cash transfers payments and operational modalities are delivered to extreme poor and vulnerable and marginalised households on a transparent, accountable and sustainable basis
Output Score	A
Impact weighting (%)	35%		Impact weighting revised since last AR?	Yes

Output Indicator		Starting logframe target	Revised logframe target	Final logframe result	Final PCR Score
Indicator 2.1 / Number of beneficiaries accessing timely LEAP cash grant (results disaggregated by gender and disability status).		350,000 LEAP beneficiary HH (1,505,000) individuals receiving timely cash payments	Indicator closed / December 2022	343,434 households reached (1,641,321) individuals. / Payments were not regular or timely.	Outputs met expectation (A)
Indicator 2.2 / Level of implementation of the Social Welfare Case Management and referral and reintegration system in 50 districts in Ghana including number and percentage of LEAP beneficiaries with active NHIS membership		80% of LEAP individuals with active NHIS.	Indicator closed March 2023	78.5% of LEAP beneficiaries with active NHIS	Outputs met expectation (A)
Indicator 2.3 / Level of implementation of the Shock Responsive Social Protection Emergency Early Warning System		Initial emergency processes, data collection/sharing protocols, and gaps identified, to provide skeleton for shock-responsive SP roadmap	Indicator closed December 2022	Data has been collected, assessment done and report submitted to the GoG to guide development of SRSP strategy.	Outputs met expectation / (A)
Indicator 2.4 / Dry Spell project – number of beneficiaries accessing timely cash grant/ transfer (results disaggregated by gender and disability status)		Indicator added March 2023	8,500 most vulnerable farmers receiving timely cash payment / (Female-headed 43.1%: Male 56.9%).	8,500 farmers received timely cash payment. / (Female-headed 56.6%; Male 44.4%)	Output met expectation / (A)
[note] LEAP recorded 100 percent on-time payments in 2019; 49 percent in 2020; and 83.3 percent in the year 2021. Analysis of the MOGCSP’s Program Based Budgeting for various years shows that timely LEAP payments correspond to the timely release of funds by MOF. In 2020, when 49 percent of LEAP payments were on time, 61 percent of the allocated budget had been released, and in 2019, when timeliness was 100 percent, execution was 99 percent. There were no on-time LEAP payments in 2022, reflecting the deep macroeconomic crisis due to large fiscal deficits and external financing needs, significant energy and financial sector costs, which affected budget releases to most MDAs. (World Bank 2022)

Overall output 2 achieved a final score of A. This reflects continuous high performance throughout the period. The key deliverables from output 2 include reaching 350,000 LEAP beneficiary households with cash transfers. Although the cash transfer component of this output was closed earlier than expected due to budgetary considerations, FCDO undertook a series of engagements with the World Bank to ensure that the early closure of the WBTF component was conducted responsibly, and TA support continued even after close of the indicators.

Output 2.1 intended to reach 350,000 LEAP beneficiary households - equivalent to approximately 1,505,000 individuals - with timely cash payments. By the end of the reporting period, 343,434 households (98% of the target) were reached, and 1,641,321 individuals (110% of the target) benefited. While the coverage target was largely achieved, the regularity and timeliness of payments remained a significant challenge. The COVID-19 pandemic and the resulting fiscal pressures severely constrained the government’s ability to fund social sector programmes, including LEAP. This led to disruptions in the disbursement of earmarked funds, compounded by persistent delays, uncertainty around payment schedules, and limited communication with beneficiaries. These issues were further exacerbated by a prolonged leadership vacuum at the Ministry of Gender, Children and Social Protection (MoGCSP), which hindered strategic and policy direction during a critical period. Additionally, communication between MoGCSP, the Ministry of Finance, and the Controller and Accountant General’s Department was often reactive and limited to payment periods, weakening coordination and disrupting the feedback loop between the LEAP Secretariat and its beneficiaries. As average inflation went up to 20% per annum between 2019 and 2024, delays in transfers significantly eroded the real value of monthly cash payments, substantially reducing beneficiaries’ purchasing power. One key lesson is the need for stronger inter-agency collaboration and proactive communication to ensure more predictable and transparent delivery of social protection services.

Output 2.2 aimed to ensure that 80% of LEAP beneficiaries were enrolled with active National Health Insurance Scheme (NHIS) coverage. However, this indicator was closed in March 2023 due to changes in programme priorities. Prior to its closure, 78.5% of LEAP beneficiaries were reported to have active NHIS subscriptions. The National Health Insurance Authority (NHIA) could not independently verify this figure, as the NHIS Management Information System (MIS) categorises LEAP beneficiaries under the broader "indigent" group. This group also includes other vulnerable populations, such as individuals with mental health conditions and those referred by the Department of Social Welfare. However, the team believes the figure of 78.5% to be a sufficiently credible basis for the scoring. A key lesson from this experience is the critical need for a robust and interoperable data system across all social protection agencies to improve targeting, verification, and service delivery.

Output 2.3 focused on developing a shock-responsive social protection (SRSP) assessment as a foundational step toward formulating a comprehensive SRSP strategy for the Government of Ghana. This output involved identifying initial emergency response processes, data collection and sharing protocols, and existing gaps within the system. These elements served as the framework for a national roadmap to enhance the shock responsiveness of Ghana’s social protection system. The assessment also evaluated the system’s readiness to maintain routine functions during crises, with particular attention to disability, gender, and age-responsive approaches. Although this indicator was officially closed in December 2022, the programme successfully met its target by completing the initial assessments and laying the groundwork for the SRSP roadmap.

Output 2.4: In response to a prolonged dry spell between July and mid-August 2024, Output 2.4 was initiated to provide timely cash transfers to 8,500 vulnerable farmers. Ultimately, 71,055 farmers were reached - an outcome made possible through the concerted efforts of multiple development partners.
The dry spell, which affected large parts of central and northern Ghana, severely disrupted rainfed agriculture and exacerbated an already fragile food security situation. With limited irrigation infrastructure and declining food stocks, communities faced reduced access to food, rising prices, and diminished purchasing power. At the time, over 1.05 million individuals were projected to experience food insecurity - one of the highest estimates in recent years in Ghana.
In collaboration with development partners, the Government of Ghana implemented emergency interventions, including a temporary ban on cereal exports, increased food imports, and support through the LEAP programme and the Ghana Agriculture Agribusiness Platform (GHAAP), which provided seeds, fertilizers, and cash assistance.
WFP collaborated with the Ghana National Household Registry (GNHR) under the Ministry of Gender, Children and Social Protection (MoGCSP) to significantly enhance the accuracy of beneficiary targeting. This partnership also enabled the expansion of the beneficiary list beyond the LEAP programme, strengthening the government’s capacity for future emergency responses.
Between October 2024 and March 2025, the United Kingdom and USAID contributed £1.5 million and £1.1 million, respectively. The beneficiary targeting mechanism developed with the MoGCSP was subsequently adopted by the German Federal Foreign Office (£462,000) and is currently being utilised by South Korea and USDA, who have committed £3.7 million and £1.1 million, respectively, for lean season support (June - August 2025).
This experience underscored the importance of coordinated inter-agency action, harmonised donor support, and robust, interoperable targeting systems that are scalable and adaptable to future shocks. While the UK’s contribution was part of an acute emergency response, the targeting systems developed have since been adopted for medium-term interventions. MoGCSP has integrated many of the identified beneficiaries into its systems for future climate-related responses - demonstrating that well-designed, short-term interventions can lay the groundwork for sustainable, long-term resilience.

Output 3	Increased access to quality integrated, disability inclusive community based and recovery oriented mental health and other health services including services delivered by traditional and faith-based leaders
Output Score	A
Impact weighting (%)	10%		Impact weighting revised since last AR?	Yes

Output Indicator		Starting logframe target	Final logframe target	Final logframe result	PCR Score
Indicator 3.1 / Extent of implementation of Quality Rights Initiatives in health facilities.		Reassessment of 8 Health Facilities to document WHO QR improvements completed.	Indicator Closed Sept 2022	Re-assessment of 8 Health Facilities to document Quality Improvement completed.	Output met expectation (A)
Indicator 3.2 / GoG procurement of psychotropic drugs and availability of psychotropic drugs at all levels.		Availability of Psychotropic Medicines at all levels of care.	Indicator Closed Dec 2023	Psychotropic drugs supplied to temporal central medical centres and distributed to three psychiatric hospitals and regions, but distribution was incomplete.	Output moderately did not meet expectation (B)
Indicator 3.3 / Number of persons with disabilities including mental health conditions and other vulnerable groups benefiting from community-based initiatives including through civil society and / Self Help Groups (SHGs).		(a) 640 people benefiting from continued SHG activities / (b) Sensitization of all 16 regions on the revised DACF guidelines completed / (c) 3,000 people benefiting from Evidence and Effectiveness Grants	Final target updated in September 2024 after original targets were exceeded. / (a) 1360 (720 new) people benefiting from continued SHG activities / b) Sensitization of all 16 regions on the revised DACF guidelines completed / (c) 3,000 people benefiting from Evidence and Effectiveness Grants	(a) 1430 people benefitted from SHG activities / (b) all 16 regions sensitised. / (c) 29,658 people benefitted from Evidence and Effectiveness Grants	Output exceeded expectation (A+)

Output 3 is scored A reflecting continuous high performance throughout the period. Key achievements include successfully piloting three district demonstration sites for district mental healthcare plans which improved access to mental healthcare. Development of primary healthcare demonstration sites increased detection and treatment of mental health conditions. Output 3 also delivered improved accessibility of health facilities, and higher quality mental health and social services.

Output 3.1 sought to assess and improve the implementation of Quality Rights Initiatives in health facilities. This output assessed eight health facilities with the view to documenting WHO Quality Rights Improvements. This activity was successfully delivered before its closure in September 2022. Service improvement plans were developed and implemented to address identified gaps and a post-implementation assessment was subsequently conducted to evaluate progress. Preliminary findings from eight health facilities - comprising five general hospitals and three psychiatric hospitals - indicated notable improvements in people-centred and human rights-based care. These included staff training on de-escalation techniques to manage aggression without resorting to physical restraints. Additionally, several facilities undertook infrastructure modifications to enhance accessibility for persons with disabilities.

Output 3.2 set out to ensure availability of quality and affordable psychotropic medicines at all levels of care for the management and treatment of persons with psychosocial, intellectual, and cognitive disabilities. By December 2023, psychotropic medicines had been supplied to central medical centres and distributed to three psychiatric hospitals and regions, but distribution was incomplete as of the close of this output. Through FCDO’s Partnership Beyond Aid (PBA) Programme, it is anticipated that key bottlenecks related to the prioritisation, procurement, and distribution of psychotropic medicines will be addressed.

Output 3.3 aimed to reach 640 beneficiaries through Self-Help Groups (SHGs) and 3,000 beneficiaries through Evidence and Effectiveness Grants. LNOB also worked extensively at the community level supporting SHGs and community volunteers to provide guidance on how to enhance access to social services and safety nets. This engagement included supporting people to sign up to the NHIS, as well as in-depth stakeholder engagements to ensure that local government funds were used more equitably. By the end of the programme, the number of beneficiaries reached were significantly exceeded, primarily due to an underestimation of potential beneficiaries at baseline, which was influenced by the lack of reliable data.

Output 4	Attitudes, behaviours and norms related to people with disabilities and including mental health conditions transformed
Output Score	A
Impact weighting (%)	10%		Impact weighting revised since last AR?	Yes

Output Indicator		Starting logframe target	Final logframe target	Final logframe result	PCR Score
Indicator 4.1 / Number of people reached with mental health and disability inclusive messages.		(a) 5 grantees have developed a workplan as part of the SBCC delivery strategy. / (b) World Mental Health Day partly supported by the programme. / (c) Accessible COVID-19 materials disseminated.	The indicator was updated in March 2022 following the successful delivery of original targets. / (a) Undertake evaluation of SBC grant. / (b) Grantees most significant change stories reported and disseminated.	(a) Evaluation of SBC grant completed. / (b) Grantees most significant change stories disseminated.	Output met expectation (A)
Indicator 4.2 / Number of health professionals, community members and traditional leaders trained in stigma reduction, discrimination and human rights violations.		Supportive supervision following mhGAP training in 4 regions completed (Greater Accra Region (GAR), Eastern Region (ER), Volta Region (VR) & Central Region (CR)	Indicator Closed / September 2022	Supportive supervision following mhGAP training in 4 regions (GAR, ER, VR & CR)	Output met expectation (A)
Indicator 4.3 / Extent of CSOs and DPO actors participation in advocating for social accountability and improved mental health services and support.		(a)Two civil society organisations implementing advocacy grants / (b)Launch of sustainability and legacy grants for DPOs and WROs	Indicator targets were updated in Sept 2024 to strengthen sustainability of programme interventions / (a) Mental Health Alliance for Mental health Advocacy in Ghana Supported / (b) Evaluation of 6 Advocacy grants and 4 / Legacy grants.	a) Mental Health Society of Ghana Supported. / b) Evaluation of 6 advocacy grants completed and evaluation of 4 legacy grants completed	Output met expectation (A)

Output 4 is scored A as a result of achievement of all indicator targets. It has consistently met all annual review targets. Key achievements included the successful delivery of mental health advocacy by CSOs.

Indicator 4.1 supported five grantee organisations in developing a Social and Behaviour Change Communication (SBCC) delivery strategy, promoting World Mental Health Day, and disseminating COVID-19-related materials. Upon successful completion of these activities, the indicator was updated to focus on evaluating the SBCC grant and sharing grantees’ “Most Significant Change” stories. A series of grants were awarded to small, community-based organisations. These grants served as an effective mechanism to engage selected CSOs in SBCC-focused projects that connected with community leaders, persons with disabilities (including those with mental health conditions), and duty bearers. The programme demonstrated positive shifts in the interactions between service providers and persons with disabilities, enabling individuals to express their needs more confidently and access social welfare support. The grants significantly strengthened grassroots advocacy and amplified the voices of marginalised groups, particularly in under-resourced areas such as mental health.

Indicator 4.2 aimed to provide supportive supervision following Mental Health Gap Action Programme (mhGAP) guidelines training across four regions: Greater Accra (GAR), Eastern (ER), Volta (VR), and Central (CR). The indicator was successfully delivered and subsequently closed. Through this initiative, approximately 17,000 health professionals, community members, and traditional leaders were trained in stigma reduction, anti-discrimination, and the prevention of human rights violations. This experience highlighted the importance of Integrating human rights and anti-stigma training into health systems as these can drive broader cultural transformation in how mental health is understood, addressed, and supported

Indicator 4.3 was meant to support two civil society organisations (CSOs) in implementing advocacy grants and launching sustainability and legacy grants for Disabled Persons’ Organisations (DPOs) and Women’s Rights Organisations (WROs). As the programme evolved, the indicator was updated to focus more broadly on strengthening the sustainability of programme interventions. This revision introduced two new components:
Support to the Mental Health Alliance for Mental Health Advocacy in Ghana and Evaluation of six advocacy grants and four legacy grants. These activities were successfully delivered, demonstrating that adapting programme indicators to reflect evolving priorities can significantly enhance the relevance and long-term impact of interventions, especially when sustainability and advocacy are central to driving systemic change.

Capacity-building trainings and mentorship sessions enabled four grantees—Ghana National Association of the Deaf (GNAD), Ghana Blind Union (GBU), Women with Disability Development and Advocacy Organisation (WODAO), and Duapa - to create action plans and secure funding to pursue their own capacity-strengthening priorities. Importantly, the legacy and sustainability grantees actively shared their knowledge and experiences with the programme’s evidence and effectiveness grantees, fostering peer learning and collaboration. The output demonstrated that investing in organisational capacity and sustainability planning can empower local actors to lead long-term change and strengthens the overall ecosystem through shared learning and collaboration.

Output 5	Effective scale up of disaggregated data collection across all partnerships and generation of high-quality research, evidence, learning and what works to inform programming.
Output Score	A
Impact weighting (%)	20%		Impact weighting revised since last AR?	Yes

Output Indicator		Starting logframe target	Final logframe target	Final logframe result	PCR Score
Indicator 5.1 / Level of secondary analysis of Multiple Indicator Cluster Surveys (MICS) Ghana Living Standards Survey (GLSS data to identify vulnerable girls and boys as well as their caregivers as well as socioeconomic & geographic determinants of vulnerabilities impacted by Covid 19.		Demographic and Health survey conducted using updated sampling frame from 2021 census to track data over 30 Sustainable Development Goal (SDG) indicators	Indicator closed December 2022	Demographic and Health Survey has been conducted and report released on January 2024	Output met expectation (A)
Indicator 5.2 / Extent of interoperability of social welfare system Management Information Systems (MIS) with other databases.		Transition of hosting of SWIMS from UNICEF to the Government owned servers in collaboration with the National Information Technology Agency (NITA)	Indicator closed December 2022	UNICEF has transitioned the hosting of SWIMS to Government and currently being used as GoG’s social protection MIS	Output met expectation (A)
Indicator 5.3 / Extent to which findings from a) the Safeguarding Review and b) the Rapid Review Scoping Study and Assessment on Disability and Gender inclusion informs the Ghana Productive Safety Net Programme (GPSNP).		SDD team deliver agreed 1 to 1 support to LNOB IPs as part of the LNOB Safeguarding review and submission of final project report	Indicator closed February 2020	SDD team delivered 1 to 1 Safeguarding review support to LNOB IPs	Output met expectation (A)
Indicator 5.4 / Assessment Instrument for Mental Health Systems (AIMS) implemented and extent to which it informs the implementation of the Mental health Strategy.		AIMS report conducted and disseminated	Indicator closed September 2022	AIMS survey report finalised and disseminated.	Output met expectation (A)
Indicator 5.5 / Progress on implementation of legislation relating to disability, including the Disability Amendment Bill		Ongoing advocacy and policy support provided for the passage of the Disability Amendment Bil	Indicator closed March 2023	A report on Disability Amendment Bill was produced and shared	Output met expectation (A)
Indicator 5.6 / Access to quality integrated services at the primary health care level for people with disabilities, including mental health disabilities		Legislative instrument for the Disability Amendment Bill is finalised and submitted to Attorney General's Department	Indicator closed March 2023 / Indicator updated September 2024 / Dissemination of District Mental HealthCare Plan pilot learning.	District Mental HealthCare plan pilot learning disseminated	Output met expectation (A)
Indicator 5.7 / Proportion of target districts with district plans which integrate disability, including mental health at a primary care level		100 % of districts who have met levels A, B, C and D (i.e. D) have trialled MH&D HMIS indicators)	Indicator closed Jan 2023 / Indicator updated Jan 2023 Advocacy tool for Accessibility completed	Advocacy tool for Accessibility completed	Output met expectation (A)
Indicator 5.8 / Number of operations research studies conducted and disseminated that support an enabling environment, policy and practice.		Programme produces 1 dissemination product	Indicator updated September 2024 / (a) Programme produces 2 Dissemination products / (b) Key programme evidence is disseminated	a) Five papers have been produced and disseminated / (b) Two Papers on / witchcraft accusations and psychotropic drug supply produced	Outputs moderately exceeded expectation (A+)

Output 5 has consistently achieved an ‘A’ rating throughout the LNOB programme, reflecting its strategic contribution to strengthening social protection systems and advancing inclusion for the most vulnerable. It measured the effective scaling up of disaggregated data collection and generation of high-quality research, evidence, and learning. Despite evolving indicators and some implementation challenges, the output delivered significant achievements that have supported a more resilient social protection system.

From inception, Output 5 was designed to support systems-strengthening and evidence generation through the ‘Synergy Fund’, building a more inclusive and responsive social protection system. A major achievement was the nationwide rollout of the Social Welfare Information Management System (SWIMS) to 160 districts. As of June 2025, SWIMS has been expanded to cover 170 districts out of 261.

Output Indicator 5.1 aimed to ensure that the Demographic and Health Survey (DHS) was conducted using the updated sampling frame from the 2021 Census, enabling the tracking of over 30 Sustainable Development Goal (SDG) indicators. Through the LNOB programme, enumerator training and household registration for the DHS were successfully completed, leading to the closure of the indicator. Subsequently, data collection, analysis, and finalisation of the DHS report were supported under FCDO’s Partnership Beyond Aid (PBA) Programme.

Output Indicator 5.2 was intended to ensure the successful transition of SWIMS hosting from UNICEF to the Government of Ghana, in collaboration with the National Information Technology Agency (NITA). This transition was successfully completed, resulting in the formal closure of the indicator. This reinforces the need for early planning and strong collaboration between development partners and national institutions, such as NITA for ensuring smooth and sustainable transitions of digital systems like SWIMS. Government ownership from the outset enhances long-term system sustainability and integration into national frameworks.

Output Indicator 5.3 aimed to conduct a Safeguarding Review and a Rapid Review Scoping Study and Assessment on Disability and Gender Inclusion, with the goal of informing the Ghana Productive Safety Net Programme (GPSNP). The delivery partner provided tailored, one-on-one support to LNOB Implementing Partners (IPs) as part of the safeguarding review process. This support included technical guidance, and the submission of final project reports aligned with safeguarding and inclusion priorities. Following successful delivery, this indicator was closed. Similar initiatives should emphasise individualised support to implementing partners as this can effectively translate safeguarding and inclusion findings into actionable improvements within national programmes such as GPSNP.

Output Indicator 5.4 focused on conducting an Assessment Instrument for Mental Health Systems (AIMS) to inform the implementation of the national Mental Health Strategy. The assessment was successfully carried out, and the findings were disseminated among a broad group of stakeholders in January 2023. Recommendations were made to guide government policy on mental health. AIMS will track improvements and provide baseline data for monitoring further change and enable Ghana to develop information-based mental health plans. The report highlighted the existing governance structures for delivering mental health services in the country, identified key protection mechanisms, and outlined critical gaps that needed to be addressed such as the absence of a dedicated budget line for mental health at the subnational level. The recommendation to ensure mental health services are embedded within primary health care and linked to other social services for a holistic approach has been successfully piloted in three districts (Output Indicator 5.7).

Output Indicator 5.5 was geared towards providing ongoing advocacy and policy support to facilitate the passage of the Disability Amendment Bill (DAB). Although the ambition to directly advocate for the Bill’s passage was curtailed, due to funding cuts, a comprehensive report on the Bill was developed and widely disseminated in March 2022. This report is intended to inform and guide future legislative efforts.

Output Indicator 5.6 (up to March 2023) was designed to provide advocacy and policy support for the passage of the Disability Amendment Bill (DAB). During the programme implementation period, LNOB contributed to this effort through the Ghana Disability Forum (GDF), the Parliamentary Caucus on Disability, and direct engagement with the Ministry of Gender, Children and Social Protection (MoGCSP). The Caucus was supported to develop a clear sustainability action plan and formulate parliamentary questions addressing key issues affecting persons with disabilities (PWDs). Although this bill could not be passed in the previous parliamentary session; the current government is committed to passing the bill as announced by President Mahama.
[note] Government to pass Persons with Disability (Amendment) Bill | Ghana News Agency

Output Indicator 5.6 (from September 2024) was to ensure that 100% of target districts (Bongo, Asunafo North and Anloga) achieved ‘Level D’ - indicating they had trialled Mental Health and Disability (MH&D) Health Management Information System (HMIS) indicators. This aimed to assess the proportion of districts with plans that integrate disability, including mental health, at the primary care level. The programme strengthened the capacity of 84 non-mental health professionals from 15 selected health facilities across the three districts. A Training of Trainers (ToT) session was conducted, along with the training of 87 community health volunteers. As a result, all three districts have established District Mental Health Operational Teams, developed supervision plans, and initiated the supervision of primary healthcare staff and community volunteers.

Output Indicator 5.7 focused on the development and completion of an accessibility assessment tool designed to evaluate the readiness of facilities. This tool was subsequently used as an advocacy instrument to promote accessibility and facilitate access to quality, integrated primary health care services for people with disabilities, including those with mental health conditions. This output was successfully delivered. The tool is expected to have several positive impacts, including raising awareness among policymakers and service providers about the importance of accessible infrastructure and services for persons with disabilities (PWDs), providing practical guidance for integrating accessibility standards into district-level planning and implementation, and strengthening accountability by offering a reference point for monitoring progress on accessibility commitments.

Output Indicator 5.8 was significantly exceeded. In total, the programme successfully produced five dissemination papers and two major evidence-based documents, against an original target of one. These included: a cross-sectional health facility survey; a situational analysis of mental health services in five districts in Ghana; a study on depression and quality of life among individuals accused of witchcraft; an assessment of mental health and disability outreach; and an examination of the effects of mental health stigma on deaf individuals.

Impact of the documents has been strong. A key piece of programme-generated evidence widely used by stakeholders was a study investigating the prevalence of depression, quality of life, and gender dynamics associated with witchcraft accusations against women in the Northern and Northeast regions of Ghana. The findings significantly contributed to a national discourse on social protection for vulnerable populations, particularly women accused of witchcraft and banished to live in camps. The study intensified advocacy efforts, ultimately contributing to the passage of the Anti-Witchcraft Bill. Substantial work was also undertaken to improve access to psychotropic medicines. This included stakeholder workshops and the development of a policy brief on psychotropic drug supply. These efforts played a critical role in securing consensus for the inclusion of psychotropic medicines in the national health insurance package.

Another critical contribution is the suite of documents developed under the District Mental Healthcare Plan Framework, which has been instrumental in informing government mental health policy and planning at the sub-national level. Additionally, the Evidence-Based Review of the DACF Disability Fund Disbursement and Management Report has become a key reference for policy reform and advocacy efforts aimed at improving the efficiency, transparency, and impact of disability fund allocations. These documents have not only strengthened the evidence base for inclusive social protection and mental health policy but have also enhanced the programme’s visibility and influence in national policy dialogue. The indicator was revised to reflect the expanded scope and strategic value of these outputs.

The output also contributed to a growing body of high-quality research and learning. Through the GSD programme, numerous evidence digests, case studies, and research papers were produced, offering practical insights into disability inclusion and intersectionality in social protection. These resources are not only valuable for national stakeholders but also provide scalable models for inclusive programming in similar contexts.

Although tracking performance was complicated by shifting indicators, reporting gaps and limits to the resources of the partners Government agencies, the output’s influence is evident in the systems and tools now in place. The ambition to use GNHR for all targeted social protection programmes holds long-term potential, and future collaboration between FCDO, the World Bank, and LEAP Management Systems will be essential to ensure inclusive targeting methodologies are maintained. With the development of tools like SWIMS and GNHR, once fully operational, they can transform how social services are delivered and coordinated.

Output 6	Increased access to quality integrated Maternal Mental Health inclusive of community-based healthcare and Community Health Planning and Services (CHPS) in deprived hard-to-reach rural and urban locations, particularly poor rural communities, urban slums and informal settlements and migrant settlements
Output Score	A
Impact weighting (%)	5%		Impact weighting revised since last AR?	Yes

Output Indicator		Starting logframe target	Final logframe target	Final logframe result	PCR Score
Indicator 6.1 / Ghana has a comprehensive Maternal Mental Health Situational Analysis that identifies gaps in service provision, cultural context, existing policies, systems, resources, local needs, and barriers to care.		Indicator added March 2023	(a) Consultant recruited / (b) The study protocol approval by the Ethics Committee received / (c)The establishment of the National Stakeholder group with agreed ToR / (d) E-platforms for data collection and databases, pretested and functional. / (e) Stakeholder engagements organized. / (f) The maternal mental health situation analysis report compilation and validation	(a) A lead consultant recruited / (b) Ethics Committee approval has been received for the protocol / (c)The National Stakeholders Group is established and functioning, with the ToR agreed / (d) Data collection tools are available / (e) Five Stakeholder engagements organised / (f)The MMH situational analysis result report is publicly launched and available for use	Output met expectation (A)
Indicator 6.2 / The Maternal Mental Health Situational Analysis findings and recommendations are publicly disseminated and discussed to sensitise policy makers.		Indicator added March 2023	(a)Launch of the MMH situational analysis result report / (b)Four activities / events are organised for dissemination	(a)The MMH situational analysis result report launched and available / (b)Four activities (one National and three zonal disseminations completed	Output met expectation (A)
Indicator 6.3 / Advocacy engagement and ownership building is achieved with the relevant stakeholders for integration of maternal mental health into existing policies.		Indicator added March 2023	80 % of stakeholders participated during the Advocacy and Stakeholder engagements. / (a) Three Zonal consultations and national dialogue convened; / (b) Advocacy engagement for MMH integration; / (c) Capacity building of 64 (four in each region) selected nurses, doctors and managers at regional level.	80% of stakeholders participated in / (a)National and three zonal disseminations / (b) Advocacy engagement for MMH / (c) Capacity of 475 nurses, doctors and nurse managers built at regional level.	Output met expectation (A)

Overall output 6 scored an A as each of the three sub-indicators was met. This output was delivered by the WHO from March 2023 to support maternal mental health. Originally, this investment was for six months, however, this was extended to May 2024 to enable completion of activities. This component led to the delivery of a major Situational Analysis Report concerning the role of mental health in the delivery of maternal health services. This new Maternal Mental Health element was introduced to the LNOB programme to improve maternal and child health outcomes, especially for poor and vulnerable women in Ghana. Research, engagement, dissemination and capacity building linked to research findings all went according to plan. LNOB partners’ Options/Basic Needs-Ghana worked closely with WHO in delivering the situational analysis and assessment of MMH services to implement stakeholder consultations with GHS. These consultations discussed coordination of policy and advocacy activities to build consensus and ensure integration of mental health within existing national maternal and neonatal, infant and child health policies and strategy.

Output Indicator 6.1 aimed at recruiting a consultant to support the implementation, having the study protocol approved by the Ethics Committee, establishing the National Stakeholder group with agreed ToR, ascertaining the extent of data collection tools developed as well as organising five stakeholder engagements and compiling and validating the maternal mental health situation analysis report, which were all achieved.

Output Indicator 6.2 aimed at launching the MMH situational analysis result report and organising four activities / events to disseminate findings. The Situational Analysis and two policy briefs were instrumental in influencing NHIS to commit to covering four priority mental health conditions—an unexpected but major achievement. The situational analysis revealed some critical gaps in Mental Health Service Delivery, barriers to access and awareness, resource and infrastructure deficiencies and a major barrier of social stigma against women with MMH conditions.
Output Indicator 6.3 successfully achieve 80% of stakeholders' participation during the Advocacy and Stakeholder engagements. Additionally, Output Indicator 6.3 set out to build the capacity of 64 (four in each region) selected nurses, doctors and managers at regional level. This was exceeded, with the capacity of 475 nurses, doctors and nurse managers built at regional level and Continuous professional development (CPD) credits points of 3 assigned for all participants.

This first phase of the MMH initiative, primarily donor-led, aimed to pave the way for a government-led phase two focused on policy design and implementation. Following the closure of LNOB, phase two transitioned to FCDO’s ‘Partnerships Beyond Aid’ (PBA) programme under its results-based aid component with the MHA, placing more responsibility on the Government of Ghana, but retaining donor support. The Government of Ghana has since adopted the LNOB supported situational analysis and is working with key agencies to develop a national roadmap and policy for MMH implementation to address identified service delivery gaps. However, at a wider sustainable outcome and impact level it is not clear that the level of mental health service delivery achieved during the programme can be fully maintained beyond the length of the programme, although many elements of support and impact will continue to be felt.

Output 7	A strengthened sub-national social protection system (through strengthening individual capability) that can effectively identify, respond to and prevent social protection risks and address needs
Output Score	A+
Impact weighting (%)	5%		Impact weighting revised since last AR?	Yes

Output Indicator		Starting logframe target	Final logframe target	Final logframe result	Final PCR Score
Indicator 7.1 / Child protection in Emergencies, GBV and SEA risk mitigation recommendations are developed and shared across sectors in line with the Minimum Standards for Child Protection in Humanitarian Situations.		Indicator added Sept. 2024	100 multisectoral workers sensitised on Gender-Based Violence risk management interventions.	154 frontline staff (65 women and 89 men) received refresher training on the Child Protection Community Facilitation	Outputs moderately exceeded expectation (A+)
Indicator 7.2 / Effective case management and social services are available and used by people, including children, experienced or at risk of violence, exploitation and abuse		Indicator added Sept. 2024	(a) 100 district social welfare and community development officers and their CSO partners supervised and coached on case management SOPs and the use of SWIMS / (b) 3,000 people profiled for case management. / (c) 300 people to benefit from case management.	a) 100 participants trained on the Minimum Standards on Child Protection in Humanitarian Situations, PSEA, GBViE, PFA and MHPSS. / b) 14,462 people profiled for case management. / c) 4,885 people benefited from case management.	(A++)
Indicator 7.3 / Community members know various protection risks and how to prevent, report and seek help from competent authorities		Indicator added Sept. 2024	(a) 35,857 members of affected communities sensitised on where and how to report SEA and GBV; / (b) 4,500 of people reached by community sensitisation	a) 45,391 community members sensitised on where and how to report SEA and GBV / b) 6,105 people were educated on sexual abuse and exploitation, including how and where to report cases or seek support	Outputs moderately exceeded expectation (A+)

Overall output 7 scored A+ as some targets were significantly exceeded. This component provided matched funding for UNICEF’s response to the Volta Flood Emergency, covering the period from October 2024 to March 2025. This output not only delivered refresher training but also effectively leveraged existing staff and systems, surpassing the conservative numerical targets initially set.

Output Indicator 7.1 aimed to sensitise 100 multisectoral workers on Gender-Based Violence (GBV) risk management interventions. By the end of the programme, a total of 154 workers were trained. The training covered Child Protection Community Facilitation, Protection from Sexual Exploitation and Abuse (PSEA), Gender-Based Violence in Emergencies (GBViE), Psychological First Aid (PFA), and Mental Health and Psychosocial Support (MHPSS). Trained personnel were then able to conduct targeted community outreach, identify and respond to protection concerns more effectively, and integrate GBV risk mitigation into broader emergency response activities. Their enhanced skills also contributed to stronger referral pathways, improved case management, and greater community awareness on safeguarding and child protection issues.

Output Indicator 7.2 targeted the training of 100 district-level Social Welfare and Community Development Officers, along with their Civil Society Organization (CSO) partners, on case management Standard Operating Procedures (SOPs) and the use of the Social Welfare Information Management System (SWIMS). The target also included profiling 3,000 individuals and providing case management support to 300 people. Due to the emergency nature of the interventions and the unexpectedly high demand for services, these targets were significantly exceeded. By the end of the programme, over 14,000 individuals were profiled, and a substantial number received case management support. This surge reflects both the scale of need and the responsiveness of the programme in adapting to the evolving context. Given the short duration of the project, a higher caseload was achieved by leveraging the Social Welfare Information Management System (SWIMS) instead of traditional paper-based methods. SWIMS has an integrated feature to strengthen family tracing and reunification in the case of shocks and emergencies and SGBV incident monitoring. Community leaders, including chiefs and village elders, expressed a renewed appreciation for the role of social protection, recognizing its critical importance during times of crisis.

Output Indicator 7.3 planned to sensitise 35,857 affected community members on where and how to report Sexual Exploitation and Abuse (SEA), and to reach 4,500 individuals through community sensitisation activities. These targets were exceeded, with over 45,000 and 6,000 community members reached, respectively. Given the emergency nature of the response, the scale of outreach was not initially anticipated, which contributed to the surpassing of the original targets.

It is evident that pre-existing tools like SWIMS and the Child Protection Community Facilitation Toolkits enabled rapid mobilisation of resources and effective case management for the flood affected communities. A critical lesson emerging from the programme is the importance of addressing secondary impacts of emergencies—such as gender-based violence (GBV) and child protection—which are often deprioritised during crisis response. A key recommendation from Output 7 was for the Government of Ghana to prioritize social welfare as a core component of emergency response. It is crucial to integrate GBV and child protection considerations into emergency planning and response frameworks to ensure comprehensive and inclusive support for affected populations. An unexpected insight emerged from social workers being embedded in displaced communities, allowing them to better understand local dynamics - such as the risks of night fishing involving children - and to tailor mitigation strategies accordingly. UNICEF also contributed to preparedness planning in selected regions, which informed the broader shock response assessment work.

## D: Value for Money

The LNOB programme delivered strong VfM relative to the original Business Case proposition despite challenging operating contexts and budget reductions totalling £13.4million out of the £39.2million approved in the business case. Due to the complexity and diverse delivery mechanisms of the LNOB programme, implementing a unified VfM framework as originally envisioned in the Business case was not feasible as cross-component VfM comparisons could not be conducted. VfM principles were nonetheless embedded within partner agreements and assessed through regular reporting and Annual Reviews. Overall, the project delivered some substantial sustainable changes in a large complex system relating to the lives and wellbeing of Ghana’s most vulnerable people. The Government of Ghana’s delivery of public services, including social safety nets, has been demonstrably changed as a result of LNOB interventions, affecting the way hundreds of millions of pounds are spent, as well as the way disadvantaged people are treated within that system.
[note] Total reduction from the World Bank and GSD components - £8.9m and £4.5m respectively
Effectiveness: The programme achieved its objectives, meeting or exceeding output and outcome targets as outlined in earlier sections of this review. It reached over 1.6 million individuals through LEAP cash transfers and an additional 71,000 through emergency support during the dry spell. Key targets were surpassed in areas such as community-based mental health services, advocacy, and social protection system strengthening.
A strong focus on technical assistance and systems strengthening enhanced sustainability and helps ensure that the impact of changes achieved are felt beyond the direct beneficiaries and into the future. The ISS/SWIMS case management and referral system is now active in 170 of Ghana’s 261 districts, linking vulnerable individuals to NHIS, social protection, child protection, DOVVSU, and other social welfare services. This integrated approach improved user experience and enabled comprehensive support. During the 2024 Volta floods, SWIMS facilitated rapid emergency case management for 4,885 individuals (1,244 women, 1,025 men, 1,366 girls, and 1,250 boys). Similarly, our investment into the GNHR facilitated more effective targeting of LEAP beneficiaries as well as victims of the recent dry spell in the North. Although our support to GNHR ended early, GoG institutionalised it within MoGCSP (as a Unit), ensuring its continued use. The registry supports LEAP by improving targeting, enrolment, and graduation through household progress tracking and phasing out those no longer eligible. Integration with NHIS and National Identification Authority systems enhances data validation and streamlines beneficiary transitions. Essentially, the overall case for VfM is that the LNOB programme has demonstrated value through its economy, efficiency, and effectiveness, with a deliberate emphasis on equity across interventions. It has delivered sustainable change that justifies our £27 million investment.
An independent review of the LNOB and Partnerships Beyond Aid (PBA) programmes to assess effectiveness of both programmes to inform future programming confirmed the effectiveness of the Results-Based Aid (RBA) model in driving mental health reforms, though its success depended on sustained government commitment, which was occasionally challenged by economic constraints. While RBA was largely effective, it posed risks of long-term dependency on FCDO support. To address this, and in line with the transition to the Partnerships Beyond Aid (PBA) programme, a sustainability plan is being co-developed with the Mental Health Authority to reduce external reliance and strengthen national ownership.
Overall, the review concluded that LNOB’s delivery mechanisms were appropriate, while noting that funding cuts and compressed timelines limited the scope of evaluation.
Efficiency: Efficiency was achieved through adaptive programming and diversified delivery mechanisms, including the use of Trust Funds for cash transfers, strategic partnerships with UN agencies, and direct grant disbursements.
The integration of digital platforms such as SWIMS and mobile money significantly improved the speed and transparency of case management and cash transfers. However, systemic inefficiencies—such as recurring LEAP payment delays and leadership gaps within the Ministry of Gender, Children and Social Protection (MoGCSP)—hindered optimal performance. The use of the Ghana National Household Registry (GNHR) during the dry spell response enabled more accurate targeting of non-LEAP beneficiaries, reducing duplication and ensuring equitable emergency support.
Structured grant-making processes supported NGOs, Women’s Rights Organisations (WROs), and Civil Society Organisations (CSOs), contributing to impactful destigmatisation and behaviour change campaigns. The Self-Help Group (SHG) model proved to be a cost-effective, community-driven approach that leveraged local structures for sustainable behavioural transformation.
The programme adopted globally recognised tools rather than investing in new systems where it could. This included the PRIME model for district mental healthcare planning and WHO’s mhGAP for training 22,210 healthcare workers—indirectly benefiting over 444,000 individuals. The WHO Quality Rights Toolkit also guided training for regional MHVCs.
Economy: Strong economy was demonstrated by leveraging existing government systems (LEAP, SWIMS, GNHR) to minimise duplication and reduce costs. Procurement of psychotropic medicines through GHANEPs and the use of mobile money for emergency transfers lowered logistical expenses. Online training, such as mhGAP, further expanded reach while reducing in-person delivery costs. A robust comparison of overhead cost across components have not been possible. However, overhead costs for all partners have been kept within FCDO benchmarks. For GSD for example, personnel costs met fee rate targets. The average unit cost of STTA was £410 per day; this was lower than the original contract proforma benchmark of £521. Overheads for multilateral partners were aligned to global FCDO framework agreements. RBA was paid based on achievement of agreed milestones.
Equity: The whole principle of LNOB was reaching the most excluded and vulnerable. Not only were the majority of direct beneficiaries in this category, but wider national and ongoing systems designed to support the vulnerable were strengthened, in most cases on a sustainable basis. LNOB prioritised the extreme poor and excluded groups, especially women, girls, and persons with disabilities—focusing on those with mental health conditions. While gender was tracked in results, the primary emphasis was placed on other dimensions of equity, as outlined below:
- Gender-Sensitive and Inclusive Programming: All five GSD grantees were OPDs or WROs. In 2023, 55% of 51,686 people reached were women; 48% were persons with disabilities.
- Accessible Budgeting: GSD grantees budgeted for disability-inclusive accommodations, improving access for women with disabilities and mental health conditions.
- Targeted Cash Transfers: LEAP supported 343,343 poor households (about 1.6m people); WFP drought response provided $60 to 14,211 households (approx. 71,055 individuals), delivering critical financial relief to the most vulnerable.
- Policy Impact: LNOB evidence informed the development of a national Maternal Mental Health policy, supported by strong stakeholder engagement.

E: Risk

Overview of risk management
The LNOB programme maintained a moderate risk rating throughout its implementation, consistent with FCDO Ghana’s risk appetite. Despite significant cross-cutting challenges - including two national elections, the COVID-19 pandemic, and staffing gaps within the FCDO Human Development Team, - these risks were effectively mitigated. Risk assessments were conducted quarterly at a minimum and regularly discussed in weekly team meetings, partner engagements, and periodic FCDO Policy and Delivery Board meetings.

The programme demonstrated a receptive risk appetite, operating within the overall FCDO risk appetite.

Key Risks and Mitigation Measures

In the final year, the programme continued to operate within a moderate residual risk threshold. Key risks identified under FCDO’s standard categories included:

Strategic and Contextual risks: The evolving global and national contexts significantly influenced programme implementation. In the UK, the reprioritisation of Official Development Assistance (ODA), coupled with the COVID-19 pandemic, led to shifts in funding priorities. In Ghana, macroeconomic instability between 2021 and 2024 resulted in reduced and inconsistent investments in social sectors, particularly social protection. These challenges were further compounded by the political dynamics surrounding the national elections in the programme’s final year.
Human rights risks persisted, notably with the Family Values Bill, which remained stalled at the presidential level and unresolved by the programme’s end. During the economic downturn, FCDO, UNICEF, and other partners supported the Government of Ghana in IMF negotiations, contributing to the 2023 national budget’s prioritisation of key social protection programmes such as LEAP and school feeding.

Reputational Risks: Funding reprioritisation led to delays and reductions in partner allocations, resulting in staff turnover within certain workstreams, diminished trust, and the early closure of some components—most notably the UK’s contribution to LEAP through the World Bank. These risks were mitigated through proactive stakeholder engagement, including high-level consultations, financial scenario planning and transparent communication. FCDO collaborated with partners to reprogramme activities and jointly develop mitigation strategies. In the case of the cash transfer component for example, FCDO engaged the World Bank extensively to ensure that elements that were reprogrammed or terminated were backfilled by the World Bank to avoid a cliff edge.
Safeguarding was a critical focus due to LNOB’s engagement with vulnerable populations. All implementing partners (IPs) underwent comprehensive safeguarding assessments covering organisational culture, HR, governance, SEAH prevention, and case management. These assessments confirmed that appropriate controls were largely in place across all components. Findings were not averse and were addressed through a monitoring plan. Safeguarding cases that arose during the life of the programme were duly reported and resolved according to FCDO policy.
Financial and Fiduciary Risks: FCDO conducted due diligence assessments on all implementing partners prior to agreement finalisation, while IPs carried out similar assessments for downstream partners before disbursements. Recommendations from the due diligence assessments were monitored during the life of the programme. GSD/Options provided quarterly monitoring and fiduciary capacity-building support to strengthen financial management systems. All alleged financial fraud cases were reported and resolved during the programme period. Annual audits were conducted for GSD with findings monitored and resolved through an implementation plan.

People and Operational Risks: Ghana’s volatile macroeconomic environment during programme implementation, characterised by fluctuating prices of goods and services—complicated forecasting and operational planning. FCDO worked closely with partners to minimise forecasting inaccuracies through regular communication, proactive market monitoring, and robust advance planning. Staffing gaps within the LNOB team during the final year of the programme led to increased workloads and a temporary loss of technical expertise, particularly in social protection, gender and social inclusion. The team mitigated these challenges by prioritising work and leveraging support within the Human development Team.

Residual Risks
Despite mitigation efforts, some risks remained at programme close, including:
- Full operationalisation of the Mental Health Review Tribunal (MHRT) and regional MHVCs
- Continued development and implementation of District Mental Health Care Plans
- Sustained government funding for mental health, which remains limited despite policy commitments

To support sustainability of our interventions, we continue use our diplomatic and political influence to advocate for more GoG attention and investment into mental health financing.

Update on Partnership Principles
Results-based aid provided direct funding (non-budget financial aid) to the GoG via an MoU with the MoH. The partnership principles of poverty reduction and the sustainable development goals; management of public finances; tackling concerns about human rights abuses and corruption; and improving domestic accountability are regularly assessed by FCDO. The last update has recently been undertaken (June 2025).

Commitment to reducing poverty and achieving the Sustainable Development Goals (SDGs):
Ghana has demonstrated strong commitment to reducing poverty and achieving the SDGs by aligning its national development plans with global goals Ghana’s Medium-Term National Development Policy Framework (MTNDPF) 2022–2025 integrates SDG targets into national planning, ensuring coherence between local development and global objectives. Despite fiscal constraints, the government has prioritised pro-poor spending, including increased disbursements to persons with disabilities through the District Assemblies Common Fund (DACF). SDG-related funding rose significantly between 2021 and 2022, and initiatives like the Ghana CARES Programme aim to build resilience post-COVID. The President has reaffirmed Ghana’s dedication to sustainable development, with continued collaboration with international partners. While limited fiscal space remains a challenge, the new government has reaffirmed its commitment to the social sectors by significantly increasing budgetary allocations in 2025. The School Feeding Programme budget rose by 33%, with the feeding cost per child increasing from GHS 1.50 to GHS 2.00 per day. The Capitation Grant increased by 73.2%, from GHS 84 million to GHS 145.5 million. The Livelihood Empowerment Against Poverty (LEAP) programme allocation rose by 30.8%, from GHS 728.8 million to GHS 953.5 million. The National Health Insurance Scheme (NHIS) allocation is GHS 9.93 billion following the uncapping of the NHIS levy.
[note] Data source: Gov’t increases Feeding Programme Capitation to GH¢145.5m

Commitment to respecting human rights and other international obligations:
Human rights records in Ghana are generally considered good, as Ghana is a signatory to several international human rights instruments and Ghana was recently elected as a member of the UN Human Rights Council. Moreover, Ghana has well developed democratic structures that promote fundamental human rights and support civic activism. Nevertheless, violence and discrimination against women and girls, child marriage, and early pregnancy persist. In addition, the new ‘Family Values’ bill (yet to be signed into law) seriously threatens the human rights of minorities based on gender and sexual identity.

Commitment to strengthening financial management and accountability and reducing the risk of funds being misused through weak administration or corruption:
Ghana agreed a new, 3-year, $3bn Extended Credit Facility with IMF following debt default in December 2022. This was aimed at restoring macroeconomic stability and debt sustainability. The programme was largely premised on a reformist agenda with conditionalities that aimed to support improved Public Financial Management (PFM) and greater transparency. IMF also conducted a Governance Diagnostic Assessment for Ghana, from which it hoped to encourage future reforms that can drive improved governance outcomes, including anti-corruption. In December 2024, just prior to the election that brought in the new administration, IMF approved $360 million under the Extended Credit Facility after the successful completion of the third review of Ghana’s performance – bringing the total disbursement to $1.92 billion since the Extended Credit Facility started. “Ghana’s performance under the programme has been generally satisfactory, and reform efforts are paying off. Growth is recovering rapidly, inflation has declined - though at a slower pace - and fiscal and external positions have improved,” IMF stated. A broader reform agenda had a positive effect on the government enabling environment within which LNOB was operating.
[note] https://mofep.gov.gh/news-and-events/2024-12-04/imf-approves-360-million-for-ghana-as-economic-recovery-gains-momentum

Commitment to strengthening domestic accountability:
Ghana’s commitment to domestic accountability is obvious in duty bearers’ cooperation and responsiveness to citizens’ and CSOs’ voice. CSO partners met during this review confirmed that they had access to both the executive and legislative arms of government. Moreover, the Right to Information (RTI Bill) that was passed into law in March 2019 boosted more transparent and accountable governance. This review learnt that CSOs, including the media, made use of the RTI Bill to hold government institutions to account. However, there are some risks related to government not always being able to hold its appointees to account due to political exigencies.

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Commercial Performance
The LNOB programme was a complex initiative comprising 10 components and 7 logframe outputs. While it was well-positioned to meet Business Case objectives and respond to emerging needs and changing contexts, the breadth of components introduced operational complexity. A variety of agreement modalities were employed to accommodate the diverse nature of implementing partners. Agreements with UNICEF, WHO, and GSD were extended (both costed and no-cost) with GSD undergoing six contract amendments to address funding cuts, COVID-19 pivots, and the completion of key activities.

Annual reporting confirmed that key partners (GSD, MoH/MHA, WHO, UNICEF, WB, WFP) consistently submitted timely and complete reports. From inception, partners established robust financial management and procurement systems, which helped minimise fiduciary risks. Due diligence assessments were conducted prior to agreement signings, with recommendations fully implemented. Financial audits confirmed that transactions were compliant with FCDO Financial Regulations and legislative authority with no adverse findings.

Most programme activities were delivered as planned. Where funding varied, the programme adapted through financial scenario planning to maintain alignment with UK priorities and ensure relevance. An independent review concluded that the funding modalities were appropriate for delivering expected outputs, though it recommended reassessing the use of results-based aid for future government funding.

Milestone assessments and result verifications were conducted prior to fund disbursements. Suppliers acknowledged that the programme fostered joint working and collective accountability, though some noted a strong emphasis on reporting and timely input delivery. A more focused approach on sustainability could have further enhanced long-term outcomes.

Financial performance and programme delivery
The planned budget approved in the Business Case was £39.2million. At the end of the programme, actual disbursement was £27.627million. Table 2 below outlines the total budget allocation for LNOB by component and the total funding disbursed at the end of the programme. The wide budget-actual spend variance is largely due to budget cuts in alignment with changing FCDO priorities and changing global contexts. By the final year, the largest single expenditure was the one-off £1.5 million in humanitarian funding through the World Food Programme (WFP) for drought response in northern Ghana—accounting for a significant portion of the £2.3 million final-year budget.
Table 2: Allocation and Disbursement over the lifetime of LNOB

Allocation and Spend over the lifetime of LNOB - based on Components
Component | Description	Partner	Planned Budget Allocation (£)	Total Spend (£)	Comments
300385-102 | LNOB - Ghana Productive Safety Net- Trust Funds	World Bank	21,000,000.00	12,100,000.00	Budget cuts of £8.9m
300385-103 | LNOB- World Health Organisation Quality Rights Rollout	WHO	1,350,000.00	1,350,000.00
300385-104 | LNOB- Monitoring and Evaluation	Various Partners	276,988.82	241,460.52
300385-105 | LNOB - UNICEF strengthening referral and reintegration to social Services	UNICEF	2,450,000.00	2,450,000.00
300385-107 | LNOB- Disability and Mental Health	Options/ GSD	11,968,000.00	7,460,783.94	Budget cuts of £4.5m
300385-108 | LNOB- Support to Ministry of Health	MHA/MoH	2,000,000.00	2,000,000.00
300385-109 | Support to BasicNeeds Ghana to improve mental health policy and services	Basic Needs Ghana	150,000.00	125,169.93
300385-401 | Strengthening Integrated Maternal Mental Health Service in Ghana	WHO	300,000.00	300,000.00
300385-402 | Addressing Child Protection, GBV and Prevention of Sexual Exploitation and Abuse	UNICEF	100,000.00	100,000.00
300385-404 | Support to Dry Spell in Northen Ghana.	WFP	1,500,000.00	1,500,000.00
Total Spend at Programme End			27,627,414.39

Despite having multiple partners with varied delivery mechanisms, FCDO maintained good working relationships. Key partners met during PCR interviews stated that communication between FCDO and partners improved during the programme. The programme team had to deal with (human) resource gaps at various points resulting in heavy workloads. The Team however managed to deliver in line with PrOF requirements, prioritising key areas of work as required and in line with country business plans. Programme management remained consistently robust over the years albeit challenging for capacity because of managing multiple workstreams and partners. The final year of the programme was particularly difficult without a Social Development Adviser and early departure of the Health Adviser; this meant a significant gap in technical leadership and direction which subsequently stretched programme management capacity thinly.

The programme’s successful pivot during COVID-19 demonstrated its adaptability and resilience, while also offering valuable lessons for future programming - particularly the importance of well-documented decision-making processes and ensuring that reprioritisation efforts remained aligned with long-term goals and the country business plan.

Asset management
Assets procured by implementing partners - primarily office and health equipment - were recorded in asset registers maintained by both FCDO and partners. Annual asset verification exercises were conducted with no adverse findings. Most assets remained in good condition at programme end. Where losses occurred, FCDO procedures were followed. Upon closure, assets were disposed of in accordance with FCDO-approved processes, with transfers made to government partners and NGO/CSO grantees.

Programme-level approach to monitoring and evaluation
FCDO maintained comprehensive oversight of implementing partners (IPs) throughout the LNOB programme using a multi-layered approach that combined structured planning, regular engagement, and collaborative monitoring. All partner workplans, budgets, and deliverables were reviewed and approved by FCDO, with ongoing support provided to improve the quality of reporting. Regular engagement included monthly technical calls with GSD, quarterly reviews with WHO and UNICEF, and biannual technical sub-committee meetings involving all programme partners. These engagements ensured alignment, accountability, and timely resolution of implementation issues.
Challenges in accessing high-quality, reliable data affected logframe reporting. Additionally, shifts in context—such as the COVID-19 response and budget reductions - necessitated adjustments to the theory of change and, consequently, the logframe. These changes were not always comprehensively documented, which impacted the continuity and clarity of performance tracking. Although the Business Case aimed to track VfM across all programme components, this was not achieved due to the programme’s complexity and the absence of a unified framework. Instead, VfM principles were embedded in individual partner agreements and monitored through regular reporting and Annual Reviews.
Progress was tracked through quarterly or semi-annual narrative and financial reports, complemented by joint reviews with key stakeholders such as the Mental Health Authority, Ministry of Health, and the World Bank. Field visits, participation in partner-led events, and World Bank missions provided FCDO with direct insights into implementation realities. GSD played a central role in monitoring and capacity building for grantees through structured site visits and a robust MEL framework, which included a learning agenda and risk mitigation strategies. Safeguarding was actively managed through a dedicated audit and partner-specific action plans. Additionally, an external programme-level review in late 2024 was commissioned to inform future programming under FCDO’s human development and capital portfolio.
Evidence
LNOB supported generation, uptake and evidence use across the mental health, disability and social protection sectors. GSD Programme staff, in collaboration with stakeholders, carried out regular field visits, for example to assess the impact trainees had on the delivery and accessibility of services; and consultants collected health facility survey data which informed programme approaches. Evidence generated has included formal primary research; desk reviews of existing information; story collection and grantee-led research. This has led to numerous reports (often supported by a digestible summary), learning products, policy briefs, and a remarkable 14 journal publications. GSD also developed the evidence-backed investment case for mental health with the Mental Health Authority and partners for policy-change advocacy.

UNICEF’s documentation and evidence fed into national roll-out of the ISS model to share good practice and lessons among government staff, evaluate operations and outcomes, and influence national roll-out. UNICEF actively generated evidence such as the ‘Vulnerability and Exclusion Assessment’ and advocated for more fiscal space for social protection through various stakeholders, with one of the major advocacy efforts and technical advice targeted to IMF-GoG negotiations leading to prioritisation of social protection and LEAP payments. MHA’s research work on knowledge and integration of mental health has provided information for their strategic plans.

Learning

Learning was a core element of the LNOB programme, integrated across all outputs. Annual reviews and partner-led events enabled reflection and adaptive decision-making at the programme level.
At the component level, GSD supported grantees through peer exchanges and structured learning sessions. In December 2023, 60 community volunteers participated in a review meeting to inform 2024 planning. Each grant round was independently evaluated, with findings used to improve future implementation - ensuring continuous learning and refinement.
To capture learning, GSD produced short films on disability advocacy and conducted a self-evaluation shared with FCDO. Lessons from District Mental Health Care Plan pilots are informing scale-up efforts.
Date of last narrative financial report	1.GSD: 27/09/2024 / 2.UNICEF: 30/07/2024 / 3.WHO:15/07/2024 / 4.MoH/MHA: 12/02/2024	Date of last audited annual statement	GSD: 29/01/2025

LNOB PCR Process
The Project Completion Review (PCR) was conducted by a team of independent consultants, with inputs and revisions provided by the FCDO Ghana team—including the LNOB Programme Team, Delivery Excellence Team Leader, Results Adviser, Human Development Team Leader, and Development Director.

The review process involved a combination of methodologies, including:
- A series of workshops
- Key informant interviews with stakeholders
- Document reviews conducted by the consultants
- One-on-one discussions and a dedicated meeting with FCDO advisers for deeper interrogation and validation of findings

This collaborative and consultative approach ensured that the PCR was comprehensive, evidence-based, and reflective of both independent analysis and programme-level insights.

Annex 1: LNOB Theory of Change

Annex 2: Business Case VfM Proposition

Economy: getting the right price for project inputs	Competitive unit costs of key inputs at the required quality, given equity considerations; / Best practice in procurement of goods and services; competitive bidding environments for projects/evaluations and other research products; / Fee rates compared to market rate; / Understanding and managing key cost drivers: grants, research costs, staffing and travel before going to the market (see commercial case for more info); / LEAP: maximises economy through cutting down costs by switching from manual to digital/electronic targeting using tablet devices, reducing the time sent from 45mins to 8mins.
Efficiency: optimising the cost of turning inputs into outputs/outcomes	Unit costs of key outputs (e.g. number and cost per beneficiary reached) ensuring that only like for like units are compared and ensuring that targeting of hard-to-reach people is not dis-incentivised by pressure to lower cost per beneficiary; / Policies and procedures to monitor and maximise conversion of inputs to outputs/ outcomes. / Costs of communicating research outputs most efficiently; / E-payments for cash transfers reduce the time and transportation costs of collecting and distributing payments – improving efficiency – reducing fiduciary risk; / LEAP e-payment system is efficient as it ensures beneficiaries are paid cumulative benefits as their money is credited every cycle and balance shown when biometric fingerprint is verified and authenticated; / The use of tablets to assist in targeting processes to identify new LEAP beneficiaries has provided efficiency savings, including in the time taken to administer questionnaires and the accuracy of data collected; / Mental Health: focus on community-based rehabilitation and PHC, de-institutionalisation rather than hospital level for MH will also reduce the costs of inputs versus outputs for the system.
Effectiveness: optimising the cost of turning outputs into outcomes and impacts	Regularity of cash transfer payments to enable beneficiaries to meet day to day household needs. / Number of extreme poor, people with disabilities and mental health conditions supported through evidence-based interventions e.g. accessing quality education; healthcare, jobs/livelihoods; / Extent to which interventions are targeted (geographically and/or to particular groups and institutions) where they can have most impact; / Extent to which evidence is used to improve programme design and understanding where gaps are most compelling; / Development and use of mechanisms to support learning and coordination across innovation and scale-up projects; / Number of smaller DPOs whose capacity has been built to increase impact and reach; / Measures of whether the outcome for the programme is being achieved compared to other ways of achieving the outcome; / Number of development organisations and level of Government ministries/agencies commitment to increase action and investment on disability inclusion/mental health; and qualitative progress on disability inclusion e.g. a partner’s capability built; mental health funding by GoG; / Cost per DALY averted on a periodic basis; / Extent to which implementing partners have updated understanding of research production, research impact and the costs associated in different techniques.
Equity	Input level: / Extent to which staffing policies and infrastructure are fully inclusive of people with disabilities; / Extent to which staffing policies (e.g. maternity leave) are representative of the population and fully inclusive; / Extent to which equity is considered and valued when procuring goods and services; / Number and experience of staff with disability and gender expertise; / Extent to which LEAP targets the extreme poor and marginalised and vulnerable groups. / Output level: / Extent to which data is disaggregated by disability status (a key requirement for the programme) using Washington Group Questions (WGQs); / Extent to which data is being collected on other diversity indicators e.g. sex, age, socio-economic status; / Extent to which outputs consider and assess equity e.g. services delivered are designed to be inclusive and leave no one behind; / Number of DPOs supported who target the extreme poor and harder to reach populations and issues; most notably people with disabilities. / Outcome level: / Extent to which sectors, locations, issues that have benefitted from funding, are inclusive; / Extent to which evidence generated, in addition to the extreme poor and people with disabilities, is applicable to all population groups i.e. projects are relevant to older, younger, women and men, rural and urban.

ANNEX 3: LNOB PARNERS AND DELIVERY TIMELINES