 Annual Review Template – from April 2020

Title: LEAVE NO ONE BEHIND AS GHANA MOVES BEYOND AID
Programme Value £ (full life): £39.2 million		Review date: 17th February 2022
Programme Code: [AMP ID 300385]	AMP start date: -March 2019	AMP end date: March 2024

Summary of Programme Performance
Year	2020	2021	2022
Overall Output Score	A	A	A
Risk Rating	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300385/documents
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300385/documents

A. SUMMARY AND OVERVIEW

Description of programme

Leave No One Behind (LNOB) provides £39.2 million over five years (2019-2024) to support the Government of Ghana to deliver services to the poorest and most excluded. It will focus on social protection and realising the rights of people with disabilities and Mental Health conditions. LNOB is FCDO Ghana’s largest bilateral programme of support working across poverty, disability inclusion and Mental Health.

LNOB contributes to four areas of change: (1) Improved policy, leadership, resources and governance systems that promote disability inclusion and Mental Health for all and enable equal recognition and respect for human rights of the extreme poor and marginalised; (2) the extreme poor and marginalised, people with disabilities and Mental Health conditions enjoying high quality and integrated health and social protection systems; (3) full, active participation and representation and reduced stigma for the extreme poor and persons with disabilities and Mental Health conditions, discrimination and human rights violations; and (4) improved knowledge and evidence-based understanding of exclusion and what works to improve wellbeing, social and economic outcomes and rights. The LNOB programme has three delivery mechanisms:

Social Protection – delivered through the World Bank Trust Fund – working with the Government of Ghana (GoG) through the Ministry of Gender, Children and Social Protection (MoGCSP), and UNICEF building on the first phase of the Livelihood Empowerment Against Poverty (LEAP) programme.

Mental Health and Disability - delivered through the Ghana Somubi Dwumadie (Ghana Participation) programme and a consortium of NGOs, research organisations - to support Government to scale up delivery of quality and integrated Mental Health services, particularly at the primary health care and community level and provide sub-grants to civil society organisation (CSOs) and Disabled Peoples Organisations (DPOs) to support community-based rehabilitation and inclusion, support empowerment and recovery and develop anti-stigma campaigns.

Synergy Fund-managed by FCDO - to provide support for activities which create synergies and linkages between tackling poverty and promoting disability inclusion. These include supporting UNICEF to strengthen integrated services, case management and referral and reintegration pathways; Results-based financial aid to Ministry of Health (MoH) to support the strengthening and integration of Mental Health provision; MoU with WHO to support Quality Rights through Technical Assistance (TA); Scoping Study on LEAP delivered by the Social Development Direct (SDD).
The programme builds on FCDO’s previous support to LEAP (£35 million over 6 years (2012-13 to 2017); and to Mental Health under the Health Sector Support Programme (HSSP). The 2020 ICAI review of Overseas Development Assistance (ODA) spend in Ghana found that both programmes had made effective contribution to Ghana’s development results. The findings assessed UK aid to have made an essential contribution to improved access to Mental Health care and a strong contribution to strengthening access to social safety nets for the most vulnerable. However, the report stated that, while it found the LEAP programme likely to be sustainable, there is a risk that development gains in Mental Health provision will be reversed without a sustainable exit strategy for financing in place.

Therefore, while recognising the huge need for strengthened safety nets and access to quality Mental Health services so that no one is left behind, this programme focuses more on strengthening policy, leadership and governance systems to transform attitudes and social stigma related to people with Mental Health conditions, moving away from a focus on service delivery and to support Government of Ghana (GoG) towards self-reliance and sustainability.

The COVID 19 pandemic has drastically impacted the lives of those in the bottom billion in Ghana - the extreme poor and vulnerable including those with disabilities and Mental Health conditions.

Summary supporting narrative for the overall score in this review

The overall score for this review is an A. The programme is on track to deliver against expected outcomes and impact. In term of progress at the outcome level, LNOB contributed towards public awareness and sensitisation to Mental Health and disability in Ghana e.g. through various programme components. These include Ghana Somubi Dwumadie which reached 31,673 people in 2021 though the expansion of Self-Help Groups (SHGs)and Social and Behaviour Change Communications (SBCC) support at the district level which positively impacted attitudes and behaviours. Under the psychosocial grants component,16,042 individuals were reached which exceeded the target of 4,000 for the review period. This was an unintended benefit which was achieved by grantee partner Christian Health Association of Ghana (CHAG) who cascaded training and psychosocial support to stakeholders to pivot in response to the Apam drowning emergency which took place on 8th March 2021. Furthermore, through WHO’s Quality Rights initiative 17,685 individuals were reached. Throughout 2021, the COVID-19 pandemic has continued to have wide-reaching impacts, threatening hard-won progress on the LNOB programme and risks the reversal of progress made in Ghana. Furthermore, ODA cuts to the programme in 2021 meant that we were unable to support key components under the World Bank Trust Fund as well as various outputs under the Ghana Somubi Dwumadie resulting in some output indicators not being measured during this FY. Despite these significant cuts to the social protection component delivered through the World Bank, through UNICEF we were able to deliver TA to strengthen the social protection system. In addition to that, through our support to UNICEF, LNOB was able pivot to respond to Government and meet new unplanned needs. For example, to mitigate against the risks of COVID, the programme used new modalities to operationalise emergency cash transfers via mobile money to reach new categories of vulnerable and excluded groups outside the programme. In this way, the programme has been able to deliver against expected outcomes and impact and has also been agile in responding to the changing context by expanding its reach. Despite these challenges the LNOB programme continued to achieve good progress across most of its components. In 2021 notable achievements of LNOB include:

UNICEF- UNICEF provided technical assistance to the Ministry of Gender, Children and Social Protection to strengthen social protection systems and operationalise LEAP and COVID-19 emergency cash transfers to reach 64,319 individuals including street children, Kayayei (adolescent girls selling in markets), flood victims, homeless, persons with disabilities and elderly women in witches camps. The Integrated Social Services (ISS) initiative was scaled up including the Social Welfare Information Management System (SWIMS) to 100 districts – as of December 2021, SWIMS was launched in 2021 and has over 520 users managing over 4,950 cases. Intersectoral Standard Operation Procedures for Child Protection and Family Welfare (ISSOPs), and the Directory of Social Service, standards, tools, and guidance designed to strengthen social workers as part of wide-ranging care reforms. To guarantee that FCDO investment will make a sustainable impact, UNICEF worked with NDPC to ensure that the ISS is included in the District Medium Terms Development Plans (DMTDPs) of the MMDAs for 2022-2025.

Options - Ghana Somubi Dwumadie (GSD) reached 31,673 people in 2021. This included 16,052 people reached by COVID-19 Psychosocial and Resilience grantees, 6913 people reached by our Evidence and Effectiveness grantees, and 2773 people reached through SHGs. Additionally, 5935 people were also reached through various activities directly implemented by the Programme and its consortium partners. Other successes included the establishment of task groups, and subsequent agreement of pilot regions for the Mental Health Review Tribunal and Regional Mental Health Visiting Committees to establish key human-rights structures which will protect the rights of people with Mental Health conditions and hold duty bearers accountable. Another key achievement in 2021 was the strengthened synergies and linkages between partners e.g. between Ghana Federation for Disability Organisations (GFD) and Ministry of Gender, Children and Social protection, Ministry of Health and Local Government on the development of guidelines for the District Assembly Common Fund disability Fund (DACF) component.

World Health Organisation (WHO) - WHO made good progress in 2021 - this included 105 primary health care nurses (including 46 female) in 3 regions (Volta, Central and Eastern) of Ghana have benefited from a training in the management of common Mental Health conditions, which they are using to improve Mental Health service delivery. 7 facilities have successfully developed Mental Health care service transformation plans in line with human-rights-based approach following a gap analysis; the plans are currently under implementation. The WHO QualityRights Initiative has successfully created awareness among 17,685 individuals who have earned a certificate in the e-training. These individuals are using the knowledge to promote a human rights-based approach to Mental Health care among healthcare professionals in training and in active service, persons with lived experience and their caregivers, civil society, religious leaders, and community members. Forty volunteers signed up as ‘digital angels’ to promote the QualityRights initiative. Continuous Professional Development (CPD) accreditation for the QualityRights training has been renewed for five health professional bodies for the year 2022.

Mental Health Authority (MHA) - MHA successfully launched the 12-year Mental Health Policy and disseminated 1,000 copies of the policy which aims to give direction to key stakeholders and ensure the delivery of quality Mental Health services. In addition, some progress has been made in establishing the Mental Health Tribunal, Visiting Committees and Mental Health Subcommittees. At the same time, there have been challenges in establishing key governance structures e.g., the Mental Health Board which is critical in order to successfully establish the Mental Health Tribunal and Visiting Committees. Towards the end of 2021, there was a pause on activities to assess and evaluate various challenges and determine the way forward.

Major lessons and recommendations for the year ahead:

The LNOB programme has been reviewed over the past two years by various actors including ICAI, the Quality Assurance Unit (QAU), the Disability Inclusive Development (DID) Helpdesk, the Social Development Direct (SDD) and the Social Protection Approaches to COVID 19 (SPACE) programme. There are a few outstanding recommendations from these reviews as well as a few from the 2020 AR.

Advancing gender equality and women’s and girls’ rights and promoting sustainable growth, stability and poverty reduction are core parts of the UK Government’s commitment and mission, including the Foreign Secretary’s network of liberty agenda. In 2021, the FS announced that we will put women and girls front and centre of foreign and development policy. In order to align and respond to current Ministerial priorities, LNOB will ensure that data on all components will be disaggregated by sex and disability status to track results. Furthermore, the UK made a commitment during the recent 2022 Global Disability Summit - hosted by Norway and co-hosted by Ghana to ensure we strengthen consultations with Organisations of Persons with Disabilities (OPDs).- As a result of this commitment, LNOB will consult with Women’s Rights Organisations (WROs) and Organisations of Persons with Disabilities (OPDs) to strengthen their voices and agency in order to unlock the freedoms of marginalised and vulnerable groups to empower them to identify sustainable solutions. LNOB is still able to deliver despite reduced budgets in relation to support through the World Bank Trust fund and Options. In relation to social protection, we are supporting the operationalisation of LEAP and emergency cash transfers under UNICEF as well as providing TA to the MoGCSP to support the passage of the social protection bill and to increase budgetary allocation on social protection.

Due to the Country Business Planning process, it is still unclear which aspects of our programming will be prioritised. As such, we may need to reassess the following recommendations once there is more clarity to determine priorities for the coming FY:

Safeguarding review - There’s evidence to suggest that COVID-19 has increased safeguarding risks among the vulnerable. A key recommendation from the previous AR was for LNOB to conduct a Safeguarding review to assess compliance among implementing partners and downstream partners in relation to human rights violations in the overall disability/Mental Health component specifically regarding Sexual, Exploitation, Abuse and Harassment (SEAH) in view of COVID-19 and increasing safeguarding risks among the most vulnerable. A key recommendation for the year ahead is for LNOB to work closely with implementing partners to prioritise key recommendations from the report findings to address gaps in their safeguarding frameworks. This includes strengthening spot checks and monitoring and ensuring guidance is provided to mitigate against any safeguarding risks (Q1 and Q2)

Whole VfM framework - Whilst work on this commenced in 2021 and guidance provided by the FCDO economist, progress has stalled. This was as a result of the ODA cuts and reprioritisation and due to the reprogramming of LNOB. As such, there wasn’t as much progress on this recommendation as initially anticipated. Previously, implementing partners took a siloed approach and only provided VFM frameworks for their respective components. However, having understood the reasons for an overarching VfM framework, they have agreed to work together to develop a whole LNOB VfM framework. The LNOB will work with implementing partners to draw up and agree VfM indicators focusing on the 4Es (economy, efficiency, effectiveness and equity) with appropriate benchmarks and monitoring framework to facilitate future VfM analysis. (Q1)

Governance arrangements - FCDO to continue to lead on coordination with implementing partners with Options providing logistical support for the High-Level Steering Committee (HLSC) meetings. LNOB to strengthen collaboration with Ministry of Health and explore ways to engage more closely around Universal Health Care and Mental Health overall goal of ensuring 80% coverage of Ghanaians having access to essential health services – this includes a target of reducing by one-third Mental Health (Q1).

COVID 19 vaccination messaging - LNOB has made progress in terms of integrating COVID-19 messaging into programming (e.g. through UNICEF’s communications for Development unit as well as SHGs to raise awareness on COVID-19 vaccines among the vulnerable in Ghana. A key recommendation would be to engage the Health Advisor in identifying, assessing and tracking areas in the LNOB programme where strengthened work to address vaccine hesitancy is required. FCDO will continue to work with implementing partners to increase COVID-19 vaccination messaging into communications and disability and Mental Health outreach activities. Particular focus will be on persons with disabilities and Mental Health conditions, women and the elderly. This will help to determine the different concerns from different groups in relation to vaccine uptake and to find ways these concerns can be addressed (Q1 and Q2).

Vulnerability & Exclusion (V&E) assessment findings - LNOB to use V&E assessment findings to inform policy and programming and to share findings with partners and provide guidance and influence multilateral and GoG on the recommendations provided (Q1)

Strengthening multilateral collaboration LNOB to establish closer collaboration with multilaterals (WB and UN agencies) to strengthen areas of synergies and to develop a joined-up advocacy plan and influencing strategy. Due to the reputational impact caused by ODA cuts we intend to work closely with multilaterals in order to strengthen collaboration and mitigate risks, Specifically, we will explore opportunities to strengthen our work on gender equality and social inclusion (Q1 and Q2).

Self-reliance and Sustainability – a key Ministerial priority is to promote self-reliance through sustainable growth, stability and poverty reduction. Over the next year, FCDO will need to consider the Business Case and plans to transition Ghana out of aid into self-reliance and, our ambitions in relation to e.g., supporting the social protection sector and the role we will play (if any) in addressing Ghana’s acute humanitarian needs as well as promoting the investment case for increased domestic financing of Mental Health (Q2 and Q3).
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s Theory of Change (ToC), including any changes to outcome and impact indicators from the original business case.

In 2021, in order to address key recommendations, set out in the 2020 AR, implementing partners conducted a general review/ stocktake of the programme to assess where the programme is most/least effective and where others, including GoG, could step up to cover the gaps. This also included a review of the ToC to ensure the programme was still on track and to ensure the assumptions still hold. During the review, implementing partners found that whilst COVID-19 and the ODA cuts would impact programme delivery of immediate outcomes, the overall LNOB programme was still on track to achieve longer term outcomes and impact and that the assumptions still held true. The review took place on 27th October 2021, in consultation with implementing partners during the LNOB Technical Sub-Committee Meeting where they assessed the programmes level of ambition and its ability to effect change.
As a result of the COVID-19 pivot in 2020, revisions were made to the LNOB logframe and ToC. and a Submission was approved setting out the revisions in relation to: 1. Conducting a V&E assessment to support the GoG’s V&E Strategy 2. New COVID-19 support to UNICEF, Options and LEAP emergency cash transfers. The most significant change was to the World Bank Trust Fund. This was to reallocate funds from Productive Financial Inclusion (PFI - all of our £5m) and Ghana National Household Registry (GNHR £2.5m - half of the original allocation) towards emergency cash transfers. This allowed the temporary expansion of LEAP. While FCDO Ghana are no longer funding PFI, the European Union has helped to bridge the funding gap along with World Bank. Further revisions were made to the LNOB logframe and ToC in 2021 to reflect changes made to the LNOB programme as a result of ODA cuts.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Despite the ODA cuts in 2021 and significant changes to the programme, the LNOB programme remains relevant in the face of COVID-19 as a vehicle supporting GoG to respond to some of the acute need arising from the pandemic while still retaining the focus on programme target groups and in 2020/21 expanded its reach to include even more vulnerable and excluded groups. These included: street children, Kayayei (adolescent girls selling in markets), flood victims, homeless, persons with disabilities and elderly women in witches camps. The modality of expanding support to this group brought up new challenges e.g. difficulties in supporting groups which are transient and outside of households as well as new challenges in terms of shifting to a new payment system e.g. mobile money. Under the Mental Health components, significant achievements have been made in key delivery areas, and some progress has been made establishing robust and joined up Mental Health and social protection systems. Due to the ODA cuts several milestones were not measured (including regular cash transfers, shock responsive social protection, GNHR, TA to MHA) during the reporting period. However, on the whole identified milestones at both the output and outcome level are largely being achieved, the programme is on track to deliver against expected outcomes and impact. LNOB continues to contribute to outcomes on social protection through its support to the Ministry of Gender, Children and Social Protection (MoGCSP). In relation to Mental Health, the programme continues to occupy a need in Mental Health that is not being addressed by other development partners, and the theoretical justification for the wider programme and its constituent parts continues to be affirmed by implementing partners and stakeholders.

Whilst the ODA cuts to the GPSNP under the World Bank Trust Fund in 2021, affected the delivery of social protection components under that mechanism, through UNICEF under the Synergy Fund, FCDO continues to deliver operational support to enable the delivery of emergency cash transfers via mobile money as well as providing TA through UNICEF to support policy actions for social protection. As such, FCDO continues to provide support to the social protection sector as well as participating in quarterly Social Protection Sector Working Group meetings and monthly Social Protection Development Partner meetings. The Business Case (BC) emphasises that UK funding would gradually reduce funding to cash transfers over time and increasingly focus on system strengthening to help people out of poverty as part of a responsible exit. However, due to COVID-19, funds for systems strengthening were reallocated to emergency cash transfers in response to an urgent request by GoG to respond to C19. At that time, LNOB was the only mechanism in place for reaching the excluded and most vulnerable.

Whilst this took the programme slightly off track, COVID-19 and the ODA cuts highlighted the fact that external donor finance and technical assistance is still required to meet the most immediate needs e.g. emergency cash transfers as well as shock responsive social protection to build a more resilient social protection system to not only respond to COVID-19 but to other shocks e.g. floods, droughts etc. Over the next year, FCDO will need to consider the Business Case and plans to transition Ghana out of aid into self-reliance and, our ambitions in relation to supporting the social protection sector and the role we will play (if any) in addressing Ghana’s acute humanitarian needs.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

LNOB’s implementing partners and stakeholders continue to affirm that the LNOB programme is needed now more than ever to respond to and address some of the challenges of the most vulnerable and marginalised in Ghana. LNOB fits with current Ministerial priorities in relation to women and girls and towards promoting self-reliance through sustainable growth, stability and poverty reduction The UK continues to be a trusted partner having had a longstanding relationship with the GoG and has providing many years of valuable TA expertise and financial aid to the social protection sector. Furthermore, as the only significant donor supporting Mental Health in Ghana, the UK continues also adds value in terms of scaling up delivery of quality and integrated Mental Health services, particularly at the primary health care and community level, providing grants to civil society organisation (CSOs) and Disabled Peoples Organisations (DPOs) to support community-based rehabilitation and support anti-stigma campaigns. However, despite the current need, the programme will need to take into consideration the potential for further reductions and reprioritisation in the next FY.

The LNOB is unique as it brings together two sectors – health and social protection – convening a wide range of actors who would not otherwise work closely together on these issues e.g. MoGCSP, Ministry of Health (MoH) and the Ministry of Local Government and Rural Development (MoLGRD). The bi-annual LNOB High Level Steering Committee meeting and quarterly LNOB Technical Sub-Committee meetings, provide platforms for implementing partners to engage in one space to strategise and to consider achievements, challenges and risks within the programme and to explore ways to strengthen synergies and linkages.

During the LNOB technical sub-committee meetings, implementing partners are able to drill down into technical issues e.g., to review, interrogate and revise ToCs, logframes and assess annual workplans. Due to COVID-19, the programme was able to pivot to respond to immediate needs of the most vulnerable in alignment with GoG’s COVID-19 response. Despite the cuts in 2021, the programme is still able to demonstrate impact in the lives of the most vulnerable and marginalised in Ghana which provides a strong justification for the continuation of the programme.

Yet, there is still room for the programme to improve and to become more transformational. In line with FCDO’s “force for good” and in order to build on our past investments on poverty, gender and disability, we will strengthen diplomacy and advocacy opportunities with implementing partners to strengthen our work on gender equality and social inclusion – we will also work closely to influence multilaterals such as the World Bank, and UN agencies in Ghana.

The programme components continue to represent good Value for Money (VfM) and programme level outcomes are still achievable and realistic despite the ODA cuts. The LNOB Business case recommends that VfM indicators should have been agreed during the programme inception phase with all partners. Although each implementing partner has separate VfM indicators in place for different components of the programme, work is on-going to develop an overarching VfM strategy with indicators. Once finalised, the overall VfM of the programme will mean that at the effectiveness level the programme will be more easily assessed.

The key cost drivers indicated in the Business Case, are expected to remain the same. The main ones include emergency cash transfers; Results-based non-budget support financial aid; Mental Health and disability work (grants to NGOs/CSOs/DPOs, community-based rehabilitation services, empowerment and capacity building interventions, anti-stigma and discrimination activities) by Options through Ghana Somubi Dwumadie; TA support; as well as funding to WHO and UNICEF.

## C. DETAILED OUTPUT SCORING

Output Title	Improved policy, leadership, resources and governance systems that recognises and respects the human rights of the extreme poor and marginalised, including all people with disabilities and Mental Health conditions.
Output number:		1	Output Score:	B
Impact weighting (%):		15%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1.Extent to which intersectoral monitoring and accountability mechanisms strengthen GoG systems delivering Mental Health services and disability inclusion	(a) Nominations received for MH Tribunal in agreed pilot areas. (b) Nominations received for MH Visiting Committees in agreed pilot areas	(a) Achieved (b) Partially Achieved
1.2 % of LEAP beneficiaries selected using Ghana National Household Registry (GNHR) data. Results disaggregated by gender and disability status.	Not applicable	This milestone has been removed and will not be assessed a funding to the World Bank Trust Fund for this financial year has been cut.
1.3 Level of implementation of Government's Vulnerability and Exclusion (V&E) Strategy	The V&E assessment completed, report to be validated and recommendations to inform MOGCSP’s action plan	Partially achieved – due to be assessed in March
1.4 Level of Technical Assistance to Ministry of Gender, Children and Social Protection to strengthen social protection system and implement, map and coordinate COVID-19 activities and advocate for increased resources.	a) Technical assistance provided to the provision of COVID-19 Relief Transfers to at least 75,000 vulnerable individuals. b) Data and lessons learned from COVID-19 SP response are documented.	(a) Partially achieved by 64, 319 (b) Achieved
1.5 Extent to which the Legislative Instrument (LI) of the Mental Health Act (846) and national Mental Health policy established and guide implementation of Mental Health services.	All the necessary documentations regarding the Mental Health Regulations, 2019 (L.I. 2385) sent to Parliament for approval.	Achieved

Briefly describe the output and provide supporting narrative for the score.

This output has been scored at A. It measures work done by the Mental Health Service Provider – Options and the Consortium, UNICEF’s V&E and TA to MoGCSP and the operationalisation of LEAP, and the Mental Health Authority (MHA’s) progress on Results Based Aid (RBA) indicators.

Indicator 1.1 Extent to which intersectoral monitoring and accountability mechanisms strengthen Government of Ghana systems delivering Mental Health services and disability inclusion.

There are two milestones under output indicator 1.1 for this review period and these are “Nominations received for Mental Health Tribunal in agreed pilot areas” and “Nominations received for Mental Health Visiting Committees in agreed pilot areas”.

Nominations received for Mental Health Tribunal in agreed pilot areas:
The UK Government through the FCDO Ghana Somubi Dwumadie (Ghana Participation) project committed to providing technical support to the Mental Health Authority to establish and operationalise Mental Health Review Tribunal to function in accordance with the Mental Health Act 2012 to ensure that the human rights of persons with mental illness are protected.

Significant progress has been made with this commitment and the milestone has been achieved. Coordinated efforts between consortium members of the Ghana Somubi Dwumadie project (Options, Sightsavers and Tropical Health) led to the selection of three pilot regions, Ashanti, Central and Greater Accra Regions, focusing on locations with psychiatric hospitals or departments within hospitals. Nominations received for the Mental Health Review Tribunal included 1 from each of the regions for the chairperson position; 8 nominations from the Psychiatrists Association for all regions; 2 from Psychologists Association for all regions; 4 for service users; and 7 from the Mental Health Nurses group for all regions.

(b) Nominations received for Mental Health Visiting Committees in agreed pilot areas:

The Mental Health Regional Visiting Committees play human rights roles and supplement the work of Regional Coordinators by inspecting locations that persons with Mental Health conditions are kept - formal and informal settings (psychiatric hospitals and prayer camps). 5 piloted regions had been focused, Ashanti, Central, Upper East, Western and Greater Accra Regions. Some progress had been made in the formation of the Mental Health Visiting Committees - milestone was partially achieved. The milestone was not fully achieved because the nominated Visiting Committees members were yet to be validated and out-doored.

Indicator 1.3 - Vulnerability and Exclusion (V&E) Assessment. UNICEF commissioned ODI to conduct a V&E assessment to analyse the primary drivers of social vulnerability and exclusion in Ghana, examine coping mechanisms used by vulnerable groups, assess the access and responsiveness of social protection programmes and key social services (education and health) provided by the government and other providers in addressing key vulnerabilities and to provide recommendations and policy options to address existing gaps. There were initial delays in the commencement of the assessment due to COVID-19. In mid-March 2021, an inception meeting and the final inception report were completed. Later on in 2021, UNICEF made further progress by engaging members of the V&E technical steering committee to provide technical backstopping and to quality assure products from the research institution during a workshop to elicit current understandings of vulnerability and exclusion amongst active practitioners in Ghana. This milestone was partially achieved – the analysis and revision is ongoing. The report is expected to be released in March 2022. Findings are expected to be shared with the V&E technical steering committee to be followed by a validation workshop and then finalisation of the report in collaboration with MoGCSP and with support from FCDO.

Indicator 1.4 - Technical assistance for COVID-19 support and data and lessons learned – Section A of this milestone provided technical assistance for COVID-19 Relief Transfers to at least 75,000 vulnerable individuals – this milestone was partially achieved. UNICEF provided technical operational support to LEAP in areas of planning, payroll, reconciliation, communication, and monitoring. Furthermore, UNICEF supported LEAP in testing out new approaches to communication and monitoring and evaluation by using free SMS-surveys via its RapidPro platforms, through 6 rounds of brief surveys to recipients. In addition, UNICEF provided technical assistance and the operationalisation of LEAP and d COVID-19 emergency cash transfers. As of February 2022, 64,319 individuals had received emergency cash transfers all of which had been supported through TA from UNICEF.

Section B of this milestone focuses on documenting data and lessons learned from COVID-19 SP response – this was achieved. Within the review period in order to promote evidence sharing and lesson learned, qualitative research on the impact of COVID-19 on children and families in Ghana was undertaken and documented in conjunction with the Social Policy Research Institute. Together with the World Bank and government partners, UNICEF is discussing the way forward to document operational procedures developed, further assess some specific areas, and document lessons. Concrete next steps include a ‘retreat’ on payments related issues, a process evaluation of emergency transfers, and an overall SP systems preparedness assessment. The intention is for these processes to feed into efforts to strengthen shock responsiveness of Ghana’s Social Protection System, including development of a government roadmap.

Indicator 1.5 - Extent to which the Legislative Instrument (LI) of the Mental Health Act (846) and national Mental Health policy established and guide implementation of Mental Health services.
The milestone for this indicator during the review period was to have all the necessary documentations regarding the Mental Health Regulations, 2019 (L.I. 2385) sent to the Parliament of Ghana for approval. Following the passage and approval of the Mental Health Regulations (L.I.2385) in July 2019, some errors were found in the document and that necessitated the correction. In this regard, reports of meetings held between Mental Health Authority, Ministry of Health and Attorney General’s Department regarding Mental Health Regulations, 2019 (L.I.2385) were submitted to the parliament of Ghana through the Attorney General’s Department. Second, the Ministry of Health submitted the corrected regulations including re-designed forms to the Parliament of Ghana through the Attorney General’s Department. Third, the Attorney General’s Department submitted the finalised Regulations to the Parliament of Ghana for approval in January 2022. While the milestone was achieved, the finalised Regulations are yet to be approved by the Parliament of Ghana.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

Whilst each implementing partner has developed their own VfM framework, there are no specific VfM metrics relating to this output in the business case. There are clearly strong VfM implications for the programme outcomes stemming from this output. The ability of long-term ability and commitment of GoG to respond effectively and inclusively to the issues the programme is addressing will be strengthened by the systems and legislation supported by the activities described.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The weighting of the output was raised from 10% to 15% during the 2020 AR period as a reflection of the increasing importance of systems building. This increase remains relevant during this AR period. Due to ODA cuts, revisions were made to the logframe to reflect outputs which were affected.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

During the period in review, due to cuts to our support to the World Bank Trust Fund, recommendations focused on engaging WB to support MoGCSP to set out a clear plan for GNHR did not materialise. Due to the cuts, FCDO’s main focus during 2021 was to mitigate potential reputational and delivery risks. We were successful in doing this by virtue of the strong relationship which had already been established with the World Bank and we were able to engage in dialogue which resulted in the restructuring of the GPSNP. During the review period, we also worked closely with the World Bank team at the centre to cascade messaging and engaged closely with other country teams who experienced cuts to their support to the World Bank Trust Fund. FCDO continued to engage with the World Bank through the Social Protection Sector Working Group meetings, Social Protection Development Partner meeting, Gender Sector Working Group (GEST) meetings. FCDO’s relationship with the UN and the broader UN family strengthened during 2021. This was as a result of closer collaboration on key areas of engagement e.g., V&E assessment, Integrated Social Services. There are plans for FCDO and the UN to hold quarterly meetings to explore areas of synergies and ways to strengthen collaboration going forward and to develop joint advocacy plans.

However, last years’ recommendation to ensure clear division of focus between LNOB and Partnerships Beyond Aid (PBA) was achieved. During the review period, both LNOB and PBA teams had discussions about the work being done with e.g., UNICEF as well as STAR in relation to CSOs in order to ensure there was a clear division of focus between programmes. Another key recommendation from the last AR was to use the V&E assessment report to engage multilaterals and GOG in implementing the findings. The report will be released early this year and there are plans for various dissemination workshops with multilaterals and with GoG to ensure the recommendations are taken on board.

Furthermore, in relation to key lessons learned during the review period in terms of UNICEF’s technical assistance for COVID-19 support, is the need to strengthen coordination and monitoring at all levels to ensure effective targeting and distribution of support items and to avoid double targeting and duplication. UNICEF’s report found that there was limited communication prior to the distribution of COVID-19 items and beneficiaries were not always informed of the form of support they were entitled to. In addition to that, another key lesson learned was for Development Partners (DPs) to provide support to GoG to ensure there is up to date data on poor and vulnerable households as a preparedness measure and underscore the need for a national emergency plan to aid a coordinated response in the future. Finally, coordination between various actors – public, private, CSOs etc is critical especially to delineate roles and leverage on mandates for an effective collaboration approach in COVID-19 and other emergencies.

Recommendations for this year:

LNOB to use V&E assessment findings to inform policy and programming and to share findings with partners and provide guidance and influence multilateral and GoG on the recommendations.

LNOB to establish closer collaboration with multilaterals (World Bank (WB) and UN) and to explore areas of synergies and to develop a joined-up advocacy plan and influencing strategy

To ensure strengthened engagement in Social Protection Sector Working Group meetings as well as Social Protection Development meetings to engage with GoG and other key agencies, CSOs, NGOs and private sector to align plans in order to avoid duplication and ensure more effective collaboration during COVID-19 and in other emergencies.

Output Title	Effective cash transfers payments and operational modalities are delivered to extreme poor and vulnerable and marginalised households on a transparent, accountable and sustainable basis
Output number:		2	Output Score:	B
Impact weighting (%):		35%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of beneficiaries accessing timely LEAP cash grant (results disaggregated by gender and disability status).	This milestone will not be assessed because funding to the WBTF was cut for this FY	N/A
2.2 Level of implementation of the Social Welfare Case Management and referral and reintegration system in 50 districts in Ghana including number and b) percentage of LEAP beneficiaries with active NHIS membership	50% of LEAP individuals with active NHIS cards	Exceeded - 78%
2.3 Level of implementation of the Shock Responsive Social Protection Emergency Early Warning System	N/A	This milestone will not be assessed as funding to the WB Trust Fund was cut for this FY
2.4 Number of LEAP beneficiaries enrolled onto the Productive Inclusion and accessing financial services (start-up grants) – complimentary livelihoods asset support scheme (CLASS) including % of women and persons with disabilities and Mental Health conditions – results disaggregated by gender and disability status.	N/A	This milestone will not be assessed as funding to the WB Trust Fund was cut for this FY

Briefly describe the output’s activities and provide supporting narrative for the score.

The output score is B. It measures against work carried out by UNICEF on Integrated Social Services components including Social Welfare Case Management and referral and reintegration systems.

Indicator 2.2 – Integrated Social Services (ISS) - Social Welfare Case Management - There has been good progress in the development of the social welfare and case management system by UNICEF. In 2021, the implementation of ISS has been scaled up to 100 MMDAs, including 50 MMDAs with support from FCDO, who are now coordinating activities with social welfare, LEAP, health insurance, health services, planning, local government, and finance at national and sub-national level. Through the ISS initiative, the Government of Ghana has made budgetary allocation to the 100 districts in the ISS for social welfare services in the 2022 national budget, with plans to expand to an additional 60 MMDAs in 2022. The ISS Initiative has had promising initial results and has benefited from continued innovation in tools and mechanisms to increase access of vulnerable children and households to multiple social protection, child protection and health services. In 2021, 30,423 children benefitted from integrated case management services across 100 districts. Of these, approximately 74% (22,639 children including 12038 girls and 10601 boys) accessed social protection support while 7,784 children (4,355 girls, 3,429 boys) subjected to sexual and physical violence received multi-sectoral case management services.

UNICEF has supported extensive National Health Insurance Scheme (NHIS)-LEAP dialogues on developing a strategy for further increasing enrolment, simplifying renewal, innovating protocols, and data-sharing to ensure that as many LEAP beneficiaries as possible also have access to free health insurance. There are now discussions ongoing for the extension of validity of cards for indigents beyond one year. However, the important successes the LEAP-NHIS linkage has seen, these need to be capitalised on to ensure that they are sustained. By the end of the 2021, it was recommended that the ISS formalise LEAP-NHIA protocols for enrolment and renewal. Free enrolment onto the NHIS for LEAP has increased by 5% in new enrolment. As of November 2021, 1,190,402 individuals (representing 78 percent of all LEAP beneficiaries) were enrolled on NHIS and all have active NHIS cards. This milestone was exceeded.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year]

The output continues to represent VfM, particularly at the economy and efficiency levels. The issue of appropriate targeting is a large driver of effectiveness, so the new 125,000 individual beneficiaries reached through emergency cash transfer payments further highlights the effectiveness of targeting the most vulnerable. The programme achieved efficiency in a number of ways. The onset of COVID-19 brought to the fore the need for flexibility in implementing projects. Specifically, the use of electronic and other virtual means of communication and monitoring project activities has proven to be efficient and cost effective. Throughout 2021, the programme deployed innovative approaches including the use of mobile money to reach new beneficiaries. As such, beneficiaries were reached rapidly and in greater numbers e.g., with emergency transfers, communication, and monitoring. The use of innovative technology during the COVID-19 pandemic was also effective in reducing the spread of the virus as well as the numbers of beneficiaries having to carry large sums of cash – this approach saved time and reduced fiduciary risks.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

In May 2021, FCDO informed implementing partners of cuts to the UK’s Official Development Assistance (ODA). The ODA cuts were brought about as a result of the impact of COVID-19 on the economy required the UK Government to take a difficult decision to announce a reduction in the UK’s global ODA budget from 0.7% to 0.5%. Thereafter, FCDO undertook an internal business planning process to reprioritise the reduced ODA budget for 2021/22 in accordance with UK strategic priorities.
As a result of this, there were cuts to the LNOB programme in 2021. This meant cutting the entire projected funding to the World Bank Trust fund to the tune of £4.5m. Therefore, during 2021 there was no further support towards regular cash transfers and shock responsive social protection.
During FY2020/21, emergency cash transfers were due to be paid to 125,000 individual beneficiaries. Payments were disbursed in instalments from December 2020 and have been rolling out on an ongoing basis. However, during the time of the last AR, not all 125,000 emergency cash transfers were paid – yet LMS/World Bank had indicated that all 125,000 individuals had been paid and that the milestone had been achieved. The original milestone for this FY was reached but this milestone is carried over from the previous year which has affected the overall progress of this output. As such this milestone cannot count as being fully achieved. This component should have been incorporated into our milestones for this FY but at the time, the programme was facing significant challenges and risks. There were reputational risks as a result of the cuts to the World Bank Trust fund which threatened the relationship between FCDO and the MoGCSP. Whilst FCDO Ghana worked hard with FCDO team at the centre to mitigate these reputational risks, there were inevitable tensions between FCDO and the World Bank as a result of the cuts which put a strain on the relationship. In terms of delivery risk, there were delays in disbursing the emergency payments due to the 2020 December elections and political transition. In addition to that there was a leadership vacuum at the MoGCSP resulting in a slow burn rate of project funds. This led to the non-renewal of consultant contracts and non-approval of service contracts. All of these issues adversely impacted the delivery of programme activities in 2021. Development partners, including WB and UNICEF, are continuing to follow up with the MoGCSP and have also written to the Ministry of Finance to ensure the speedy renewal of consultant contracts for the smooth and timely implementation of emergency cash transfers and other social protection activities. By March 2021, a total of 54,088 beneficiaries had been paid in Tranche 1 and 9,441 in Tranche 2. According to LMS and UNICEF, the final payment is still in progress and is expected to be completed in 2022.
In August 2021 LNOB logframe was revised to reflect these changes e.g., in 2021/22 milestones for GPSNP programme activities. As part of the 2020 Annual Review recommendation, the ToC was revised to be linked more closely to the logframe. The ToC will continue to be assessed to ensure that the necessary adjustments are made to reflect expected progress towards the outcomes and impacts of the programme.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The AR recommendation for 2020 prioritised risks around safeguarding and requested that LNOB works with World Bank to ensure that recommendations on safeguarding are actioned. This included ensuring that the issue of safeguarding was a standing item at the High-Level Steering Committee (HLSC) meeting. LNOB were able to highlight the issue of safeguarding risks in terms of the WB’s new GPSNP 2 programme and also in terms of key actions for the Rapid Scoping Study on LEAP action plan. The issue of safeguarding and subsequent review by SDD was highlighted in the HLSC meeting held in April 2021 and subsequently during the LNOB Technical Sub-Committee meeting in October 2021.
The previous AR recommendations also included a focus on setting key priorities around strengthening coordination and building synergies between the various LNOB implementing partners. With reduced funding now more than ever it is critical to coordinate more closely with partners. There were also specific recommendations around strengthening governance and coordination and reporting arrangement with implementing partners. In terms of governance, there were recommendations for FCDO to lead on coordination with implementing partners with Options providing support logistics for HLSC. During the HLSC in April, FCDO were able to lead the coordination and engagement of implementing partners. This approach was welcomed by implementing partners and helped to strengthen synergies and linkages among partners and across LNOB programme components.
Finally, the previous AR recommendation highlighted the need for improvements in terms of version control in relation to the LNOB logframe as well as reporting timelines. Within the period in review, the logframe has been revised and version control addressed, the overall reporting has been regular. However, there were delays in receiving the Q4 report from the World Bank – this is due to challenges in large part caused by slow or non-approval of activities on the side of MoGCSP as a result of absence of project staff whose contract have not been renewed.
Recommendations for this year:

FCDO should work closely with LEAP Management Secretariat (LMS)/MoGCSP to address key delivery risks including the challenges delaying the disbursement of emergency cash transfers and to look for ways to mitigate the various delivery risks. This includes strengthening monitoring of subsequent emergency payments and engaging Ghana Interbank Payment and Settlement Systems Limited (GhiPPS) to provide a cash withdrawal report / mobile money account statements as a second level of authentication to confirm cash credit and / or withdrawal status.

FCDO to work with partners to explore other innovative monitoring measures e.g., using interactive voice messaging in addition to SMS in communicating and monitoring of emergency payments with beneficiaries.

In an effort to strengthen governance arrangements and coordination with implementing partners, LNOB should engage more closely with Ministry of Health to ensure Mental Health becomes a priority issue on the Ministry of Health’s agenda as part of its focus on Universal Health Coverage (UHC). E.g., FCDO will work with the Ministry to host the bi-annual HLSC in 2022 and to strengthen dialogue on Mental Health and UHC. This platform will also be used to make an investment case for GoG to increase domestic resources into Mental Health.
Output Title	Increased access to quality integrated, disability inclusive community based and recovery oriented Mental Health and other health services including services delivered by traditional and faith-based leaders
Output number:		3	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Extent of implementation of Quality Rights Initiatives in health facilities.	Improvement plans implemented and re-assessment conducted.	Achieved
3.2 GoG procurement of psychotropic drugs and availability of psychotropic drugs at all levels.	Distribution of Medicines bought in 2020 completed.	Achieved
3.3 Number of persons with disabilities including Mental Health conditions and other vulnerable groups benefiting from community-based initiatives including through civil society and Self Help Groups (SHGs).	(a) 4,000 people benefitting from COVID-19 psychosocial resilience support (b) 560 people benefiting from continued SHG activities (28 SHGs strengthened) (c) Revised DACF guidelines recommended to Office of District Common Fund Administrator (d) 6400 people benefiting from Evidence and Effectiveness Grants (Ref: GSD Output Indicator 2.3)	(a) Exceeded – 16.052 (b) Exceeded - 637 (c) Partially Achieved (d) Achieved
3.4 Number of persons with disabilities including Mental Health conditions and other vulnerable groups benefiting from COVID-19 support.	N/A	This milestone has been finalised and has now been closed.

Briefly describe the output’s activities and provide supporting narrative for the score.

The output score is A. It measures against work to increase quality integrated disability inclusive community based Mental Health services.

This milestone was achieved during the period under review. Following the training of a pool of facilitators on Mental Health service improvement plans that was organised in April 2021, two (2) psychiatric hospitals and five (5) General Hospitals with psychiatric units were supported to develop service improvement plans based on a gap analysis using the WHO QualityRights toolkit. These facilities are currently implementing service improvement plans in line with person-centred and human rights-based approaches. There are dedicated teams that ensure systematic guidance and monitoring of the service improvement plans’ implementation in each facility. An ex-post assessment of the facilities’ progress vis-à-vis the improvement plans expected to be undertaken six months after the improvement plan development workshop, was completed in September 2021 - this is due to take place in March 2022.
 Indicator 3.1 Extent of implementation of Quality Rights Initiatives in health facilities.

Indicator 3.2 Government of Ghana procurement of psychotropic drugs and availability of psychotropic drugs at all levels.
The aim of this indicator is to provide quality and affordable psychotropic medicines at all levels of care for the management and treatment of persons with psychosocial, intellectual, and cognitive disabilities, in line with appropriate prescribing practices and procurement procedures. The milestone is to have completed the distribution of medicines bought in 2020, and that milestone was achieved. Eight hospitals (Accra Psychiatric, Ankaful, Komfo Anokye, Korle Bu, Ho, Tamale and Cape Coast) received various quantities of 28 different psychotropic drugs as part of the 2020 procurement. Ten of Ghana's 16 regions (Western, Greater Accra, Volta, Oti, Central, Eastern, Northern, Ashanti, Upper West and Bono), also received 19 different psychotropic drugs during the period.

The MHA used the Ministry of Health procurement systems to complete the 2020 procurement cycle and subsequently distributed the psychotropic medicines to the respective psychiatric hospitals and regions. The rationale was to ensure that psychotropic medicines became part of the Ministry of Health Logistics Management Information System for sustained supply of the medicines even after the UK Government support.

Indicator 3. 3 Number of persons with disabilities including Mental Health conditions and other vulnerable groups benefiting from community-based initiatives including through civil society and self-help groups.

This indicator is made up of four milestones focusing on different thematic areas under the Ghana Somubi Dwumadie:

4,000 people benefitting from COVID-19 psychosocial resilience support
This milestone exceeded expectations during the period under review. 16,052 people benefitted from the COVID-19 Psychosocial and Resilience grants, that is about four times the targets for January 2022. This was an unintended benefit which was achieved by grantee partner Christian Health Association of Ghana (CHAG) who cascaded training and psychosocial support to stakeholders in response to the Apam drowning emergency which took place on 8th March 2021.

560 people benefitting from continued Self Help Group activities (28 Self Help Groups strengthened)
The target was to reach 560 Self Help Group members but as of the end of January 2021 about 637 people from 27 Self Help Groups received training to increase their knowledge and awareness about the existence of a COVID-19 vaccine. This means the programme exceeded the target for this milestone. In addition, members of Self-Help Groups, particularly the leaders were provided with basic knowledge on record-keeping. The groups were also introduced to the concept of safeguarding and the procedure for reporting a safeguarding concern using the Ghana Somubi Dwumadie safeguarding framework.

Revised District Assembly Common Fund guidelines recommended to Office of District Common Fund Administrator
The Republic of Ghana adopted the guideline for the disbursement and management of District Assembly Common Fund Disability Fund in 2010. There have been a lot of changes since its adoption, and these include institutional re-organisation and global commitment by the Government of Ghana. This called for a review of the guideline to make it consistent with the current structural environment, and review changes consistent with Ghana’s global commitments on disability. In furtherance of this, the UK Government through the Ghana Somubi Dwumadie programme provided technical support to the Ghana Federation of Disability Organisations to undertake an evidence-based review of District Assembly Common Fund Disability Fund disbursement and management guidelines. While substantial progress had been made for this milestone, the target was partially achieved because a planned national workshop to adopt the revised District Assembly Common Fund Disability Fund and Disbursement guideline originally scheduled to take place on 25 January 2022 could not happen due to strike action by a section of public sector workers in Ghana.

6400 people benefitting from Evidence and Effectiveness Grant
This milestone was achieved. The target was to reach 6,400 people under the Evidence and Effectiveness grants but 6,913 people were reached. The Evidence and Effectiveness grants were awarded to nine grantees in April 2021 under the Ghana Somubi Dwumadie programme. The grants comprised of five small grants and four large grants. The organisations that received the grants are ABAK Foundation, Hope for Future Generation, VOICE Ghana, CALID Ghana, Centre for Peoples Empowerment and Rights Initiative, Ghana National Association of the Disabled, FOCEP Ghana and Songtaba Ghana.

VfM

WHO Quality Rights e-training on Mental Health, human rights and recovery, was successfully rolled out nationally among service providers, health & non-health professionals, families, faith-based organisations, people with lived experience, NGOs, DPOs & wider community. Using the QR e-training platform, beneficiaries are now reached swiftly and efficiently. Furthermore, costs have been saved through e-training as it reduces printing of manuals, travel costs as well as lower procurement costs with the use of local Consultant. These are low-cost strategies that enable high reach and large impact.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

In the last AR, the weighting revised up to 20% from 15%. This has not been revised in this AR. During the review period, the WHO no-cost extension was approved to extend their agreement for a further 6 months in order to complete outstanding programme activities, impacted by COVID-19 by June 2022.

A key recommendation from last year’s AR was to urgently review Quality Rights Assessments of facilities in light of safeguarding concerns. In 2021, the LNOB programme began conducting a safeguarding review on 5 implementing partners including WHO. This concern has been flagged and will be review during the review and recommendations taken forward.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

A key recommendation from the previous AR was to for LNOB to urgently review Quality Rights assessments of facilities in light of findings on possible safeguarding concerns Following these concerns, LNOB conducted a safeguarding review in 2021 – which is currently ongoing. LNOB will ensure that recommendations from the findings are taken forward to mitigate safeguarding risks.

LNOB ensured that safeguarding was a key priority in the review period. As such LNOB commissioned SDD to undertake a Safeguarding review to assess compliance among 5 implementing partners and downstream partners. This was in relation to SEAH in view of COVID-19 and increasing safeguarding risks among the most vulnerable.

- In terms of progress, the review is now well underway. Desk review of documents from 5 of LNOB’s implementing partners (WHO, MHA, Options, Basic Needs and LEAP Management Secretariat (LMS) has been carried out, the staff survey has been completed and the FGDs with staff and service users is currently underway. Thereafter, the SDD project team will provide a report with findings on the strengths and gaps in LNOBs safeguarding framework and implementation and provide a roadmap of recommended and prioritised actions and 30 days of technical assistance.
- A key recommendation for the year ahead would be for LNOB to ensure that recommendations from the safeguarding review are prioritised by LNOB implementing partners and downstream partners. This includes ensuring implementing partners and downstream partners receive periodic and ongoing training on safeguarding – particularly on SEAH.

Furthermore, in light of findings on possible safeguarding concerns in 2021, the programme needs to increase spot checks and monitoring and ensure guidance is provided to mitigate against any safeguarding risks.

Output Title	Attitudes, behaviours and norms related to people with disabilities and including Mental Health conditions transformed.
Output number:		4	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 Number of people reached with Mental Health and disability inclusive messages.	a) 5 grantees have developed a workplan as part of the Social and Behaviour Change Communications (SBCC) strategy delivery (measured by the submission of their workplans)- (GSD Output 3- output indicator 3.2) & Programme SBCC grantees have developed positive and inclusive language in 5 local languages (b) World Mental Health Day partly supported by the programme (c) Accessible COVID-19 materials disseminated (d) Communications plan delivered	(a) Achieved (b) Achieved (c) Achieved (d)Achieved
4.2 Number of health professionals, community members and traditional leaders trained in stigma reduction, discrimination and human rights violations.	17,000 health professionals, community members and traditional leaders trained in stigma reduction, discrimination, and human rights violations.	Achieved
4.3 Extent of CSOs and DPO actors participation in advocating for social accountability and improved Mental Health services and support.	(a)TA plan agreed and delivered as per plan to strengthen governance and advocacy of key DPO organisation – Ghana Federation of Disability Organisations (GFD) (b) TA plan agreed and delivered as per plan to strengthen governance and advocacy of key DPO organisation – Mental Health Society of Ghana (MEHSOG) (c)10% of SHG leaders strengthened to participate in local governance (under GSD output 1 - indicator 1.2)	(a) Achieved (b) Achieved (c) Achieved
4.4 Level of awareness of COVID-19 related risk communications by persons with disabilities and Mental Health conditions	N/A	This milestone was not assessed. No further work planned.
4.5 Number of health professionals, equipped with guidance on COVID-19, mental wellbeing, and rights-based approaches	N/A	This milestone was not assessed. No further work planned.

Briefly describe the output’s activities and provide supporting narrative for the score.

The output score A. It measures against work to transform attitudes, behaviours and norms related to people with disabilities and Mental Health conditions.

Indicator 4.1 Extent of public awareness and sensitivity to Mental Health issues in Ghana.

The milestones for this indicator during the period under review comprised of four areas:

5 grantees developed a work plan as part of the SBCC strategy delivery and programme SBCC grantees developed positive and inclusive language in 5 local languages.
The UK Government under the Ghana Somubi Dwumadie project awarded grants to nine civil society organisations in April 2021, which comprised of five small grants and four large grants. This milestone was achieved because the grantees submitted their workplans to the Ghana Somubi Dwumadie project team and they were reviewed and currently being implemented.

World Mental Health Day partly supported by the programme
This milestone was achieved because the World Mental Health Day, celebrated in October 2021 was partly funded by the Ghana Somubi Dwumadie project. FCDO Ghana hosted LNOB implemented partners and used our convening power to influence GoG and other stakeholders in terms of increasing investment into Mental Health. The theme for the celebration was “Mental Health in an Unequal World” with emphasis on the need to increase investment on Mental Health in Ghana and globally.

Accessible COVID-19 materials disseminated
This milestone was achieved as 1,130 COVID-19 Easy Read materials were disseminated during the period under review. In addition to the 650 materials distributed disseminated earlier, 480 of the materials were distributed to the regional leaders of the Ghana Federation of the Disable during their capacity building training in December 2021. Also, 3,000 vaccine uptake materials were distributed to persons with disabilities through the federation.

Communication Plan Delivered
This milestone was achieved during the period under review. The Ghana Somubi Dwumadie project’s communication plan and social behaviour change strategy were finalised in January 2021 and the purpose was to tackle discrimination and stigma against persons with disabilities including those with Mental Health conditions. This was delivered through a granting mechanism to support civil society organisations to influence behaviour change, and support persons with disabilities, including those with Mental Health conditions.

Indicator 4.2 17,000 health professionals, community members and traditional leaders trained in stigma reduction, discrimination, and human rights violations.

The project through the QualityRights Initiative has successfully created awareness among 17,685 individuals who have earned a certificate in the e-training. These individuals are using the knowledge to promote a human rights-based approach to Mental Health care among healthcare professionals in training and in active service, persons with lived experience and their caregivers, civil society, religious leaders, and community members. This milestone has been achieved.
.
Indicator 4.3 Extent of Civil Society Organisations and Disable People Organisations actors’ participation in advocating for social accountability and improved Mental Health services and support.

TA plan agreed and delivered as per plan to strengthen governance and advocacy of key Disabled People Organisations.
This milestone was achieved. The Ghana Somubi Dwumadie programme developed TA plans with the Ghana Federation of Disability Organisations (GFD) in 2021 and delivered to plan to include leadership training for GFDO regional leaders, and Trainer of Trainer on rights-based advocacy as a tool for engaging with duty bearers. During the period under review, the Ghana Somubi Dwumadie programme trained 90 participants drawn from Northern, Savannah, Northeast and Upper East Regions. The purpose of the training was to strengthen their leadership and governance, and their networks and collaboration across different groups with shared interests.

TA plan agreed and delivered as per plan to strengthen governance and advocacy of key Disabled People Organisation e.g. MEHSOG.
As with milestone (a), this milestone was also achieved and the narrative for this is the same as milestone (a).

10% of Self-Help Groups leaders strengthened to participate in local governance
This milestone was achieved as the Ghana Somubi Dwumadie programme continued to support 28 Self Help Groups which constituted 10% of leaders during the period under review. In this regard, there was collaboration with the Mental Health Alliance to foster close relationships between Self Help Groups and their respective district assemblies, using the World Mental Health Day as entry point.

The 28 Self Help Groups were trained on rights-based advocacy, facilitation skills, record keeping, safeguarding and COVID-19 protocols to among others strengthen their capacities in engaging with Local Government Authorities.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The weighting is 15% it has not been revised since last year’s AR

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The previous AR, focused on ensuring this output was strengthened in terms of Monitoring & Evaluation (M&E) to establish indicators which are more suited to measure the change sought and not just delivery itself. Whilst implementing partners have discussed plans to revise these outputs, the specific output indicators are yet to be revised to demonstrate whether there have been any changes in attitudes, behaviours and social norms over time.

LNOB implementing partners to revise M&E framework to demonstrate whether there have been any changes in attitudes, behaviour and social norms over time.

LNOB has made progress in terms of raising integrating COVID-19 messaging into programming (e.g. through UNICEF’s communications for Development unit as well as SHGs to raise awareness on COVID-19 vaccines among the vulnerable in Ghana.

LNOB will continue to work with implementing partners to increase COVID-19 vaccination awareness with a particular focus on persons with disabilities and Mental Health conditions, women and the elderly. This will help to determine the different concerns from different groups in relation to vaccine uptake and to find ways these concerns can be addressed.

FCDO will monitor implementing partners progress in integrating COVID-19 vaccination messaging into communications as well as disability and Mental Health outreach activities in order to change perceptions, attitudes, behaviours and social norms in relation to COVID-19 vaccines. This is to ensure that Ghana’s COVID-19 response targets the most marginalised and vulnerable and to ensure it is based on equity, evidence and transparency.

Output Title	Effective scale up of disaggregated data collection across all partnerships and generation of high quality research, evidence, learning and what works to inform programming.
Output number:		5	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
5.1 Level of secondary analysis of Multiple Indicator Cluster Surveys (MICS) Ghana Living Standards Survey(GLSS data to identify vulnerable girls and boys as well as their caregivers as well as socioeconomic & geographic determinants of vulnerabilities	Panel phone interviews based on GLSS sampling framework in collaboration with GLSS and WB completed.	Achieved
5.2 Extent of interoperability of social welfare system Management Information Systems (MIS) with other databases.	Initial discussion with other MDAs (e.g. MoLER) to identify linkages between different MIS and SWIMS	Achieved
5.3 Extent to which findings from the Rapid Review Scoping Study and Assessment on Disability and Gender inclusion informs the Ghana Productive Safety Net Programme (GPSNP).	Implementation strategies developed/Action plan underway	Achieved
5.4 AIMS implemented and extent to which it informs the implementation of the Mental Health Strategy.	Assessment Instrument for Mental Health (AIMS) /ATLAS study (ATLAS is a compilation of data provided by countries around the world on Mental Health policies, legislation, financing, human resources) Study conducted and findings and report available	Partially achieved – the report is due to be submitted in March 2022
5.5 Extent to which findings from the COVID-19 Rapid Review Scoping Study informs the GoG COVID-19 response and secondary impact mitigation interventions.	N/A	This milestone will not be assessed. The programme produced the report and shared. No further work planned.
5.6 Progress on implementation of legislation relating to disability, including the Disability Amendment Bill	Advocacy and policy support provided for the passage of the Disability Amendment Bill	Achieved
5.7 Proportion of target districts with district plans which integrate disability, including Mental Health at a primary care level.	100% of demonstration districts have met indicator measure level A. (i.e. A) have an integrated MH plan)	Achieved
5.8 Access to quality integrated services at the primary health care (PHC) level for people with disabilities, including Mental Health disabilities.	Accessibility assessments are completed in 2 PHC facilities.	Achieved
5.9 Number of operations research studies conducted and disseminated that support an enabling environment, policy, and practice.	Programme produces 1 dissemination product	Achieved

Briefly describe the output’s activities and provide supporting narrative for the score.

This output scored A. It measures the effective scaling up of disaggregated data collection and generation of high-quality research, evidence and learning and what works to inform programming. The weighting for this output was raised in 2020 from 5% to 15% and has been retained as it contains some of the more crucial elements to enabling a more joined up social protection and social welfare system.

Indicator 5.1 – Level of Secondary Analysis data to identify vulnerable girls and boys

In November 2021, UNICEF Ghana – in collaboration with the Social Policy Research Institute (SPRI Global) – published The Impact of COVID-19 on Children and Families in Ghana: Qualitative Research with Caregivers and Children research report. This study aims to gain an insight into the perceptions of caregivers and children in Ghana on dealing with the COVID-19 pandemic and was conducted by engaging with caregivers and children of different ages directly through qualitative research methods. A total of 60 respondents were engaged in this research study, between July and September 2021.Key findings of the research were wide-reaching and varied, and cover the thematic areas of Health, Nutrition, Education, Mental Health and Psychosocial Wellbeing, Child Protection and Safety in the Community, Socioeconomic Wellbeing and Social Protection, and Water, Sanitation and Hygiene (WASH). The research report has presented recommendations, informed by the participatory inputs from the respondents, which cover the themes above. This milestone was achieved. Ghana Statistical Services (GSS) implemented Wave 1&2 in June and September 2000 and Wave 3 in December 2021. Reports for Wave 1 and 2 were published by SPRI ‘GSS recently released a summary of the results for Wave 3. The main report/ publication for Wave 3 is due to be released in 2022.

Indicator 5.2 – Interoperability of SWIMs with other databases
Building on experience gained in Integrated Social Services (ISS) districts throughout the programme, work in 2021 has focused on the development of additional collaboration protocols between the NHIS and LEAP to simplify enrolment and renewal onto the health insurance system, and on strengthening data interoperability between LEAP and Ghana Heath Services (GHS). This milestone was achieved. There is an SP Programmes MIS meeting scheduled bi-weekly to assess the performance of various MIS supporting SP programmes including LEAP and NHIS. In addition, there is a meeting scheduled between the World Bank and UNICEF in March 2022 to begin discussions on how Social Welfare Information Management Systems (SWIMS), LEAP MIS can be used as a steppingstone towards SP MIS interoperability.

Indicators 5.3 - Extent to which findings from the Rapid Review Scoping Study and Assessment on Disability and Gender inclusion informs the Ghana Productive Safety Net Programme (GPSNP).

This was a key piece of work which sought to understand the extent to which vulnerable households that include people with disabilities have been appropriately included into LEAP and if there have been any challenges. The research found evidence for attitudinal, institutional and environmental barriers in access to social protection programmes in Ghana by people with disabilities particularly disabled women and women with disabled children who were more likely to report feeling isolated and unsupported. In 2021, LMS made progress in drawing up an action plan to implement key recommendations from the scoping study report. This included revisions to the LEAP operations manuals and technical documents to incorporate considerations regarding gender and disability inclusion. Some of LMS staff were trained during a workshop funded through the FCDO funded Gender Responsive SP TA on gender and social safeguards into LEAP processes and practices. Furthermore, FCDO were also able to engage with the World Bank to encourage them to prioritise social safeguards in LEAP as well as in the new GPSNP project. Following the current LNB safeguarding review, the World Banks social safeguards team have expressed an interest in collaborating with FCDO in strengthening the Ministry of Gender, Children and Social Protection’s social safeguards as well as other government agencies. This milestone was achieved. LMS developed a plan to undertake a safeguarding review of pay points and drafted a ToR for the establishment of an Advisory Group of people with disabilities, including Mental Health disabilities to support LEAP to mainstream disability across its operations.

Output Indicator 5.4 AIMS implemented and extent to which it informs the implementation of the Mental Health Strategy.

The January 2022 milestone for this indicator is to ensure that AIMS/ATLAS study conducted with findings and report available, but this milestone was partially achieved. The research team of the University for Development Studies were successfully selected for the WHO Assessment Instrument for Mental Health Systems (WHO-AIMS) study. Following a competitive selection process and successfully obtaining ethical approval for the data collection from the Ghana Health Service Ethics Review Committee in August 2021. Data collection commenced in September 2021 after funds were transferred to the University. A progress report shared in November 2021 indicated that the data collection was about 60% complete. The Research team is expected to complete data collection and submit the final report by March 2022 after which dissemination of key findings to stakeholders will be planned.
Indicator 5.6 - Progress on implementation of legislation relating to disability, including the Disability Amendment Bill

The milestone for this indicator is advocacy and policy support provision for the passage of the Disability Amendment Bill, and this milestone was achieved. During the period under review the Ghana Somubi Dwumadie programme supported the launch and dissemination of the Mental Health policy in Accra (for the southern sector) and Tamale (for the Northern sector). One of the key areas of work was to support the progression of the Disability Amendment Bill and in this regard technical support was provided to the Ghana Federation of the Disabled to successfully advocate for the establishment of the National Council for Persons with Disabilities board in November 2021. This also included the formation of a committee to push for the passage of the Bill and formation of the Disability Caucus in Parliament to sense check the draft Bill.

Output Indicator 5.7 Proportion of target districts with district plans which integrate disability, including Mental Health at a primary care level.

The milestone for this indicator was to ensure that 100% of demonstration districts (Bongo, Ansunafo North and Anloga) have an integrated Mental Health plan, and this milestone was achieved. District mental healthcare plans are an important strategy for supporting scaling up of high quality and accessible mental healthcare services. In furtherance of this, the Ghana Somubi Dwumadie programme conducted Theory of Change training in the three demonstration districts and supported each district team to develop a Theory of Change map detailing the pathways of change needed to improve wellbeing and quality of life of people with Mental Health conditions in these districts.

Output Indicator 5.8 - Access to quality integrated services at the primary health care level for people with disabilities, including Mental Health disabilities.

The milestone for this output was achieved during the period under review. Two accessibility audits of primary health care facilities were carried out in the Upper East region (in Bawku and Bongo hospitals), using the accessibility audit tool developed in line with the Ghana Accessibility Standards in 2020. The main findings were that most of the doors, ramps, pathways, height of beds did not meet the accessibility standard, therefore, the assessment team made recommendations to help improve access to persons with disabilities. To remedy the situation, the Ghana Somubi Dwumadie programme intensified its advocacy and produced a documentary on the Ghana Accessibility Standard for Built Environment and Government of Ghana Agenda 111 programme.

Output Indicator 5.9 -Number of operations research studies conducted and disseminated that support an enabling environment, policy, and practice.

The milestone for this indicator was to produce one dissemination product, and that milestone was achieved. During the period under review the Ghana Somubi Dwumadie submitted a paper to the International Journal of Mental Health Systems for publication focusing on the district situation analysis undertaken prior to the development of the district Mental Health workplans. The programme also undertook a health facility survey to evaluate the outcomes in the Theory of Change maps generated by each demonstration district. Data for the survey were collected at the health facility level to assess access to quality Mental Health services, case detection and treatment, and availability of psychotropic drugs.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The LEAP Rapid review identified gaps in LEAP e.g., in relation to gender equality and safeguarding. There has been some progress following the last AR specifically in terms of LMS’s plans to conduct a safeguarding study to ensure women with disabilities are not put at increased risk through travel or payment arrangements and to establish an advisory group to inform LEAPs programming, Furthermore, as part of GPSNP 2, the World Bank have strengthened the amount of expertise on safeguarding at the country level. Recommendations for the year ahead:

FCDO will work closely with LMS to review the extent to which women with disabilities are put at risk due to travel or payment arrangement as well as to train and District Social Welfare Officers (DSWOs) and sensitise Community Focal Persons (CFPs) and other stakeholders on the LEAP guidelines on pay point set-up, pay point safety, and required travel time for beneficiaries.

FCDO will engage LMS to monitor their efforts to establish an advisory group of people with disabilities, including Mental Health disabilities, be established by MoGCSP/LMS, to support LEAP to mainstream disability across its operations.

The FCDO team will continue to work closely with the WB and their new social safeguards team as well as LNOB delivery partners to monitor the extent to which the recommendations from the rapid review are being put into action.

D: RISK [½ to 1 page]

Overview of risk management [1/2 page]

The overall programme risk continues to be moderate, which is within the acceptable risk appetite for the country office. The risk register has also been updated to align with the seven new risk category areas.

Several risks were, through robust mitigation and proper management, successfully closed this reporting year. COVID-19 continues to be a risk with its resultant effects on programme delivery by some Implementing Partners (IPs). The LNOB programme took immediate mitigation measures, including revising grantee workplans to accommodate delays in implementation and to find alternative ways to continue to deliver activities under COVID-19 restrictions.

Some risks carry a ‘severe’ rating and these include: (a) reputational risks to FCDO as a result of cuts to the ODA budget for the 2021/22 fiscal year and beyond; (b) safeguarding - where a human rights violation or safeguarding incident happens in a Mental Health facility or any reputational risks associated with the overall disability/inclusion component of the programme;(c) financial & fiduciary risks - where monies disbursed by implementing partners to downstream partners, including Government Ministries/agencies are not used in line with FCDO policy; (d) policy & programme delivery risks occurring due to the capacity of Government ministries to effectively implement the programme and be responsive to FCDO demands and (e)delays with LEAP payment cycles which represents the greatest threat to LEAP’s effectiveness.

The FCDO programme team continues to monitor the identified risks as well as any emerging ones to ensure appropriate mitigation measures are put in place Three meetings were held at various points during this review period to review and update the programme risk register as well as mitigation measures.

As a result of the safeguarding risks identified, FCDO has commissioned SDD to undertake a safeguarding review of the LNOB programme to assess the extent to which LEAP recipients with disabilities, and other vulnerabilities could be put at risk from Pay Point distribution mechanisms, in particular focusing on ways to ensure women with disabilities are not put at increased risk through travel or payment arrangements and also support implementing partners to ensure that all those involved in working with disabled people and/or carers of disabled children undergo disability awareness and equality training alongside safeguarding training. The review will also cover work conducted under the Mental Health components of the LNOB programme, being implemented by WHO, UNICEF, Options and MHA.

Safeguarding is a priority area that is closely monitored given the nature of the work of LNOB grantees, some of whom work with children and other vulnerable groups. During the reporting year, new grantees received safeguarding training on in order to effectively identify and/or escalate safeguarding-related issues.

Update on Partnership Principles
All Financial Aid to Government which FCDO provides is subject to the Partnership Principles, which set out FCDO’s expectations of Governments in relation to: (1) commitment to poverty reduction; (2) commitment to human rights and other international obligations; (3) strengthening financial management and accountability and reducing the risks of funds being misused through weak administration or corruption; and (4) commitment to strengthening domestic accountability. This programme relates to all four partnership principles.
The partnership principles are regularly assessed by FCDO, and the last update was done in January 2021, plans are underway to update the assessment for 2022.

COVID-19 has increased the risk of reversal of some of the gains made towards poverty reduction and the SDGs. In a context of extreme fiscal constraint, poverty reduction expenditure (for Primary Education, Health and Social Protection) continues to be at risk of stagnating or falling, driving poor people even deeper into poverty whilst creating new categories of poor and vulnerable struggling to meet their basic needs. Stronger and sustained GoG commitment to increasing the share of resources allocated to the social sectors and leave no one behind is required to progress the Ghana beyond Aid ambition. It is assessed that the Government of Ghana is broadly committed to the four UK’s four Partnership Principles.

Annual Statement of Progress (financial aid programmes only – delete if n/a) [1 page]
Current level of fiduciary risk and direction of travel since last ASP	Stable
Specific assessment of corruption risk and direction of travel since last ASP	Stable
Is a full FRA update required?	Yes: the process of contracting started but securing the right service provider for the Health FRA delayed. Work is currently ongoing and the report expected this FY.

The last Fiduciary Risk Assessment (FRA) of the sector was in 2015 before the LNOB programme began in 2019. Annual Statements of Progress (ASP) have been conducted since then until 2018. The process of recruiting a consultant to conduct the next FRA begun in 2019, but after reviewing the ToR and setting out the agreed date, the consultant declined unexpectedly, and the COVID-19 pandemic hit. In the absence of the FRA, the team depended on the risks register of the programme, which was closely monitored and updated regularly. Risks associated with RBA to MHA are dependent on the Health FRA which is currently ongoing.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and DFID, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency. [max 1 page]

Delivery and Quality of financial management

FCDO reviewed and agreed workplans, deliverables, budgets, and set logframe targets/milestones with all implementing partners (the World Bank (WB), World Health Organisation (WHO), UNICEF, Mental Health Authority (MHA), and Options Consultancy Ltd. The LNOB/FCDO team monitored performance of all the implementing Partners through monthly/quarterly progress meetings, ongoing communication and coordination, engagement in programme activities and agreed periodic reporting. Due to COVID-19 and various restrictions in travel by multilaterals (UN/WHO) during the review period, the programme was unable to carry out frequent physical monitoring visits and spot checks. However, monitoring will be strengthened in 2022.

World Bank Trust Fund (WBTF)
FCDO’s contribution to WBTF for the GPSNP programme is managed through an Administration Arrangement with the WB which sets out the guiding principles and procedures. The programme is structured in two components: a Recipient-executed grant, which constituted funding to be disbursed to MoGCSP and MoLGRD to support delivery of cash transfers to both regular LEAP beneficiaries (and an emergency stimulus package to the poor and vulnerable beneficiaries outside the regular LEAP programme as a result of COVID-19.

The last disbursement to the WBTF was £4m in September 2020, purposely for the COVID-19 Relief Cash Transfer which targeted 125,000 beneficiaries to support extremely poor and vulnerable persons who had been negatively affected by the COVID-19 pandemic. The beneficiaries included homeless persons in Accra and Kumasi, persons living with disabilities, persons in alleged witch camps, persons affected by floods as well as other extremely poor and vulnerable persons in the poorest regions of Ghana. The Ghana National Household Registry (GNHR) under the MoGCSP was used to determine the poverty/vulnerability status as well as the eligibility of all potential individuals and households for the COVID-19 Relief Cash Transfer.

As of September 2021 (a year later), 54,088 individual beneficiaries had received payments. Even though this payment should have been fully disbursed in 2020, payment to beneficiaries has significantly delayed due to the verification of individual beneficiary data used for processing payments. See table below for detailed breakdown:

Source: GPSNP Q3 report

FCDO has so far disbursed £12.1m to the WBTF, with a balance of £8.9m originally planned for the rest of the programme. The result of the budget reprioritisation in FY 21/22 was a budget cut to the WBTF programme amounting to £4.450m planned for the 20/21 FY and this was officially communicated to the WB. The decision on the remaining £4.450m for FY 22/23 FY will be known once spending review discussions conclude.

The WB provides financial information relating to receipts, disbursements, and fund balances quarterly on the website. Even though GPSNP reports are expected annually, FCDO has been given access by the WB to be able to easily access quarterly reports on their central data system and so far, Q1-3 reports have been received. Quarter 4 reports are expected in April/May 2022.

The WB Group financial audit for the FY 20/21 indicated that the Trust Fund maintained, in all respects, effective internal control over financial reporting as of 30 June 2021. Development partners may also access the most up-to-date financial data directly from the WB Trust Fund Donor Centre secure website.

Options Consultancy Ltd (Options)
Since January 2020, Options has held a commercial contract with the FCDO to deliver on the Disability and Mental Health component of the LNOB programme. Options continued to flex aspects of their programme to respond to COVID-19 in 21/22 FY The flex meant that Options was unable to deliver some of its planned activities directly. However, they worked with their downstream/grant partners to fill the gaps by undertaking activities that were affected by cuts from COVID-19 flex; for example, provision of TA to NCPD. The 2021/22 budget allocation was originally £3.5m and was later reduced to £2m due to FCDO overall budget cuts across the country programme. As a result, Options reviewed their annual workplan/milestones targets within the FY to align with the new budget. This called for an amendment to the contract to reflect the budget reduction., The contract amendment also covered changes in key staff on the programme as well as a formal move (of the contract) from inception to implementation.

Options has spent £1.568m as at quarter 3 (end of December 2021) of this financial year 21/22 out of the allocated £2m according to reports received with a forecast of £430k in quarter 4. Options have also reallocated £38k planned for MHA agreed activities as a result of an ongoing pause. The amount has nonetheless been allocated towards other Mental Health related activities. Quarterly reports (including the annual report) and invoices were received on time and covered the key reporting areas agreed. Monthly progress review meetings continue to be held between FCDO and Options to discuss progress of work and address any (emerging) challenges. The 20/21 FY audit has begun (including Options’ grant partners), and the final report expected at the end of March 2022. A SRM scorecard has not been completed for Options this year. Options maintains a risk register and an asset register which they update and submit to FCDO quarterly.

Synergy Fund
Under the Synergy Fund, Contribution Agreements were signed with WHO and UNICEF; an Accountable Grant with Basic Needs Ghana (project completed), an MoU with Government (Ministry of Health through the Ministry of Finance) for Results-based financial Aid (RbA) and a contract with the Social Development Direct (SDD) under the Monitoring and Evaluation component of the programme.

WHO: The contribution agreement with the WHO was originally signed in November 2019 for the delivery of the agreed project “Improving Access to Good Quality Mental Health Services in Ghana.” This agreement has since been amended to reflect new dates for releasing funds for planned activities in the agreed work-plan. During the review period, WHO requested for a no-cost extension on 27th August 2021 due to delays in implementation as a result of the effect of the COVID-19 pandemic on their core operations. This was approved and therefore the new project end date is 30th June 2022.

Total fund allocation for this component totalling £1,350,000 (US$ 1,737,452) has been disbursed and WHO have so far spent £1,286,000 (US$1,654,547), leaving a balance of £64,000 (US$ 82,906). The six-monthly and annual reports (narrative and financial reports) were received on time. The programme team will ensure that progress against the planned activities is monitored regularly to improve programme spend. As part of project monitoring, FCDO followed up and received updates on the recommendations from the due diligence assessment that was conducted in October 2019 (before the project started). Largely, WHO has adequately robust systems that provide assurance for delivery. Challenges remain with those recommendations that are dependent on WHO’s global systems such as public access to recent audit reports (to assess financial capability) and policies around handling of fraud and misconduct which are drawn from the global framework. The financial audit reports for the review period are, however, expected in April 2022 and FCDO will duly follow up on this.

Within the new FY, FCDO will review the due diligence assessment recommendations and consider a refresh by April 2022. Notwithstanding the challenges, the recommendation to recruit a local staff within the WHO Country Office to provide technical assistance to the project has resulted in some savings which has been used to procure a vehicle to support the Mental Health Unit of the Ghana Health Service.

UNICEF: The initial Contribution Agreement for £1,550,000 with UNICEF was signed off in December 2019 for work in Strengthening Integrated Social Services and Vulnerability & Exclusion assessment Following further discussions with FCDO, an additional support of £900,000 was made available to UNICEF to support activities in response to COVID-19, bringing the total budget allocation to £2,450,000. As a result, the contribution agreement was amended to reflect the additional funding and new grant value. FCDO has so far released £2,300000, with a balance of £150,000. Although FCDO anticipated releasing the balance in March 2022, this will now not be possible given the current balance of circa £807,000 (US$ 1,023,145.96) held by UNICEF as of 31st December 2021 (out of total disbursement made). FCDO has had discussions with UNICEF to flag the risks around the apparent slow delivery and huge balance being held. UNICEF has indicated that since December 2021, more payments have been made but are yet to be reconciled and will further reduce the balance. They are also working to pick up the pace of delivery to ensure that delivery is back on track towards the end date 30th June 2022. The financial audit reports are expected from UNICEF in April 2022 and will serve as the basis for a more thorough review of the funding position and next steps. In the meantime, FCDO is conducting a review of the UNICEF’s finances to get understand these barriers to spending. FCDO will continue to actively follow up on these risks (slow spend and delivery) to ensure full delivery by June 2022 or enable the FCDO to make an informed decision on the approach that best provides value for our investments.

MoH/MHA: The MoU signed in 2020 was earmarked as results-based aid to the Mental Health Authority MoH/MHA for delivery of improved Mental Health services in Ghana. Total allocation for the RbA was £2,000,000 over five years ending 2024. Payments are released based on delivery of agreed milestones/targets (agreed at the beginning of each calendar year) using the verification guidelines agreed by both parties and as set out in the MoU. A total allocation £400,000 has been forecast in the 2021/22 FY to be released based on the submission of annual reports from MHA and verification exercise conducted to verify agreed targets/milestones. From discussions held with MHA during the review year to informally assess progress, MHA appear to be on track to have fully delivered on their milestones; the ongoing verification will confirm the extent of achievement and amount to be disbursed.

Social Development Direct TA (SDD): During the 2021/22 FY, SDD was contracted to carry out a Safeguarding Review on some selected implementing partners based on recommendations from the Rapid Review Scoping Study in 2020 which focused on understanding the extent to which vulnerable households (people with disabilities) have had appropriately included in LEAP The contract amount for the Safeguarding Audit has been agreed at £65,555 and work is expected to end in August 2022. Work on this contract has commenced and SDD staff are gathering data from the programme implementing partners (IPs) and also conducting focus group discussions with the selected IPs. Submission of assessment report and roadmap with suggested deliverables is expected in March 2022 and the final report in expected in August 2022.

Date of last narrative financial report	WBTF: 15/02/2022 WHO: 03/02/2022 UNICEF: 15/02/2022 MHA: 09/02/2022 OPTIONS:31/01/2022
Date of last audited annual statement	WBTF: 11/08/2021