 Annual Review Template
Title: LEAVE NO ONE BEHIND AS GHANA MOVES BEYOND AID
Programme Value £ (full life): £39.2 million		Review date:
Programme Code: [AMP ID 300385]	AMP start date: -March 2019	AMP end date: March 2024

Summary of Programme Performance
Year	2020	2021	2022	2023
Overall Output Score	A	A	A	B
Risk Rating	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300385/documents
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300385/documents

A. SUMMARY AND OVERVIEW

Description of programme

Leave No One Behind (LNOB) aimed to provided £39.2 million over five years (2019-2024) to support the Government of Ghana to deliver services to the poorest and most excluded. It will focus on social protection and realising the rights of people with disabilities and Mental Health conditions. LNOB is FCDO Ghana’s largest bilateral programme of support working across poverty, disability inclusion and Mental Health. LNOB contributes to four areas of change: (1) Improved policy, leadership, resources and governance systems that promote disability inclusion and Mental Health for all and enable equal recognition and respect for human rights of the extreme poor and marginalised; (2) the extreme poor and marginalised, people with disabilities and Mental Health conditions enjoying high quality and integrated health and social protection systems; (3) full, active participation and representation and reduced stigma for the extreme poor and persons with disabilities and Mental Health conditions, discrimination and human rights violations; and (4) improved knowledge and evidence-based understanding of exclusion and what works to improve wellbeing, social and economic outcomes and rights. The LNOB programme has three delivery mechanisms:

Social Protection – delivered through the World Bank Trust Fund – working with the Government of Ghana (GoG) through the Ministry of Gender, Children and Social Protection (MoGCSP), and UNICEF building on the first phase of the Livelihood Empowerment Against Poverty (LEAP) programme.

Mental Health and Disability – delivered through the Ghana Somubi Dwumadie (Ghana Participation programme), a consortium led by Options Consultancy, with BasicNeeds-Ghana, Sightsavers International, Kings College London and Tropical Health – to support Government to scale up delivery of quality and integrated Mental Health services, particularly at the primary health care and community level and provide sub-grants to civil society organisation (CSOs) and Disabled Peoples Organisations (DPOs) to support community-based advocacy and inclusion, support empowerment and recovery and develop anti-stigma campaigns.

Synergy Fund – managed by FCDO – to provide support for activities which create synergies and linkages between tackling poverty and promoting disability inclusion. This includes supporting UNICEF to strengthen integrated services, case management and referral and reintegration pathways; Results-based financial aid to Ministry of Health (MoH) to support the strengthening and integration of Mental Health provision; MoU with WHO to support Quality Rights through Technical Assistance (TA); Scoping Study on LEAP delivered by the Social Development Direct (SDD) and Safeguarding review (SDD).
Summary supporting narrative for the overall score in this review

Despite continued uncertainty in terms of the external context and funding, the LNOB scored a B. During the year, Ghana’s fiscal and debt vulnerabilities worsened in an increasingly challenging external environment. The high levels of inflation seen in 2022 put increased pressure on poor and vulnerable households, pushing more into absolute poverty. Even prior to the COVID-19 pandemic, the Ghana Living Standard Survey report indicated that 2.4 million Ghanaians were extremely poor. 28.2% of Ghanaian children were monetary poor, while 73.4% suffered from multidimensional poverty. On top of this, soaring food prices have posed a significant threat to food security by reducing the purchasing power of millions of Ghanaians, especially vulnerable and marginalised groups.

In 2022, there were further budget reductions to the LNOB programme and for the second year running, funding to the World Bank Trust Fund (for 2022/23) was reduced by £4.4m. As FCDO’s Administrative Agreement with the World Bank is due to terminate in December 2023, plans are currently underway to close out the Ghana Productive Safety Nets Programme (GPSNP) 1 programme. In addition, the total contractual budget for the Ghana Somubi Dwumadie (GSD) programme was reduced from £3,275,961 to £2,500,000– a reduction of 23.6%. In addition, an ODA programme pause was announced in August 2022. The pause continued through to October resulting in the rescheduling, reforecasting and ultimately discontinuing some of LNOB activities across most of its components.

From the end of 2021 through to September 2022, the Mental Health Authority (MHA) component was paused. During the pause, LNOB implementing partners, were able to identify alternative ways to deliver MHA activities. Furthermore, in 2022, the UK Government published the International Development Strategy (IDS) which outlined the UK’s focus on promoting women with the freedom they need to succeed, unlocking their future potential, educating and supporting their employment and protecting them against violence. The IDS also highlighted the UK’s new approach to development in terms of taking a patient approach to build strong foundations and systems for longer term development. It also stressed the importance of utilising British expertise and giving our High Commissioners greater authority to deliver outcomes for us on the ground. At the same time, as part of the Business Planning process, the new Women & Girls Handrails set out a series of steps to restore budget allocation in alignment with policy prioritisation. As a result, LNOB implementing partners increased focus on women and girls revising milestones to ensure strengthened engagement, agency and empowerment.

Key achievements during 2022 are detailed below:

UNICEF - despite further significant cuts to the social protection component delivered through the World Bank, FCDO continued to fund UNICEF to deliver the Integrated Social Services (ISS) and the Social Welfare Information Management Systems (SWIMS). In 2022, ISS was scaled up to 60 new Metropolitan, Municipal and District Assemblies (MMDAs), increasing the total number of MMDAs implementing ISS to 160 and supporting vulnerable children to access quality services. UNICEF is providing technical support to MLGDRD to improve data quality. A recent UNICEF review found an improvement in the quality and completeness of data reported by MMDAs, including stronger compliance with, and understanding of, reporting template completion and indicator disaggregation. UNICEF also provided training to the Ministry of Gender, Children and Social Protection (MoGCSP) and decentralised SWIMS users, as well putting in place mechanisms for the Government to host the SWIMS server and data in line with the data protection law.
To maximise the sustainability of FCDO investments, UNICEF worked with the National Development Planning Commission (NDPC) to ensure that ISS is included in the District Medium Terms Development Plans (DMTDPs) of the Municipal Metropolitan Districts Assemblies (MMDAs) for 2022-2025. NDPC will also take on more of a leading role from 2023 onwards to ensure stronger alignment with Ghana’s Government systems. Furthermore, the Vulnerability and Exclusion Assessment (V&E) was finalised in 2022 and published. A V&E programmatic response document is currently being developed, which will translate recommendations into actionable strategies.

Options / Ghana Somubi Dwumadie (GSD) – in the review period, GSD reached 49,074 people directly (of which 26,181 were women), and 95,773 people indirectly. During the year in review, GSD developed a Technical Assistance (TA) plan with MoGCSP to operationalise Commitments made by Government of Ghana at the Global Disability Summit in February 2022. Despite a lengthy pause in activities with Mental Health Authority (MHA), GSD maintained a strong relationship, so that after the MHA Board was re-established in September 2022 and after the MHA pause was lifted, GSD was able to rapidly support the inauguration and training of the Mental Health Review Tribunal and Regional Visiting Committees.

World Health Organisation (WHO) - As of October 2022, 42,784 people had visited the Quality Rights e-training website. 26,859 participants started the course and 22,210 participants (including 9,900 females) received WHO Quality Rights e-training certificates (equivalent to a diploma certificate in Human Rights). Between January – October 2022, 4,539 participants were awarded with certificates. Following a gap analysis, seven facilities successfully developed and implemented Mental Health service transformation plans in line with a human rights-based approach. Forty volunteers (including 16 females) signed up as ‘digital angels’ to promote Quality Rights and received training to raise awareness. Continuous Professional Development accreditation for Quality Rights training was renewed for 5 health professional bodies in 2022.

Mental Health Authority (MHA) – MHA were able to support the inauguration of the MHA board. They trained five regional Mental Health visiting committees to improve the protection of human rights in the provision of Mental Health services. Furthermore, MHA commenced procurement of psychotropic drugs and began processes to evaluate the tender document awaiting the issuance of contracts for 2022. In addition, 200 copies of the newly developed research agenda were printed and disseminated to improve evidence-based planning and decision making.

Major lessons and recommendations for the year ahead:

The LNOB programme has been reviewed by various actors during the review period e.g. Social Development Direct during the Safeguarding (SEAH) Review in 2021-22 and by the Social Protection Technical Advice and Resources Facility (STAAR).

# In view of ODA cuts, pauses, the release of the IDS and continued prioritisation of women and girls, LNOB will need to continue to be agile to pivot to the evolving priorities and uncertainties. Within the current context of reduced funding due to UK’s socio-political situation as a result of the Russia/Ukraine crisis and the on-going economic downturn in Ghana. As the LNOB programme enters its final year, FCDO will engage in the Business Planning process, feeding into Campaign Goal 2 in terms of human development outcomes for the bottom billion. Under LNOB, we will continue to engage with social protection development partners through the sector working group to continue to advocate for better prioritisation with sectors to ensure budget adequacy, efficiency and equity. While we will no longer be able to provide support through LNOB, we can continue to engage through Partnerships Beyond Aid (PBA) taking an integrated approach across social protection, health and education as they are considered macro-critical sectors. In this way, we will continue to engage in on-going conversations with development partners and with the IMF.
# During the review period, the programme learned major lessons due to the MHA pause., This included discovering that e.g. WHO could mitigate delivery risks by engaging partners such as the Mental Health Society of Ghana (MESHOG) to deliver critical activities such as the re-assessment psychiatric and general hospitals to implement improvement plans. Due to the prolonged MHA pause and its effect on high level advocacy, LNOB partners able to reach consensus and make a case for the lifting of the MHA pause on strategic advocacy activities which meant high level activities to mark World Mental Health Day in October 2022, we able to go ahead. Yet overall, the biggest threat to the programme’s impact is around sustainability. With reduced funding we would need to consider how to maintain our relationships, credibility and social capital with reduced spend. We would need to consider using all our levers e.g. our convening power, influencing skills to keep our seat at the table. We also need to consider the funding gap that may be created and ways we can ensure a ‘responsible exit; from on-going commitments and areas we have been heavily involved in such as LNOB to ensure we don’t reverse gains already made or do harm. In the final year of the programme, it is important to ensure that key Ministerial priorities concerning self-reliance and sustainability are realised. In terms of lessons learned, FCDO will continue to consider the Business Case, the continuing relevance of the Ghana Beyond Aid agenda (and process for reviewing the transition process), our ambitions and the role we will play (if any) in addressing Ghana’s emerging humanitarian needs in the North as well as advocating for increased domestic financing of Mental Health and social protection.
In terms of sustainability, under the ISS, according to UNICEF evidence shows that it is necessary to continue strengthening the ISS approach in line with GoG decentralised and integrated planning to strengthen sustainability, effectiveness, and efficiency of GoG’s child and women specific policies. Strong budget analyses, fiscal space analyses and related technical support is timely in the new context of IMF programme as well as strengthening the demand and accountability structure of Integrated Social Protection. ISS is an approach which can be used further to address child needs in an integrated and efficient way also when strengthening shock responsiveness of social protection and resilience of the communities. UNICEF is currently supporting the NDPC to coordinate with other agencies and come out with a governing structure to support delivery of integrated social services both at national and local levels.

Below are key recommendations for the year ahead including those outstanding ones from the previous Annual Review:

Maternal Mental Health – in alignment with the IDS and the FCDO’s women and girls’ agenda, FCDO will implement a new Maternal Mental Health Programme to improve maternal and child health outcomes, especially for poor and vulnerable women in Ghana. The programme will be developed in two phases. Phase one will include a situation analysis and assessment of maternal Mental Health services and Phase two will focus on the development of broad stakeholder consensus and an implementation plan for the inclusion of Mental Health modules into maternal health services. The initiative is in line with GoG policy to strengthen the quality of maternal and newborn care through the adoption of respectful maternal care modules. The WHO and Ghana Health Service will lead the work but will engage various partners including Options and Basic Needs Ghana (BNG). A key recommendation for the year ahead would be for LNOB partners - WHO, Options / Basic Needs Ghana to 1) work closely in Phase one to implement stakeholder consultations with Ghana Health Services (GHS) to coordinate policy and advocacy activities e,g, national dialogues with key stakeholders including policy-makers, midwives, medical officers to build broad based consensus and 2) ensure integration of Mental Health into existing policies into Ghana’s national maternal and neonatal, infant and child health policy and strategy at the next review (Q1 &2).

Safeguarding review – During the review period, the Social Development Direct (SDDirect) Safeguarding review was commissioned to assess compliance among five of LNOB’s implementing partners and downstream partners in relation to Sexual, Exploitation, Abuse and Harassment (SEAH) and human rights violations across the programme. The review highlighted key recommendations which with the support of FCDO implementing partners could prioritise in the remaining time that the programme is being implemented. These include: 1) Taking a consortium wide approach – FCDO should support partners through regular safeguarding training on SEAH and disability inclusive safeguarding practices. 2). Establishing a safeguarding community of practice – to foster more open discussions and shared learning benefiting using FCDO Ghana’s leadership to promote peer learning exchange of good practices (Q1&2).

Data and dissemination of evidence – over the lifetime of the LNOB programme, implementing partners have generated and amassed a significant body of data and evidence – e.g. on Mental Health and social protection (through UNICEF) – specifically during COVID-19. For example, a key lesson learned under the GSD programme is the need for the dissemination of research on Mental Health. Research on Mental Health is integral to strengthening health systems and achieving sustainable development. Such research can be used to identify the most pressing Mental Health challenges and influence change. With FCDO Support, UNICEF, the World Bank, and the Ghana Statistical Services conducted multiple waves and reports of the impact of COVID-19. The first wave focused on the economic impact of the COVID-19 pandemic on households and the second wave on the impact on children and family situations. The third wave which data was collected in the first two weeks of December 2021 was released in January 2022 (Q2).

Communications Strategy – as the programme enters its final year, it is important to develop a communications strategy to shed a light on LNOB activities, events and to demonstrate the impact that the programme is making on the lives of the vulnerable and marginalised in Ghana. For example, the dissemination of the most significant change stories under GSD Evidence and Effectiveness grants. Strengthening communications will help to highlight the scope and breadth of work being carried out under the programme (Q1).
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s Theory of Change (ToC), including any changes to outcome and impact indicators from the original business case.

In 2022, as part of an overall programme review, FCDO convened LNOB implementing partners to review the Theory of change (ToC) and logframe. This assessment was critical in view of the various ODA cuts to the programme and pauses which delayed activities under the programme.

The ToC was stress-tested to examine whether existing assumptions were valid. Implementing partners concluded that they were confident that the ToC is sound. However, in view of Ministerial priorities, FCDO asked implementing partners to increase focus on gender.

Our annual logframe review identified that further clarity was needed for several output indicators and milestones, and that others needed to be revised. All amendments for 23/24 will be made and reflected in a revised lograme on devtracker. Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Despite funding cuts and pauses the LNOB programme remains on track to contribute to the expected outcomes and impact. On the whole, identified milestones at both the output and outcome level are being achieved. The impact of COVID-19 and the Russia-Ukraine crisis continues to put pressure on budgets and spend on the social sectors, which reveals that external donor finance and TA is still required to meet the needs of the extreme poor, food insecure and vulnerable. While the programme is still on track, we remain concerned about the issue of sustainability and GoG’s ability to become self-reliant, to generate domestic revenue and move beyond aid. In preparation for further budget cuts, the programme will continue to explore with implementing partners various scenarios to ensure the programme is still able to contribute to outcomes to achieve impact.

Our support to UNICEF ended in December 2022 after a six month no cost extension (July – December 2020). The Integrated Social Services intervention will continue to strengthen sustainability through local capacity building focusing on the district level and mechanisms were put in place to facilitate government ownership and leadership during and beyond the programme implementation. It is anticipated that by working through existing government systems and building on initiatives and capacities that already exist, rather than piloting a model that government cannot sustain in the long run, the case management and referral model will build capacity, systems and leadership with government that can continue beyond the length of this programme.

As our bilateral support for social protection has ended, both under the WBTF and UNICEF. We will draw on the support of Centrally Managed Programmes (CMPs) e.g. Social Protection Technical Assistance Advice and Resources Facility (STAAR) Gender Responsive Social protection (GRSP) and Better Assistance in Crisis (BASIC). Following a request for support from the MoGCSP, STAAR plans to provide TA support to review Ghana’s National gender policy through a social protection lens. It will engage FCDO and GIZ build capacity of Gender Desk Officers and strengthen gender and disability-inclusive social protection in LEAP. We also intend to continue our engagement in the Social Protection Sector Working Group and Donor Partner meeting, to influence DPs to advance policy priorities in Ghana, including the issue of sustainable financing through joint advocacy.

Over the next year, key priorities delivered by LNOB implementing partners - MHA and Ghana Somubi Dwumudie (GSD) - will include the continued establishment of the Mental Health Review Tribunal, Visiting Committees, and the procurement of psychotropic drugs. GSD will continue to deliver and support grantees and recipients of the Legacy and Sustainability grants, support MoGCSP to deliver on Disability Commitments made at the 2022 Disability Summit, build the capacity and institutional sustainability of Disabled Persons Organisations (DPOs) and the dissemination of evidence, and what works on Mental Health in Ghana.

FCDO’s support to WHO ended in October 2022. In the next FY, FCDO will engage WHO to lead the implementation of a new Maternal Mental Health programme to improve maternal Mental Health services to support the Ministry of Health module within the respectful maternal health services framework. However, due to the ODA pause, this component commenced later than planned. The programme will be developed in two phases. Phase one will include a situational analysis / assessment of maternal Mental Health services with key stakeholders including GSD and Basic Needs Ghana. The findings from the stakeholders’ analysis will determine the scope of Phase two. A key focus will be to collaborate with Ghana Health Services to develop an implementation plan for the inclusion of Mental Health into maternal health services.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

LNOB’s implementing partners and stakeholders continue to affirm that the LNOB programme is needed now more than ever to respond to and address some of the challenges of the most vulnerable and marginalised in Ghana. The UK continues to be a trusted partner having had a longstanding relationship with the GoG and has providing many years of valuable TA expertise and financial aid to the social protection sector. Furthermore, as the only significant donor supporting Mental Health in Ghana, the UK continues also adds value in terms of scaling up delivery of quality and integrated Mental Health services, particularly at the primary health care and community level e.g. through the expansion of Self Help Groups (SHGs). The programme continues to occupy a need in Mental Health that is not being addressed by other development partners. The continuing justification for the programme continues to be affirmed, most recently in the Universal Periodic Review (UPR) assessment of Ghana’s human rights record in January 2023, where numerous recommendations were made to GoG in terms of addressing issues around disability and Mental Health.

Over the years, LNOB has strengthened linkages and synergies bringing together actors who would not otherwise work together including the MoGCSP, Ministry of Health and Local Government e.g. through the District Assembly Common Fund (DACF) review and guidance. Internally, during the Business Country Planning process, there may be opportunities to establish more of a cross-mission focus on the bottom billion. Externally, FCDO should put together an influencing plan for multilaterals to ensure that leave no one behind remains a key issue on the top of their agenda.

## C. DETAILED OUTPUT SCORING

Output Title	Improved policy, leadership, resources and governance systems that recognises and respects the human rights of the extreme poor and marginalised, including all people with disabilities and Mental Health conditions.
Output number:		1	Output Score:	B
Impact weighting (%):		15%	Weighting revised since last AR	No

Indicator(s)	Milestone(s) for this review	Progress
1.1. The existence and functionality of a government mechanism to monitor and provide accountability for disability, including Mental Health	Members of Mental Health Review Tribunal and Visiting Committees trained	Achieved
1.2 % of LEAP beneficiaries selected using Ghana National Household Registry (GNHR) data. Results disaggregated by gender and disability status.	Not applicable	This milestone has been removed and will not be assessed a funding to the World Bank Trust Fund for this financial year has been discontinued.
1.3 Level of implementation of Government's Vulnerability and Exclusion (V&E) Strategy	Programmatic response document developed to translate recommendations of the assessment into workable actions for the relevant implementing institutions	Partially achieved (programmatic response document not finalised)
1.4 Level of Technical Assistance to MoGCSP to strengthen social protection system and implement, map and coordinate COVID-19 activities and advocate for increased resources to contribute to the sustainability of the social protection sector	a) Technical assistance provided to the provision of COVID-19 relief transfer to at least 120,000 vulnerable individuals b) Shock Responsive social protection assessment commissioned	(a) Partially achieved (only 107,574 beneficiaries reached) (b) Achieved
1.5 Extent to which the Legislative Instrument (LI) of the Mental Health Act (846) and national Mental Health policy established and guide implementation of Mental Health services.	a.) Availability of functioning Mental Health Board. b.) Availability of functioning Mental Health Visiting Committees in 5 regions. c.) Availability of Mental Health Research Agenda.	a) Achieved b) Achieved c) Achieved

Briefly describe the output and provide supporting narrative for the score.

This output has been scored at B. It measures work done by Options and the Consortium, UNICEF’s V&E and TA to MoGCSP and operationalisation of LEAP.

Indicator 1.1 - Extent to which intersectoral monitoring and accountability mechanisms strengthen Government of Ghana systems delivering Mental Health services and disability inclusion.

This milestone was achieved during the year under review, made possible by the established of the Mental Health Board (indicator 1.5) with the powers to establish Mental Health Tribunals and Visiting Committees. With support from the GSD, 15 Mental Health Review Tribunal members and 35 Visiting Committee members were trained in November and December 2022. As such, the programme made considerable progress on the Mental Health Review Tribunal and Regional Visiting Committees during 2022. Tribunal members of three pilot regions (Greater Accra, Ashanti, and Central) were appointed, inaugurated and trained in November 2022. Training of the Visiting Committees took place in December 2022 with members from Ashanti Region, Central Region, Western Region, Greater Accra Region and Upper East Region.

Indicator 1.3 - Vulnerability and Exclusion (V&E) Assessment. UNICEF commissioned ODI to conduct a V&E assessment to analyse the primary drivers of social vulnerability and exclusion in Ghana, examine coping mechanisms used by vulnerable groups, assess the access and responsiveness of social protection programmes and key social services (education and health) provided by the government and other providers in addressing key vulnerabilities and to provide recommendations and policy options to address existing gaps. Report on The Vulnerability and Exclusion Assessment has been completed, validated, and published. A programmatic response document which is to translate the recommendations into actionable strategies is still undergoing final review and approval by the Ministry of Gender, Children and Social Protection. This milestone was partially achieved.

Indicator 1.4 – Level of technical assistance to MoGCSP to strengthen the social protection system and implement. Map and coordinate COVID-19 activities and advocate for increased resources for the sustainability of the social protection sector

Technical assistance provided for the provision of COVID-19 Relief Transfers to at least 120,000 vulnerable individuals.
Technical assistance provided in the area of communication and monitoring and evaluation of the provision of the COVID-19 relief transfer in which 53,151 beneficiaries received COVID-19 cash transfers in 2022 bringing the total recipients to 107,574 since 2020. This milestone was partially achieved.

Shock Responsive social protection assessment commissioned
The Shock Responsive social protection assessment commenced with final report expected in 2nd quarter of 2023. This milestone was achieved. Assessment of Ghana’s social protection system readiness for shock response ongoing by the American Institutes for Research has started. It aims to assess the country’s social protection system’s readiness highlighting disability, gender- and age-responsive approaches to maintain its routine function in times of crisis and/or adjust on its own or in coordination with other departments/ministries to accommodate new populations and needs as a result of shock; and to contribute to resilience building of individuals, households, communities and systems to future shocks. To ensure a holistic assessment for Ghana, a Technical Working Group (TWG) made up of experts from a number of Ministries, Departments and Agencies (MDAs) representing government interest, CSOs and DPs has been set up to oversee, monitor and review the work of the research team undertaking the assessment. It is expected that with the guidance of the TWG, the research will come out with recommendations setting out a series of potential options highlighting gender- and age-responsive and disability inclusion approaches that the Government of Ghana, will use as a basis for reflections to respond to the needs of households and individuals affected by emergencies such as climate change hazards and man-made disasters.

Indicator 1.5 - Extent to which the Legislative Instrument (LI) of the Mental Health Act (846) and national Mental Health policy established and guide implementation of Mental Health services. The milestone for this FY was revised in 2022 to include: a) inauguration of the Mental Health Board, b) the establishment, orientation and training of five Regional Mental Health Visiting Committees to begin their work to improve the protection of human rights in the provision of Mental Health services and c) the printing and dissemination of 200 copies of the newly developed MHA research agenda – delivered to MHA stores. The primary goal for the research publication is to establish a Mental Health research agenda, build capacity, mobilise funding and begin research and publication. One key strategy for achieving this policy goal is to create a research agenda to help improve evidence-based planning and decision-making for Mental Health research. This milestone was achieved, however, an assessment of the full set of RbA 2022 milestones is yet to be completed for the Year in review.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The weighting of the output was maintained at 15% and remains relevant during this AR period. Changes were made to the 2022 milestone for Output indicator 1.5 to incorporate MHA activities including the establishment and inauguration of the MH Board, the inauguration, orientation and training of the 5 Regional Visiting Committees and the printing and dissemination of the research agenda publications.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

In terms of progress on recommendations from the previous AR, FCDO’s relationship with multilaterals in particular, UNICEF, continued to be strengthened through on-going collaboration on key areas of engagement including the Vulnerability & Exclusion (V&E) assessment, Integrated Social Services (ISS) /Social Welfare Information Management System (SWIMS). There were a few lessons learned during the review period. For example, FCDO’s lack of visibility became apparent e.g. in the publication of the V&E assessment. Going forward, there is a need to ensure FCDO maintain visibility and are acknowledged in on-going work in relation to the V&E assessment and ISS. As the V&E programmatic response document is finalised, there may be opportunities for FCDO to lead engagement with UNICEF, DPs and the MoGCSP towards developing an action plan and roadmap to implement the reports’ findings.

Recommendations for this year:

Vulnerability & Exclusion (V&E) assessment findings – With the COVID-19 pushing more people into extreme poverty while LEAP maintains its limited coverage, there is a greater need for access to existing social protection programmes to be expanded to reach some of the V&E identified in the report. FCDO could play an active role engaging with multilaterals, DPs and GoG on the finalisation and dissemination of the V&E programmatic response document. There are opportunities to strengthen our engagement with the World Bank as they seek to work collaboratively with FCDO and UNICEF and will share findings from the World Bank’s recent social inclusion analysis to ensure we take a joined-up approach to putting forward recommendations for both reports to the Government. Furthermore, FCDO should continue to engage with GoG, multilaterals and key stakeholders during Social Protection Sector Working Group and Social Protection Development meetings and find opportunities to share expertise and develop joined up advocacy plans and influencing strategies.

Shock Responsive Social Protection – FCDO to continue to engage in the Technical Working Group (TWG) with DPs to provide inputs into the report findings, make recommendations in order to build a more resilient and responsive shock responsive social protection system to address the needs of vulnerable communities affected by emergencies such as climate change hazards and man-made disasters. The TWG, in keeping with the HD’s proposed integrated approach to shock response, will adopt a cross sectoral approach addressing the impact of shocks on the health, education and on the most vulnerable and excluded.

Launch and dissemination of the District Assembly Common Fund / Disability Component - Options to bring key Ministries (Ministry of Gender, Children and Social Protection, Ministry of Health and Ministry of Local Government as well as DPs and CSOs and DPOs together to facilitate the launch and dissemination of the revised District Assembly Common Fund (DACF) and guidance.

Continued alignment between Options/GSD and the WHO on the Director Generals’ (DG’s) Special Initiative for Mental Health – Options to continue to align activities e.g. Mental Health Review Tribunal, Visiting Committees with WHO to complement their work and to prevent duplication.

Output Title	Effective cash transfers payments and operational modalities are delivered to extreme poor and vulnerable and marginalised households on a transparent, accountable and sustainable basis
Output number:		2	Output Score:	B
Impact weighting (%):		35%	Weighting revised since last AR	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of beneficiaries accessing timely LEAP cash grant (results disaggregated by gender and disability status).	350,000 LEAP beneficiary HH (1,505,000) individuals - receiving timely cash payments	Not achieved (343,434 households reached)
2.2 Level of implementation of the Social Welfare Case Management and referral and reintegration system in 50 districts in Ghana including number and percentage of LEAP beneficiaries with active NHIS membership	80% of LEAP individuals with active NHIS cards	Partially achieved (78.5%)
2.3 Level of implementation of the Shock Responsive Social Protection Emergency Early Warning System	a) MoU signed b) Initial emergency processes, data collection/sharing protocols, and gaps identified, to provide skeleton for shock-responsive SP roadmap	Partially achieved (data collection and sharing protocols are yet to be finalised)
2.4 Number of LEAP beneficiaries enrolled onto the Productive Inclusion and accessing financial services (start-up grants) – complimentary livelihoods asset support scheme (CLASS) including % of women and persons with disabilities and Mental Health conditions – results disaggregated by gender and disability status.	N/A	This milestone will not be assessed as funding to the WB Trust Fund was cut for this FY

Briefly describe the output’s activities and provide supporting narrative for the score.

The output score is B. It measures against work carried out by UNICEF on Integrated Social Services components including the Social Welfare Information Management system.

Indicator 2.1 – Operationalisation of timely LEAP cash payments – This milestone was not achieved. Efforts to pay 350,000 LEAP beneficiary households was not achieved as the number of households paid peaked at 344,786 and declined to 343,434. Though payments for 6 cycles were made in 2022 in three combined cycles, there still remains one cycle for 2022 outstanding as the six cycle payments made had one outstanding from 2021. Moreover, none of the payments made in 2022 was made on time as there were delays ranging from two months to six months with all six cycles combined in three tranches. LEAP communication was weak with communication mainly related to payment as and when it was being made. No communication went out to beneficiaries during the long period of waiting. LEAP Payment-related messages were not clear and timely enough thus beneficiaries are not aware of what is due them and how much is outstanding, if any. Efforts to support the adoption of the beneficiary community communication with existing government communication channels at the local levels were not successful due to lack of administrative commitment from the MoGCSP and inadequate funding as well. Data on LEAP payment is obtained from the LEAP Management Secretariat through payment cycle reports.

Indicator 2.2 – Integrated Social Services (ISS) - Social Welfare Information Management System (SWIMS) - There has been good progress in the development of the ISS and SWIMS social welfare and case management system by UNICEF. In 2022, the implementation of ISS was scaled up to 100 MMDAs, including 50 MMDAs with support from FCDO, who are now coordinating activities with social welfare, LEAP, health insurance, health services, planning, local government, and finance at national and sub-national level. Through the ISS initiative, the Government of Ghana has made budgetary allocation to the 100 districts in the ISS for social welfare services in the 2022 national budget, with plans to expand to an additional 60 MMDAs in 2022. The ISS Initiative has had promising initial results and has benefited from continued innovation in tools and mechanisms to increase access of vulnerable children and households to multiple social protection, child protection and health services.

In the review period, through ISS/SWIMS, linkages between LEAP households and NHIS were further strengthened. UNICEF has supported extensive National Health Insurance Scheme (NHIS)-LEAP dialogues on developing a strategy for further increasing enrolment, simplifying renewal, innovating protocols, and data-sharing to ensure that as many LEAP beneficiaries as possible also have access to free health insurance.

During the review period, 78.5% of LEAP beneficiaries were reported by the LEAP Management Secretariat as enrolled onto the NHIS, but the NHIA is not able to confirm this as the NHIS MIS classifies LEAP beneficiaries under the indigent category, which is made up of LEAP, as well as other vulnerable people such as persons with mental illness and others referred to the NHIA by the Social Welfare Department. Further efforts are needed to be done to address the above. This milestone was partially achieved.

a) MoU signed

b) Initial emergency processes, data collection/sharing protocols, and gaps identified, to provide skeleton for shock-responsive SP roadmap Assessment of Ghana’s social protection system readiness for shock response ongoing by the American Institutes for Research has started. It aims to assess the country’s social protection system’s readiness highlighting disability, gender- and age-responsive approaches to maintain its routine function in times of crisis and/or adjust on its own or in coordination with other departments/ministries to accommodate new populations and needs as a result of shock; and to contribute to resilience building of individuals, households, communities and systems to future shocks. To ensure a holistic assessment for Ghana, a Technical Working Group (TWG) made up of experts from a number of MDAs representing government interest, CSOs and DPs has been set up to oversee, monitor and review the work of the research team undertaking the assessment. It is expected that with the guidance of the TWG, the research will come out with recommendations setting out a series of potential options highlighting gender- and age-responsive and disability inclusion approaches that the Government of Ghana, will use as a basis for reflections to respond to the needs of households and individuals affected by emergencies such as climate change hazards and man-made disasters. Currently, data collection and data sharing protocols are yet to be finalised. This milestone has been partially achieved.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

In 2022, further ODA cuts to the LNOB programme meant cuts to the World Bank Trust fund in the tune of £4.4m. This meant that we could no longer support the delivery of regular cash transfers and shock responsive social protection. Cuts to our support to the WBTF resulted in delivery risks and reputational damage which threatened our relationship with the World Bank and with the MoGCSP. However, these were mitigated through high level dialogue and engagement between the World Bank and FCDO Ghana’s at the senior leadership level.
Whilst there was a leadership vacuum at the MoGCSP for most of 2022, towards the end of the year, a new substantive Minister was vetted and approved by Parliament. As a result, this has mitigated various delivery risks to the LEAP which the Ministry had been facing. Whilst FCDO will no longer be providing bilateral support to the MoGCSP for social protection, we have begun to explore opportunities through the CMP – STAAR – to provide TA to support the Ministry’s work on strengthening gender responsive social protection.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The previous AR recommendation prioritised mitigation of safeguarding risks. During the review period, the SDDirect Safeguarding / SEAH review was undertaken and the final report was completed and shared with partners taking forward various lessons learned and recommendations. This includes strengthening engagement with Ministries of Gender and Health on SEAH. E.g. tapping into existing knowledge from the Ministries of Gender and Health’s service mapping tools to build on rather than duplicate work already done and identify gaps in inclusive service mapping to strengthen the provision of accessible referral pathways for persons with disabilities. FCDO should also leverage WB social safeguards expertise – find opportunities to learn lessons and share best practices with the WB in terms of social and environmental safeguards. There may also be opportunities to engage in the Global Framework – the Safeguarding Unit will set up a steering committee on SEAH in 2023 which will include countries such as Ghana. This is a good opportunity for LNOB implementing partners to share learning and best practices on SEAH.
Recommendations for this year: FCDO to continue to strengthen engagement with GoG and Development partners within the social protection sector. In the next FY, it is recommended that FCDO continues to engage in the sector both by providing TA support to strengthen gender inclusive social protection and to influence GoG, multilaterals and other DPs through participation in the Social Protection Sector Working Group and Social Protection DP meetings.

Output Title	Increased access to quality integrated, disability inclusive community based and recovery oriented Mental Health and other health services including services delivered by traditional and faith-based leaders
Output number:		3	Output Score:	B
Impact weighting (%):		20%	Weighting revised since last AR	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Extent of implementation of Quality Rights Initiatives in health facilities.	Reassessment of the 8 Health Facilities to document WHO Quality Rights improvements completed.	Achieved
3.2 GoG procurement of psychotropic drugs and availability of psychotropic drugs at all levels.	Availability of Psychotropic Medicines at all levels of care.	Partially achieved (psychotropic drugs not yet disseminated)
3.3 Number of persons with disabilities including Mental Health conditions and other vulnerable groups benefiting from community-based initiatives including through civil society and Self Help Groups (SHGs).	640 people benefiting from continued SHG activities Sensitisation of all 16 regions on the revised District Assembly Common Fund (DACF) guidelines completed. 3,000 people benefiting from Evidence and Effectiveness Grants	(a) Exceeded – 16.906 people benefited from SHG activities (attendance at meetings and home visits by community volunteers) (b) Partially achieved – 10/16 regions sensitised by Dec 2023 (end of prog Year 3) (c) Exceeded – grants activities have directly reached 29,658 people
3.4 Number of persons with disabilities including Mental Health conditions and other vulnerable groups benefiting from COVID-19 support.	This milestone has been finalised and has now been closed.	N/A

Briefly describe the output’s activities and provide supporting narrative for the score.

The output score is B. It measures against work to increase quality integrated disability inclusive community based Mental Health services.

This milestone was achieved during the period under review. The WHO Quality Rights assessment for the 8 facilities were completed and achieved. Service improvement plans were developed and implemented based on gaps identified and a post implementation assessment was completed to measure the gains made. A reassessment of 8 health facilities was completed in September 2022 which included 3 psychiatric hospitals and 5 general hospitals with in-patient psychiatric facilities. Preliminary findings revealed an improvement in people-centred and human-rights-based care, including training of staff on de-escalation techniques to manage aggression instead of resorting to physical restraints. Some of health facilities modified their infrastructure to make them more disability inclusive in order to accommodate clients with mobility challenges. A key challenge noted by staff at some of the health facilities was the lack of adequate resources available to implement the full set of recommendations identified for improvement. A monitoring visit to the psychiatric facilities revealed a few positive practices being rolled out by pro-active health professionals. E.g. community Mental Health drives, community screenings and fundraising events to fill gaps due to budget shortages.
 Indicator 3.1 Extent of implementation of Quality Rights Initiatives in health facilities.

Indicator 3.2 Government of Ghana procurement of psychotropic drugs and availability of psychotropic drugs at all levels. The aim of this indicator is to provide quality and affordable psychotropic medicines at all levels of care for the management and treatment of persons with psychosocial, intellectual, and cognitive disabilities, in line with appropriate prescribing practices and procurement procedures. the outputs for this indicator have been positive. The procurement of psychotropic medications was completed for 2021, including the distribution at psychiatric hospitals across the country. The procurement of the 2022 medications commenced through a competitive tendering process, the drugs will be distributed in 2023. There are also ongoing efforts by MHA to ensure Mental Health is included in the NHIA benefits package. This milestone was only partially achieved as dissemination of the psychotropic drugs is yet to be done. An assessment of the full set of 2022 RbA milestones is yet to be completed for the Year in review.

Indicator 3. 3 Number of persons with disabilities including Mental Health conditions and other vulnerable groups benefiting from community-based initiatives including through civil society and self-help groups.

This indicator is made up of three milestones focusing on different thematic areas under the GDS:

640 people benefitting from continued Self Help Groups activities
This milestone exceeded expectations during the period under review, the work of the SHGs and community volunteers reached 16,906 people. This included training and interface meetings, as well as community volunteer support for nearly 800 SHG meetings (including SHGs beyond the 32 receiving additional support from the programme) and over 3,000 home visits. Over the year, 8,229 SHG members (4,617 women) were reached by community volunteers with COVID-19 safety and hygiene messages.
Sensitisation of all 16 regions on the revised District Assembly Common Fund (DACF) guidelines completed.
This milestone was partially achieved. Regional sensitisation on the revised DACF Disability Fund guidelines reached ten of the 16 regions in Ghana with excellent levels of engagement at the local level with civil society and government. The remaining six regions will be reached before the end of the programme year in March 2023, having been delayed during 2022 following an activity pause from FCDO. The roadshows have generated high interest and commitment by senior government officials, including Regional Ministers, Chief and Coordinating Directors, and heads of DSW at both regional and district levels.
C) 3,000 people benefiting from Evidence and Effectiveness Grants
This milestone was exceeded. Through grantees, 29,658 people were reached during the year, of which 51% were women. Overall, the programme directly reached 49,074 people.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The weighting has not been revised in this AR. During the review period, the WHO no-cost extension was approved to extend their agreement for a further 6 months in order to complete outstanding programme activities, impacted by COVID-19 by June 2022.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations the year ahead

Due to previous safeguarding concerns, a key recommendation from the previous AR was for LNOB to conduct a safeguarding review. LNOB commissioned SDDirect to undertake a Safeguarding review to assess compliance among 5 implementing partners and downstream partners (WHO, Basic Needs Ghana, Options, Mental Health Authority (MHA) and the LEAP Management Secretariat (LMS).

The Safeguarding /SEAH review was finalised in August 2022 and thereafter, the SDD project team provided a report with findings on the strengths and gaps in LNOBs safeguarding framework and implementation and provided a roadmap of recommended and prioritised actions and 30 days of technical assistance.

A key recommendation for the year ahead is for LNOB to ensure that recommendations from the safeguarding review are prioritised by LNOB implementing partners and downstream partners. Furthermore, FCDO should ensure that the previous recommendation to ensure implementing partners and downstream partners receive periodic and ongoing training on safeguarding is taken forward. This includes increased spot checks and monitoring to ensure guidance is provided to mitigate against any safeguarding risks.

Output Title	Attitudes, behaviours and norms related to people with disabilities and including Mental Health conditions transformed.
Output number:		4	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 Number of people reached with Mental Health and disability inclusive messages.	a) Positive language guides being disseminated b) Vox Pops for World Mental Health Day (WMHD) disseminated c) Communications plan delivered	(a) Achieved (b) Achieved (c) Achieved
4.2 Number of health professionals, community members and traditional leaders trained in stigma reduction, discrimination and human rights violations.	Supportive supervision following MHGAP training in 4 regions (Greater Accra Region (GAR), Eastern Region (ER), Volta Region (VR) & Central Region (CR) completed	Achieved
4.3 Number of civil society organisations which have participated in or had engagements with government in advocacy, policy development or implementation of policies linked to the rights of people with disabilities, including Mental Health, within their grant mechanism	(a) Two CSOs implementing advocacy grant agreements B) Launch of sustainability and legacy grants for DPOs and WROs	(a) Achieved (b) Achieved
4.4 Level of awareness of COVID-19 related risk communications by persons with disabilities and Mental Health conditions	N/A	This milestone was not assessed. No further work planned.
4.5 Number of health professionals, equipped with guidance on COVID-19, mental wellbeing, and rights-based approaches	N/A	This milestone was not assessed. No further work planned.

Briefly describe the output’s activities and provide supporting narrative for the score.

The output score A. It measures against work to transform attitudes, behaviours and norms related to people with disabilities and Mental Health conditions.

Indicator 4.1 Extent of public awareness and sensitivity to Mental Health issues in Ghana.

The milestones for this indicator during the period under review comprised of three areas:

Positive language guides being disseminated.
The UK Government under the GSD project awarded grants to nine civil society organisations in under the Evidence and Effectiveness grant which comprised of five small grants and four large grants. Grantees developed local language guides that are contributing to the increased use of positive disability and Mental Health language. This included VOICE and Hope for the Future Generation (HFFG) / PsyK Forum who have disseminated soft copies of the positive language guides. This milestone was achieved.

Vox Pops for World Mental Health Day (WMHD) disseminated
Vox pops were disseminated on programme YouTube channel and shared through partner social media channels, Mental Health Alliance, and on BNGh WhatsApp platforms, Coalition for Mental Health Reform, and the Mental Health Advocacy group, and to grantees and district demonstration sites. The advocacy goal (inauguration of Tribunal and Visiting Committees) was attained. This milestone was achieved

Communications plan delivered
A communications plan was enacted during the review period, including dissemination of short films on the work of COVID-19 Resilience grantees; supporting high-level round table on alleged witches’ camps; engaging in International Women’s Day (IWD) and International World Mental Health Day (WMHD); supporting launch of Legacy Grants. This milestone was achieved.

Indicator 4.2 - Number of health professionals, community members and traditional leaders trained in stigma reduction, discrimination and human rights violations.

Supportive supervision following MHGAP training in 4 regions (Greater Accra Region (GAR), Eastern Region (ER), Volta Region (VR) & Central Region (CR) completed
Under the review period, 732 health and non-health professionals and persons with lived experiences were trained. (male – 472 and female- 360). In addition, 152 traditional and faith-based practitioners were trained (male – 98 and female 58). This milestone was achieved.

Indicator 4.3 Number of civil society organisations which have participated in or had engagements with government in advocacy, policy development or implementation of policies linked to the rights of people with disabilities, including Mental Health, within their grant mechanism.

Two CSO organisations implementing advocacy grant agreements
The GSD through 2 large grantees – the Ghana National Association of the Deaf (GNAD) and Songtaba, continued their implementation of advocacy grants agreements. They conducted evidence to bolster policy influencing and advocacy work to address stigma and discrimination on the unmet Mental Health needs of deaf people, and women accused of witchcraft, respectively. As part of their respective dissemination plans, on 31 August 2022, BHC hosted a roundtable addressing issues of witchcraft allegations, featuring Songtaba, CHRAJ, and an anti-witchcraft allegations bill. In December, GNAD presented their research findings at the MHA International Research Conference. This milestone was achieved.

The Launch of Sustainability and Legacy grants for DPOs and WROs
As with milestone (a), this milestone was also achieved. The Legacy and Sustainability grants round was launched in June 2022 and grantees were selected and started implementation in November 2022. This was the GSD’s third round Call for Proposals. Due diligence was undertaken successfully on all applicants and grant agreements signed. A 4-day capacity-building training was organised for successful applicants and organisational capacity assessments were undertaken.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The weighting is 15% it has not been revised since last year’s AR. The Output 3.1 was revised during the period in review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

A previous recommendation was to work with implementing partners to increase COVID-19 vaccination awareness with a particular focus on persons with disabilities and Mental Health conditions, women and the elderly. This would help to determine the different concerns from different groups in relation to vaccine uptake and to find ways these concerns can be addressed.

Under the Ghana Somubi Dwumadie (GSD) programme there were engagements with GoG to advise GHS health promotions unit on the development of messaging featuring people with disabilities, and this was used to reach 8,229 SHG members (4,617 women) by community volunteers with COVID-19 safety and hygiene messages.

In terms of recommendations for the year ahead, FCDO will continue to monitor implementing partners progress in integrating COVID-19 vaccination messaging into communications as well as disability and Mental Health outreach activities in order to change perceptions, attitudes, behaviours and social norms in relation to COVID-19 vaccines. This is to ensure that Ghana’s COVID-19 response targets the most marginalised and vulnerable and to ensure it is based on equity, evidence and transparency.

Output Title	Effective scale up of disaggregated data collection across all partnerships and generation of high quality research, evidence, learning and what works to inform programming.
Output number:		5	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR	No

Indicator(s)	Milestone(s) for this review	Progress
5.1 Level of secondary analysis of Multiple Indicator Cluster Surveys (MICS) Ghana Living Standards Survey (GLSS data to identify vulnerable girls and boys as well as their caregivers as well as socioeconomic & geographic determinants of vulnerabilities	Demographic and Health survey using update sampling frame from 2021 census to track data for over 30 SDG indicators	Partially achieved (data collection is not yet completed and is ongoing with result expected in 2nd quarter 2023 and final report in 3rd quarter 2023).
5.2 Extent of interoperability of social welfare system Management Information Systems (MIS) with other databases.	Transition of hosting of SWIMS from UNICEF to the Government owned servers in collaboration with the National Information Technology Agency (NITA)	Partially achieved (the testing and full transition have not been completed. This is expected to be completed by early 2023).
5.3 Extent to which findings from a) the Safeguarding Review and b) the Rapid Review Scoping Study and Assessment on Disability and Gender inclusion informs the Ghana Productive Safety Net Programme (GPSNP).	SDD team deliver agreed 1 to 1 support to LNOB implementing partners as part of the LNOB Safeguarding review and submission of final project report	Achieved
5.4 Assessment Instrument for Mental Health Systems AIMS implemented and extent to which it informs the implementation of the Mental Health Strategy.	AIMS conducted and report disseminated	Achieved
5.5 Extent to which findings from the COVID-19 Rapid Review Scoping Study informs the GoG COVID-19 response and secondary impact mitigation interventions.	This milestone will not be assessed. The programme produced the report and shared. No further work planned.	N/A
5.6 Progress on implementation of legislation relating to disability, including the Disability Amendment Bill	Ongoing advocacy and policy support provided for the passage of the Disability Amendment Bill	Achieved
5.7 Proportion of target districts with district plans which integrate disability, including Mental Health at a primary care level.	100% of demonstration districts have met indicator measure level A, B and C, (i.e. A) have and approved plan B) have conducted relevant training and C) have an ongoing supervision plan for Primary Health Care (PHC) staff on Mental Health	Achieved
5.8 Access to quality integrated services at the primary health care (PHC) level for people with disabilities, including Mental Health disabilities.	Advocacy tool for Accessibility completed	Achieved
5.9 Number of operations research studies conducted and disseminated that support an enabling environment, policy, and practice.	Programme produces 1 dissemination product	Exceeded

Briefly describe the output’s activities and provide supporting narrative for the score.
This output scored A. It measures the effective scaling up of disaggregated data collection and generation of high-quality research, evidence and learning and what works to inform programming. The weighting for this output was raised in 2020 from 5% to 15% and has been retained as it contains some of the more crucial elements to enabling a more joined up social protection and social welfare system.

Indicator 5.1 – Level of Secondary Analysis data to identify vulnerable girls and boys

Enumerator training and household registration for the Demographic and Health Survey (DHS) has been done. Data collection ongoing with result expected in 2nd quarter 2023 and final report in 3rd quarter 2023. This milestone was partially achieved.

Indicator 5.2 – Extent of interoperability of SWIMS with other databases

Throughout 2022, UNICEF has been supporting MoGCSP in collaboration with NITA and UNICEF- HQ Primero Team to develop the Local Hosting of SWIMS. The proposed solution delegates the responsibility for managing the physical infrastructure to local country teams while keeping the responsibility for managing and operating Primero services with UNICEF. The testing and full transition are expected to be completed by early 2023 This milestone was partially achieved.

Indicators 5.3 - Extent to which findings from a) the Safeguarding Review and b) the Rapid Review Scoping Study and Assessment on Disability and Gender inclusion informs the Ghana Productive Safety Net Programme (GPSNP).

A) Between August 2021 and August 2022, LNOB commissioned SDDirect to undertake a Safeguarding review to assess compliance among 5 implementing partners and downstream partners (WHO, Basic Needs Ghana, Options, Mental Health Authority (MHA) and the LEAP Management Secretariat (LMS). The review was finalised in August 2022 and thereafter, the SDD project team provided a report with findings on the strengths and gaps in LNOBs safeguarding framework and implementation and provided a roadmap of recommended and prioritised actions and 30 days of technical assistance. This milestone was achieved.

B) This was a key piece of work which sought to understand the extent to which vulnerable households that include people with disabilities have been appropriately included into LEAP and if there have been any challenges. The research found evidence for attitudinal, institutional and environmental barriers in access to social protection programmes in Ghana by people with disabilities particularly disabled women and women with disabled children who were more likely to report feeling isolated and unsupported. In 2021, LMS made progress in drawing up an action plan to implement key recommendations from the scoping study report. This has been completed with LMS developing a plan to undertake a safeguarding review of pay points and drafted a ToR for the establishment of an Advisory Group of people with disabilities, including Mental Health disabilities to support LEAP to mainstream disability across its operations (due to cuts to our support to the WBTF and LEAP, this piece of work has been concluded).

Output Indicator 5.4 AIMS implemented and extent to which it informs the implementation of the Mental Health Strategy.

This milestone was achieved. AIMS conducted and report disseminated among a wide stakeholder group with recommendations to guide government policy and strategy development and implementation.
AIMS will track improvements and provide a baseline for monitoring further change and enable Ghana to develop information-based Mental Health plans. The findings highlight the governance structures available for delivery of Mental Health services in the country, including key protections and inherent gaps.

Indicator 5.6 - Progress on implementation of legislation relating to disability, including the Disability Amendment Bill

The milestone for this indicator is advocacy and policy support provision for the passage of the Disability Amendment Bill, and this milestone was achieved. During the period under review, GSD provided support through the GFD, the Parliamentary Caucus and directly to MoGCSP. The caucus was assisted to develop a clear action plan for their sustainability and developed questions to ask in parliament on key issues such as: progress of the Disability Amendment Bill; ratification of African Disability Protocol; implementation of the Ghana Accessibility Standard on the Built Environment (GAS); and inclusive education.

Output Indicator 5.7 Proportion of target districts with district plans which integrate disability, including Mental Health at a primary care level.

The milestone for this indicator was to ensure that 100% of demonstration districts (Bongo, Ansunafo North and Anloga) have an integrated Mental Health plan, and this milestone was achieved. During the period in review, Mental Health Gap Action Programme (MHGAP) training built the capacity of 84 non-Mental Health professionals from 15 selected health facilities across all three demonstration districts. A 2-day training of 17 trainers who then trained 87 Community Health Volunteers was also carried out. The three District Mental Health Operation Teams have a supervision plan and have started supervision of PHC staff and volunteers. Standard Operating Procedures (SOP) developed and supervision is underway.

Output Indicator 5.8 - Access to quality integrated services at the primary health care level for people with disabilities, including Mental Health disabilities.

The milestone for this output was achieved during the period under review. The Accessibility Toolkit for Advocacy has been developed. It provides the steps for raising awareness, engaging relevant duty bearers and conducting accessibility audits in existing buildings and environments.

Output Indicator 5.9 -Number of operations research studies conducted and disseminated that support an enabling environment, policy, and practice.

The milestone for this indicator was to produce one dissemination product, and that milestone was exceeded. During the period under review the GSD submitted key piece of evidence developed by the programme which continues to be used by GoG and civil society stakeholders titled ‘Why Ghana needs to invest more in Mental Health’. The other most commonly cited pieces of evidence are a suite of documents under the District Mental Healthcare Plan Framework, used for government Mental Health policy and planning, and the Evidence-based Review of the DACF Disability Fund Disbursement and Management Report, used for policy and advocacy work.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

There has been progress in relation to recommendations from the previous AR and support in terms of the LEAP Rapid review has been completed.

Going forward, there are opportunities for FCDO to learn lessons from ISS and SWIMS. In particular, during the UNICEF’s monitoring visit in October and November 2022, it was acknowledged that SWIMS is a game changer in data collection and in facilitating individual case management.

Prior to SWIMS, case management and data recording in terms of social welfare and child protection were paper based. This had issues with data completeness, quality, sensitive data protection and overwhelming workload for the staff writing and managing papers.

As a result of SWIMS, district staff testified that districts have stronger data tracking, collection and disaggregation, case monitoring, reporting and referrals. Currently, a discussion is ongoing with the Ministry of Employment and Labour Relations to build a system interoperability between SWIMS and the Ghana Child Labour Monitoring System (GCLMS).

Given FCDO’s focus on the North and insecurity, it is interesting to note that UNICEF is also exploring opportunities to add new features in SWIMS to strengthen family tracing and reunification in the case of shocks and emergencies (including potential Sahel crisis in the North) and SGBV incident monitoring.

## D: VALUE FOR MONEY

Key cost drivers and performance:
The main cost drivers of the programme remain project staff costs including overheads, grants (to downstream partners via our main implementing partners), technical assistance as well as other project activity related costs.

VfM performance compared to the original VfM proposition in the business case

The main cost drivers identified in the Business Case (BC) remain valid i.e., grants; staffing/technical assistance; programme/research activities; communication and monitoring and evaluation. Per the Business case, FCDO planned to develop an overarching Value for Money (VfM) framework at inception to cover all components of the programme. However, while this was not done, all partners drew up project specific VfM indicators to cover the standard 4 Es being economy, efficiency, effectiveness, and equity which they report against at the end of each respective agreed reporting period.i.e. quarterly or six monthly.

Economy

WHO: The cost of in person training workshops such as the MHGAP (Mental Health Gap Action Programme) and Quality Rights (QR) initiative have been kept to a minimum as the approach has been to deliver a Trainer of Trainers - style workshop to build the capacity of regional trainers in addition to e-training of participants. With this, the expectation is for downstream training to be cascaded to the district level at minimum cost. The recruitment of local staff by the WHO Country Office to provide technical assistance to the project also resulted in some savings of about $24,000 which contributed towards the procurement of a vehicle for the Mental Health Unit of Ghana Health Service to improve efficiency of delivery. The QR also reduced the need for printing of manuals and travel costs typically associated with in person trainings. These are low-cost strategies enabled high reach (22,210 people fully trained with certificates) and large impact.

Options/Ghana Somubi Dwumadie (GSD): Unit costs for short term technical assistance (STTA) reduced by 11% in the last year, and 48% less than the original proforma benchmark. In line with the programme’s approach of leveraging national expertise, national STTA accounted for 68% of all STTA days in 2022, which is a 12% increase on the previous year. Consolidated average daily fee rates for 2022 also represent a reduction against the benchmark, and a continued reduction on the Year 2 figure of GBP 214. This is driven by having a stable team and careful management of fees.

UNICEF: Under the V&E assessment and Shock Responsive consultancy, contracts were competitively awarded and cost effective.

Efficiency

WHO: The application of the QR methodologies for implementation means that for every 1 person trained, it is estimated that the lives of at least 20 more people will be positively impacted through the sharing of knowledge acquired on Mental Health best practice that ensure improvement in quality of Mental Health care. Therefore, by training 22,210 people in Ghana, the lives of an estimated 444,200 people (patients and carers) are improving (indirect impact of the project). Additionally, the MHGAP relies on integration, thus maximising the efficiency of health workers to prevent, detect and refer, inter alia, reducing long-term costs of the burden of Mental Health on the health system.

Options/Ghana Somubi Dwumadie (GSD): The programme captures, uses and disseminates evidence in a wide variety of ways including through learning events for grantees, the development of evaluation reports, learning products and journal papers. The programme also uses a range of externally produced evidence to inform and support the work, e.g. the work on district Mental Health care plans continues to be based on the Programme for Improving Mental Health Care (PRIME) model and MHGAP tools from WHO were used to train healthcare workers. WHO QR Toolkit was used as a basis for training the Regional Mental Health Visiting Committee members, using both the original tools for assessing formal facilities, and having developed adapted tools for assessing informal facilities. The programme design and use of locally embedded expertise, supplemented by global evidence as relevant, drives programme efficiencies.

RBA: The pause on activities with the MHA remained for most of the FY which did not allow FCDO to agree milestones for RBA with MoH/MHA. Notwithstanding, the MoH/MHA proactively worked towards various milestones intended to be put forward following initial discussions with FCDO. Once the pause was lifted, FCDO worked quickly with the MoH/MHA to agree the milestones for assessment.
UNICEF: The overall design and implementation of interventions have been evidence based and ability to leverage investments across sectors, while capitalising on existing investments to avoid duplication. For example, the delivery of ISS/SWIMS and social welfare system strengthening contributes to the improvement of the overall performance of social protection and social welfare service delivery.

Effectiveness

WHO: QR and MHGAP interventions, including capacity building, service assessments and improvement/transformation plans, are evidence-based and have demonstrated effectiveness in improving capacity, whilst promoting all rights-based approaches to Mental Health services and other agencies related to health such as the Department of Social Welfare. Collaborations with other agencies such as UNICEF and the GSD project were put in place to strengthen the project’s overall effectiveness.

Options/Ghana Somubi Dwumadie (GSD): The programme was able to deliver each quarter’s deliverables on time, and in full, to the FCDO. Grant disbursements to grant partners were made on time i.e. within 30 days of an accurate and approved disbursement request being received.

RBA: FCDO was able to agree milestones with MoH/MHA once the pause was lifted before end of calendar year December 2022. The MoH/MHA worked quickly to submit their reports for FCDO assessment by the January 2023 agreed date to ensure that the assessment of milestones could be carried out in time for fund disbursement by end of FY 2022/23.

UNICEF: The ISS/SWIMS case management and referral system through linking vulnerable beneficiaries to multiple services across health/NHIS, social protection, child protection, DOVVSU and social welfare highlights the effectiveness of the intervention. The use of SWIMS and the shift from manual case management to electronic and digital means has proven to be cost effective. This has in turn increased the number of beneficiaries who now have access to quality social services and referral systems.

Equity (including gender equality and disability):

WHO: This project enabled progress towards ensuring that people with Mental Health conditions, psychosocial and intellectual disabilities (with emphasis on gender equality and Mental Health conditions) have equitable access to training aimed at building capacity, changing attitudes and practices among a wide range of national stakeholders including service providers. Through this project, 685 primary health care staff (including 274 females) across the country have strengthened capacity in the identification and management of common Mental Health conditions, which they are using to improve Mental Health service delivery. Key target groups were the youth (both males and females) and service users who have been empowered to advocate for equity and inclusiveness of all groups. The Quality Rights Initiative has successfully created awareness among 22,210 individuals (including 9900 females) who have earned a certificate in the e-training.

Options/ Ghana Somubi Dwumadie (GSD): The grantees under the Evidence and Effectiveness grants are implementing SBC (social behaviour change) and advocacy interventions to reduce stigma and discrimination. All grantees were assessed against their participatory approaches at application stage, and this forms part of regular monitoring. In view of this, all the programme’s grants recipients are inclusive and participatory. Two of the current large grantees, Ghana National Association of the Deaf (GNAD) and VOICE Ghana, are DPOs (Disabled People’s Organisations) and the remaining two, Songtaba and Hope for Future Generations (HFFG) are WROs (Women’s Rights Organisations).
All the five new Legacy grantees are either DPOs or WROs addressing core issues of gender equality, VAWG and disability or Mental Health. In 2022, the programme successfully reached a total of 49,074 people directly, of which 26,181 were women, through its grants and non-grants activities. The ongoing grantees have been encouraged to include accessibility budgeting to support the attendance of both those with disabilities and their carers and assistants, and this is likely to be a good strategy for increasing the number of women with disabilities or Mental Health conditions who would be reached.
UNICEF: Interventions such as ISS/SWIMS prioritise investment and support to the most excluded and marginalised populations in Ghana.
Assessment of whether the programme continues to represent value for money
As noted above, partners have delivered against their VfM markers around the 4Es. The linkages in how partners on the programme have worked together (where there have been synergies) are clear and promote the 4Es. Evidently the programme continues to represent value for money through savings made, efficient use of resources (even through hard budget cuts and pauses) and effectiveness in delivering outputs and outcomes to ensure that the marginalised are adequately reached and impacted.
The programme also continues to play an important role in the wider FCDO portfolio by providing lessons and data on innovations in human development with the potential to have a transformational impact.
Recommendation: Given that the programme is entering into its final year with nearly all components closed/closing, the LNOB Team must continue to monitor VfM on existing workstreams and ensure indicators are still relevant and being met.

E: RISK

Overview of risk management

The LNOB programme maintains an overall moderate residual risk rating. This is within FCDO Ghana’s acceptable risk appetite for the country office. A few risks identified during programme implementation around operational, reputational and delivery risks have been successfully closed including one SEAH issue which was reported and subsequently closed within this FY. No further SEAH incidents have been reported by partners. Partners maintain risk registers which helps to monitor risks per project.
Other major risks remain high in the programme which the programme team continues to actively monitor and work to mitigate. A key risk area is safeguarding as LNOB continues to work with vulnerable groups, including where there have been documented human rights violations/abuses within formal and informal institutions such as prayer camps and psychiatric hospitals, etc. As part of mitigating the safeguarding risk, the programme carried out an extensive safeguarding assessment on all IPs, reviewing the following areas of work: Organisational Culture; Human Resources; Partners and Programming; Governance and Accountability; Risk Management; Safeguarding against SEAH Framework; and Whistleblowing and Case Management. This was done to ensure that the necessary SEAH awareness and controls were in place within all components of the programme and to ensure quick response systems were available in the event of any safeguarding issues that would arise.
Another risk that is keenly monitored is financial & fiduciary risks – particularly where monies disbursed by implementing partners to downstream partners, including Government Ministries/agencies may not be used in line with FCDO policy. As part of the mitigation measures, implementing partners ensure that robust due diligence assessments are conducted on all downstream partners before agreements are made and funds are disbursed. Options Consultancy/GSD conducts quarterly grantee monitoring visits and provides capacity building support to their grantees. As part of WHO’s controls, Direct Implementation (DI) is used where the WHO pays directly for the services required for programme implementation as a way of reducing fiduciary risks.
FCDO also receives audited financial statements from the multilateral partners and has a contract in place with PwC for an annual audit of the GSD programme. The first audit of the GSD programme did not find any significant issues that would deter continuous programme implementation. However, an audit implementation plan which contained a summary of findings and action points was produced as a tracking tool. Options as lead partner has put measures in place to address all the findings satisfactorily. At the time of this review, the second annual audit has begun.
Delayed delivery was noted as a risk area and occurred due to the capacity of Government ministries to effectively implement the programme and be responsive to FCDO demands. A pause put in place by the FCDO on some aspects of delivery resulted in the temporary halt in the delivery of some activities within the FY. This was in addition to a programme pause on our work with MHA and resulted in underspends against originally approved budgets as partners were unable to progress some activities. ODA budget cuts delayed confirmation of budget allocations also affected partners’ ability to deliver and to mitigate. FCDO gave as much information as was available to partners and worked with partners to move forward with activities as was possible within the operating context at the time.
There also remains a major risk related to Strategy and Context. GOG is faced with the challenge of funding due to the current macro-economic crisis in Ghana. FCDO, in collaboration with UNICEF and other DPs are supporting Government in an ongoing IMF bailout negotiation process which is expected to stabilise the economy. The lack of political will remains a challenge and means government does not appear to prioritise spend on social protection. According to the 2023 National Budget statement, the IMF Programme is expected to prioritise social protection programmes (including the Livelihood Empowerment Against Poverty (LEAP) and School Feeding Programme), to ensure that the impact of the adjustment on the vulnerable and poor is minimised, and this partly became possible due to series of engagements held with GoG by Development Partners, influencing the GoG to allocate more resources to the sector.
The current high rates of inflation, prices and exchange rates in the country also makes forecasting problematic and unpredictable. The mitigation measure has been to work closely with partners to ensure regular reforecasting and planning.

Update on Partnership Principles

The LNOB programme provides some direct funds to Government through Results-based Aid under an MoU with the Ministry of Health. The partnership principles of poverty reduction and the sustainable development goals; management of public finances; tackling concerns about human rights abuses and corruption; and improving domestic accountability are regularly assessed by FCDO. The last update was done in April 2022.

In a context of extreme fiscal constraint, poverty reduction expenditure (especially for health and Social Protection) continues to fall, driving poor people even deeper into poverty whilst creating new categories of poor and vulnerable struggling to meet their basic needs. For instance, the LEAP cash transfer to the extreme poor has been in arears while government’s ability to enrol more extreme poor people onto the programme could not be realised due to the fiscal challenges. Similarly, disbursement of the District Assembly Common Fund (DACF) which is the main source of revenue for poorer districts and relied on by PWDs who face economic difficulties was erratic over the period under review. Stronger and sustained GoG commitment to increasing the share of resources allocated and expended on the social sectors has for the main not been realised during the 2022 AR period but is urgently required to stop the reversals, and restart work on achieving the SDGs.

Ghana’s human rights records is considered generally good. It has well developed democratic structures that promotes fundamental human rights and enabling environment that supports civic activism. However, persistent inequalities and discrimination in experience still exist. There are significant gender disparities and violence against women and girls remain widespread. Currently, a Private Members Bill is before parliament to criminalise LGBT+. The Bill if passed potentially increase stigmatisation and reduce access to social services (especially health) by the LGBT+ communities if the Bill is passed into law.

On domestic accountability, Ghana’s commitment is evident in cooperation and responsiveness of duty bearers (e.g., Ministers, parliamentarians, civil servants etc) to CSOs/citizens demands. CSO partners had access to both the executive and legislative during the period under review.

It is assessed that the Government of Ghana is broadly committed to the UK’s four Partnership Principles. The overall risk is assessed as high.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

World Bank Trust Fund: FCDO did not transfer the remaining balance of £8.9m to the WB due to budget cuts as a result of the economic situation in the UK over the past two years. An official letter was sent to the WB Country Head to formally inform him of the budget cuts. The Administrative Agreement was amended accordingly to reflect the exact amount transferred as at the time of writing. The audited financial reports covering the period July 2021 – June 2022 conducted by Deloitte and Touche for the SDTF was received. The audit report obtained an unqualified audit opinion and the TF according to the report, maintained in all material respect, effective internal financial controls implemented in line with the Financing Agreement. Quarters 1 and 2 progress reports were submitted while quarters 3 and 4/Annual Reports are yet to be received. The Ghana Productive Safety Net Project, a four-year programme ended in December 2022 to make way for the second phase II of the project with no funding commitments from FCDO.

MoH/MHA: The MoU was signed in January 2020 for the MoH/MHA to deliver improved Mental Health services in Ghana in the RbA. Total allocation for the RbA is £2,000,000 over four years. Payments are based on delivery of agreed milestones using the verification guidelines agreed by all parties and as set out in the MoU. FCDO has so far released a total of £1,190,000. The forecast for the 2022/23 financial year is £400,000. Due to the delay in lifting the MHA activity pause, milestones were agreed late (though preliminary discussions had been initiated). The assessment of the agreed milestones is ongoing at the time of this review, and funds will be released afterwards based on the results of the assessment/verification.

WHO: The Contribution Agreement was signed in November 2019 for delivery of Quality Rights training from 2019 to 2022. Total fund allocation of £1,350,000 has been fully transferred to WHO. Originally, the Contribution Agreement was expected to end on 30th June 2022 but WHO was granted a no-cost extension to 30th September 2022 due to delays in implementing one key programme activity i.e., “Assessment of the Mental Health Facility” which delayed due to the MHA pause. WHO spent 99% of their total budget from the contribution agreement. FCDO received the final project reports and declared a balance of $1,007/£822.82. According to a 2022 due diligence assessment conducted by FCDO, there was no indication that WHO Ghana was internally audited in the year 2020/2021. However, there was a compliance audit in October 2021 with an implementation/action plan on the recommendations from that audit. The latest version of WHO’s external audit report that was publicly available is the 2019 edition. WHO received an unmodified/unqualified audit opinion - meaning the financial statements were presented, in all material respects, in accordance with applicable financial reporting standards. The audit also concluded that the transactions that were reviewed and tested as part of the audit of the financial statements were, in all significant respects, compliant with the Financial Regulations and legislative authority. There is however delay in the publishing of the 2020 and 2021 reports. Overall, reports were submitted on time and regular catch-up meetings held with FCDO to discuss progress of the project.

UNICEF: The Contribution Agreement for £1,550,000 with UNICEF was signed off in December 2019 for work in Strengthening Integrated Social Services and Vulnerable & Excluded assessment. Additional £900,000 was provided to respond to the impact of the COVID-19 pandemic, bringing the total budget allocation to £2,450,000. As a result, the contribution agreement was amended on 20th July 2020 to reflect the additional funding. This programme was planned to end by June 2022 but was granted a no-cost extension to complete outstanding activities and therefore ended in December 2022. This extension was necessary due to delays with activities at the MoGCSP because of the absence of a substantive sector Minister. Overall, reports were submitted on time and regular catch-up meetings held with FCDO to discuss progress of the project. The end of project reports are expected in March 2023.

Options/Ghana Somubi Dwumadie (GSD): The GSD programme is delivered through a four-year commercial contract signed from January 2020 with Options Consultancy Services as lead partner of a five-member consortium to deliver on the Disability and Mental Health component of the LNOB programme.
The 2022/23 budget allocation was originally £3,275,961 and was reduced to £2,500,000 (reduction of 23.6%). While no further reductions were made, a pause on specific activities with MHA was introduced in August 2022, continuing through September and extending into October, which resulted in rescheduling and reforecasting. However a combination of an extended pause, rescheduled grant disbursements and exchange rate variances indicates that expenditure for Year 3 at circa £2,114,912.

Options have requested a contract amendment to cover changes in key staff on the programme as well as the change in budget. Options has spent £1,654,823 as at end of quarter 3 (end of December 2022) of this financial year 22/23 with a forecast of £460,089 for quarter 4. Quarterly reports (including the annual report) and invoices were received on time and covered the key reporting areas agreed. Monthly progress review meetings continue to be held between FCDO and Options to discuss progress of work and address any (emerging) challenges. The second annual audit covering the period 21/22 FY has begun (including Options’ consortium and grant partners), and the final report expected at the end of March 2023. A SRM scorecard has not been completed for Options this year. However, FCDO has worked with Options to complete two rounds of KPI reporting required by the UK Cabinet Office in line with transparency requirements. Options maintains a risk register and an asset register which they update and submit to FCDO quarterly.

Asset management

The assets procured by implementing partners (mostly laptop computers/tablets and health equipment) are listed in respective partner asset registers maintained by both FCDO and related partners. Asset Registers have been updated by Options and WHO. An asset verification exercise was carried out during the reporting year with no adverse findings. Majority of assets were in good condition and where assets had been lost or misplaced, FCDO processes have been initiated to address these. A request from WHO on behalf on the Ghana Health Service was submitted to FCDO to retain one vehicle bought as part of WHO’s project. This is being worked on at the time of the review. Options has also submitted a request on behalf of 3 grantees who benefitted from the COVID-19 Grants to retain assets for continued work and sustainability of their projects.

Monitoring activities throughout the review process

The LNOB programme Annual Review process was led by the FCDO Ghana Social Development Adviser with support from the Social Development Adviser from FCDO Tanzania and Programme Managers. The review begun with an inception meeting with the technical subcommittee of the programme where the FCDO review team introduced the approach to the annual review exercise in more detail ahead of one-on-one meetings with various implementing partners. One-on-one meetings were held with UNICEF, WHO, MoGCSP/LMS, Options Consultancy Services Ltd, MoH/MHA and key staff at the Accra Psychiatric Hospital.

As part of this review, the team conducted a field visit to the Kwabre East Municipal Assembly in the Ashanti Region, basically to review progress of work done by partners so far during the implementation period. The team first paid a courtesy call on the District Chief Executive, Hon. Kweku Agyeman Bonsu to brief him on the purpose of our visit in the district. During the field visit, the team met with the Department of Social Welfare and Community Development staff and were briefed on Integrated Social Services (ISS) and how their collaboration with social Protection actors such as the Assembly, Health, Education, Police Service, NGOs, NHIA, and other actors at the decentralised and national levels have improved the delivery of social services across the district.

The team was introduced to the Social Welfare Information Management System (SWIMS – discussed in detail above) and was taken through its functions. The team also interacted with LEAP Beneficiaries at the Ahodwo Community and saw the demonstration of how the CP tool kit is used to engage LEAP beneficiaries gathered at the centre. Finally, the team met with the NHIA District Manager to learn more about NHIA’s work under the ISS - Community outreach, provided statistics on number of indigents enrolled, and how renewals are made for LEAP.

The team had their last meeting with Mental Health Nurses at Jumapo in the New Juaben District in the Eastern Region, where we interacted with the Nurses regarding Quality Rights (QR) and MHGAP training they had benefitted from. According to them, QR has improved their services by way of listening to clients more which was not previously the case, and this has also improved recovery cases. The training has also helped them to stop an old practice of putting medication in the food of clients without their knowledge which they observed was a bad practice. They also observed that probing cases further helps to better administer the right medication which helps clients to recover faster. Some of the clients are now able to work and pay for their medication which prevents relapse. All these meetings and engagements with beneficiaries during the field visit helped give a clearer picture of achievements, challenges and risks in delivery.

Date of last narrative financial report	Options: 31/01/2023 WHO: 20/12/2022 UNICEF: 31/01/2023 MHA/MoH: 31/01/2023 WB: 19/12/2022	Date of last audited annual statement	Options: March 2022 WHO: October 2021 UNICEF: to be confirmed from UNICEF HQ as at time of review WB:12/08/2022