## Annual Review Template – September 2020

Title: LEAVE NO ONE BEHIND AS GHANA MOVES BEYOND AID
Programme Value £ (full life): £39.2 million		Review date: 18/02/2021
Programme Code: [AMP ID#]300385	AMP start date: February 2019	AMP end date: March 2024

Summary of Programme Performance
Year	2020	2021
Overall Output Score	A	A
Risk Rating	Moderate	Moderate

Devtracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/47969225.odt
Devtracker Link to results framework:	http://iati.dfid.gov.uk/iati_documents/54009392.xlsx

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]

Description of programme
Leave No One Behind (LNOB) programme is FCDO Ghana’s largest bilateral programme of support working across poverty, disability inclusion and mental health. The Business Case for LNOB proposed up to £39.2 million over five years (2019-2024) to support the Government of Ghana (GoG) to deliver services to the poorest and most vulnerable and excluded.

LNOB aims to contribute to four areas of change: (1) Improved policy, leadership, resources and governance systems that promote disability inclusion and mental health for all and enable equal recognition and respect for human rights of the extreme poor and marginalised; (2) the extreme poor and marginalised, people with disabilities and mental health conditions enjoying high quality and integrated health and social protection systems; (3) full, active participation and representation and reduced stigma for the extreme poor and persons with disabilities and mental health conditions, discrimination and human rights violations; and (4) improved knowledge and evidence-based understanding of exclusion and what works to improve wellbeing, social and economic outcomes and rights.

The LNOB programme has three delivery mechanisms:

1. Social protection delivered through World Bank Trust Fund working with the Ministry of Gender, Children and Social Protection (MoGCSP) and UNICEF; building on the first phase of Livelihood Empowerment Against Poverty (LEAP).

2. Mental health and disability through the Ghana Somubi Dwumadie (Ghana Participation) programme, a consortium led by Options working with Government, civil society organisations and research partners and aims to support Government and other service providers to scale up delivery of quality and integrated mental health services, particularly at the primary health care and community level.

3. Synergy Fund managed directly by FCDO to provide support for activities which create synergies and linkages between tackling poverty and promoting disability inclusion. These include: supporting UNICEF to strengthen case management and referral and reintegration pathways; Results-based financial aid to Ministry of Health (MoH) to support the strengthening and integration of mental health provision; MoU with WHO to support Quality Rights through technical assistance.
Summary supporting narrative for the overall score in this review [1-2 paragraphs]

1. The programme has largely achieved against its milestones in an extremely challenging year. In 2020, the outbreak of Covid-19 saw the Government of Ghana (GoG) shutting borders and schools and imposing lockdowns in urban centres. This hit the poorest hardest with reports of poverty, gender-based violence and teenage pregnancy all increasing during 2020. GoG provided 5 months of free electricity and 3 months of free water; and looked to provide new cash transfers to vulnerable individuals not reached by LEAP, notably people without housing and residents of so-called ‘witches camps’. ).
3. LNOB pivoted quickly to support the government’s response and meet new, unplanned for needs. Funding was moved from the system strengthening and exit from aid elements (GNHR and PFI) to cash transfers and service delivery, reaching an additional 80,000 households in 2020. LNOB is increased the budget for cash transfers to £12.5m from the planned £5m (and £7.5m less on system strengthening); includes new spend on medical equipment to allow gender-based services to continue despite Covid-19; and has a new strand of work on how to provide services to people with Mental Health Conditions and Covid-19. Milestones were adjusted to take into account the pivot to covid-19 response.

In this way the programme has been responsive to the change in context , and has been scored an A. Highlights include emergency payments to vulnerable individuals, the switch to mobile money for cash transfers, the success of the RBA in supporting Mental Health Panels by MHA and the progress on more comprehensive case management

However, in pivoting to meeting the immediate need the programme has moved away from its original direction of travel of building Government capacity to support vulnerable groups. System strengthening has suffered as a result (e.g. PFI was not rolled out, GNHR’s future is unclear). The programme still has work to do in terms of ensuring coherence. Safeguarding remains a risk. The biggest threat to the programmes outcome and impact is around sustainability. The Government’s increased debt servicing and reduced levels of economic growth due to Covid -19 could impact on their commitment to fully fund cash transfers; and certainly, reduces the likelihood of increased coverage. steps will need to be taken to realign with full intention of the Business Case over the next twelve months. Given that the amount of ODA available to FCDO Ghana is likely to fluctuate over the remainder of the programme, the ability to flex and remain as effective as possible within the over-all budget envelope will also need to be considered.

Major lessons and recommendations for the year ahead [1/2 page]

The programme and FCDO’s Social Protection approach have been reviewed by a number of actors, including ICAI and the IDC, the Quality Assurance Unit (QAU) and the Social Protection Approaches to COVID 19 (SPACE) programme. There are recommendations that are still outstanding from these reviews, as well as ones from the last AR. Along with the recommendations below, these needs to be prioritised and sequenced appropriately.

The programme will need to respond to FCDO Business planning and budget prioritisation processes, including the challenge presented by the reduction in ODA. It will be important that this is done bearing in mind where the programme is most/least effective; where others, including GoG, can step up to cover gaps left; and how to ensure our previous investments are built on. This is in line with ICAI recommendations. FCDO should use Q1 of 2021 to do a comprehensive stock-take of the programme, assessing the level of ambition and FCDO’s actual level of traction with government and partners to effect change.

The Theory of Change should be revised, made more specific, and closer to a theory of action, based on decisions on how funds are being spent. More action-oriented pathways of change should be established, with close ties to other parts of the monitoring framework, including logframe to allow for better judgement of progress towards outcomes. This may include a Business case addendum. The programme must take on board QAU recommendations not to spread too thinly, even more pertinent given Covid 19 has added in another element. This means bringing in CMPs and influencing multilateral spend, rather than the LNOB programme trying to do more. (Q1)

Linked to this, FCDO should focus on working even more closely with multilaterals in social protection in Ghana given not just the LNOB contribution but the central core contributions to the World Bank and UNICEF. This will mean FCDO Ghana working closely with central teams to establish a joined up advocacy and influencing strategy and plan, with agreed outputs. (Q1 and 2)

The sustainability indicators and supporting outputs and activities should be made more prominent and explicit in the monitoring framework and management of the programme. GoG should be aware of and have ownership of these indicators where appropriate and where they are not already jointly owned. (Q1)

Alongside the above, a whole programme VfM framework should be established by the FCDO team, linked explicitly to the revised theory of change for effectiveness indicators. (Q1)

There is still a gap between the vision of the programme and the reality in terms of synergies and a coherent approach. While there are good examples of joined up working and added value , partners continue to deliver their own priorities and engage with others only on an ad hoc basis. FCDO should review the governance and coordination arrangements of the programme, and in particular assess whether Options are the right partner to coordinate the programme. It is recommended that FCDO are far more directive and closely involved with the coordination of the programme, more directly supporting government to bring stakeholders together in line with establishing ways of working that will be sustained beyond the end of FCDO financial support.(Q1)

FCDO should assess with partners the feasibility of integrating vaccination messaging into both communications for LEAP and other outreach activities.(Immediately)

Safeguarding: FCDO should conduct a light touch safeguarding audit of the programme to highlight major risk areas, and safeguarding risk(s) should be recognised in component risk registers. The safeguarding risks in the FCDO risk register should be revised as appropriate, The Steering Committee should ensure that safeguarding risk is captured in the programme risk register. FCDO Ghana to work with IFID to leverage WB safeguarding expertise be brought to bear on the LEAP programme.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

The ToC for the programme is represented below. It, along with the logframe has been revised to respond to Covid-19, which includes the withdrawal of funding from PFI and the reduction of spend on GNHR –a reduction in spend on system strengthening. These did not require a BC addendum given changes were at output level. They were approved by the Development Director given the urgent needs around Covid-19, and that LNOB was the best mechanism for reaching the most vulnerable in the FCDO Ghana portfolio. How the programme reverts to the original intent more concretely in the third year of the programme will need to be a focus for FCDO.
There is a disconnect between the ToC and the Business Case. The BC envisages a dynamic process where UK funding of cash transfers reduces over time while the ToC does not make this explicit, and there are no markers with the ToC to map the change pathway to this point. The ToC requires regular review, and for more specifics to be introduced to map out the change pathway. This will allow for assessments to be made against expected progress towards the outcomes and impacts as the programme enters the second half of its cycle, and for adjustments to programming to be made off the back of this.

Various changes to the LNOB programme were flagged before the year in question but were not deemed to be a material change. E.g. the decision not to provide MoGCSP with £1.5m to support their V&E strategy but to fund UNICEF to deliver a V&E analysis to provide MoGCSP with recommendations to facilitate a more systems based response to the V&E in Ghana.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

The programme had to make significant adjustments in 2020 to remain relevant in the face of Covid-19, and to become a vehicle to respond to some of the acute need arising from the pandemic and national lockdown while still retaining the focus on programme target groups. Significant achievements have been made in key delivery areas, and some progress has been made establishing robust and joined up health and social protection systems. Identified milestones at both the output and outcome level are largely being achieved, and the programme continues to occupy a need that is not being addressed by other development partners, and the theoretical justification for the wider programme and its constituent parts was affirmed by stakeholders.

FCDO has been engaging more closely with the World Bank through the course of 2020, including through discussions on social protection and LEAP held in September. This senior level engagement on social protection has the potential to be a crucial mechanism for FCDO to advance policy priorities in Ghana and will strongly complement technical level engagement. As was highlighted during the UK/WB meeting in September 2020, key issues such as the financial sustainability of the SP sector to finance GNHR, increase the value of the LEAP cash transfers and expansion of LEAP are all critical issues which will be pursued through joint advocacy with World Bank.

However, there are prominent gaps emerging that could jeopardise LNOB’s contribution to FCDOs overarching objective to support Ghana to move beyond aid, and there is a risk that the ambitious breadth of the programme could result in key parts of the change pathway being missed. LNOB was always an ambitious programme, and was based on the assumption that Ghana ability to generate its own revenue and finance its own social protection system. Covid-19 presents a serious challenge to this assumption. The impact of Covid-19 and the necessity to reallocate parts of the budget has emphasised that external donor finance and technical assistance is still required to meet even the most immediate needs. and the continued pressures on budgets that are likely to continue to manifest over the remainder of the programme mean that this should be seen as the new normal. In particular, there are very real questions about the extent to which the programme is driving more joined up ways of working between government departments; around the sustainability a viability of the GNHR as a national reference point; around the value of cash payments being eroded; and about the national reach of LEAP and recertification.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

Stakeholders affirmed that the LNOB programme continues to be a programme that is responding to a need that would not otherwise be met. The approach of the programme – building systems, capacity and commitment to leaving no-one behind in health and social protection efforts – strongly supports the FCDO approach in Ghana, moving away from direct large scale service provision to facilitating Ghana’s ambition to move beyond aid, and leveraging our expertise to make targeted, catalytic interventions which improve work that is being carried out by other development partners and government. The programme undoubtedly brings together actors who would not otherwise work closely together on these issues, not least the bringing together of the MoGCSP, Ministry of Health (MoH) and Ministry of Local Government (MoLG) in the High Level Steering committee. There is therefore a strong justification for the continuation of the programme from the design level.

The programme has also demonstrated tangible examples of this approach making a difference,
but risks not being more than the sum of its parts. There are notable initiatives that have not been completed in 2020 but are on track to be completed early in 2021 including supporting civil society organisations, but for the programme to be transformational and have sustainable impact, FCDO needs to be much more proactive in convening partners and supporting partners to work closely together at the technical as well as the leadership levels. Practically, having a KPI related to joint planning and working would give this ambition more visibility.

The FCDO Business plan is an opportunity to set out the extent of cross-mission ambition on LNOB and the bottom billion. It will need to be in line with FCDO’s “force for good” and build on our past investments on poverty, gender and disability. The BHC should set out a clear influencing and advocacy plan on inclusion with country partners, and in addition work with the centre to ensure multilaterals have inclusion/LNOB at the heart of their work.

The programme continues to represent value for money in its component parts, and at the programme levelshould the outcomes be achieved, assuming that the outcomes are still realistic with reduced funding. This latter point is something that the FCDO will need to assess once the budget position for FY 21/22 and for the remainder of the programme becomes clearer.

According to the Business case, Value for Money (VfM) indicators should have been agreed during the programme inception phase with all partners. With the different components of the programme starting at different times and quite late in the programme year, an overarching VfM strategy with indicators has not been designed. Options have a VfM framework for their delivery, and the reporting format shared with WHO and UNICEF requires them to provide some VfM targets/results/achievement. However, the overall VfM of the programme at the effectiveness level remains difficult to assess.

The cost drivers indicated in the Business Case, are expected to remain the same. The main ones include: cash transfers, GNHR and productive inclusion (with associated costs); results-based non-budget support financial aid; mental health and disability work (grants to NGOs/CBOs/DPOs, community-based rehabilitation services, empowerment and capacity building interventions, anti-stigma and discrimination activities) by the Supplier; TA support; as well as grants to WHO and UNICEF. Again, should the focus of the programme shift in response to budget adjustments, the cost drivers will need to be reassessed.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Improved policy, leadership, resources and governance systems that recognises and respects the human rights of the extreme poor and marginalised, including all people with disabilities and mental health conditions.
Output number:		1	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	Yes up

Indicator(s)	Milestone(s) for this review	Progress
1.1.Extent to which intersectoral monitoring and accountability mechanisms strengthen GoG systems delivering mental health services and disability inclusion	Establishment of working group on Mental Health Review Tribunal / Inauguration of Mental Health Review Tribunal [Revised Milestone]	Partially Achieved
1.2 % of LEAP beneficiaries selected using Ghana National Household Registry (GNHR) data. Results disaggregated by gender and disability status.	a)GNHR structural listing with GSS and data collection in Northern region commenced and b) emergency data collection of GNHR in Accra and Kumasi [revised milestone]	Achieved
1.3 Level of implementation of Government's Vulnerability and Exclusion (V&E) Strategy	Research institution recruited and V&E inception report completed. [revised milestone]	Partially Achieved
1.4 Level of Technical Assistance to Ministry of Gender, Children and Social Protection to strengthen social protection system and implement, map and coordinate COVID 19 activities and advocate for increased resources.	a) 322,000 LEAP beneficiary households benefit from modified implementation and operations which safely and effectively continue delivery of cash transfers with public health messaging / b) In COVID-19 response, front line workers are equipped to safely deliver critical child protection, human rights, judicial and SGBV services to vulnerable groups. / c) analytical support provided to SPD on key SP budget and financing issues, in order to effectively engage in 2021 budget discussions re: SP COVID response and recovery needs [revised milestone	Achieved
1.5 Extent to which the Legislative Instrument (LI) of the Mental Health Act (846) and national mental health policy established and guide implementation of mental health services.	a) Landscape analysis on implementation of mental health & disability legislation report agreed and informs subsequent milestones b) Correction of errors in Mental Health Regulations, 2019 (L.I. 2385) and submission for Parliamentary approval and c) Submission of Disability Amendment Bill to Attorney General's Department	Achieved

Briefly describe the output’s activities, and provide supporting narrative for the score. [max 1/2 page]

This output, relating to systems strengthening was achieved. It measures work done by the MH supplier, Options, with the MHA, MoG’s systems (GNHR and V&E), output of WB and UNICEF TA to MoG, and MHA progress on RBA indicators.

Indicator 1.1: Mental Health Authority (MHA) was supported to set up a working group, with the selection criteria for MH Tribunal members and of role description completed. MHA has written to the Attorney General (AG) requesting nominations for the Chairperson/s of the Mental Health Review Tribunal. The MH Review Tribunal was not inaugurated because nominations have not been received from the AG’s Department. However, the process in it self was highlighted as something that, combined with the district level mental health plans, was making a real difference in bringing together MHA and the MoH, so that they are working together rather than in competition. This is an example of the improved ways of working that the programme is aiming to leverage across the board.

Indicator 1.2: A key achievement has been FCDO’s collaboration with the government and development partners to expand the coverage of the GNHR by around 80,000 households during 2020. GNHR continued the roll-out of data gathering, with good examples of it being used both for social protection payment targeting (for the emergency payments), and for wider uses, including by WFP for their Cash Transfer programme which targeted vulnerable women in lockdown areas in Accra and Kumasi. GNHR Structural Listing and Data Collection was completed in the North East, Savannah and the Northern regions with 490,733 households profiled. Emergency data collection in Accra was completed, with data gathered on 78,741 vulnerable individuals. Data collection in Kumasi was started but not completed in 2020. In the emergency payments the use of GNHR data meant that new categories of vulnerable people, such as street children, residents of alleged witches camps and homeless people. who were not previously captured by LEAP household level data could be reached. This reinforces the importance of the GNHR to supporting the aim of targeting and reaching the extreme poor and most vulnerable.

However, there remain significant questions about the scale and sustainability of the system. Whilst FCDO have funded GNHR in the Northern region, at no point has the GNHR had the funding to gather data nationwide, and there are challenges to GNHR becoming the foundation for a more efficient and effective social have a comprehensive registry. In 2020 only 3000 households (representing 0.857%) were enrolled for LEAP payments using GNHR data. It is currently funded exclusively by donor funds, and there are no concrete plans to fund it through government funds at current levels, let alone to increase funding to a level where is can be the national and up to date resource that the programme aimed for. It continues to be rolled out on a on a region by region basis, and some regions were part of the initial piloting four years ago, which means that the GSS faces choices between targeting regions which have not been covered to date in pursuit of national coverage, or repeating data collection in regions which are likely to have more need of robust and up to date data for targeting of social protection and other programmes.

Indicator 1.3: For the vulnerability and exclusion assessment, UNICEF has commissioned ODI. The Assessment timeline originally encountered delays due to COVID-19 and further during the contracting process. An inception meeting and the final inception report are expected to be completed by mid-March 2021.

Indicator 1.4 UNICEF supported the MoGCSP and GNHR was critical to identifying new recipients for emergency LEAP payments, ensuring that emergency and regular LEAP payments could be made in a Covid secure manner, which included to ensure covid related safeguarding and protection risks were mitigated. 322,000 households (1.45 million people, including 695,036 children and 131,915 people with disabilities) benefited from COVID-19 adapted delivery of a LEAP extraordinary payment in April/May to mitigate negative socio-economic impacts of the crisis and enable good public health practices. Partners provided in-depth technical assistance and innovation in design and operational preparation of the transfers, data and payroll management, communications with beneficiaries and implementers, and monitoring through various channels.

Through support from UNICEF, frontline service workers were supported with updated guidelines and protective equipment, in order to monitor and continue delivering critical services to vulnerable children and groups in the face of potential increases in the incidence of violence against children and women, sexual abuse and child marriage. 43,428 masks (870 packs), 43,500 pairs of gloves (870 packs), 870 bottles of hand sanitiser (500ml each) and 58 contactless thermometers reached 750 staff of Domestic Violence and Victims Support Unit and 300 staff of Judicial Service of Ghana working in 20 child-friendly gender-based violence courts.

In terms of policy support, UNICEF supported a fiscal space analysis aimed at initiating dialogue on SP financing including the passage of the Social Protection Bill. The analysis will feed into a High-Level Forum on social protection financing to be convened by MoGCSP and MoF in April, which will include the issue of sustainable financing mechanisms for social protection in response to shocks.

Indicator 1.5: The Disability Amendment Bill was submitted to AGs office but may need to be resubmitted with support of new minister following the elections. The List of identified errors in the Mental Health Regulations were compiled through stakeholder meetings with psychiatrists and other mental health professionals Corrections effected and forwarded to MoH for submission to Attorney General’s Department and parliamentary approval as appropriate.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

Although Options do have a VfM framework agreed, there are no specific VfM metrics relating to this output in the business case. There are clearly strong VfM implications for the programme outcomes stemming from this output. The ability of long-term ability and commitment of GoG to respond effectively and inclusively to the issues the programme is addressing will be strengthened by the systems and legislation supported by the activities described. If the ToC is revisited an updating of the VfM framework alongside this would be useful.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

The weighting of the output was raised from 10% to 15% as a reflection of the increasing importance of systems building as the programme progresses. Changes were made to the logframe in line with the pivot to Covid-19, and in response to recommendations from the last AR.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

The year 1 AR recommendations including agreeing milestones with the MoH by April 2020 , support the supplier build up partnerships with GoG and NGOs and reviewing and expanding Output 1 indicators in the logframe were completed, and the weighting was increased from 10% to 15%.

The AR also contained recommendations on the use of GNHR data as the basis of LEAP targeting, specifically around change in eligibility, and how the MoGCSP will support those who will no longer qualify for cash transfers following GNHR and the re-assessment process, especially for people with disabilities; analysing the demographic breakdown of those no longer eligible and set out a clear support strategy for households no longer eligible for LEAP; clear communications and support to access other social protection support including the 3% Common Fund. Little progress has been made on these recommendations, but to large extent this is due to the fact that little progress has been made on switching to GNHR. GNHR data collection activities had to be delayed due to Covid-19 and the elections. The reassessment process has now been approved and activities are underway. Even without the question of moving from LEAP targeting to GNHR registry targeting, the issue of recertification and eligibility is a live one. The eligibility of LEAP recipients has not been reassessed since 2015. It is therefore not possible to say whether the right people are still benefiting from LEAP or whether there has been any successful graduation from the programme.

Recommendations for this year:

- FCDO to established urgently what plans there are for funding to GNHR to cover our £2.5m and how this will fit with the census work in 2021 to ensure VfM.
- WB to support MoG set out clear plan for GNHR in terms of roll out and sustainability (how often updated, at what cost) and also in terms of support to those no longer qualifying for LEAP.
- FCDO team to use V&E assessment to bring in CMPs; and influence multilateral and GoG spend bearing in mind QAU recommendations not to spread the programme too thinly.
- It is inevitable in taking a cross -sector approach where there are limited partners, that different FCDO programmes end up working with the same partner (e.g. UNICEF). FCDO team to ensure clear division of focus between LNOB (which is about MH and cash transfers) and PBA (PFM, budgeting across social sectors).

Output Title	Effective cash transfers payments and operational modalities are delivered to extreme poor and vulnerable and marginalised households on a transparent, accountable and sustainable basis.
Output number:		2	Output Score:	A
Impact weighting (%):		35	Weighting revised since last AR?	Yes down

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of beneficiaries accessing timely LEAP cash grant (results disaggregated by gender and disability status).	a) Post-payment monitoring and spot checks across 32 LEAP communities by CSOs in the wake of COVID 19 to ensure transparency and accountability completed for extraordinary payments; commenced for COVID-19 temporary payments	Achieved
2.2 Level of implementation of the Social Welfare Case Management and referral and reintegration system in 50 districts in Ghana including number and b) percentage of LEAP beneficiaries with active NHIS membership	LEAP and NHIA sharing data in 50 districts and agreed on outreach protocols.	Achieved
2.3 Level of implementation of the Shock Responsive Social Protection Emergency Early Warning System.	a) MoU signed / b) Initial emergency processes, data collection/sharing protocols, and gaps identified, to provide skeleton for shock-responsive SP roadmap	Partially Achieved
2.4 Number of emergency LEAP payments to vulnerable including street children, kayayei, persons with disabilities, flood victims and elderly women in witches’ camps.	124,000 new beneficiaries	Achieved

Briefly describe the output’s activities, and provide supporting narrative for the score. [max 1/2 page]

This output was achieved and measures progress against the service delivery aspect of the programme. While spend on this was envisaged in the BC to decrease over time, 2020 saw more spend under this output (£4m in total) to support the the pivot to Covid-19 response. In order to reflect the programme’s ambition to move away from direct funding of cash transfers, and the need to place greater emphasis on systems building and sustainability, the weighting for this output was decreased from 60% to 35%, as recommended in the previous AR. However, it still has a third of the impact weighting for the whole programme, and in terms of spend and number of people directly being supported the first indicator “Number of beneficiaries accessing timely LEAP cash grant (results disaggregated by gender and disability status)” is a huge driver for the success or otherwise of the ambition of the programme to alleviate poverty and leave no-one behind. In the first year the milestone for this indicator was simply the number of people reached. This year the milestone is less of a direct reflection and focuses more on the monitoring and feedback systems which support the programme, rather than the number of people reached.

Final reporting had not been received from the World Bank at time of writing. As of September 2020 enrolled a total of 335,013 households are eligible to receive bi-monthly cash grants. This translates into 1,455,475 individuals comprising 799,055 females (54.9%) and 656,420 males (45.1%). The current enrolled number of beneficiaries falls short of the national target of 350,000 households. LEAP made 6 payment cycles in 2020 (64th – 69th payment cycles – though the regular cash payments themselves were not funded by FCDO. In comparison to previous years the timing of the payments was much improved, although only 1 of the six cycles was disbursed exactly when planned. One cycle was disbursed early, 2 were within a week of planned, 1 within 2 weeks, and the final payments delayed by two months, largely attributable to GoG releasing funds late because of the elections. There was also an emergency payments made, which targeted new groups, including people without fixed addresses and residents of alleged witches camps. While these groups are genuinely left behind, the communication about the emergency, one-off- nature of the payments had not landed with recipients interviewed, who expected to be now absorbed into the regular LEAP programme. This could suggest a weakness in the communications of the programme, although more investigation is required to assess whether these people representative of ‘typical’ LEAP beneficiaries.

Indicator 2.1: Efforts have been made to increase the space for client feedback in LEAP. In 2020 Independent monitoring activities were undertaken in collaboration with national CSO platforms working under the UNICEF/CSOs social accountability programme in 16 districts and in 32 communities across the country, reaching almost 650 respondents as part of LEAP post-payment monitoring, generating key insights into operational and delivery successes and challenges with the temporary payment approach. UNICEF also worked with the CSO platform on the SDGs (SDG 10) to monitor and collect feedback on the broader social protection COVID-19 response through Townhall meetings organized in Accra, Kumasi and Tamale with citizen groups including existing SP beneficiaries. Technical assistance was provided to development of an M&E framework for emergency monitoring. SMS technology was used to conduct mass surveys aimed at soliciting real-time feedback from over 10.000 beneficiaries, focal persons and social welfare officers during the LEAP extraordinary payments and inform in-field monitoring efforts. The same is being leveraged to communicate basic information on the COVID-19 relief emergency cash transfers capture experiences on associated usage, access and challenges through free SMS.

Despite this there are ongoing safeguarding concerns. Beneficiaries interviewed were not aware of complaints channels and were completely reliant on volunteers and District Welfare Officers for information, complaints, and the cash itself. This creates a high risk of abuse. It is notable that no safeguarding or corruption case have been surfaced through the programme, and the findings from the Rapid Disability Assessment that SEA was seen as a risk by clients came as a surprise to some respondents. An action plan is being developed off the back of this, and it will be crucial to ensure that concrete steps are taken to address the risk. Stakeholders should be aware that a significant amount of education at all levels is generally needed to ensure that there is widespread understanding of what is acceptable or non-acceptable behaviour, and clients need to be confident complaints will be investigated appropriately and that they will not suffer negative repercussions from making complaints. Although the move to mobile money should reduce the direct risks of SEA from programme implementers, the need to cash out will still create points of risk and this should be considered.

Over time the GoG has increased its support to the SP sector and to LEAP cash transfers in alignment with the Ghana Beyond Aid agenda in an effort to move towards self-financing. For example they invested GHS 45m in 2012; GHS 168m in 2018 and 2019; GHS 200.7m in 2020. Whilst the annual budget for 2021 is yet to be determined, the MoGCSP Chief Accountant confirmed that MoF has approved an estimated budget of GHS 52.4m (for each quarter /3 months).  If the projected amount is maintained over the 4 quarters, it means that the total for 2021 would be approximately GHS 210m which would be a slight increase from last year. The framework for sustainable financing of the LEAP programme, and wider social protection efforts will include the passage of the SP bill and legislation which is supported by the programme. GoG provides $140m (all towards cash transfers), WB ($60m) FCDO ($20.5m). In percentage terms - GoG’s -63%, IDA -27% and FCDO-10%. In terms of GoG commitment to social protection. NPP 2020 manifesto states that the GoG will strengthen the NHIS, expand social protection and safety nets, combine all flagship SP programme databases through interoperability and link them to the National ID card to create a single registry system.

There are ongoing concerns with the registry of LEAP beneficiaries with eligibility based on both poverty and category (e.g. Orphans and vulnerable children, pregnant women with children under 2 years, chronically disabled, and the elderly), so some very poor people do not qualify; each district has a quota so some poor households miss out; the system is not agile enough to add/remove beneficiaries as circumstances change). LEAP only covers 1.4 million of Ghana’s estimated 2.4 million extreme poor. Furthermore the value of the grant has not been adjusted for six years, which means that its value has been eroded by inflation.

Indicator 2.2: There has been good progress in the development of the social welfare and case management system by UNICEF. This includes progress in bringing different strands of social welfare together, focusing on Social Welfare Case Management and referral and reintegration system e.g. expanding collaboration between LEAP and GHS and strengthening data sharing and best practices for community outreach and referrals by GHS/CHPs. Implementation with GHS, NHIS and Social Welfare services has been initiated in 60 participating districts and UNICEF has supported the development of a technical operational protocols between LEAP and NHIS to ensure that LEAP households receive expedited access to health insurance as well as home visits from community health nurses. Tools such as simplified animated flowcharts and step-by-step instruction guides have been developed and disseminated to guide frontline workers. As a result, LEAP and NHIS in the 60 districts actively share household lists, significantly increasing the efficiency of district level transactions between the services. However, there are some questions about the number of beneficiaries holding NHIS cards as opposed to being registered on NHIS, as the cards need to be renewed on an annual basis and it is unclear as to the effects of Covid restriction on the people’s renewal of cards. This means that LEAP beneficiaries may not all be able to benefit from NHIS when they need it.

A major achievement of the year, and a good example of the programme bringing stakeholders together to improve ways of working in new ways is the support to MoGCSP and the Office of the Head of Local Government Service (OHLGS) to develop and disseminate Intersectoral Standard Operating Procedures for Child Protection and Family Welfare (ISSOP). Cases handled include domestic and gender-based violence, teenage pregnancies and child marriage, child labour and trafficking and support to persons with disabilities and mental health conditions. The ISSOP provides a harmonized framework of agreed standards, principles and procedures for all child protection and family welfare stakeholders to understand each other’s roles and responsibilities, to 60 MMDAs.

Indicator 2.3: The programme planned for an expansion of support to the establishment of shock responsive social protection systems. The MOU was not signed in 2020, and discussions with MoGCSP are being re-started. It was originally agreed to delay this discussion until Q4 due to focus on COVID-19 response. Given focus in Q4 on COVID-19 payments and uncertainty due to elections, this was then delayed to Q1 2021. UNICEF has been working the MoGCSP and the World Bank to document processes and track gaps/challenges that have arisen during the COVID-19 response activities, in order to inform the next steps on strengthening the longer-term shock-responsiveness of the SP system. This includes adapting and modifying the payment system to mobile money and to capture the experiences of beneficiaries via SMS. The use of mobile technologies in LEAP mark an important turning point that will have implications beyond the response to COVID-19 to the overall shock responsiveness of Ghana’s cash transfer system.

Indictor 2.4 A major achievement for the year is the emergency payment to very vulnerable groups such as street children, kayayei, persons with disabilities, flood victims and elderly women in witches’ camps. It should be noted that although this was part of the submission, this indicator does not appear in the latest logframe shared by the partners. Target beneficiaries were identified using GNHR data. Payments were significantly above regular LEAP payment amounts. The review team spoke to recipients of emergency payments, and the money was largely used to meet need arising from Covid-19, with some investment into businesses. However, there was some lack of understanding about how the emergency payments related to the regular payments, with expectations of being absorbed in to the LEAP scheme.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

The output continues to represent VfM, particularly at the economy and efficiency levels. The regularity of payments and how this impacts on beneficiaries ability to meet household needs as a VfM indicator has improved this year. WB data gathering on the impact of payments on LEAP beneficiary household finances allow better measurement of this. The question of appropriate targeting is a large driver of effectiveness, so the ‘missed’ beneficiaries reached through the emergency payment should provide more data on how effective the targeting is in terms of reaching the most left behind and vulnerable.

The programme achieved efficiency in a number of ways: The programme also achieved efficiency through the e-payment system for cash transfers.  Using the e-zwich payment platform, beneficiaries are now reached easily and on time without the additional overheads which were associated with the previous manual system. This also saves individuals having to carry large sums of cash to distribution centres. It therefore saves time and reduces fiduciary risk.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Weighting revised, and changes to outputs and milestones as noted above.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

The previous AR reflected on the first year of the programme in which efforts had been focused on setting up and contracted the new elements. It looked ahead to 2020, setting key priorities around building synergies between the different programme partners so that it is more than the sum of its parts.
This will involve the supplier focusing on safeguarding, at the same time as mainstreaming mental health into GoG’s disability work; ensuring GNHR is completed, regularly updated, and that the implications of it are thoroughly thought through.
There were also specific recommendations around aligning of reporting, (The World Bank should agree with FCDO by end March 2020 a reporting timetable be aligned to FCDO’s annual review timetable). WB has provided more regular and comprehensive reports, although notably the annual report has not yet been submitted, which means that it is not aligned with FCDO reporting needs.
The AR also noted the need to improve the safeguarding approach. As noted above this process of improvement has been started and will need to be monitored closely over the coming year.
Recommendations for this year:

FCDO should set out the risks and recommendations around safeguarding. FCDO to work with WB to ensure that recommendations on safeguarding are actioned. The workplan should be agreed and updates given at the High Level Steering Group as a standing item.

Reporting continues to not align, and there is a lack of clarity version control on the logframe. FCDO team should work with partners by end of Q1 to agree reporting timelines and finalise the logframe. If it is not possible to change partner reporting dates FCDO should establish what information can be provided ahead of formal reporting to allow for the annual review to have at least logframe level data at an earlier date. FCDO should emphasise reporting delays at high level meeting with WB.

Output Title	Increased access to quality integrated, disability inclusive community based and recovery oriented mental health and other health services including services delivered by traditional and faith-based leaders.
Output number:		3	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
3.1 Extent of implementation of Quality Rights Initiatives in health facilities.	Quality Rights assessments of 7 hospitals disseminated and Improvement Plans in development	Partially Achieved
3.2 GoG procurement of psychotropic drugs and availability of psychotropic drugs at all levels.	a)2019 Procurement of Psychotropic medicines delivered and distributed to the 3 psychiatric hospitals and regions b) 2020 Procurement – Procurement process initiated, c) baseline assessment on availability and access to psychotropic drugs complete and action plan agreed	Achieved
3.3 Number of persons with disabilities including mental health conditions and other vulnerable groups benefiting from community based initiatives including through civil society and self help groups (SHGs).	7 civil society organisations providing psychosocial support to people with disabilities, including MH conditions, healthcare workers, and Covid-19 survivors - 4,000 people benefiting and 300 SHGs supported to reopen	Partially achieved

Briefly describe the output’s activities, and provide supporting narrative for the score. [max 1/2 page]

Indicator 3.1 Quality Rights is a WHO–designed framework with associated training and guidance to improve the quality and human rights conditions of mental health facilities. It builds capacity among health care professionals, family members, people with lived experience, NGOs and DPOs to understand and promote human rights; supports civil society movements to conduct advocacy and influence policy-making; and reform policies in line with best practice and international human rights standards. The WHO QualityRights toolkit is used in the comprehensive assessments of quality and human rights conditions in services to address service delivery gaps and work towards consolidating gains in the targeted facilities in a manner that respect the rights and dignity of service users. A total of 7 facilities comprising 2 psychiatric hospitals (Accra and Ankaful Psychiatric Hospitals), and 5 regional hospitals with psychiatric units (Koforidua and Sunyani Regional Hospitals, Korle-Bu, Ho and Okomfo Anokye Teaching Hospitals) were assessed to measure the quality-of-service delivery and human rights standards. Through the assessments both good and bad practice were highlighted, including evidence of physical and mental abuse, which will need to be addressed. The programme has also promoted wider training on disability and human rights through online courses. The work of the partners and the social media campaign has culminated in 17,138 people registering for the e-training, 10,542 starting the course, and 8745 people as of 15 January 2021, receiving the WHO QR e-training certificate equivalent to a Diploma certificate in Human Rights.

Indicator 3.2: AS noted in last year’s AR, the purchase of psychotropic drugs is a significant achievement for the programme. Progress has continued on a positive trajectory this year, with the mental health authority have gone through the contracting process for supply and forecast & request for procurement submitted to MoH. Procurement was done in accordance with national procurement guidelines. i.e. National Competitive tendering, evaluation of bids, award of contracts. The MHA have been able to look at supply chains, and have put in place plans for 2022, and have raised the issue of mental health to a level where funding for drugs has been included in budgeting plans, including with discussions with the world bank. This represents a huge shift to a demand-based system, getting the drugs to where they are needed, rather than the more ad hoc supply based system that existed previously. In addition, the Results Based Aid approach has generated interest across government as a model.

Indicator 3.3: An immediate response to COVID-19 by the programme was to undertake a rapid assessment of COVID-19 in Ghana, specifically relating to people with disabilities and mental health disabilities. This informed adaptations across several areas of the programme, and supported plans for developing a fast-track COVID-19 Psychosocial Resilience Grant call, for small grants up to GHS200,000 each for 12 months. Seven grantees were awarded grants funding under this call, with individual grant award amounts ranging between GHS 117,000 and GHS 200,000 to implement COVID-19 related activities across Ghana. Grantees were further supported with a 3-day capacity building session 29 November to 1 December 2020 at Tomreik Hotel, East Legon, Accra. Three people attended from each grantee organisation, including leadership, finance and operations functions.

171 SHGs which had been closed due to COVID-19 restrictions were supported to re-open, of 300 planned. Through the reopening of SHGs, all SHG members were sensitised on COVID-19, using the Easy Read COVID-19 materials developed by the programme in collaboration with GFD and reviewed by the GHS Risk Communications Committee. The materials were also shared with COVID-19 grantees and the psychiatric hospitals via MHA.

VfM

WHO QualityRights e-training on mental health, human rights and recovery, rolled out nationally among service providers, health & non-health professionals, families, faith-based organizations, people with lived experience, NGOs, DPOs & wider community. Using the QR e-training platform, beneficiaries are now reached easily and on time without the additional costs which could not been associated with the manual system. This also saves costs of having to print lots of training tools/manuals for all participants from all the regions. Procurement of experienced and as well as use of local Consultants, which is less expensive while providing the expected level of expertise. Programme interventions build on existing tools and materials hence did not require additional cost. All Quality Rights and mhGAP interventions have already been developed and hence no development costs are involved. They are also low-cost strategies that enable high reach and large impact.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Weighting revised up to 20% from 15%. Pivot to Covid-19 response as described.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

FCDO should urgently review Quality Rights Assessments of facilities in light of findings on possible safeguarding concerns. Although the facilities are not funded by FCDO, the extent to which the findings of QRAs are acted on is a direct indicator of their effectiveness.

Options should review MHAs path to move away from TA support through the programme and agree a clear sustainability strategy with milestones.

Output Title	Attitudes, behaviours and norms related to people with disabilities and including mental health conditions transformed.
Output number:		4	Output Score:	B
Impact weighting (%):		15	Weighting revised since last AR?	[If Yes, up or down?]

Indicator(s)	Milestone(s) for this review	Progress
4.1 Number of people reached with mental health and disability inclusive messages.	100 key media actors trained in disability and mental health inclusion	Partially achieved
4.2 Number of health professionals, community members and traditional leaders trained in stigma reduction, discrimination and human rights violations.	a) Actual number of volunteers who have signed on to become 'digital angels' for the Quality Rights initiative; b) actual number of health bodies that have included Quality Rights modules in their CPD program	Achieved
4.3 Extent of CSOs and DPO actors participation in advocating for social accountability and improved mental health services and support.	Grant strategy and mechanism developed and call for proposals issued	Exceeded
4.4 Level of awareness of Covid-19 related risk communications by persons with disabilities and mental health conditions	17,000 (reached directly) and 700,000 (reached indirectly) persons with disabilities, including mental health disabilities able to access accessible materials and information	Partially Achieved:
4.5 Number of health professionals, equipped with guidance on COVID-19, mental wellbeing, and rights-based approaches	a) 136,247 healthcare workers equipped with guidance on mental wellbeing and staying safe with Covid-19, and b) on rights-based approaches for equitable treatment of people with disabilities, including mental health disabilities during Covid-19. + 100 healthcare workers trained in management of COVID-19 in mental health settings and healthcare worker mental wellbeing	Partially Achieved:

Briefly describe the output’s activities, and provide supporting narrative for the score. [max 1/2 page]

Indicator 4.1: In response to COVID-19, significant progress was made by engaging the media around disability and mental health, and in particular considering reporting of COVID-19. Training sessions were held with media, with 115 invited out of which 73 attended. The programme trained media actors from both print (newspapers, online portals), electronic (TV, radio), Ghana Journalist Association and National Media Commission on mental health and disability. Trainings were held in Accra and Tamale. The target of 100 was not met because some media actors did not turn up for the training. There were also a range of World Mental Health Day (WMHD) activities supported by the programme, with a focus on media activities, and on the themes of accessibility as well as investment in mental health.

Indicator 4.2: WHO embedded their Quality Rights Module in the health system, with 40 volunteers signed up to become 'digital angels' for the Quality Rights initiative and 5 health professional bodies accredited the Quality Rights modules in their CPD program. One institution included Quality Rights modules in their curriculum. mental health conditions as well as share the knowledge gained as part of the dissemination to other colleagues.

Indicator 4.3: The programme accelerated engagement with CSOs. The 2 rounds of grants represent a significant achievement, particularly given the challenges relating to Covid-19 and the pivot that this demanded. Work on developing the programme grants strategy with manual and tools to inform the programme’s approach to advocacy, Social and Behaviour Change Communication (SBCC), and operations. The grants strategy drew heavily on the wider Political Economy Analysis, which was the product of the 5 simultaneous stakeholder assessment activities, (CBR mapping, the District Mental Health Plan baseline, Self-Help Groups and DPOs mapping, Landscaping Analysis, and COVID-19 Rapid Assessment). A grant mechanism was agreed with GoG and calls for proposals issued. In addition an immediate response to COVID-19 by the programme was undertook a rapid assessment of COVID-19 in Ghana, specifically relating to people with disabilities and mental health disabilities. This informed adaptations across several areas, and supported plans for developing a fast-track COVID-19 Psychosocial Resilience Grant call.

Indicator 4.4: The programme rolled out Covid risk awareness materials to people with disabilities. 4,044 persons with disabilities, including mental health disabilities were reached directly with the programme’s accessible materials. 24,768 were reached indirectly with the programme’s accessible materials. This represents fewer people reached than planned, and also the ratio of people reached directly and indirectly was significantly smaller than planned (1:41 planned, 1:6 actual). While there may be less awareness raising on this topic this year, there will likely be other topics that the programme may want to address – notably on vaccines, so it would be useful to unpack why the assumptions on reach and ratio did not hold up, and whether any adjustments need to be made to the approach as a response,

Indicator 4.5: Covid-19 adapted QualityRights and wellbeing guidelines for health workers were developed but not disseminated to health care workers because the programme is awaiting sign off from MHA and GHS. 131 healthcare workers were trained in management of COVID 10 in MH settings and healthcare worker mental wellbeing. The WHO Mental Health Gap Action Programme (MhGAP) intervention guide was used in training prescribers in 13 regions of the country. 443 primary care providers (75 doctors, 176 physician assistants, and 192 nurses trained as of November 2020). This will improve the capacity of these primary care staff in managing common

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

The indicators for this output are very focused on delivery, rather than the results of delivery. The milestones for future years have not been established for all indicators, but as they stand they will not demonstrate whether there has been any change in attitudes, behaviours or norms. FDCO should work with partners, as part of the general refresh of the M&E framework, to establish indicators that are more suited to measure the change sought.

Output Title	Effective scale up of disaggregated data collection across all partnerships and generation of high quality research, evidence, learning and what works to inform programming.
Output number:		5	Output Score:	B
Impact weighting (%):		15	Weighting revised since last AR?	Increased

Indicator(s)	Milestone(s) for this review	Progress
5.1 Level of secondary analysis of MICS/GLSS data to identify vulnerable girls and boys as well as their caregivers as well as socioeconomic & geographic determinants of vulnerabilities	Analysis of MICS and GLSS data to determine the magnitude of vulnerability of children and caregivers based on equity perspectives commenced.	Achieved
5.2 Extent of interoperability of social welfare system MIS with other databases.	Stocktaking of social protection MIS interoperability undertaken and piloting of SWIMS (social welfare MIS).	Achieved
5.3 Extent to which findings from the Rapid Review Scoping Study and Assessment on Disability and Gender inclusion informs the Ghana Productive Safety Net Programme (GPSNP).	Evidence that Scoping study informs GoG with planning activities and interventions and Action plan developed	Partially achieved
5.4 AIMS implemented and extent to which it informs the implementation of the Mental health Strategy.	AIMS/ATLAS study conducted and key recommendations outlined for implementation.	Partially achieved
5.5 Extent to which findings from the Covid-19 Rapid Review Scoping Study informs the GoG Covid-19 response and secondary impact mitigation interventions	Evidence that assessment of COVID-19 risks to persons with disabilities and MH inform GoG Covid-19 response and mitigation interventions for health and social protection	Partially Achieved

Briefly describe the output’s activities, and provide supporting narrative for the score. [max 1/2 page]

The weighting for this output was raised this year from 5% to 15%, and contains some of the more crucial elements to enabling a more joined up social protection and social welfare system. With FCDO Support, UNICEF, the World Bank, and the Ghana Statistical Services worked together on the GNHR structural listing and collected and analysed emergency data on the impact of COVID-19 on households and children. A nationally representative longitudinal study is being conducted based on phone interviews with 3000 households and 2000 caregivers, with the intention of tracking impacts and changes over the course of the pandemic. First and second rounds of data collection took place in June and September 2020, and the third round will be conducted in February 2021. A mapping of the overall Social Protection MIS architecture and assessment of interoperability was completed in consultation with key stakeholders, including a draft roadmap on key areas to strengthen the overall architecture and increase interoperability.

Indicator 5.2: UNICEF worked in collaboration with the OHLGS and DSW to set up the Ghana Social Welfare Information Management System (SWIMS). SWIMS was piloted with 6 districts, and as of January 2021, 26 districts have gone live and started using SWIMS. Protocols for implementation of Integrated Social Services (ISS) initiative was agreed with all key national level stakeholders –MoGCSP [including Department of Social Welfare (DSW), Department of Children (DOC), Livelihood Empowerment Against Poverty (LEAP)Programme], Office of the Head of Local Government Service (OHLGS), Ghana Health Service (GHS), National Health Insurance Authority (NHIA), Ministry of Finance (MoF).

Indicators 5.3 and 5.5: The Rapid Review Scoping Study was a key piece of work which highlighted concerns around some of the wider safeguarding issues particularly during cash outs at pay points, and the extent to which disability is being recognised in the various initiatives. Following the scoping study an action plan was developed.  LMS are leading the implementation of recommendations from the final report. Evidence from the study has informed GPSNP specifically GNHR who have adopted the Washington Group of Questions and consulted DPOs and engaged GFD in training of enumerators for data collection in the 5 Northern regions.

Indicator 5.4 WHO has completed the ATLAS Survey and the AIMS study is currently out to tender.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Last year’s annual review made a number of recommendations about this output, both on the weighting and on moving the indicators to the appropriate outputs. These have largely been completed, and the revised logframe reflects these recommendations.

The review recommended that MOGCSP engage the Federation of Person with Disabilities and other CSOs to work with GNHR on support and capacity building around collection of data on disability, including use of Washington Group questions. Washington group questions were incorporated into the GNHR data gathering for emergency payments.

The rapid review demonstrated that there were gaps in LEAP with regards to inclusion and safeguarding. Given the WB has been supporting the LEAP programme for a number of years, it is valid to question the amount of expertise in this field that is being brought to bear on the programme. The WB has an extensive policy base and strong central capacity on human development, exclusion and safeguarding. The FCDO should seek reassurances that there is sufficient capacity in country to strengthen these aspects of the programme.

The FCDO team should work closely with the WB and delivery partners to monitor the extent to which the recommendations from the rapid review are being put into action.

D: RISK [½ to 1 page]

Overview of risk management [1/2 page]

The risk register has been kept up to date throughout the year to reflect the changing context due to Covid-19. The most significant risk category in terms of both the levels of risk and the number of risks identified is delivery, with 7 risks identified, including a severe risk relating to Covid-19. This is deemed to be within risk appetite, and mitigation measures were set out in the submission which amended the logframe, approved by the Development Director. FCDO programme teams are actively working on the mitigation of risks, for example facilitating relationships between the supplier and government, and the health adviser engaging with MHA. Safeguarding is also a significant risk category, with four risks identified. However there is notably no safeguarding risk identified with the LEAP part of the programme, which given the concerns outlined in this and the previous AR would seem to be a major omission. Contextual risks are appropriately identified, as fiduciary, reputational and operational. The team should continue to review the risks regularly as the situation in response to Covid and its impacts are likely to happen quite rapidly, and could see safeguarding, fiduciary and operational risks in particular become more likely to manifest.

Update on Partnership Principles

All Financial Aid to Government which DFID provides is subject to the Partnership Principles, which set out DFID’s expectations of Governments in relation to: (1) commitment to poverty reduction; (2) commitment to human rights and other international obligations; (3) strengthening financial management and accountability and reducing the risks of funds being misused through weak administration or corruption; and (4) commitment to strengthening domestic accountability. This programme relates to all four partnership principles.

The partnership principles of poverty reduction and the sustainable development goals, management of public finances, tackling concerns about human rights abuses and corruption, and improving domestic accountability are regularly assessed by FCDO, and the last update was done in January 2021.

COVID-19 has increased the risk of reversal of some of the gains made towards poverty reduction and the SDGs. In a context of extreme fiscal constraint, poverty reduction expenditure (for Primary Education, Health and Social Protection) continues to be at risk of stagnating or falling, driving poor people even deeper into poverty whilst creating new categories of poor and vulnerable struggling to meet their basic needs. Stronger and sustained GoG commitment to increasing the share of resources allocated to the social sectors and leave no one behind is required to progress the Ghana beyond Aid ambition.

It is assessed that the Government of Ghana is broadly committed to the four UK’s four Partnership Principles

Annual Statement of Progress (financial aid programmes only – delete if n/a) [1 page]

Current level of fiduciary risk and direction of travel since last ASP	Minor/Moderate/Major/Severe / Improving/Stable/Worsening
Specific assessment of corruption risk and direction of travel since last ASP	Minor /Moderate/Major/Severe / Improving/Stable/Worsening
Is a full FRA update required?	[Yes: likely to be needed where risk levels have worsened / No: where the situation is stable or improving]

[Read the Fiduciary Risk Assessment Smart Guide to help you answer these questions. If you have sensitivity concerns about publishing this assessment, you should complete this ASP in a separate document to submit to your HoD alongside this Annual Review. You can then delete this section.

What are the key fiduciary risks? Include a brief description of the risks, planned mitigation measures, and progress achieved/remedial actions.
- Is there a credible PFMA reform programme? Is donor support for PFM aligned behind a single government-led action plan?
- Can you cite examples of positive progress to report which could feed into FCDO external publications?

List the sources used in preparing this Annual Statement of Progress, e.g. government/donor reports, meeting minutes, CSO indices.]

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency. [max 1 page]

As noted in the QAU assessment of the programme, LNOB is a complex programme with high levels of ambition. The need to bring the component themes of the programme together was reaffirmed by respondents in the AR, who noted that this was a gap, and bringing partners together to offer a more integrated and inclusive response was not only the correct strategic choice, but also filled a gap that wasn’t being addressed otherwise. This year has seen some initial steps in establishing a more joined up approach to working, with the convening of the steering committee and two technical working groups. However, after two years of the programme it is valid to look critically at whether the different parts are bring brought together effectively to achieve the programmes overarching goals and whether systems and ways of workings are being established that this collaboration is sustained beyond the programme period.

The first thing to note is that in terms of relationship management stakeholders were appreciative of FCDO’s way of engaging. However, while there are some positive examples of collaboration and partners’ adding real value to each other’s’ work, there is still a fairly common feeling that there is a shared lack of understanding of both the overall programme goals and of each of the components being sufficiently understood within the overarching framework. One respondent noted that there was a gap between the various elements in the programme as described in the business case and the reality of how partners worked and could prioritise on the ground, which made components significantly less compatible than envisaged. Another noted that they felt there was a lack of understanding by FCDO on the mandate of the partner and how they related to government, which meant that they were being held accountable for actions that were the responsibility of government. Options were brought on board in 2020, and were tasked with acting as a coordinating agent for the programme – effectively taking control of logframe development, convening meetings and workshops and facilitating increased interaction and integration of partners in pursuit of the programme goals. Their ability to do this has been hampered by the fact that a year of the programme had already passed, and covid-19 has made meetings and workshops significantly more challenging. However, in addition to this there have been challenges relating to the amount of traction that they have over other partners. Theoretically regular steering group meetings would help keep the ‘programme’ on track, but the current extent to which partners engage in a systematic and proactive way with each other is limited, which means that different components remain relatively siloed.

Led by Options, the logframe was reviewed this year, both based on recommendations from the previous AR and to ensure that it captured the new strands of work and emphasis of the Covid response. Due to delays on both the partner and FCDO side, this was not approved until September 2020. It remains quite a complicated document, and it is not always clear where responsibility lies for various milestones. Partners are able to populate ‘their’ parts of the logframe, but the extent to which the logframe aligns fully to partner reporting metrics, methodologies and timelines is unclear.

The reality is that if the FCDO wants to drive a more joined up programmatic approach then they need to play a more interventionist role at the programme level. If partners are not brought together on a regular basis it is unlikely that they will become accustomed to each others’ ways of working and priority areas.

The review has had meetings with the majority of major stakeholders in the programme, including MoGSD, GNHR, World Bank, Unicef, WHO, Basic Needs Ghana and FCDO advisers and programme managers. In addition field visits were conducted to solicit inputs from partners the regional level, and from direct beneficiaries of the programme. Field visit opportunities and more wide-ranging discussions were more limited than ideal because of Covid restrictions.

Contract management.

WB
FCDO’s contribution to SDTF for the GPSNP programme is managed through an Administration Arrangement with the WB which sets out the guiding principles and procedures. The programme is structured in two components:  A Recipient executed grant, which constituted funding to be disbursed to MoGCSP and MoLGRD to support delivery of cash transfers both Regular LEAP beneficiaries and (included emergency stimulus package) to the poor and vulnerable beneficiaries outside the regular LEAP programme as a result of COVID-19, productive inclusion, TA, Shock Responsive social protection and GNHR). After the GPSNP restructuring in August 2020, production inclusion was excluded from FCDO’s project component and the original allocation to GNHR has been reduced by half.  A WB executed grant, which supports technical Assistance, capacity building activities, and WB activities (programme management and administration, implementation support costs) and Trust Fund fees. Approximately £3m was allocated to this component, reinforcing WB capacity to provide support and technical assistance to the GPSNP.

The Grant Agreement signed between the WB and GoG sets out the terms and conditions governing the project including the value of the project, project description, implementation arrangements and payment schedule. In addition, the WB’s Project Appraisal Document (PAD) serves as the overarching guiding document for implementation management of the programme.

The GPSNP has a Secretariat to ensure closer coordination between all relevant partners, provide programme implementation oversight and the WB provide strategic guidance and direction on implementation of the SDTF activities. The WB and FCDO also have regular catch-up meetings every months. Effective professional relationships were maintained, even though it was a difficult period for everyone as a result of COVID-19 and the restrictions that came with it, and DFID project management was very robust with a real focus on quality delivery in accordance agreed plan.

The meetings focus on overall programme progress, challenges, implementation and TA gaps, and additional opportunities to strengthen programme implementation. Emphasis is also on a forward look at issues of sustainability of the programme, especially in the current context of the COVID-19 global pandemic and its impacts. Sustainability issues and priority actions will need to continue to feature strongly in all future discussions with the GoG.

Quality of financial management
WB: The WB provides FCDO with financial information relating to receipts, disbursements and fund balances. The aide-memoire of GPSNP programme implementation support missions from 5-12 October 2020 which was shared with FCDO summarises key findings, recommendations and agreements reached during the mission. Quarter 1-3 progress reports have been submitted and quarter 4/Annual Reports are yet to be received. The 2021 workplan has been shared and provides forecasts figures for the year. FCDO can also access the most up-to-date financial data directly from the WB Trust Fund Donor Centre secure website. £4m was released this financial year for emergency cash transfers to the poor and vulnerable as a result of COVID-19 (these beneficiaries are outside the Regular LEAP). By November 2020, FCDO had disbursed a total of £ 12.1m out of the £21m allocation.  The audited financial reports covering the period as at June 2019 and that to 30 June 2020 conducted by Deloitte and Touche for the SDTF have been received. The audit report obtained an unqualified audit opinion and the TF according to the report, maintained in all material respect, effective internal financial controls are implemented in line with the Financing Agreement.  The MoGCSP under the GPSNP was audited for 2019 and obtained unqualified audit opinion. The project team will be following up on the recommendations. The GPSNP Secretariat also conducted financial management expenditure verification in the third quarter and provided technical support to District Social Welfare Officers in 30 selected districts and the final reports are yet to be finalised.

WHO: FCDO has a contribution agreement with the WHO was originally signed in November 2019 for the delivery of the agreed project “Improving Access to Good Quality Mental Health Services in Ghana”. This agreement has since been amended to reflect new dates for releasing funds for planned activities in the agreed workplan. Overall, funds allocation for this component is £1,350,000, £500,000 released in 2019, representing 37% of the total contribution agreement budget. The final tranche of £850,000 is expected to be released in February 2021 because WHO has not received funds since the first tranche was released because actual implementation of activities was put on hold for some time due to the COVID pandemic situation in Ghana. Activities were carried out this year from savings and balances held. Following that, the government enforced several public health interventions which included temporary lockdown and other restrictions to ensure social distancing, which impacted negatively on the implementation of the FCDO supported Mental Health Project. The six-monthly and the annual report (including the financial reports) were received on time. The programme team should ensure that progress against the planned activities is monitored regularly to improve programme spend.  FCDO followed up and received updates on the recommendations from the due diligence that was conducted in October 2019 before the project started.

WHO – Vfm: The main cost drivers of the project have been the grants to partners, as well as general operational and expenses costs. This has not changed significantly from what was originally envisaged in the business case. Procurement of experienced local Consultants, which is less expensive while providing the expected level of expertise. Also, through the agreement with WHO, programme interventions build on existing tools and materials hence did not require additional cost. All Quality Rights and mhGAP interventions have already been developed and hence no development costs are involved.

UNICEF: The Contribution Agreement for £1,550,000 with UNICEF was signed off in December 2019 for work in Strengthening Integrated Social Services and V&E assessment. The first tranche payment of £350,000 was made in December 2019. During the year and following discussions and correspondence between FCDO and the implementing partner, FCDO provided additional support of £900,000 earmarked for use as per UNICEF’s proposal for COVID-19 response activities bringing the total budget allocation to £2,450,000. As a result, the contribution agreement was amended on 20th July 2020 to reflect the additional funding.  FCDO and UNICEF are currently deciding on second amendment to the contribution agreement to revise the disbursement schedule.

UNICEF – Vfm: The main cost drivers of the project have been the grants to partners, staff and other personnel costs, supplies and commodities as well as general operational costs. This has not changed significantly from what was originally envisaged in the business case. Procurement of experienced local Consultants, which is less expensive while providing the expected level of expertise were hired during the period. Also, through the agreement with UNICEF, programme interventions build on existing tools/materials hence did not require additional cost.

BasicNeeds: FCDO signed an Accountable Grant Arrangement with BasicNeeds Ghana in September 2019 to implement the project ‘improving mental health policy and services in Ghana’. The allocated budget was for £150,000 for a six-month period which ended in February 2020. The payment mechanism agreed with the delivery agent is a quarterly advance payment. In actual amount transferred was £125,170. The project final reports (Narrative/Financial) were submitted and their final project audit obtained unqualified opinion. Asset register is kept and submitted to FCDO quarterly but these have now been handed over to Options Consultancy Service, a consortium implementing FCDO’s “Mental Health & Disability” project under LNOB.

MoH/MHA: The MoU was signed in January 2020 for the MoH/MHA to deliver improved mental health services in Ghana in the RbA. Total allocation for the RbA is £2,000,000 over four years. Payments are based on delivery of agreed milestones using the verification guidelines agreed by all parties and as set out in the MoU. The first release of £400,000 in 2019, made through the MoF to the MoH and then to MHA/GHS. The forecast for the second release for the 20/21 financial year was also £400,000. The team held a verification meeting Monday 1st Feb with the MoH and MHA to go through the agreed milestones and what they had achieved.  Overall, they have achieved everything but the 1st milestones around the Mental Health Bill, there were some errors that have to be corrected. They are supposed to send a letter to the attorney General for correction through the MoH. The letter was rather sent to the MoH, but the Ministry had not actioned it. As a result, FCDO agreed to pay them £380,000 instead of the £400,000 originally planned.

The programme holds one commercial contract, with Options consultancy.

Contract management:
The contract commenced on 20th January 2020 with the 6 months inception phase beginning straightaway in January 2020. In response to the COVID pandemic and the need to flex programmes to support C19 interventions, a contract amendment was completed in June 2020 to include a  C19 responsiveness plan which was  aligned to the programme ToC.  The original payment deliverables were also amended to reflect the inclusion of C19 interventions. Although the inception period ended in June 2020, the programme has not moved fully into implementation as there was a need to further develop solid work plans that met FCDO’s expectations. The move into implementation was also halted by the ‘pause’ in spending and reprioritisation of country budgets. This resulted in a reduction in the pot of funds available for Options from about £2.2m originally agreed with them for FY 2020 to £1.8m; the result was a revision again to the payment deliverables and workplan for the remainder of the FY. The latest central directive to pause the signing of new agreements with implications for spend in the FY 2021 means that we are still unable to move the contract formally from inception to implementation. Notwithstanding the uncertainties, the Options-led consortium is currently engaging in scenario planning and trying to carry on with current work plans until they receive concrete confirmation from FCDO on next steps re the contract amendment. Meanwhile, FCDO Ghana has sent Options a ‘holding email’ in consultation with PCD to lay out the challenges which have prevented the move into implementation pending final communication from the centre on budgets and agreements.

Quarterly reports (including the annual report) and invoices were received on time and covered the key reporting areas agreed at the start of the contract. Fortnightly meetings are held between FCDO and Options to discuss progress of work and address any challenges. Options has put in place a grant operations manual to guide its grants management with oversight by the Team Leader and Grants Manager.

Options have complied with the supplier code of conduct and there have been no issues so far. A SRM scorecard has not yet been completed for Options but the overall outlook from the FCDO perspective is that Options is on track to deliver on the programme KPIs with guidance from FCDO.

Options has duly produced a delivery chain map which includes the major risks to delivery, a risk register is also maintained and updated each quarter and an asset register is kept and submitted to FCDO quarterly. A total of 37 payment deliverables were delivered over the one year period of the programme and were submitted on time.

VFM:
Options has a VfM framework which is monitored and updated throughout the year. The key cost drivers for the programme have not changed although the vfm indicators were revised in Q3. The key cost drivers for the contract remain: staff costs, grants to partners, as well as payment deliverables and operational costs.

The effect of COVID 19 has meant staff working from home and therefore some reduction in cost of operations; the resultant effect being minor variances to each quarter’s financial projections. The COVID 19 restrictions have also impacted spend in that most ‘face to face’ meetings were converted to virtual meetings and travels were kept to minimum and were for very business-critical needs.

Forecasting accuracy was acceptable with minimal variances averaging about +/- 7 to 10% over the first year. Options have been challenged to target lower variances particularly in view of the budget cuts.

Social Development Direct (SDD):  The “Rapid Review Scoping Study” to assess disability and gender inclusion in the LEAP programme” ended in April 2020. All contractual deliverables milestones have been met. Presentation of findings to the World Bank, DFID and Government with a roadmap and action plan to integrate findings into GPSNP has been completed and final payment has been made. The MoGCSP has agreed to take the action plan forward and plans are underway to organise a meeting in March 2021 with NCPD and other stakeholders to discuss the action plan and integrate them into the future workplans.

Asset management
Partners maintained an assets register/inventory, with each item having a tag number and other relevant information. The inventory lists are updated and submitted to DFID with quarterly reports. However, due to the COVID-19 pandemic, partner organisations were working from home and therefore was not possible to undertake physical assets verification exercise.

Date of last narrative financial report(s)	Options Consultancy Services: 30th January 2021 / WHO: 27th January 2021 / UNICEF: 15th February 2021 / WBTF/GPSNP: 28th February 2021 / BasicNeeds: 30th March 2020 / MoH/MHA (RbA): 15th February 2021
Date of last audited annual statement (s)	WBTF: 30 June 2020 / MoGCSP: 31st December 2020 / BasicNeeds: 30th April 2020