## Annual Review – Education Research in Conflict and Protracted Crisis (ERICC)

Title: Education Research in Conflict and Protracted Crisis (ERICC)
Programme Value £ (full life): £26.5m		Review date: 01/12/2025
Programme Code: 300405	AMP start date: 01/09/2016	AMP end date: 30/06/2028

Summary of Programme Performance
Year	2018	2019	2020	2021	2022	2023	2024	2025
Overall Output Score	B	B	B	A	A	A	A	A+
Risk Rating	Moderate	Low	Major	Major	Major	Major	Major	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0006795.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0003065.xlsx

## A: SUMMARY AND OVERVIEW

Description of programme
The UN estimates that globally there are 234 million school aged children and youth affected by emergencies and protracted crises. Of these, 85 million are not in school (43 million girls and 17 million children with a disability) and a further 59 million are in school but not learning.[1] The number of crises is increasing due to both conflict and climate change, and these crises are becoming increasingly drawn out with the average conflict lasting almost a decade. In this context, education is a vital source of protection, psychosocial support, and hope through learning and qualifications. To date, there are major evidence gaps on “what works” to provide quality education in conflict and protracted crisis.
[1] ECW Global Estimates 2025: global_estimates_report_2025.pdf

Education Research in Conflict and Protracted Crisis (ERICC) is a £26.5m programme over seven years (2021 – 2028). The programme aims to organise, synthesise, advance and communicate the evidence base on what works to improve the holistic learning of children, and strengthen the coherence of education systems in conflict and protracted crisis contexts. Through a focus on research co-construction at the country level, strengthening Global South academic institutions and knowledge networks, and a responsive Helpdesk function, ERICC evidence is grounded in the needs and priorities of stakeholders, helping to enable greater evidence relevance, uptake and use. The programme primarily operates in eight focal countries: Bangladesh (Cox’s Bazaar), Iraq, Jordan, Lebanon, Myanmar, Nigeria, South Sudan, and Syria. The programme has four components:

1. Research on the most effective approaches to education provision in conflict and protracted crises at the global and country level – a £19.5m commercial contract managed by International Rescue Committee (IRC), with a Research Programme Consortium (RPC) co-led by University College London (UCL) and IRC, with the Centre for Lebanese Studies, Common Heritage Foundation, Inclusive Education Foundation, OTHERWise, Overseas Development Institute (ODI), Osman Consulting and Queen Rania Foundation as downstream country research partners.
2. Operational in-country support – a responsive Helpdesk that provides support to FCDO advisors, under the same commercial contract led by IRC.
3. Evidence Dissemination and Uptake – a £0.8m Accountable Grant held by the Inter-agency Network for Education in Emergencies (INEE).
4. Knowledge Systems Strengthening – a £3.8m Accountable Grant held by the British Academy.
Summary supporting narrative for the overall score in this review

The ERICC programme scores an A+, with outputs 1 and 2 scoring A+ and outputs 3 and 4 scoring As.  Between October 2024 and October 2025, ERICC has demonstrated strong overall performance, with the majority of output indicators either met or exceeded across its four core components. Notable achievements include the initiation and completion of a high number of context-specific and comparative studies, with 59 journal articles and 8 books/book chapters to be published this year across components 1 and 4. This provides valuable new evidence for strengthening education in conflict and crisis settings. Component 2, the ERICC Helpdesk has been particularly impactful, responding to 20 rapid research and technical assistance requests with a 100% satisfaction rate and expanding its reach to additional countries and global audiences, while directly achieving measurable impact in several contexts. The programme has also made good progress in making evidence accessible, with strong country-level engagement and a growing global audience with over 10,000 downloads and 11,000 webpage views of ERICC resources, ensuring inclusivity through translation of key publications into Arabic, French, and Spanish. Capacity building efforts to build a future pipeline of education in emergencies researchers including from the Global South have been robust, with 181 researchers trained and 33 teaching capacity activities delivered, strengthening knowledge systems in the Global South.

Major lessons and recommendations for the year ahead

Table 1: Key recommendations for ERICC
	Action	Responsible Agent	Deadline
1	Increase the visibility and use of ERICC evidence through a sector-wide symposium or a series of strategic regional conferences. Bring together key education in conflict/emergencies researchers, policy makers and practitioners to bridge dialogue between evidence and practice.	IRC	October 2026
2	Review and refine country-level dissemination and engagement strategies to ensure they consistently reach a broad spectrum of stakeholders, including government, donors, local organisations, and civil society. Ensure that recommendations in all working papers and policy briefs are well developed and tailored for these different audiences.	IRC	January 2026
3	Present findings from the ERICC global evidence reviews on effectiveness and cost-effectiveness to the Global Evidence in Education Advisory Panel (GEEAP), seeking endorsement of the reports and strengthening GEEAP’s conflict and crisis evidence lens.	IRC and FCDO	February 2026
4	Develop a communications and evidence uptake phased handover plan between IRC/ODI and INEE ahead of INEE’s accountable grant ending in September 2026.	INEE, with IRC and ODI	July 2026
5	Review targets on the number of events and INEE-developed outputs, increasing the level of ambition and available support to synthesise and communicate common research findings across all components of the programme.	INEE	January 2026
6	Chairs should identify or create a minimum of one engagement opportunity with government, policy makers and donors to communicate key research findings in the final months of the accountable grant.	British Academy	March 2026
7	FCDO should consider how to expand the ERICC Helpdesk service, including under FCDO's Centre of Expertise, and review lessons learned in order to replicate its success in future programmes.	FCDO	September 2026
8	Develop the ERICC external endline evaluation terms of reference and procure an evaluation partner.	FCDO	TOR finalised: April 2026; Procurement completed: September 2026

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The ERICC Theory of Change (TOC) posits that if the programme organises and builds a rigorous body of evidence on what works for EiEPC, provides responsive evidence support to education programmes in FCDO focal countries, while building Southern thought leadership on EiEPC evidence, and ensures decision-makers have access to this research, then the programme will contribute to evidence-based policies and better value for money programmes, which will ensure that more children get better quality education in conflict and protracted crisis contexts (Annex A).

During the 2024–2025 reporting period, the ERICC programme undertook a comprehensive revision of its TOC as per the annual review recommendation, reflecting both implementation experience and the evolving needs of the sector. This process was led jointly by the FCDO programme management team and the International Rescue Committee (IRC), following the outcomes of the cross-component coordination meeting. Over three months, FCDO and IRC worked collaboratively to update the TOC. The revised TOC was subsequently circulated to all ERICC partners for feedback and finalised following their input.

Key features of the revised TOC include:
- Integrated impact chain: The TOC now explicitly maps the progression from inputs to outputs, outcomes, and impact across all components, highlighting the interdependencies and collaborative mechanisms required for success.
- Political economy assumptions: The TOC incorporates new assumptions regarding the wider political economy, recognising that factors such as short-term financing, competitive programming, conflicting organisational mandates, and lack of consensus on core measures and tools can constrain evidence uptake. These assumptions are now explicitly articulated as critical considerations in the pathway from outputs to outcomes and impact.
- Cross-component collaboration: The revised TOC emphasises the importance of collaboration between components. For example, research produced under Component 1 (RPC) is disseminated and amplified through Component 3 (INEE), while knowledge systems strengthened under Component 4 (BA) support both the generation and uptake of evidence. The Helpdesk (Component 2) provides responsive, demand-driven support that draws on expertise from across Component 1 and Component 4.
- Co-construction and local ownership: The TOC cements the programme’s commitment to co-constructing research agendas with local stakeholders, ensuring that evidence is relevant, accessible, and actionable. This approach has facilitated early uptake of findings in policy and programme design, as seen in recent examples from Nigeria and Myanmar (box 2 and box 6).
- Sustainability and iterative learning: The TOC now recognises the cyclical and iterative nature of ERICC’s work, with ongoing refinement of strategies and activities based on emerging evidence and changing contexts.

The revised Theory of Change provides a more coherent, integrated, and contextually grounded framework for the ERICC programme. It reflects the complexity of delivering education research in conflict and protracted crisis settings, and the need for collaborative, locally owned, and politically informed approaches to evidence generation and use.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Outcome 1: Development of a rigorous body of evidence on what works for education in conflict and protracted crisis (component 1):
Indicator(s)	Milestone(s) / for this review	Progress
Outcome indicator 1.1: Number of external citations of ERICC RPC outputs in peer reviewed publications	5	7 - Exceeded
Outcome indicator 1.2: Number of external conferences and/or other high-profile events at which the ERICC RPC's research is presented or discussed	3	6 - Exceeded

Outcome 1.1 (academic citations) is on track. Over the past year the RPC has made concerted efforts to advance its academic publications (Annex B) and this in turn has led to seven citations of ERICC research in peer-reviewed journal publications by academics outside the programme, reflecting the growing interest and confidence in the evidence produced by ERICC. Studies cited include: the ERICC Conceptual Framework, Evidence Review of South Sudan and Global Evidence Review of Teacher Management in conflict and crisis settings.

Outcome 1.2 (conferences) is also on-track. This outcome captures the confidence in the research quality, indicated by acceptance to present studies at esteemed academic and other external, high-profile events. This year, ERICC presented 2 papers at the Comparative and International Education Society’s Conference (CIES) (March 2025), featured prominently at the Education in Emergencies conference hosted by the University of Helsinki and Finn Church Aid (May 2025) and presented an impressive 12 papers at the Education and Development Forum (UKFIET) conference (September 2025). Research on teacher professional development, gender inclusive education during conflict and crisis, and education in emergencies financing was also presented and discussed at notable policy events including Asia Pacific ASPBAE Regional Workshop on Gender-Transformative Education (August 2025), UNESCO World Teachers Summit (August 2025), and the UN General Assembly (UNGA) (September 2025).

Outcome 2: Strengthened education programmes in FCDO focal countries / regions (component 2):
Indicator(s)	Milestone(s) / for this review	Progress
Outcome indicator 2.1: Number of high-quality impact stories demonstrating the ERICC Helpdesk's contribution to practices, approaches, strategies, research and evidence, or policy recommendations	4	5 - Exceeded
Outcome indicator 2.2: Number of requesters and percentage who note that ERICC Helpdesk support has strongly contributed to the development of new practices, approaches, strategies, or policy recommendations	6 / 65%	14 /100% - Exceeded

Outcome 2 is on track, with indicators 2.1 and 2.2 exceeding expectations. The responsive ERICC Helpdesk has continued to see strong demand from FCDO advisors, and numerous return requests, demonstrating confidence and satisfaction in the service provided. See Box 1 below for an example of impact, and Output 2 for more detailed discussion.

Box 1: Impact Story – Improved safety, quality and equity of examinations and learning in Sudan / Since the onset of the conflict in Sudan in 2023, secondary school examinations were suspended, despite their critical role in enabling young people to pursue higher education, employment, or migration to more stable settings. The Helpdesk’s audit of Sudan’s December 2024 secondary school exams, commissioned by FCDO, addressed key equity and protection issues after exams resumed only in SAF-controlled areas. The resulting report directly shaped donor and cluster policy, including the British Embassy Sudan’s position, and highlighted the need for safe student movement. It drew attention to youth-led Emergency Response Rooms, which consequently received donor support in the next exam cycle. The report improved inter-cluster coordination, increasing Protection Cluster engagement, and its recommendations led to better-informed exam planning. Several organisations have since requested further analysis, demonstrating the report’s significant influence and ongoing relevance in shaping education and protection responses in Sudan. / A second Helpdesk analysis on Sudan’s education sector provided rare, evidence-based insights linking current service delivery to historical patterns of exclusion in education, highlighting how conflict perpetuates systemic inequities. The report clarified the role and constraints of international actors, enabling FCDO Sudan to advocate for more equitable, coordinated funding. Widely disseminated and presented to donors and partners, the report directly influenced the expansion of the Global Partnership for Education (GPE) Systemic Transformation Grant to include Darfur and Kordofan. It also led to a new UK scope of work to improve alternative learning pathways, revealing the need for investment in quality and harmonisation of non-formal education. The research has already shaped multiple donor conversations and planned investment across the sector.

Outcome 3: Decision-makers access and use evidence on education in conflict and protracted crisis (components 1 and 3):
Indicator(s)	Milestone(s) / for this review	Progress
Outcome indicator 3.1: Number of policy documents, guidelines, and working papers referencing ERICC evidence	6	6 - Met
Outcome indicator 3.2: Percentage of relevant decision makers identified through target audience mapping that find ERICC evidence useful in making policy and programming decisions	55%	76% - Exceeded
Outcome indicator 3.3: # of impact stories demonstrating use of ERICC evidence	2	2 – Met

Outcome 3.1 (policy and practitioner citations) has been met. Since October 2024, ERICC evidence has been cited in six sector relevant publications, from global strategic documents to programmatic country plans, including:
- U.S. Government Strategy on International Basic Education, FY 2024-2029[2] which was informed by the ERICC Conceptual Framework;
  [2] The Strategy is no longer available online following the closure of USAID under the Trump administration.
- UNESCO’s policy brief Renewing the promise of development effectiveness for transforming education which draws upon ODI’s ERICC analysis of the political economy and domestic and household spending on education in fragile contexts;
- UNHCR’s West and Central Africa: Education Report (Oct 2024) which highlights the ERICC Global Evidence Review on Inclusion of Refugees in Host Country Education Systems;
- World Food Programme’s Evaluation of the EU MADAD Project which cites the ERICC Mapping of Education Data Systems in Lebanon (August 2025);
- UNESCO-IIEP's Education Sector Analysis in Jordan, with ERICC country research cited as part of the review of progress ahead of developing the country’s new Education Strategic Plan (2026–2030)[3]; and
  [3] These citations are reported by IRC and INEE but were not picked up by Overton reporting as the documents are not publicly available outside of the country yet.
- Global Partnership for Education (GPE) Systems Transformation Grant strategic plan in Myanmar, which draws on a range of ERICC country research.[4]
  [4] Ibid.
Additional forthcoming policy documents and working papers are anticipated to cite ERICC evidence, following INEE’s targeted engagement in the reporting period. This includes UNESCO Beirut’s forthcoming MENA Strategy for which an ERICC regional synthesis was developed; World Bank modelling for education financing in fragile and conflict affected countries in West Africa which has been influenced by the ERICC findings on domestic and household financing; as well as a new Save the Children education programme under design which utilises a range of ERICC evidence. Overall, the ERICC programme is well-known[5] and respected, and as these examples illustrate the research is already having a tangible impact on policy and programmes at a global, regional and national level.
[5] Overton reporting also highlights a number of citations that refer to the ERICC programme’s design and key objectives, suggesting a range of key actors are looking to use ERICC research in the future (e.g. Organisational Evaluation of Education Cannot Wait; World Bank’s The Foundational Learning Compact Umbrella Trust Fund Progress Report and UNHCR submission to the International Development Committee Inquiry: FCDO’s approach to displaced people)

Outcome 3.2 (perceptions of usefulness) was exceeded. Following a strategic global and regional stakeholder mapping undertaken by INEE last year, key actors were identified and engaged with during the reporting period. In September 2025, a survey went to key stakeholders to understand the utility of ERICC evidence. Survey responses were received from 25 key stakeholders, 11 of whom work at the global level, 1 in West Africa, 2 in MENA, 7 from Southeast Asia and 2 across the African continent. In response to the statement “ERICC evidence can help inform policy or programming decisions”, 52% of the respondents agreed with the statement and 24% strongly agreed with the statement. Additionally, 47% of respondents agreed or strongly agreed with the statement “I have used or cited ERICC evidence in internal discussions, planning, or advocacy” – indicating almost half the respondents have been able to directly apply or use ERICC evidence.

Outcome 3.3 (impact stories) was met, with two clear use cases of ERICC evidence by the IRC RPC. ERICC evidence has been most instrumental in informing country-led policy and programmatic discussions, through component 1 of the programme. See box 2 and Output 1 for more details.

Box 2: Impact Story: Strengthening the Nigerian Government’s policy reforms through community-based insights and engagement / The ERICC Universal Basic Education study in Adamawa is supporting education continuity in conflict-affected areas by harnessing community-driven insights. Through a collaborative research process, the Adamawa State Ministry of Education and Local Government Education Authority (LGEA) are actively testing innovative approaches to improve access to basic education and reduce out-of-school children, especially in areas impacted by Boko Haram. Notably, the LGEA has piloted reforms suggested by community members as part of ERICC research, including the introduction of flexible school timetables, accelerated learning programmes during holidays, and mechanisms for community input into the curriculum. These pilots are being evaluated for effectiveness in the third ERICC Nigeria study. The Ministry and LGEA have also dedicated staff to participate and observe different stages of the research. This collaboration is strengthening local capacity and is expected to further influence the Nigerian National Assembly’s review of the 2004 Universal Basic Education Act which began in August 2025.

Efforts by INEE to support evidence uptake have had limited success to date. However, important groundwork that can lead to impact has been established. This includes a recent closed-door workshop with the INEE Mental Health, Psycho-Social Support and Socio-Emotional Learning Working Groups, an Arabic language roundtable event with EiEPC practitioners in the MENA region, and ongoing discussions with Education Cannot Wait (ECW) as part of the Technical Advisory Group to inform ECW’s new strategic plan. These entry points can be further followed up in the coming months.

Outcome 4: Knowledge systems strengthened for research on education in conflict and protracted crisis (component 4):
Indicator(s)	Milestone(s) / for this review	Progress
Outcome indicator 4.1 Percentage of surveyed stakeholders who believe ERICC is making a strong contribution to strengthening the production of knowledge on education in conflict and protracted crises	75%	88% - Exceeded

Outcome 4 has exceeded expectations. As all three ERICC bilateral Chairs come to the end of their tenure, a survey by the British Academy was sent to beneficiaries of the knowledge systems strengthening component in Bangladesh, Iraq and Lebanon. Of those surveyed (52), 88% believe that ERICC is making a strong contribution to the production of knowledge on education in conflict and protracted crises, 90% stated that the programme has made a strong or very strong impact on strengthening knowledge production within their own academic institutions, and 88% reported that the programme had a strong or very strong impact on their personal development. Moreover, 82% reported that these efforts had also strengthened evidence-policy dialogue in their country. Qualitative feedback further highlighted the value of “strong connections with a range of researchers”, “remarkable” networks working on projects and themes across universities and countries in the Middle East, as well the “collaborative learning” approaches and "highly valuable, practical training sessions” that strengthened individual researcher capacity. A testimonial is included in Box 3 below.

Box 3: Testimonial: Networking to bridge evidence, policy and practice in Bangladesh / “The Chair-facilitated convening and brokering that leads to funded collaboration has been most impactful—specifically, the colloquium-to-grant pathway that produced the AMS networking grant. This activity transformed a one-off event into a resourced, long-term North–South network linking academia, policy influencers, and communities; enabled child participation as co-researchers; and seeded practical collaborations (e.g., BRAC-IED knowledge exchange and the Flying Seagull school partnership). Because it builds durable relationships and a pipeline from evidence to policy and practice, this Chair-led networking model has the strongest potential for lasting, system-level impact.” / Academic participant from Bangladesh

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

ERICC is widely considered by the education sector to be delivering actionable and rigorous research for policy and practice. The programme addresses long-standing evidence gaps and is gradually contributing to a shift in the culture of evidence use within education in emergencies and protracted crisis sector. The A+ score of this AR, outperforming realistic and stretching targets, reflects that the programme is high performing.

ERICC supports the Research and Evidence Directorate Departmental Plan and advances a number of the Foreign Secretary’s key priorities, including the focus of addressing fragility and preventing conflict, and to promote a new development approach based on genuine respect and partnership with the Global South.

## C. DETAILED OUTPUT SCORING

Output Title	The ERICC RPC produces context-specific and comparative research based on demand-driven research agendas aligned to the ERICC Conceptual Framework
Output number:		1	Output Score:	A+
Impact weighting (%):		45%	Weighting revised since last AR?	Increased by 5%

Indicator(s)	Milestones for this review	Progress
1.1 # of studies initiated that address the ERICC conceptual framework and/or stakeholder priorities, disaggregated by study level (country, cross-regional, global)	30	38 - Exceeded / (22 country studies; 16 global studies)
1.2 # of studies completed that address the ERICC conceptual framework and/or stakeholder priorities disaggregated by study type and level.	10	26 – Exceeded / (19 formative research; 1 design research; 3 implementation research; 3 political economy analysis)
1.3 % of ERICC studies from which comparative publications are produced	25%	38% - Exceeded
1.4 # of engagement meetings held with key stakeholders across ERICC focal countries	21	97 - Exceeded
1.6 # of externally peer reviewed publications submitted for publication in relevant disciplines from the ERICC research portfolio, disaggregated by publication type (journal article, special issue article, book, book chapter) and geographic scope (single-context, multi-country, global)	24	33 – Exceeded / (12 country studies; 21 global studies)
1.7 % of peer reviewed publications submitted from the ERICC research portfolio accepted for publication	75%	66.6% - Not met
1.8 % of peer reviewed publications from the ERICC research portfolio published to open access sources	100%	100% - Met
1.9 # of conference paper, presentation, and/or panel discussion submissions approved or accepted.	10	17 - Exceeded
1.10 # of working papers published from the ERICC research portfolio, disaggregated by geographic scope (single-context, multi-country, global)	6	11 – Exceeded / (8 country studies; 1 multi-country study; 2 global studies)
1.11 # of technical, policy, or advocacy briefs published that include key findings from ERICC research	14	32 - Exceeded
1.12 % of peer reviewed publications submitted from the ERICC research portfolio whose lead author is / a) female / b) from the global south / c) either/or	a) 60% / b) 60% / c) 60%	a) 65% / b) 50% / c) 85% / Met
1.13 # and % of relevant ERICC studies that use inclusion-oriented disaggregated data to report differential findings for individual-level data on / a) gender, / b) disability, and / c) migration/citizenship status	20/100% / a) 100% / b) 25% / c) 75%	23 / 96% - / a) 96% / b) 65% / c) 83% / Met
1.14 # and % of ERICC research outputs which include specific focus for gender analysis, and are considered gender responsive, according to DAC guidelines	70%	52% / Not met

Briefly describe the output’s activities and provide supporting narrative for the score.
Overall, this output scores an A+, reflecting that eight indicators have been exceeded, three indicators have been met, and two indicators did not meet expectations.

During the reporting period, the RPC initiated 38 new studies and completed 26 studies (indicators 1.1 and 1.2). Country level research and global, multi-country research together will provide both deep, nuanced contextual evidence as well as comparable data for insights on the effectiveness of different types of education systems and interventions across conflict-affected contexts. Country level studies completed during the reporting period included lessons from Jordan on reducing drop out, the impact of war on pre-existing equity and inclusion factors in Lebanon, the effectiveness of pastoralist education interventions in South Sudan and the context-related determinants of education system and outcomes in Syria, among others.

Additionally, significant progress was made on global, multi-country studies (MCS). This includes:
- MCS-1 and MCS-3: Two studies examining learning pathways and teachers’ professional development undertook tool piloting and data collection in Bangladesh, Jordan, Myanmar and South Sudan.
- MCS-2: As part of the ‘what works’ global evidence review series, studies were completed on (i) improving students’ mental health and wellbeing, (ii) safety in and around schools, (iii) equity and social cohesion, (iv) continuity of education in conflict and crisis, (v) socio-emotional learning and (vi) foundational literacy and numeracy.
- MCS-4: Innovative evidence on the intersection between climate change and conflict on education system resilience was progressed in South Sudan and Syria with data collection initiated.
- MCS-5: Concept note and plans were finalised for new empirical research on education’s role in delivering peace, equity and social cohesion outcomes in the conflict-affected contexts of Bangladesh, Myanmar and Jordan.
A full list of studies is included in Annex B. Targets on the number of studies initiated and completed exceeded expectations as a result of planned thematic areas expanding in scope to produce multiple related studies and additional resource being made available to the IRC through fellowships with partner institutions.

Studies are appropriately disaggregated data by gender, disability and migration/citizenship status to improve understandings on individual-level experiences of education in conflict and protracted crisis (indicator 1.13). However, while there have been improvements year on year, continued work is needed to ensure more studies have strong gender analysis that can inform responsive and/or transformative approaches to education in conflict (indicator 1.14).

Notably, the RPC exceeded the target of 24 journal articles submitted, submitting 33 articles to journals for publication (indicator 1.6). This included 10 articles sent to the Education and Conflict Review (ECR) as part of a Special Issue focused on rigorous reviews of research evidence on promising education policies, programmes and practices in education in conflict-affected and protracted crises. The target set was stretching and realistic considering both the stage of the programme and that only 2 studies were submitted to journals in the previous year and the overachievement reflects the concerted efforts of UCL and IRC to focus on peer-reviewed academic outputs in the reporting period. Of the papers that have received responses from journals to date, 66.6% were accepted (indicator 1.7), suggesting that the rigour of research across the RPC is not uniformly high. Based on feedback from the journals, the RPC have identified key areas for improvement and are working to revise and resubmit the rejected papers.

During this reporting period, the RPC also continued to ensure visibility and uptake of ERICC research. Engagement with stakeholders remains very strong (output 1.4), with 97 engagements held across the seven focal countries with government, donors, INGOs, NGOs and civil society. The overachievement of this target reflects that country research teams have taken advantage of additional opportunities for arising and consistent stakeholder demand for evidence. The RPC also attended 6 conferences presenting 17 presentations throughout the course of the year (indicator 1.9). Moreover, to ensure that research outputs are accessible and relevant to policymakers, ERICC teams have published in a variety of formats, delivering 11 working papers (indicator 1.10), and 32 technical and policy briefs (indicator 1.11) as well as numerous blogs and other media products that are tailored to the needs of policymakers in ERICC contexts. More technical and policy briefs were developed than planned, due to the significant shifts in the EiE sector which presented additional opportunities to feed in research insights through tailored briefs for key stakeholders, including FCDO and multilateral organisations, upon request.

Box 4: Impact Story: Improving working conditions for temporary contract teachers in Jordan / Since 2016, KfW development bank has supported Jordan’s education response to the Syrian refugee crisis, financing temporary contract teacher (TCT) salaries in double-shift and camp schools under Germany’s Special Refugee Initiative. By mid-2024, grant support exceeded €202 million and a 2022/23 evaluation confirmed the programme’s success in education delivery and job creation. / However, challenges persist around TCT job security, as teachers are employed on one-year contracts due to annual funding cycles and fiscal constraints. Recent policy changes, such as Jordan’s Bylaw No 33/2024, may further restrict the rehiring of TCTs, shifting focus from retaining experienced staff to broader job distribution. / In spring 2025, QRF presented the ERICC studies to KfW, highlighting TCTs’ concerns about low pay, short-term contracts, inconsistent evaluations, and limited training. KfW have since incorporated ERICC recommendations into negotiations with the Jordanian Ministry of Education, advocating for improved record-keeping, experience-based hiring, and stronger contractual protections. KfW is considering making future support conditional on these reforms to better support TCTs. This will improve the working conditions of between 5,400–7,000 TCTs and benefit tens of thousands of Syrian children to have improved quality teaching without negatively impacting Jordanian students.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Additional weighting of 5% has been added to this output, reflecting the reduced weighting made to output 2. Indicator targets were reviewed and revised to ensure appropriately stretching and ambitious seven months prior to this AR.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on recommendations from the previous AR:
All recommendations from the previous AR have been taken forward. The level of effort of quantitative research expertise has significantly increased. A senior quantitative academic from UCL has been onboarded as a co-PI and an additional three mid-level quantitative researchers have joined the IRC team. This has resulted in a strengthened capacity to deliver the methodology and analysis on the multi-country research studies.

Steps have also been taken to improve the quality of academic outputs. This includes a revised academic publishing strategy, a strengthened internal peer review process and the establishment of an academic writing group to advance journal publications among country research teams who may be less experienced in publishing for international audiences. As a result of these efforts, the RPC has exceeded targets on studies completed and peer reviewed publication submissions and citations.

Furthermore, the RPC has integrated stronger political economy, and gender and inclusion analysis across the research portfolio. 11 consortium colleagues participated in a PEA capacity building course offered by ODI, while UCL and IRC updated the consortium’s Gender Equity and Social Inclusion (GESI) strategy, have reviewed concept notes to ensure gender and inclusion themes are properly integrated at the outset of studies, and are delivering a capacity building session on disability inclusive research in October 2025.

Lessons learned this year and recommendations for the year ahead:
Interviews with FCDO education advisors based in the focal countries and a listening session with IRC downstream global south partners were conducted as part of this AR to identify lessons learned and pertinent recommendations.

Country-level engagement remains strong, with mechanisms such as Country Advisory Committees proving particularly effective. In South Sudan, these committees have fostered robust government involvement and regular participation from donors, (I)NGOs, and other stakeholders; the government is even considering adopting this model to strengthen its own research capacity. In Jordan, the Queen Rania Foundation (QRF), as the country research partner, also supports the Local Education Group, further embedding research within policy discussions. In Myanmar, the country research team leverages existing coordination structures, such as the Myanmar Education Consortium—the primary donor coordination group—to present evidence and ensure ERICC research is demand-driven and informs sector-wide decisions.

These approaches facilitate dialogue between evidence and practice, ensuring ERICC research remains relevant to stakeholder needs and that emerging insights are communicated promptly to inform policy and programme development. Still, engagement strategies vary in approach and effectiveness across focal countries. For example, Nigeria demonstrates exemplary federal and state government engagement but has not maintained the same level of engagement among donor groups meaning that ERICC evidence remains underutilised among these stakeholders. Going forward, the RPC country research teams should review and refine their dissemination and engagement strategies to ensure they consistently reach a broad spectrum of stakeholders, including government, donors, local organisations, and civil society. Country research teams should identify the most relevant policy or programme design windows to communicate key research findings for maximum impact, prioritising strategic engagements.

Overall, research produced by the RPC is to a high standard. Efforts to improve peer-review processes and the on-boarding of additional expertise from both UCL and IRC have resulted in stronger academic outputs. FCDO advisors in the focal countries appreciated the relevance and quality of the evidence but also encouraged the RPC to look at strengthening policy briefs and working papers, by ensuring recommendations have clear actors, timelines, steps and rationales, taking into consideration the broader political economy. Additionally, further efforts are needed to improve the journal submission acceptance rate to meet the 75% target going forward. This may require ongoing capacity strengthening of some country research teams (such as Nigeria).

Output Title	The RPC establishes a demand-driven call down mechanism to provide technical expertise and small-scale research support
Output number:		2	Output Score:	A+
Impact weighting (%):		20%	Weighting revised since last AR?	Decreased by 5%

Indicator(s)	Milestones for this review	Progress
2.1 # and % of ERICC Helpdesk requests where clients note satisfaction with the request response	9 / 75%	10 / 100% - Exceeded
2.2 # of completed ERICC Helpdesk requests, disaggregated by geographic scope	12	20 - Exceeded
2.3 % of selected ERICC Helpdesk request respondents who are: a) from the global south; and /or b) female	a) 50% / b) 50%	a) 48% / b) 52% / Met

Briefly describe the output’s activities and provide supporting narrative for the score.
Overall, this output has exceeded expectations and scores an A+. The ERICC Helpdesk provides rapid (10 days), medium-term (30 days) and long-term (90 days) evidence support to FCDO. The Helpdesk allows ERICC to increase its geographical footprint beyond the main eight focal countries, with studies and technical assistance being conducted this year in additional countries/regions such as the Sahel, Sudan, Occupied Palestinian Territories, and Türkiye. Alongside this, the Helpdesk has produced evidence-based guidance for global audiences including the World Bank and UNHCR’s INSPIRE programme on refugee inclusion, and guidance notes for British Embassy staff on EiE in disaster management under FCDO’s Centre of Expertise for Education. Moreover, the Helpdesk organised a successful capacity strengthening workshop for 28 FCDO Education Advisors on systems strengthening in conflict affected contexts, demonstrating the service’s ability to build FCDO’s capability.
Following this component's success, additional funding from FCDO’s Girls’ Education Department has been channelled to the Helpdesk to open a new ‘climate’ window, providing support to FCDO advisors to respond to the Foreign Secretary’s priority on climate change as well as the intersecting and overlapping crises of conflict and climate change that an increasing number of countries are experiencing. This demonstrates the Helpdesk’s ability to quickly identify and onboard strong experts to its roster and meet the emerging needs of education stakeholders working in protracted, acute, multi-faceted and complex crises.
The Helpdesk received 20 requests and completed 20 during the review period (indicator 2.2). Requests ranged from rapid evidence synthesis on topics such as the role of education in migration and security; to sector reviews and primary data collection on issues including aid efficiency for refugee integration, curriculum reform and peace education; as well as technical assistance to map parallel education systems and education data availability. Currently, 3 requests are in process. Annex C includes a full list of requests, disaggregated by geography.
Box 5: Impact Story – Regional education support to Syrian refugees wishing to return / The civil war in Syria caused one of the world’s biggest humanitarian and displacement crises. After President Bashar Al Assad fled Syria in December 2024, the Syrian Salvation Government assumed caretaker control and urged refugees to return. However, many Syrians remain hesitant, especially families with school-aged children who require assurances of quality education before considering return. / In response, FCDO requested a rapid Helpdesk review to develop a comprehensive understanding of education-related enabling and inhibiting factors with the potential to influence return decisions among Syrian families. The study consolidated and analysed data across Syria, Türkiye, Jordan and Lebanon. / The findings have informed the UK’s Regional Syria Returnee Strategy, shaped the third year of FCDO’s Syria Education Programme, and guided new bilateral investment in Türkiye. They also strengthened FCDO’s engagement with UNICEF as regional lead, improving cross-country coordination, and highlighted the critical role of education in supporting returnees, influencing global humanitarian approaches.

Helpdesk users express a strong appreciation for the Helpdesk’s work, ranking an average of 4.6/5 on a Likert scale for satisfaction on post-request surveys (indicator 2.1). The Helpdesk scored an average of 4.8/5 for timeliness and clarity of communication, 4.6/5 for content, 4.5/5 for the rigour of research, and 4.3/5 for usability for the research, illustrating the high quality of query responses. Furthermore, 100% of requestors who provided survey feedback noted that they intend to use information from the Helpdesk response to influence or inform stronger practices, research, strategies or policy recommendations. An example of impact resulting from the Helpdesk service is included in Box 5, above. All survey respondents noted that they were either extremely likely (83%) or somewhat likely (17%) to use the Helpdesk again for their work.
A high number of Helpdesk responses continue to be led by women or scholars from the Global South, reflecting the programme’s intention to promote equitable knowledge production (indicator 2.3). This ability to leverage local experts and academics has enabled ERICC to collect and consolidate data on hard-to-reach populations, ensuring that minority and marginalised groups are better represented in education sector planning. An example of this unique value add is described below in Box 6.
Box 6: Impact story – Addressing key data gaps to inform Myanmar’s education service delivery / Since Myanmar’s 2021 coup, education provision has fragmented across de facto authorities (SAC), parallel government (NUG), and ethnic providers, leaving significant research and knowledge gaps, especially in SAC-controlled areas. The ERICC Helpdesk played a unique role by analysing complementary, community-led education initiatives in SAC territories, where direct research is highly risky. Their findings, highlighting overlooked issues such as continuity of education, informed the Global Partnership for Education’s Systems Transformation Grant and contributed to the Joint Response Framework revision process. / Additionally, the Helpdesk conducted a complementary study to analysis of access to education across Myanmar’s parallel systems. While the World Bank’s recent Myanmar Subnational Phone Survey sought to provide a national picture of education provisions, their reported enrolment for ethnic education schools was substantially lower than what was generally assumed, raising concerns among educational stakeholders. The ERICC Helpdesk synthesis of primary data highlighted key insights on the number of children accessing ethnic education provision. The findings were validated by key donors, INGOs and NGOs supporting ethnic education and has prompted the World Bank to update its statistics, informing forthcoming discussions and programming of education stakeholders.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
In line with recommendations from the 2024 AR, the weighting for this indicator has been decreased to reflect that the scope of component 2 was reduced compared to the Business Case and no longer includes an innovation fund. Recognising the strong performance of the Helpdesk, targets for the next reporting period should be increasingly ambitious.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

Progress on recommendations from the previous AR:
During the reporting period, the Helpdesk has developed its communications strategy and workplan to maintain momentum and demand. The Helpdesk collaborated closely with the RPC and FCDO Advisers on component 1 research gaps which could be addressed through Helpdesk support, while maintaining proactive communication with FCDO Advisors to identify emerging evidence needs. In conversation with FCDO staff, the Helpdesk have facilitated nine dissemination events including with Local Education Groups and regional actors (for example, an education evidence dialogue series in the Sahel) to maximise the reach and utility of completed requests. Meanwhile non-confidential Helpdesk outputs have been published to ERICC’s INEE website.
Lessons learned this year and recommendations for the year ahead:
The communication and dissemination activities mentioned above have been successful and this approach could be more consistently delivered across all requests where appropriate. IRC should continue work closely with INEE to highlight relevant and non-sensitive Helpdesk reports which are of relevance to the wider sector and could feature in upcoming webinars, syntheses, e-newsletters and other multi-media promotions.

The Helpdesk should consider how it can strengthen efforts to ensure feedback is provided across a higher proportion of requests that are completed. Currently, the Helpdesk has a survey response rate of 70% following completed requests which is acceptable but could be improved.

FCDO should consider how this component might be expanded in the future to include additional countries given significant demand. Interviews with FCDO country advisors as part of this AR emphasised that the Helpdesk is highly valued across multiple countries for its quick turnaround, flexibility, and ability to provide targeted, context-specific support. The Helpdesk was recognised as providing rapid, high-quality evidence synthesis and advice, which has enabled FCDO and its partners, including government, to adapt to changing needs and make informed decisions. The Helpdesk should continue its exemplary work.

Output Title	ERICC evidence is made available in an equitable manner to a diverse range of EiE actors and stakeholders
Output number:		3			Output Score:	A
Impact weighting (%):		25%			Weighting revised since last AR?	No
Indicator(s)			Milestones for this review	Progress
3.1 # of translations of ERICC publications made available via the INEE website in languages other than English			15 (15 in this reporting period)	15 (15) - Met
3.2 # of INEE-produced resources amplifying ERICC evidence			6 (5 in this reporting period)	6 (5) - Met
3.3 # of downloads of ERICC evidence and resources from the INEE website			7500 (cumulative)	10,164 – Exceeded
3.4 # of views to the ERICC webpages on the INEE website per year			8000	8,889 - Met
3.5 # of INEE-hosted ERICC events conducted			7 (4 in this reporting period)	7 (4) – Met
3.6 # of INEE-hosted ERICC events with a majority of presenters/panelists from crisis-affected contexts			3 (2 in this reporting period)	2 (2) - Met
3.7 # of INEE-hosted ERICC events conducted in non-English languages			2 (2 in this reporting period)	2 (2) - Met
3.8 # of EiE evidence-related funding calls referencing ERICC evidence or related themes			2	1 – Not Met
3.9 # of strategic and technical documents produced by the BE2 EiE SIG informed by ERICC			1	0 – Not Met
3.10 # of country and regional plans or programs referencing ERICC evidence			2	3 - Exceeded

Briefly describe the output’s activities and provide supporting narrative for the score.
Overall, this output scores an A, reflecting that two indicators have been exceeded, six indicators have been met, and two indicators moderately did not meet expectations.

The availability of EiE evidence in languages other than English was identified as a key barrier to evidence uptake as part of INEE’s consultations with stakeholders during the 2024 inception phase and, therefore, translation has been prioritised for key resources. INEE have met the target for translations, with 8 studies translated into Arabic, French and Spanish (indicator 3.1). INEE also produced an evidence synthesis on ERICC research emerging from the MENA region, as well as a series of 5 blogs on topics such as girls’ education and research ethics to promote visibility of ERICC (indicator 3.2). Annex D lists INEE ERICC resources. ERICC does not have a standalone website and uses INEE’s website to publish its research – this decision was taken to ensure the research remains accessible following the closure of the programme, and recognising that INEE is already the ‘go to’ source for EiEPC evidence and guidance. This year, INEE have undertaken improvements to the website to enhance the ease of finding ERICC research and webpage views have continued to grow as the number of ERICC publications and dissemination efforts increase (indicator 3.4). The INEE network is an engaged audience[6], with the number of downloads of ERICC evidence exceeding targets (indicator 3.3).
[6] INEE has approximately 25,000 network members. Web analytics shows there are a notable number of active users (4000) and engaged sessions (4,536) whereby the web browsing session lasts longer than 10 seconds, has a key event (like downloading a resource), or has at least 2 pageviews or screenviews.

INEE has organised four events towards disseminating ERICC evidence. They hosted two virtual webinars and an in-person regional roundtable (indicator 3.5), ensuring Global South representation (indicator 3.6) and in languages for international audiences (indicator 3.7) (Table 2). In addition, INEE held a workshop for the RPC and Helpdesk to generate insights on emerging findings from across the research portfolio. This was sparked following insights from the FCDO’s Research on Improving Systems of Education (RISE) Programme evaluation which highlighted that greater impact would have been achieved had key messages been communicated earlier on and in dialogue with the sector. These efforts will support dissemination of synthesised evidence insights for target audiences in the next reporting period.

Table 2: INEE hosted ERICC event series
Date	Event	Speakers	Attendees
March 2025	Ethically Building an EiE Knowledge Base (webinar in English only)	ERICC – Centre for Lebanese Studies & Osman Consulting; University of Auckland	54
April 2025	What Works for Foundational Learning in Emergency Contexts (webinar in English, with live French translation)	ERICC – IRC; Luminos Fund; Youth impact; Imagine Worldwide.	119 (116 views on YouTube following the webinar)
September 2025	Building Recovery on Evidence: War, Displacement, and the MENA Region (in-person event in Arabic)	ERICC – Centre for Lebanese Studies, Osman Consulting & Queen Rania Foundation	28

INEE have regular engagements with key actors in the sector, enabling them to identify notable policy or programme windows. As a result, INEE was able to support the RPC’s engagement at ASPBAE Regional Workshop on Gender-Transformative Education (August 2025), UNESCO World Teachers Summit (August 2025), and UNGA80 (September 2025). INEE also highlighted opportunities to the RPC country research teams, providing introductions that resulted in ERICC evidence being included in country and regional plans or programmes in Jordan, Lebanon and Myanmar (indicator 3.10).

As part of broader efforts to improve the EiE ecosystem, INEE co-chairs the Building Evidence in Education (BE2) special interest group (SIG) on EiE with FCDO (indicators 3.8 and 3.9). This year, INEE drafted a mapping of research initiatives across BE2 members; however, due to challenges faced in getting active engagement including as a result of the closure of USAID, the mapping did not develop into a fully fleshed out strategic resource. INEE and FCDO are currently speaking with members of the BE2 EiE SIG to identify key activities that will be useful and relevant to members in a changed funding landscape. The overall intention of this workstream is for INEE to support alignment, coordination and organisation of EiE evidence, and, where applicable, use ERICC evidence and the conceptual framework to better organise the sector for stronger evidence uptake.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
Indicator targets were reviewed and revised to ensure they were achievable six months prior to this AR. This was done in the context of INEE undergoing its own major organisational restructure, following leadership and funding changes.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on recommendations from the previous AR:
INEE has deepened its regional engagement and started to strengthen regional EiE networks. This has been particularly notable in MENA, where INEE has enhanced evidence-based advocacy through a combination of activities: a tailored MENA evidence synthesis, translating key briefs into Arabic-language and hosting regional roundtable events. This has helped to address language access gaps and begun fostering a stronger regional debate around education evidence. In South/Southeast Asia, engagement is also growing, with regional stakeholders more acquainted with ERICC Myanmar and Bangladesh research as well as the conceptual frameworks, which have helped stakeholders to connect with the broader EiE agenda. In contrast, in West Africa, reduction in foreign aid have weakened INEE’s core network leading to limited engagement to date. A costed-workplan has been developed and approved by FCDO to target additional key policy windows in key regions over the next year.

Lessons learned this year and recommendations for the year ahead:
By December 2026, FCDO and INEE should review logframe targets to ensure these are appropriately stretching. In particular, the number of expected INEE-produced resources and events should be more ambitious. More curated synthesis products should be prioritised and commissioned by INEE. Bringing together a range of ERICC evidence and situating findings within a broader evidence base, such synthesis products should be used by INEE to tailor key findings and messages for specific audiences, from donors of EiEPC programmes to practitioners in (I)NGOs and as part of the Cluster. INEE should continue to work with all ERICC research partners to arrive at consolidated and coherent key messages from the ERICC evidence base, building on the informative initial discussions from the internal ERICC Evidence Uptake Workshop in July 2025. Similarly, INEE should maximise opportunities to host webinars on topics that are of broad interest to stakeholders in their network, such as financing, cost-effectiveness, and what works to strengthen literacy and numeracy outcomes.

By November 2025, following the ongoing bilateral conversations with members of the BE2 EiE SIG, INEE should identify two tangible outputs that can be collectively achieved over the upcoming reporting period to drive improvements in the EiE evidence culture. For example, activities might include a comprehensive mapping on research initiatives, developing shared advocacy messages based on common understanding of the evidence base, or a targeted workshop series could pursue stronger alignment between donors on how evidence needs to be reviewed, applied and collected as part of EiE project funding applications.

By July 2026, INEE should develop a clear handover plan for communications and uptake of ERICC evidence, ready to hand over this workstream to IRC and ODI from the end of September 2026. As their accountable grant comes to a close in the next reporting period, INEE should support a smooth transition for ERICC communications including through facilitating joint meetings with key stakeholders, sharing insights and lessons learned, and identifying future opportunities that could be leveraged by IRC and ODI.

Finally, INEE management should ensure adequate staff time and capacity is allocated to the programme, in order to improve the timeliness of agreed deliverables and reporting.

Output Title	Knowledge systems strengthened for research on education in conflict and protracted crisis
Output number:		4	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review (cumulative)	Progress
4.3 Number of research outputs, e.g., policy briefs, fact sheets, journal articles, books/chapters, evidence summaries, online blogs.	120 (28 in this reporting period)	203 (111) - Target exceeded / (25 translated research outputs; 49 journal articles; 8 books/book chapters; 2 edited special issues; 6 policy briefs; 34 evidence summary/fact sheet/research report; 31 blog posts/Op-eds; 18 podcasts; 19 Conference presentations; 11 reports / blogs / policy briefings.)
4.4 Number of activities undertaken to develop teaching capacity i.e., online seminars, workshops.	35 / (18 in this reporting period)	50 (33) – Target exceeded
4.5 Number of activities undertaken to develop research capacity i.e., research ethics workshops, academic writing workshops, summer schools.	75 / (18 in this reporting period)	85 (28) – Target exceeded
4.6 Number of academics and researchers participating in the training to develop research capacity.	450 / (56 in this reporting period)	575 (181) – Target exceeded
4.7 Number of Southern researchers and students supported. E.g., fellowships, bursaries, internships, placement opportunities and conference attendance funds.	120 / (19 in this reporting period)	116 (15) – Target not met
4.8 Aggregated number of institution-level govt./policy engagements between Research Chairs/Fellows and govt./policy officials.	35 (11 in this reporting period)	30 (6) – Target not met
4.9 Aggregated number of govt./policy officials engaged by projects.	130 / (30 in this reporting period)	128 (28) – Target not met

Briefly describe the output’s activities and provide supporting narrative for the score.

Overall, this output scores an A, reflecting that four indicators have been exceeded, while three indicators were moderately not met.

The British Academy appointed three Chairs to support strengthen knowledge systems in the Global South: Dr Justine Howard (BRAC University in Bangladesh, and Swansea University); Professor Kelsey Shanks (Koya University in Iraq, and Ulster University) and Professor Maha Shuayb (Centre for Lebanese Studies in Lebanon, and Cambridge University). All three Bilateral Research Chairs have been active throughout the review period, delivering a range of activities to build both institutional and individual capacity to produce rigorous research on EiEPC from these contexts. In July 2025, Dr Maha Shuayb’s Chair concluded, and she is now in her final reporting period. Professor Kelsey Shanks and Dr Justine Howard will complete their Chair awards in March 2026.

Through these partnerships, 83 research outputs have been produced in the reporting period, bring the cumulative number of publications to 203 (indicator 4.3). Studies published in this period include evidence from Lebanon, Türkiye and Australia on the determinants of refugee children’s language comprehension difficulties; analysis of narrative learning and minority representation in Iraqi early education textbooks; findings from a visual study on nurturing coexistence in Algerian refugee communities; and a book on transforming humanitarian partnerships in education. A full list of peer-reviewed publications is provided in Annex E.

Partner institutions have been supported throughout the review period with a total of 33 activities to strengthen teaching capacity (indicator 4.4). In Bangladesh, this has included the INSPIRE Seminar series at BRAC University with sessions on education and child development, storytelling as methodology and reviews of current research on poverty and children’s educational aspirations, as well as a review of modules for BRAC University’s Masters programme (Education). Meanwhile, in Iraq, a varied programme of teaching capacity related activities has included workshops on ‘Just Pedagogies for Reconciliation: Creating and Sustaining Change in Higher Education”, and development of co-developed Training of Trainers manuals on research skills, research ethics, curriculum design, translated into Kurdish and Arabic (see Box 7 for more details).

Box 7: Case Study: Strengthening Due Diligence and Financial Systems – Lessons from Iraq / Over a three-year period, the collaboration between the University of Ulster and Koya University, Iraq developed individual researchers capable of conducting rigorous, locally relevant education studies; embedded Koya faculty within regional and international networks, improving the academic environment, and established functional institutional systems so that the university could directly receive and manage research funding. / Institutional capacity exchange was the most complex and time-intensive element of the project. Initially, Koya University’s inability to meet British Academy due diligence standards revealed critical gaps in financial accountability, ethics oversight, and anti-fraud measures. In response, the project established six dedicated committees—spanning research ethics, financial procedures, legal affairs, health and safety, audit, and administration—to map and reform existing policies. These committees, comprising academic and administrative staff, collaboratively developed bilingual (Kurdish and English) policy drafts, drawing on Ulster University’s models but adapting them to Koya’s context. These policies were reviewed for legal clarity and institutional fit and then workshops were held to train staff on the finalised new policies. / Another major innovation was the creation of a dedicated sub-account for project funds, ensuring clear separation from the university’s core budget and enabling transparent financial reporting. The project introduced rigorous disbursement procedures, including multi-step authorisation, documentation requirements, and secure cash handling, tailored to the local cash-based economy. These reforms not only strengthened financial integrity but also built staff confidence in managing international research funds. While the transition to formal accountability systems created anxiety for some staff assuming signatory responsibilities due to corruption concerns, the ERICC-funded partnership fostered supportive dialogue, training and risk management. / Overall, ERICC funding has laid the foundation for Koya University’s financial independence, reducing reliance on Global North intermediaries and enabling future direct participation in international research partnerships. The project highlights that co-designed governance reforms are more likely to succeed when grounded in local realities and supported by ongoing mentorship over time and the importance of institutional trust and buy-in.

Alongside institutional strengthening, the research capacity of more than 181 individual scholars, primarily from the Global South, have been strengthened through research capacity building activities this year (indicator 4.6). The 28 events have ranged from summer schools and writing workshops, to academic networking and mentorship events (indicator 4.5). Capacity has been built on a range of topics, including research methodologies, research ethics in conflict affected settings and writing for policy impact. Fellowships, bursaries, internships, placement opportunities and conference attendance funds have benefited 15 early career researchers, moderately missing the indicator target of 19 (indicator 4.7).

Targets for policy and government engagement have also been narrowly missed (indicators 4.8 and 4.9) with Chairs instead prioritising efforts on producing research outputs and strengthening academic capacity. Nonetheless, the engagements that have occurred have been at senior level and provided strong opportunities to influence policy and practice. For example, in Iraq, round table events with the British Consulate in Erbil as well as the Ministry of Education in the Kurdistan Region of Iraq, offered Koya based scholars invaluable experience in sharing their ERICC research findings with policy orientated audiences. Additionally, a two-day flagship conference on Education, Peace and Politics conference in February 2025 was attended by over 100 people, including 10 policy makers, and representatives from institutions including the Ministry of Education (Kurdistan Region), the Ministry of Higher Education (Iraq), British Council, and UNESCO Iraq. Similarly, in Lebanon a close working relationship has been established with the newly appointed Minister of Education providing opportunities to disseminate findings.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The logframe targets were reviewed and agreed six months ahead of the AR to ensure they were stretching and maintained a significant level of ambition across all three British Academy Chairs. Overachievement across several indicators reflects that Chairs’ went above and beyond their agreed workplan, illustrating their passion and commitment to develop research capacity in their partner institutions.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

Recommendations from the previous AR
The British Academy developed a sustainability and exit plan to promote the training tools and resources developed by the three Chairs to a wider audience and capture key lessons learned on how to strengthen knowledge systems and build equitable partnerships in protracted crisis contexts. Implementing this plan, the Academy are making prioritised journal articles open access (currently 75% of journal publications are open access), developing case studies to share approaches that can be replicated across the research sector for stronger Global South academic leadership, and translating and publishing materials on topics such as writing for academic publications, grant writing, communicating research and others which are useful to a wider audience than the focal country partners.

Lessons learned this year and recommendations for the year ahead
Delivering the Chairs’ programme of research and capacity strengthening activity in regions of active conflict and crisis has required flexibility from both the Chairs, the British Academy and FCDO. As we have seen in the review period and beyond, active conflicts impact upon delivery plans. Flexibility is a necessity, and in particular the willingness of Chairs to work responsively is essential for the programme to succeed. While all Chairs are set to achieve their targets on time and within budget, future programmes working in similar contexts should consider how flexibility can be built into design and management from the outset.

In the final months of the accountable grant, British academy should work with the Chairs to effectively communicate research findings, especially with government and policy makers in the three countries. Activities might prioritise in-person presentations at the Local Education Group (LEG) or Education Sector Working Group (ESWG) meetings, and bilateral meetings or round table discussions with government stakeholders.

## D. VALUE FOR MONEY

The core VFM proposition in the ERICC business case rests on the ability of the programme to deliver insightful, actionable research and strengthened academic institutions that improve the effectiveness of FCDO’s education investments in crisis contexts. Key cost drivers include staffing fees related to academic time, data collection and analysis, and evidence uptake activities, as well as currency exchange and inflationary pressures in the countries of operation, notably in Lebanon, Nigeria, South Sudan and Myanmar.

Economy is rated good, with two partners keeping spending within budget variance guidance, competitive staff and consultant rates across all partners, and significant cost savings through discounts and pro-bono support.
Indicators	Judgement	Evidence
Overall % spending variance benchmarked against budget (All components)	Fair	All partners must keep variance below 10%. The Research Programme Consortium (RPC) underspent by 3% compared to the budget allocated. Underspend was due to rescheduling data collection activities in focal countries due to external context-related disruptions. / The Inter-agency Network for Education in Emergencies (INEE) underspent by 44.29% compared to the budget allocated. This is due to delay in timelines of completed activities. / The British Academy underspent by 4.73% compared to the budget allocated. This has been from budget lines on networking and uptake, and mentoring and cohort meetings.
Staff, Consultants and Fellow fee rates are competitive (All components)	Excellent	RPC staff and consultant fee rates are competitive. Benchmarked against the FCDO fee rate cap, these have an average discount rate of 66% for Programme Management and 50% for Technical Advisors, for their respective categories. / INEE staff and consultant fee rates are competitive. / On average, British Academy ERICC fellows cost just under £5,000 compared to £6,666 per month for British Academy Visiting Fellows.
Discounted or pro-bono rates / (Components 1 & 2)	Excellent	The RPC realised approximately £276,195 in cost savings resulting from discounts and pro-bono support provided from staff at IRC, UCL, ODI, and QRF to work on programme administration, contracts and compliance support, financial reviews and support, at no extra cost to FCDO. Additionally, ERICC is leveraging the £195,000 in external complementary funding for the coMOOC programme in Myanmar, a programme which is being researched by ERICC’s Myanmar team.

Efficiency is excellent, with the number of studies and Helpdesk requests completed exceeding targets, and all Helpdesk requests delivered within budget.

Indicators	Judgement	Evidence
% of studies completed on time, benchmarked against the timing of studies indicated in the costed workplan (Component 1)	Excellent	The RPC planned to complete 10 studies but finished 26, exceeding the on-time target. Effective monitoring, streamlined reviews, and clear division of responsibilities helped ensure timely completion.
% of requests made to the ERICC Helpdesk completed within the agreed upon time frame (Component 2)	Excellent	ERICC completed 20 Helpdesk requests, exceeding the target of 12, with 85% finished on time, well above the 75% benchmark. Delays were due to late feedback from requestors. Efficient processes and strong demand contributed to this performance.
Development of learning and training resources for Global South Academic Institutions (Component 4)	Good	British Academy Chairs have made progress to enhance efficiency and use of resources. For example, library training materials from the University of Mosul were translated into Kurdish and will be available online and at the University of Koya, benefiting Kurdish universities indefinitely. Additionally, new academic networks in Gaza and Syria were established to support early career researchers, providing valuable international engagement. All activities were delivered at a modest cost, with the Chair working pro-bono and a no-cost extension granted.

Effectiveness is good, with a fair acceptance rate for peer-reviewed publications, strong impact stories and good sustainability of partnerships.
Indicators	Judgement	Evidence
% of peer reviewed publications submitted from the ERICC research portfolio successfully published (Component 1)	Fair	The RPC submitted 33 journal articles for peer-reviewed publication. Of those that have received a response, 10 have been accepted for publication—achieving a 66.6% acceptance rate, below the 75% target.
# of high-quality impact stories demonstrating the ERICC Helpdesk's contribution to new practices, strategies or policy (Component 2)	Excellent	The RPC planned to complete 4 impact stories but finished 5, exceeding the target. Technical reviews, sectoral analysis and evidence syntheses supported new practices and policy recommendations in education for conflict-affected contexts.
# of policy documents, guidelines, and working papers referencing ERICC evidence (Component 3)	Fair	INEE had a target of 6 but only achieved 3. While many policy documents currently cite ERICC’s programme goals and its approach demonstrating awareness of the programme, INEE-led efforts to reflect specific research insights in non-focal country, regional and global policy documents is still building momentum. Engagement is being deepened with core stakeholders as the evidence base develops.
Sustainability of the bilateral institutional partnerships (Component 4)	Good	Institutions have built partnerships that will continue after the initial funding, allowing ongoing collaboration and future joint funding applications. The British Academy has a strong sustainability plan that makes research accessible, supports early career researchers, and builds lasting partnerships. The plan includes training, working with international organisations, and sharing resources.

Equity assessment is excellent, with high representation of female and Global South authors, strong inclusion-oriented data practices, and substantial support for female Global South scholars.
Indicators	Judgement	Evidence
% of relevant ERICC studies that use inclusion-oriented disaggregated data (Component 1)	Excellent	Of the 20 RPC studies where data disaggregation would have been relevant, 19 disaggregated by gender (95% - against a target of 100%), 13 were disaggregated by disability status (65% - against a target of 25%), and 19 were disaggregated by citizenship status (95% - against a target of 75%).
% of ERICC Helpdesk request respondents who are from the Global South and/or are female (Component 2)	Good	The RPC achieved 48% Global South Helpdesk respondents, slightly below the 50% target, but exceeded the female respondent target with 52%. The shortfall for Global South respondents was due to requester-driven selection, which is outside the RPC’s control.
% of INEE-hosted ERICC events conducted in non-English languages (Component 3)	Good	INEE conducted 2 (100%) events in non-English languages, a foundational learning webinar translated in French and an Arabic language dissemination event.
Support to Female Global South scholars (Component 4)	Excellent	Overall, 61% of Global South researchers supported by the British Academy are women (against a target of 50%).

E: RISK

Overview of risk management
The overall risk rating of the programme is Major, driven by strategy and context risks as well as financial risks. There is no change to this risk rating from the 2024 ERICC AR. The FCDO programme team actively monitors risks and mitigating measures through monthly progress review meetings with all components and quarterly reports, as well as a quarterly internal risk discussion between the SRO, PRO and Programme Manager. Category level risks are analysed and explained below, in reference to the most up to date risk appetites.

Strategy and Context – With the programme operating in highly unstable environments, this is a key risk labelled major. Examples include governance shifts and security concerns in Syria, political and economic instability in Lebanon, temporary disruption of research in Jordan due to regional conflict, and increased security risks in Nigeria, Iraq, and South Sudan. Mitigation strategies developed at the outset of the programme as well as frequent ongoing formal and informal communication and coordination have allowed the RPC to maintain flexibility and continue delivery. The RPC should continue to monitor conflict related risks throughout the life of the programme, including maintaining its proactive communications with FCDO on risks and mitigation strategies. More broadly, the global aid architecture has been impacted by USAID cuts which resulted in having to cancel an ERICC RCT in Nigeria and disrupted INEE and IRC’s operations. The UK government’s decision to move to 0.3% ODA is likely to further impact funding to the EiEPC sector, although has not resulted in any reductions to ERICC spend or ambition. The residual risk is major.

Policy & Programme Delivery – There is a moderate risk of disruption to research activities from natural disasters and extreme weather events, alongside conflict-related challenges. For example, data collection in South Sudan and Myanmar was affected by conflict and monsoon seasons, requiring adaptive planning. All teams maintain up-to-date security protocols and flexible plans. Delivery risks are generally well managed, but delays may still occur, particularly in areas prone to instability. The residual risk is moderate.

Safeguarding - Safeguarding remains a notable risk due to the vulnerability of populations in fragile and conflict-affected settings (FCAS) and power imbalances in research settings, particularly regarding sexual exploitation, abuse and harassment (SEAH). Mitigation includes regular safeguarding discussions, policy reviews, and robust reporting mechanisms, with ongoing input from safeguarding specialists. No incidents were reported this period, and safeguarding training was refreshed for staff and enumerators. A meeting with the FCDO safeguarding lead and the safeguarding leads at IRC ensured policy and practices meet expectations. Data protection risks, such as potential leaks affecting research participants, are actively monitored and follow the ERICC Consortium’s data management policy. Residual safeguarding risk is moderate, while data protection risk remains minor.
Financial and Fiduciary - Moderate risks include ensuring partners maintain sufficient controls to prevent misuse of funds and uphold value for money. Due diligence assessments for IRC, INEE, and the British Academy are up to date. A fraud incident at IRC was investigated and reported to FCDO via the reporting concerns line, which had minimal impact on funds and was managed effectively. Onboarding new research partners in Myanmar required enhanced due diligence and risk mitigation to address potential financial and ethical risks. High inflation and exchange rate fluctuations, particularly in Nigeria, Lebanon, Iraq, and South Sudan, present ongoing challenges. Approved exchange rate methods are used where standard rates are unavailable. Risks are mitigated through accurate quarterly financial forecasts, use of GBP/USD pricing, and management of funds in foreign exchange accounts. Regular meetings and reporting with FCDO ensure timely oversight of any changes. The residual value of this risk is moderate.
People - A potential risk in this category is delays in recruitment and high turnover of essential staff leading which could lead to disruption of programme delivery. Staff turnover was minimal, though the Asia Regional Research Director position was vacant for an extended period before being filled this reporting period. The safety and wellbeing of staff has remained a priority, with contingency plans and flexible working arrangements in place in high-risk areas. Residual people risk is considered low, but ongoing monitoring is required to ensure staff welfare in volatile settings.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The FCDO programme team holds monthly meetings with IRC and INEE, and quarterly meetings with the British Academy, to monitor programme progress, oversee operational activities such as contracting, finance, and risk management, address any arising issues, and provide technical and strategic guidance for the programme.

International Rescue Committee: IRC has a commercial contract with FCDO from December 2021 to December 2027, valued at £19.5m. IRC’s spend to date is £11,821,205 (60.62% of the total value of the contract) with a forecast variance of -4.03% for the annual review period. IRC performance is assessed through four Key Performance Indicators (KPIs) (Annex F), which are reported on a quarterly basis, as well as the number of deliverables reviewed each quarter, linked to a payment by results modality. IRC has consistently met these KPIs and reports efficiently on them, demonstrating strong performance and accountability throughout the reporting periods.

IRC continues to provide FCDO with accurate and timely monthly financial forecasts, compiled from downstream partner projections and spend analysis. For Q1 and Q2 of FY25/26, payment frequency was temporarily changed from quarterly to monthly to support IRC following USAID funding cuts. IRC have been updating the proforma to reflect changes in operational plans and are preparing for a commercial contract amendment to include the new research director in Bangladesh and quantitative research lead. Financial and narrative reporting remain consistent and detailed, providing FCDO with clear oversight of deliverables and contextual information. IRC maintains up-to-date risk and asset registers, as well as a delivery chain map, all submitted quarterly. As part of risk management, IRC conducts safeguarding and fraud/ethical reporting training.
As contract lead, IRC has provided strong support to downstream delivery partners, with a particular focus on improving financial management capacity. Before finalising contracts, IRC assesses each partner’s ability to deliver the ERICC commercial contract, identifying any gaps in financial systems through a thorough due diligence process. Where needed, special conditions are added to sub-contracts to help partners strengthen their financial management during implementation. For example, one local contractor addressed significant financial management challenges through a targeted six-month action plan developed with IRC, which included enhanced oversight, additional resources, regular meetings, and focused training. This collaborative approach has led to ongoing improvements in financial systems and reporting, ensuring more accurate and efficient financial management across the programme and supporting compliance and effective delivery.
As part of this AR, the programme team held a listening session with downstream partners under IRC, where partners highlighted that they valued regular and supportive communication from the contract lead as well as the co-creation process of the research agenda. Feedback highlighted two key areas for improvement, including the need for more streamlined financial and reporting processes, and a more pragmatic and empowering peer-review process for academic journal submissions. FCDO has provided this feedback to IRC and requested the implementation of operational improvements, including more face-to-face engagement and simplified reporting for local partners.
Inter-agency Network for Education in Emergencies: INEE holds an Accountable Grant agreement with FCDO from February 2024 to September 2026, totalling £800,000. To date, expenditure stands at £408,949, representing 51.11% of the total grant value. INEE’s forecast-to-spend variance rate is -39.65%, as INEE has not completed certain activities within the planned quarterly timelines. FCDO is closely monitoring their costed workplan, with an emphasis on prioritising strategic activities to ensure timeliness and value for money. INEE’s programme management could be strengthened, as there have also been delays in invoicing and reporting, largely due to reduced capacity following an organisational restructure and USAID funding cuts. As no assets have been acquired since the commencement of the agreement, an asset register is not necessary.
British Academy: The £3.88m Accountable Grant, April 2020 to March 2026, has a spend to date of £3,519,926 (90.72% of the total value). The British Academy provide quarterly forecasts, invoices and succinct narrative reports. Their forecast to spend variance rate over the annual review period is 10.76%, as a result of budget lines being reallocated to later in the financial year. Quarterly narrative reporting is succinct, covering a comprehensive narrative of activities, VFM indicators and risk management. The Due Diligence Assessment was updated and completed this year. Financial management remains strong, with no significant risks identified. Safeguarding policies require further review as there is no current standalone safeguarding document, although information on safeguarding is included in their internal regulations and regularly explained to all staff. The British Academy are currently reviewing their safeguarding policy and will share updates when completed. They will also share an updated M&E framework once this has been updated. The British Academy also submitted a costed delivery chain map as per last year's AR recommendation.

G: MONITORING, EVIDENCE AND LEARNING

The Annual Review is FCDO’s primary mechanism to measure progress against Logframe indicators over the previous 12 months. For this annual review extensive listening sessions and interviews were conducted with downstream partners and FCDO education advisors to inform findings and recommendations. In addition, partners submit quarterly progress updates, and FCDO programme staff meet regularly with partners, wider delivery partners and stakeholders to discuss progress. Furthermore, the programme team conduct regular monitoring of programme implementation. For example, this year, the PRO attended key academic conferences to understand how ERICC studies were received by the academic community and maintained regular communication with FCDO staff in focal countries to understand local experiences of the programme. FCDO also hold bi-annual cross-component coordination meetings, facilitating dialogue and lesson learning between ERICC partners. Six months ahead of the AR, FCDO programme team worked with all partners to review logframe indicators and targets to ensure they were stretching but realistic. FCDO plans to conduct an external endline evaluation of the programme, to understand what has been successful and sustainable, and why, to inform future FCDO research programming.

ERICC RPC: A culture of learning is proactively fostered by the RPC. Country research teams and the global research leads meet bi-weekly via different working groups to advance research and receive critical and constructive feedback. These groups also function as de-facto capacity building opportunities, as well as opportunities for knowledge exchange between Global South and Global North scholars (and vice versa) on methods, approaches and cultural relevance of research. The RPC meets annually for a dedicated, externally facilitated learning reflection session which helps to highlight bottlenecks and strengthen research strategies. The RPC continues to leverage the Monitoring and Reporting Strategy to conduct MEL activities, and the MEL Working Group meet monthly to discuss indicator progress and reporting requirements.

INEE: INEE have developed an integrated monitoring and evaluation framework as part of their costed workplan, with key deliverables clearly identified to support strategic planning and effective budgeting. FCDO has held reflection sessions with INEE to assess progress and set out expectations during the reporting period and continue to monitor these deliverables through regular monthly meetings to ensure targets are met and challenges are addressed promptly.

British Academy: The British Academy continues to regularly engage with the Bilateral Research Chairs, with two regular meetings per quarter. The British Academy has a Monitoring and Evaluation team to increase internal MEL of activities and programmes. This year, British Academy facilitated lesson learning among Chairs to identify resource sharing across the regions, develop a sustainability and exit plan, and build out case studies of lessons learned throughout the Chairs, to inform future research partnerships.

Date of last narrative financial report	IRC: 31/10/25 / INEE: 31/10/25 British Academy: 25/11/25	Date of last audited annual statement	IRC: 30/09/24 / INEE: 30/09/24 / British Academy: 31/03/25

List of acronyms
BA	British Academy
BE2	Building Evidence in Education
CAC	Country Advisory Committee(s)
CLS	Centre for Lebanese Studies
CRT	Country Research Team(s)
ECW	Education Cannot Wait
EiE	Education in Emergencies
EiEPC	Education in Emergencies and Protracted Crisis
ERICC	Education Research in Conflict and Protracted Crisis
FCAS	Fragile and Conflict-affected States
FCDO	Foreign, Commonwealth and Development Office
GRA	Global Research Agenda
INEE	Inter-agency Network for Education in Emergencies
IRC	International Rescue Committee
KPI	Key Performance Indicator
MEL	Monitoring, Evaluation and Learning
MCS	Multi-Country Studies
ODA	Overseas Development Assistance
ODI	Overseas Development Institute
PbR	Payment by Results
QRF	Queen Rania Foundation
RPC	Research Programme Consortium
SEAH	Sexual Exploitation, Abuse and Harassment
SIG	Special Interest Group
TOC	Theory of Change
WFP	World Food Programme
UCL	University College London
UNESCO	United Nations Educational, Scientific and Cultural Organization
UNHCR	United Nations High Commissioner for Refugees
UNICEF	United Nations Children’s Fund

Annex A: Theory of Change

Annex B: ERICC RPC publications

Global studies:
- ERICC Conceptual Framework 2.0
- Sequencing Fit-for-Purpose Research for Greater Impact: The Education Research in Conflict and Crisis (ERICC) Methods Framework
- Meta-analysis: Foundational learning in Conflict and Crisis settings
- Meta-Analysis Socio-Emotional Learning: Impact and Cost-Effectiveness of education interventions on SEL in Conflict and Protracted Crisis Settings
- What Works to Improve Early Childhood Development Outcomes in Conflict and Crisis Affected Settings? A Review of Rigorous Impact Evaluations
- What works to support Socio-Emotional Learning
- Expanded Roles, Limited Support: A Critical Review of Teacher Professional Development and Professionalisation in Conflict and Protracted Crisis Settings
- A Crisis Within a Crisis: A Scoping Review of Teacher Management in Crisis Contexts
- Insights from a Rigorous Evidence Review: Approaches to Girls' Education and Gender Equality in Conflict- and Crisis-Affected Contexts
- What evidence-based interventions contribute to violence reduction and improved safety in schools in conflict and crisis settings?
- Supporting Children’s Mental Health and Wellbeing in and through Education in Conflict and Protracted Crises: A Rigorous Evidence Review
- Bridging gaps in education for marginalised learners in conflict and protracted crises: A rigorous review of evidence
- Expanding refugee access to national education systems: An intersectional analysis of the evidence
- Continuity of Education in Conflict- and Crisis-Affected Settings: Findings from an Extensive Literature Review
- Educational reforms for peace with justice in conflict-affected societies

Country studies:
- Co-creating an agenda for education research in conflict-affected contexts of Myanmar
- Evaluating Holistic Learning Outcomes in the Myanmar Curriculum in Cox’s Bazar: Opportunities, Challenges, and Implications for Educational Quality
- Religious (Madrasa) education insights and dynamics in Rohingya camps of Cox's Bazar: an analysis of access, quality, and coherence
- Exploring Trends and Factors Influencing Learning Outcomes in Madrasa Education: Evidence from Cox’s Bazar, Bangladesh
- Understanding Community Responses to Religious Education in Conflict settings (Madrasa)
- Priorities, programming and the political economy of education in ‘post-insurgency’ North-east Nigeria
- The Provision of Compulsory, Free Universal Basic Education in the Aftermath of the Boko Haram Insurgency: the case of Adamawa State
- Nigeria’s Universal Basic Education Act in Contexts of Conflict and Protracted Crisis
- The De-weaponisation of Education in Syria: Towards a Peaceful Future
- The hybrid governance of education in Lebanon: A frontstage/backstage analysis
- The Experience of Education Amidst War, Displacement, and Crises: An Intersectional Lens for a More Inclusive Education in Lebanon
- A critical methodology for education monitoring in Lebanon
- As Above, So Below: Exploring Barriers to Education amidst South Sudan’s Polycrisis
- Expanding Access to Education in Crisis Contexts: Evidence from South Sudan’s Pastoralist Education Programme
- Community resilience in ensuring learning during the protracted crisis in Adamawa State, Nigeria
- Education Policymaking from the bottom up: Evidence from participatory action research in a conflict-affected area of northern Nigeria (UBE II)

Annex C: ERICC Helpdesk requests

Completed Requests (October 2024 – September 2025)
1. Global – Role of education in global security and migration
2. Global – Guidance notes on EiE in disaster management
3. Global – Recommended tools for responses to Vanuatu Earthquake
4. Global – Capacity building workshop on Technical Assistance for Systems Strengthening
5. Jordan – Aid Efficiency for Refugee Integration
6. MENA – Lessons on curricular reform
7. MENA Region – Syrian Refugee Education and Implications for Returnees
8. Myanmar – Status of education provisions
9. Myanmar – Access to parallel education systems
10. Nigeria – Security and Islamic Education
11. OPT – Curriculum Review
12. Sahel Region – Koranic Education Integration
13. Sahel Region – Mother Tongue Language in Education
14. Sahel Region – Nomadic Pastoralists Education
15. South Sudan – Evidence synthesis on disability inclusion
16. Sudan – Technical assistance for the Transitional Education Programme (TEP)
17. Sudan – Impact of conflict on education landscape
18. Sudan – Administration of examinations
19. Syria – Rapid Political Economy Analysis
20. Syria – Peace Education

Ongoing Requests
- Bangladesh – Impact of school closures due to climate change and political unrest
- Myanmar – Data Systems mapping
- MENA Region – Innovative financing

Annex D: INEE produced ERICC Resources

Including Evidence Outputs made available in languages other than English

ERICC evidence briefs:
Expanding Refugee Access to National Education Systems: translated to Arabic, French, and Spanish.
Teacher Management and Crisis and Conflict Settings: translated to Arabic, French, and Spanish.
Promising Practices to Support Girls’ Education in Conflict and Crisis Settings: translated to Arabic and French.
ERICC Conceptual Framework: Systematic, holistic approaches to Education Research, Policy and Practice (revised 2024): translated to Arabic and French.
Understanding the Dimensions of Conflict and Crisis: translated to Arabic and French.
Strengthening the delivery of Universal Basic Education (UBE) in conflict-affected areas of Adamawa State, Nigeria: translated to French.
Implementing Nigeria’s Universal Basic Education Act: The Case of Adamawa State: translated to French.
Shaping the Future of Education in Emergencies in MENA – Insights from ERICC Research: translated to Arabic.

ERICC blogs:
Strengthening Ethical Practices in Education in Emergencies (EiE) Research: translated into Arabic, French, Portuguese, Spanish.
The Researcher’s Role in Strengthening Ethical Research Practice in EiE: translated into Arabic, French, Portuguese, Spanish.
The Funder’s Role in Strengthening Ethical Research Practice in EiE: translated into Arabic, French, Portuguese, Spanish.
What Works for Girls’ Education in Crisis Settings? Emerging Evidence from ERICC.

Annex E: British Academy peer-reviewed academic publications

Lebanon:
Journal articles:
1. Hammoud, M., Shuayb, M., & Crul, M. (2022). Determinants of Refugee Children’s Social Integration: Evidence from Lebanon, Turkey, and Australia. Social Sciences, 11, Article 12. https://doi.org/10.3390/socsci11120563
2. Abu Moghli, M., & Shuayb, M. (2022). Reconceptualizing and reimagining citizenship education in light of youth-led global movements. In Citizenship Teaching &amp; Learning (Vol. 17, Issue 3, pp. 333–340). Intellect. https://doi.org/10.1386/ctl_00096_2
3. Shuayb, M. and Al-Sarraf, D, (2022) The portrayal of women in history curricula and textbooks in Lebanon: A history of systematic exclusion. Citizenship Teaching & Learning, Volume 17, Issue 3, Sep 2022, p. 437 – 453. https://doi.org/10.1386/ctl_00102_1
4. Abu Moghli, M., & Shuayb, M. (2022). Equitable Partnerships for Education: A Myth or a Panacea. Recherches sociologiques etanthropologiques, (53-2), 177-201. https://journals.openedition.org/rsa/5766
5. Mai Abu Moghli (2023) Research ethics in the occupied West Bank and the Gaza Strip: between institutionalisation and the power of praxis, Globalisation, Societies and Education. https://doi.org/10.1080/14767724.2023.2165479
6. Shuayb, M and Brun, C. (2023) Twenty years of the Inter-agency Network for Education in Emergencies: towards a new ontology and epistemology, Globalisation, Societies and Education. https://doi.org/10.1080/14767724.2023.2191936
7. Itab Shuayb, & Doueiry, S. (2023). Impact of COVID-19 on the education and healthcare services of persons with disabilities in Lebanon. Frontiers in Public Health, 11. https://www.frontiersin.org/journals/public-health/articles/10.3389/fpubh.2023.1111972/full
8. Diab, J.L.(2023). From Exclusionary to Participatory Feminist Peacebuilding in Lebanon: Examining the Roles of Refugees, Migrants and Women in All Their Diversity. Al-Raida, 47(1), 116-123. https://alraidajournal.lau.edu.lb/images/From%20Exclusionary%20to%20Participatory%20Feminist%20Peacebuilding%20in%20Lebanon%20Examining%20the%20Roles%20of%20Refugees%2C%20Migrants%20and%20Women%20in%20All%20Their%20Diversity.pdf
9. Diab, J. L. et al (2023), The Gender Dimensions of Sexual Violence against Migrant Domestic Workers in post-2019 Lebanon, Frontiers in Sociology. https://doi.org/10.3389/fsoc.2022.1091957
10. Diab, J. L. (2023), Safe Return and Voluntary Repatriation for Syrian Refugees from Lebanon: What Needs to Happen Next?, United Nations University Centre for Policy Research. https://bit.ly/3lCHp0j
11. Diab, J. L. & Scissa, C. (2023), Gender, Migration and Environment in the MENA: Vulnerabilities, Frameworks and Ways Forward, Journal of Migration Affairs, Vol. V(1-2): 11-20, https://migrationaffairs.com/gender-migration-and-environment-in-the-mena-vulnerabilities-frameworks-and-ways-forward/
12. Fouad, F. M., Hashoush, M., Diab, J. L. et al (2023), Perceived Facilitators and Barriers to the Provision of Sexual and Reproductive Health Services in Response to the Syrian Refugee Crisis in Lebanon, Women’s Health 19, Retrieve at: https://doi.org/10.1177/17455057231171486
13. Diab, J. L. & Jouhari, I. (2023), Conflict, Crisis and Migration: Maritime Irregular Migration from Lebanon Since, Friedrich Naumann Foundation for Freedom, Retrieve at: https://www.freiheit.org/publikation/conflict-crisis-and-migration
14. El-Zakka Y. & Diab J. L. (2023), Youth development and spatial configurations: socio-spatial inequalities in Palestinian refugee camps in Lebanon, Frontiers in Sociology 8:1192511, doi: 10.3389/fsoc.2023.1192511
15. Diab, J. L., Asfour, O., Abbara, A. (2023). COVID-19 in the Eastern Mediterranean Region: A Driver of Inequality for Refugees and Vulnerable Groups. In: Kraemer, A., Medzech, M. (eds) Covid-19 pandisziplinär und international. Medizin, Kultur, Gesellschaft. Springer VS, Wiesbaden. https://doi.org/10.1007/978-3-658-40525-0_17
16. Hammoud, M (2024). Pathways to Integration and Language Acquisition: A Comparative Analysis of Refugee Children's Social Integration and Foreign Language Difficulty in Lebanon and Australia.” The paper was submitted to the Journal of international migration and integration. https://link.springer.com/article/10.1007/s12134-024-01201-5
17. Nidal Sleiman: published an article in Arabic in Manhajiyat on October 5, 2023. The English article: Al Haj Sleiman, N. (2024). Leadership as a socially and culturally informed praxis: The question of internationalisation in international school leadership. Perspectiva Educacional, 63(1). https://dx.doi.org/10.4151/07189729-Vol.63-Iss.1-Art.1519
18. Diab J. L. (2024), Rapid Gender Analysis: Gender, Conflict and Internal Displacement in and from South Lebanon, CARE International and UN Women, https://lnkd.in/dH6sYAfC
19. Kaloti, R., Diab, J. L. Alkhalil, M. & Abbara, A. (2024), Compounding challenges for Syrian refugees in Türkiye in the wake of the earthquake, The Lancet Global Health, https://www.thelancet.com/journals/langlo/article/PIIS2214-109X(24)00044-5/fulltext
20. Diab J. L. , Samneh B., Masoud D. and Cravero K. (2024), Gender identity as a barrier to accessing adequate and inclusive healthcare for Syrian refugees in Lebanon’s Northern regions, Front. Hum. Dyn.5:1205786. doi: 10.3389/fhumd.2023.1205786
21. Diab, J. L. (2024). Refugees and Human Rights Law During the Trump Administration. In: Aldama, A., Ordaz, J. (eds) Resistance and Abolition in the Borderlands: Confronting Trump’s Reign of Terror. The University of Arizona Press. https://lnkd.in/duTQDS9D
22. Hammoud, M., Al Samhoury, O., Shuayb, M. et al. Determinants of refugee children’s language comprehension difficulties: Evidence from Lebanon, Türkiye and Australia. Int Rev Educ 71, 209–233 (2025). https://doi.org/10.1007/s11159-024-10115-4
23. Câmara, J.N. Towards critical, anti-colonial and anti-racist education in national and global contexts. Int Rev Educ 71, 255–279 (2025). https://doi.org/10.1007/s11159-024-10110-9
24. Câmara, J. N. (2025). Relational ethics of care in research with young people: reflections from a study with young refugees and their families. Cambridge Journal of Education, 55(2), 159–188. https://doi.org/10.1080/0305764X.2025.2469849
25. Published the following article: Shah, R., Menashy, F., Chinnery, J., Bird, L., Bender, L. C., Ali, A., Shuayb,M. (2024). Reimagining education in emergencies: a conversation between practitioners and scholars. Compare: A Journal of Comparative and International Education, 1–19. https://www.eenet.org.uk/resources/docs/Reimagining%20education%20in%20emergencies%20a%20conversation%20between%20practitioners%20and%20scholars.pdf
26. Integration or exclusion: Has the humanitarian education response for the Syrian crisis in Lebanon delivered for refugees and nationals? Authors: Shuayb – Brun – Hammoud – Nehme
27. Hammoud, M., Al Samhoury, O., Shuayb, M. et al. Determinants of refugee children’s language comprehension difficulties: Evidence from Lebanon, Türkiye and Australia. Int Rev Educ 71, 209–233 (2025). https://doi.org/10.1007/s11159-024-10115-4
28. Camara, J. N. (2024). Young refugees: access and learning inequalities in England’s education system. EAL Journal, 23, 51-53. https://naldic.org.uk/publications/eal-journal/issue-23
29. Diab, J. L. (2025). Bordering belonging: A qualitative exploration of educational integration for Syrian refugees in Lebanon across perceived value and impact. Education, Citizenship and Social Justice, 0(0). https://doi.org/10.1177/17461979251356887
30. Shuayb, M., A political economy analyses of bureaucracy in the education response for Syrian refugees in Lebanon, editors Nina Gren, Dalia Abdelhad, Martin Joormann Refuge, Open Access
31. Shuayb, M., & Hammoud, M. (2025). Determinants of Refugee Children’s Self-Perceived Educational Performance: A Comparative Study of Lebanon, Turkey, and Australia. Social Sciences, 14(7), 440. https://doi.org/10.3390/socsci14070440
32. Abdo Ahmad, I; Fakih, A; & Hammoud. M(2023). Parents' perceptions of their children's mental health during COVID-19: Evidence from Canada, Social Science & Medicine. https://doi.org/10.1016/j.socscimed.2023.116298
33. Fakih, A., Hammoud, M., & Sayour, N. (2023). Youth voting and institutional change in the post-Arab Spring MENA region. Economic and Political Studies, 12(3), 318–344. https://doi.org/10.1080/20954816.2023.2226827
Book Chapters:
1. Mohammad Zreik: Evaluating Lebanon's Economic Policy Response to the Syrian Refugee Crisis: Challenges and Alternatives. Submission Details: Accepted for publication in the book "Media Representation of Migrants and Refugees" published by IGI Global. Current Status: Will appear soon online. - https://www.igi-global.com/chapter/evaluating-lebanons-economic-policy-response-to-the-syrian-refugee-crisis/349470
2. Shuayb, M., Crul, M., & Lelie, F. (2022). The consequences of emergency and humanitarian relief education for Syrian refugee children in Turkey and Lebanon. In M. Suarez-Oroszco & M. Sánchez Sorondo (Eds.). Education: The Global Impact. New York: Columbia University Press. (In lieu of an article) - The consequences of education in emergency for Syrian refugee children in Turkey and Lebanon - Vrije Universiteit Amsterdam
3. Book Chapter: Education as an Emergency Response: Time for Radical Change, In Education, Migration and Development by Dr. Mai Abu Moghli. https://www.researchgate.net/publication/363122728_Education_as_an_Emergency_Response_Time_for_Radical_Change
4. Shah, R., Menashy, F., Chinnery, J., Bird, L., Bender, L. C., Ali, A., Shuayb, M. (2024). Reimagining education in emergencies: a conversation between practitioners and scholars. Compare: A Journal of Comparative and International Education, 1–19. https://doi.org/10.1080/03057925.2024.2395864
Books:
1. Shuayb, M. (Ed.). (2025). Education in times of war: Lebanon's crisis response. Centre for Lebanese Studies and Manhajiyat https://lebanesestudies.com/wp-content/uploads/2025/06/E_Education-in-times-of-war_by-pages.pdf
2. Zakaria, Z, Menashy, F., Shuayb, M. Transforming Humanitarian Partnership, Bristol University Press. https://bristoluniversitypress.co.uk/transforming-humanitarian-partnerships
3. Elias, A. (2024). إشكالية تعليم التاريخ في لبنان [The Problematic of Teaching History in Lebanon]. Lebanese Association for History. Retrieved from https://lahlebanon.org/ar/teaching-history-in-lebanon-crises-and-solutions/
Edited Special Issues:
1. Shuayb, M., Moghli, M.A. & Câmara, J.N. Lifelong learning in emergencies: From saviourism to solidarity. Int Rev Educ 71, 195–207 (2025). https://doi-org.ezp.lib.cam.ac.uk/10.1007/s11159-025-10165-2
2. Shuayb, M. and Abu Moghli, M. (2022) Reconceptualising and Reimagining Citizenship Education in light of youth led global movements, Citizenship Teaching & Learning. Volume 17, Issue 3, Sep 2022, p. 333 – 340 DOI: https://doi.org/10.1386/ctl_00096_2

Iraq
Journal Articles:
1. Shanks, K., & Paulson, J. (2022). Ethical research landscapes in fragile and conflict-affected contexts: understanding the challenges. Research Ethics, 18(3), 169-192. https://doi.org/10.1177/17470161221094134 (https://educationpeaceandpolitics.org/ethical-research-landscapes-in-fragile-and-conflict-affected-contexts-understanding-the-challenges/)
2. Saeed, K.M., Ahmed, A.S., Rahman, Z.M. et al. How social support predicts academic achievement among secondary students with special needs: the mediating role of self-esteem. Middle East Curr Psychiatry 30, 46 (2023). https://doi.org/10.1186/s43045-023-00316-2 (Open Access)
3. Wshyar, M. (2025). Stories for Peace and Coexistence: Analyzing Narrative Learning and Minority Representation in Early Education Textbooks. The Social Studies, 1–10. https://doi.org/10.1080/00377996.2025.2503267
4. This Special Issue has 8 papers included within it: Saeed, K.M., Ahmed, A.S., Rahman, Z.M. et al. How social support predicts academic achievement among secondary students with special needs: the mediating role of self-esteem. Middle East Curr Psychiatry 30, 46 (2023). https://doi.org/10.1186/s43045-023-00316-2

Evidence summary/factsheet/research articles/reports:
Shanks publication (1 October 2023) Bringing peacebuilding to nexus thinking in education in emergencies: promising practices to overcome injustices. https://inee.org/resources/bringing-peacebuilding-nexus-thinking-education-emergencies-promising-practices-overcome

Bangladesh
Journal articles
1. Boukhari, S. and Howard, J. (2025) Nurturing coexistence: Algerian children’s visual narratives on refugee communities from educational and social psychology perspectives. In C. Pracana & M. Wang (Eds.), Proceedings of the International Psychological Applications Conference and Trends (InPACT 2025) (pp.239–243). Lisbon, Portugal: in Science Press. ISBN 978-989-35728-4-9.
2. Boukhari, S. (2025) The Relational Refugee Child: Trauma-Informed and Culturally Responsive Approaches to Educational Inclusion. Education Sciences, 15(6), 649. https://doi.org/10.3390/educsci15060649

ANNEX F

KPI 1	Total # of research products and % of planned research products produced by ERICC researchers and affiliates on ERICC themes, questions, or foci
KPI 2	% of selected requests for technical advice satisfactorily delivered in ERICC focal countries
KPI 3	Timely and accurate quarterly reporting and forecasting (variance within 10%)
KPI 4	Proportion of ERICC research products on which global south researchers are the lead author