## Annual Review Template

Title: Scaling Up Family Planning in Tanzania Programme
Programme Value £ (full life): 65,146,845		Review date: May 2025
Programme Code : 300415	AMP start date: 14/10/2017	AMP end date: / 31/12/2026

Summary of Programme Performance
Year	2018	2019	2020	2021	2022	2023	2024
Overall Output Score	A	B	B	A	A	A	A+
Risk Rating	Major	Major	Major	Major	Major	Major	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/20372373.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0006749.xlsx

# Acronyms
COCs	Combine Oral Contraceptives
CHE	Comprehensive Health Eduction
CHW	Community Health Worker
DHMT	District Health Management Teams
CHMT	Council Health Management Teams
CCHP	Council Comprehensive Health Plans
CPD	Continuous Professional Development
DHIS	District Health Information System
DHS	Demographic and Health Survey
EH	Engender Health
EN	Embedded Nurses
FCDO	Foreign, Commonwealth and Development Office
FGD	Focus group discussion
FP	Family planning
GoURT	Government of United Republic of Tanzania
IUCD	Intrauterine contraceptive device
ICRH-K	International Centre for Reproductive Health – Kenya
IP	Implementing Partner
IRC	International Rescue Committee
KII	Key informant interview
LARC	Long-Acting Reversible Contraceptive
mCPR	Modern contraceptive prevalence rate
MSI	MSI Reproductive Choices
MoH	Ministry of Health
MoE	Ministry of Education
MCDGC	Ministry of Community Development, Gender and Children
NBS	National Bureau of Statistics
PORALG	President’s Office for Regional and Local Government
PwD	People with Disability
PPFP	Post-Partum Family Planning
UNFPA	United Nations Family Planning Fund

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]

Scaling up Family Planning (SuFP) in Tanzania is a nine-year (2017 - 2026) comprehensive sexual and reproductive health programme that enhances women and girls’ choice and agency to lead healthy sex lives. The programme integrates family planning, treatment of Gender Based Violence (GBV) and life-threatening complications due to unsafe abortion. The programme specifically strengthens capacity of government facilities to reach more young people, people with disabilities (PwD) and extremely poor clients with SRHR services.

The programme is implemented by three partners, Engender Health International (EH), MSI Reproductive Choices and the United Nations Population Fund (UNFPA) across 22 regions of Tanzania mainland and Zanzibar. Partners work in collaboration with the government at national and local levels to deliver systems capacity strengthening activities alongside direct expansion of services (EH and MSI). UNFPA is responsible for procuring reproductive and maternal health commodities based on national quantification processes and engages in commodity security policy and national resource mobilisation efforts.

A key aim of SUFP is to expand the coverage of SRHR services across Tanzania among hard-to-reach groups. Since 2017 the programme has provided 12 million years of contraceptive protection, preventing an estimated 6 million unintended pregnancies and 8000 maternal deaths. In November 2023, the programme was extended for two years with the explicit aim of facilitating uptake of key interventions by government by the time of programme closure.

MSI uses directly employed clinical staff working with government health workers to deliver targeted SRHR outreaches in underserved communities. This is complemented by a mentorship model in which Embedded Nurses (ENs) are stationed at high volume health centres and hospitals (hubs) supporting four smaller facilities (spokes). ENs aim to build public capacity in the routine provision of family planning (FP), especially long-term methods. They also provide mentorship on facility management and data reporting. EH activity focusses on building the capacity of government health providers via facility based clinical training, on-job mentoring and supportive supervision visits while also supporting facility-led FP outreaches.

This annual review was conducted in the aftermath of the announcement of a 90-day pause of USAID activities in January 2025. This has resulted in financial and wider resource cuts to the health system including the removal of 49,000 health staff from facilities. USAID was the largest financier of family planning services in Tanzania. Based on a thorough assessment of the sustainability of both delivery approaches, we are proposing some reprioritisation of locations of both EN placements and EH outreaches to focus on areas with extremely limited access to local facilities and/or where critical staffing gaps mean no Long-Acting Contraceptive Methods (LARCs) are being provided. Our systems strengthening support will continue establishing best practice, cost-effective training regimens with government providers and support districts to plan for using their own-source budget for the expansion of integrated SRHR services to make more efficient use of domestic financing.

While there was generally good availability of a range of contraceptives in facilities throughout the year, a notable exception was the supply of Implanon NXT which suffered global and national supply challenges. In some facilities visited as part of this Annual Review, FP commodities were stocked out since November 2024 limiting people’s access to services. For 2025, there remains a critical funding gap of $24.8 million, and the country is facing nationwide stockouts of almost all SRHR commodities from June 2025 onwards. This review has made recommendations for priority actions to secure commitment from GoURT to finance a larger proportion of the SRHR commodities bill from domestic budgets.

Recognising the unprecedented challenge and cost of standing in solidarity with Ukraine, the UK Prime Minister announced an increase in defence spending to 2.5% from 2027 offset by a reduction of UK ODA from 0.5% to 0.3% by 2027. The UK will continue its proud history of helping those in need, including in Ukraine, Gaza and Sudan, responding to humanitarian crises around the world and acting in the UK’s interests to ensure a liveable planet.

The review period saw no in-year financing reductions and partners were able to operate as planned. The widespread implications of the US funding pause and the planned UK ODA reduction by 2027, however, mean this Annual Review has considered future requirements of the programme in which pivots are anticipated to ensure its ongoing relevance and feasibility in a rapidly changing context. We will work with GoURT and our implementing partners to identify priority areas of adaptation as required.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

The review recommends an overall A+ score. Almost all milestones were met, and many were exceeded. The number of clients reached through outreach services was 771,358, exceeding the target of 706,880. The number of clients reached through routine services is above target at 486,939, indicating an improvement in the integration of SRHR into the national system. Progress on Comprehensive Post Abortion Care (CPAC) is promising, with both partners over-achieving targets. The programme sustained prior high performance in reaching young people and people living with a disability (PwDs) – at 37% and 6.1% of clients respectively. Screening for HIV/AIDS took place among 28% of all clients served. The provision of GBV services have seen a considerable over-target result, indicating both the huge demand for, and importance of, ensuring GBV preventative and curative services are widely available to all Tanzanians and linked with adequate referrals for legal services. With SUFP mentorship and engagement in key policy and operational reform processes, health workers have built their confidence and skills to screen GBV cases and provide referral services.

Strong partnership with GoURT at all levels has improved programme coordination and delivery in line with regional and district health priorities. An example of effective support to national systems strengthening is our work with council health management teams (CHMTs) to plan and budget for use of own-source funding for FP outreaches, printing of health data collection forms and the redistribution of commodities between facilities to avoid stockouts and expiries. At the national level, implementing partners and FCDO technical staff have collaborated to progress key policy agendas, including finalising the comprehensive health curriculum (CHE) and establishing interministerial coordination structures for the development of core CHE modules and their rollout in schools.

Major lessons and recommendations for the year ahead [1/2 page]

Recommendation	Action and Deadline
Considering US funding cuts, all partners in SRHR space must be coordinated by GoURT to direct the remaining limited resources to where needs are greatest. This includes supporting well-resourced public facilities to conduct their own outreach.	By April 2025 / MoH FP coordinator is mapping partner locations and resources to estimate the density of IP support in each district. This will be used to improve coordination at all levels to re-distribute support and ensure comprehensive geographic coverage. / SUFP service delivery partners (EH and MSI) contribute detailed information on their support to individual facilities as part of the MOH-led partner mapping.
Outreaches are effective at raising demand and reaching marginalised groups, including young people and the extreme poor. But they can be resource intensive and could do better to leverage wider community platforms / resources. / Given the scale of health funding cuts from US aid withdrawal, there is a need for SUFP to rationalise both the numbers and modalities of outreaches to target areas with the largest unmet need for FP and those furthest away from functional facilities with trained providers. / Areas with already high MCP rate or comprehensive access to high-quality facilities should be deprioritised as part of ongoing coordination with District Health Management Teams (DHMT) outreach plans.	By September 2025 / Review of outreach locations and EN placements to ensure integrated SRHR outreaches with other services and refocus on routine and FP ‘Service Days’ as the key modalities. Any savings from this prioritisation will be reallocated to training and OJT mentoring with public health providers on the provision of a minimum FP package inclusive of LARCs according to available stock levels. / EH and MSI to agree an approach for CHWs funded by GoURT to mobilise clients to attend outreaches rather than paying for additional social mobilisation.
Rapid HRH churn and dominance of vertical programmes have led to a lack of government ownership of public health training information and status. The SUFP programme should support GoURT to capture the locations of all trained, certified and competent staff. This is the first step in ensuring improved coordination of training and allocation of staff to where needs are greatest.	By December 2025 / EH and MSI to work with MoH to update the train SMART capturing the locations of all FP certified individuals and their current clinical competency levels.
Some key assumptions of the Theory of Change no longer hold especially on the continued scale of donor and domestic funding for procurement of commodities. Considering this major risk, some of the milestones for the next year (2025) may not be met and in-year adjustments to activities are expected.	By May 2026 / We do not anticipate altering our outcome or output targets at this stage, since the programme has managed to deliver strong results throughout periods of change (2021/2 Covid, ODA cuts). / This AR has identified appropriate pivots to support GoURT to mitigate some of the impact of USaid funding cuts and support continuity of FP services in the country. Contract amendments may be required to adjust some partner activities to be able to work within this new operating context. Performance against any amended contract requirements will be assessed in the 2025 Annual Review.
Withdrawal of US DHS programme prevents access to key source for impact measurement. FCDO will pursue two options to obtain interim measurements of MCP in Tanzania. This could include use of UNFPA’s FPET Tool or commissioning of rapid mobile survey questions on fertility.	By October 2025 / UNFPA to have worked with GoURT to update the FPET tool with service data, updated stock method mix and availability (where possible). / FCDO to explore feasibility of rapid mobile survey for a proxy for MCP rate and other fertility questions.
The long-term impact of USAID funding cut is significant with risk of reversal of gains if the GoURT does not increase domestic financing to procure commodities and take a step change in FP service delivery.	By July 2025 / FCDO to: / (i) sustain engagement with other partners and GoURT to increase its burden share of commodities bill through domestic finance – including agreement of a match funding arrangement for final tranche of UK finance for commodities. / (ii) Pursue FCDO’s separate agreement with Results4Development (R4D) for evidence generation and policy support to market shaping for external funding, procurement and development of alternative SRH commodities.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

The programme was granted approval for a time and costed extension from October 2024 to September 2026. This change, combined with lessons from five years of implementation, prompted a review of the results framework. Additional outcome indicators have been added from 2025 to capture the intended system level impacts of the programme, including:

- the total number of clients accessing family planning services in regions the UK is supporting
- the % of councils supported by the programme with functional quality improvement teams
- the % of selected service delivery points (SDPs) reporting no stock out of three modern contraceptives when visited, used as a proxy indicator for last mile stock availability.
The Theory of Change posited the following logical flow.
If the programme:
- Increases knowledge and demand for SRHR services among underserved groups, including adolescents, PWDs, people living in rural areas and refugees.
- Builds competencies of health workers, facility in charges and district health management teams to provide comprehensive SRH services in strengthened public facilities.
- Procures FP commodities on time with clear cost-sharing arrangements between GoT and development partners for effective commodity security.
Then we can expect:
- Improved SRHR knowledge and healthy decision making from clients
- Comprehensive SRHR services, sustainably provided within a stronger national health system with improved use of data for quality control and management
- Clients consistently able to choose from a range of modern commodities free of charge.
Since the programme inception, the operating context for provision of quality, integrated sexual reproductive health services has fundamentally changed. The following table provides an update and RAG rating of the key assumptions underpinning this logical flow.

Key Assumption	RAG	Update
Donor and Govt. investments in SRHR in Tanzania are prioritised		The health sector is heavily donor financed with some 45% of all health spending coming from external sources. GoURT Public Expenditure Tracking (PET) does not disaggregate by sub-sector, so the total expenditure on SRHR is unknown. Donor financing has decreased over the lifetime of the programme due to global shocks, with direct impact on services.
Other donors continue to provide support at consistent levels		US aid funding accounts for roughly 20% of the total health sector spending - by far the largest bilateral donor. Large procurements of health commodities and running of specialist HIV/AIDS clinics with some 49,000 health workers are currently paused. Should US funding not resume, this will result in significant gaps in SRHR / HIV / RMNCAH service provision from 2025 and beyond.
Donors coordinate and avoid competing interests		At a strategic level the Donor Partner Group for Health has been somewhat effective at aligning donors plans and avoiding competing interests. However, the engagement between the DPG and the managerial section of GoURT is limited resulting in poor cooperation at technical and operational levels which must therefore be pushed by individual implementing partners.
GoT is receptive to partnering with DPs to improve service quality and coverage		This has progressed well with SUFP building strong partnerships at national and regional levels to coordinate outreach, provide supportive supervision, enhance the national CPD offering and integrate disability and GBV screening into routine care, standard operating procedures and data reporting tools. An ongoing challenge of the EN mentorship model is the lack of trained, certified FP clinicians present in facilities to mentor.
National and donor investments in SRH can be tracked and GoURT is accountable for its budgetary commitments on SRH commodities		There is a downward trend in the utilisation rate of national budget commitments for SRHR commodities from 80% utilisation in 2016/17 to 8% in 2021. The budget lines are now merged such that GoURT no longer reports on utilisation of committed budget on SRHR commodities. External donors have doubled the value of disbursements on commodities since 2019, from $12.2million to $26.4 million in 2023.The future trajectory is not promising with $24.8m funding gap for 2025 and limited donor and GoURT commitment secured.
Providers with improved skills in integrated SRH services will lead to an improvement in the quality, choice and uptake of SRH services in communities they serve.		Our study on the drivers of modern contraceptive uptake found a doubling of Long-Acting Contraceptive Methods since 2015. The provision of these methods is only possible with improved knowledge and competency of health staff to provide quality counselling and effective method provision. While discontinuation rates have increased in some instances, this is more common for long-acting methods due to a desire to discontinue for fertility reasons. / Beneficiary feedback is collected through client exit interviews (CEIs) and additional focus group discussions (FGDs). Through these tools, several barriers to improved client access, choice and satisfaction were identified, including long waiting times, limited contraceptive options for men, and pervasive misconceptions about modern contraceptive methods. Youth participants recommended leveraging technology and media, along with tailored outreaches for higher learning institutions. These insights continue to inform programme strategies

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

SUFP’s intended impact is to contribute to a modern contraceptive prevalence (MCP) among married women aged 15 and 49 years (mWRA) of at least 38% and maternal mortality ratio (MMR) of less than 413 deaths per 100,000 live births by 2026. The latest Demographic and Health Survey (TDHS2022) shows an MMR of 104/100,000 meaning the indicator has already been achieved.

Less positively, MCP remained flat at 31% in 2022 among mWRA. Using the UN FPET tool, we see a projected increase to 33.3% in 2024, and 36.5% in 2027. This assumes a linear progression from the 2022 DHS data, which is over-optimistic. Given the uncertainty of future funding to DHS (a US funded programme), a recommendation of this review will be for UNFPA to update the FPET model with population projections, national service data, stock availability and updated method mix for more accurate prediction of MCP by the end date.

As recommended in last year’s Annual Review, FCDO commissioned a study on the factors driving stagnating MCP progress between 2015 and 2022 and the regional variations. The study looked at whether the level of investment in SRHR services over the period was sufficient to meet the demands of a growing population and whether high-level political criticism of FP from 2015-2021 was a significant factor behind stagnating MCP rates.

The study analysed DHS and DHIS service level data and found that, while MCP remained flat over the period, the number of clients served increased from 1.9 million users of modern FP recorded in 2015 to 3.9 million in 2022. As a proportion of all WRA, modern FP users rose from 17% to 27% in the same period. Moreover, the provision of Long-Acting Reversible Contraceptives (LARCS) rose four-fold over the same period demonstrating a shift away from short acting methods.

Women receiving FP services as reported by routine DHIS 2015 – 2022

Comparison between population change and unmet need (%) by region 2015 – 2022

Almost all regions with above average population growth (Dodoma, Morogoro, Katavi, Tabora, Simiyu, Singida, Shinyanga and Rukwa) saw a negative trend in unmet need. Conversely, regions that saw modest population growth, including Kilimanjaro, Kagera, Iringa, Njombe saw the unmet need for family planning decrease. This suggests an important interplay between a region’s growth and its ability to invest sufficient resources in SRHR services to meet demand.
[note] Unmet need is the proportion of sexually active women who want to limit or space births but are not currently using contraception and are not pregnant or infecund.

Where the close relationship between population growth and unmet FP need is mitigated, potentially through high density of implementing partner efforts to expand SRHR coverage (Geita, Mwanza, Pwani) MCP rapidly improved. In areas where population increased and unmet need remained flat or worsened, the MCP decreased (Katavi, Rukwa, Singida Dodoma, Morogoro, Ruvuma and Mtwara). Areas which saw a stagnation in MCP (Mara, Arusha, Manyara, Lindi) correspond to areas with medium or low population growth and declining unmet need.

The full analysis of MCP trends was presented at the national Technical Working Group for Family Planning and with the Director of Reproductive Maternal and Child Health at the Ministry of Health. A request for more detailed mapping of implementing partner presence and investment was also commissioned by the FP Technical Coordinator to understand how the concentration and investment of partners supported those fast-growing regions to better address challenges of FP unmet need and derive lessons for other regions struggling to keep pace with the demand.

Progress against outcome indicators and outcome confidence statement

Improving access and quality of SRHR is both a fundamental right and has direct public health outcomes, including control of sexually transmitted diseases like HIV/AIDS and the reduction of unwanted and unsafe pregnancies, a leading cause of maternal death and disability. The programme is on track to achieve its outcome indicators as outlined below.
Outcome Indicator	Actuals	Achievement
Number of annualised clients from all providers reached in focus regions	5,011,815	120%
% of clients reached who are new FP users	1,626,842 44% of all clients	146%
Couple Years Protection (CYP)	2,664,295	120%
Averted Maternal Deaths	1,418	120%
Averted Unwanted Pregnancies	1,304,984	123%
% of intensive councils with functional quality improvement teams	48%	Baseline Year– / 75% next year
Percent of service delivery points in selected regions reported no stock out of three modern contraceptives on the day of field visits	100%	125% - low confidence

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

The programme is likely to meet its outcome objectives given continued strong performance against the indicators. The analysis above has also demonstrated that the aggregate MCP rate of uptake hides significant variation within regions and masks the net uplift in numbers of services over the last 5 years to respond to increasing population demands. With the growth in women of reproductive age averaging 3% a year and improved demand for services, keeping MCP and unmet need flat takes substantial effort and investment on the part of the government to increase infrastructure and health worker numbers. This is coupled with strong support from DPs to improve the coverage and quality of SRHR provisions. This is leading to significant lifesaving outcomes for women and girls, including reduced numbers of unintended pregnancies, fewer maternal deaths and fewer DALYS from post abortive complications. We intend to keep the same outcome indicators for 2025 but may need to reduce expectations for milestones/targets considering the changing context. Furthermore, the programme has already delivered a key result of the Tanzania Country Business Plan, to provide 11.8m couple years of family protection (4.8m in the last 2 years of the programme) having already provided 12.7m to date. On its own merit and based on extremely strong performance this programme should continue with some pivots introduced to support GoURT to put in place emergency mitigations to counter the impact of the US funding cuts on the broader health landscape and SRH service provision in country.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Provision of comprehensive and inclusive family planning services
Output number:		1	Output Score:	A+
Impact weighting (%):		35%	Weighting revised since last AR?	Yes – previously 40%

Indicator(s)	Milestone(s) for this review	Progress
1.1: Number of clients accessing family planning services through outreach services.	MSI – 413,426 / EH – 293,454	MSI – 443,793 / EH – 327,565
	Total – 706,880	Total – 771,358
1.2: Number of clients accessing family planning services through routine services (including Post-Partum Family Planning).	MSI – 259,910 / EH – 187,073	MSI – 278,906 / EH – 208,033
	Total – 446,983	Total – 486,939
1.3 (a): % Young people receive family planning in outreach services	MSI – 15% / EH – 16%	MSI – 19% / EH – 18%
	Total – 31%	Total – 37%
1.3 (b): % Young people (<20 years) receiving family planning before getting pregnant	MSI – 14% / EH – 45%	MSI – 12% / EH – 47%
	Total – 59%	Total – 59%
1.4: Proportion of FP clients tested for HIV during family planning outreach services.	MSI – 1.5% / EH – 24%	MSI – 0.80% / EH – 25.20%
	Total – 26%	Total – 26%
1.5: Percentage (%) of clients satisfied with services received (disaggregated by service delivery model).	MSI – 90% / EH – 96%	MSI – 94% / EH – 99.8%
	Total – 186%	Total – 192.8%
1.6: Proportion of clients with disabilities (measured through the Washington Group Disability questionnaire) reached with family planning services.	MSI – 2.2% / EH – 0.8%	MSI – 5% / EH – 1.10%
	Total – 3.0%	Total – 6.1%
1.7: Proportion of clients who reported to receive comprehensive counselling according to FP2020.	MSI – 84% / EH – 96%	MSI – 69% / EH – 99.7%
	Total – 180%	Total – 169%
1.8: Number of clients in the refugee camps reached with family planning services.	MSI – 14,925	MSI – 13,511

Briefly describe the output’s activities and provide supporting narrative for the score.

This Output scored an A+ given most output indicators were substantially exceeded with the exception of indicator 1.8 of clients served in refugee camps.

Reports from partners, backed up by FCDO field visits, indicates a 109% achievement of outputs 1.1 & 1.2 and continued positive trend in uptake of family planning and the availability of long-term methods. The total number of family planning services offered in routine settings was 486,939 against a target of 446,983. FP outreaches remain the principal service delivery modality, with 771,358 services provided against a target of 706,880. We have seen a notable improvement this year in the provision of Long-Acting Reversible Contraceptives (LARCs) via routine modalities at roughly half of all FP services offered. In the contract extension phase, outreach was targeted to areas with low MCP. Awareness-raising and demand generation initiatives have been increased to reach more people living in poverty, more young people and more people with disabilities.

The programme is successfully reaching adolescents and persons with disabilities (39% and 6.1 % of all outreach clients) with human-centred-design activities for in-school and out-of-school youth. This combines sexual health education, income generating activities and integrated adolescent and youth friendly SRHR services. Engaging higher learning institutions and running FP awareness campaigns at both national and regional events have proven effective at accessing large cohorts of young people (e.g. International Day of People with Disabilities; World Aids Day; Cervical Cancer Awareness Month, etc). The programme reached double the number of clients with a disability than planned, which is attributed to the excellent partnerships forged between partners and local community-based organisations. In addition, partners have effectively advocated for the rollout of a disability screening tool, which is now used as standard in all public facilities. Alongside health worker training, this tool ensures appropriate counselling for PwDs to meet their needs. Integration of the PwD screening protocol into the Afya Supportive Supervision Guides Council Health Management Teams to check the presence of this tool and monitor its effective usage. At the Annual Health Summit, MOH committed to include indicators in MUTHUA health forms to capture services offered to PwD, and this continues to be a key policy objective under this output.

In 2023, SUFP implementing partners supported the government to review and update the Comprehensive Health Education (CHE) curriculum to include best practice content on SRHR, GBV and nutrition. Engender Health is now supporting effective coordination between line ministries (MoE, MOH, MCDGWSG, PORALG and TIE) to strengthen the delivery of CHE in all public schools. A revised workplan has been established to support the integration of the CHE into teachers’ pre-service training, develop guidance on the establishment of school clubs to compliment subject-specific content and support interministerial coordination and reporting of key health and nutrition indicators.

Last year’s AR recommended a renewed focus on on-job training (OJT) and mentorship with government health providers to increase their confidence in LARCs provision. A special task force was set up by the Ministry of Health (MoH) with Engender Health and MSI supporting the review of the 2023 FP procedure manual and comprehensive FP training curriculum for Tanzania. An update to the MoH train SMART database should be commenced to capture both pre-service training and Continuous Professional Development (CPD) activity of public health providers to better support integrated RMNCAH delivery. Facilities should also be encouraged to set aside budget to pay for CHWs to support demand generation/awareness raising for FP alongside vaccination drives. This would provide a more sustainable method of demand generation.

The sudden withdrawal of USAID funding brought an approximate 20% reduction in health sector spending, predominantly across HIV/AIDS and SRHR. This is on top of 60% staffing shortfalls in some areas, with facilities having to task share and prioritise life-saving care as a result. MOH and PORALG recognise the need to shift strategy to ensure continuity of SRHR services with much less resource. This will require a minimum service package to be agreed and a renewed focus on facility-based provisioning using CHWs to mobilise clients to attend clinics. The SUFP programme can support this shift where the ability exists within facilities.

A further challenge will be ensuring the full range of SRHR commodities, to which USAID was a major procurer, without the planned $6.2 million committed by US for FP commodities. There is currently no stock of Implanon or Depo-Provera at MSD national level and less than one month of stock of Microgynon or Jardelle. At the national level, the Ministry of Health and Medical Supplies Department (MSD) will need to agree emergency budget release to procure fast-moving commodities to fill the commodities pipeline. This challenge is discussed in more detail under Output 4, but we should expect major bottlenecks to programme outcomes in 2025 due to poor stock availability. We will ensure funds set aside for buffer stock are fully utilised this year to account for any shortages and advocate for domestic financing arrangements to be fast-tracked to cover some of the funding shortfall.
Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Given the unprecedented reductions in external funding for SRHR and the need to develop cost-efficient service modalities that can easily transition to government by December 2026, we recommend a renewed focus on facility-based (routine) service provision and quality improvement. This is the preferred approach of Regional Medical Officers (RMO) and national health officials to retain minimum service levels and protect quality with less external funding.

Given the scale of the funding challenges, we will review partner activities and locations to ensure we are targeting areas most poorly served by public facilities. Outreaches should prioritise chronic shortages of trained FP providers for LARC provision and an increasing rate of unmet FP need. We will also track those facilities who autonomously conduct outreaches–integrated with other health services (e.g. vaccinations and HPV). This approach can be enhanced by encouraging facilities especially those which have high volumes of clients to request additional capacity from nearby facilities during outreaches to increase the number of service providers, coordinated through the District Medical Offices. Some practices already exist in Morogoro region and Mtwara DC to replicate across the country.

Unfortunately, a trade-off of a renewed focus on facility-based care is that people with specific barriers to accessing health facilities (adolescents, people with disabilities and extremely poor people) may see their access to FP reduced. We will address this risk by doubling down on demand side activities, including raising awareness and knowledge of services among adolescents through CHE activities, and ensuring remaining outreaches target these groups.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Recommendation	Progress & Deadline
Implementing partners to ensure that (i) outreach services target underserved communities (ii) correct messaging on FP methods is provided to clients during counselling to ensure correct use of FP method. This includes correct information on the duration of injectables efficacy.	By June 2024 / MSI is advancing its advocacy to integrate best practice content into the national health worker training package. EH and MOH is considering working with professional bodies for routine supportive supervision, mentorship and coaching. This approach would require service providers to earn Continuous Professional Development (CPD) points to receive and maintain their professional registration. Engagement with professional bodies is planned for Y6Q1, following approval from MOH, PORALG, and relevant stakeholders.
Engender Health and MSI to prioritise and expand low-cost approaches to strengthen government health worker confidence and competency in providing long term reversible and permanent FP methods.	By October 2024 / Ongoing discussions with MOH and regional authorities on certification of permanent method providers. Prioritising on-the-job training (OJT), ensuring hands-on practice as a prerequisite for certification. MSI is leveraging another programme ‘Public Sector Strengthening’ projects in 243 government facilities using a global health system strengthening model.
Engender Health to work with the MOH to strengthen teaching of sexuality education through teacher training colleges, using the National Strategic Plan on Adolescents and Youth as an entry point.	By December 2024 / EH has effectively coordinated Sectoral ministries and related Ministry Departments under the leadership of MoH Directorate of Preventive Services to hold structured discussions, culminating in agreed actions and budgets to integrate CHE into teachers’ pre-service training and roll out in-school clubs, and improve national level reporting on nutrition & health education outcomes.

Recommendations for 2025

Recommendation	Action & Deadline
Ensure IPs secure buffer stock for LARCs for which they have trained providers to administer.	By March 2025 / EH and MSI to provide updates on their buffer stock quantities and emergency distribution plans from IPs.
Realign outreaches to target areas with a declining unmet need for FP and limited access to facilities with trained providers. Areas with already high MCP rate should be deprioritised to incentivise a ‘Facility first’ approach.	By September 2025 / MSI and EH to review outreach locations and EN placements to ensure integrated SRHR outreaches with other services and refocus on routine and FP ‘Service Days’ as the key modalities. Any savings from this will be reallocated to training and OJT mentoring with public health providers on the provision of a minimum FP package inclusive of LARCs according to available stock levels.
Capture more detailed information on provision of LARCs in different settings and from a commodity security perspective.	By June 2025 / EH and MSI to report LARCs in the narrative reports quarterly and include trend analyses to show change over time across all facilities and delivery modality in their focus regions / UNFPA to include disaggregation by LARCS in their analysis of stock outs

Output Title	Provision of Comprehensive Post Abortion Care (CPAC) and Preventive and Responsive Gender Based Violence (GBV) Services
Output number:		2	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
2.1: Number of clients who received Comprehensive Post Abortion Care (CPAC) in routine services.	MSI – 6,420 / EH – 14,000	MSI – 7,606 / EH – 14,412
	Total – 20,420	Total – 22,018
2.2: Number of clients who received Comprehensive Post Abortion Care (CPAC) in refugee camps.	MSI – 167	MSI – 200
2.3: Number of GBV incidences identified and services provided in routine and outreach services.	MSI – 23,961 / EH – 67,311	MSI – 24,917 / EH – 67,701
	Total – 91,272	Total – 92,618
2.4: % of GBV survivors in Nyarugusu camp and Kigoma region that are referred to appropriate referral services.	MSI – 65%	MSI – 62%
2.5: Number of EMAP sessions conducted by IRC	MSI – 54	MSI – 54
2.6: Proportion of men and boys completed EMAP who score 75%or above on the knowledge and attitudes questionnaire	MSI – 50%	MSI – 74%

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

This programme output scored an A given output indicators were largely met or exceeded.

This year 22,018 clients received comprehensive post abortion services (CPAC) at public health facilities equipped by the programme. 200 clients were treated in refugee camps. Facilities receive capacity building for health workers previously trained by the programme, regular supportive supervision and enhanced data collection and reporting systems.

Embedded Nurses (ENs) working at facilities have continued to guide health staff providing CPAC services and ensuring adequate supplies of MVA kits and other consumables. At a national level, a high-level discussion was led by MSI with leading maternal health coalitions to assess Tanzania’s progress in implementing Section 14 (2)(c) of the Maputo Protocol. There has been progress in developing National Comprehensive Post-Abortion Care Guidelines and ensuring legal provisions adhere to these, although there remain significant challenges in full domestication and enactment of the protocol in Tanzania. Given the high change of stockouts of key modern forms of contraceptives in the year ahead, the risk of an increase in the number of unsafe abortions is significant. The programme should ensure follow up of public health staff previously trained in CPAC services and consider refresher training.

GBV is widespread in Tanzania with latest estimates that 27% of all women aged 15-49 years have ever experienced physical violence, while 12% experienced sexual violence. Support under SUFP focusses on prevention and response pillars, to mitigate the health-related risks of violence for survivors. In addition, the programme cooperates with regional authorities to strengthen coordination across the referral chain for effective joined up support (social services, paralegal, etc.). At a national level partners are engaging with policy makers to revise policies to better serve the survivor, including adjusting the requirement for rape survivors to get a PF3 form from the police station prior to accessing care at health facilities.

Both partners support the screening and identification of people experiencing GBV and this has been facilitated through regular GBV trainings with public health workers and management. Overall, 92,618 GBV incidences were reported and provided referral services in routine and outreach services against a target of 91,272. Support services include social welfare services, medical services, and police gender desk services.

This year the programme expanded its focus towards GBV prevention through a programme of SRHR reduction in schools and the wider community. With some 15% of students in schools experiencing at least one incidence of sexual violence in 2022, there is an urgent need to educate children with age-appropriate content to identify and report violence. Engender Health and Pathfinder have supported School Health Clubs, using the ‘Purposeful Play’ pedagogy to help young people understand and critique the gendered dynamics of GBV, to identify different forms of violence, and build their confidence to report and seek help.

The Nutrition and Health Education Coordinator from the Ministry of Health was invited to visit one of these clubs during the SUFP Annual Review and committed to using it as the national model for CHE school clubs going forwards. While this is testament to the success of the programme, a major challenge will be scaling a ‘gold-standard’ model with limited resources. Potential harm could arise if content is diluted through poor operationalisation. To mitigate this risk, a high-level dialogue with officials from across the different line ministries will be held to outline the key requirements and level of investment needed to roll out effective school clubs nationally. Continued interministerial and donor coordination is needed to leverage resources from other areas, including potentially the World Bank BOOST and Pamoja programmes.

GBV is especially prevalent in the refugee settings in Tanzania. Integrated SRHR and GBV screening saw the identification of 55 clients of whom 39 were referred for further or specialist support as required. A three-day session on GBV referral pathways training equipped GBV social workers with the knowledge to provide quality, durable referrals to survivors of violence. The programme is providing social-behavioural change interventions with communities within and bordering refugee camps with high rates of GBV. After five years of this intensive support to communities, we recommend an external evaluation of this work to determine whether it can be scaled by local government or taken over under the FCDO humanitarian programme going forwards.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Outputs 2 and 3 (CPAC and GBV) were merged and re-weighted considering the front-loading of activity behind these outputs in earlier years. We do not plan further changes to this output in the year ahead.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Recommendation	Progress & Deadline
Changes to the log frame output indicators to reflect the change in IRC’s mandate on GBV services in the refugees’ camps.	By June 2024 / MSI provided two requested revised log frames reflecting the change in IRC’s mandate to provide GBV services alongside other revisions. FCDO approved these log frames.

Recommendations for the year ahead:

Recommendation	Action & Deadline
High rotation of staff among government health workers means those trained in CPAC at the beginning of the programme may no longer be practising or require refresher trainings to keep their skills updated.	By October 2025 / i) MSI and EH to consider refresher on job training for health workers previously trained in CPAC given risk of increase in unsafe abortions if commodities stockouts occur. / ii) Consider whether there is scope for TOT activity and increased facility-based mentorship on CPAC to build capacity.
GBV screening approach should be mainstreamed across the provision of routine services, with training on GBV and a survivor-centred approach integrated into national training plans.	By March 2026 / EH to advocate with Ministry of Health for GBV screening and response training modules to be added to the pre-service curriculum to sustain HRH skills and coverage of GBV screening.
Evaluate IRC support to EMAP and in-camp health support with a view to transitioning this to FCDO humanitarian programme for broader synergies.	By September 2025 / FCDO to discuss and agree options for the transfer of activity to FCDO humanitarian Programme.

Output Title	Health system strengthening for quality sexual and reproductive health (SRH) and GBV services
Output number:		3	Output Score:	A+
Impact weighting (%):		35%	Weighting revised since last AR?	Yes – previously 10%

Indicator(s)	Milestone(s) for this review	Progress
3.1 (b): Number of government health providers trained and certified in provision of family planning permanent methods	EH – 32	EH – 32
3.3: Number of FP service days conducted by CHMT without programme support	EH – 459	EH – 635
3.5: % of councils in all supported regions in mainland Tanzania using Afya SS during their routine supervisions with programme support	EH – 50%	EH – 95%

Briefly describe the output’s activities and provide supporting narrative for the score.

This output scored an A+ due to exceeding all indicator targets. The programme did not provide substantial pre-service training of health workers this year. Instead, the focus was on supportive supervision of facilities and on-job mentoring for FP providers alongside basic facility management (leadership, clinical supervision, data management and stock logistics etc.). A major challenge to improved systems strengthening remains the lack of health workers in government facilities. Nationally, we see around 60% staffing gaps across all clinical levels with many providers who have been trained under vertical programmes either moving out of the government system or being reallocated to non-FP services. The level of training being financed by government is not sufficient to meet growing demand for services. Furthermore, staffing gaps are limiting the time available for client consultations and may disincentivise some health workers from offering LARCS with longer procedure times, including IUCDs.

The programme has ensured the sustainability of its impact by working with District Health Management Teams (DHMTs) to plan and budget for integrated FP outreaches. In the past year, 635 outreaches have been delivered without direct programme support in intensive councils supported by the programme. Due to the presence of many partners in each district, it is unclear whether such outreaches would have occurred in the absence of any external partner support. Considering US funding cuts and the withdrawal of direct resources from many facilities, outreaches must be rationalised and made more cost-effective. This includes using CHWs and local schools and community groups to mobilise clients to attend facilities.

During annual review field visits, we spoke with facilities who had just finished EN placements. Staff reported a good level of capacity building, following formal training received at the beginning of the programme. There is also evidence of mentored staff cascading training to others. However, MSI’s impact analysis of the model reviewed facility service data prior to ENs placement and in subsequent months and years following their departure. The analysis in DHIS2, shows a significant uplift in the provision of LARCs during the period ENs are at the facility, but the effect is gradually diluted over time and almost disappears two years after departure due to various factors such as turnover of health staff in public facilities. However, reduction rates post-EN placements have slowed as the project learned and adapted through each cohort of facilities.

Some health facilities, while commending EN’s mentorship and capacity building, cited lack of equipment (sets for insertion of LARCs) as the reason to why they no longer offer services. These sets are available at MSD and health facilities can afford using their own budgets. Generally, lack of trained and certified LARC providers in public facilities with whom to build capacity is a key bottleneck. ENs inevitably end up supplementing to fill staffing gaps. In the long term, MSI should consider shifting their approach to provide less intensive in-facility resource towards a rotating team of experts that provide regular mentoring and coaching but do not directly provide services. However, given the significant staffing constraints in public facilities, limiting EN activity to facilities with high caseloads and insufficient staffing levels is an appropriate pivot. This is a risk-based strategy to mitigate the impact of US funding cuts in which a further 49,000 health workers will leave the system immediately, adding to the 60% staffing gaps in some areas.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

No changes were made to this output during the year. Following a thorough log frame review, several new capacity building indicators were agreed and will be reported on from next year:
- 3.1 (e)	% of targeted facilities that have the capability to deliver the maximum range of family planning services
- 3.2 Proportion of one stop centres providing comprehensive GBV/VAC care and support in Zanzibar
- 3.4 % of intensive councils in Mainland Tanzania with active IMPACT teams.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Recommendation	Action & Deadline
Review and adjust the EN model to explicitly acknowledge it as a supplementary approach to health resource challenges considering 60% shortages of HRH in the sector	By October 2025 / For the next rotation of ENs ensure only spokes with <50% staffing gaps are included as a means of supplementing critical HRH capacity. / Reorient ENs on HIV testing, CPAC and other emergency RMNCAH clinical skills so they are best able to provide integrated support to facilities in need of health staff
Rapid HRH churn and presence of DP vertical programmes necessitate greater government ownership of public health training status to be able to allocate trained, certified and competent staff to where needs are greatest.	By December 2025 / EH and MSI to work with MoH to update the train SMART database capturing the locations of all FP certified individuals and their current clinical competency levels.

Output Title	Family planning commodity supply and management
Output number:		4	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	Yes – previously 40% as combined with systems strengthening output 3

Indicator(s)	Milestone(s) for this review	Progress
4.1: Percent of MSD zonal offices and sales points that reported no stock out of three modern contraceptive	UNFPA – 80%	UNFPA – 82%
4.2: Percent of contraceptive methods by type expiring at MSD Zonal warehouses and sales points within six months’ time	UNFPA – 5%	UNFPA – 0%
4.3: Amount of contraceptive methods by type expired at MSD Zonal warehouse and sales point	UNFPA – 0%	UNFPA – 0%
4.4: Percent of orders delivered as per supply pipeline schedule	UNFPA – 85%	UNFPA – 100%

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

This output scored an A due to meeting all target indicators. Partners provide support to facilities and CHMTs to enable facilities to order commodities on time ensuring no shortages. However, from September last year there have been periodic issues with facilities receiving less commodities than they require leading to stockouts. This is particularly true for Implanon NXT, which was stocked out in September 2024 due to late shipments of orders being placed. Also, a batch of IUCDs was reported to expire at health facilities by January 2025.

During the reporting period, the UNFPA country office fast-tracked shipments of oxytocin, Jadelle, Implanon NXT and Microgynon to prevent national stockouts which had emerged due to delayed government and other donor partner procurements. They facilitated the transfer of excess maternal health commodities from Zanzibar and Copper IUCD from mainland Tanzania to Botswana and Nigeria to avoid stock wastage. Meeting orders as per the supply pipeline schedule means complying with expected delivery dates for commodities based on forecasting, quantification and quarterly supply plan reviews. The supply plan outlines the timeline, quantity, and total cost of the commodities, including freight and clearance costs.

The downstream challenges with the electronic Logistics Management Information System (eLMIS) triggered by the move between software versions still impairs efficiency of logistics management functions. While ordering function is fully restored in the new version, key features such as visualization of logistics reports (for analysis and re-distribution), bottom-up quantification module and systems integration are still incomplete. The challenge is exacerbated by the US ODA pause, whose programs were key TA providers for the eLMIS.

At a policy level, there has been no formal communication of GoURT fulfilment of its financial commitments to the UNFPA Supplies Compact agreement for 2024. This lack of evidence of fund disbursement may prevent government from accessing the full planned 2025 UNFPA allocation (using separate funding streams, not under SUFP programme) as well as missing out on crucial match funding. UNFPA developed a tool to track domestic disbursement and expenditure against RH commodities, but this has not been widely taken up by government.

While not in the review period, as of February 2025, there was only one month of stock of Microgynon and Jadelle and no stock of Implanon NXT and Depo-Provera at the Central Medical Stores Department (MSD). The country is due to experience long-lasting stockouts of critical commodities including Implanon and Jardelle (contraceptive implants) from June 2025 for the remainder of the year unless funding emerges for the procurement of critical orders. The funding gap for commodities for 2025 stands at around $24.8 million. GoURT has mobilised $1.1 million from philanthropic organisations but has not yet secured treasury commitment to issue recurrent financing for procurement of SRHR supplies. In response to this alarming situation the FCDO is advancing discussions of a joint Development Partner (DP) MOU agreement consisting of a match-funding arrangement for RH supplies with the timing of DP disbursement linked to actual expenditure by GoURT.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

We propose to review the sampling frame for the indicator results reported by UNFPA since there seem to be some discrepancies between results and what has been observed on the ground throughout the year both at a zonal and facility level.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Recommendation	Action & Deadline
Given the scale of funding gap for commodities ($24 million), the UK will focus the remaining year of the programme on brokering effective partnerships with GoURT that incentivise domestic financing of commodities.	By June 2025 / Commence discussions with Directorate of Policy and Planning (DPP) MOH for an MoU covering a DP-GOURT Maternal and Reproductive Health Co-financing Agreement. This should be finalised to come into effect with appropriate expenditure tracking mechanisms.
Using the funding situation as a window of opportunity to advocate for increased ownership and bottom-up quantification of reproductive health (RH) commodities, along with key market shaping work to bring in the private sector to help fill gaps. This is essential for additional financing and innovation in commodities provision.	By Sept 2025 / With technical inputs from EH and MSI, GoURT to develop a minimum benefit package for FP services and the current task force for alternative financing for RH commodities continues to establish a roadmap and key activities to leverage more financing for domestic procurement.
Consider revisions to this indicator to measure the true status of stockouts in country and activities to support greater transparency and action on commodity security on the part of GOURT	By Sept 2025 / UNFPA to revise its logframe indictors to ensure accurate measurement of stockouts at zonal and facility level. / Include advocating for government institutionalization and adoption of the accountability tool (UNFPA or R4D) to track domestic allocation, disbursement and expenditure against RH commodities

Output Title	Improving availability and dissemination of census data
Output number:		5	Output Score:	B
Impact weighting (%):		5%	Weighting revised since last AR?	N/A new indicator

Indicator(s)	Milestone(s) for this review	Progress
5.1: Number of Census monographs produced as per the roadmap	The teams will commence working on five monographs the beginning of October, 2024. / Five monographs’ structures and chapters will be in place by end of the year and the validation process will start in 2025.	At Technical Level, all the five monographs were completed by the end of 2024. Follow up activities in 2025 include verification by sharing and presenting to stakeholders and conducting dissemination sessions
5.2 Existence of functional GIS data portal that is available to the public	GIS Portal is established	GIS portal has been developed, and its features are currently being updated, but there has been no dissemination to date.

Briefly describe the output’s activities and provide supporting narrative for the score.

In 2024 the SUFP programme allocated funding for census analysis and dissemination to strengthen the evidence base for decision making around family planning, and social sector delivery more broadly. This would be achieved through supporting census analysis in key sectors to speed up the availability of critical data, and to strengthen the GIS data portal to improve accessibility of this data.

Five census analytical reports have been drafted on:
- Fertility and Nuptiality
- Mortality and Health
- Disability
- Education and literacy
- Population Dynamics and development in Tanzania
These were significantly delayed compared to the original funding proposal, where they were due to be produced and disseminated by end of 2024. Since September there has been significant progress. The reports are now available containing new data and analysis on health, population and education, although the formal validation process has not been initiated and there are still delays compared to the planned timetable.

Work has been undertaken to strengthen the GIS database to improve accessibility of data, but this has yet to be publicly available. NBS and UNFPA presented the main findings of the census monographs to interested development partners on Thursday 22 May 2025.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

The original timetable was significantly delayed but regained progress from September. 2024. The scope of work has remained the same, but the planned completion of the work changed from December 2024 to December 2025 to fully finalise the work and dissemination.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

This is a new output so there were no recommendations last year.

Recommendation	Action & Deadline
UNFPA to work with NBS and ONS to support meaningful dissemination and use of the monograph analysis, including to local government, Zanzibar and civil society.	By Dec 2025 / UNFPA to work with NBS to confirm dissemination plans
NBS to present the GIS improvements to FCDO, World Bank and other partners	By June 2025 / NBS GIS presentation.

## D: VALUE FOR MONEY

Key cost drivers and performance
The major cost drivers in 2024 were service delivery activities, including outreach operations, supplies, demand creation, and programme staff salaries. Strategic cost-saving measures—such as stationing surgeons at facilities with operating theatres to reduce travel costs, prioritising single-day outreaches, and using autorickshaws (boda-bodas) for mass-scale demand generation—helped optimise expenditures. Programme partners adopted prior AR recommendations to improve training efficiency and reduce costs, resulting in a shift to facility-based (on-the-job) training. This approach successfully controlled costs and prevented service disruptions, as health workers remained at their facilities during training.

VfM performance compared to the original VfM proposition in the business case
The original VfM proposition was based on cost per couple years of protection (CYP), cost per disability-adjusted life year (DALY) averted, cost per maternal death averted, cost per unintended pregnancy averted, and cost per unsafe abortion averted. While improved availability of sexual and reproductive health services and counselling is not solely responsible for better maternal and child health outcomes, it plays a significant role in enabling women and girls to space and limit births as part of healthy reproductive choices.
Economy. The programme successfully implemented cost-saving measures to enhance financial efficiency. UNFPA’s procurement strategy achieved a 48% cost reduction through bulk purchases, acquiring 175,008 units of Implanon NXT and 110,000 units of Jadelle. Additionally, sourcing medical supplies from the government’s Medical Store Department (MSD) rather than private suppliers ensured cost-effective service delivery without compromising quality. Further cost-effectiveness was realised through bulk procurement, community-based service delivery models, and integration of family planning services into routine government health facility operations, thereby reducing operational costs.
Efficiency. The cost per client served rose slightly from an average of £3.86 in 2023 to £4.81 across both service delivery partners. The costed extension shifted focus from direct client outreach to strengthening the broader health system’s capacity, resulting in slightly lower client targets. Increases in operational costs (fuel, food, accommodation, etc.) may have also contributed to the rise in cost per client. The programme streamlined operations wherever possible to keep costs low. Resource efficiencies were achieved through strategic monthly cross-functional planning (covering outreach, data, and commodities management) with GoURT, and by combining supportive supervision visits with district health management teams (DHMTs) to avoid duplication. MSI’s split-team outreach model saved costs while expanding coverage, especially to marginalised populations. The cost per young person reached increased from £5 in 2023 to £10 in 2024, reflecting the programme’s extensive integration of human-centred design and comprehensive health education (CHE) interventions aimed at long-term impact. UNFPA delivered 100% of pipeline orders and expedited emergency stock requests, maintaining a steady national-level supply of commodities.
Effectiveness The programme demonstrated significant impact in 2024 across all output and outcome areas, averting 1,418 maternal deaths against a target of 1,184, with a cost per maternal death averted of £6,638. The average cost per CYP was £3.64, and the cost per DALY averted stood at £4.44, compared to the original business case estimate of £7.70. Additionally, the cost per additional user was £11.51.
Equity The programme remains committed to equitable service delivery, ensuring underserved populations receive family planning services. From 2020 to 2024, the proportion of young people reached through outreach increased from 27% to 37%, while the percentage of youth reached before their first pregnancy rose from 44% to 59%. The share of people with disabilities accessing services grew from 3% in 2023 to 6% in 2024. Outreach efforts prioritized poorer communities, increasing their representation from 69% in 2023 to 72% in 2024. Peer networks, community health workers, and youth-led organizations played a critical role in mobilization. The programme also leveraged international and national events such as International Youth Day, World AIDS Day, and National Farmers Day to further generate demand and reach wider audiences efficiently.
Cost-Effectiveness The programme has demonstrated strong cost-effectiveness compared to similar family planning initiatives in lower- and middle-income countries. The integration of FP outreach, CPAC, and PPFP services within government health systems has helped minimise operational costs while expanding coverage. High-impact interventions and strategic mobilisation ensured that every pound spent delivered maximum impact. Going forward, the programme will build on this principle of service integration within routine health settings—a ‘Facility First’ approach—to ensure continued effectiveness and sustainability through national delivery systems
Assessment of whether the programme continues to represent value for money

The programme continues to offer strong value for money, as evidenced by its ability to deliver cost-effective, equitable, and impactful services. Despite a slight increase in the cost per client served, efficiencies gained through strategic planning, bulk procurement, and integrated service delivery have ensured optimal resource utilisation.

Moreover, the programme’s commitment to equity enhances its value by ensuring that marginalised populations—including young people, people with disabilities, and those living in poverty—receive family planning services. It is important to note that full integration of FP services within government systems has not yet been achieved. External financing remains necessary to expand the full range of SRHR services to the most marginalised communities. Programme partners and FCDO technical advisors continue to focus on integration at both facility and policy levels, advocating for clearly defined and utilised recurrent budget allocations, improved national training regimens, and sufficient health worker deployment for FP provision. These efforts are key to ensuring long-term sustainability, cost-effectiveness, and reduced dependency on external funding.

E: RISK

Overview of risk management
The overall risk for the Scaling Up Family Planning programme remains Major and has not changed from the business case. While strong mitigation measures have been implemented, the external funding landscape has deteriorated, primarily due to unpredictable domestic financing, exacerbated by declining donor support and the termination of US funding.
The major change in the risk landscape is that of likely stock-outs and under-resourced health facilities in the year ahead, with potential impact of under-achievement of key results in 2025.
Given the immediate impact of US aid cuts on commodity supply and health worker personnel, we will initiate monthly meetings with UNFPA and the Commodity Security Coordinator MOH, to monitor progress against specific actions. We have presented our analysis of the potential impact of US aid cuts in health to the Donor Group for Health and have held two high-level meetings with GoURT and initiated discussions on a potential MoU to match fund donor investment in commodities to domestic financing (see section C, Output 3).
To further address these risks at a policy level, the programme intensified advocacy through key platforms to push for increased government funding and transparency in RH commodity expenditure tracking. The SUFP Programme Officer is part of a task force working on a revised mobilisation strategy for commodities security along with implementing partners and MOH.
We are also enhancing our facility support to improve the coordination and capacity-building of health workers, including the management of targeted re-supply efforts of key commodities to prevent stock outs where possible. In 2025, our IPs will be authorised to procure buffer stock which they can use in the event a facility they are working in on any given day does not have sufficient stock.
Additionally, through support from the UK-funded Total Market Approach initiatives, we are accelerating the government’s efforts to engage the private sector in commodity procurement and supply. Supply chain weaknesses, particularly inefficiencies in the Electronic Logistics Management Information System (ELMIS), have affected stock visibility and data reliability, although we understand this is an area the government has already stepped in to fund.
We consider these mitigation measures to adequately manage the risk to within appetite although we will continue to report to Head of Department for their oversight and advice.
FCDO maintains zero tolerance for fraud and safeguarding violations, with these issues remaining a standing agenda item for quarterly risk discussions. Over the review period, there has been notable improvement in reporting on fraud and safeguarding cases. We had four cases which were successfully managed, with three cases closed and one case about to be closed. This has contributed to strengthened partner systems and enhanced compliance measures. Lessons learned from these cases have informed better risk management practices and institutional resilience among implementing partners.
Given the continued uncertainty surrounding ODA budget reductions (from 0.5% to 0.3%), the risk will remain Major, as funding constraints could impact service delivery and programme sustainability.
F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.
The programme is implemented by MSI Reproductive Choices, Engender Health, and UNFPA. MSI and Engender Health operate under commercial contracts, which include partial or full payment by results, while UNFPA operates under a contribution agreement. MSI and Engender Health have agreements with downstream partners for specific aspects of service delivery. The programme maintains a proactive approach to risk management, with regular updates to delivery chain risk mapping and quarterly risk discussions. Partners consistently identify potential risks and mitigation measures, facilitating robust programme risk management.
All programme performance reports were submitted on time and met the required quality standards, providing comprehensive insights into programme progress. Budget forecasting accuracy has remained strong, with partners demonstrating improvements in financial planning and management. Audit reports were received on time for this Annual Review, with all organisations receiving clean audit opinions. Financial and asset spot checks were conducted during the review period, with positive improvements noted in asset management for both partners (MSI and Engender Health). However, challenges persist regarding the timely disposition of assets, which has delayed the reallocation of funds for programme use. Recommendations have been made to MSI to address this issue and ensure greater efficiency. Additionally, due diligence for UNFPA was conducted and completed, with recommendations being tracked and addressed to ensure compliance with FCDO requirements.
Following the programme’s time and cost extension, all necessary contract amendments were successfully completed with the support of the commercial lead. MSI and Engender Health’s contracts are now extended to September 2026. The MoU amendment with UNFPA has also been finalised, aligning the programme’s revised end date to September 2026. The commercial approach remains focused on delivering value for money by leveraging lessons learned over the past five years and embedding best practices and innovation into the remaining implementation period.

To strengthen sustainability, the programme has undergone a Logframe revision, supported by the results adviser, to refine output and outcome indicators—making them more realistic, comprehensive, and aligned with long-term impact goals. Results reporting against this revised Logframe will commence in January 2025.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
Throughout the review period, monitoring and evaluation (M&E) activities were conducted at multiple levels to assess programme progress, enhance learning, and inform decision-making. These activities included structured partner engagements, field visits and beneficiary consultation (see Annex A). The logframe was revised, with additional indicators added to better track the programme’s influence on longer term capacity and overall family planning provision in focus areas, in addition to a continued focus on effective, direct service provision.
Quarterly joint meetings with SUFP IPs facilitated cross-learning and coordination, ensuring the programme collectively delivered on its outcomes while strengthening sustainability pathways. Building on this, two joint quarterly meetings were held this year, including the bi-annual and annual meetings, providing additional opportunities for strategic alignment. Individual partner quarterly review meetings enabled in-depth discussions on implementation progress, challenges, and emerging lessons.
Field monitoring visits were conducted in Morogoro in collaboration with Engender Health, where programme performance was assessed through service delivery, beneficiary feedback, and in-depth interviews with government officials and healthcare providers on system strengthening. The Annual Review took place in Mtwara Region and Kibaha (Pwani Region), selected based on historically lower modern contraceptive prevalence rates (MCPR) in Mtwara and the absence of prior monitoring visits in Kibaha. The review assessed EH and MSI service delivery models, sustainability mechanisms, and overall impact. A focused review of UNFPA’s support for supply chain management was conducted through key informant discussions with officials from the Medical Stores Department (MSD) and the Ministry of Health. The review highlighted the need to increase government financing and strengthen the total market approach to ensure contraceptive availability and sustainability.
A structured focus group discussion with youth and women provided direct beneficiary insights. Participants reported increased awareness and service accessibility, reductions in unintended pregnancies, and improvements in postpartum family planning. Beneficiaries appreciated that family planning methods were provided at no cost. However, persistent barriers were identified, including long waiting times, limited contraceptive options for men, and misconceptions about modern contraceptive methods. Youth participants recommended leveraging technology and media, along with tailored outreach for higher learning institutions. Women emphasized the need for stronger stakeholder engagement, including training religious and community leaders and increasing male involvement through targeted awareness campaigns. These insights inform programme strategies for improved service delivery and sustainability.

Learning & Advocacy

Over the past year, the programme has actively captured and shared lessons through high-level engagements, technical presentations, and documentation of best practices. The programme through its implementing partners submitted 11 abstracts across three major conferences, Tanzania Health Summit, International Primary Health Care Conference, and the Global Health Practitioner Conference, securing eight oral presentations and a technical roundtable discussion. These platforms enabled the programme to showcase key achievements and innovations in family planning service delivery. The programme also documented its successes through technical briefs and success stories, highlighting impactful interventions such as provider training, community health worker engagement, and peer educator initiatives. A notable forum, Transforming the Health System for Inclusive SRH Services in Tanzania: The Case of PWDs, further contributed to national dialogue on inclusive healthcare.
Key lessons emerging from programme implementation include the sustained improvements in Zanzibar’s project performance, affirming the effectiveness of previous interventions. The programme's strategies for reaching new family planning clients, particularly youth, continue to yield positive results. Additionally, engagement with interministerial stakeholders has been instrumental in advancing the agenda of integrating Comprehensive Health Education (CHE) into pre-service training, marking a significant milestone in strengthening future healthcare workforce capacity. Participation in national forums has further proven to be a valuable advocacy tool, with the integration of PWD-inclusive services demonstrating tangible progress in ensuring equitable healthcare access.
Table of formal studies commissioned and completed in the year and their findings:

Study	Findings
MSI & NIMR study on the use, accessibility and challenges of Emergency Contraceptives (EC) in Tanzania.	Due to concerns raised by parliamentarians on a perceived excessive use of ECs, Ministry of Health was considering restricting ECs use in private pharmacies. The study corrected this assumption in finding low use of ECs in communities and health workers due to stigma, limited availability and inconsistent guidelines. NIMR presented the findings at the Tanzania Health Summit and to the Ministry of Health to strengthen guidance and improve the administration of EC use.
IRCHK & DAMAX ‘Understanding the Drivers of Low Modern Contraceptive Prevalence Uptake in Tanzania’	Age, wealth, and location continue to influence contraceptive uptake, with adolescent girls having the lowest use and women in the lowest wealth quintile. Low levels of government commitment for FP and inadequate disbursement, coupled with poor coordination of vertical programmes, may have resulted in stagnating MCP rate over the years. The study highlights inefficiencies and inconsistent financing of key activities (particularly in demand creation and outreach) which is leading to low MCP uptake in underserved populations. To address these challenges, there is a pressing need for the Tanzanian government to increase its domestic funding for FP, improve coordination of remaining partners, and enhance transparency and accountability in budget tracking to ensure long-term sustainability and effectiveness of resources in health. Findings were disseminated through the Family Planning Technical Working Group, informing ongoing policy and programmatic decisions.

Date of last narrative financial report	EH - 31/12/2024. / MSI - 31/12/2024 / UNFPA 31/12/2024	Date of last audited annual statement	EH - 30/06/2024. / MSI - 31/12/2024 / UNFPA - 01/05/2019

Annex A - Beneficiary Feedback

To:	From: / CC: Division: Human Development Team / Date: 11th February 2025

BACK TO OFFICE REPORT
Background
As part of our annual review process, on 24th January 2025, at Dar es Salaam Region, we conducted a Monitoring and Evaluation (M&E) exercise through Focus Group Discussions (FGDs) with programme beneficiaries, specifically women and youth, to gain deeper insights into their experiences with family planning services. The primary objective of these discussions was to understand how the programme has benefited them, identify challenges in access and quality of services, and explore areas for strengthening the programme.

The discussion was guided by questions covering the following key areas:
Changes and improvements in family planning services based on beneficiary feedback.
Quality of services, including availability of methods, information, and support.
Timeliness of service provision and the availability of supplies.
Impact of family planning services on individuals, families, and the community.
Community involvement in improving access to family planning.
Stakeholder engagement, particularly the role of different players in strengthening the programme.
.
Key Findings/Observations
Improvements and Positive Impact
Increased awareness and education: More young people and women are now receiving education on family planning, which was previously limited. Young people are no longer stigmatized for seeking services.
Male involvement has improved: More men are showing interest in family planning, especially after seeing public awareness campaigns.
Beneficiaries appreciated that family planning methods, including condoms, injectables, and implants, are provided at no cost.
Reduction in unintended pregnancies: Many women and youth reported that access to family planning has helped reduce teenage pregnancies and improve economic stability in families.
Improved service delivery: The process of receiving family planning services at health facilities has become smoother and more structured.

Challenges Identified
Long waiting times at health facilities: Many beneficiaries reported that service delays discourage them from seeking family planning services, which is due to Shortage of service providers: In some clinics, the same healthcare workers handle multiple services (e.g., immunization and family planning), leading to long queues.
Limited contraceptive choices for men: Men expressed interest in more family planning options beyond condoms.
Myths and misconceptions: Misconceptions about side effects (e.g., weight gain, infertility) still prevent many from using certain family planning methods.
Limited outreach and engagement: Some groups, such as university students and men, are not well targeted in family planning education.
Lack of community-based services: Many women and youth suggested that door-to-door services or community-based health workers should be introduced to reach those who do not visit health facilities.
Uncertainty about programme sustainability: Some beneficiaries expressed concerns about whether family planning services would continue to be free in the future, especially if donor funding ends.
Recommendations and Programme Strengthening Strategies
Service Delivery Improvements
Ensure a consistent supply of all contraceptive methods, particularly condoms, which some participants reported as being scarce.
Strengthen community-based education through door-to-door outreach to address myths and misconceptions about family planning.
Increase male engagement by conducting targeted awareness campaigns for men, possibly in collaboration with local leaders or workplaces.
Expand outreach to university students by introducing family planning education in universities by exploring innovative setting.

Leveraging Technology and Media
Use social media and influencers to reach young people with family planning content on platforms like Facebook, Instagram, and WhatsApp.
Develop a toll-free hotline where beneficiaries can call for family planning information and referrals.
Enhance media presence by incorporating family planning education into popular TV and radio programs.

Strengthening Stakeholder Involvement
Train religious and community leaders on family planning so they can help educate their followers.
Engage youth as family planning ambassadors to spread information within their communities.
Advocate for family planning services to be covered under health insurance schemes, ensuring sustainability beyond donor support.