3 July 2025

Dear Faisal Yousaf, / Amendment to the Contribution Arrangement for the Partnership for Learning for all in Nigeria (PLANE) Programme – Education in Emergencies Project

Project Name:	Partnership for Learning for all in Nigeria (PLANE) –	Education in Emergencies (EiE) Programme

FCDO Project Number:	300416-110

UNICEF Grant Number:	SM210943

I refer to the Contribution Arrangement for the above-mentioned project, signed by the Foreign, Commonwealth & Development Office (FCDO) and UNICEF on 16th December 2017, as well as the subsequent Amendment No. 1 of March 2023.

Following recent discussions regarding the project’s budget, scope, and the revised disbursement schedule for PLANE Education in Emergencies (EiE) programme and given changes in the financial situation and programme priorities of the UK government, FCDO proposes the following amendments to the existing arrangement.

That the budget ceiling for the contribution arrangement under the PLANE EiE project be revised downward from £16,000,000 to £13,882,543.63

It is proposed that the end date of PLANE EiE project, as stated in paragraph 1(b) of the initial Contribution Arrangement, be amended from 31 December 2025 to 31 December 2027

Subsequently that the disbursement schedule on paragraph 2 of Amendment No.1 of March 2023 be updated as follows:

	Payment due date	Amount (GBP)
1	Upon signature of agreement	2,500,000
2	April 2022	2,322,448
3	October 2022	500,000
4	April 2023	2,000,000
5	November 2023	872,441
6	April 2024	2,000,000
7	Feb 2025	187,654.63
8	July 2025	1,500,000
9	March/April 2026	500,000
10	December 2026	1,500,000

This letter of amendment will place on record our common understanding of the above changes and will come into operation on the date you sign your confirmation below. This note will be known as Amendment No.2 of July 2025.

Please sign both copies of this document; return one to me and retain the other for your own records.

Signed on behalf of FCDO:
Name:	Susan Mshana
Position:	pp Development Director
Address/Contact Details:	British High Commission / Plot 1137, Diplomatic Drive / Central Business District / Abuja
Date:	09 July 2025

Signed on behalf of the Partner:
Name:	Faisal Yousaf
Position:	Senior Advisor, Public Partnership Division
Address/Contact Details:	UNICEF / Public Partnerships Division / UNICEF House, 3 United Nations Plaza, New York / NY 10017 / United States
Date: