## Annual Review

Title: Partnership for Learning for All in Nigerian Education (PLANE)
Programme Value £ (full life): £170 million		Review date: December 2025
Programme Code: 300416	AMP start date: 26/03/2019	AMP end date: 31/08/2028

Summary of Programme Performance
Year	2019	2020	2021	2022	2023	2024	2025
Overall Output Score	A	B	A	A	A	A+	A+
Overall programme risk rating	Major	Major	Major	Major	Major	Major	Major

DevTracker Link to Business Case:	PLANE Business Case
DevTracker Link to results framework:	PLANE Portfolio Results Framework

A. SUMMARY AND OVERVIEW
Description of programme

Nigeria faces a learning crisis. Literacy rates are low, and lower still for marginalised children. It is thought to have the largest number of primary-aged out of school children (OOSC) in the world. Public investment in education is insufficient, and millions of children are failing to learn the basics. Improving participation of marginalised children in schooling and ensuring children learn when in school are critical to building human capital and driving inclusive growth.

Partnership for Learning for All in Nigerian Education (PLANE) is FCDO Nigeria’s flagship basic education programme, agreed in 2018 to invest up to £170 million over nine years (2019-28) to improve foundational skills (reading, writing and mathematics) for children. It works at the federal level, and in Kano, Kaduna Jigawa, Borno and Yobe states. In the last year, PLANE has continued its shift away from direct service delivery and towards a partnership approach that emphasises technical assistance and policy influence. PLANE is an integral component of the Nigeria-UK Strategic Partnership signed by the Foreign Secretary in November 2024, which commits the UK and Nigeria to work together to support human capital development.

PLANE aligns with Government of Nigeria priorities and is tailored to support the Nigerian government’s requests from UK at federal and state level – as part of the UK’s modern development partnership with Nigeria. PLANE is key to improving access to quality education and foundational learning for marginalised children, including girls. It is the UK’s main vehicle to support education reform priorities at federal and state level, taking a ‘thinking and working politically approach’ to harness high potential policy windows and provide targeted TA to catalyse change. The focus of these efforts has been to provide support to the priorities identified by the Federal Minister of Education, Dr Tunji Alausa, as part of the Nigeria Education Sector Reform Initiative (NESRI) agenda. PLANE is supporting progress toward Nigeria achieving self-reliance in education – critical to building human capital to drive growth.

1. PLANE was designed to balance evidence-based classroom and child-level interventions with higher risk / higher return system-level interventions – aimed at catalysing lasting change in the education sector. It delivers its objectives through three windows and an FCDO managed component:
  1. Window One (W1, commercial contract with DAI as the lead consortium partner): ‘Getting the Foundations right - a systems approach’. More focused teaching and learning, improved governance (for state and non-state education delivery) and increased use of data and evidence through a large technical assistance (TA) programme to support schools and improve systems, delivered through a contracted consortium.
  2. Window Two (W2, Memorandum of Understanding (MoU) with UNICEF): ‘Education in Emergencies (EiE)’. Support to help marginalised children affected by conflict learn foundational skills and support for recovery of systems, delivered through partnerships with UNICEF and NGOs.
  3. Window Three (W3, Accountable Grant (AG) with Save the Children): ‘Community Support to Learning (CStL)’. Improving inclusion and learning for marginalised children through an accountable grant to a consortium of non-governmental organisations.
  4. FCDO managed component (via a commercial contract with Ecorys) ‘FCDO Nigeria Human Development Evaluation, Learning and Verification Service (DELVe). Support to implementation of the programme such as third-party monitoring, independent research, evaluation, reviews, audits and programme funded advisory support.
  5. An additional EdTech AG has been initiated in July 2025, to expand TA and support the effective introduction of digital and AI in basic education, following a Ministerial request. It is implemented by the FCDO led EdTech Hub and managed by a consortium led by R4D.

1. PLANE works synergistically with FCDO advisory expertise and wider levers to deliver education outcomes in Nigeria. It is aligned to wider development partner support and seeks to influence additional reform through others, which is vital given the scale of need in Nigeria. Over the period covered by this annual review, the synergies include:
  1. FCDO Nigeria’s education expertise, including the direct engagement of FCDO education advisers with government and development partners. This provides direct advisory support to government on key priorities (e.g. where this would have greater value / impact than deploying PLANE), and deeper understanding of international evidence, context and opportunities, allowing better prioritisation of PLANE resources.
  2. Education Development Partners Group (EDPG), which is chaired by FCDO and brings together development partners working in education. This provides a forum for discussing synergistic working between FCDO education experts and other development partner staff, and between PLANE and other initiatives.
  3. Mutual Accountability Frameworks (MAFs), FCDO Nigeria’s cross-cutting partnerships with Governors of Kano, Kaduna and Jigawa states on development programming. This provides checkpoints to ensure alignment with state priorities, and to leverage progress on Governors’ own education reform priorities that match support through PLANE – e.g. mass teacher recruitment onto state payrolls following training provided by PLANE.
  4. FCDO bilateral governance programmes, such as the Partnership for Agile Governance and Climate Engagement (PACE) programme, which work in tandem with PLANE to inform reforms that will improve education outcomes - for example, federal financing reforms.
  5. British Council, including alignment on advocacy, event organisation and the Education World Forum
  6. Department for Business and Trade, which works in a complementary fashion on higher education partnerships and Transnational Education, drawing on PLANE connections and expertise.
  7. Centrally Managed Programmes (CMP), such as the Education Research in Conflict and Protracted Crisis (ERICC) programme, the What Works Hub for Global Education (WWHGE) and the Scaling Access and Learning in Education (SCALE) programme, which have contributed expertise and support in a range of areas. The SCALE CMP, in conjunction with the FCDO advisory team, have developed a complementary innovative partnership investment in two other NW Nigerian States on accelerated basic education for out of school children, using PLANE evidence and best practice. If funding is allocated, this will expand collaboration between PLANE and SCALE in the coming reporting period.

This annual review (AR) period is aligned to the third implementation school year under PLANE, September 2024 to August 2025. The last AR covered September 2023 to August 2024. This review provides insights up to December 2025, including the announced abolition of the National Language Policy in November 2025 and announcements of major reductions in FCDO ODA resources that will impact the remaining implementation phase of PLANE (see below).

Changes in the operating context

Political: The Federal Minister of Education – Dr Tunji Alausa – and Minister of State for Education – Prof. Suwaiba Ahmad – were appointed in October 2024, shortly before the start of this annual review period. They have focused on advancing major reforms at pace through the Nigeria Education Sector Renewal Initiative (NESRI), as well as initiating an Education Sector Wide Approach (E-SWAp). Notable developments include the appointment of Aisha Garba – a former World Bank expert – as Executive Secretary of the Universal Basic Education Commission (UBEC), the launch of a dedicated SWAp Office in the Federal Ministry of Education (FME) and the launch of the Nigeria Education Data Initiative (NEDI). A number of Federal level policies have been approved, including the Non-State Education Policy, the National Teacher Policy and the National Policy on the Enhancement of Almajiri Education (all with PLANE support). In November 2025, the Federal Minister announced the abolition of the National Language Policy and a major shift to English as the approved language of instruction for schools at all levels. In wider political developments, the suspension and closure of USAID early in 2025 meant that US-funded education programmes were abruptly frozen and then permanently cancelled. This has had a particular impact on the North East when combined with major reductions in US-funded humanitarian programming. The long run implications of wider cuts to funding for UN agencies and reductions in aid from a range of other partners are likely to be substantial.

Economic: Inflation rates have begun to fall since mid-2025, following the rapid increase in prices associated with the removal of fuel price subsidies and macro-economic and currency reforms in 2023. However, the benefits of reforms are not yet being felt in terms of increased education spending, and the cost-of-living crisis has continued with disruptive knock-on effects for communities and teachers. Food insecurity remains high in the North, and the federal government school feeding initiative remains frozen, following fiduciary concerns flagged in 2024.

Security: Trends from the past annual review period have largely continued. The North East zone remains extremely fragile – particularly with the reductions in humanitarian assistance – and insecurity and banditry have continued to spread into the North West zone, impacting communities, schools and the operating environment for partners. In November 2025, there were two major instances of school kidnapping - 215 schoolchildren and 12 teachers were abducted from a school in Niger State, following an attack on a school in Kebbi State where 25 schoolgirls were abducted and the vice-principal was killed. These attacks contributed to a global outcry and led to the early closure of large numbers of boarding schools across the country shortly after which were re-opened in January 2026.

Education: Nigeria continues to face a learning crisis, with one of the highest numbers of out of school children (OOSC) globally. No new authoritative population or learning data sources are available, results from the UBEC NALABE 2023 national learning assessment have not been released and a population census continues to be delayed, despite major investments. UNESCO analysis from 2022 gave an estimate of 20 million OOSC aged 6-18. Many children that are in school fail to learn the basics. A UNICEF 2021 sample survey found that only 26.8% children aged 7-14 years were able to demonstrate foundational reading skills, the figure is as low as 9.5% in the North West compared to 55.6% in the South East. The education sector is severely underfunded, but increasing funding alone will be insufficient. The timely release of allocated funds and their efficient use is critical.

Changes to UK Official Development Assistance

The reduction in ODA has resulted in key changes to this programme. This Annual Review reflects that the programme has had to refocus resources and so will deliver against a new plan with new results targets. As a result, the findings of this Annual Review reflect on a programme in transition.

About changes to UK ODA
- At this time of profound change, with conflicts overseas undermining security and prosperity, the UK Prime Minister has taken the difficult decision to increase spending on defence to 2.5% of GDP from 2027, funded by reducing the UK’s Official Development Assistance (ODA) and reinvesting it into defence. The ODA budget will be gradually reduced to the equivalent of 0.3% of GNI by 2027, to help smooth the transition.
- The UK remains fully committed to playing a globally significant role in humanitarian aid and development. The transition to spending 0.3% of GNI on ODA will require significant shifts, building on those already underway as the government implements its modernised approach to development, which centres on establishing long-term partnerships based on mutual interests and respect.
- ODA allocations and the impact on programmes are being worked through based on various factors, including impact assessments. We will be taking a rigorous approach to ensure all ODA delivers value for money and maximises the impact of our work to best support the people it benefits, including those in humanitarian crises.
- We remain committed to spending 0.7% of GNI on ODA when the fiscal circumstances allow.

Summary supporting narrative for the overall score in this review

Overall, PLANE has continued to make strong progress across output areas over the last annual review year and has moderately exceeded expectations – leading to a score of A+. The score is driven by continued high performance against Outputs 1 and 2 by the DAI consortium (Window 1), as well as against Output 5 by UNICEF (Window 2). In contrast, Output 6 – led by Save the Children (Window 3) moderately underperformed, partly due to the decision to cancel the final enrolment due to budget uncertainties and the decision to change the focus of the component to align with the Government of Nigeria’s emerging priorities on non-formal education.

Output	Weighting [1]	Score
Window 1 – Output 1: Evidence based teaching and learning approaches and materials in use, in better managed schools and colleges	39%	A+
Window 1- Output 2: Improved planning, personnel management, public financial management practices, to deliver foundational skills	24%	A+
Window 1 – Output 3: Improved management & performance of non-state sector in delivering foundational skills	8%	A
Window 1 – Output 4: Effective generation, communication & use of evidence informs citizen engagement & service delivery	8%	A
Window 2 – Output 5: Effective approaches to teaching and learning and more resilient systems for children affected by conflict	13%	A+
Window 3: Output 6: Communities support children’s participation & learning, including marginalised groups	8%	B
[1] Weightings are based on the financing ratio between the 3 operational windows, and the split across the four, Window 1 Outputs, as agreed in the approved portfolio logical framework.

A key sign of success over the last review year has been the growing adoption and scale up of the PLANE approach by State Governments, which has meant that learning support has been delivered indirectly to a further 1,407 schools (370 Kano, 1037 Jigawa), 2,351 teachers, and 490,974 learners. Further scaling of the approach is also anticipated through the World Bank HOPE Education programme[2], which will be a major source of funding for the Nigeria system in coming years. PLANE has been engaging closely with the programme and heavily involved in work on the design of the pedagogical packages it will fund.
[2] The World Bank–supported HOPE Education programme in Nigeria—formally known as HOPE for Quality Basic Education for All (HOPE‑EDU)—is a major national reform initiative designed to expand access, improve learning outcomes, and strengthen education systems across the country. The programme is backed by approximately $552 million in financing from the World Bank and the Global Partnership for Education and is structured to reach 29 million children, empower 500,000 teachers, and upgrade over 65,000 public schools and 10,000 non‑formal learning centres nationwide. It prioritises foundational literacy and numeracy, digital innovation, teacher development, and reducing the number of out‑of‑school children.

Programme interventions are also demonstrating strong, but varied, evidence of improving learning outcomes. This year, results for literacy under Window 1 interventions surpassed the target, with 67.9% of Primary 4 children achieving Foundational Literacy (defined as reading at least six words per minute (w.p.m.) on an Oral Reading Fluency test). 60% of Primary 4 children exceeded 10 w.p.m. in the test. Similarly, results for numeracy also surpassed the target, with 84% of P4 pupils in the sample of Window One Foundational Learning schools achieving Foundational Numeracy[3]. Window Three also reported strong progress with 50% of graduates from community learning interventions achieving both foundational literacy and numeracy. Progress for Window Two was more varied depending on the learning intervention, with foundational literacy being achieved for 43 per cent of children in Teaching at the Right Level (TaRL) classes, 26 per cent in Kanuri Arithmetic and Reading Arithmetic Intervention (KARI), 45 percent in Accelerated Basic Education Programme (ABEP) classes. Similar improvement was also identified in numeracy skills.
[3] Precise, internationally comparable, benchmarks of minimum proficiency levels of literacy and numeracy are difficult to apply across interventions and assessment methods. Students in P4 (primary grade 4) are typically 10 years old, that aligns to the global ‘learning poverty’ benchmark (inability to read a simple sentence).

Major challenges on access, quality service delivery and learning outcomes persist. Despite PLANE achieving strong progress in implementation and working in partnership with Federal and State governments, there are persistent gaps in education access and quality. Learning outcomes have improved in PLANE schools but remain low in the system overall. Similarly, W2 and W3 have noted successes in mainstreaming, but all estimates of the numbers of out of school children continue to be high and attendance rates of students and teachers have been impacted by inflation and food insecurity. Flooding exacerbated by climate change has contributed to school closures and the security situation is increasingly uncertain, with two high profile school kidnappings occurring at the end of 2025 that led to protracted closure. Classroom observations conducted for the annual review also reinforce the continued critical lack of teaching and learning materials in schools. The delivery of the PLANE learning packages through weak government systems means that teacher-student contact time is too low and large class sizes inhibit individual support. Strengthening the state system therefore remains a key priority and prerequisite to achieve sustained improvements in education quality at scale and keep pace with population growth, that remains high in northern Nigeria, despite a slight downward trend.

Major lessons and recommendations for the year ahead

Recommendation 1: PLANE Window 1 activities will need to be substantially reviewed and adjusted to reflect tighter resource constraints and a more rapid phasing out of direct service delivery and reducing its operational footprint in NW states in 2026. Decisions should be made based on a clear set of criteria to ensure that activities are: (i) well-integrated and focused, working with the Government of Nigeria’s NESRI and SWAp objectives to maximise impact; (ii) aligned with UK priorities – and supporting – the World Bank HOPE-Edu and governance programmes, but retaining flexibility to capture other opportunities; and (iii) politically & technically smart – ensuring a focus on problem areas where there is political will and PLANE has the technical knowledge to contribute. The creation of a NW regional community of practice hub should be explored, to sustain and spread good practice built in the current 3 focal states, with potential to engage other NW States where demand exists. DAI should develop a credible plan which would be completed in consultation with FCDO by the end of April 2026, so as to adapt to the political cycles leading up to the 2027 Nigerian elections and provide sufficient time for deployment in support of the 2026/27 school year.

Recommendation 2: Education in emergencies will continue to be a core component of the PLANE portfolio. However, a major re-design of Window 2 will need to be undertaken by UNICEF given the major cuts in humanitarian ODA and domestic financing revisions and federal education reforms underway. Priorities should be to deconcentrate activities within the six focal LGAs and expand work in emergency prone areas where population displacement occurs, and school and teacher availability has been constrained. Close co-ordination with other humanitarian initiatives, in particular protection, psychosocial support and nutrition is essential to enhance impact. UNICEF should also link activities under Window 2 more closely with their own wider programming and other multilateral initiatives in northeast Nigeria to establish a regional community of practice hub with other NE State education leaders, in order to widen and enhance the Federal education sector wide approach reform agenda. Priorities should be aligned with those defined in the HOPE-Edu results framework and PLANE’s Window 1 work in the northwest region. This should be completed in full consultation with FCDO by mid-2026, to provide sufficient time for deployment in the 2026/27 school year.

Recommendation 3: Reprioritisation will need to take place at the PLANE portfolio level to reflect a more limited resource envelope and lessons learned through implementation. Accordingly, PLANE Window 3 should close at the end of the current agreement in September 2026, given limited potential for scalable impact of activities unsupported by government. Similarly, DELVe should be paused to allow resources to be reallocated to priority activities with the potential to re-activate for the final evaluation if needed. Alternative evidence and knowledge sharing offers should also be pursued, such as the potential to commission evaluations through other means, drawing on centrally managed FCDO research offers, or using W1’s internal resources.

Recommendation 4: The FCDO programme team will lead a process of revising the theory of change and log frame (including output and outcome indicators) to reflect the findings of the midline evaluation and wider shifts in programme priorities and delivery mechanisms. This will include closure of completed targets and the addition of stretch targets in a number of areas to reflect higher than anticipated performance. These revisions should be completed and signed off by the end of June 2026 to be in place before the 2026 annual review
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

No major changes to the PLANE business case theory of change (ToC) took place during this annual review period. However, its assumptions were reviewed during the PLANE midline evaluation that was concluded during the review period. Changes will be made in the coming review year to reflect the findings and wider changes linked to decisions made in response to ODA reductions.

The current theory of change is set out below:

The Midline evaluation noted seven cross-cutting assumptions that underpin the PLANE portfolio theory of change. The evaluation assessed the extent to which these assumptions have held and remained since 2023, applying a three-point RAG scale (see table on following page). It found that both of the two programme assumptions - FCDO funding, and the programme enabling effective linkages between supply and demand - are partially held but under strain. FCDO funding is under pressure and reducing going forwards. Whilst supply and demand for education have both improved, PLANE’s non-involvement (by design) in infrastructure improvements creates a gap in quality supply.

Table: Summative review of ToC Assumptions
Level of ToC	Assumption	Rating
Programme assumption	Availability and reliability of FCDO funding	Partially held
	Programme enabling effective linkages between supply and demand	Partially held
External Assumptions	Insecurity and conflict do not restrict programme delivery and access	Partially held
	Programme and education delivery is not hindered by Covid-19	Mostly held
	Federal and state governments continued political will to prioritise education, poverty, gender and learning needs of marginalised children	Mostly held
	Wider political, macro-economic and security conditions remain stable, including election stability	Partially held
	Multiple indicator core survey (MICS) and Annual School Census (ASC) education data sources are available on time and reasonably accurate	Barely held

Of the five external assumptions, the evaluation finds that two are mostly held with minimal/manageable risk; two are partially held (as above); and one is barely held. The lack of hindrance to programme and education delivery caused by COVID-19 means that this assumption has held and remains a minimal risk; there also remains strong political will for access to quality basic education at federal and state levels, with several government agencies responsible for and prioritising girls’ education and marginalised children’s learning (such as Almajiri).

Assumptions of manageable insecurity and conflict, and political and economic stability are partially held, with some strain and risks associated with these assumptions that do and may continue to impinge upon PLANE and the wider education system. Insecurity periodically disrupts teaching, learning and supervision across northern Nigeria; and can reproduce caregivers’ fear and reluctance about schooling. While economic and political conditions have not hindered education delivery completely, they have had negative effects: altered federal education reform agendas and priorities since 2023; high inflation, fuel and food poverty, all present risks to this assumption.

One assumption has barely held and is a significant risk to PLANE: the availability of accurate education data. Many datasets at federal and state level are still not available for the last two academic years and previous data have inconsistencies and are unreliable. This is a major hindrance to effective education planning and delivery. Whilst demographic data is unreliable, all recent proxy estimates suggest that despite moderate declines in fertility rates there will be sustained and rapid population growth that will in turn lead to rising numbers of school age children. This is a strong driver and contributor to risks on poverty, climate, conflict and inadequate financing. The ToC updates should consider demography more explicitly, as it makes SDG-4 education achievement by 2030 an impossibility in Nigeria, overall.

These findings align with the points raised in the previous section regarding the changing context in which PLANE operates and demonstrates the continuing challenges facing the programme in terms of achieving improvements in education outcomes.

Updates to the PLANE theory of change in the coming year will incorporate the reassessment of the underpinning assumptions set out here, as well as changes to the programme structure, funding and activities that will be undertaken in line with reductions in ODA allocations and the continued shift away from direct service delivery (except in Education in Emergencies contexts in the NE) and towards a focus on partnership and technical assistance. This implies a less direct causality from outputs to outcomes and impact indicators, as PLANE ceases to directly fund education delivery. However, it is important to note that no changes will be made to impact and outcome statements.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

As noted in Section A, PLANE has demonstrated largely strong to satisfactory progress against annual targets, with the exception being moderate underperformance against Output 6. This conclusion is supported by data shared against the log-frame by the implementing partners, as well as feedback from stakeholders collected at all levels of the system during this annual review.

Progress continues to be made against the intermediate outcomes of the programme, with the programme exceeding targets for volume of children reached directly by the PLANE package, as well as State governments beginning to successfully implement the package at scale. There is also growing evidence of strengthened learning outcomes, albeit with some variations across the different modalities of PLANE. This progress is particularly notable given the continued challenges noted in terms of delivery through weak state systems, persistent issues with inflation and livelihoods, as well as rising insecurity. The table below summarises outcome indicators and performance at the approximate mid-point of the programme. Foundational learning outcomes are on track, or better in targeted schools, but a shift in emphasis to overall statewide performance will be taken in PLANE’s outer years. Data constraints limit reporting on primary completion rates, but data to track changes from baseline is expected in late 2026. More problematic is tracking trends on domestic financing on education. States report impressively high budget shares allocated on education, but utilisation data is fragmented and inconsistent.
Table: Progress on Log frame Outcomes
Outcome indicator	Milestone (August 2025)	Achieved	Rating
Increase in % of learners in targeted schools achieve foundational competencies in literacy and numeracy	50% of P4 learners - and those who have completed community based interventions - have basic Hausa literacy, and 50% of them have basic numeracy skills (W1, W2 and W3)	W1:67.9% of P4 children rank at “foundational level” (level 3) in literacy / (M 67.8%, F 68.1%) / 84% of P4 children had foundational level skills in mathematics (sample based, assessment) / (M 82.5%, F 85.7%) / W2 and W3 more mixed: / Foundational literacy in local language – TaRL 43%, KARI 26%, ABEP 42%, LB 20% / Foundation literacy in English – TaRL 37%, CuC 24% / Foundational numeracy – TaRL 44%, KARI 75%, ABEP 42%, NB 66%	On track, although focus up to midline on Hausa, not English
Primary education completion rate	States Average: 59.27%	N/A	Awaiting data from 2026 MICS to see State level trends, from 2021 baseline
State budget allocated and utilised for education	States Average Utilisation: 65.90%	States Average Utilisation: 72.81%	Unreliable and inconsistent data means in practice very difficult to track tends

The potential for sustained impact has also improved. There are numerous examples of PLANE positively engaging with State governments to shape and strengthen policies, but also increasingly examples from the Federal level that should lead to impact at a greater scale. PLANE’s technical engagement with the World Bank HOPE-Edu programme is also likely to result in a significant expansion of the PLANE package, given the close alignment between the design of the pedagogy and teaching and learning materials with the requirements of the World Bank programme. Continuing this high-level engagement, alongside technical support to States to take advantage of World Bank funds, is a significant priority for the coming year as part of the continued shift away from ‘direct delivery’ to an emphasis on technical assistance and policy-focused influencing.

PLANE continues to take an opportunistic approach to promoting gender equality and inclusion, for example through supporting Kano State Gender Policy, training gender desk officers on monitoring School-Related Gender-Based Violence (SRGBV), developing GEDSI Minimum Standards to guide inclusive teaching, learning, and infrastructure, and engaging with communities through Windows 2 and 3 to shift narratives on gender and disability.

As noted above and in Section A, Output 6 – delivered by Save the Children under Window 3 – is the only area in which the programme is off track against the log frame. The planned closure of Window 3 in September 2026 and the ongoing shift in delivery approach during the next programme year will address this to some extent. However, this will form only one part of a larger reorganisation of PLANE to prioritise following significant reductions in ODA allocations. Revisions to the theory of change and log frame (including output and outcome indicators) will be necessary to reflect shift in priorities and delivery mechanisms.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

1. PLANE has now demonstrated strong performance against annual targets for over two years of full-scale operational activity and has begun to make good progress on outcome level indicators. The programme has demonstrated that it can have a significant role in shaping education policy and reforms at both a State and Federal level, and the PLANE package of interventions and learning materials is now being scaled up by several State Governments. The programme is therefore well positioned to make a successful transition away from direct delivery in non-emergency contexts and to have a significant impact through technical assistance and support to policy reforms, as well as through influence on the World Bank HOPE-Edu programme and states’ ability to draw on its resources.
2. Closing the programme at this stage would represent poor value for money. Allowing the programme to continue – with adjustments to reflect the findings of the midline performance evaluation and shifts in the budget profile – will allow the programme to build on the reputation and networks that it has established at both the Federal and State level, and to continue to shape education policy, reforms and priorities during the crucial initial stages of the HOPE-Edu programme and the pre-election period ahead of polls in 2027.

As FCDO Nigeria’s flagship bilateral education programme, PLANE continues to be a key component of the Country Business Plan, supporting Nigeria to accelerate its human development and address its ongoing humanitarian crisis. It also underpins wider shared UK Nigeria objectives on security and growth, noting universal education’s underpinning role in all nations’ prosperity and stability. It supports wider UK education investments and initiatives (e.g. the Global Partnership for Education financing to HOPE-Edu). PLANE technical assistance and support is also well-valued by States and the Federal Ministry of Education, speaking to the alignment with the approach of operating through genuine partnerships and the contribution of the programme to the UK’s standing in Nigeria. Closing the programme would undermine UK credibility and diminish our standing in Nigeria, as well as limiting UK influence on the various multilateral funds and mechanisms active in Nigeria.
C. DETAILED OUTPUT SCORING

Output Title	Evidence based teaching and learning approaches, and materials in use in schools and colleges, that are better managed, more inclusive, and safer.
Output number:		1	Output Score:	A+
Impact weighting (%):		39%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of schools, teachers and learners reached by a substantive set of PLANE/State financed initiatives to improve foundational learning skills	PLANE foundational skills package reaches 2,525 schools; 11,500 teachers; and 980,000 learners Disaggregated milestone for learners: 443,900 girls; 443,900 boys; 7,000 learners with a disability	Milestone exceeded: / PLANE foundational skills package directly delivered to 2,562 schools (580 AL; 1,982 FL), (1,113 Kano; 699 Kaduna; 750 Jigawa); 12,018 teachers, and 1,400,413 learners (717,023 F, 683,390 M) / State government scale up means that the package has been delivered indirectly to a further 1,407 schools (370 Kano, 1037 Jigawa), 2,351 teachers, and 490,974 learners.
1.2 Number of in-service and pre-service teachers and lecturers demonstrating knowledge of inclusive foundational skills instruction through participation in PLANE professional development activities	11,500 teachers trained in inclusive foundational skills, with at least 50% of teachers demonstrating sufficient understanding of GESI responsive pedagogy, safeguarding and inclusive foundational skills and practices, as documented in PLANE dashboards	Milestone exceeded: / 12,018 teachers (3,442 AL; 8,576 FL), (4,026 F; 7,992 M) (5,704 Kano; 3,792 Kaduna; 2,522 Jigawa) (11,295 in-service teachers; 723 Pre-service teachers) trained. / A further 2,351 P1 teachers (854 Kano, 1,497 Jigawa) have been trained as part of state government scale-up. / PLANE supported teacher coaching showed that 82.5% of teachers demonstrate sufficient understanding of GESI responsive pedagogy, safeguarding and inclusive foundational skills and practices.
1.3 Number of Head Teachers and SBMCs demonstrating knowledge of inclusive school leadership through participation in PLANE training on effective school management	2,500 Head Teachers and SBMCs trained in inclusive school leadership and at least 20% of them demonstrate sufficient understanding of GESI responsive school management, safeguarding and inclusive foundational skills	Milestone exceeded: / 16,517 (11,396 head teachers, 5121 SBMC members) trained in school leadership. / 11,396 (8,055 Kano, 3,341 Kaduna), (1,405 F, 9,991 M) head teachers trained in inclusive school leadership and management prior to the conduct of school self-evaluation. / 5,121 SBMCs (1,382 Jigawa, 1,832 Kaduna, 1,907 Kano) members trained. / Rapid MEL assessment conducted in year 3 revealed that 39% of headteachers and SBMC members demonstrated understanding of inclusive school leadership.

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 1 is delivered by the DAI-led consortium under the PLANE contract (Window 1) and delivery against its targets is impressive. All milestones for this annual review period have been exceeded, and progress has moderately exceeded expectations (A+).

The reach of the PLANE package has continued to expand, both through direct programme action and scaling by government partners. PLANE has now reached approximately 1.4 million learners and 12,018 teachers across 2,562 schools in the three KKJ states with high-quality foundational or accelerated learning materials and support. State governments have also begun to adopt the PLANE model at scale, as evidenced by increased budget allocations and commitments to scale approaches across additional LGAs and states. This increased interest and ownership by State governments is attributed partly to the demonstration effect of PLANE’s successful direct implementation, but also the deliberate development of a robust evidence base and close relationships between the programme and state level actors. State government scale up means that the PLANE package has been delivered indirectly to an additional 490,974 learners and 2,351 teachers across 1,407 schools (370 Kano, 1037 Jigawa). The gender balance of these results has been mixed. Over half of the learners reached directly by PLANE have been girls (51.2%), but significant gender disparities persist in terms of the training of teachers (33.5% female), head teachers (12.3% female) and SBMC members (29.7% female).These skewed gender ratios are a reflection of the low proportion of women in the workforce, especially in Jigawa and Kano. PLANE has strongly promoted more recruitment of women, see Output 2.

Additional activities to support and strengthen foundational learning include the distribution of Teaching and Learning Material (TLM), the delivery of two sessions of Accelerated Learning Holiday Camps (ALHCs) to support struggling learners, and targeted initiatives to reduce material gaps. PLANE also facilitated distribution of P4 Hausa literacy and mathematics pupil books and teacher guides, alongside replenishment of P1–P3 materials.

PLANE delivered quality teacher professional development and coaching initiatives directly to 12,018 teachers, with an additional 2,351 teachers supported as part of the state-led scale up of the approach. Training appears to have been effective, with classroom observation visits conducted by PLANE as part of monitoring of the teacher coaching finding that 82.5% of trained teachers demonstrated fidelity to the training content and materials. This assessment included understanding of gender equality, disability and social inclusion (GEDSI) responsive pedagogy, safeguarding and inclusive foundational skills.

Training effectiveness targets for headteacher and School Based Management Committee members were achieved with rapid MEL assessments finding 39% of those trained demonstrated understanding of GESI-responsive school management, safeguarding, and inclusive foundational skills. The trainings were conducted in Year 1 and 2 as part of a tripartite collaboration between State Universal Basic Education Board (SUBEB), the Nigeria Union of Teachers (NUT) and PLANE that resulted in 11,396 head teachers and 5,121 SBMC members developing skills in school leadership. Cost sharing with SUBEB and the union allowed for a much larger reach than anticipated by the milestone. In the current reporting year, PLANE built upon this momentum through SSO School Support Visits and engaging with Head Teachers in the Primary 4 training to ensure they possessed the content knowledge to support teachers in foundational skills, classroom management, and safeguarding.

PLANE expanded and strengthened Community Learning Hubs (CLHs) through a combination of continued programme provision and state-government scale up. CLHs , increase education awareness and provide informal learning opportunities, especially for out-of-school children. A total of 265 CLHs are now operational (230 through PLANE’s direct support, 35 scaled up by SUBEBs) and have been attended by 105,595 learners (F:54,704, M: 50,891; of which 8,995 with disabilities). The CLHs are welcomed by communities and are playing an innovative role in the identification of out-of-school children to mainstream into formal schools. Alongside the CLHs, PLANE has led complementary community-driven education campaigns with School-Based Management Committees (SBMCs), Mothers’ Associations, and traditional leaders.

PLANE has continued to make strong progress in areas of its work plan that are not captured by the portfolio log frame. This includes ongoing provision of system strengthening support in a range of areas, such as teacher training, safeguarding and data collection & usage. School support officers (SSOs) had a two-day training refresher course led by PLANE and have visited 1,705 schools (95% of Foundational Literacy and Numeracy: FLN – schools), to provide support and monitoring. Progress is also being made on state adoption of the model. Kano SUBEB, with PLANE’s technical assistance, scaled the PLANE’s coaching model statewide in May 2025 and PLANE supported the uBoraBora research of scalable school-based coaching approaches in two schools each in Jigawa and Kaduna. At pre-service level, PLANE convened five Colleges of Education (COEs) in March 2025 and identified several joint priorities, including curriculum reform, capacity building programme, and teaching practice frameworks. These have now been integrated into Year 4 planning.

87% of schools had developed safeguarding plans and demonstrated satisfactory progress in their implementation, with 79% of schools having a Designated Safeguarding Lead (DSL). Collaboration with other programmes has also strengthened referral systems and cross-sector data sharing – expanding LGEAs participating across all three states. At the federal level, PLANE trained gender desk officers on monitoring School-Related Gender-Based Violence (SRGBV) and developed Minimum Standards to guide inclusive teaching, learning, and infrastructure.

PLANE activities also enhanced the utilisation of the school monitoring education dashboard by improving navigation, integrating school support visits and registration data, and installing tools on laptops and mobile devices for accessibility and timely decision-making. Training was provided to Education Secretaries, Planning, Research and Statistics (PRS) Directors/Heads, and Education Management Information System (EMIS) Officers to interpret and apply dashboard data in tracking attendance, fidelity of implementation, CLH activities, and safeguarding mechanisms. In addition, PLANE provided TA to stakeholders in Kano state to scale their own data system for school support visits across all schools.

PLANE has continued to develop and promote a range of high-quality teaching and learning materials and strategies, working closely with government counterparts. PLANE has developed 20 evidence-based T&L packages in collaboration with the government partners with high reported levels of satisfaction amongst both teachers and state officials. Progress has also been made on promoting inclusive TLM, with PLANE convening a range of workshops aimed at adapting P1-P2 materials into braille and field-test adapted RANA+ lessons in two special schools in Kano. PLANE has also supported a two-day English Materials Strategy Workshop with 30 participants from federal and state agencies to develop vocabulary lists, songs, games, and activities aligned with the national curriculum to aid P1–P3 learners’ transition from Hausa to English; draft Transition-to-English materials were subsequently field tested, and feedback is guiding finalisation. The Transition-to-English materials are set to be piloted in Year 4.

At the national level, PLANE is continuing to support the set-up of the World Bank HOPE-Edu programme through sustained technical engagement. PLANE contributed to the World Bank’s technical assessment of evidence-based structured pedagogy TLMs, including RANA+, USAID’s Early Grade Reading, Jolly Phonics, and PLANE’s numeracy package (the only structured numeracy resource currently available in Nigeria), evaluating them against the Global Proficiency Frameworks for Reading and Mathematics. In addition, PLANE, is collaborating and providing TA to UBEC to review structured pedagogy materials in line with the recommendations from the World Bank’s assessment workshops. These include materials developed by now-closed USAID progammes – such as Mu Karanta, Jẹ́ Ká Kàwé, Ka Anyị Gụọ, and Let’s Read – as well as FCDO/PLANE’s RANA+, Mathematics, and Transition to English, which are expected to serve as core materials for the HOPE-EDU Programme.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no significant changes to Output 1 in Year 3, other than expansion of foundations laid in Years 1 and 2, including an increasing focus on technical assistance for governments to institutionalise and scale interventions. In Year 4, this shift will accelerate with the discontinuation of all support to service delivery and a sole focus on technical assistance to enable partners to take full ownership of learning interventions, including transition to English and Braille materials, as well as to support States to leverage World Bank HOPE funding for scaling. Further changes to learning materials will be considered once further details emerge on the national policy shift towards English as the sole language of instruction.

Progress on recommendations from the previous AR (if completed),

Output 1, Recommendation 1: Adjust Output 1 ‘reach’ and associated learning outcome milestones beyond August 2025 (M4) to reflect the adjusted trajectory of foundational literacy and numeracy (FLN) programming in upper primary grades, as part of the ‘mid-term’ annual review in late 2025. Output indicator 1 to be adjusted for Year 4 to align with the evolving trajectory of foundational literacy and numeracy programming in upper primary grades

Output 1, Recommendation 2: W1 and FCDO to agree a transition-to-English package approach, specifically geared towards Hausa speakers using new PLANE materials under development and review with states. Transition-to-English materials for P1–P3 are nearly finalised, with validation was conducted in September 2025 and piloting has now begun in Year 4.

Output 1, Recommendation 3: Work with Federal agencies, State Agencies for Mass Education (SAME) and LGEA to develop local structures to support and sustain Community Learning Hubs, and to link attendees to pathways for returning to formal education or accelerated education and skills programmes. Discussion around a light-touch intervention to refer CLH attendees to education opportunities underway and DARASI pilot to reach more OOSC underway in Kano state.

Lessons learned this year and recommendations for the year ahead

The main lessons learned during Year 3 relate to the importance of engaging with government stakeholders from the outset, with the benefits of building ownership, strengthening capacity, and driving sustainability and scale-up being demonstrated by Jigawa’s FLN scale-up across 20 LGEAs and Kano’s scale-up of coaching across all 44 LGAs. Coaching and mentoring SUBEB staff especially has been pivotal in driving improved ownership, fostering innovation and facilitating a long-term shift in behaviour to support safeguarding initiatives.

Output 1, new recommendation 1: Major cuts to domestic ODA will require PLANE to accelerate its transition away from service delivery and towards a full focus on technical assistance. This will need to be reflected in both PLANE’s geographic footprint and staffing decisions. PLANE and FCDO to decide how to manage and implement these changes in early 2026 ahead of the new financial year.

Output 1, new recommendation 2: The decision of the Federal Minister of Education to cancel the National Language Policy – which promoted early primary use of mother tongue instruction has major implications for the PLANE package, given its focus on Hausa instruction. Priorities include understanding the timeline for implementation, close engagement with the World Bank to understand the implications for mother tongue instruction funded from September 2026, and the development of English-language materials in addition to the current focus on English-transition and Braille.

Output 1, new recommendation 3: Strengthen pre- and in-service teacher education systems by embedding evidence-based structured pedagogy and developing teacher coaching models with stakeholders, to scale through packages to be funded by HOPE-Edu’s results finance approach from September 2026.
Output Title	Improved planning, personnel management and public financial management practices, to deliver children’s foundational skills as part of an accessible, high quality and inclusive education system
Output number:		2	Output Score:	A+
Impact weighting (%):		24%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of evidence-informed policies and plans drafted, reviewed and endorsed to promote gender equality, safeguarding and disability inclusion in education	4 new or revised policies, plans or implementation frameworks developed and validated by stakeholders in three states to address specific education systems challenges	Milestone exceeded. / 4 new policies validated and approved / Federal Non-State School Policy / Kaduna Safety, Security and Violence Free Schools Policy / Kano State Non-State Schools Policy / Kano Gender Policy / 5 revised policies validated and approved / Kano Girls’ Education Policy / Kano Teacher Development Policy / Teachers’ Recruitment, Deployment and Replacement Policy Jigawa / National Quality Assurance Policy / Teachers’ Recruitment, Deployment and Replacement Policy Kaduna (only validated, approval awaiting)
2.2 Number of meetings held with key stakeholders to advocate for state-wide roll-out of teaching and learning resource provision	3 state-level steering committees strengthened through 6 bi-annual meetings during the year facilitated by PLANE	Milestone met. / PLANE facilitated bi-annual meetings for State Steering Committees (SSC) to influence inclusive education reforms in Jigawa, Kaduna and Kano.
2.3 Numbers trained through PLANE, demonstrating improved capabilities in transparent and responsive budget processes and public procurement	105 state staff trained on budget processes in year-3 and at least 25% of staff demonstrate sufficient knowledge	Milestone exceeded. / 343 state staff (39F) trained on budget processes and 25% of staff demonstrated positive change in knowledge (pre/post evaluation).
2.4 Number of initiatives to improve accountability mechanisms on effective monitoring	3 state-level accountability forums/mechanism functional and at least 6 initiatives launched to improve accountability education reforms	Milestone met. / 3 Accountability Forums in KKJ supported and 112 members (23 F, 89 M) (Jigawa 29, Kaduna 30, Kano 53) trained in effective monitoring and budget analyses. / 7 initiatives launched and monitored by accountability forums across the three states.
2.5 Progress on state government strategies/roadmap co-developed and co-rolled out to increase teachers (especially female)' recruitment, retention and leadership	State partners supported implementing 5% of strategic activities reflected in the teacher recruitment and deployment roadmaps to influence the recruitment of teachers	Milestone met. / Teacher Recruitment and Management Roadmap completed for Jigawa and Kano. The Kaduna State Government is in the process of approving a Consolidated Teacher Management Framework. / An analysis conducted by PLANE in Year 3 revealed that 15% of the 34 strategic actions outlined in Jigawa State’s TRDR Policy Implementation Framework are being implemented.

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 2 is delivered by the DAI-led consortium under the PLANE contract (Window 1). All milestones for this period have been met or exceeded, and progress has moderately exceeded expectations (A+). It collaboratively advances policy reforms through partnership with Federal and State governments, facilitating a strong and sustained political commitment to delivering a more inclusive and effective education system.

Strong progress has been made in promoting inclusive education through policy reforms through the validation and approval of nine education policies – four new and five revised – alongside four pieces of legislation aimed at strengthening education sector governance. Key policies approved include the Federal Non-State School Policy, Kaduna State Safety, Security and Violence-Free Schools Policy, Kano State Gender Policy, and the Teacher Development Policy. In addition, seven policies are currently in draft development, including the Jigawa State Safety, Security and Violence-Free Schools Policy, the School-Based Management Committee (SBMC) Policy, and the Quality Assurance Policy are nearing completion. Jigawa State has also enacted 4 pieces of legislation to formalise new institutions (the State Education Quality Assurance Agency, the Tsangaya Education Board, the Education Resource Agency, and the Senior Secondary School Education Board) to enhance education governance and delivery. Important political economy analysis behind the scenes has continued with UBEC, regarding the process to increase and reform domestic financing provisions of the UBE Intervention fund, a major bill is anticipated for approval in 2026.

PLANE facilitated bi-annual meetings for State Steering Committees (SSC) to influence inclusive education reforms and improve provision of teaching and learning resources in Jigawa, Kaduna and Kano. The SSCs worked in collaboration with citizen-led accountability platforms to address the findings on PLANE supported research on learning outcomes, which includes acute supply issues for TLM across schools. State Steering Committee engagements have led to commitments by stakeholders (including Local Governments) to improve the supply of TLMs to schools and use of a performance management (PM) system to track progress. Priority areas have been defined and progress made, including increased enrolment in ABEP (Kaduna), teacher recruitment (Kano and Jigawa), school infrastructure (Kaduna and Kano).

PLANE made progress in strengthening the efficiency and improved funding of education by supporting KKJ states to meet HOPE Project Disbursement Linked Indicators (DLIs). PLANE provided capacity-building support to state officials on budget processes leading to the development and validation of the 2024 Annual Education Sector Performance Review (AESPR), Education Medium-Term Sector Strategy for 2026-2028 and Annual Operational Plans. These will contribute to the achievement of HOPE-GOV and HOPE-EDU DLIs. In collaboration with PACE, PLANE also trained local government staff across Kano’s 44 LGAs, enabling states to meet DLI 2.3 on strengthened budget planning and execution for primary healthcare and basic education.

PLANE enhanced the capacity of citizen-led accountability platforms through strategic plans and initiatives to strengthen institutional capability in the education sector. Plans for the accountability forums K-SAFE, KADBEAM and JEAF in Kano, Kaduna and Jigawa States respectively were developed and a range of initiatives to strengthen accountability were competed. In Jigawa, the Education Accountability Forum (JEAF) conducted a statewide survey tracking book supply and distribution. In Kaduna, the Local Government Accountability Mechanism (KADLGAM) implemented a Citizen Participatory Audit of education projects and developed a Scorecard that strengthened budget transparency and community participation. In Kano, the State Accountability Forum on Education (K-SAFE) carried out school monitoring visits across 13 LGAs, using findings on teacher performance and learning resources to inform budget advocacy and promote improved learning conditions.

Improved teacher recruitment policy and practices have led to tangible improvements in government leadership. Political Economy Analysis (PEA) has informed engagements by PLANE and its partners to identify key challenges affecting teacher quality, numbers, gender balance, and deployment, to amplify these issues on states’ policy agenda. States are now following stricter, rules-based process to select teachers accountably, a major historic problem has been politicised teacher recruitment. PLANE has supported through facilitation of participatory workshops and design of data tools. In Jigawa, progress was made towards a merit-based recruitment and equitable teacher deployment. To date, 19,788 teachers (31% of whom are women) have been recruited in Kano and Jigawa. Kano made better progress on female teacher recruitment than Jigawa although continued dialogue around women’s leadership and pro-women teacher deployment polices is still required. In Kaduna, a Harmonised Teachers performance management framework has been developed and PLANE plans to work with the accountability mechanisms to advocate to implement mass teacher recruitment (the delay is associated with fiscal pressures and state debt).

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no changes to Output 2 in Year 3.

Progress on recommendations from the previous AR (if completed)
Output 2, Recommendation 1: During policy development, it is important to ensure that all relevant stakeholders, including departments and agencies of the state and federal education ministries are sighted on the process and, where appropriate, engaged according to their relevant interests and equities. PLANE worked with key institutions to ensure that all stakeholders relevant to the intervention are fully sighted and informed and participate as necessary.

Output 2, Recommendation 2: The positive start made to the work of the Thematic Working Groups (TWGs) should be consolidated, with TWGs taking a greater interest in wider donor-funded initiatives and in LGAs outside PLANE’s focus. This will strengthen coordination across initiatives and encourage the extension of programme impact beyond initial focus locations. PLANE has become more strategic and deliberate in ensuring that TWGs and Steering Committees are all encompassing, involving different stakeholders. TWGs provide a platform for more technical discussions, with a focus on Foundational Literacy and Numeracy (FLN) and OOSC. State specific TWGs led by W1 in the KKJ States also promote co-ordination between PLANE partners, state government and other education programmes.

Output 2, Recommendation 3: PLANE should support the strategic development of civil society led accountability initiatives. This includes supporting them to plan activities to complement, rather than duplicate, government-led action. PLANE assistance to these initiatives should focus on developing actionable advocacy, for which PLANE activities can support government responses. PLANE’s capacity strengthening and institutional development support has enabled accountability forums to plan, implement and report on activities that complement supply side actions.

Lessons learned this year and recommendations for the year ahead

Policy making is a transaction intensive process. It is therefore essential to ensure that individuals who are knowledgeable about policy issues are identified to participate in the policy development process. It is also important to negotiate the consistent participation of the same set of individuals throughout the policy development process. This reduces significant knowledge loss and delays that often happen when there is a high turnover in the policy development team.

PLANE’s support when strategically targeted and linked with other development interventions can lead to economies of scale benefits, representing good value for money, including unlocking other funding sources for much-needed investments in the education sector. This is evidenced by PLANE’s support to the Kaduna State Safe School Policy and the potential for similar results in the World Bank HOPE-Edu Project.

The successes emanating from engagements by the Accountability Mechanisms around TLMs indicate that citizens voices can influence government policy priorities if advocacy ‘asks’ by citizen groups are data-informed and engagements around the ‘asks’ are politically aware and responsive.

Output 2, new recommendation 1: Deepening collaboration with stakeholders in northwest states in achieving HOPE DLIs and other sources of basic education financing by proactively exploring partnerships with stakeholders such as the nascent NW Development Commission and Dangote Foundation (noting recent major philanthropic focus on education and private sector engagement and work to promote a broader northern region compact on Human Capital Development). Mapping of partners and institutional links established by September 2026.

Output 2, new recommendation 2: PLANE should continue supporting policy implementation and alignment by influencing relevant supply-side actions and working with Accountability Forums to strengthen advocacy around education policy priorities that have local resonance, especially in the northwest states and with the potential to align with Federal policy and financing.

Output Title	Improved engagement, management & performance of non-state sector in delivering foundational skills.
Output number:		3	Output Score:	A
Impact weighting (%):		8%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Percentage of non-state schools that meet the required policy and regulatory requirements for private education delivery and are safe, secure and inclusive schools	State policy guidelines on non-state schools finalised and endorsed by stakeholders and 61% of non-state schools that meet the required policy and regulatory requirements	Milestone met. / The Federal Non-State School Policy was approved by the National Council on Education in 2024. A 'Non-State School Policy' was approved by the State Executive Council in Kano. The remaining 2 private school policies for Kaduna and Jigawa are awaiting State Executive Council approval. PLANE also supports the domestication of the national non-state school policy in Lagos, Ogun and Oyo states. / The percentage of non-state schools that meet the desired policy and regulatory requirement has increased from the baseline of 60% (12,579 out of 20,965) to 69% (14,543 out of 20,965). The 9-percentage point increase is split across Jigawa (691), Kaduna (829) and Kano (444).
3.2 Number of innovation hubs pilots launched in PLANE supported IQS and private schools to integrate learning in IQS and support institutional strengthening	Innovation hubs modelled and replicated by one Government and Private Schools Board	Milestone met. / In addition to the three innovation hubs established in Kano, Kaduna and Jigawa in previous review years, the State Governments in Jigawa and Kano States have provided additional spaces and staff for replication.
3.3 Number of stakeholder forums established to promote coordination of activities on non-state schools and implementing strategic plans	At least 3 stakeholders forums functional and two strategic plans implemented	Milestone met. / 3 stakeholders forums (KSAFE, JEAF, KADBEAM) are functional and strategic plans have been finalised in Kaduna, Kano and Jigawa. The plan for Kano State has been fully implemented, while Kaduna and Jigawa have been partially implemented.
3.4 Number of affordable loans and financial products issued to schools	At least one financial services package delivered to 1,000 schools	Milestone met / Four financial products (e-wallets for students, financial literacy for low-cost schools, health insurance packages of 300,000 Naira, and digital training) have been produced. / 2,000 non-state schools across the KKJ states and South West states have accessed school improvement loans to meet government regulation requirements.

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 3 is delivered by the DAI-led consortium under the PLANE contract (Window 1). All targets for this period have been met and overall satisfactory progress (A) has been made.

PLANE has made sustained progress in supporting the development and adoption of frameworks and regulatory approaches for non-states schools. The National Non-State School Policy was approved early in the review year, subsequently Kano approved its version, and Kaduna and Jigawa are awaiting State Executive Council approval. PLANE has also collaborated with the Development Agenda for Western Nigeria (DAWN) Commission, to support the domestication of the national non-state school policy in Lagos, Ogun, and Oyo States. Work on a similar approach for Almajiri education (community led Islamic education), with the Federal and Kaduna State Ministries of Education is underway, with the National policy approved in late 2025.

PLANE continued to support quality improvements for non-state schools. The percentage of non-state schools that meet the desired policy and regulatory requirement has increased from the baseline of 60% (12,579 out of 20,965) to 69% (14, 543 out of 20,96). The 9 percentage point increase is split across Jigawa (691), Kaduna (829) and Kano (444). Cumulatively, pilot graded assessments have been rolled out across 2,912 schools (Jigawa 973, Kaduna 1,345, Kano 594) in 24 LGAs across the KKJ States. Graded assessments conducted in Year 3 across Kaduna and Lagos states revealed systemic weaknesses requiring improvement. In addition, PLANE ran safeguarding training for non-state and Tsangaya head teacher, teachers and managers in Jigawa, as well as working in collaboration with Kaduna State Schools Quality Assurance Authority (KSSQAA) to support non-state schools to develop School Improvement Plans to meet registration requirements.

PLANE officially launched its work in Southwest and Southeast Regions in 2024, with the focus on private schools serving low-income households. PLANE’s policy work is aiding Lagos State’s transition towards a more cooperative relationship with non-state schools.

Innovation Hubs in Kano, Kaduna, Jigawa, and Oyo States are now fully operational and State Governments in Kano and Jigawa have provided additional spaces for replication. The Hubs are also pivoting to have a stronger focus on supporting policymakers to make EdTech decisions that address the learning crisis. PLANE has demonstrated effective EdTech applications to enhance classroom delivery in both state and non-state schools, generating evidence for scalable, cost-effective technology adoption. Kaduna State have used the hub to support a state-wide basic education assessment and the development of a non-state school database. The Innovation Hub in the Southwest is located at the Development Agenda for Western Nigeria (DAWN) Commission in Ibadan, Oyo State. In Jigawa, Kano and Oyo the Hubs are fully functional, and work is ongoing to support government-led replication in Year 4.

PLANE-supported education stakeholder forums are fully operational across Kaduna, Kano and Jigawa States with strategic plans in place. In Kaduna, the forum reviewed and strengthened the non-state school monitoring tool. In Jigawa, the forum improved their strategic plan, governance and resource mobilisation for basic education. In Kano, the forum conducted quarterly monitoring visits to assess classroom practice. In the Southwest, where a low-cost private schools coalition was established in September 2024, the reviewers heard positive feedback from members. Perceived benefits are inclusion in state policy development, support with school registration and administration, and amplification of member priorities.

Progress also continues to be made on expanding financial inclusion for non-state schools. Four financial products (e-wallets for students, financial literacy for low-cost schools, health insurance packages and digital training) have been produced and 2000 non-state schools have accessed school improvement loans to meet government regulation requirements. PLANE has provided TA to the National Coalition of Non-State Schools for inclusive loan access and is facilitating partnerships across low-cost private schools, Presspay, and Lagos State Employment Trust Fund. With Jigawa State Government, a PPP finance model with the Bank of Industry is being developed.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

During the reporting year Output 3 underwent a strategic realignment, shifting focus from financial inclusion and innovation hubs to supporting the Federal and State Governments to address the out-of-school children crisis. In practice, this meant efforts in Kano, Kaduna, and Jigawa States concentrated on expanding access within the non-state sector. At the federal level, PLANE prioritised strengthening policy and regulatory frameworks for targeting out-of-school children and education public-private partnerships (e-PPPs). In the Southwest, focus centred on regulatory improvements, strategic private sector engagement, and improving e-PPP initiatives.

Progress on recommendations from the previous AR

Output 3, Recommendation 1: Provide focused support to federal, state and regional partners to implement the non-state schools’ policies that have been developed, school leadership standards, taxation guide, and learning outcomes benchmarks to facilitate effective regulation and improved learning outcomes in non-state schools. PLANE supported implementation of non-state school leadership standards, learning outcome benchmarks, and policy frameworks across multiple states. Training manuals and facilitator guides were developed and deployed, with the British Council extending training to 7 additional states. In KKJ states, non-state school managers, teachers, and School Support Officers were trained on Learning Outcomes Benchmarks (LOB), which Kano State has adopted for both state and non-state schools. In the Southwest, PLANE collaborated with DAWN Commission to train 25 school leaders in Oyo State on Professional Standards for School Leaders, with an additional 165 school leaders trained virtually. Quality Assurance Officers from Oyo, Lagos, and Ogun States received training on LOB, with stakeholders agreeing to integrate early childcare education benchmarks into State Ministry frameworks. PLANE is providing support to the Federal Ministry of Education on implementing some provisions of the National Policy by providing Technical Assistance on the implementation of various models of education PPPs.

Output 3, Recommendation 2: Deepen engagement with the Federal Ministry of Education, UBEC and National Commission for Almajiri and Out Of School Children Education (NCAOOSCE) to address the OOSC issue, including supporting reforms focused on greater equity in UBE fund allocations and rationalising support to OOSC. Key achievements include supporting NCAOOSCE's development of its national strategic plan across seven key areas: data collection, quality education, child protection, advocacy, policy development, sustainable funding, and skills acquisition. PLANE assisted Almajiri policy, covers operations, management, learner and teacher welfare, infrastructure, and funding for Almajiri education systems. PLANE supported institutional capacity building for key agencies, including NCAOOSCE, UBEC, NEMIS, and State Ministries of Education. A workshop in April 2025 established a Data Management, Governance, and Dashboard Framework for tracking Almajiri and out-of-school children, involving the National Bureau of Statistics and the National Population Commission. The PLANE-supported Almajiri and OOSCE Technical Working Group, strengthened federal coordination and mandates. Following disbursement-linked indicator fulfilment, UBEC released ₦4 billion (£2m) in intervention funds to initiate implementation activities, however larger volumes of federal/state finance are still urgently needed to make real progress in the North, where bio-data for ~1m OOSC was logged.

Lessons learned this year and recommendations for the year ahead

Disparities in the performance of federal and state governments on non-state reforms highlight the need to prioritise efforts more strategically in Year 4. The approval and dissemination of the National Non-State School Policy, supported by PLANE, highlights the critical role of national-level endorsement in generating sub-national commitment. At the federal level and in Kano, where the state government has been pursuing ambitious reforms to implement, the focus should shift to building broader buy-in across constituencies and support delivery and financing commitments. In Kaduna and Jigawa, while there has been some progress, delays in state executive council approval have slowed implementation and more follow up will be required.

Output 3, new recommendation 1: PLANE should continue working with State governments to domesticate and implement policies including the National Non-State School Policy, National Policy on Almajiri, and Education Technology Strategy. Priority should particularly be given to states such as Kaduna and Jigawa, whose adoption of non-state school policies has been slower, with the aim of these policies being fully approved by state authorities, mid-2026.

Output 3, new recommendation 2: On education PPP models and financial inclusion, PLANE should continue sharing global evidence, supporting implementation of relevant taxation and policy guidelines, and collaborate with the Bank of Industry and like-minded partners to support federal and state interventions. Access to finance should be a priority for low-fee private schools in Lagos to help relieve pressure on oversubscribed state schools and PLANE should adopt a cross-state approach in the Southwest to increase non-state school registration, share best practice (including technology innovation in Lagos), and increase the collective capacity to educate an expanding population of children.

Output 3, new recommendation 3: On out of school children, PLANE should increase its operational support to the NCAOOSCE in Kano state to improve access to quality education, including the Digital and Remote Access School Instruction (DARASI) Programme, which is being developed by NCAOOSCE in cooperation with the Kano State Government.

Output Title	Effective evidence generation, communication and use of evidence informs citizen-state engagement and improved service delivery.
Output number:		4	Output Score:	A
Impact weighting (%):		8%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 Extent of effective and robust MEL system operational in targeted locations	4 quarterly reviews and VfM analyses carried out to distil learning and produce quarterly reports and digital dashboard. At least 6 rapid assessments on PLANE's interventions carried out	Milestone met. / 4 quarterly reviews and VfM analyses carried out to distil learning and generate quarterly reports and digital dashboard. / 6 rapid assessments on teaching and learning materials; safeguarding action plans, learning outcome validation and SBMC/Headteacher knowledge.
4.2 Number of PLANE's supported data and evidence products published and used by stakeholders	Number of evidence-based state research outputs produced with 10% uptake at LG and state levels	Milestone met. / I 20 data and evidence products from 4 key assessments created and shared. / Uptake calculated at 43% (excluding stories of change, in areas on Book management and utilisation, learning outcomes and financial flows).
4.3 Number of champions of change (CoCs) identified and engaged at federal and state levels who support governments in scaling good practices, implementing context-specific education reforms, enhancing governance mechanisms for state and non-state education delivery	At least 35 CoCs identified and engaged to bring systemic education reforms	Milestone exceeded. / 111 CoCs identified and engaged. / Breakdown: 21 Female and 90 Male. / Kano 21; Jigawa 21; Kaduna 26; Federal 10; Southwest 33.

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 4 is led by the DAI-led consortium under the PLANE contract (Window 1) and incorporates the work of the independently contracted DELVe component, that has implemented the midline performance evaluation (see Section G). All targets for this annual review period have been met, and overall satisfactory progress (A) has been made.

Progress has been made on strengthening both in-house and government-led MEL systems, prioritising smart technical assistance, quality data and evidence products and tracking uptake for data-driven decision-making. On communications and influencers, there has been expanded reach and visibility, with measurable growth across social media and mainstream platforms, including doubling website traffic. There are concerns that trade-offs between quantity and quality/depth/impact are sometimes misaligned, and that the strong engagement and buy-in within the focal States has not translated into as much influence for transformational change at the national/federal level as desired.

Better data and evidence products generated have informed and helped drive government action. These have contributed to large scale teacher recruitment in Kano and Jigawa, with meritocratic assessment and deployment systems that have clearly been influential in improving learning outcomes, especially in Jigawa State. State Quality assurance agencies are scaling PLANE’s innovative approach, around school support visits (SSV) and reflective school self-evaluations, with data uploaded to management dashboards. The federal UBEC and HOPE-EDU programme has expressed strong interest in utilizing and adapting the book distribution Track and trace (TnT) system pioneered by PLANE nationally, in tandem with book use and specification guidelines. Evidence products include the Year 3 Learning Outcome Assessment, Book Management and Utilisation Surveys, Financial Flows to Basic Education, and Tsangaya School Learning Assessments. Value for Money analysis has been extended, including an environment/climate dimension and cost-benefit analysis recalculated for the first three years of implementation.

PLANE significantly expanded and strengthened its communications reach and visibility, achieving major growth across social and mainstream media platforms. A collection of ten Stories of Change and six high-quality videos capture the impact of PLANE’s interventions through compelling human-interest narratives. The Kaduna EduPACT International Education Summit co-created by PLANE was a major success in promoting a strong government led reform agenda with senior attendance (State Governor, Federal Ministers, UK Deputy High Commissioner), building on the Kano recovery conference in the previous year. A strategic partnership with Arewa24 TV Hausa language channel, with a potential reach of over 45 million viewers, has further amplified public awareness of education advocacy efforts and demand for reform. The Bètá Nigeria Advocacy Campaign has launched its first series of podcasts with influential actors being interviewed by articulate female students and the Champions of Change (CoCs) network of influencers, mostly from ‘within’ the public sector education network are being engaged to promote strategic campaigns. However, Bètá Nigeria has been slow to initiate and gain real traction amongst decision makers, or civil society and the public.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no substantive changes to Output 4 indicators in Year 3. With the midline review, large scale ODA funding cuts for upcoming years, the pivot away from service delivery in the 3 focal States of Window 1, and a shift to systems strengthening and government delivery it will be important to take stock and adapt this output, as outlined in the new recommendation detailed below.

Progress on recommendations from the previous AR (if completed)

Output 4, recommendation 1: PLANE follows up on the Kano Education Recovery Conference and engage the Kano State Government on the theory of change, result framework and SWOT analysis. PLANE should also support the Kaduna State Education Summit planned in 2025, taking a flexible and pragmatic approach. PLANE supported development and agreement of the Kano Education Emergency Response Plan (KEERP), it was formally adopted as a state policy document and has been influential on increasing education budgets, teacher recruitment and supply volumes. Work on a broader Kano Out of School Action Plan is now underway. The Kaduna Summit was implemented successfully (see above) in July 2025.

Output 4, recommendation 2: Work in synergy with other outputs across all PLANE Windows and DELVe to develop knowledge management products that create greater understanding of approaches that can inform uptake pipeline World Bank/GPE HOPE finance.	PLANE published the first in a series of learning products: Strategy for Scaling PLANE’s Foundational Learning Approach.

Output 4, recommendation 3: The Beta Nigeria campaign[4] should expand engagement with coalition partners, who will be supported to work together with their own resources and political capital, to demand change. With the government and civil society stakeholders, the ‘Voices of the Future’ podcast launched, providing a platform for senior stakeholders to share insights on reform areas. It is uncertain how effective this has been to build demand for reform.
[4] The Beta Nigeria campaign is a nationwide movement launched in early 2024 to make education a top priority and ensure that every Nigerian child is enrolled, stays in school, and receives quality learning. The campaign, funded by PLANE and driven by Nigerians, works with civil society, media, policymakers, teachers, and communities to push for improved investment in education and increased government accountability. Through nationwide roundtables and capacity‑building workshops, Beta Nigeria has mobilised diverse stakeholders, highlighted the country’s education crisis, and amplified calls for urgent reforms to secure Nigeria’s future. It emphasizes shared responsibility across society and seeks to build a broad coalition advocating for better funding, stronger systems, and long‑term educational transformation.

Output 4, recommendation 4: Explore options regarding the use, consolidation and reporting of both PLANE intervention and non-PLANE LGA ‘comparison’ learning data. Reporting comparison data from non-PLANE LGAs on learning outcomes and teacher performance is now in place for the previous year, using the W1 FHI360 led impact evaluation datasets, in agreement with FCDO and DELVe.

Lessons learned this year and recommendations for the year ahead

FCDO acknowledges that the generation of data and evidence and how it will be used to inform policy and adapt and reform practice is both an unpredictable and non-linear agenda. Overall PLANE is generating a knowledge base that presents a strongly positive impression of the programme, albeit at times with a slight tendency to provide voluminous information that potentially overclaims PLANE’s impact in a complex federal education system that is inherently difficult to reform or enhance. W1 influence in the focal States has not always translated into national influence, with an example arising on the annual school census (ASC) and integration into the national EMIS system. PLANE’s approach was not integrated into the new federal National Education Data Initiative (NEDI). Over the past year high rates of flux in senior federal education appointments and abrupt shifts arising from the Nigeria Education Sector Renewal Initiative (NESRI) rollout has inhibited PLANE, and all development partners’ ability, to engage, align and strategically support on evidence and data.

Output 4, New recommendation 1: PLANE W1 activities on data and evidence will need to be substantially reviewed and adjusted to reflect changes to the programme due to ODA reductions. W1 should support the major adjustment needed to the PLANE portfolio log frame and generate a new workplan for Year 5 and beyond by mid-2026. In collaboration with FCDO, W1 should identify fewer, but strategic areas on data and evidence that fit with: (i) the NESRI/ sector wide agenda of the Federal Ministry, and (ii) the HOPE-Edu results framework areas. These should avoid duplication with other development partner support and seek to complement the approach in the northeast (see Output 5), whereby PLANE W1 offer broader data and evidence support to the wider cluster of northwest Nigeria regional States, using insights and experience built in Kano, Kaduna and Jigawa states.
Output Title	Effective approaches to teaching and learning and more resilient systems for children affected by conflict.
Output number:		5	Output Score:	A+
Impact weighting (%):		13%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
5.1. Number of children benefited from TaRL, KARI and ABEP interventions / TaRL – Teaching at the Right Level; KARI – Kanuri Arithmetic Reading Initiative; ABEP – Accelerated Basic Education Programme	261,665 (Cumulative) / 77,440 (annual) / TaRL Cumulative 173,630 / KARI Cumulative 30,555 / ABEP Cumulative 57,480 / (Original intent: 15% children with disabilities; >50% girls)	Milestone exceeded / Cumulative 340,532 (178,992 girls 53%) 98,083 (annual) / Borno:183,168 (96,762 girls) / Yobe: 157,364 (82,230 girls) / Children with disability: 3,326 (1%), 1,490 girls (45%) / Borno: 2,034 (920 girls), Yobe: 1,292 (570 girls) / TaRL 241,689 (51% girls) / KARI 38,421 (51% girls) / ABEP 60,422 (59% girls) / Substantial over-achievement on reach – 130% cumulative and 127% annual but underachievement on equity (CwD only 1%)
5.2: Percentage of girls benefit from life skills sessions who transition effectively to JSS	60% (annual)	Milestone exceeded / 98% 8,552 Primary Grade 6 girls (annual) / Cumulative number of girls who have received life skills sessions (P5 and 6): 61,753 (Borno: 29,715, Yobe: 32,038)
5.3: Percentage of LGAs with improved conflict-responsive, disability and gender inclusive education sector plans, using data on CwD for planning support	100% (annual)	Milestone met / 100% (all 6 focal LAGs)

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 5 is delivered by UNICEF through a memorandum of understanding (Window 2). All milestones for this annual review period have been met or exceeded, and progress has moderately exceeded expectations (A+).

1. Activities under Output 5 focus on more secure urban LGAs of Borno and Yobe States, with an influx of displaced population due to conflict over the past decade. This is distinct to more rural areas which are supported by ‘education in emergencies’ (EiE) humanitarian actors, including for residents of Internally Displaced People (IDP) camps. Support includes:
  1. Improving the quality of teaching to deliver foundational numeracy and literacy (FLN). This is achieved through three packages, which each year are rotated to new schools/centres:
    1. Teaching at the Right Level (TaRL), which helps children in upper primary to catch-up to where they should be in their learning, through grouping students by levels of prior learning rather than by age-grade.
    2. Kanuri Arithmetic and Reading Intervention (KARI) help Kanuri-speaking children in school in grades P1-3 to learn foundational literacy and numeracy in their mother-tongue.
    3. The Accelerated Basic Education Programme (ABEP) helps children out-of-school to acquire FLN. They receive a condensed and accelerated primary curriculum, delivered by volunteer teachers in the afternoons after the regular school day has finished.
  2. Enabling girls and children with disabilities to complete primary and transition to junior secondary education. This is delivered through running “life skills” courses to girls in primary grade 6, including through water, sanitation and hygiene (WASH) awareness sessions. Construction of WASH infrastructure halted due to budget limitations in the previous year.
  3. Improving well-being, protection and safeguarding of conflict-affected children, particularly girls and children with disabilities. This is delivered through training teachers and school-based management committees (SBMCs) on child-protection, psycho-social support and gender-responsive pedagogy.
  4. Strengthening the capacity of governments and communities to plan, finance and implement education in emergency context in line with evidence and best practices.

Continued strong performance, positive feedback and over achievement on quantifiable indicates over the last year justifies a score of A+. This is based on UNICEF reporting, five school visits conducted in Damaturu and Potiskum LGAs, Yobe State and interviews with key stakeholders from both State governments. Deep and trusted partnerships were evident with UNICEF throughout the visit and good practice observed, such as (i) FLN taskforces sustaining better teaching across each LGEA, (ii) TaRL Learning Corners with painted infographics of learning games and activities to aid professional development, (iii) portable handwashing stations and solar boreholes used for community and tree cultivation and (iv) effective Level I and II ABEP classes run by young qualified unemployed teachers in large urban primary schools in the afternoon, enabling a 2nd chance education for older children. The collection of TaRL baseline learning assessment data was being effectively used to group and teach children in the upper primary grades according to ability. These visits also highlighted ongoing challenges in early grade teaching, particularly in Hausa speaking communities without the KARI programme, A visit to one school found roughly 80% of Primary 4 students were still struggling with single digit addition by counting and simple word recognition. Intermittent attendance and cessation of school feeding were both cited as contributory factors, but clearly the early grade teaching process needs review.

North-East Nigeria continued to experience a volatile security environment. Sporadic attacks, displacements, and military operations disrupt access to education services. Families are hesitant to send children to school and the psychological toll, coupled with deep widespread poverty and food insecurity greatly inhibit school attendance and child development. Government school feeding has also ceased. In this context, the outputs and outcomes are impressive.

Overall, since the start of this output, over 340,000 disadvantaged children (53% girls) have benefited from improved teaching and learning. This has considerably exceeded overall cumulative targets on reaching children. Each year the intensive FLN support is rotated to a new selection of schools, expanding reach, whilst providing backstopping support to previously supported schools to sustain the improved teaching approaches. Learning assessment data reported substantial ‘in-year’ increases in foundational literacy: from 8 to 43 % in TaRL, 5 to 26% in KARI, and 12 to 42 % in ABEP students. Similar trends were confirmed in numeracy as well. Whilst not directly comparable to robust global benchmarks or to robust comparison groups, these results do provide confidence in the packages’ ability to effectively support rapid acquisition of essential foundational skills. For the first time, data is available on OOSC transition into upper primary or junior secondary school. In Borno and Yobe states 4,284 ABEP students (2,570 girls) were successfully mainstreamed into formal schools for the 2025/26 school year. This represents about one third (34%) of the cohort and is a highly positive outcome, with an older age profile, many will have followed other pathways, such as vocation skills training or work.

A smaller cohort of 8,727 girls than previous years participated in life skills sessions. This was due to an exclusive focus on P6 students, rather than P5 and P6 as in previous years. The sessions emphasised critical thinking, communication, creativity, collaboration, hygiene knowledge and interpersonal relationships. These sessions boost confidence and self-esteem, foster resilience and enable more informed decisions on transitions to adulthood. Almost all (98%) successfully transitioned to junior secondary school. This is in part due to this initiative, but also due to World Bank AGILE programme investments, that build new junior secondary schools and providing cash transfers to support progression for deprived girls.

The programme supported local government education officers to develop data-driven, result-oriented, gender-sensitive, disability-inclusive, crisis-responsive costed local education sector operational plans. Mass training in safe school minimum standards, psychosocial support and child protection has also been implemented. Broad support has also been provided to focal States on data, both for HR management and the digitalisation of the Education Management Information System (EMIS), using a federally endorsed system developed by UNICEF’s technical partner. Collectively these enhance capacity for planning and implementation of the major HOPE-EDU programme, which commenced implementation in February 2026.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Due to the cuts in international aid globally, the number of EiE Working Group NGOs operating in North-East Nigeria fell from 42 to 23. Pressure intensified following the abrupt mass closure of the US funded Opportunity to Learn (OTL) non-formal centres in February 2025. State governments and UNICEF pivoted quickly with FCDO support using PLANE and GPE programme resources to enrol 18,889 children from closed OTL centres into other ABEP centres in Borno and Yobe, directly avoiding mass dropout and enabling continued learning. This is highly commendable.

With the two-year extension of the component, and continued evolution of the security situation and national education reform agenda and financing situation, this review has clearly identified the need for a re-design and shift in activities that can be rolled out in the 2026/27 school year and beyond. The direction is outlined in the new Output 5 recommendation below, with an emphasis on sustainability and adjusting the geographic focus to more insecure areas. Choices on language of literacy and instruction, Kanuri, Hausa and English require careful attention and trade-offs.

Progress on recommendations from the previous AR

Output 5, recommendation 1: To enable planning for sustainability, W2 partners should help state governments to develop a clear understanding of the respective objectives and costs of the different foundational learning packages.	UNICEF has taken several steps to strengthen State governments’ understanding of the objectives, components, and cost implications of different foundational learning (FLN) packages. Key actions include: (i) joint development of minimum viable packages (MVPs) for KARI, ABEP, and TaRL, through which State government teams actively conducted a detailed costing of the various components of each FLN model; (ii) co‑creation of the ABEP Investment Case in Yobe State, which modelled multiple costing scenarios for expanding ABEP; and, (iii) collaborative development of a fully costed five‑year FLN scale‑up plan, outlining phased expansion, financial requirements, and sustainability pathways.

Output 5, recommendation 2: For the programme to be able to deliver its original objectives within the total budget envelope, a no-cost time extension is recommended. This has been completed, with a no-cost extension agreed in mid-2025, extending the programme end date to December 2027. Given reduced ODA commitments from a range of actors and shifts in the overall PLANE budget, negotiations are ongoing in ways to adapt and maximise the impact and sustainability of W2 investments, with more emphasis on government ownership and financing.

Output 5, recommendation 3: The W2 risk register should capture and monitor the nuances of working with Borno and Yobe state governments in their challenging contexts. Risks associated with working with state governments and poor coordination across levels of the federal system were included in the risk matrix shared by UNICEF in September 2025. However, the challenges identified in relationship management between various State government agencies appear to have been resolved, and active adaption to the dynamic environment, such as the flood response in late 2024, handled appropriately. Relationships with the Yobe State government, and its openness to actively collaborate on broader joint initiatives, for example AGILE junior secondary school expansion are particularly welcome. A meeting with the Commissioner of Education in Borno State elicited a strong request for a counselling and psychosocial support initiative adapted for displaced, survivors of violence and ex-combatant children, to enable pathways to resume education effectively Acting on this will be prioritised as part of UNICEF’s workplan over the programme year.

Output 5, recommendation 4: W2 partners should participate fully in upcoming DELVe research projects. DELVe have completed research related to ABEP, policy influencing and the overall portfolio midline performance evaluation during the reporting period. Satisfactory engagement from programme and government actors in the northeast was provided, evidenced from DELVe outputs.

Lessons learned this year and recommendations for the year ahead

A useful lesson emerging from data analysis regarding the lower-than-expected participation of children with disabilities in the programme, was on low identification rates of children with less obvious difficulties in mainstream schools and lack of engagement with existing special needs schools. Reflections included that original estimates of prevalence were unrealistically high, and the need to work with teachers on identification approaches and more intensive support provision in existing ‘special needs’ classes.

UNICEF has been successfully supporting Borno and Yobe states to scale FLN initiatives in more stable, urban areas, but with a trade-off on reach in less secure areas with more acutely marginalised children with very constrained access to education. The World Bank’s HOPE EDU (Education Programme) presents a major opportunity to both sustain and scale good practice and move from a project paradigm, to one in which government actors are supported to utilise domestic financial resources and strengthen education service delivery, with enhanced quality and inclusion.

Output 5, new recommendation 1 With the major cuts in development ODA announced by USAID and other actors, as well as domestic financing revisions and federal education reforms underway, UNICEF needs to undertake a major re-design of the Window 2 EiE component of PLANE that moves beyond repetition of the three FLN initiatives in the current six focal LGAs. It should encompass more work in less secure LGAs and resettlement areas where population displacement has occurred, but government is reopening schools and teacher deployment is happening. Co-ordination with other humanitarian initiatives, in particular protection, psychosocial support and nutrition should be encouraged. This will enhance the broader impact of accelerated non-formal provision and primary structured pedagogy to build FLN and reduce the numbers of out-of-school children. In tandem with other education resources managed and coordinated by UNICEF in northeast Nigeria, establishment of a broader regional ‘Centre of Expertise’ hub with other NE State education leaders should be explored to mirror work in the northwest, to widen and enhance the Federal education sector wide approach reform agenda. Where possible, metrics and indicators of success should be aligned with those defined in the HOPE EDU results framework and PLANE’s Window 1 work in the northwest region. This should be completed in full consultation with FCDO by mid-2026, to provide sufficient time for deployment in the 2026/27 school year and necessary adjustments to the Window 2 MoU agreement.

Output Title	Girls and boys participate in community-based learning interventions in a supportive community environment, including for marginalised groups
Output number:		6	Output Score:	B
Impact weighting (%):		8%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
6.1 Number of girls and boys enrolled in Community-based learning interventions (disaggregated by type of intervention literacy / numeracy boost (LB / NB), Catch-up Club (CuC), remote learning, age, sex and disability status)	70,294	Milestone not met. / 38,251 children were enrolled in CuC or LB/NB. / 17,793 male and 20,458 female. / Children with Disabilities – 2,057 (1017F, 1040 M)
6.2 Children with disability supported to enrol in schools (disaggregated by age / sex)	750	Milestone not met. / 597 Children with disabilities were supported to enrol in schools (256 F, 341 M).
6.3 Number of girls and boys receiving case management support and/or referral to child support services (disaggregated by age, sex and disability status)	687	Milestone exceeded. / Total – 1379 / Boys – 713 / Girls – 666 / Children with Disabilities – 163 / Boys – 78 / Girls – 85
6.4 % of households in supported communities reached by Social Behaviour change communication (SBCC) programs (radio programs and live interaction)	40%	Milestone exceeded. / 47% of households in supported communities reached by SBCC programs (radio or live).

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 6 is implemented by Save the Children International under an accountable grant (Window 3). This output is undergoing a major pivot to focus on delivering the government-aligned Accelerated Basic Education Programme (ABEP) and performance against targets has been mixed over the past review year. Progress is moderately below expectations (B).

PLANE continued to enrol children in Community-Based learning interventions but failed to meet targets due to the cancellation of the final planned session. During the review period, PLANE W3 enrolled 38,251 children in community‑based learning interventions across Jigawa, Kano and Kaduna, comprising 17,793 boys and 20,458 girls. 2,057 were identified as children with disabilities (CwD). The two principal intervention types were Catch‑up Clubs (CuC) and Literacy/Numeracy Boost (LB/NB). CuC accounted for 33,264 learners (15,497 boys; 17,767 girls), while LB/NB reached 4,987 learners (2,296 boys; 2,691 girls). Attendance and progression data indicate strong participation: club attendance averaged 84% overall. In parallel, program supervision and mentoring by state and partner teams strengthened delivery quality and supported learner retention across learning spaces. The programme’s community sensitisation and mobilization, including place‑based sessions and structured handover to head teachers for mainstreaming, helped drive enrolment and continuity. However, budget uncertainties (late, but ultimately full annual allocation notification by FCDO in mid-2025) led to a decision by SCI to cancel the final sessions for the CuC and LB/NB, leading to a shortfall versus the enrolment targets. Enrolment into the 2025/26 ABEP cycle conducted towards the end of the annual review period has been on target with 8,517 children (4,479 girls, 4,038 boys) signed up.

Support to children with disabilities led to 597 (256 F, 341 M) being enrolled in mainstream schools, but this fell short of the target of 750. Drivers of this progress included community‑centred actions and targeted inclusion measures. Core groups, facilitators, traditional leaders and LGEA officials collaborated to mainstream out‑of‑school learners into nearby formal schools, with structured handover processes and follow‑up for vulnerable children. Community‑generated support such as provision of school materials and school uniforms also helped reduce immediate financial barriers. Assistive devices were distributed across communities, with monitoring showing that these devices significantly motivated children to attend or return to school. Caseworkers and government social workers strengthened identification, safe referral, and documentation. Community dialogues on gender and disability inclusion reached 4,551 participants, including persons with disabilities, improving understanding of disability rights and schooling. Challenges such as insecurity and procurement delays were noted as risks to sustaining enrolment efforts.

W3 exceeded targets for the numbers of children that received case management support and referral to child support services, as well as strengthening state capacity. A total of 1,379 children received case management services and/or referrals, including 713 boys and 666 girls; 163 of these were children with disabilities (78 boys; 85 girls). Capacity‑building underpinned service strengthening, with 46 case workers and 6 government social workers trained, alongside recruitment of 25 community‑based caseworkers. A range of risks were addressed including alternative care for unaccompanied boys, prevention of early marriage, and curbing corporal punishment in schools. Material and financial support complemented referrals: 97 children received non-food items (NFIs), 100 received school kits, and 108 children/caregivers received conditional assistance to support school enrolment/retention, often linked to Village Savings and Loan Association (VSLA) groups for long‑term resilience. Sensitisation campaigns strengthened protective norms and encouraged community‑driven reporting. Safeguarding systems were also strengthened by expanding Feedback and Reporting Mechanisms (FRMs) and improving partner compliance through training and monitoring.

VSLAs continued to play a critical role in strengthening household economic resilience and supporting children’s participation in education across Jigawa, Kaduna, and Kano States. No new VSLAs were established during the reporting period, but the 56 existing VSLAs were sustained, engaging 1,400 members, with 72% being caregivers of learners in Catch‑up Clubs, Literacy/Numeracy Boost, and newly mainstreamed children. These groups collectively saved NGN 32.6 million and generated NGN 1.57 million in social funds, providing a vital safety net for emergencies. The NGN 39.7 million (~ £20,000) share‑out enabled members to invest in small businesses, meet household needs, and cover education‑related expenses—especially for girls and children with disabilities.

PLANE exceeded targets for reaching households with social and behavioural change communications. 47% of households in W3 supported communities received SBCC interventions, surpassing the 40% milestone. The programme delivered 16 weekly radio drama episodes and established listening groups in four communities to encourage dialogue on girls’ education, disability inclusion and harmful norms. 21 community dramas reached 6,068 individuals, including 210 persons with disabilities. Additionally, 4,320 IEC materials were distributed across JKK states to reinforce key messages. Despite the activity being deprioritised following the exit of the CITAD SBCC partner, the programme exceeded targets. SBCC messaging worked in synergy with wider mobilisation structures -core groups, religious leaders and town‑hall platforms- contributing to shifts in community norms around inclusive education.

W3 has made progress in tracking and evidencing the mainstreaming of CuC and LB/NB graduates into formal schooling. It was found that 15,861 children that completed the learning interventions from the previous year (7,544 boys and 8,317 girls) (41% of those enrolled in CuC and LB/NB in this period) were mainstreamed or continued in formal school due to work carried out by Community Core Groups under their community action plans and wider education initiatives.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The focus of Output 6 and PLANE W3 is transitioning from Catch Up Clubs and Literacy/Numeracy Boost interventions to the government‑aligned Accelerated Basic Education Programme (ABEP), with ABEP sessions that started in September 2025. This shift aims to create a more sustainable model for reaching out‑of‑school children at scale. Core pedagogical elements -semi‑structured instruction, strengthened supervision, and inclusive disability support- are retained to preserve learning gains. To ensure readiness, PLANE W3 has intensified engagement with government partners, strengthening SUBEB ownership and integration of ABEP into state plans and budgets. Kaduna SUBEB has already allocated 2025 funding to support the transition of current learners into formal schools. The programme has also recruited and trained new facilitators, including 30 adolescent support facilitators in Kano and Jigawa, to deliver ABEP. Community mobilisation has expanded to prepare families and enrol vulnerable learners. Additionally, safeguarding systems and feedback and reporting mechanisms have been extended to ABEP target LGAs to manage risks during scale‑up.

Progress on recommendations from the previous AR (if completed)

Output 6, Recommendation 1: There remains significant work to finalise the design and approach to shift the implementation geography and interventions of this output and its results framework for the 2025/26 implementation year. This should include shorter term process and readiness indicators to provide confidence that a sustained rollout is feasible from September 2025, with a mechanism to track individual children’s learning outcomes and transition pathway, during and after direct education interventions. The ABEP detailed design plan should be informed by the on-going DeLVE study commissioned on reviewing the cost effectiveness and scalability of ABEP and how it can be integrated into State led implementation plans in Kano and Jigawa States. This will require sustained engagement with W1, DELVe and NERDC as the government curriculum agency that initiated ABEP and is lobbying for institutional reforms to support it to be scaled and financed with Federal, State and local actors. (by 31/03/2025) Finalisation of implementation plans for ABEP aligned with the ABEP study guidance and lessons learned from CuC and LB/NB implementation. Actual implementation began in August 2025. Alongside this, there has been increased state‑level engagement through participation in joint planning, reviews and supervision processes. Strengthened government ownership has been demonstrated e.g. Kaduna SUBEB’s 2025 budget allocation to mainstream children into formal schools.

Output 6, Recommendation 2: Currently the Accountable Grant governing this output is due to finish in September 2026, at the end of the first full cycle of the new ABEP education intervention. During the next Annual Review dialogue in late 2025, there will be a requirement for Save the Children to make a strong, evidence-based costed plan and justification on the case to agree a no-cost extension for the continued implementation of this output beyond September 2026 (by 31/10/2025). Reductions in ODA and decision to prioritise PLANE’s continued shift away from direct service delivery led to an agreement that W3 will close when the current accountable grant ends in September 2026.

Lessons learned this year and recommendations for the year ahead

Semi‑structured instruction and close mentoring significantly improved attendance and foundational learning outcomes of marginalised children and adolescents. Community mobilisation with Core Groups, religious leaders, and VSLAs is essential for shifting social norms and addressing structural barriers for girls and children with disabilities. VSLAs also provide economic empowerment, which directly supports enrolment and retention. Sustainability requires deeper integration of PLANE approaches into state systems and further strengthening of government capacity.

Output 6, new recommendation 1 Save the Children – in conjunction with FCDO – should develop a clear and responsible exit strategy for W3 by March 2026 to protect gains, sustain community and government ownership, and ensure continuity for vulnerable learners. This will include basic elements – asset transfer management, staff exit plans and knowledge sharing with a wider range of actors – in time to allow implementation before the end of the current accountable grant in September 2026.

Output 6, new recommendation 2 Save the Children should give priority to actions that will enable state governments to take over ABEP centres or otherwise provide sustainability when the window closes. This includes working closely with W1 and State Governments to integrate the centres into proposals for the World Bank HOPE Education Programme and ensuring strong engagement and capacity building of State and LGEA officials to ensure knowledge transfer. Plan to be in place by June 2026.

Output 6, new recommendation 3 Work plans and budgets for Window 3 should discontinue the use of mainstreaming kits, to both maximise the reach of the ABEP courses and to align more strongly with the wider PLANE partnership approach, and instead efforts to mainstream ABEP graduates should focus on working with a range of actors at the community level (i.e. through VSLAs and Community Action Groups), the LGEA level (education officials) and the state level (State Mainstreaming committees) rather than the direct provision of materials. Plan to be in place by March 2026.
## D: VALUE FOR MONEY

Key cost drivers and VfM performance compared to the original VfM proposition in the business case

The major cost drivers identified by the business case proposal were fees, expenses and overhead costs of service providers. Analysis from PLANE W1 for the last annual review year continues to support this analysis. By geographic location, central-level utilisation accounted for approximately 65% of total expenditure, while the three states of Jigawa, Kaduna and Kano represented 31% of the total programme spending. It is important to note that centrally managed costs also include procurement and services utilised within the states, which were centrally procured to ensure best VfM,

Overall analysis suggests that the PLANE programme continues to demonstrate strong value for money.

On Economy, PLANE W1 exceeded the target to bid ratio set for procurement, with averages of 4.5 – 5 against a target of 3. The higher the number of bids received per procurement, the higher the likelihood of obtaining a better rate for the transaction. These figures reflect a deliberate strategy to drive down costs by competitive bidding; over time the programme has consistently demonstrated achievement of competitive unit costs and value for money. W1 has estimated savings of £3.5m, accrued over the programme lifetime up to December 2025. These savings have been reinvested, in consultation with FCDO. Similarly, management overheads costs have stayed below 8%, well below an indicative 20% benchmark.

On Efficiency, W1 can demonstrate a very low unit cost for the foundation learning package, of £3.62 ($4.80) per student reached and leveraged other resources to deliver its objectives. The unit cost is favourable to other comparable programmes internationally that estimate $6 - $10 per child. Other programmes in Nigeria estimate costs at $8.50 - $11 per child. However, the PLANE programme anticipates a further reduction in delivery costs as the programme pivots to systems strengthening, where more direct costs are covered by government. For instance, Jigawa State Government committed £88,000 to scale PLANE’s foundational learning packages, across 1,284 schools in 20 LGAs of the state. This collaborative effort made it possible to reach more schools than would otherwise have been possible.

Increased proportion of students in W1 and W2 achieving foundational learning levels, coupled with continued low unit costs at large volume scale, combine to enhance PLANE effectiveness. Investment in policy reform processes seek to drive long sustainable improvements, such as the Teachers Recruitment and Deployment Education Policy and four legislative reforms in Jigawa. The Girls’ Education Policy in Kano, which promotes gender equity in education, was approved at an estimated accrued cost of £0.011 per beneficiary girl child.. Approval of the Girls’ Education policy significantly promotes gender equity programming at minimal and sustainable levels. W2 have also driven done teacher training and equipment costs with State partners, by developing minimum viable packages of support, that limit time spent in expensive, residential training and makes use of locally made, no-cost teaching aids.

On equity, the programme has been intentional on reaching out to marginalised groups – particularly the girl child and children living with disabilities or in remote areas. Girls consistently represent over half of supported children across interventions. A twin track approach has improved data on disability, fostered a broader inclusive school ethos and targeted support interventions. W1’s focal areas include 17% of schools in hard-to-reach and volatile areas, that are often very neglected. Additionally, there has been deliberate effort to engage more female teachers in its activities, noting the context within which the programme exists where few female role models exist.

In terms of empowerment, the programme has done well in having women in leadership positions. All suppliers have women in leadership positions and FCDO actively encourages suppliers to support more women get to these positions. This will continue to be monitored throughout the life of the project, and reinforces trends in government appointments in the education sector.

In the last annual review year, environment has also been added to the VFM matrix in line with wider FCDO practice. These indicators reflect PLANE’s commitment to promoting environmental responsibility alongside its educational interventions. Having commenced in year 3, the monitoring and reporting of environmental indicators will continue systematically throughout Year 4. Investments in solar power at three W1 offices are generating considerable cost and carbon savings, through reduced diesel generator usage.

W1 have updated and refined their overall cost effectiveness analysis and estimate a cost benefit analysis of 3.77 over the programmes initial three years. This slightly exceeds the original business case estimate of 3.42 and represents an internal rate of return (IRR) of 23%. Benefits accrue largely from projections of future enhanced earnings associated with high levels of education and skills, as well as the health and demographic benefits associated with girls’ education. However, a rapid review of the CBA approach conducted in early 2026 suggested that the IRR was likely too high as the methodology utilized underestimated the costs (by only include direct PLANE implementation costs, rather than wider costs) and there was weak evidencing of benefit valuation, both in terms of the impact of education on earnings and wider non-wage benefits linked to girls education. These methodological issues will need to be addressed in future analyses.

Assessment of whether the programme continues to represent value for money

Based on the analysis of VFM presented above, the programme continues to represent good value for money. It continues to respond to Nigerian education reforms as well as UK interests, ensuring transformational societal benefits, which should continue to accrue as engagement continues. If PLANE’s effective education interventions are scaled and sustained by government, the programme’s true value and potential will be realised.

This is the 3rd full year implementation year of the programme and the VFM assessment remain on a positive trajectory. Despite significant budget cuts, partners have been able to flexibly respond and deliver the programme within critical VFM considerations.

E: RISK

Overview of risk management

The risk rating for the programme remains major, although the policy and programme risk was upgraded to ‘severe’ during the year under review owing to the likely programme budget cuts required by UK ODA cuts (from 0.5% to 0.3% of GNI, announced in 2025), the shifts in priorities by UK Ministers and the exit of USAID which was the largest bilateral donor in Nigeria. The ‘severe’ rating is however, within the FCDO Nigeria’s Risk Tolerance threshold.

Risk management has continued to be prioritised in the Quarterly Programme Management Board which brings together portfolio implementing partners to review progress and challenges across the portfolio. The team uses standard risk management instruments including delivery chain risk maps, delivery plans, horizon scanning and fraud risk assessments to monitor implementation risks. A comprehensive Fraud Risk Assessment for the portfolio was carried out in November 2024, with Risk Registers updated on a quarterly basis.

Key risks assessed over this period included: insecurity, particularly school kidnapping for ransom; key personnel changes; budget cuts; delivery risk as a result of abrupt USAID closures; and high inflation impacting basic food and fuel prices. Although the National Bureau of Statistics released figures indicating reduced rates of inflation, these are yet to alleviate high rates of general poverty and food insecurity. The risk of ODA budget cuts has been managed through portfolio rebalancing, although the specifics remain to be worked out. Although kidnapping for ransom remains a major risk, this is out of the direct control of the programme, though enhanced security protocols have been activated as safeguards for staff and beneficiaries. PLANE will also continue to work on school safety issues in Year 4 to address risks at the system level.

Climate Change risk remains assessed as moderate. FCDO continues to proactively look for ways to promote ‘do no harm’ and to ensure climate change is mainstreamed in its activities. Window 1 within the period under review transited to solar power, providing green energy and reducing carbon emission footprint in three of its offices. There has also been complementary pilot activity carried out by the FCDO climate adaption programme, CRIBS, around renovation of facilities in Jigawa and Kano. These renovations were focussed on making public structures climate smart and resilient to heat, storms, flooding (building drainages, tree planting, raising levels of structures) and drought (provision of boreholes). Enhancing school infrastructure is beyond PLANE’s scope, but it is an area for potential cross-programme coordination on technical assistance, with the expectation that it will contribute to student progression and learning outcomes.

There is continued uncertainty around fiscal autonomy of local governments, following supreme court rulings. PLANE continues to work with PACE to understand the implication for the education sector given LGAs prominent role in primary education. Supporting the emergence of more equitable and inclusive education finance is a priority. FCDO and programme staff will need to mitigate risks that might emerge from operational shifts and unintended consequences.

FCDO has continued to encourage strong safeguarding compliance in terms of reporting and management of Sexual Exploitation, Abuse and Harassment (SEAH) by partners within the reporting period. Two cases of SEAH were reported, investigated by the Safeguarding team and successfully closed. Partners have continued to refresh protocols and training on the subject given its extensive interactions with children and vulnerable people. This was checked and reviewed during AR field visits to schools and learning centres, that showed good levels of awareness and compliance. Some head teachers were able to discuss cases of bullying or inappropriate behaviour that had been dealt with locally, that didn’t merit escalation. The importance of a focus on wider child protection issues including gender-based violence was clear from the visits, given prevailing high levels of poverty, insecurity and harmful traditional socio-cultural norms. Whilst adequate sensitisation and reporting structures appear to be in place, the very limited number of cases logged, remains a generic concern. All implementation partners will continue to monitor and apply strong Gender Equity, Disability and Socially Inclusive (GEDSI) operating principles.

Portfolio Risk Register has continued to be reviewed and updated on a quarterly basis, drawing on risks review and update by portfolio partners. The Register will be updated at the beginning of 2026, with further periodic reviews continuing. Although programme and policy level is at severe, fiduciary risk is rated as minor due to regular financial meetings with partners and three layers of scrutiny for invoices and financial transactions (Programme Officer, Deputy Programme Manager and Senior Responsible Owner). Partners are aware of FCDO’s zero tolerance for fraud and have reported cases as they occur. The only due diligence assessment conducted in the reporting year was for the EdTech Hub and the minor recommendations made are being actioned with oversight from the relevant Programme Officer. Progress made on this will be available before the end of June 2026.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The PLANE programme is delivered through a mixture of instruments – two Accountable Grants (AG), two contracts, and a Memorandum of Understanding (MoU). Regular programme meetings have ensured FCDO is aware of any challenges. All partners have been assessed to be implementing within FCDO rules. A complex Contract amendment (CA4) was completed within the period under review for W1. This amendment updated midterm outcome based KPIs, 2024- 25 annual workplans and portfolio results framework. Key personnel changes and updated price schedules occasioned by movement of funds across budget lines were required. Other amendments included reduction of the financial limit and an extension of the end date on the AG for W2. A midline PLANE portfolio performance and evaluation (see section G) has been carried out within this period and the recommendations are being used to inform the restructuring of PLANE’s instruments, proposed in Section A.

Partner performance

Both W1 and W2 have completed a third full year of implementation in focal States, working directly with government stakeholders. W3 started implementation in mid-2023 and after expanding to an additional three LGAs in 2023 -2024, they have now narrowed implementation to two states (Kano and Jigawa) as part of a wider pivot to strengthen sustainability by implementing the government backed Accelerated Basic Education Programme (ABEP). The independently contracted Human Development Evaluation, Learning and Verification Service (DELVe) support to PLANE has completed small research studies whilst focusing work on the Midline Evaluation of performance; findings from which have been integrated into this AR and its recommendations.

Overall partners have performed well given the complex and risky contexts within which they have operated within the reporting period. Naira exchange rates have stabilised, but partners faced significant budget uncertainties and major shifts in the wider aid context such as the total collapse of USAID. W1 have been able to channel support to aid implementation of the government’s NESRI agenda, while W2 were able to rapidly reprogramme in order to successfully support many children affected by the unplanned and rapid exit of the USAID-funded Opportunities to Learn (OTL) Programme. W3 have been able to execute a major pivot to implementing ABEP – which should improve the sustainability of programme impact – but also cancelled a planned cohort of their existing interventions due to budget uncertainty (see Output 6 for detail).

Feedback on partner performance from government and beneficiary community stakeholders during AR meetings and visits has been overwhelmingly positive, demonstrating trust and maturing relationships that are now bearing fruit – including strong quantitative performance against milestone deliverables. Financial reporting has been generally good. Spend to forecast has largely remained within the 3% variance threshold and have been presented in timely manner. Where there have been reasons for delays, these have been discussed and agreed with FCDO ahead of time.

FCDO management

The FCDO PLANE programme team comprises: the SRO (senior education adviser) supported by two education advisers, and programme officer leads for each window overseen by the programme manager (who also directly manages the Window 3 component of the portfolio) – with support from the FCDO Nigeria Human Development and Demography (HDD) block senior programme manager (who provides 30% support to the portfolio).During the period of this AR, there has been continuity of the SRO, which has assisted to maintain consistently high levels of engagement and support. The number of education advisers has fallen from three to two due to the ending of a 50% FTE post in December 2024. Portfolios and responsibilities have been reallocated in line with the transition plan developed to mitigate the impacts of the change.

Coordination across the PLANE portfolio within FCDO has been achieved through fortnightly HDD block and monthly education team meetings, and lead advisers and programme managers meeting regularly with delivery partners. Regular fortnightly meetings are held with the larger W1 programme management team to maintain frequent communications.

The key governance and management structure in place for PLANE include an operational focused Programme Management Board (PMB) established in 2022, that has met quarterly and involves all partners. A major joint PMB retreat meeting was held in May 2025 with senior government officials also present. These enable FCDO and partners to discuss strategic direction, engagement with government, emerging challenges, risk and opportunities for co-ordination and synergies with PLANE and beyond. Discussions focused on adapting the programme to a lower ODA budget context and achieving closer alignment to the Education Minister’s NESRI agenda. PMB meetings have been complemented by quarterly Technical Learning Platform (TLP) meetings convened by FCDO, W1 and DELVe, where emerging evidence and knowledge from the programme is presented and discussed, such as the Midline Evaluation.

More detailed technical discussions take place within Technical Working Groups (TWG) focused on Foundational Literacy and Numeracy (FLN) and OOSC. State specific TWGs led by W1 in the KKJ States also promote co-ordination between PLANE partners, state government and other education programmes. A high level, standalone PLANE Steering Committee, has not been established. Alignment to the government led donor co-ordination mechanisms, in particular the joint Nigeria Education Group (NEG) and thematic TWG co-ordination forums, has been adequate to incorporate oversight and alignment to government priorities.

On changes in partner instruments / agreements, as anticipated in the last annual review, a 4th contract amendment (CA4) was agreed with the DAI-led consortium for W1 to reflect further shifts in context and implementation. A 5th will be needed in 2026, to reflect a reduction in resource availability. A no-cost extension was signed for W2 that extended implementation to December 2027 and strengthened the focus of activities on capacity building and ensuring sustainability, with emphasis on preparing states to take over activities with funding coming from the World Bank HOPE Education (HOPE-Edu) programme. The partner agreement for W3 will close as scheduled in September 2026. An accountable grant was agreed with the EdTech Hub in July 2025 in response to a request for support from the Federal Minister of Education. Initial work has been promising and plans are in place for the coming AR period; the Hub’s scope of work is summarised in Annex A. The DELVe contract is to be suspended from April 2026, due to the reduction in funding. Changes to partner instruments set out in this review are particularly shaped by anticipated reductions to funding and reflections on the efficacy of activities, as well as alignment to the UK’s wider ODA strategy and Nigeria specific business plan.

Financial reporting has been generally good, but could be further strengthened. FCDO Programme Management (PM) has reactivated the quarterly PM meetings with service providers to help manage finances and to ensure that any challenges and issues are mitigated. Spend to forecast has largely remained within the 3% variance threshold. The Business Case value of the PLANE Programme is up to £170m. Out of this, a total of £83m was formally approved for spend by Ministers for the portfolio with a request to get back to Treasury for the approval of the balance once this amount was exhausted. Spend to date is £70,111,354. Reporting has been timely and the proactive scrutiny of financial returns and requests have been maintained to ensure every pound spent was on intended purposes. Partners have at times found delayed announcement of approved FCDO budgets for PLANE to be problematic, in particular W3 (see Section C, Output 6). Uncertainty on future budgets will continue to be challenging and require active communication with FCDO to limit spend variance.

Fraud Reporting has remained positive within this period, with partners taking proactive steps to show commitment to FCDO’s zero fraud policy.  Within the period under review, two new cases were reported- one of which has been successfully investigated and closed. Three other long drawn cases were closed, which means four cases were closed during the period under review. There are four cases currently under investigation, one of which is at write off stage. The programme team continues to engage partners to ensure cases are promptly reported, investigated and closed.

The annual audit exercise for the portfolio is underway with the final report expected by end of April 2026. The exercise covers the period October 2024 – September 2025 and covers financial and programme issues as well as asset management. The draft Report is “Unqualified” and gives the Development Director the assurance to sign off the Annual Review Report for the corresponding period.

This annual review presented opportunity to further test delivery chain risk mapping and counter aid diversion discussions in focal states. For the first time in 5 years, there was opportunity to visit the programme activities in Yobe state which previously remained unvisited due to security challenges. This made it possible to observe FCDO interventions in the state and review aggregate results covering the state. Feedback received from a wide range of beneficiaries across the focal states indicate appreciation for regular training for teachers and state school supervisors, given the limited ability of states to do so. This has helped in teaching quality and school attendance for both teachers and children. Additionally, beneficiaries expressed appreciation for the introduction and training on Village Savings Loans Associations (VSLAs) as instrument of financial empowerment to parents and hence needed support for children’s education. Downstream partners also reported strengthened working relationships with main implementing partners since the recommendations from the last AR. However, with the end of the direct delivery model, there will be sustainability implications, but the programme is actively working with state government partners to address them.

Recommendations from the last AR which aimed to strengthen financial management, manage conflict of interest and better manage down steam partner relationships were actioned within the period under review. These included reconstituting procurement committees every six months to reduce unconscious bias and conflict of interest, downstream partners participating more in lead partner events to align expectations, which was noted particularly in progress meetings for the annual review; and, ensuring payment of Daily Subsistence Allowance to workshop participants within 2 weeks, with partners deploying additional resources to make this happen.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evidence

As noted under Output 4, PLANE has made progress strengthening in-house and government-led MEL systems, with a focus on smart technical assistance, quality data and evidence products, as well as tracking uptake for data-driven decision-making. PLANE’s reach and visibility have also improved in terms of knowledge products, as evidenced by increased engagement across social media and mainstream platforms, including doubling website traffic. However, it is important that trade-offs between quantity and quality/depth/impact are carefully considered.

Better data and evidence products generated have informed and helped drive government action. These have contributed to large scale teacher recruitment in Kano and Jigawa, with meritocratic assessment and deployment systems that have clearly been influential in improved learning outcomes, especially in Jigawa State. State Quality assurance agencies are scaling PLANE’s innovative approach, around school support visits (SSV) and reflective school self-evaluations, with data uploaded to management dashboards. The federal UBEC led HOPE-Edu programme has expressed strong interest in utilising and adapting the book distribution Track and trace (TnT) system pioneered by PLANE nationally, in tandem with book use and specification guidelines. Evidence products include the Year 3 Learning Outcome Assessment, Book Management and Utilisation Surveys, Financial Flows to Basic Education, and Tsangaya School Learning Assessments. Value for Money analysis has been extended, including an environment/climate dimension and cost-benefit analysis recalculated for the first three years of implementation.

There have been a range of visits to PLANE programme sites in Kano, Kaduna and Jigawa over the last annual review year, many of which were integrated into travel plans for other purposes (e.g. the Kaduna Education Summit, CRIBS annual review and launch events, and the UK parliamentary International Development Committee (IDC) visit).

Field visits for this annual review covered Borno, Kaduna and Kano, but also extended to PLANE activities in Lagos and Yobe state. State visits focused on observing schools and learning centres and meeting government officials and community/civil society stakeholders. In addition, federal government and implementation partners meetings were held in Abuja to discuss implementation progress, challenges and recommendations to course correct the programme.

Learning

The Midline Evaluation of PLANE was conducted over the last annual review year. It commenced in March 2025 with a midline design, gathered primary data in June-July 2025, and delivered a draft findings validation workshop in October 2025. A final version was submitted towards the end of January 2026. The midline evaluation also drew from DELVe’s PLANE-Supported Policy Influencing for Systemic Education Reforms: Final Report (Nov 2025) that critiqued progress across an 8 step cycle of support to a range of specific policy development processes.

DELVe’s Performance Evaluation approach (utilised for the baseline in 2023 and midline in 2025) is based on Contribution Analysis (CA). CA is a theory-based evaluation approach that provides a rigorous and structured methodology for evaluating the complex PLANE programme, based on its own Theory of Change (ToC). The evaluation is not experimental and does not include counterfactual analysis, although the evaluation utilises programme partners’ quasi-experimental studies on student learning outcomes to evaluate PLANE’s intended outcomes and impact.

Conceptually, the midline is structured around the PLANE portfolio theory of change and looks at evidence of PLANE’s contributions to change through six ToC change pathways that each contribute to the programme’s outcome and impact. The evaluation also integrates insights from existing and emerging research and learning and data analysis to make adjustments to the evaluation. It was designed to be practical, inclusive, and sensitive to gender and power dynamics in all aspects of its design, operationalisation, data analysis and reporting. DELVe’s overall approach to PE works across five modules (see below) that link to Evaluation Questions that align with the six OECD-DAC evaluation criteria (OECD, 2019).

The evaluation used mixed methods, combining primary and secondary quantitative and qualitative data. Primary qualitative data included interviews and discussions with students, teachers, head teachers, School Based Management Committees (SBMCs) and community members at local level, and with government officials at state and federal levels. Primary quantitative data were gathered through classroom observations and School Checklists. The evaluation interviewed 1,122 individuals in total. The sample was consistent with the baseline evaluation for longitudinal reporting with visits to 53 schools across nine Local Government Authorities (LGAs) in all five states of PLANE operations, including state and non-state schools, public, nomadic, and Islamic schools, in rural and urban locations, and delivering foundational and/or accelerated teaching methodologies. Secondary data were gathered into an annotated bibliography comprising over 150 documents for review; and data from sources including Annual School Census reports and Windows log frame data.

The headline finding of the midline evaluation was that PLANE has made substantial positive strides towards achieving its intended outcome through the interventions and gains of each of its three Windows. There is robust evidence, in which the evaluation has a high degree of confidence, that student learning outcomes in PLANE formal schools and non-formal learning centres have improved since the 2022 baseline evaluation, due to PLANE’s interventions in teaching, learning and inclusion. The midline evaluation has been quality assured by FCDO’s independent EQUALS facility, meeting the highest internal compliance rating band. The full report will be released on the FCDO Devtracker website, later in 2026.

Other major findings include:

PLANE has adapted well to changes in the political economy since 2023 and is managing more recent macroeconomic and education policy instability well. Alignment, and efforts to align, with federal and state government priorities – including the federal government’s Nigeria Education Sector Renewal Initiative (NESRI) 2025 – are visible and well-received by government and non-government stakeholders alike.

Federal and state education policy and governance reforms have been bolstered by PLANE’s contributions in the areas of teacher recruitment, deployment and retention; safe schools; and girls’ education. In the last two years, policy influencing and technical support to policy development has been a significant part of Window 1 and Window 2’s work, providing space for sustainability of the programme and its gains.

Some interventions show strong potential to be sustained beyond PLANE – particularly policy reforms with budgets and plans, long-lasting training and capacity building, and improved attitudes and practices around inclusion and inclusive education. In contrast, resource-intensive interventions (such as intensive teacher coaching, mentoring, and assistive devices for individual children with disabilities) are unlikely to be sustainable by government. Measuring impact is constrained by weak data systems; progress in this area has been limited.

PLANE faces significant contextual risks, including reduced global funding, instability, demographic and systemic pressures affecting national education priorities.

Despite these challenges, opportunities remain: leveraging technology to strengthen education data systems, advancing policy reforms through efficient partnerships and sustained commitment, improving teaching practices through wider adoption of materials, and deepening collaboration with state and non-state actors.

Key recommendations from the midline evaluation include:

That PLANE should continue and prioritise: (i) Basic education policy influencing (e.g. Teacher recruitment, deployment and retention; Safety, Security and Violence-Free Schools (SSVFS); and Non-state school policies and regulation), (ii) language of instruction evidence-based influencing and technical advice; (iii) Teacher training and professional development; (iv) SSO capacity development / strategic support; and, (v) Village Savings and Loan Association advocacy and strategic support.

That Government and/or newly financed programmes should adopt and sustain the following from PLANE: (i) Teaching and Learning Materials procurement, production, distribution and tracking; (ii) Student learning assessments; (iii) Local Government Authority capacity development for decentralised education management; (iv) Strategic support for children of school-age living with any disability; (v) ABEP as a key element of renewed focus on out-of-school children under the federal government’s 2025 NESRI; (vi) Support and regulation of all non-state schools.

Overall the midline performance evaluation provides strong reassurance on the performance and value of PLANE’s work to date, with useful recommendations on course correction as the portfolio adapts in its outer years. The strong relationships built, and knowledge shared with government partners, including through major events such as the Kaduna Summit, Nigeria Education Forum and Teacher Summit, all provide a strong basis to consolidate and enhance UK’s support to Nigeria’s priority reform of basic education systems, that should deliver quality education for all.

Date of last narrative financial report	30/09/2025	Date of last audited annual statement	30 September 2025

Annex A: EdTech Hub accountable grant (£500k, July 2025 – March 2027)

In January 2025, Minister Alausa of the Federal Ministry of Education (FME) requested assistance from FCDO to support a comprehensive digital transformation of Nigeria’s education sector. This led to an accountable grant with the EdTech Hub with Results for Development as the prime recipient. The grant supports Nigeria Education Sector Renewal Initiative (NESRI), the Federal Ministry of Education’s flagship agenda, and feeds into the National EdTech Strategy launch planned for early 2026.

There are three components to the grant: a review of the national teacher training strategy; advancement of Nigeria’s eLearn platform; and a flexible technical assistance offer to the FME and its connected agencies. An EdTech Hub Nigeria Country Lead was appointed in October 2025 to lead and coordinate grant activity. At the time of review, the team were developing conducting stakeholder mapping and further scoping requests for technical assistance.

The initial list of activity seems broad and ambitious. In addition to a review of large and complex initiatives such as the teacher CPD strategy and eLearn platform, requests include work on climate disruption, teacher digital literacy, state-level data collection, development of the national EdTech strategy, and teacher device distribution and use. The implementing partner should manage agency expectations, prioritise, and set achievable deliverables.

Inter-agency coordination will be vital to the grant’s success. Division of responsibly, budget lines, remits and political priorities between government agencies and development partners, both at federal and state level, appear to be complex. At the time of review, the UBEC and FME did not appear aligned on their priorities for technical assistance. Despite the stakeholder mapping exercise there is a risk that the individual TA activity will lack strategic coherence or lack sufficient buy-in from relevant agencies. The EdTech Hub Country lead should leverage the FCDO’s convening power and strategic steers to manage these factors.

Annex B: Selected photographs from annual review visits

Women in Village Savings and Loan Association (VSLA) in Barebari Makoda LGA, Kano State

Pupils engaged in learning activity at Nayi Nawa Primary School, Damaturu, Yobe State

 Use of improvised teaching materials at Layi Primary School, Potiskum, Yobe State

FCDO representatives with Hon. Chairman for Kaduna South and his staff

Annex C: Acronym Table

Acronym	Definition
PLANE	Partnership for Learning for All in Nigerian Education
FCDO	Foreign, Commonwealth & Development Office
OOSC	Out-of-school children
AMP	Annual Management Plan
W1 / W2 / W3	Window 1 / Window 2 / Window 3
DAI	Development Alternatives Incorporated
UNICEF	United Nations Children’s Fund
AG	Accountable Grant
CStL	Community Support to Learning
DELVe	FCDO Nigeria Human Development Evaluation, Learning and Verification Service
TA	Technical Assistance
MoU	Memorandum of Understanding
NGO	Non-Governmental Organisation
EDPG	Education Development Partners Group
PACE	Partnership for Agile Governance and Climate Engagement
ERICC	Education Research in Conflict and Protracted Crisis
WWHGE	What Works Hub for Global Education
SCALE	Scaling Access and Learning in Education
NESRI	Nigeria Education Sector Renewal Initiative
E-SWAp	Education Sector-Wide Approach
UBEC	Universal Basic Education Commission
FME	Federal Ministry of Education
NEDI	Nigeria Education Data Initiative
NALABE	National Learning Assessment of Basic Education
USAID	United States Agency for International Development
UNESCO	UN Educational, Scientific and Cultural Organisation
MAFs	Mutual Accountability Frameworks
NUT	Nigeria Union of Teachers
TLM	Teaching and Learning Materials
ALHCs	Accelerated Learning Holiday Camps
FLN	Foundational Literacy and Numeracy
SSO	School Support Officer
PRS	Planning, Research and Statistics
EMIS	Education Management Information System
RANA+	Reading and Numeracy Activity Plus
HOPE-Edu	World Bank HOPE Education Programme
SSV	School Support Visits
TnT	Track and Trace
CoE	Colleges of Education
SRGBV	School-Related Gender-Based Violence
GEDSI/GESI	Gender Equality, Disability & Social Inclusion
SBMC	School-Based Management Committee
LGA/LGEA	Local Government Area / Local Government Education Authority
ASC	Annual School Census
MICS	Multiple Indicator Cluster Survey
ToC	Theory of Change
SSA	Senior Secondary School Education Board
TRDR	Teacher Recruitment, Deployment and Replacement
KSSQAA	Kaduna State Schools Quality Assurance Authority
DAWN	Development Agenda for Western Nigeria
e-PPP	Education Public-Private Partnership
NCAOOSCE	National Commission for Almajiri and Out-of-School Children Education
TaRL	Teaching at the Right Level
KARI	Kanuri Arithmetic and Reading Initiative
ABEP	Accelerated Basic Education Programme
WASH	Water, Sanitation and Hygiene
NFIs	Non-Food Items
VSLA	Village Savings and Loan Association
SBCC	Social Behaviour Change Communication
IEC	Information, Education and Communication
KEERP	Kano Education Emergency Response Plan
IDC	International Development Committee
OECD-DAC	Organisation for Economic Co-operation & Development – Development Assistance Committee
CPD	Continuing Professional Development
CRIBS	Climate Resilient Infrastructure for Basic Services
SEAH	Sexual Exploitation, Abuse and Harassment
DDA(s)	Due Diligence Assessments
PMB	Programme Management Board
TLP	Technical Learning Platform
TWG	Technical Working Group
NEG	Nigeria Education Group
SRO	Senior Responsible Owner