## Annual Review 2025

Title: UK-India Tech Start-up Fund
Programme Value £ (full life): £138 million		Review date: 08/07/25
Programme Code: [AMP ID#] : 300421	AMP start date: 08/04/19	AMP end date: 31/03/34

Summary of Programme Performance
Year	2020	2021	2022	2023	2024	2025
Overall Output Score	A	A	A	A+	A+	A+
Risk Rating	Major	Major	Major	Major	Major	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/32275700.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/48856661.xls

A. SUMMARY AND OVERVIEW

Description of programme
India's size, with a population of 1.4 billion people makes it crucial for achieving the UN’s Sustainable Development Goals (SDGs). Emerging technologies like artificial intelligence have the potential to bring disruptive advancements that can accelerate the global goals. Even though the Indian start-up sector is the third largest worldwide, it does not address development challenges in areas such as climate and environment, economic and social issues especially for women and girls at the scale required by India.

Government of India (GoI) has emphasised the role of the start-up sector to drive economic growth and job creation. The UK-India Tech Start-up Fund (‘Programme’ or ‘TSF’) is a result of a commitment made between the UK and Indian Governments in November 2016[1] to support tech start-ups. Further, in April 2025 – during the Economic and Financial Dialogue – both sides ‘agreed to boost this partnership, with a shared ambition to match mutual commitments … in green enterprises, tech start-ups, and climate adaptation’. Further, TSF also supports delivery of UK Government priorities on climate using modern partnership approach and contributes to the growth in both countries. TSF has two components:
[1] The UK’s commitment to start-up was agreed in the joint statement between Indian Prime Minister Modi and UK Prime Minister May in November 2016. Link here
- Development Capital Investment - Financial Transaction, FT[2] (£130m): TSF will invest up to £130m in a portfolio of funds (‘Investee Funds’). Department for Promotion of Industry and Internal Trade (DPIIT), Ministry of Commerce, GOI and the UK Government agreed to provide match-fund up to £30m each (Phase 1). TSF aims to attract further investments into these Investee Funds backed by commitments from both the Governments. These Investee Funds provide capital to high potential innovative technology-driven start-ups to attract other investors who can help scale.
  [2] FT investment is an investment instrument which is recognised as a financial asset on UK Government’s balance sheet. This includes instances where UK Government provides funding in exchange for an equity holding.
- Technical Assistance TA (£8m) – is utilised to support necessary compliance, due diligence processes, and lesson learning.

Summary supporting narrative for the overall score in this review
Overall Progress: This sixth review assesses the period from July 2024 to June 2025. Following a steady performance during last year, this review proposes a score of A+. During the year, TSF exceeded most of the target indicators, created new partnerships and helped raise profile of the UK’s initiatives (details in Output section below). Key highlights are below:
- In July ’24, TSF helped curate a broader partnership with State Bank of India – GOI’s largest financial institution via a MoU. This will help strengthen the UK-India corridor with joint investments and policy initiatives in climate and tech sectors.
- TSF committed an additional £10m investment into Avaana Sustainability Fund. This helped set up one of India’s largest climate tech funds focused on start-ups with a corpus exceeding £100m.
- In October ’24, DPIIT – the Line Ministry - acknowledged the UK’s contribution and impact to start-up sector in India via an appreciation letter and outlined new areas for partnership to help build markets. Some of these were progressed in the current year (details under Output 3).
- In Feb ’25, TSF team helped curate a showcase session for the UK’s Secretary of State, Department for Energy Security and Net Zero to understand how UK-India tech partnership works on ground. This feeds into overall strategy and helps shape partnership approach.
- Several awards and recognitions for investees under the portfolio including ‘Project of the Year’ award to Hygenco, a Neev II investee in Green Hydrogen, for developing one of India’s first commercial green hydrogen plant at an Industry Association event.

Investments and Policy Advocacy: TSF has investments in Neev II Fund, managed by SBI Ventures Limited (SVL)[3] and Avaana Fund. These are amongst few climate-tech funds in the entire industry. Both the Fund Managers under TSF are taking initiatives to disseminate learnings and build capacity via industry engagements. This helps demonstrate viability of climate tech as an investment avenue (Details under Output 3). TSF has made progress in shaping the policy environment using expertise at the fund manager and investees’. This helps in effective utilisation of public resources (refer Output 3).
[3] is a direct subsidiary of GOI owned State Bank of India.

Delivering results: TSF has successfully mobilised new investors in climate and curated several advocacy initiatives (Details in Output 1 – 3 below). TSF has exceeded the targets on mobilisation, unlocking 8x from other investors for every £ of public capital invested. This is in spite of challenging market conditions where only c. 2.5%[4] of clean tech start-ups can access growth capital. Currently, 100% of TSF funding is focused on climate given the massive financing gap[5] and higher additionality of public capital. TSF contributes to the UK’s commitments to International Climate Finance (ICF) and its priorities on Growth, Climate and Development.
[4] Read here
[5] Funding requirement of $170b-200b p.a. as per estimates. Link here

Implementation delays: During the review period, TSF also initiated a process to identify new fund manager for implementation of the remaining budget.

The reduction in ODA has resulted in key changes to this programme. This Annual Review reflects that the programme has had to refocus resources and so will deliver against a new plan with new results targets. As a result, the findings of this Annual Review reflect on a programme in transition.

About changes to UK ODA
- At this time of profound change, with conflicts overseas undermining security and prosperity, the UK Prime Minister has taken the difficult decision to increase spending on defence to 2.5% of GDP from 2027, funded by reducing the UK’s Official Development Assistance (ODA) and reinvesting it into defence. The ODA budget will be gradually reduced to the equivalent of 0.3% of GNI by 2027, to help smooth the transition.
- The UK remains fully committed to playing a globally significant role in humanitarian aid and development. The transition to spending 0.3% of GNI on ODA will require significant shifts, building on those already underway as the government implements its modernised approach to development, which centres on establishing long-term partnerships based on mutual interests and respect.
- ODA allocations and the impact on programmes are being worked through based on various factors, including impact assessments. We will be taking a rigorous approach to ensure all ODA delivers value for money and maximises the impact of our work to best support the people it benefits, including those in humanitarian crises.
- We remain committed to spending 0.7% of GNI on ODA when the fiscal circumstances allow.

Major lessons and recommendations for the year ahead

Investment Policy initiatives
- Interventions at scale are important to maximise impact created and to enhance VFM. Institutional investors have higher appetite for large ticket funding and that needs to be factored in the design process. Public capital should be used to help raise ambition of the private sector and create successful examples. Action: TSF team to develop options for FT partnership by Sep ‘25.
- There is potential to create systemic impact by joining up start-up entrepreneurs/Fund managers at the right forums with Government. This can help unblock policy challenges and push for evidence backed policy reform.
- TSF team to scope policy initiative under the SBI MoU that help unlock barriers for tech sector in India. This can be used to engage and positively influence financing institutions both locally and internationally to bridge funding gap using innovative instruments. Action: SRO/PRO to regularly review progress plan with SBI.

x-HMG strategy
- Expertise within the portfolio investees’ can also help shape the UK’s wider tech strategy in India. TSF team to work together with x-HMG leads on Tech pillar of Comprehensive and Strategic Partnership, Tech and Security Initiative and Research Hub teams for collaboration. Action: SRO
- Facilitate close engagement between DBT leads and Fund Manager for Growth Links. Action: PRO to agree plan by August ’25.
Gender and inclusion
- Active engagement on Gender has yielded positive results. It is important to continue to engage at investee levels to understand challenges on ground. This approach has led to higher accountability towards the gender mainstreaming agenda. TSF team to feed into the Women and Girls strategy for FCDO. Action: Inclusion lead to provide inputs and feedback / case studies.
- There is potential to join up with relevant Government stakeholders given GOI’s ‘Nari Shakti’ (translated as ‘women power’) initiative. This will help TSF team x-learn and raise profile of the UK initiatives in India. Action: Inclusion lead to develop plan by August ’25.
Lesson learning
- Showcase learnings from the portfolio at industry events and other forums to advocate for higher investments in under-served tech sectors. Action: PRO to agree a plan by August ’25.
- Revise output indicators to reflect programme status keeping ambitions high. Action: PRO
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]
Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

TSF has delivered strong results against the output and outcome indicators. Despite being at the early stage, the initial investments made under TSF have shown good results. TSF has unlocked its portfolio relationships to help deliver agreed objectives and to influence the market.

At an outcome level, TSF mobilised overall investments of c.£240m (c.£115 in current year) at Fund Manager and investee levels i.e. 8x the amount committed. TSF has contributed towards induction of several new investors in India’s climate investment landscape which has helped broaden the market for tech for development (details under Output 1 and 2). Similarly, on other indicators, TSF has achieved its targets by creating 7,000 green jobs and impacting more than 0.8m beneficiaries positively.

Output 1 scores an A+ largely driven by strong performance by both fund managers in spite of difficult market conditions where fund raise has been challenging. As per recent reports, out of 2,600 climate tech startups in India, only about a fifth survive. Lack of patient capital is cited as one of the main reasons for high mortality which TSF is trying to address. Both, Neev II and Avaana have unlocked capital from marquee investors including the Green Climate Fund, US Development Finance Corporation, European Investment Bank, Japan International Cooperation Agency and others. This corroborates the Theory of Change for use of public capital to build markets.

Output 2 scores an A++ backed by progress in scaling at investee levels. TSF investees managed to unlock £94m in new investor commitments i.e. 4.7x the target. However, c.50-60% of this is attributed by a start-up in waste sector that have been able to scale successfully. Active engagement is needed to help others achieve similar scale and create systemic impact. Few of the investee start-ups have also received recognition from Government and industry bodies attesting their high potential. However, active management and oversight is much needed to manage high mortality risk of start-ups.

Output 3 scores an A and has delivered based on a strong collaboration among the TSF team, x-HMG and partners to work with Government and industry stakeholders. The Fund Managers have engaged with the Line Ministries, think tanks and other senior industry stakeholders to work on sectoral initiatives to bring in investments, encourage innovation and strengthen Environment, Social and Governance practices.

Output 4 scores a B recognising further scope in gender mainstreaming at the portfolio level. TSF team along with fund managers have taken several initiatives for x-learning and capacity building. There is positive momentum that needs to be carried forward to show results and create broader industry impact. This progress is in context of the challenging landscape where women led start-ups comprise <5%[6] share. TSF has had a good start by setting up one of India’s largest climate focused funds.
[6] Reference here

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

TSF should continue as it supports objectives of both Governments to make joint investments in climate and tech sectors as highlighted in the 13th UK-India Economic and Financial Dialogue held in April 2025. TSF also supports delivery of UK Government priorities on Climate and Growth agenda using modern partnership approach with an emerging superpower.

TSF is aligned with the UK-India partnership priorities as mentioned by Foreign Secretary during his July ’24 visit. The FS launched new Tech Initiatives and mentioned ‘… strengthening our investment partnership, to unlock the potential of pioneering Indian enterprises working on climate and technology. These initiatives are specifically focussed on delivering green development while empowering women’.

TSF delivers UK’s objective under Growth and Investment Partnerships by helping raise new investments in priority sectors. It helps create sustainable markets and catalyse growth of new sectors to achieve SDGs focused on driving low carbon growth using the power of technology. It works with GOI and investors to reduce risks and barriers to investments, which helps to mobilise finance for development at scale. There are clear development and financial returns to the UK and Indian taxpayers.

TSF resonates with India’s own political and economic priorities, with a potential to provide job opportunities to large number of women and girls. This is an important agenda for India and one that PM Modi has backed including in various speeches[7].
[7] Link here

## C. DETAILED OUTPUT SCORING

Output Title	Invest in a portfolio of impact focused fund managers to operationalise the DevCap (at fund level)
Output number:		One	Output Score:	A+
Impact weighting (%):		35	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of new investors inducted into existing funds	2 (cumulative 9)	Exceeded. / 4 new investors. Cumulative total is 14. Both investment funds supported under TSF – Avaana and Neev II - have now achieved the target corpus.
Total amount mobilised by funds	£40m (cumulative £140m)	Partially met (£28m). / Cumulative amounts mobilised till date is £150m. / Both investee funds have benefitted from initial support under TSF that helped unlock institutional investment from others.
Percentage of fund invested on climate and environment	Up to 70%	Exceeded. 100% of the fund investments till date contribute to climate and environment.
Return on equity	Capital protection at portfolio level with max 5% deviation	Tracking above the milestone based on estimates. Exact returns will be known when we exit the investments.

Briefly describe the output’s activities and provide supporting narrative for the score.

This output has scored an A+ indicating it has exceeded the milestone targets. Both investee funds supported by TSF - Avaana and Neev II - have exceeded their initial target and have investible corpus of £100-£120m backed by initial funding from GOI and TSF. Avaana achieved its financial closure this year at $135m creating one of India’s largest clean tech funds. Full report here.

Media report on Investee Funds

Similarly, early signs of success under Neev II has encouraged partners (SVL) to design a new deep-tech fund for climate innovations that is 2x the size of Neev II. This is another example of how public capital can help influence wider market and its risk-taking ability.

Progress at portfolio level

During the review period, investee funds mobilised £28m while onboarding 4 new investors – both at domestic and international level. Both funds are now in implementation mode. These investee funds will help address the market failure for tech start-ups which are perceived riskier. A December 2024 report by the Observer Research Foundation (ORF) stated that of over 2,600 registered climate tech startups in the past decade, only about 800 are active now. Of these 800 startups, only 25% have secured funding, mainly in the seed stage, with only 2.5% reaching growth-stage capital. There’s a shortage of patient capital for climate tech startups, and it’s a gap that needs to be bridged if we want to accelerate innovation in this space.

Both investee funds help demonstrate viability of tech investments in India and encourage others to take higher risks. TSF helps boost the ecosystem of tech entrepreneurs, incubators, and mentors through increased funding and market signalling. Both investee funds are investing 100% into climate and environment against the target of 70% indicating higher additionality of public capital.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes were made to this output during the past year. Team to review milestone indicators for outputs in view of delays in investment process and completion of fund raise process at investee funds.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress has been made on recommendation from last year's AR, as shown in the table below.
Recommendations	Action
TSF team to engage closely with GOI stakeholders for co-investment under extended programme budget (Phase II). Action: TSF alongside x-HMG teams	Ongoing. / Ongoing discussions with Government partners and other stakeholders to explore co-investment opportunities.
It is important to engage with new Fund Managers early for alignment on development approaches. TSF team should plan development workshops with the new Fund Managers and disseminate the UK’s development priorities. Action: TSF team to ensure development workshops are embedded in the on-boarding processes by August ‘24.	Not relevant this year. / No new fund manager was selected during the review period.
TSF team will build on the portfolio learning to have higher exposure to small number of funds for maximising influence.	Ongoing and has been factored in the selection process.

Lessons Learnt
- Interventions at scale are important to maximise impact created and to enhance VFM. Institutional investors have higher appetite for large ticket funding and need to be factored in the fund design process. Public capital should be used to help raise ambition and create successful examples that can be replicated.
- UK Government can play a strategic role in mobilising finance by engaging with potential co-investors. This can help during the fund raise process of new investee funds especially with institutional investors.
Recommendation for next year
- Work with Government stakeholders and think thanks to help design use of innovative instruments for attracting climate finance in India. Action: SRO with climate finance leads.
- Progress ongoing discussions with shortlisted fund managers to scope new investment opportunities under tech. Action: SRO
- Progress discussions with Government institutions for partnership opportunities on tech.
Output Title	Facilitate investment into high potential innovative start-ups for sustainable growth
Output number:		Two	Output Score:	A++
Impact weighting (%):		35	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of start-ups that have received investment from the programme Funds	No of start-ups – 10 (cumulative 20)	Exceeded (11): Eleven new start-ups onboarded during the last year. Cumulative total of 22 start-ups has been supported till now.
Amount of follow-on equity leveraged by the start-ups that received Fund investment.	£20m (cumulative £40m)	Substantially Exceeded (£94m): Follow-on funds mobilised by the start-ups this year is £94m. Cumulative amount is £165m.
Number of jobs created, and number of which are green jobs.	300 (cumulative 2100) (70% are green jobs)	Exceeded (3,127): This year programme created 3,127 jobs. Overall jobs created are 7035 (100% as green jobs).

Briefly describe the output’s activities and provide supporting narrative for the score.

The output has scored an A++ indicating that the target indicators have substantially exceeded. Eleven start-ups have onboarded this year as compared to six in 2024. Both the funds have a strong pipeline of innovative tech start-ups. These span high potential climate sectors like agriculture, cooling solutions, energy efficiency and others where tech can play a disruptive role and accelerate progress.

Mobilisation targets have been exceeded by 4x. However, almost half of this is attributed to progress made by Blue Planet – an investee of Neev II - which has now scaled up as a nation-wide platform for waste management using tech. Few other investees in the portfolio have also shown potential to scale and active engagement is needed at the portfolio level.

One of the investees in the business of ESG reporting could not achieve product market fit and has been written off. Active engagement is needed to manage mortality risks of early-stage start-ups. The overall portfolio performance remains satisfactory.

Jobs generated have also exceeded the initial estimates significantly and have created livelihood opportunities across different sections viz. farmers, labourers, women, girls and youth from marginalised communities and others. The investments under TSF also contribute to International Climate Finance (ICF) by supporting initiatives that promote cleaner air, renewable energy, and attracting new investors in these areas.

Awards and achievements
- India’s first commercial green hydrogen plant setup by Hygenco – a Neev II investee, was awarded ‘Project of the Year 2024’ at the India Energy Storage Awards.
- Hygenco was represented at a World Economic Forum's Roundtable on Green Hydrogen Hubs focussing on the potential of green hydrogen for India’s energy transition.
- Solinas received the Startup Sustainability Pioneer Award 2024 for its commitment to sustainable innovation. This recognition highlights their impactful contributions toward environmental responsibility and development.
Case Study – TSF Pushing the green frontier with India’s conglomerates
GPS Renewables , an investee of Neev II, is a leading clean fuels company in India, specialising in biogas production. GPS has developed proprietary biogas technology and has deployed over 100 small and large-scale biofuel plants. GPS has partnered with Reliance – India’s largest conglomerate - to execute several Compressed Biogas projects in record time. It has forged strategic partnerships by entering a 50:50 joint venture with Indian public sector oil majors viz. Indian Oil Corporation and Bharat Petroleum Corporation Limited to support their green transition. GPS had earlier helped set up Asia’s largest waste to BioCNG plant in Madhya Pradesh to manage municipal waste.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
No changes were made to this output during the past year. Review the targets under output indicators based on current status while keeping ambitions higher.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress has been made on recommendation from last year's AR, as shown below –
Recommendations	Action
Continue to strengthen alignment at investee level with FCDO’s refreshed ESG framework. Action: TSF team to track via periodic reports and monthly meetings.	Ongoing as the portfolio develops. Both funds provide quarterly reports which are discussed periodically.
TSF team to strengthen collaboration between Fund Managers/investees in the portfolio and the relevant DHCs. As portfolio scales, this can create win-win especially on trade and investment and help raise profile of the UK’s initiatives in states. Action: TSF team to agree approach with partners by July 2024.	Progress underway. TSF team joined up with DHCs for investee engagement. Leads for UK links were passed on to Trade teams in water sector.

Lessons Learnt
- There is potential to create systemic impact by joining up start-up entrepreneurs/Fund managers at the right forums with Government. This can help unblock policy challenges and push for evidence backed policy reform.
- Close engagement with Fund Managers helps to ensure alignment on additionality and choice of sectors. This helps push Fund Managers to be more ambitious and take higher risks.
Recommendation for next year
- Showcase learnings from the portfolio at industry events and other forums to advocate for higher investments in tech sectors. Action: PRO to agree a plan by August ’25.
- Facilitate close engagement between DBT leads and Fund Manager for Growth Links. Action: PRO to agree plan by August ‘25
- Revise output indicators to reflect programme status keeping ambitions high. Action: PRO
- Continuous engagement on ESG is important especially in early stages to ensure governance risks are well managed. Action: Periodic review by Inclusion and Sustainability Lead/PRO.
Output Title	Supporting Policy objectives to reduce obstacles in unlocking investment opportunities for Start-ups and supporting compliance under TSF
Output number:		Three	Output Score:	A
Impact weighting (%):		10	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of policy and advocacy initiatives supported by UK Government and Fund Managers	Target: / 2 during the year (8 overall)	Achieved (2). Summary below: / Partnered with GOI’s Start-up India team and Niti Aayog to recognise tech innovations in climate through a Challenge event for entrepreneurs. / Several industry level initiatives with investees on to showcase successes in tech innovations and advocate for building new markets.
Number of initiatives to unlock FT and new investments in investee Funds and start-ups	Target: 2 during the year (8 overall)	Achieved (2). Summary of key ones below: / Partnership with SBI on climate and tech for policy and investments to build UK India corridor. / Several outreach events by both Neev and Avaana Capital through roundtables, workshops, and other platforms, both domestic and international to create awareness, mobilise capital, form new partnerships with investors and industry experts.

Briefly describe the output’s activities and provide supporting narrative for the score.

The output has scored an A indicating that the output indicators are on track. The tools for delivering this output utilise minimal financial resources. This is delivered via technical support from fund manager, investees, and in-house HMG expertise, policy advocacy and soft influence. Few examples are below.

Initiatives with GOI/Institutions
FCDO India signed an MoU with SBI to jointly invest in sectors that contribute positively towards climate and technology for development. This helps in market signalling and also influences India’s largest Bank to consider investment opportunities in under-served sectors. This will help unlock opportunities for climate entrepreneurs for innovative ideas that can receive funding. The partnership will also leverage SBI’s vast expertise and network in India and the UK to strengthen bilateral corridor.

TSF Team joined up Avaana to support Grand Challenge event for climate tech Innovation. This was designed as a challenge event for tech entrepreneurs to showcase innovative ideas. The event was organised by GOI teams led by Start-up India. This created a buzz in the tech ecosystem; 500+ applications were received from 22 states including 40% from women. The UK’s Development Director represented on Grand Jury - as the only bilateral - with senior Government stakeholders to assess the finalists. This helped raise profile of the UK’s initiatives and build relationships.

In March ’25, TSF team joined up Avaana and DPIIT to support the Startup Mahakumbh — one of the world’s largest symposiums for start-up innovations. This brought together pioneering ventures showcasing their tech solutions across sectors like energy efficiency, advanced materials, biotech and others. TSF team represented on panels to share learnings and showcase the UK’s initiatives. Several TSF investees also represented to engage with global investors. This is a high priority initiative of GOI, and the UK’s support was well received.

During Feb ’25, TSF team showcased various tech innovations under the UK India partnership to the visiting DESNZ SOS. These included initiatives across sectors like sustainable agri, clean transport, waste management and others. This helped senior stakeholders see up close how UK India partnership delivers impact and can help shape future approaches.

Other initiatives include advocacy by TSF team and Fund Managers to share learnings and feed into investment policy e.g. with Ministry of Environment, Forest and Climate Change (MoEFCC), at the Green Climate Fund, National Bank for Agriculture and Rural Development (NABARD) and others.

Industry engagement for policy advocacy

In June ‘25, Hygenco organised a launch event for their Green Ammonia Plant in Odisha, for storing Green Hydrogen. This was attended by the Odisha Chief Minister and helped raise profile of state level initiatives for clean energy driven industrial growth.

Nutrifresh, an investee of Neev II - in the business of sustainable agriculture – provided technical inputs to Ministry of Agriculture for advancement of horticultural sector in sustainable manner.

TSF backed Fund Managers - Neev II and Avaana – and their investees participated in several investor roundtables to explore how innovative financial instruments can be used to solve challenges related to patient capital in under-served sectors like climate tech.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes were made to this output during the past year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress has been made on recommendation from last year's AR, as shown in the table below.
Recommendations	Action
TSF team should engage with Government counterparts working on investment in tech e.g. Ministry of Electronics, Department of Economic Affairs, DPIIT, Niti Aayog and institutions such as SBI. This can sharpen our approach and create partnership opportunities on co-investment. Past engagements via G20 and Mahakumbh have helped strengthen G2G partnerships.	Completed. / TSF team engaged with Government stakeholders at various platforms like Start-up Mahakumbh, National Start-up-day and others; / MOU with SBI for joint initiatives on investment and Policy; letter of appreciation from DPIIT for UK-India collaboration on start-ups. TSF should keep the momentum.
(Ongoing) Technical support – TSF team and Fund manager to continue to track opportunities for helping reduce policy barriers in new sectors. Team to liaise with x-HMG teams, BII and partners for knowledge sharing and driving collaboration actively.	Ongoing / TSF team to continue to work with x-HMG teams on Tech, DHCs, DBT and others for collaboration opportunities.

Lessons learnt
- There is scope to further leverage expertise at partner level to influence policy landscape. This can help maximise impact without pressure on scarce resources.
- Expertise within the portfolio investees’ can also help shape the UK’s wider tech strategy in India. Active engagement at strategic level can help drive success.

Recommendations for next year:
- TSF team to scope policy initiative under the SBI MoU that help unlock barriers for tech sector in India. This can be used to engage and positively influence financing institutions both locally and internationally to bridge funding gap. Action: SRO/PRO to review progress plan with SBI.
- Engage with x-HMG team working on Tech and Security Initiative, Research and others for collaboration opportunities. Action: SRO/Inclusion Lead (ongoing)

Output Title	Mainstreaming Gender and inclusion in the investment portfolio and disseminate learnings
Output number:		Four	Output Score:	B
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Participation of women in workforce and at senior levels in businesses	At least 25% portfolio aligns with gender inclusion targets	Achieved. / TSF Fund Managers have integrated Gender Action Plan in their core strategies which has led to progress. Compared to last year, out of 17 investees, c.30 % have achieved set milestones on inclusion. About 4-5 investees have recently been added to the portfolio and their progress will be captured in the next AR. There is however a good scope in improving the gender numbers further.
New initiatives to embed gender and inclusion in the portfolio and inform the sector	Target: 6	Achieved. / Several initiatives taken up by FCDO, Fund Managers and investees. These include capacity building, policies on gender and recruitment; advocacy events with the industry. Details below.

Briefly describe the output’s activities and provide supporting narrative for the score
The output has scored B. Some parts of the portfolio have shown signs of progress; there is further scope to improve. This requires structured and long-term engagement to create a systemic impact. Targeted initiatives such as ‘Gender Action Plan’, policy initiatives and focused recruitment strategies have brought about the change. These action plans are designed to create measurable improvements in gender representation across all levels of the organization, from entry-level positions to senior leadership roles. There are some positive developments worth noting. However, consistent effort is required to make an impact given low representation (<15%) of women in start-up sector. Some positive examples include:
- Avaana capital’s portfolio companies have 28.5% women employees
- Neev II portfolio companies have 33% women employees
- At Chakr Innovation, women constitute 42% of the management team
- At Nutrifresh, women constitute 59% of the workforce and 33% of management team
- Dreamfly, with a woman co-founder has 67% women at managerial positions
- Phyx 44 and Dharaksha have 25% women representation in managerial roles
Progress at Fund level
TSF team engaged with the Fund Managers to encourage a gender diverse mix of start-up founders in the portfolio. This year for the first time, three new start-ups were on-boarded that are co-founded by women. The proportion of women at leadership roles in the portfolio is around 25%. The following initiatives are taken across the portfolio level in gender mainstreaming:
- Women mixers events: Avaana curated a formal network of women investors / entrepreneurs and organised outreach events across cities. This helped in x-learning and building networks in the climate tech space for women leaders, entrepreneurs and investors.
- Neutral Policies at work: Implementing non-discrimination as part of policies, ensuring equal opportunities in hiring, promotion, and other practices. FCDO’s ESG framework includes specific policies on safeguarding and reporting concerns to help create conducive work environment.
- Creating new opportunities ideas: TSF team and Avaana joined up with GOI teams to support Grand Challenge for tech start-ups. c.40% of the applicants were women-led or women co-founded startups. c.35% of the shortlisted finalists were start-ups founded by women which points to a positive response if the right tools are used.
- Nutrifresh, an investee in the sustainable farming organised specialised training programmes for its workforce – largely women - on advanced farming and operational technology.
Other initiatives at TSF level
In May ’25, TSF team organised learning sessions on ‘Gender in Businesses’ for the portfolio companies. More than 40 participants from funds and investees participated in the workshop. This helped nudge the partners to deepen gender mainstreaming during recruitment, promotions and develop inclusive workplace policies.

In March ’25, UK Government organised a workshop on ‘advancing women in investment industry’ with new cohorts of fund managers and entrepreneurs. The panels discussed structural barriers, opportunities and strategic levers to remove gender bias through policy. The event was also attended by GOI erstwhile Cabinet Minister who supported the initiatives.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes were made to this output during the past year.

Progress on recommendations from the previous AR (if completed)

Recommendations	Action
Presence of Fund Managers on Boards of investees has helped drive inclusion in senior management. Fund Managers and TSF team need to actively track progress on women in decision making roles. Action: TSF team/Fund managers on quarterly basis.	Completed. TSF team tracks progress via periodic reporting and discussions.
Lesson learning within portfolio and dissemination of best practices help cross pollinate ideas which can positively impact results overall. Action: TSF team/Fund managers. Action: TSF team.	Completed. TSF team organised x-learning sessions within the portfolio and industry stakeholders. Details above.
Update Logframe with milestone on gender and inclusion with targets for outer years. Action: TSF team by August ’24.	Logframe to be reviewed by September ’25.

Lessons learned this year
- Active engagement on Gender has yielded positive results. It is important to continue to engage at investee levels to understand challenges on ground. This approach has led to higher accountability towards the gender mainstreaming agenda.
- Dedicated sessions on gender mainstream help raise awareness. It is important to ensure these do not remain women-only discussions to ensure wider impact.
Recommendations for the year ahead
- There is potential to join up with relevant Government stakeholders given GoI’s ‘Nari Shakti’ (translated as ‘women power’) initiative. This will help TSF team x-learn and raise profile of the UK initiatives in India. Action: Inclusion and Sustainability lead to develop plan by Aug ’25.
- TSF team to feed into the Women and Girls strategy for FCDO. It will be important to further align the current portfolio’s gender activities to achieve the objectives laid out in the strategy. Action: Inclusion and Sustainability lead to provide inputs and feedback / case studies.
- TSF team to organise capacity building sessions with implementation partners for x-learning. Team to consider co-designing with industry platform for a systemic impact Action – PRO/Inclusion Lead to develop plans by August ’25 and organise by Q3 2025.

Key cost drivers and performance
Key cost driver is management fee charged by Fund Managers from the investors to cover the costs of running the fund. The management fee generally tends to decrease after the initial commitment period once the fund starts exiting from portfolio.

VfM performance compared to the original VfM proposition in the business case
A brief assessment of the VfM indicators against those set out in the Business Case is provided below.
Economy: Investments under TSF are expected to create development impact and also generate financial returns for the taxpayers. This is a feature available only in the case of FT which enables a return of capital to be recycled for other initiatives. Fees and costs of the funds are competitive vis-à-vis market and have been agreed after competitive bidding, rigorous negotiations and market benchmarking.

Efficiency: TSF leverages on efficiency and pace of delivery of private sector by partnering with private fund managers and investees. TSF builds on the ability of partners to scale their businesses by unlocking other investors. During the review period, several portfolio investees expanded footprint across the country. This enables TSF to multiply the impact created through the same investment.

Effectiveness: TSF has unlocked more than 8x in co-investment from other investors for every £ of invested capital. This has resulted in increased effectiveness of the UK’s investment. TSF benefits from association with credible co-investors who facilitate in spotting opportunities with their existing networks. This has already led to unlocking c.£240m of capital overall across the portfolio. TSF has benefitted more than 0.8m women and men including from marginalised communities who are most affected by climate change.

Equity: TSF focuses on delivering for a diverse set of beneficiaries across gender and income groups. This is achieved by way of selection of Fund managers who align with our approach on development impact. Each investee fund has a focus on inclusion and diversity. The Fund Managers ensure this is embedded in approach at the portfolio level. All investments are screened by the development committee at the Fund Manager to ensure there is alignment. Progress on development indicators, gender and ESG is tracked periodically by TSF team.

Assessment of whether the programme continues to represent value for money
TSF has delivered strong results against the target indicators as mentioned above in the outputs and at outcome level. For example, number of jobs generated is higher than the target and the population benefitted has met its target milestone. TSF has also met its target to attract new investors into climate sectors. With an extended investment budget, TSF will now focus on increase its influence and building on economies of scale. As Fund managers are on-boarded, TSF will widen its reach to pioneering sector and businesses. TSF remains strategically aligned to UK India partnership priorities.

E: RISK

Overview of risk management
The overall risk rating for the Programme has remains ‘Major’ due to the high risk of failure amongst start-ups. The appetite for each of the risk categories has been uploaded on to AMP for this Annual Review. The net risks identified were all largely minor or moderate, and so remained within the overall risk appetite. The team reviews the risk register regularly. Risk forms a part of regular conversations with programme partners. Key risks are noted below.

Risk Category	Risk Description	Residual Risk	Mitigation Strategy
Strategy & Context	Lack of political support (UK /India) – shift in government policies, laws and regulations leading to programme being closed early.	Minor	Programme has been identified as part of joint priorities and delivers on climate which is central to the G2G partnership. / GOI acts a co-investor in the funds selected and Start-up India is a flagship initiative of the GOI. / MoU signed with State Bank of India – GOI’s largest financial institution to strengthen the UK-India corridor with joint investments and policy initiatives in climate and tech sectors.
Policy & Programme Delivery	Failure to identify suitable Investee Fund Managers leading to delay in investment of full FT budget.	Moderate	Investment / procurement process is driven via UK India Development Cooperation Fund (UKIDCF) who have the necessary expertise on selection and contract negotiations. / Early market engagement; clear selection criteria for the Fund Manager; Fund manager appointed with a track record in asset management in similar sized funds, sectors though competitive transparent processes; robust due diligence as per best practices.
Policy & Programme Delivery	Financial risk – Loss of FCDO capital due to investment failure and/or unfavourable exchange rate fluctuations.	Moderate	Appointment of Investee Fund Managers with a track record in asset management in similar sized funds, sectors. / Investment Committee will take decisions based on rigorous analysis of the potential investment opportunity with experts on committee. / Regular oversight by team members on portfolio performance and quarterly/ annual reporting and monthly meetings with Fund Managers. / Periodic interactions with the Fund Manager and the portfolio entities to assess the financial performance and take adequate course correction measures if the investment is not on track. / Deep dive analysis of the valuation reports and cashflow assumptions in the report to avoid any future surprises.
Reputational	Financial frauds, / safeguarding and ESG risk at Fund and Investee level leading to risk of reputation.	Moderate	Careful examination of investments by the Programme team / Investment Committee / development framework before every approval. Continuous monitoring and timely action in case of incidents. / Quarterly utilisation reports, annual audited statement of accounts. / Performance linked incentives for Fund Managers and for their employees. / Timely escalation of suspected issues to Fraud Unit. / TSF is developing a standard operating approach with HQ for managing risks.
Financial & Fiduciary	Valuation Risk: Difficult to assess the valuation of private companies/ Start-ups leading to potential fraud or collusion between Start-ups and/or Fund Managers.	Moderate	Due diligence on Fund Manager and selection based on past track record and experience of delivery. / Independent valuation for assessing financial performance on bi-annual basis and oversight with Finance department. / Independent audit of finances of Fund Managers on annual basis. / Quarterly and Annual reports.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
Summarise the performance of partners and FCDO, notably on commercial and financial issues.
As part of the programme management processes, TSF team receives regular quarterly, annual and audit reports from the Fund Managers. Their reports contain information on financial performance, risks, ESG, progress on development indicators and others. Monthly meetings are held to review programme progress with both funds. Site visits and promoter meetings are held time to time and prior to investment as part of the DevCom. Monitoring of the funds is carried out via the Investor Advisory Committee (IAC) comprising co-investors and the Fund Manager. There have been no issues on contract or financial compliance with both funds. The UK Government helps to shape the Fund’s overall strategy through representation on the IAC and the Development Committee.

Under the Technical Assistance part of the Programme, compliance related contracts were signed and implemented to seek advice on legal and tax matters. These contracts have clear objectives and deliverables with timelines. Payments are made in arrears and based on successful completion of milestones.

Disbursements are closely monitored, and forecasts are regularly reviewed and uploaded on to programme and financial management systems. Payments are made in ongoing projects only after outputs undergo mandatory quality assurance process by the SRO. The FT agreement with the Neev II and Avaana Fund Managers has built in forecasting and reporting requirements such as annual audited reports, valuation reports, Quarterly progress report, and ESG reports for periodic monitoring review.

The Programme spend as of 30th May 2025 is £14.28m consisting mainly of FT. Available resources have been utilised through careful programme management and informed choices with inputs from experts. The management of contracts, finances, and delivery expectations have remained of the highest standards and demonstrated economy and efficiency.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
The programme performance is measured against the results framework, work plan and previous year’s recommendations. The programme was part of the MAP verification commission done by FCDO India Delivery Unit to check all the key documentation related to procurement, payments and programme implementation approvals. Information regarding the programme was added to PSCMD’s return seeking inputs for a review by the Independent Commission for Aid Impact (ICAI) on HMG investments/interventions that support energy transition, as the programme spends 70% of the budget on ICF. Monthly programme review meetings are held with Fund managers. Standing agenda items include risk management, finance management, investment pipeline, stakeholder engagement and relationships management. Fund Managers have regular meetings with investees and field visits are held to understand ground realities with periodic update to the Investment Committee and the Investor Advisory Committee (IAC). TSF team engages with Fund investees via site visits and Development Committee (DevCom) meetings. As part of DevCom, team has already visited the existing and potential investees of Neev II and Avaana. Dignitaries from UK have also visited investee companies at various opportunities.

Evidence
The quarterly progress reports, financial reports, audit reports and annual impact reports shared by the fund managers are good evidence base for reporting progress made by the programme during the year. Field visits are also vital for gathering evidence and interacting directly with stakeholders. The programme team had undertaken site visits and holds regular monthly meetings with the Fund Managers to discuss the progress and future pipeline.

Learning
The learnings during the year have been captured under each Output in Section C.
Date of last narrative financial report	UKIDCF audited financial report as of Mar 2025. UKIDCF Valuation report as on 31 March 2025.	Date of last audited annual statement	Audited financial statements as on 31 March 2025.