Programme Completion Review

Title: South Sudan Health Pooled Fund - Phase 3
Final Programme Spend £ (full life): / £348.5m total, including: £154m (FCDO); £194.5m (other donors)	Review Date:	September 2025
Programme Code: 300427	Start Date: 24th January 2018	End Date: 31st March 2025 (end of implementation)

Summary of Programme Performance

Year	2018	2019	2020	2021	2022	2023	2024
Programme Score	B	A	A	A	A	A+	A+
Residual Risk Exposure Rating	Major	Major	Major	Major	Major	Major	Major

DevTracker Link to Business Case (and any addendum):	https://iati.fcdo.gov.uk/iati_documents/43101673.odt
DevTracker Links to all logframes used during programme lifetime:	https://iati.fcdo.gov.uk/iati_documents/D0004399.xlsx

List of Acronyms

ANC	Antenatal Care
AR	Annual Review
BEJ	British Embassy Juba
BHI and BHWs	Boma Health Initiative/Workers
C20, 21, 22	Consignment 20, 21, 22
CES	Central Equatoria State
CHDs	County Health Departments
CMEs	Continuing Medical Education
CPR	Contraceptive Prevalence Rate
CYP	Couple Years of Protection
DALYs	Disability-Adjusted Life Years
DHIS	District Health Information System
DMPA	Medroxyprogesterone acetate
EES	Eastern Equatoria State
EmONC	Emergency Obstetric and Neonatal Care
EPI	Expanded Programme on Immunisation
EU	European Union
FM	Fund Manager
FP	Family Planning
GAVI	Global Alliance for Vaccine and Immunisation
GBV	Gender-Based Violence
GESI	Gender Equity and Social Inclusion
GRSS	Government of the Republic of South Sudan
HFs	Health Facilities
HMIS	Health Management Information Systems
HPF3	Health Pooled Fund Phase III
HSTP	Health Sector Transformation Project
HW	Health Worker
ICPD@25	International Conference on Population and Development
INGOs	International Non-Governmental Organisation
IPA	International Procurement Agency
IPs	Implementing Partners
LQAS	Lot Quality Assurance Sampling
MNCAH	Maternal, Newborn, Child and Adolescent Health
MNCH	Maternal, Newborn and Child Health
MOH / MoHA	Ministry of Health / Ministry of Humanitarian Affairs
MUAC	Mid Upper Arm Circumference
NBeG	Northern Bahr el Ghazal
NGOs	Non-Governmental Organisations
OPD	Outpatient Department
PHCC	Primary Health Care Centre
PHCU	Primary Health Care Unit
QOC	Quality of Care
QSC	Quantified Supervisory Checklist
RCCE / RRC / RMNCH	Risk Communication and Community Engagement / Relief and Rehabilitation commission / Reproductive, Maternal Newborn and Child Health
SBA	Skilled birth attendant
SEAH	Sexual Exploitation, Abuse and Harassment
SGBV	Sexual Gender Based Violence
SIDA	Swedish International Development Agency
SMOH	State Ministries of Health
SRM	Strategic Relationship Management
UN	United Nations
UNFPA	United Nations Population Fund
UNICEF	United Nations Children's Fund
USAID	United States Agency for International Development
VFM	Value for Money
WASH	Water, Sanitation and Health
WB	World Bank
WBeG	Western Bahr el Ghazal
WES	Western Equatoria State
WGSSQ	Washington Group Short Set of Questions
WHO	World Health Organisation

A. Summary and Overview

Figure 1: Map showing HPF3 interventions across South Sudan

Description of the programme and what it has achieved The Health Pooled Fund Phase 3 (HPF3), implemented from October 2018 to January 2025, was a flagship multi-donor programme that delivered life-saving health and nutrition services at scale across South Sudan. Operating in eight of the country’s ten states, HPF3 served as the humanitarian backbone of the health and nutrition response, reaching underserved and crisis-affected populations through both facility-based and community-level interventions. In the context of South Sudan’s protracted crisis, where population-level humanitarian needs remain acute, HPF3’s model prioritised coverage at scale with a strong focus on equity, ensuring access to essential care for even the most remote and vulnerable communities.
Funded by the UK (FCDO), Canada, Sweden (SIDA), USAID, the European Union, and Gavi, HPF3 mobilised a total of £348.5 million, with the UK contributing £154 million, accounting for 44% of the total funding. For every £1 of UK Official Development Assistance (ODA), the programme successfully leveraged an additional £0.79 from other donors. As the lead donor, the UK played a central role in managing and coordinating donor contributions, ensuring strategic alignment and effective use of pooled resources.
HPF3 also merged the previous HPF2 and Integrated Community Case Management (iCCM2) programmes, creating a unified platform for health service delivery. At its peak, the programme supported 797 health facilities and nearly 8,000 healthcare workers, including 4,400 Boma Health Workers (BHWs), significantly expanding access to primary healthcare across South Sudan.

HPF3 aimed to reduce maternal and child mortality while stabilising subnational health systems. It achieved significant gains: skilled birth attendance rose to 86.1%, modern contraceptive use more than doubled, and child wasting fell below emergency thresholds. Although we do not have population-level data on maternal and child mortality, these gains would certainly have contributed to stronger health outcomes. However, mid-cycle funding cuts forced a reduction in geographic coverage (from 8 to 7 states), withdrawal from 220 PHCUs and 9 state hospitals, and a scale-down in training, supervision, and GESI activities. These cuts tempered the programme’s original ambition and placed pressure on delivery systems.

Until 31st July 2024, HPF3 was delivered through a consortium led by Crown Agents Limited (CA), in partnership with Montrose International and the International Procurement Agency (IPA). The KIT Royal Tropical Institute led operational research until its exit in 2022 due to funding cuts. The programme was implemented through 19 Non-Governmental Organisation (NGO) Implementing Partners (IPs) operating at State and County levels, responsible for delivering services across initially eight states. A core feature of the delivery model was the centralised procurement and distribution of essential medicines and medical supplies, with kits delivered to supported health facilities three times per financial year, ensuring continuity of care in a highly fragile context. Following CA’s liquidation on 1st August 2024, Mott MacDonald was contracted to manage the closure phase, overseeing final payments, asset handover, and the transition to the World Bank and Government-led Health Sector Transformation Programme (HSTP).

Key achievements of HPF3 programme from 2018-2025 in the eight supported States of South Sudan.
- 86% of institutional deliveries were attended by skilled birth attendants, a critical intervention for reducing maternal and newborn mortality.
- 33 million+ outpatient consultations delivered, enabling timely diagnosis and treatment of common illnesses, preventing complications and deaths.
- 1.5 million children under one year of age received three doses of pentavalent vaccine, protecting against five life-threatening diseases; 40.6% reached through outreach, improving equity.
- Over 10 million children screened for malnutrition using MUAC, early identification and referral for severe acute malnutrition helped prevent child deaths.
- 9 facilities equipped for CEmONC and 147 for BEmONC, ensuring comprehensive and basic emergency obstetric and newborn care was available to manage life-threatening complications.
- 358,00 new family planning users and 254,000 couple years of protection, reducing maternal deaths by preventing unintended pregnancies.
- 7.1 million community-level treatments provided by Boma Health Workers, timely care for malaria, pneumonia, and diarrhoea, the leading causes of child mortality.
- Health information reporting reached 100% at facility level and 99.6% at community level, enabling data-driven decisions.

The programme operated in a context of chronic insecurity, conflict spillovers and refugee influx from Sudan, internal displacements, and climatic shocks, including widespread flooding and conflict-related disruptions. The outbreak of the COVID-19 pandemic and other epidemics e.g Ebola, Yellow fever, Measles, Cholera and Malaria,among others, caused unprecedented challenges and risks during the implementation of the HPF3. At the same time, a worsening economy with very high levels of inflation and drastically reduced government revenues reduced the government’s ability and willingness to contribute to health. In FY 22/23, only 0.7% of total the Government of South Sudan’s (GoSS) spending went to health (approximately US$10m which is less than $1 per capita per year) with an allocation of 2% for FY 23/24. This is well below the Abuja Declaration, which calls for 15% of total national annual budgets to be allocated to health.

Despite the challenges, the programme continued to meet its overall objective of delivering primary health services to the population of South Sudan. HPF3 scored an A+ overall, as outlined in Table 1 below. HPF3’s success in delivering services, medicines, and commodities effectively in a fragile and conflict affected state (FCAS) provided a lifeline for the population, and despite the paucity of mortality data, certainly saved countless lives. Given the challenging operating context, the ambition of Output 4 on health systems strengthening was reduced over time, with increased emphasis on stabilisation of existing systems and services.

Output	Score	Definition	Description
1. Facility-based service delivery	A	Met expectation	33m+ Outpatient department (OPD) visits, 86% births attended by skilled birth attendants (SBA), 254,000 Couple Years of Protection (CYPs); reduced coverage due to funding cuts.
2. Community-level interventions	A+	Moderately exceeded expectation	Over 7m children treated, 92% defaulter referral, 14.7m reached via family health sessions; strong Boma Health Initiative (BHI) rollout.
3. Supply chain	A+	Moderately exceeded expectation	98% timely delivery; expired reduced to 16%, 90% tracer availability, 100% reporting.
4. Health systems strengthening	A	Met expectation	100% DHIS/Boma reporting, high proportion of health facilities receiving county level supervision.
5. Value for money, equity, and inclusion	A	Met expectation	Cost per consultation £2.82, and £17.04 per Disability-Adjusted Life Year (DALY) averted.

As the final phase, HPF3 was extended to December 2024 to support the transition to HSTP, which began in July 2024. While HPF3 leaves behind a strengthened subnational health system and critical service delivery infrastructure, the sustainability of these gains hinges on continued investment, government ownership, and resilience in the face of ongoing instability.

Major lessons learned, evidence generated and recommendations

HPF3 demonstrated that it is possible to deliver high-impact, cost-effective basic health and nutrition services in one of the world’s most complex humanitarian settings. Over the course of the programme, more than 33 million consultations were provided, ,nearly 8,000 health workers, were supported and over 250,000 couples were protected from unintended pregnancy. . HPF3 also underscored the importance of embedding gender equality and social inclusion (GESI), community engagement, and data-driven decision-making into health programming. HPF3’s integrated delivery model, linking facility-based care, community-level interventions, and a robust supply chain proved both resilient and cost-effective, with a cost per consultation of just £2.82 and £17.04 per Disability-Adjusted Life Year (DALY) averted.

However, HPF3 also revealed the fragility of health gains in the face of funding volatility, insecurity, and climate shocks. Mid-cycle budget cuts led to reduced coverage, withdrawal from 220 Primary Healthcare Units (PHCU), and scaled-back training and supervision. The programme’s experience underscores the need for a more integrated approach between government, humanitarian and development actors, especially as South Sudan transitions to the Health Sector Transformation Project (HSTP). Without working more closely with government and strengthening its health system, there will be no clear pathway out of the current dependence on donors to support basic health service delivery. Ultimately, HPF3 maintained GoSS’s donor reliance , and a third party led implementation model that did not strengthen government institutions and systems as capacity-building was outside programme scope.

Implementing Partners (IPs) played a central role in HPF3’s success, acting as the operational backbone of service delivery, capacity building, and innovation. Their deep contextual knowledge, flexibility, and ability to operate in insecure areas were critical. As South Sudan transitions to the HSTP, the role of IPs must evolve from direct service delivery to technical assistance, mentorship, and systems strengthening.

Key lessons and recommendations from HPF3 are summarised as below for implementation under future programming, particularly HSTP:

- Drive and push for stronger GoSS commitment to the health sector, including through budget execution and payment of healthcare worker salaries.
- Establish a joint mapping and coordination mechanism between HSTP and the Health and Nutrition Cluster to regularly identify underserved populations and align service delivery, ensuring gaps in coverage are promptly addressed through complementary interventions.
- Integrate nutrition into routine services by maintaining Mid-Upper Arm Circumference (MUAC) screening, linking to treatment pathways and counselling, and coordinating with WFP/UNICEF for supply continuity.
- Strengthen CHD and SMoH capacity and accountability for planning, supervision, and coordination within HSTP.
- Preserve and expand the Boma Health Initiative (BHI) to ensure continuity and equity of community-based services, especially in hard-to-reach and crisis-affected areas beyond health facility catchment areas.
- Phase integration of multisectoral community activities and services within BHI such as disease surveillance, WASH, and nutrition.
- Use data for decision-making by sustaining DHIS2 investments, ensuring data quality, and building local capacity for analysis and use at all levels, including integration of Health and Nutrition Cluster data into DHIS2 to improve visibility of humanitarian needs and ensure more coordinated, life-saving responses.
- Maintain a unified national supply chain with buffer stocks and last-mile delivery capacity that serves both routine and emergency needs.
- Institutionalise biometric HR and payroll systems to improve transparency, reduce fraud, and ensure timely payment of health worker incentives.
- Strengthen family planning services by ensuring consistent commodity supply through maintaining close coordination with UNFPA, tailoring commodities to demand, and embedding adolescent-friendly and male-inclusive approaches.
- Invest in WASH and infrastructure at Primary Healthcare Units (PHCUs) and Primary Healthcare Centres (PHCCs) to sustain quality of care and infection prevention and control, particularly in flood-prone areas.
- Embed GESI and accountability mechanisms across all platforms, including feedback loops, disability inclusion, and GBV response in both development and emergency settings.
- Redefine the role of IPs to focus on technical assistance, mentorship, and systems strengthening, while maintaining readiness to surge in humanitarian contexts.

How this reviewwas conducted

The HPF3 Programme Completion Report was developed through a comprehensive mixed-methods approach, combining routine programme data, independent surveys, and field-based validation. Quantitative data was drawn from the national District Health Information System (DHIS2), and Implementing Partner (IP) reports. Key outcome indicators were validated through Lot Quality Assurance Sampling (LQAS) surveys conducted in 2020 and 2023. Qualitative insights were gathered through field visits, supervision reports, and insights captured from meetings with implementing partners and government stakeholders. KIT Royal Tropical Institute contributed to operational research and healthcare access studies during the programme’s early years, providing valuable evidence on service reach and equity. A team of British Embassy Juba Health advisers and programme specialists conducted the report.

Actions following approval of this report

Below are remaining follow up actions that will be required after completion of this review:

- Final HPF3 invoices relating to Crown Agents Liquidation to be paid alongside internal financial closure.
- Follow up on disposal letters of assets transferred to HSTP partners, ensuring maximum VfM, and reclaiming of any lost assets/closure of FLAC cases primarily due to insecurity.
- Share lessons learned from HPF3 with HSTP partners.
## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	Estimated Programme total fund value (full life) up to £426.5 million. (£175 million UK contribution and £251.5 million from other donors)	£348.5 million (£154million UK contribution and £194.5 million from other donors)
Timeframe	5 Years	6 Years
Outcomes	Improved health and nutrition outcomes / Improved community accountability	Met expectations

Overall assessment of programme outcomes, sustainability and VfM

The HPF3 programme made notable strides in improving health and nutrition outcomes for the population it served, but the extent of achievement must be viewed within the context of its limitations and the persistent humanitarian crisis in South Sudan.

HPF3 significantly expanded access to lifesaving services. Over 554,000 deliveries in health facilities were recorded, with 86.1% attended by SBAs. Modern contraceptive use rose to 11%, and the prevalence of child wasting dropped to 5.6% in 2023 from 16.2% in 2019. The programme supported over 33 million outpatient consultations and vaccinated 1.5m children with three doses of pentavalent vaccine. Community-level interventions were equally impactful: BHWs treated over 7m cases of malaria, pneumonia, and diarrhoea among children under five, and over 10 million children were screened for malnutrition. These results reflect a strong service delivery model in an FCAS combining facility-based care, outreach, and community engagement.

However, these gains were not uniform across the country. HPF3 did not cover the entire population, and its reach was constrained by funding cuts, the transition of Unity State to other programmes, insecurity, and logistical challenges, particularly in remote and flood-prone areas. Community-level interventions, such as the BHI, expanded access to care, but coverage gaps remained, especially in underserved bomas and among displaced populations. These gaps underscore the importance of stronger coordination with humanitarian actors, particularly through the Health and Nutrition Clusters, to ensure that populations outside HPF’s reach are identified and supported by humanitarian partners.

Data limitations further complicate the assessment: outcome indicators relied heavily on Health Management Information System (HMIS) data, which is of variable quality, and population figures are based on an outdated 2008 census, failing to account for population growth, displacement, and returnee influxes. Survey data were infrequent and geographically limited, making it difficult to assess the representativeness of findings.

Community accountability mechanisms were strengthened through the BHI and facility health committees, with high levels of client satisfaction reported. County-led supervision and quality improvement visits were conducted in nearly all facilities, reinforcing local oversight and accountability. These achievements demonstrate that community engagement and decentralised governance can be effective even in fragile settings.

The programme achieved a cost per consultation of £2.82 and a cost per DALY averted of £17.04, well below global benchmarks. Equity was a core focus: 56% of the population reached through BHI lived more than 5 km from a health facility. Services aimed to be inclusive of people with disabilities, adolescents, and survivors of GBV. However, significant equity gaps remain. Large swathes of the population were not covered due to insecurity, geographic isolation, and funding constraints. The withdrawal from 220 PHCUs and 9 state hospitals further reduced access in underserved areas.

HPF3 laid a strong foundation for long-term resilience through investments in biometric HR systems, DHIS2, and CHD capacity. However, mid-programme cycle funding cuts exposed vulnerabilities in infrastructure, training, and supervision. The transition to HSTP offered an opportunity to consolidate gains, but will require continued investment, government ownership, and flexible funding to respond to shocks and close persistent equity gaps. One of the major constraints to the sustainability of the health system is limited domestic investment in basic health service delivery.

Acute humanitarian needs, widespread poverty, and systemic barriers, such as poor infrastructure, insecurity, and health worker attrition, continue to undermine equitable access and sustainability. While HPF3 laid a strong foundation for future programming, the outcomes achieved reflect progress within a constrained and fragile context, rather than concrete steps toward health system strengthening. Its greatest success was saving lives at scale, particularly by expanding access to essential services in underserved and crisis-affected areas. These achievements were driven by a strong humanitarian imperative and proved more effective than many traditional humanitarian approaches by combining service delivery with long-term systems support.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.

The HPF3 Theory of Change, set out in Figure 2, explains how HPF3’s inputs, namely the provision of essential medicines and equipment, support to State MoHs and CHDs and technical support and oversight including training and supervision to health workers would lead to:
Delivery and increased availability/readiness of quality health services at facilities.
Community level interventions that increase awareness, prevention, and treatment of common conditions.
Availability of safe, effective and quality essential medicines and supplies.
Stable health systems that enhance accountability and are responsive to the needs of the people.
Funds and processes that are efficient, effective, inclusive and offer value for money.

The achievement of these outputs was expected to result in increased coverage, access and utilisation of quality lifesaving health, sexual and reproductive health, and nutrition services (the programme outcome) which will lead to improved health and wellbeing for the population of South Sudan (the programme impact). HPF3 programme contributed meaningfully to the impact of increased delivery and uptake of health and nutrition services that save lives and reduce morbidity, but the achievement was partial and context-bound. Key service indicators, such as institutional deliveries, modern contraceptive use, and child wasting, showed marked improvements in HPF3-supported areas. However, the programme did not cover the full population, and its reach was reduced over time due to funding cuts and insecurity.

The theory of change makes a range of assumptions including that health workers and civil servants are paid by the government, that funding levels are maintained, clinical staff are enrolled on government payroll system, commodity supply is robust, UN partners continue to provide nutrition commodity support, that humanitarian partners provide famine reduction support and funding for surveys is available. The assumptions underpinning the theory of change held only partially. While improved access and quality did lead to better outcomes where services were available, the assumption of government capacity and accountability was challenged by limited public sector engagement, inconsistent health worker payments, and weak responsiveness to community feedback. Political and security instability further undermined service continuity. Data limitations, reliance on outdated census figures and infrequent surveys, also constrained the ability to fully assess impact.

Under HSTP, achieving this impact will require expanded geographic coverage, stronger government stewardship, reliable health worker salaries, robust data systems, and deeper community engagement, especially in underserved bomas. Sustained investment in infrastructure, supply chains, and emergency preparedness will be essential to ensure equitable and resilient service delivery. This will be increasingly challenging with aid reductions.

One important change to the outcome and impact indicators in Year five was the removal of a “Lives Saved” indicator. It was agreed that this indicator would no longer be tracked in Y5 and beyond because of the complicated, multifaceted methodology used to calculate it, and the fact that it resulted in unrealistic figures.

Closeout and transition to HSTP indicators

The transition from HPF3 to the HSTP was guided by a structured closeout framework and programmatic indicators, which included mentorship, asset handover, contract closure, and documentation. One of the key successes was the tailored mentorship provided to new HSTP IPs seven lots. HPF3 IPs, in collaboration with County Health Departments (CHDs), conducted targeted sessions to transfer institutional knowledge, tools, and operational practices. Champions were identified within CHDs and health facilities to sustain institutional memory and continuity. Additionally, over 5,000 assets were successfully transferred to UNICEF, CHDs, and local NGOs, with all documentation completed and signed off by recipients.

Despite these achievements, the transition faced several challenges, particularly in navigating the political economy of South Sudan’s health sector. Moving from a third-party implementation model to one led by the UN and more closely aligned with government systems introduced new layers of complexity. Managing expectations from various actors, some of whom viewed the transition as an opportunity for influence or resource capture, required careful diplomacy and strong donor coordination. Delays in onboarding new HSTP IPs led to compressed mentorship timelines, particularly in conflict-affected areas like Tambura. Staff attrition and the liquidation of Crown Agents created temporary gaps in financial reporting and contract management, which were mitigated somewhat by Mott MacDonald’s takeover. Nonetheless, the programme achieved nearly all its closeout milestones, including full staff demobilisation, contract closure, and documentation archiving.

Figure 2: HPF3 Theory Of Change

## C: Detailed Output Assessment

Output Number 1 and Title	Delivery and increased availability/readiness of quality health services at facilities.
Output Score	A
Impact weighting (%)	40	Impact weighting revised since last AR?	No

Output Indicator	Baseline (March 2019, other than for 1.4 and 1.6, in March 2020)	Final Logframe Target / (Year 5, March 2024)	Final Result Achieved (Year 5, March 2024)
Indicator 1.1 Number of deliveries in a health facility attended by a skilled birth attendant (SBA)	55,793	80,630	86,921 (107.8% performance)
Indicator 1.2: Number of children vaccinated with three doses of Pentavalent vaccine	190,590	302,912	330,934 (109.3% performance)
Indicator 1.3: Number of outpatient consultations (disaggregated by sex, age)	6,356,022	4,226,611	4,265,404 (100.9% performance) / Total Males: 1,707,551 / Total Females: 2,557,853 / Total under 5 consultations: 1,592,181
Indicator 1.4: Percentage of health facilities delivering a minimum number of modern methods of contraception available (3 methods for PHF, 5 for UHF)	Peripheral: 28% / Health facilities: 64%	Peripheral: 75% / Health facilities: 92%	Peripheral: 68.8% (91.7% performance) / Health facilities: 92.3% (100.3% performance)
Indicator 1.5: Couple Years of Protection* (CYPs) delivered.	32,084	49,970	52,515.6 (105.1% performance)
Indicator 1.6: Number of new users of modern family planning methods.	48,771	63,332	70,773

 * The estimated protection provided by family planning services during a one-year period, based upon the volume of all contraceptives sold or distributed free of charge to clients during that period.

Output 1 aimed to increase the availability and readiness of quality reproductive, maternal, and child health services at health facilities across South Sudan. The programme delivered strong results across all six logframe indicators, scoring an A+, with five exceeding targets and one (minimum contraception availability at peripheral facilities) narrowly missing the target.

Coverage: HPF3 made significant strides in expanding access to essential health services across South Sudan, particularly in maternal and child health, immunisation, and family planning. Despite a 36% reduction in supported health facilities by Year 5, the programme maintained or exceeded most service delivery targets, demonstrating strong resilience and adaptability.

Equity: Equity was a central focus - services reached remote and underserved populations through outreach and boma health worker strategies, while gender and disability inclusion were embedded in facility design and community engagement. However, persistent challenges, such as insecurity, flooding, staff shortages, and cultural barriers, limited access in some areas. Disparities existed in performance across states with Western Bahr el Ghazal underperforming on most indicators except 1.2 and 1.4, and Lakes and Warrap falling short on at least two indicators. These gaps highlight the need for targeted interventions to ensure equitable service delivery across all states. Addressing these systemic barriers remains critical for improving equitable health outcomes in South Sudan.

Indicator 1.1: Percentage of deliveries in HPF3 supported health facilities attended by a skilled birth attendant (SBA - doctor, clinical officer, nurse, or midwife). / Source: DHIS2 (routine HMIS data), validated through LQAS surveys and partner reports / Moderately exceeded expectations

This indicator is used to monitor the effectiveness of the health system in providing safe delivery care, which is a key determinant of reducing maternal and neonatal mortality. In total, during HPF3, there were 554,397 institutional deliveries of which 477,160 (86.1%) were attended by skilled birth attendants (SBAs). In Year 586,921 deliveries were attended by SBAs, exceeding the target of 80,630 (107.8%). The steady increase of SBA attended births annually from 69.1% during the inception period to 85.9% by the end of the project period, highlights the extent of progress. HPF3 also ensured that 94.5% of mothers received uterotonics in the third stage of labour. These efforts, combined with training, community outreach, demand creation activities, and incentives for antenatal and delivery service uptake, created a more accessible environment for maternal health services.

HPF3 supported nearly 8,000 healthcare workers with regular incentive payments, which were critical for motivation, retention, and consistent service delivery in fragile and remote settings. A biometric system was introduced to verify healthcare workers and eliminate ghost workers and fraudulent payments, enhancing accountability and ensuring that only verified staff received incentives at the facility level.

Despite these gains, only 6 facilities met all 7 BEmONC signal functions and 7 met all 9 CEmONC functions. Gaps in equipment (e.g. vacuum extractors), staff confidence, and training limited full readiness. Insecurity, flooding, poor roads, and staff attrition also disrupted service continuity in some counties.

Indicator 1.2: Number of children (under 1 year of age) vaccinated with three doses of pentavalent vaccine DTP-HepB-Hib) at 6,10, and 14 weeks of age according to the national immunisation schedule in HPF3 supported states. / Source: DHIS2 / Moderately exceeded expectations

This indicator is used as a proxy to measure immunisation coverage within HPF3 supported counties and to help identify gaps in vaccine delivery and uptake. A total of 1,507,219 children were immunised with at least three doses of pentavalent vaccine, with 40.6% reached through outreach strategy across the programme implementation period with up to 330,934 children under one having received third dose of pentavalent vaccine in Year 5 (109.3% of target). This strong performance was supported by fixed, outreach, and mobile immunisation strategies, including Periodic Intensification of Routine Immunisation (PIRI) in flood-prone and hard-to-reach areas. HPF3 also immunised 286,495 children against measles and 212,687 people against COVID-19, demonstrating successful integration of routine and emergency immunisation. During donor monitoring visits in Torit, Yei, and Juba in 24/25 we observed the positive impact of HPF3’s tickler file system which was used by healthcare workers to identify and trace children missing immunisation appointments, linking them to BHWs. IPs played a key role in supporting health facilities to conduct outreach sessions.

However, it is important to note that progress stagnated in Year 3 and 4 as a result of fewer HPF3 supported health facilities and mobile sessions due to budget cuts. Measles coverage also remained below target, raising concerns about immunity gaps and the risk of outbreaks. Contributing factors included vaccine stockouts, cold chain limitations in remote areas, and population displacement due to flooding and insecurity. Strengthening last-mile delivery and improving coordination with national immunisation campaigns will be critical for future programming.

Indicator 1.3: Number of outpatient department (OPD) consultations (disaggregated by sex, and age) in HPF3 supported health facilities. / Source: DHIS2 / Met expectations

This indicator is used to monitor access to and utilisation of health services; to identify health-seeking behaviour patterns across different population groups; to support planning and resource allocation in health systems and to track equity in service delivery. During HPF3 implementation, a total of 33,091,346 OPD curative consultations were managed in HPF3 supported HFs, of whom, 63% (20,838,893) were above five years and 37% (12,252,453) were under five years old. Out of the 33 million consultations, 4,265,404 OPD consultations were recorded in Year 5, slightly exceeding the target of 4,226,611 (100.9%). Of these, 37% were for children under five. There is a drop of around 2 million consultations from Y3 to Y5 as a result of the reduction in HPF3-supported HFs. The programme maintained service utilisation despite reduced facility coverage, supported by integrated outreach and improved drug availability.

HPF3 also demonstrated strong performance in nutrition service delivery, particularly in the management of severe acute malnutrition (SAM). Cure rates in both Outpatient Therapeutic Programmes (OTP) and Stabilisation Centres (SC) consistently exceeded the SPHERE standard of 75%. Over 10 million children were screened using MUAC, with 2.8% identified as SAM and referred for treatment. Integration of nutrition with health and WASH services, regular on-the-job coaching, and consistent supply of therapeutic foods and essential medicines contributed to these outcomes. However, challenges such as delayed referrals, incomplete reporting, and looting of supplies in some areas highlight the need for stronger coordination and protection mechanisms.

WASH infrastructure and infection prevention control (IPC) were critical enablers of quality service delivery in HPF3-supported health facilities. The programme introduced the WASH FIT tool, conducted assessments in over 500 facilities, and supported the construction of latrines, placenta pits, and incinerators. By Y5, 100% of hospitals and over 90% of PHCCs and PHCUs had handwashing stations and sharps containers. However, gaps remained in latrine functionality, water storage, and safe waste disposal, particularly in PHCUs. Flooding and poor soil conditions led to latrine collapses, and limited funding constrained infrastructure upgrades.

Service delivery was impacted by a range of political and security factors, notably including industrial action by healthcare workers in 2019 following the introduction of the harmonised Ministry of Health (MoH) incentive scales. This change represented a significant reduction in actual remuneration for many healthcare workers leading to widespread dissatisfaction and disruption of services. Additionally, political uncertainty during the formation of transition government in early 2020 further affected the programme operations, contributing to delays and operational instability in several regions. In Y2, three months of COVID-19 lockdowns affected service utilisation, while in Y3 the insecurity in Tambura County, Western Equatoria State, and Greater Tonj counties in Warrap State led to displacement of HCWs and looting of HFs which affected service delivery. In Northern Bahr el Gazal, user fees introduced in Y3 led to a 60% drop in utilisation, highlighting the sensitivity of service access to cost-sharing policies. Although reporting on DHIS2 was low, implementing partners supported county health departments to collect and upload data, and triangulated this against their own reporting to the Fund Manager.

Indicator 1.4: Percentage of HPF3 supported health facilities delivering a minimum number of modern methods of contraception available (3 methods for peripheral health facilities, and 5 for hospitals) / Source: DHIS2 / Moderately did not meet expectation

The purpose of this indicator is to assess availability and choice in family planning services; to monitor readiness of health facilities to meet contraceptive needs and to support planning and supply chain management for reproductive health commodities.
The percentage of hospitals which delivered five (5) or more FP methods increased from 64.0% (16/25) in Y1 to 100% (13/13) at the end of the project (Y6). In addition, peripheral HFs which delivered three or more FP methods increased from 28.4% (219/771) in Y1 to 67.2% (334/497) at the end of the project (Y6).
All supported hospitals met the target at 100%), whereas peripheral facilities achieved 67.2%, which was slightly below the 75% target. HPF3’s strong coordination with UNFPA was critical to ensuring that family planning commodities were prioritized within the HPF3 supply chain system: family planning commodities were included in regular drug consignments, and implementing partners were able to access additional supplies from UNFPA if needed. Stockouts, staff shortages, and cultural resistance affected peripheral performance. Nonetheless, method mix improved, with implants and injectables widely available.1,516 (660 female, 856 male) healthcare workers were provided training and or mentorship to improve their knowledge and skills on family planning.

Indicator 1.5: Couple Years of Protection (CYPs) estimates the protection provided by FP services over one year, based on all the volume of contraceptives distributed for free to clients during that period. / Source: Implementing Partners Reports - CYP=∑ (Quantity of each method distributed × CYP conversion factor) / Moderately exceeded expectations

This indicator estimates the protection provided by HPF3 supported FP services and enables us to compare service delivery at the subnational level.

HPF3 delivered 241,588 couple years of protection (CYPs) to women across the programme, with the highest CYPs generated from implants, followed by injectibles. There was stark variability between States, with Central and Western Equatoria generating over 50% of the over CYPs, with Unity and Lakes States under 5%, highlighting cultural barriers and misconceptions regarding long-acting reversible contraception.

The increased demand for long-acting reversible contraception (LARC) was driven by continuous medical education (CME) for 18,707 (7,120 female, 11,587 male) HCWs, provision of LARC equipment, and training on value clarification and attitude transformation (VCAT). Female condoms and emergency contraceptive pills generated the least CYPs at 0.1% (292/254,168) and 0.5% (1,315/254,168), respectively, due to low male consent and their use in emergencies.

The cost per CYP was £4.49, demonstrating strong value for money. However, stockouts of injectables (e.g. Sayana Press) in some counties affected method choice.

Indicator 1.6: Number of new users of modern family planning methods (individuals who began using a modern method of contraception for the first time, or after a significant lapse in use, during HPF3) / Source: Implementing Partners reports / Moderately exceeded expectations

This indicator is a proxy to assess the acceptance and uptake of family planning, and the effectiveness of community engagement and demand generation activities by boma and healthcare workers.
During the HPF3 implementation period, a total of 358,099 new users of modern family planning methods were registered, reflecting a significant expansion in access and uptake of FP services across South Sudan. The programme saw a steady increase in new users, with the proportion rising from 13.6% in Year 1 to 19.8% in Year 5. Except for Y3 (94.1%) and Y6 (88.6%), the programme achieved the annual milestone targets. During HPF3 implementation, WES had the highest number of new users at 29.8% (106,608/358,099), followed by CES at 15.4% (55,267/358,099) with Lakes State contributing to the least new users at 3.2% (11,492/358,099).
This growth was driven by a multifaceted strategy that included the development and implementation of a demand creation strategy on sexual and reproductive health rights (SRHR) and FP, the distribution of over 4,000 communication materials, and the training of 4,400 BHWs across 746 bomas. These BHWs played a pivotal role in raising awareness, referring clients to health facilities, and conducting targeted community meetings with key leaders to foster a supportive environment for FP. Raising awareness about the safety and efficacy of various methods and training HCWs was significant. Additionally, the programme recruited and trained male champions to engage men in SRHR discussions, which helped address cultural barriers and improve male acceptance of FP.

Despite these achievements, the programme faced persistent challenges, including negative attitudes among some healthcare workers (HCWs), myths and misconceptions about FP, and threats or intimidation from community leaders in certain regions. These issues were particularly pronounced in Lakes, Northern Bahr el Ghazal, and parts of Western Bahr el Ghazal and Eastern Equatoria. To address these barriers, HPF3 implemented Value Clarification and Attitude Transformation (VCAT) training for HCWs and community leaders, and promoted the use of women- and girl-friendly spaces and school health programmes to reach adolescents. The programme also highlighted the importance of integrating FP awareness into broader community engagement efforts, such as GESI and BHI activities, which helped build trust and optimise resources. These efforts contributed to a more enabling environment for FP uptake and laid the groundwork for sustained improvements in reproductive health outcomes.

B. Lessons learned through this output, and recommendations for future programming

Lessons learned:
- Integrated Service Delivery Enhances Impact: Combining facility-based services with community-level interventions (e.g. BHW referrals, outreach, and health promotion) significantly increased access and uptake of maternal, newborn, child health (MNCH), and family planning (FP) services.
- Health Worker Capacity and Motivation Are Central to Quality: Continuous training, incentives, mentorship, and supportive supervision of HCWs improved service quality, including SBA deliveries, newborn resuscitation, and post-abortion care. However, retention was challenged by lack of salaries, low incentives and poor working conditions.
- Infrastructure and Equipment Gaps Undermine Service Readiness: Inadequate infrastructure (e.g. maternity wards, water supply, lighting) and missing equipment (e.g. MVA kits, vacuum extractors) limited the ability of some facilities to provide full BEmONC and CEmONC services.
- Community Engagement Drives Service Utilisation: Demand creation through BHWs, community Chiefs, male champions, and women-friendly spaces increased ANC attendance, facility deliveries, and FP uptake.
- Data Use Improves Service Quality and Accountability: Routine data reviews at facility and county levels helped identify underperforming sites and guided targeted interventions (e.g. uterotonic use, newborn resuscitation).
- Gender and Social Inclusion Boosts Equity and Outcomes: Facilities with women-led committees and youth-friendly services saw improved uptake of SRH services. Addressing stigma and involving men helped overcome cultural barriers to FP.

Recommendations:

- Protect and Expand Gains in Family Planning: Ensure method mix availability at all levels of care.
- Institutionalise FP counselling and service delivery in ANC, PNC, and immunisation visits.
- Strengthen Referral Systems and Emergency Transport: Maintain and expand ambulance networks and referral protocols. Link BHWs and facilities through mobile communication and transport support.
- Strengthen defaulter tracing systems: Institutionalise collaboration between BHWs and vaccinators to maintain high referral rates for immunisation defaulters.
- Scale up community engagement strategies: Expand use of male champions, school health clubs, and women’s groups to address cultural barriers and improve health-seeking behaviours.
Sustain and scale up integrated outreach: Continue integrated BHW and outreach services in underserved areas to maintain coverage of ANC, deliveries, immunisation, and FP, and consider phased multisectoral integration of WASH and nutrition services.

Output Number 2 and Title	Community level interventions that increase awareness, prevention, and treatment of common conditions
Output Score	A+
Impact weighting (%)	25	Impact weighting revised since last AR?	No

Output Indicator	Baseline	Final Logframe Target (Year 5, March 2024)	Final Result Achieved (Year 5, March 2024)
Indicator 2.1 Number of cases of children under 5 in the community treated for diarrhoea, malaria, and pneumonia (disaggregated by diarrhoea, malaria, and pneumonia)	358,235 (2019)	1,557,781	1,673,686 (107.4% performance)
Indicator 2.2 Number of children in the community, below one year who have been identified as immunisation defaulters and referred	14,286 defaulters (2020)	Total defaulted and identified = 90,069 / Total defaulted and referred= 87,107 / Proportion of those referred out of total defaulted and identified = 97%	Total defaulted and identified = 74,460 / Total defaulted and referred= 74,333 / Proportion of those referred out of total defaulted and identified = 99.8%
Indicator 2.3 Number of community members reached for family health sessions	270,248 (2019)	3,913,998	4,565,186 (111.24% performance)
Indicator 2.4 Proportion of mothers and caregivers with children under 5 with knowledge of danger signs of childhood illnesses	52.8% (2021)	75%	45.5%
Indicator 2.5 Proportion of mothers who know at least three primary danger signs of pregnancy	64.9% (2021)	75.5%	78.8% (105.1% performance)

Output 2 aimed to strengthen primary healthcare through provision of services at the community level. HPF3’s community-level interventions significantly expanded access to essential health services in hard-to-reach areas through the Boma Health Initiative (BHI), scoring an A+ for Output 2. A total of 4,400 BHWs treated over 7.1 million cases of malaria, pneumonia, and diarrhoea in children under five. From Year 2 onwards, the programme was implemented across all 55 counties in seven of South Sudan’s ten states. However, coverage slightly declined from 746 to 634 bomas between Years 4 and 5 due to the transition of 112 bomas in Unity State to the UNICEF/World Bank-supported project.

Immunisation defaulter tracing was highly effective, with 92.7% of 430,676 identified children referred for vaccination. Over 14.7 million people were reached through family health sessions, and knowledge of pregnancy danger signs among women exceeded programme targets. Despite these achievements, challenges persisted, including frequent stockouts of BHI commodities, low literacy among BHWs affecting data quality, perceived low incentives, and uneven BHW distribution. HPF3 provided strong evidence of BHI’s critical role in delivering sustainable primary healthcare in an FCAS context.

This output measured implementation of the BHI, a GoSS initiative introduced in 2017 to strengthen community health services and improve awareness, prevention, and treatment of common conditions, particularly among children under five. Overall, all indicators met or exceeded expectations except for Indicator 2.4. On balance, the output was assessed to have moderately exceeded expectations, with a final score of A.

Indicator 2.1: Total number of children under five years old who received care for diarrhoea, malaria, or pneumonia by HPF3 supported boma health workers in the community. / Source: Community Health Information System and DHIS2 Moderately exceeded expectations

Over the course of HPF3, more than 7.1 million cases of diarrhoea, malaria, and pneumonia were treated at the community level, surpassing the 2024 target. This outcome underscores the effectiveness of the BHW model in delivering timely care to children in remote and underserved areas. Malaria remained the most frequently treated condition (49%), followed by pneumonia (28%) and diarrhoea (23%). The programme’s success in this area was driven by consistent availability of essential medicines, regular supportive supervision by Boma Health supervisors and implementing partners, robust last-mile delivery systems, and strong community trust in BHWs.

However, challenges persisted. Insecurity and seasonal flooding disrupted access in several counties, and occasional stockouts of key commodities, such as malaria rapid diagnostic tests (mRDTs), led to reliance on presumptive treatment. Despite these constraints, the scale and reach of community-based treatment under HPF3 represents a major achievement in reducing child morbidity and mortality in South Sudan.

Indicator 2.2: Proportion of children under 12 months who have missed one or more scheduled immunisation doses (defaulters) and have been identified and referred for follow-up or catch-up immunisation services / Source: Community health information system and DHIS2 / Moderately exceeded expectations

During HPF3 implementation, over 400,000 children were identified in the community as immunisation defaulters, with 92.7% (384,955/415,037) referred for immunisation services. The proportion of defaulters identified and referred for routine immunisation services increased from 82.9% in Y1 to 99.8% in Y5. In some counties, over 90% of referred children were confirmed to have received their vaccinations.

This high level of performance reflects the strength of the community-facility linkage system established by HPF3. BHWs played a central role in identifying defaulters and referring them to health facilities, using tools such as tickler files and household registers. Coordination between vaccinators, supervisors and BHWs was enhanced through shared defaulter lists and regular review meetings with community leaders.

BHWs played a pivotal role in community-based disease surveillance by identifying and referring immunisation defaulters and zero-dose children, contributing to early detection and response to outbreaks such as measles and yellow fever. To expand this role, future programmes should integrate BHWs into formal surveillance systems, equip them with mobile reporting tools, and train them in early warning signs of epidemic-prone diseases.

Nonetheless, the programme faced difficulties in tracking outcomes for all referred children, particularly in areas affected by displacement, nomadic lifestyles, or vaccine stockouts. Despite these limitations, the indicator demonstrates the potential of community-based systems to close immunisation gaps and reduce dropout rates.

Indicator 2.3: Number of community members (disaggregated by age group and sex) reached for family health sessions / Source: BHI HIMS and DHIS2 / Exceeded expectations

HPF3 reached over 14 million community members through family health sessions with majority of the participants being female (55%) as compared to male (45%). These sessions covered a wide range of topics, including family planning, maternal and child health, nutrition, and gender-based violence. Women constituted the majority of participants, reflecting the programme’s focus on reproductive and maternal health. The success of this indicator can be attributed to the integration of health education into routine BHW activities, the use of pictorial job aids, provision of over 500 bicycles, and the engagement of community champions. These sessions were instrumental in improving health-seeking behaviours and increasing demand for services such as antenatal care and facility-based deliveries. However, the quality and consistency of facilitation varied across counties, and cultural resistance to sensitive topics like GBV and FP remained a barrier in some areas. The programme’s ability to reach such a large audience is commendable, but future efforts should focus on building linkages with community chiefs and schools to strengthen behaviour change on FP.

Indicator 2.4: Percentage of mothers or primary caregivers of children under five years old who can correctly identify at least a minimum number of key danger signs that require medical attention / Source: LQAS survey / Not met expectations

This indicator helps to identify gaps in caregiver knowledge that could delay seeking care. During HPF3, two surveys were conducted by Liverpool Associates in Tropical Health (LATH) in 2020 across all ten South Sudan States and another by an independent firm ‘We are the People’ (WAP) in 2023 at the end of Y4. The 2023 survey revealed that 45.5% of mothers and caregivers could identify at least two danger signs of childhood illness, compared to 52.8% in the 2020 LQAS survey. It is important to caveat this analysis with recognition of quality issue with the underlying data. The 2023 mini-LQAS survey, which informed this indicator, included a broader respondent base, mothers and caregivers of children aged 0–59 months, compared to the 2020 LQAS, which focused only on mothers of children aged 0–11 months. This change in methodology may have introduced variability in the results due to differences in recall and exposure to health education.

Nonetheless, this result suggests that while outreach activities were extensive, they did not consistently translate into improved knowledge retention. Several factors may have contributed to this outcome, including low literacy levels, inconsistent messaging, and recall bias in survey responses. HPF3 responded by intensifying community health education and mentoring BHWs on the use of Integrated Management of Childhood Illness (IMCI) job aids. However, the findings highlight the need for more targeted, repetitive, and culturally appropriate messaging to ensure that critical health information is understood and retained by caregivers. This indicator underscores the importance of not only reaching communities but also ensuring the effectiveness of communication strategies.

Indicator 2.5: Percentage of mothers who can correctly identify at least three key danger signs during pregnancy that require immediate medical attention. / Source: LQAS / Moderately exceeded expectations

This indicator demonstrated strong performance, with 78.8% of mothers able to identify at least three primary danger signs of pregnancy, showing a notable improvement from 64.9% in 2020. Data quality issues related to LQAS explained in indicator 2.4 also apply here. This progress reflects the effectiveness of BHWs in disseminating information through antenatal care sessions, community meetings, and family health education forums. The use of pictorial job aids and targeted messaging helped reinforce key messages, particularly in areas with low literacy.

KIT Royal Tropical Institute’s operational research during HPF3 highlighted that while knowledge levels were improving, disparities persisted across states, and knowledge did not always translate into timely care-seeking behaviour. KIT also noted that community-level data collection tools were not always consistently applied, and that some BHWs faced challenges in accurately recording and reporting health education outcomes due to limited literacy or training.

Despite these limitations, the indicator reflects a positive trend in maternal health awareness. To sustain and deepen this progress, future programmes should continue to invest in community-based education, strengthen data collection tools and training for BHWs, and ensure that knowledge gains are matched by improvements in service access and utilisation.

B. Lessons learned through this output, and recommendations for future programming

 Lessons learned:
- Community Health Workers Are Essential Frontline Providers: BHWs significantly expanded access to treatment for malaria, pneumonia, and diarrhoea in hard-to-reach areas, treating over 7.1 million children under five.
- Integrated Community and Facility Services Improve Continuity of Care: Linking BHWs to nearby health facilities enabled effective referral of immunisation defaulters and zero-dose children, with 92.4% successfully referred. Integration of health promotion, treatment, and referral strengthened the continuum of care.
- Equity challenges: Geo-mapping revealed that nearly half of BHWs were located within 5km of health facilities, contrary to the BHI strategy, highlighting the need for more equitable distribution of BHWs based on service delivery gaps.
- Data systems must be adapted to local realities: Many BHWs were illiterate, making it difficult to use standard registers. Pictorial tools and simplified reporting formats are more effective. DHIS2 did not fully accommodate community-level reporting, requiring accessory tools and manual aggregation.
- Cultural Norms and Gender Dynamics Influence Health-Seeking Behaviour: Myths, stigma, and male dominance in decision-making limited uptake of FP and immunisation in some regions.
- Community adaptability and knowledge are powerful assets: Despite literacy barriers, BHWs used recall to complete registers and track immunisation schedules, demonstrating that communities can innovate and should be actively involved in the health system.
- Gender dynamics in BHW retention matter: The attrition study showed higher dropout rates among men, despite their literacy advantage. Women, though less literate, had greater retention - suggesting that prioritising women in BHI recruitment could enhance program stability and enable stronger connections with mothers and children. Community ownership and involvement in BHW selection and supervision improved accountability and service uptake.

Recommendations:
- Institutionalise and Expand the Boma Health Initiative (BHI): Scale up BHI to all counties, including peri-urban and underserved areas within 5 km of health facilities. Ensure BHWs are equitably distributed based on population and distance from facilities.
- Improve BHW Incentives, Tools, and Supervision: Increase and harmonise BHW and supervisor incentives to reflect workload and living costs. Provide pictorial registers and mobile-based reporting tools for illiterate BHWs. Institutionalise regular CHD-led supervision and mentorship with dedicated budgets.
- Strengthen Community-Facility Linkages: Formalise referral pathways between BHWs and health facilities, including feedback loops. Use tickler files and digital tools to track immunisation defaulters and zero-dose children.
- Invest in Community Engagement and Behaviour Change Communication: Continue using male champions, school health clubs, and women-friendly spaces to promote SRHR, FP, child health, and other key determinants such as WASH and nutrition. Tailor messages to local contexts and address harmful norms through dialogue.
- Integrate Community Data into National Health Information System: Upgrade DHIS2 to accommodate BHW-level reporting and disaggregation. Train CHDs and IPs in data use for decision-making and performance monitoring.
- Enhance Emergency Preparedness at Community Level: Equip BHWs with basic disease surveillance, emergency response training, and supplies (e.g. ORS, mRDTs). Include BHWs in county-level surveillance, emergency planning and response coordination.
- Promote Gender Equity and Inclusion in Community Health: Prioritise recruitment of female BHWs to improve access for women and girls.
- Strengthen supply chain planning and budgeting for BHI commodities to prevent frequent stockouts, especially of high-demand items like Malaria RDTs, future programmes should quantify, and budget BHI supplies separately from general facility supplies. This ensures consistent availability and reduces reliance on presumptive treatment.

Output Number 3 and Title	Availability of safe, effective and quality essential medicines and supplies
Output Score	A+
Impact weighting (%)	15	Impact weighting revised since last AR?	No

Output Indicator	Baseline (2019)	Final Logframe Target (2024)	Final Result Achieved (2024)
Indicator 3.1 Proportion of health facilities receiving commodities within a defined time period (21 days)	42%	93%	98.3%
Indicator 3.2 Percentage of facilities visited with any expired drugs	38%	17%	16%
Indicator 3.3 Proportion of health facilities that supply complete commodity consumption reports	66%	97%	100%
Indicator 3.4 Proportion of health facilities that have all relevant tracer medicines available, and in the last three months	84%	90%	90%

The HPF3 supply chain demonstrated remarkable achievements in ensuring the timely and efficient delivery of essential medical commodities across South Sudan. By Year 5, 98% of health facilities received supplies within 21 days, up from 42% at baseline, reflecting major improvements in logistics coordination and last-mile delivery. This is a strong achievement in a fragile and conflict affected state.

The proportion of facilities with expired drugs dropped from 38% to 16%, and complete commodity consumption reporting reached 100%, enabling accurate forecasting and procurement. Additionally, the availability of tracer medicines rose dramatically from 19% to 90%, ensuring continuity of critical services. Key achievements also included the distribution of family planning commodities and vaccines, training for logisticians, and procurement of vehicles and bicycles for last mile deliveries. However, weaknesses persisted, particularly in the early years, where delays, stockouts, and poor reporting practices were common.

HPF3 relied on a push system, with pre-packed kits assembled outside the country in India, which limited the ability to tailor supplies to the specific needs of individual health facilities. Challenges such as difficult terrain, insecurity, and limited infrastructure occasionally disrupted distribution and contributed to medicine expiries. Despite these hurdles, the programme’s adaptive strategies and strong coordination mechanisms fostered a resilient and responsive supply chain system in a fragile and conflict-affected setting - earning it an A+ rating. These learnings must be implemented and maintained within the World Bank and Government co-led HSTP.

Indicator 3.1: Proportion of HPF3 supported health facilities receiving commodities within a defined time period (21 days) / Source: Logistic Management Information System (LMIS) / Substantially exceeded expectations

HPF3 achieved a significant improvement in the timeliness of commodity delivery, increasing from 42% at baseline to 98% by Year 5. This success was largely due to enhanced coordination, clear communications to implementing partners, and the establishment of a reliable distribution schedule with three deliveries per year. Implementing partners played a vital role in ensuring last-mile delivery, even in hard-to-reach areas. However, it is important to recognise that the push system, where kits were pre-packed outside the country, limited flexibility, as kits were not tailored to the specific needs of each facility. This sometimes led to mismatches between supply and demand. A key lesson is that while the push system certainly ensured consistency and predictability in fragile settings, which was a key determinant of HPF3’s success, it must be complemented by strong feedback loops and consumption data collected by implementing partners and county health departments to improve responsiveness. Implementing partners played a pivotal role in supporting last-mile delivery, rotating stock between health facilities, and procuring supplies locally before stockouts occurred. Medical logisticians also provided a focus person in each lot, responsible for final mile deliveries and good storage practice within the facility stores.

Indicator 3.2: Percentage of health facilities visited with expired drugs / Source: Logistic Management Information System and Implementing Partner reports / Moderately exceeded expectations

The proportion of health facilities with expired drugs dropped from 38% in 2019 to 16% in 2024, reflecting improved stock management, better storage practices, and regular supervision. The programme’s emphasis on training, strengthening inventory management practices at county and facility levels, supportive supervision, stock rotation (moving commodities from facilities with low consumption to facilities with high consumption), the introduction of drug disposal protocols, stock status monitoring, physical count and use of the Logistics Management Information System tool for recordkeeping contributed to this success.

However, the push system’s rigidity meant that some facilities received medicines they did not need or could not use before expiry, especially when demand patterns shifted or patient volumes fluctuated. A key lesson is that while centralised procurement and kitting can streamline logistics, integrating facility-level consumption data into procurement planning is essential to minimise wastage and ensure appropriate stock levels. A recommendation for future programmes is to establish a national-level policy for accepting donated medicines and a clear protocol for managing expired drugs in the field to minimise waste and ensure quality.

Indicator 3.3: Proportion of health facilities that supply complete commodity consumption reports / Source: Logistics Management Information Systems and facility visits / Substantially exceeded expectations

Reporting completeness improved from 66% at baseline to 100% by Year 5, a major achievement that enabled accurate forecasting and procurement. The reports included information on stock status and utilisation in each county. This was driven by implementing partners and the Fund Manager following up and driving accountability at the county level for collating and sharing data, as well as consistent training and the use of standardised tools. The availability of reliable data also allowed for better stock rotation and emergency procurement when needed. However, the initial years of HPF3 were marked by inconsistent reporting and limited capacity at the facility level. The lesson here is that investing in health information systems and building county level capacity for data collection and use is critical for supply chain performance, especially when operating under a push system that relies heavily on accurate consumption data for future quantification.

Indicator 3.4: Percentage of health facilities reporting no stock outs of tracer medicine (disaggregated by state/county/facility level) / Source: Logistic Management Information System, facility visits, and implementing partner reports / Met expectations

Availability of tracer medicines improved dramatically from 19% in Year 1 to 90% in Year 5, ensuring continuity of essential services such as malaria treatment, maternal care, and child health. Availability of tracer medicines (a list of 13 priority medicines that are regularly monitored to assess effectiveness of the distribution) is a key indicator of supply chain performance and rational use of medicines. This was achieved through rationalisation of tracer lists, buffer stock management, stock rotation, and emergency procurement mechanisms. Tracer medicines were marked with bright-colored stickers to prioritise delivery during phased distributions.The push system helped maintain a baseline level of availability, but its limitations became evident when specific tracer items were over- or under-supplied due to uniform kit contents. IPs were given a budget line to fund emergency procurement of tracer products from local suppliers, and the Juba warehouse kept a buffer stock of the seven highest demand tracer items, allowing IPs to request and collect these products to replenish facility stock levels as necessary. The key takeaway is that while a push system can stabilise supply in fragile contexts, it must be paired with flexible, responsive mechanisms to address localised shortages and surpluses.

Lessons learned:
- Implementing Partners (IPs) and Medical Logisticians: IPs and their medical logisticians were instrumental in ensuring last-mile delivery, rotating stock between facilities, and managing emergency procurement—especially in hard-to-reach areas.
- County-Level Accountability Strengthens Performance: Regular supervision, data verification, and stock monitoring at the county level improved reporting rates and reduced expired drugs, highlighting the importance of local accountability structures.
- Data-Driven Decision-Making Enhances Responsiveness: Monthly consumption reporting and analysis enabled better forecasting and stock rotation, even within a push system. This helped align supply with actual facility needs over time.
- Push System Offers Stability but Limits Flexibility: While the push system ensured predictable supply in a fragile context, its rigidity led to mismatches between supply and demand. Tailoring kits based on facility-level data remains a challenge.

Recommendations:
- Adapt the Push System with Modular or Hybrid Approaches: Maintain the push system for stability, but introduce modular kits or hybrid models that allow for partial tailoring based on facility consumption data and seasonal disease patterns.
- Strengthen Contingency Planning for Insecurity and Looting: Develop protocols for rapid redistribution of supplies, pre-position buffer stocks in secure hubs, and coordinate with local authorities to safeguard health commodities during crises.
- Mandate and Monitor Monthly Consumption Reporting: Make timely and complete reporting a contractual requirement for IPs and CHDs. Link reporting performance to funding disbursements and provide feedback loops to facilities.
- Invest in Communication Infrastructure and Coordination Platforms: Equip CHDs and IPs with tools to share delivery schedules, stock alerts, and consumption trends via monthly reporting, on DHIS2, and in real time.
- Standardise and Enforce Expiry and Stock Rotation Protocols: Require IPs and CHDs to conduct quarterly stock audits and rotate near-expiry items between facilities. Include this in supervision checklists and performance reviews.
- Develop a National Policy on Kitting and Kit Customisation: Collaborate with MoH and donors to define a national policy on consignments, frequency, and flexibility. Include guidelines for adapting kits based on epidemiological data and facility profiles.

Output Number 4 and Title	Stable health systems that enhance accountability and responsive to the needs of the people
Output Score	A
Impact weighting (%)	10	Impact weighting revised since last AR?	No

Output Indicator	Baseline (2020)	Final Logframe Target (2024)	Final Result Achieved (2024)
Indicator 4.1 Proportion of facility health committees which are functional and attended by a female chair/ cochair	28%	80%	88.5%
Indicator 4.2 Completeness of health information systems reporting (Community and DHIS)	Community Not set (achieved 54% in 2020)	99%	99.6%
	DHIS/ Health Facility 98%	95.0%	99.8%
Indicator 4.3 Proportion of health facilities receiving county led supportive supervisory (QSC) /quality improvement visits (QOC)	QSC: 65% / QOC: 55%	QSC: 95% / QOC: 95%	QSC: 99.6% / QOC: 99.6%
Indicator 4.4 Percentage of community members who express satisfaction with the availability and quality of health facility services	Not set	70%	95.9%

Under Output 4, HPF3 made significant strides in stabilising South Sudan’s fragile health system by supporting nearly 8,000 healthcare workers (HCWs) and 4,400 BHWs through training, supervision, and incentive payments. Feedback from a Medical Officer in a County Health Department in Wau highlights the impact of training for BHWs, and how this improved their capability to identify immunisation defaulters and zero dose children.

The programme introduced biometric verification to reduce fraud, strengthened county and state-level governance through co-location and capacity building, and improved data systems via DHIS2 integration and HMIS tool distribution. Despite these achievements, systemic challenges persisted. South Sudan’s health system remains heavily reliant on donor-funded incentives due to the lack of GoSS investment in health leading to irregular government salary payments which undermine sustainability.
‘Orientation of BHWs in WBeG on the updated BHI registers with indicators of zero dose and defaulters reported on separately. The BHWs were able to distinguish data for zero dose and defaulters in the updated registers hence leading to the reduction in the number of defaulters’…said CHD medical officer in Wau county.

While Output 4 was scored an A for exceeding performance targets in capacity building and system stabilisation, the indicators used, such as training numbers, supervision visits, and reporting completeness, are proxy measures that do not fully capture the stability, accountability, or responsiveness of the health system. In a context marked by corruption, conflict, and weak governance, particularly at subnational and county levels, HPF3 faced ongoing barriers including insecurity, poor infrastructure, and limited government ownership. These realities underscore that while progress was made, and this needs to be built upon, South Sudan remains a long way from being able to independently manage and sustain its health system. Future programmes need to consider how all programming, including humanitarian, can support building capacity within government and or local health systems (e.g. county health departments and community chiefs).

Indicator 4.1: Proportion of facility health committees which are functional and attended by a female chair/ co-chair / Source: Facility records and implementing partners reports / Moderately exceeded expectations

This indicator reflects HPF3’s efforts to strengthen community health governance through inclusive leadership. The proportion of facility health committees (FHCs) with a female chair or co-chair rose from 28% at baseline to 93.9% by Year 6, driven by targeted mentorship and training of 1,542 committee members. Female-led FHCs contributed to tangible improvements, including facility renovations, staff housing construction, and solar power installations. Community mobilisation efforts supported infrastructure upgrades in Barmayen PHCC (NBeG) and Tanamuko PHCU (WES), including a two-room grass-thatched structure for ANC and FP services.

However, challenges included entrenched gender norms, limited female literacy, and occasional resistance from male-dominated community structures. Sustaining this progress will require continued investment in leadership development, community sensitisation, and institutionalising gender equity in health governance frameworks.

Indicator 4.2: Completeness of health information systems reporting (Community and DHIS) / Source: DHIS2 and BHW reports / Moderately exceeded expectations

The completeness of health information systems reporting under HPF3 was measured by tracking the proportion of health facilities and community-level units (Boma Health Workers) that submitted timely and complete reports using standard HMIS tools, with data entered into the national DHIS2 system. Reporting completeness was calculated monthly, with health facilities expected to submit by the 15th of each month. Community data, though not directly entered by BHWs, was compiled by supervisors and submitted through linked facilities.

Outline of flow of data from community level to decision-makers:
1. Boma Health Workers (BHWs) collect community-level health data.
2. Health Facilities collect facility-level data using HMIS tools.
3. M&E clerks compile health facility and BHW reports and submit them to the County Health Departments (CHDs).
4. CHDs review and enter all data into the DHIS2 system.
5. HPF3 Monitoring Team uses DHIS2 data for performance tracking and decision-making.

Successes included a rise in facility reporting from 92% at baseline to 99.9% by Year 5, and community reporting from 54% to 99.9%, driven by extensive training of over 700 staff, distribution of over 100,000 HMIS tools, mentorship, and persistent follow-up and feedback mechanisms.

However, challenges persisted, such as outdated population census data affecting denominator accuracy, parallel reporting systems (especially in nutrition), and limited inclusion of key indicators like disability and FP new users in DHIS2. Transition from DHIS1.4 to DHIS2 in 2019 improved data systems but introduced challenges due to administrative restructuring and lack of initial training for IPs, which HPF3 addressed through targeted capacity building. Overall, the programme’s integration of government systems and proactive mentorship ensured robust data quality and timely reporting.

Indicator 4.3: Proportion of health facilities receiving county led supportive supervisory/quality improvement visits / Source: DHIS2, Quality of Care assessments, and IP reports / Moderately exceeded expectations

HPF3 demonstrated strong performance in promoting accountability and service quality through county-led supervision. By Year 5, 98.8% of supported health facilities had received Quantified Supervisory Checklist (QSC) visits, and 99.8% had undergone Quality of Care (QoC) assessments. These visits were instrumental in identifying gaps in service delivery, infrastructure, and documentation, and led to the development of tailored quality improvement plans. Success was attributed to joint supervision efforts involving CHDs, IPs, and HPF3 teams, as well as the establishment of QoC teams and use of digital tools for assessments. Donors and third-party monitors conducted regular visits to supported health facilities, reinforcing accountability and continuous performance monitoring.

Nonetheless, challenges included access issues due to insecurity and flooding, limited funding for WASH infrastructure improvements, and occasional gaps in feedback loops from CHDs to facilities. Despite these, the programme’s structured supervision and mentorship approach significantly enhanced service delivery standards.

Indicator 4.4: Percentage of community members who express satisfaction with the availability and quality of health facility services / Source: LQAS, Facility exit interviews / Moderately exceeded expectations

Community satisfaction with health services under HPF3 was consistently high, with exit interviews showing satisfaction rates rising from 93.9% in Year 2 to 95.9% in Year 5. The 2020 LQAS assessed client satisfaction in antenatal care (ANC), delivery of newborns, and treatment of sick children for fever, diarrhoea, or acute respiratory infection (ARI). Clients appreciated improvements in cleanliness, privacy, and staff friendliness, particularly in maternity services. However, satisfaction was lower in areas such as waiting times, medication availability, and ANC services. The programme’s success stemmed from investments in infrastructure, training of HCWs, and community engagement through BHWs and health committees.

Challenges included disparities in satisfaction among persons with disabilities (only 37.6% satisfied), and lower scores in ANC due to limited staff friendliness and service hours. The use of both community surveys and exit interviews provided key qualitative insights but cannot be extrapolated as fully representative of all HPF3 supported health facilities.

Lessons learned:
- Health systems strengthening in FCAS is challenging: HPF3’s shift in approach to focus on stabilisation of subnational/ county level systems was necessary due to political challenges at the national level.
- Proxy Indicators Have Limitations: While useful for tracking progress, indicators like supervision visits and reporting completeness don’t fully capture system stability, accountability, or responsiveness.
- Joint Supervision Enhances Transparency: Collaboration between CHDs, IPs, and HPF3 teams, along with third-party monitoring, strengthened accountability.
- Persistent Follow Up and Capacity Building: Training, mentorship, and tool distribution significantly improved the completeness and timeliness of DHIS2 reporting.
- Disparities in Service Satisfaction: Persons with disabilities and ANC clients reported lower satisfaction, highlighting the need for more inclusive service delivery.

Recommendations:
- Plan for Sustainability Through Government Ownership: Gradually transition key functions (e.g. supervision, data use, HRH management) to MoH and CHDs with capacity building. Embed HPF3 tools (e.g. QoC indicators, biometric payroll, FP tracking) into national systems.
- Strengthen Health Information Systems: Improve inclusion of key indicators (e.g., disability, FP users) in DHIS2.
- Enhance Quality and Accountability Mechanisms: Maintain structured supervision and mentorship, and strengthen feedback loops from CHDs to facilities.

Output Number 5 and Title	Funds and processes that are efficient, effective, inclusive and offer value for money
Output Score	A
Impact weighting (%)	10	Impact weighting revised since last AR?	No

Output Indicator	Baseline (2019)	Final Logframe Target)	Final Result Achieved
Indicator 5.1: Proportion of planned programme expenditure spent	105%	98%	90%
Indicator 5.2: Average cost per consultation (by region and type of services)	Not set	£3.41	£2.82
Indicator 5.3 Identifying and tracking of people with disability, as defined by the Washington group SS, accessing curative services	14,014	12,416	12,994
Indicator 5.4 Percentage of health care facilities with staff trained to identify and manage mental health illnesses	26%	92.8%	95.3%
Indicator 5.5: Percentage of health care facilities with staff trained to identify and manage sexual and gender based violence	39%	87.3%	93.2%

Output 5 scored an A due to strong performance across nearly all indicators, demonstrating that HPF3 delivered efficient, effective, inclusive, and value-for-money results. Despite fiscal constraints and external shocks, the programme maintained high levels of financial execution (90% of planned expenditure), reduced the average cost per consultation, and exceeded targets for training health workers in mental health and SGBV care. It also met expectations on disability inclusion and made significant investments in data systems and capacity. These achievements reflect a well-managed programme that adapted to challenges while maintaining a strong focus on equity, inclusion, and cost-effectiveness.

Indicator 5.1: Proportion of planned programme expenditure spent
Source: HPF3 programme completion report
Moderately not met expectations

Over the lifetime of the programme, HPF3 faced budget cuts and fiscal pressure due to COVID-19 and the Ukraine war. HPF3 was initially valued at £426.5million in the Business Case, the UK planned to contribute £175 million, with additional funds from other donors (£251.5 million). By March 2025, total expenditure from the bridging phase to Y6 was at £348.5 million (£154 millions of UK contributions and £194.5 million from other donors) and the budget was fully executed. Only £78 million was not allocated at closure due to insufficient budget availability/budget cuts across the donors. Therefore, the programme met expectactions based on the actual donors’ contribution to the pooled fund and the proportion of planned expenditure spent.

Indicator 5.2: Average cost per consultation (by region and type of services)
Source: HPF3 programme completion report
Moderately exceeded expectations

HPF3 delivered a cumulative total of over 33 million outpatient consultations across supported health facilities at a total cost of £93m. The average cost of £2.82 per consultation, shows a relative cost reduction from the initial projected cost of £3.41 per consultation over the lifespan of the programme with the programme exceeding expectations. This can be attributed to the reduction in medical drug freight costs including a decrease in demurrage and detention charges. This was achieved by the HPF3 team working closely with the MoH and Ministry of Finance for faster processing of tax exemptions and extending the holding period for goods with the supplier to ensure arrangements were in place before shipments arrived in South Sudan.

Indicator 5.3: Identifying and tracking of people with disability, as defined by the Washington group SS, accessing curative services
Source: HPF3 programme completion report
Met expectations

This output met expectations. During HPF3 implementation, a cumulative total of 247,029 PWDs (124,105 female, 122,924 male) were identified in HPF3 supported HFs using the Washington Group Short Set of Questions (WGSSQ), among which 5,621 (2.3%) were PWDs pregnant mothers that received antenatal care services. In the final year of the programme 12,994 PWD were identified against the target of 12,416 representing 104.6% completion against the indicator. Throughout the HPF3 programme, capacity building training sessions were provided to 898 HCWs (321 female, 577 male) across 181 HFs. These trainings focused on disability inclusion and the use of the WGSSQ to identify patients with disabilities. Additionally, 1,267 HCWs (352 female, 915 male) in 288 HFs were trained to use the Snellen chart for vision screening. The programme also provided various assistive devices to support PWDs, including 600 reading eyeglasses, 11 magnifying glasses, 493 white canes, 30 hearing aids, 63 wheelchairs, 154 crutches, and 5 tricycles. The programme met, rather than exceeded, expectations due to thedeprioritisation of some disability inclusion activities within HPF3, coupled with irregular use of the WGSSQ in some of the HFs due to the high workloads at PHCUs across South Sudan.

Indicator 5.4: Percentage of health care facilities with staff trained to identify and manage mental health illnesses
Source: HPF3 programme completion report
Met expectations

Overall, this output met expectations. Over the lifetime of the HPF3, a total of 189,064 staff have been trained to identify and manage mental health illnesses. In the final quarter of the HPF3 programme, this indicator exceeded expectations, with a commendable 95.3% of HFs (488 out of 512) having staff trained in the identification and management of mental health conditions versus the 92.8% target. Throughout the duration of the HPF3 programme, a total of 189,064 (94,260 female, 94,804 male) cases of mental, neurological, and substance abuse conditions were identified and treated in HPF3 supported HFs.

The HPF3 programme's notable achievements in mental health care was attained through a multifaceted approach that included the delivery of targeted mhGAP Training of Trainers (ToT) to HCWs, supplemented by ongoing mentorship and on job training. This ensured the practical application of their knowledge in clinical spaces. The strategy was further supported by the allocation of resources for mental health drugs, community engagement activities to enhance mental health awareness, and strengthening of monitoring and evaluation system that facilitated continuous improvement of tracking mental health data.

Indicator 5.5: Percentage of health care facilities with staff trained to identify and manage sexual and gender-based violence
Source: HPF3 programme completion report
Moderately exceeded expectations

This output moderately exceeded expectations. By the end of the HPF3 programme, 93.2% (477/512) of HFs had staff trained to identify and manage SGBV cases. During HPF3, a total of 19,470 (13,658 female, 5,812 male) SGBV survivors were identified and managed in HPF3 supported facilities. The programme conducted clinical management of rape (CMR) assessments and provided essential medical supplies to 15 CMR clinics. This support was crucial in enhancing the clinics' readiness to assist GBV survivors. There was also provision of 8,212 sanitary packs to schoolgirls, and 357 dignity kits to SGBV survivors, contributing to their well-being and dignity. In addition, the programme established 15 women and girls' friendly spaces within HFs fostered an environment where women could freely discuss appropriate issues and offer mutual support.

Lessons learned:
- Integrated service delivery models that combine humanitarian response with systems support are more equitable and efficient than traditional humanitarian approaches in fragile settings.
- Investing in frontline health workers, including BHWs, is critical for expanding access and ensuring continuity of care in hard-to-reach areas.
- Data-driven decision-making is only as strong as the systems and capacity behind it, continued investment in data quality, use, and integration is essential.
- Efficiency gains are possible even in fragile contexts, through strong coordination with government and suppliers, and proactive logistics management.

Recommendations:
- Sustain investments in DHIS2 and ensure integration of Health and Nutrition Cluster data to improve visibility of humanitarian needs and support coordinated, evidence-based decision-making.
- Institutionalise disability inclusion by embedding the Washington Group Short Set into routine data collection and ensuring consistent use across all facilities.
- Strengthen mental health and SGBV services by maintaining training, mentorship, and supply chains, and expanding community engagement to reduce stigma and increase service uptake.
- Enhance cost-efficiency tracking by disaggregating cost data by service type and region to inform future resource allocation and identify areas for optimisation.
- Ensure contingency planning for future funding shocks to protect essential services and maintain programme reach and quality.

D: Value for Money

VfM performance compared to the original VfM proposition in the business case.

The VfM measures implemented during the lifetime of the programme are similar to those identified in the original Business Case (BC), these were economy, efficiency, effectiveness, cost-effectiveness and equity with which it delivers using indicators such as cost per consultation (efficiency), cost per DALY (disability-adjusted life year) averted (effectiveness) and total cost of direct service delivery (economy).

An extensive VfM strategy was developed for the programme at the start of 2019. In line with BC, HPF3 VfM Strategy measured Economy by tracking Purchase price variance with index price, cost of items for quality purchased and cost savings. Efficiency was measured through cost per Consultation and cost per service delivered. Effectiveness was measured through the number of deaths averted, Disability-adjusted life years (DALYs) saved, and Couple Years of Protection (CYPs) provided. Cost effectiveness was tracked using the following indicators: Cost per DALY averted, Cost per death averted and Cost per CYP Provided. Equity was measured by tracking the number of hardest to reach (marginalised) beneficiaries that had received care and collecting data on the cost of providing support to the most vulnerable and percentage of female trained HCPs.

Routine quarterly reviews and assessment of VfM across all the component parts (4 E’s and Cost Effectiveness) were done to capture best practices for improving VfM and programming in general. The quarterly reviews would focus on the following:
- Identifying cost savings and the activities or actions by programme implementers that have led to such savings.
- Capturing lessons learned from cost saving activities or actions and exploring potential for transferability on the programme.
- Reviewing procurement and consumption data from previous periods and using this to inform subsequent procurement in order to contain wastages.
- Benchmarking price variance with index price based on global guidance and reviewing the quality of purchases.
- Monitoring cost per output, cost per service and cost per outcome across counties, lots and IPs and attempting the explain disparities, identify best practices and lessons that can be transferred.
- Monitoring improvements in outputs and outcomes as well as the cost per output, cost per service and cost per outcome over time in the hardest to reach areas. We have defined hardest to reach areas as those that pose geographical challenge to access including (Lot 6, 4, 7, 13 and Lot 20) and conflict areas (Lot 3 and 21).
- Reviewing qualitative narrative on scalability, sustainability, cultural acceptability and the contributions of other actors to support robust VfM judgement.
The programme performed positively during implementation, consistently meeting output expectations as evidenced by good performance during the annual reviews. Ongoing conflict made delivery more challenging, and the FM ensured VfM was still delivered by meeting targets for the provision of health services when other programmes were unable to continue. The low budget execution from the government has further limited sustainability. Other donors invested significant amounts in HPF3, recognising it as an efficient route to supporting health services. By March 2025, total expenditure from the bridging phase to Y6 was at £348.5 million (£154 millions of UK contributions and £194.5 million from other donors) This continued support ensured health service coverage could be provided to the seven states in South Sudan, and improved efficiencies through pooling resources together to achieve maximum impact.

Key cost drivers and performance

Economy: The main cost drivers have been Health Care Workers (HCWs) remuneration (comprising about 62% of IPs’ spend); drugs and medical commodities, HPF and IPs overheads and warehousing and distribution costs.

The VfM Economy approach focused on buying the inputs of appropriate quality and at the right price. To achieve economy, procurement of medicines and supplies was done principally at the Head Office where items were purchased centrally and transported by freight to HPF South Sudan warehouses and through various means of transport to the health facilities. At the central head office level, who led procurement and supply chain, focus was on the cost of supplies purchased in combination with the quality of the supplies and the time it takes to deliver the supplies to the last mile. This led to significant cost savings through strategic procurement, efficient use of resources, and innovative training methods savings, a few examples include, In Y1, a tender approach for national medicine procurement saved approximately £1,147,835 and using existing HF spaces close to the participants for training sessions reduced hall hire and accommodation costs. Y2 saw additional savings from online training sessions during the COVID-19 pandemic, saving £376-£513 per session, and using internal facilitators as opposed to external facilitators contributed to additional savings. During Y3 and Y4, the expediting of tax exemptions reduced detention costs from £16,000 to £3000 in Y3 while Y4 continued to benefit from timely tax exemption processing, saving £53,000-£125,000 per consignment which continued into Y5 with a further reduction in demurrage and detention charges at the Mombasa Port.

Overall, these measures, along with the consistent focus on health worker remuneration and centrally purchased medicines and diagnostics, resulted in substantial savings and improved cost-effectiveness throughout the project period.

Efficiency: Efficiency over the course of the programme was measured using several indicators; the main indicator used was ‘cost per consultation’.

Cost per consultation[1]: During HPF3, the cost per consultation varied significantly reflecting changes in spending and operational efficiency.
[1] Calculated as the total service delivery cost divided by the total number of ANC visits (four or more), outpatient consultations, vaccinations, family planning sessions, and the number of deliveries supported by a skilled birth attendant.

- Year 1 (Y1): £2.57
- Year 2 (Y2): Increased to £4.07 due to higher expenditure on medicines and diagnostics
- Year 3 (Y3): Decreased to £2.93 as efficiencies improved
- Year 4 (Y4): Rose to £3.37, driven by reduced support to health facilities and currency depreciation
- Year 5 (Y5): Improved to £2.82, indicating better resource allocation and management

When disaggregated by State, the cost per consultation varied significantly. See Equity section for further details.

Year	NBeG	EES	WES
Y2	£1.66	£4.84	—
Y3	£1.59	£4.00	—
Y4	£2.30	—	£4.40
Y5	£2.03	—	£3.57

Figure 3: Cost per consultation across selected States, illustrating the difference in the lowest and highest costs per consultation.

Overall, the trend shows an initial increase in costs due to scaling up of activities and procurement, followed by a period of improved efficiency, a temporary setback, and a final recovery to more efficient cost management. For example, costs were lower in Y1 because the programme supported more health facilities and reached more beneficiaries. In Y5, for example, there were less facilities supported but admin costs (including incentives) remained the same. The state-level data highlights the variability in costs due to regional differences and specific challenges faced in each area over the lifetime of the programme.

Another indicator used to measure Efficiency was ‘Cost per service delivered’. Overall, the cost for service delivery is £2.82 for all consultations. For antenatal care consultations, the overall cost per ANC was £11.73, which is within the range of costs per ANC services in other low- and middle -income countries. For skilled delivery, the cost per delivery in HPF3-supported facilities was estimated at £18.81 in Y5, which is within range of cost of vaginal delivery in lower- and middle-income countries (£4.00) in Uganda to (£30.65) in Pakistan. Cost effectiveness improved during Y5 of implementation and the cost per service estimates were lower at the end of the programme.

Effectiveness

HPF3 met its overall objective of delivering primary health services to the population of South Sudan. HPF3 scored an A+ overall across the indicators, as outlined at the start of the PCR. HPF3’s success in delivering services, medicines, and commodities effectively in a fragile and conflict affected state (FCAS) provided a lifeline for the population and offers clear evidence of how outputs at programme level have translated to outcomes.

Under the HPF3 programme Effectiveness was assessed using key indicators such as Disability Adjusted Life Years (DALYs) averted and couple of years of protection (CYP) delivered. DALYs averted and the associated costs, as well as deaths averted and their costs, were estimated for the entire HPF3 project period. Overall, across 55 supported counties, HPF3 averted 6,607,817 DALYs at a cost of £17.04 per DALY and averted deaths at a cost of £1,333.98 per death, consistently delivering value for money and underscoring its efficiency and impact.

The HPF3 programme estimated the number of DALYs, and deaths averted across all 55 supported counties over the project period:
- Total DALYs averted: 6,607,817
- Cost per DALY averted: £17.04 this is lower than the one in Business case which is £69 ($88) and is less than three times South Sudan’s per capita GDP of around $351 between 2011 and 2024. According to the WHO111, any intervention with a cost per DALY that is less than the GDP per capita of the target country should be classified as ‘extremely cost effective’. Cost per death averted: £1,333.98
These figures demonstrate strong value for money, highlighting the programme’s efficiency and impact in improving health outcomes.

Couple Years of Protection (CYP) – The programme also used CYP to measure the Effectiveness of HPF3. Overall, HPF3 delivered:
- Total CYPs provided: 254,168
- Overall cost per CYP: £4.49

These costs are within the range reported in similar programmes in other countries, such as:
- £1.08 in Sierra Leone (2015)
- £15.00 in Zambia (Scaling Up FP, Phase I)
Higher costs in some contexts, such as Zambia, were attributed to logistical challenges associated with low population density. Similarly, HPF3 faced logistical and cultural barriers that influenced cost variations across counties and years.

The HPF3 programme demonstrated a trend of initial cost increases, followed by a period of stabilisation and eventual reduction in the cost per CYP. The variations across counties and years were influenced by factors such as logistical challenges, cultural barriers, and strategic shifts in resource allocation. Despite these fluctuations, the programme consistently aimed to improve efficiency and cost-effectiveness in delivering FP services.

Cost- Effectiveness
The FM tracked cost-effectiveness over the course of the programme by monitoring the following indicators:
- Cost per DALY averted: The cost per DALY averted came to £17.04 per DALY.
- Cost per death averted: The cost per death averted is at a cost of £1,333.98 per death, consistently delivering value for money and underscoring its efficiency and impact.
- Cost per CYP achieved: The overall cost per CYP was £4.49.

Equity: The HPF3 programme prioritised equity by ensuring fair benefit distribution and reaching marginalised groups, with a focus on gender balance and access to health services in vulnerable, remote areas. Continuous efforts were made to improve access to healthcare services, including antenatal care (ANC), SBAs, modern FP methods, and immunisation, particularly for children under five and individuals with disabilities.

The variation in equity in states is mainly due to geographical challenges, remote and hard-to-reach areas, such as EES and WES, often faced higher costs due to transportation and logistical difficulties. The reduction in the number of supported HFs in Y4 also led to increased costs per consultation in states like NBeG and WES, differences in resource allocation and management efficiency impacted costs. The cost per consultation increased as there were less facilities being funded, but the same admin costs associated with it (including cost of drug transportation and implementing partner costs). For example, states with better resource management, like NBeG, saw lower costs and local contexts/ factors such as flooding, insecurity, and inter-communal conflicts affected service delivery and costs in various states. For instance, flooding in some areas increased transportation costs, while insecurity in others disrupted health services.

HPF3's focus on equity was a core principle of the programme, aiming for fair benefit distribution and reaching marginalised groups. Across all 55 supported counties, training participants were selected with a focus on gender balance, prioritising women who had never been trained. Efforts were made to include female HCWs, despite their lower numbers. For BHI activities, emphasis was placed on vulnerable and remote bomas without HFs, with supervisors ensuring quality activities across all areas.

HPF3 consistently worked to overcome barriers to healthcare access, any HFs in remote locations supported by HPF3 received the necessary resources to support all population groups, despite geographical or social isolation. The use of services like antenatal care (ANC), skilled deliveries, and modern FP methods varied across regions, but continuous efforts were made to improve these indicators. Immunisation rates for children under one year and OPD consultations, especially for children under five years and individuals with disabilities, were routinely monitored to ensure equitable access to healthcare services.

Lessons Learnt
- For a comprehensive VfM assessment, cross-cutting themes such as sustainability, scalability and cultural acceptability also need to be assessed, as they provide critical contextual information for interpreting VfM assessments.
- Implementing outcome data collection tools for use across all locations which can be aggregated and disaggregated depending on the VfM analysis required. Seek to disaggregate data at the next possible opportunity
- Gender sensitivity: Incorporating gender-sensitive approaches in health programmes is vital to ensure that the specific health needs of women and men are addressed.

E: Risk Overview of risk management over the life of the programme

The overall risk rating for the HPF3 programme remained “Major” throughout implementation, this was due to the challenging context in which it operated and the implications this had on staff safety and effective programme delivery. Risk management over the life of the programme has been robust, it was discussed weekly at the FCDO/FM meetings alongside quarterly deep dives to inform updates to the programme risk matrix. FCDO also discussed risk internally at least once a month and quarterly through BEJ embassy-level Risk Board. The risk register was updated, as necessary, following these meetings, a full review was also done quarterly on the Aid Management Platform (AMP).
The HPF3 programme was designed based on the contextual challenges, in line with FCDO’s risk management guidelines and BEJ’s risk appetite. The BEJ financial and fiduciary risk appetite is receptive. Until January 2025, this was the same at the programme level due to the high probability of looting, theft, and damage to assets at national and sub-national level and to enable HPF3 to provide live saving health services. All Risk Appetites for HPF3 programme risk Categories was revised to minimal on 28 January 2025 and and approved by the Development Director, to reflect that HPF3 was no longer delivering services and that the contract with Mott MacDonald was ending.
The appetites against the seven categories were in line with the BEJ risk appetite throughout the programme implementation period. This reflected our acceptance of risk to deliver the HPF3 programme despite major access issues in much of the country due to insecurity and flooding. This also reflects our acceptance of risk to work with Government-run health facilities, which face severe capacity and economic constraints. At different stages the statements were revised to reflect the risk environment at the time.

Risk appetites BEJ and HPF3:
Risk category	Strategy & / Context	Policy & Programme Delivery	Public Service & Operations	People	Safeguarding	Financial & Fiduciary	Reputational
BE Juba	Eager	Eager	Cautious	Cautious	Receptive	Receptive	Receptive
HPF3	Minimal	Minimal	Minimal	Minimal	Minimal	Minimal	Minimal

The key risks that have materialised or occurred are:

Strategy and Context:

Conflict and insecurity continued to be a risk throughout implementation with sub-national intercommunal violence, armed attacks, violent cattle raiding, and violent crimes. The HPF3 security procedures that were used enabled the programme to identify hotspots, halt supportive supervision activities and movement in affected areas and where possible, move activities to secure areas, to ensure the programme's continued effectiveness in addressing and preventing potential threats.
The Sudan conflict; the conflict that broke out in April 2023, in the neighbouring Sudan led to an influx of refugees, returnees and asylum seekers into South Sudan, which has led to increased strain on health care service provision. The programme managed this through close monitoring of the impact on drug consumption and stockouts and liaised closely with humanitarian actors to manage it.

Climate related risks and in particular flash floods often occurred during the rainy season, resulting in people being displaced, and health facilities being damaged, hampering access and disrupting health service provision. Poor road conditions due to heavy rains and flooding made accessibility difficult for programme teams and communities, this made the distribution of drug consignments challenging. Mitigation measures included: IPs pre-positioning drugs and essential medical supplies to health facilities before the start of the rainy season and some health facilities relocated to higher grounds to continue providing services to their communities and delivering health services in mobile settings to reach displaced communities.

Disease outbreaks. HPF3 implementation dealt with several disease outbreaks and threats including Ebola, measles, polio, yellow fever, hepatitis C and E and viral haemorrhagic fevers (VHFs). Of note was the COVID-19 pandemic that began in 2020 restricting travel, service delivery, and oversight activities. Resources were diverted to cope with the COVID-19 response putting a constraint on financial resources for the programme. The partial lockdown in Juba resulted in delayed delivery of drugs, vaccinations, and other important health supplies, people’s ability to access health services was limited, the availability of essential medicines and equipment in HFs was reduced which resulted in underperformance of certain indicators. During COVID-19 pandemic, some areas reported reduced ability to access health services especially for persons living with disabilities due to reduced opening hours of health facilities, reduced availability of essential medicines or reduced quality of care at facilities

Over the course of the programme, the economy was also highly unstable. Furthermore, the lack of resources allocated to the health sector by the government impacted on the Ministry of Health’s engagement in the programme and ultimately meant reductions in capacity-building ambitions. This led to more difficult relationships between donors and government, further reducing government engagement in the programme. Government failures to fulfil its initial health sector commitments, including payment of health workers and officials led to increased absenteeism and by the time of programme closure, most health workers were owed over 10 months’ worth of salary. HPF3 mitigated this by paying incentives to health workers involved directly in service delivery and uses diplomacy and lobbying to push for more spend on basic health services.

Policy and Programme Delivery:

HPF3 transition to HSTP: the HPF3 faced severe risks when it came to the transition to the new health service delivery programme the Health Sector Transformation Project (HSTP). Slower than expected progress toward HSTP project effectiveness impacted on HPF3 transition timelines including the planned 6-month overlap between the two programmes required to transfer intellectual property, assets and learning to prevent a gap or disruption to service delivery. In year 5, this risk rating moved from major to severe as handover timelines shortened and risks to HPF3 transition and closure increased.

This risk was managed through our engagements with the MoH, WB and UNICEF both at a technical and senior level, as well the regular weekly transition meetings between the HPF3 team, UNICEF, WB, MoH and FCDO. In addition, FCDO issued a contract amendment to extend HPF3 service delivery support to the end of June 2025 to allow for a HPF3 and HSTP transition period when it was obvious that HSTP mobilisation would be delayed.

Financial and Fiduciary

Financial resourcing constraints: The reduction in aid spending by the UK government and other HPF3 donors in response to the COVID-19 pandemic and the Ukraine crisis significantly impacted HPF3. Although it was able to continue, it had to scale down and withdraw from 229 HFs (220 PHCUs and nine state/referral hospitals) and transitioned 56 HFs in Unity State to the WB/UNICEF supported project during Y3 and Y4. At the start of year 5, a major financial risk was inadequate funding particularly to sustain activities that support the CHDs, with the IPs highlighting funding gaps for CHD incentive payments, internet connectivity, fuel for project vehicles and additional Expanded Programme on Immunisation activities. HPF3 monitored the funding and the impact of the funding gaps, prioritising budget allocations and ensured critical areas were adequately resourced. Savings from Y4 and the procurement of medical supplies also helped to bridge some of the gaps initially not funded in Year 5, like support to CHD IPs and Routine EPSI activities. However, GESI activities remained unfunded.

Asset management: Another major risk was that state authorities would confiscate HPF3 assets. This was managed by the IPs and the FM in most cases and escalated to FCDO when additional measures were required. FCDO managed the risk by working closely with the MoH, Ministry of Humanitarian Affairs (MHA) as well as the Relief and Rehabilitation commission (RRC) both at national and state levels, issuing letters for use by IPs clearly stating the assets belong to the FCDO. Other risks have included economic volatility and exchange rate fluctuations which were closely monitored throughout the year. There was also a major risk to assets when Crown Agents Limited were in financial trouble and going into liquation that if another partner wasn’t found to take over as fund manager that potential 6000 assets were at risk of confiscation and theft before they were able to be transferred to HSTP. This was mitigated by agreement from IPs to secure assets in their compounds nationwide and also due to the signing of a new contract with Mott MacDonald the day after CAL went into administration. This did however still cause delays and complications to asset handover.

Reputational
Transition to HSTP: FCDO has proactively managed potential risks reputation in South Sudan due to the delays to the mobilisation of World Bank/MoH-led HSTP. These threatened to disrupt the delivery of basic health services in facilities previously supported by HPF3 which could have led to increased maternal and child mortality. The risk was mitigated to some degree because of FCDO’s engagement with the World Bank, UNICEF and the MoH to raise potential risks and by extending the HPF3 contract to continue service delivery for an additional three months and then providing three further months of mentoring to the new IPs.

Safeguarding
Reported Cases: a total of 19 Sexual Exploitation, Abuse and Harassment (SEAH) concerns were reported during HPF3 programme and were formally submitted to the FCDO Reporting Concerns mechanism. . Investigations were completed for all 19 incidents. Given the high levels of Sexual and Gender Based Violence (SGBV) in South Sudan and the scale of the programme, the number of cases reported is relatively low. This is largely attributed to the stigma surrounding the reporting of such incidents, which often leads to fear of backlash and rejection from their communities, as well as a widespread societal acceptance of SGBV, particularly against women. Additionally, the effectiveness of the programme reporting mechanisms also played a role in low number of disclosures.
As a result of the investigations, contracts for two implementing partners (IP) staff were terminated. Furthermore, government staff involved in the incidents were either discontinued from the programme, stopped from receiving incentives, or transferred. It is important to note that most of the perpetrators were government staff receiving programme incentives, whose human resource management falls under government structures. Unfortunately, these structures often have weak safeguarding mechanisms, which posed a significant challenge to accountability and prevention efforts.
The HPF3 team and IP safeguarding focal persons met quarterly to discuss how to handle different potential safeguarding scenarios and safeguarding obligations and reporting mechanisms. Bulletins were circulated among HPF3 and IP staff following these meetings to share learning. IPs held similar sessions with all stakeholders at CHD, State Ministry of Health and gender meetings. The HPF3 programme conducted safeguarding refresher training for HPF3 staff and health care workers. The training aimed to enhance the skills and knowledge of the programme team, and to prevent harm and reduce the risk of abuse as well as to appropriately report any safeguarding concerns. IPs continued to strengthen the safeguarding awareness raising in the community through the engagement of BHWs on different safeguarding topics and encouragement of the community members and staff to report any cases or concerns immediately using the provided reporting mechanisms. There has been increase in the number of safeguarding cases reported under HPF3 compared to HPF2 and other Programmes in BEJ due to the trainings and reporting mechanisms in place. However, 19 cases over the programme lifetime are considered low given size of the programme,

Update on Partnership Principles

There was no conditionality requirements linked to this programme, as it does not channel funds directly to or through the Government. The programme, however, supported technical assistance and supervisory visits by national and state ministries of health; but these funds only covered travel expenses and did not use government systems.

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

FCDO Performance

FCDO demonstrated effective programme management throughout the HPF3 implementation period, responding strategically to contextual changes, managing risks, and ensuring appropriate budget allocations. The programme team successfully delivered four business case amendments, four contract amendments with Crown Agents Limited (now on liquidation) and one no-cost contract amendment with Mott MacDonald, alongside numerous operational adjustments. These changes often required complex decision-making and coordination with delivery partners.
At the start of each year, FCDO worked collaboratively with partners to prioritise funding for services targeting the most vulnerable populations, with a strong emphasis on output delivery, value for money, and risk mitigation.

Fund Manager Performance

Crown Agents Limited (CAL) were the lead supplier for the majority of the implementation of the HPF3 up to July 2024 when they went into liquidation. The working relationship continued to strengthen and improve between the BEJ, FM and HPF teams, which is an achievement given the challenges faced and staff turnover in BEJ throughout the programme. This enabled constructive and open discussion throughout implementation, this was especially helpful during budget reduction scenario plannings, including the selection process for lower-level facilities where HPF withdrew support in Year 3 and all state hospitals in Year 4.

Delivery Chain Contract Management

The Fund Manager continued to use a standard contracting template with all IPs setting out clear terms and conditions, KPIs with defined submission timelines, costed work plans, and detailed budgets, which the IPs submitted on monthly and quarterly bases. The FM contracts team assess and review IP performance against KPIs and assess contractual risks for all IPs on a regular basis during IP review meetings. Financial Management Assessment (FMA) were conducted at the beginning of every financial year before contract issuance.

Compliance

Supplier Code Compliance

CAL’s original assessment of compliance with the Code at organisational level took place in September 2018, where they achieved a score of 100%. Annual checks were subsequently carried out to verify continued compliance with the Code in 2019, 2020, 2021, 2022, 2023 and 2024. No areas of concern were identified during these checks until 2024, when the submission was found to be unsatisfactory, containing out of date documents and declarations. CAL received an SSRM Performance Score of 60% for January-June 2023 which increased to 64% for July-December 2023 – these are mid-range scores that did not require any specific interventions. In February 2024, HPF3’s SRO alerted Commercial SSRM about potentially unpaid subcontractors, prompting ongoing discussions between Commercial and CAL’s senior management regarding financial concerns.
By the point these issues were identified, it was clear that CAL were in serious financial difficulty and the company went into receivership shortly afterwards. CAL later entered liquidation, leading FCDO to appoint Mott MacDonald as Fund Manager and ensure proper and responsible closure of the programme.

Mott MacDonald – Code of Conduct Compliance Supplier Code Compliance:
FCDO worked promptly to bring in Mott Macdonald as the replacement supplier for the final six months of the programme. This was a huge achievement for FCDO and avoided major disruption to the health services and the potential loss of nearly 6000 programme assets.

Mott MacDonald’s original assessment of compliance with the Code at organisational level took place in October 2018, where they achieved a score of 100%. Annual checks to verify continued compliance have been conducted each year since, and we are currently in the process of reviewing their 2025 Annual Declaration submission. No areas of concern have been identified during these checks, and they have maintained a score of 100% compliance.
Profit Margins and Transparency: Mott MacDonald complies with the requirements contained in the Supplier Code of Conduct in terms of a commitment to open book accountancy and declaration of profit margins on an annual basis. We are currently reviewing their Profit Margin Declaration for 2025. Please note that due to the urgent nature of the HPF3 replacement contract as well as it’s short duration - there were no profit reporting requirements specific to this particular contract.

The BEJ team continued to assess FM performance on reporting, financial management, and project management and technical progress against the programme Key Performance Indicators (KPIs[2]), on a quarterly basis. Financial penalties were applied when KPI targets were not met, and the value of penalties are dictated by the priority given within the assessment criteria. The FM was also assessed quarterly against three output-based transparency KPIs[3] for FCDO transparency reporting purposes, assessing and reporting on the performance of its largest commercial suppliers.
[2] Examples of the KPIs included completeness and timeliness of quarterly financial reporting from Fund Manager, completeness and timeliness of monthly invoices, and completeness and timeliness of technical and financial reporting from Implementing Partners to Fund Manager.
[3] KPI 1 – Number of new users of modern family planning methods. KPI 2 – Percentage of health facilities receiving commodities within a defined time period. KPI 3 – Number of children vaccinated with three doses of pentavalent vaccine.

Reporting

ThThroughout the HPF3 programme, FCDO maintained close oversight of reporting from the Fund Manager (FM), regularly reviewing submissions and promptly following up on identified issues. The FM provided annual reports, quarterly narrative and financial reports, and an end of programme report, which were generally submitted on time. FCDO’s requests for clarification or supplementary information were typically addressed promptly.
However, the quality of reporting varied, and in several instances, reports lacked in-depth analysis of critical issues, which led to Key Performance Indicator (KPI) penalties. Specific concerns included poor quality reporting that required substantial redrafting, instances of double charging, and failure to meet financial forecast targets. These issues highlighted gaps in financial and operational oversight and required FCDO to take corrective actions to maintain programme integrity and accountability.

Finance management and budget execution

Financial management remained a focus throughout the programme period, with regular checks and communications on FM expenditure. Invoices were quality assured by two programme staff and approved for payment by a third staff member. This is a process that was then adopted by other teams in the embassy. The programme benefitted from contributions from other donors: USAID, Global Affairs Canada, Sweden, EU and and GAVI (see breakdown below). The UK was the lead donor and managed donor funds in line with strict quality standards, FCDO also the administrative and technical lead for this programme.

Proportion of Donor Contribution
Donor	Amount	%Contribution
FCDO	£153,904,919.00	44.2%
CANADA	£74,966,826.15	21.5%
SWEDEN	£49,767,178.35	14.3%
USAID	£39,059,275.17	11.2%
EU	£17,737,273.00	5.1%
GAVI	£13,047,483.56	3.7%
TOTAL	£348,482,955.23	100%

HPF3 total Programme life spent was £348.5M (81%) against an anticipated total donor's contribution of £426.5m. Only £78m as not allocated at closure due to insufficient budget availability/budget cut across the donors. The expenditure per year varied significantly, from a peak of £78,380,463 in FY2020 to a minimum of £7,064.345 in FY24. It is also worth noting that the FCDO programme team and partners managed funds effectively to ensure annual HPF3 programme budget was fully spent each year.

Annual Audited Financial Statements

In line with the general conditions of the service contract, an annual audit on the fund manager was undertaken throughout the programme lifecycle. An unqualified opinion was reported. Recommendations were tracked by the FM and they updated FCDO as required. The fund manager in turn conducted regular compliance reviews, including IP Due Diligence assessments, Financial Management Assessment (FMA) and Annual IP Audits which fed into the FM audit report.

Asset Management

The HPF3 Business Case identified looting or confiscation of humanitarian assets or supplies and informal taxation of supply convoys as a significant risk. It was a regular problem, and even at closure HPF3 partners are still dealing with the confiscation of assets by government actors. This is an issue closely monitored by delivery partners in South Sudan, and the UK and other donors take an active role in advocating against the illegal seizure of partner assets. The fund manager and all INGO/NGO maintained asset registers have policies in place for asset management. Annual spot checks were carried out by FCDO staff which mostly confirmed accuracy of partner asset registers and effective management. Minor issues were occasionally identified and quickly resolved by the partner. At closure disposal plans representing VFM for the UK taxpayer were implemented, with the majority of assets being transferred to the successor health programme (HSTP) in which FCDO plans to invest.

Risks

HPF3 programme adopted robust internal controls for risk management, which increased in strength over the life of the programme. Risk management included:
1. Partners provided updated risk matrixes in agreed reporting timeframes (usually quarterly), along with updated downstream chain risk mapping. These were regularly interrogated during partner meetings.
2. FCDO managed an overall programme risk matrix, with monthly reviews and substantive quarterly refreshes by the programme team, SRO and PRO. AMP was updated regularly.
3. FCDO and the FM discussed context updates at weekly meetings and any major security incidents involving partners are rapidly shared across British Embassy Juba.
4. FCDO contributed to the Quarterly Assurance and Compliance Board, led by the Development Director. This group discussed ongoing risks, lessons learnt and shared best practice.
5. The SRO, via the embassy risk lead, contributed to BE Juba and Directorate monthly risk updates, with a focus on substantive new risks, severe risks and/or risks outside FCDO’s risk appetite with the latter being escalated to the Development Director in line with BE Juba and wider FCDO risk management processes.
6. The SRO contributed to quarterly cross-FCDO programme board meetings where significant risks and any risks outside of the office’s risk appetite were discussed, drawing in expertise from across the FCDO office and linked to HMG management of strategic risks as appropriate.

The above activities proved effective for risk management, ensuring issues were kept live and escalated as required. Some of the key mitigation measures included:

- Donor led advocacy on humanitarian access, in conjunction with, and on behalf of, delivery partners and NGOs through line ministry and Ministry of Humanitarian Affairs. For example, the British Embassy would write to the Relief and Rehabilitation Commission requesting the return of confiscated assets when this occurred.
- Encouraging all partners to join the Preventing Sexual Exploitation and Abuse (PSEA) taskforce. FCDO monitoring visits also ensured partners implemented measures to prevent SEAH. E.g. availability of suggestion box and dedicated hotline for reporting SEAH concerns.
- FCDO programme team conducted asset spot checks and market surveillance to detect and report any incidence of medicines leaking into local markets. Local Authorities were alerted to investigate incidents and prosecute those responsible.

Value For Money

The Business Case set out various measures by which value for money (VfM) would be tracked. HPF3 developed a VfM framework in 2019. This focused on economy and efficiency effectiveness, cost-effectiveness and equity VfM measures. The VfM measures implemented during the lifetime of the programme are similar to those identified in the original Business Case, and VfM performance has consistently been reported against throughout the project implementation period. This has led to on-going updates to the framework, although these have been insufficient to overcome its initial weaknesses. Recommendations from VfM reports and on-going VfM analyses contributed to key adjustments in project implementation processes throughout the project’s lifetime. This has supported by the cross-cutting support of the BEJ Economic Advisors.

The economic deterioration and conflict have inevitably impacted on HPF3 in terms of VfM. Administrative costs have increased during the lifetime of the programme due to rising banking costs/ high fees rates charged by money transfer agents (MTAs) and currency depreciation. Increased transaction/banking costs resulted from the closure of banks in locations outside of Juba due to insecurity, this led to the need to physically transport money these areas. Nevertheless, as evidenced below, and through the exceeding of logframe targets whilst maintaining the same budget, the HPF3 programme is still considered to offer VfM, as set out in the Business Case.

Programme-level approach to monitoring and evaluation

In addition to annual reviews, several monitoring instruments were employed concurrently during HPF3. Although external monitor HPF3 was envisaged, it was not utilised to the full extent. The difficult operating environment of South Sudan also creates challenges to effective monitoring. However, key activities included:

- HPF3 maintained a logframe for the delivery of the programme where annual targets were reviewed and amended as required. Output indicators from the FM result framework were used to inform the HPF3 programme overall results framework. The results of which are presented above.
- The FCDO HPF3 team conducted field trips to project implementation areas to observe project activities and talk to partner field staff and beneficiaries to get firsthand feedback. The visit areas were largely dictated by accessibility constraints and security concerns.
- Other donors such as Global Affairs Canada, USAID, EU, SIDA and GAVI also shared feedback directly with the HPF team and with FCDO following visits.
- Further independent third-party monitoring was provided by the World Health Organization on health service functionality and through the USAID third-party monitoring by Insights, this highlighted gaps in service availability at facilities. The FM, working with the FCDO team, tracked recommendations as a result of programme monitoring and reported on progress against these, which continued to drive progress on the programme.
- Crown Agents and partners conducted their own M&E. All partners had effective monitoring mechanisms enabling them to accurately measure progress and make informed decisions to adapt programme where necessary and they used findings to improve delivery.
- Lot Quality Assurance Sampling (LQAS) was used in HPF3 to monitor key outcome indicators such as institutional deliveries, modern contraceptive use, and child wasting. Two LQAS surveys were conducted, one in 2020 across all ten States and another in 2023 in four HPF3-supported States. While LQAS provided valuable insights, its limited geographic scope and infrequency constrained its utility for national-level impact assessment. Moreover, discrepancies between LQAS and HMIS data highlighted challenges in data triangulation and representativeness.
- KIT Royal Tropical Institute was responsible for operational research in HPF3 until its exit in March 2022 due to funding cuts. KIT conducted studies on healthcare access and barriers to implementing community health worker programmes in conflict-affected areas. Their findings underscored the importance of BHWs in reaching populations beyond the reach of health facilities and informed phased training approaches. KIT’s contributions were instrumental in shaping BHI strategy and community health programming, though their early departure limited continuity in research and learning.

## Lessons Learned over life of the programme
Community engagement: Effective CE and accountability mechanisms were crucial for improving health service delivery and ensuring that community needs were met. Encouraging community ownership fostered responsibility and commitment. The use of BHWs for basic health services delivery and education at the community level significantly improved health outcomes.

Integrated services and capacity building: Combining HF services with community-based interventions, such as BHW case management for malaria, pneumonia, and diarrhoea, and health promotion initiatives, enhanced the programme’s reach and impact. Continuous capacity building for HCWs, including training and supportive supervision, was essential for maintaining and improving quality of care.

Supply chain management: Establishing a reliable and resilient supply chain system is critical to ensuring uninterrupted access to essential drugs and medical commodities, particularly in fragile and conflict-affected settings. The programme’s ability to deliver supplies three times annually, including hard to reach and insecure areas was instrumental in maintaining service continuity. The use of buffer stocks at central and state levels proved effective in mitigating stockouts and managing logistical challenges. This experience highlights the importance of advanced planning, flexible logistics, and contingency measures in sustaining health service delivery in complex environments.
Data collection and quality improvement: Using data for decision-making and monitoring progress helped identify gaps and make informed adjustments. Regular M&E identified areas for improvement, measured intervention impacts, and ensured efficient resource allocation. For example, monthly drug consumption data from HCWs informed future procurements and stock rotation. Regular assessments of quality of care, timely feedback, and implementation of quality improvement action plans led to tangible achievements in health service delivery.

Learning and adaptation: Flexibility and adaptability allowed for adjustments in response to changing contexts and emerging challenges. HPF3’s resilience was demonstrated by its ability to adapt to challenges such as insecurity, implementing innovative solutions, and maintaining flexibility to continue delivering essential health services despite external shocks, poor infrastructure, and logistical issues.

Partnerships and sustainability: Strong partnerships between the government, donors, and IPs were critical for successful implementation. This collaborative approach facilitated information sharing, risk identification, and joint mitigation strategies. Focusing on sustainable practices, such as building local capacity and strengthening health systems, ensured the long-term impact of health interventions. The sustainability of the HPF3 programme interventions depended on a robust health delivery system, supported by the IPs, and involved capacity building for oversight and quality improvement at the local level. Additionally, sustainability required ongoing investments in equipment, infrastructure, training, and incentives for HCWs, as well as continued support for HMIS and the regular supply of essential medicines.

Date of last narrative financial report	April 1st 2025	Date of last audited annual statement	April 11th 2025