Annual Review

Title: Mobile for Humanitarian Innovation (M4H)
Programme Value £ (full life): £15.5 million		Review Date: June 2019
Programme Code: 300446	Start Date: September 2017	End Date: / September 2021

Summary of Programme Performance
Year	2018	2019	2020	2021
Programme Score	A+	A+
Risk Rating	Major	Major

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/33097787.odt
DevTracker Link to Log frame:	Upload pending

## A. Summary and Overview

Description of programme

The Mobile for Humanitarian Innovation (M4H) programme works with the mobile industry and humanitarian organisations to accelerate the delivery and impact of digital humanitarian assistance. The programme focuses on catalysing partnerships, investing in innovation, unlocking policy barriers and delivering original research that will strengthen the role and sustainability of mobile-enabled services in humanitarian contexts. M4H aims to reach seven million people with improved access to and use of life-enhancing mobile-enabled services during humanitarian and disaster preparedness, response and recovery (by 2021).

M4H is working to accelerate the delivery and impact of digital humanitarian assistance by:
1. Building a base of unique insights on technology's role to improve humanitarian response;
2. Delivering tangible projects between the private sector and humanitarian community that demonstrate digital solutions in action and build evidence of what works;
3. Providing funding to support cutting edge innovations targeting humanitarian challenges through the Innovation Fund;
4. Convening private sector, public sector and the humanitarian community and advocating for enabling policies to improve the lives of those affected by humanitarian crisis.

The model proposed is applied across the following four focus areas:
1. Mobile financial services – Accelerate the provision of mobile financial services to enable digital humanitarian cash transfers and support the livelihoods and financial empowerment and resilience of disaster-affected populations
2. Mobile enabled utilities – Leverage the power of mobile-enabled off-grid energy and water innovations to improve access to these services by refugees and crisis-affected communities
3. Mobile solutions for food security, adaption and resilience to climate change – Accelerate the impact of digital technology to help improve the food security and climate change resilience of rural communities
4. Digital identity – Leverage mobile to improve beneficiary registration and support identification requirements of refugees and other crisis-affected people

Additionally, across these four focus areas, the programme will explore how the digital gender gap will impact women’s access to digital humanitarian services to ensure women are not further excluded or made vulnerable by asymmetry in access to technology in a humanitarian context. The programme will also seek to understand how people with disabilities access and use mobile services in crisis and will remain open to cross-cutting, relevant themes such as health.

Summary supporting narrative for the overall score in this review

During the second year of operation, the programme built on its progress from year one (where it set the foundation of the programme) and (1) has leveraged research and insights to explore the current state of investment, stakeholder priorities, and gaps in knowledge that the programme and its partners could help address; (2) supported an improved enabling environment for refugees; (3) catalysed innovation by selecting 9 grantees under round 2 of the innovation fund; and (4) built a pipeline of partnerships with mobile network operators and humanitarian agencies. The programme has scoped 11 projects in the past year and signed five agreements with humanitarian partners.

The programme has met or exceeded all output targets and three out of the four outcome targets for the second year. The programme is on track to reach its impact target of seven million people (directly and indirectly) with improved access to and use of life-enhancing mobile services during humanitarian and disaster preparedness, response and recovery by 2021.

Key achievements from the second year include:
- An additional three million beneficiaries have been impacted by programme activities with mobile operators. Beneficiaries were reached via the programme’s Humanitarian Connectivity Charter initiative and previous work in Haiti with the Directorate for Civil Protection (DPC) and the Alliance for Disaster Management and Business Continuity (AGERCA) to establish the Disaster and Emergency Early Warning Network (DEWN). DEWN was activated in October 2018 and 3,013,703 text messages were sent to residents of Nord-Ouest, Nord, Nord-Est, and le Plateau Central et l’Artibonite departments. The text messages were meant to calm the population following a magnitude 5.9 earthquake and inform them of precautionary measures to adopt during the aftershocks.
- 12 new research publications were published and seven videos developed during the second year of implementation, covering the five programme themes (digital financial services, digital identity, climate resilience and food security, utilities, and gender). The publications built on the 2018 landscaping reports and have been valuable inputs in the discussions and partnerships with humanitarian organisations.
- The Advocacy components of the GSMA and UNHCR MoU have been operationalized. This year also saw the launch of the Displaced and Disconnected report: an in-depth research report on the policy and legal barriers that 20 host-country governments impose on Mobile Operators in the context of offering mobile connectivity and mobile money services to refugees.
- Five partnership agreements have been signed with key humanitarian partners to deliver projects aimed at improving humanitarian delivery in Uganda, Somaliland, Pakistan and globally with the World Food Programme. Three of the five agreements were reached after the GSMA had convened and organised eight workshops bringing together MNOs, humanitarian organisations and third party suppliers, e.g. Fintechs. The workshops, received extremely positive feedback such as: “While the value of the subject and need to employ digital/mobile solutions to better the lives and economies for refugees needs no emphasis, I doubt that the consortium members individually or collectively would have made as much progress without the able convening provided by GSMA.”
- Nine grantees were selected from Round 2 of the innovation fund, including a diverse range of technological applications across Africa, Asia, the Middle East and Latin America.

Key lessons include:
- There is continued demand for quality data and rich insights: The M4H programme has engaged extensively this year with stakeholders—both through GSMA led workshops and externally organised conferences and panels. It was evident that there were significant knowledge gaps in the sector on how mobile technology can be used by people affected by crises is often non-existent. The insights provided by M4H’s work helped fill in the gap and inform stakeholders’ programmatic and advocacy work. Further, there is the need to improve the quality, relevance, and use of data and statistics and the programme has taken a robust methodological approach with the digital ecosystems study (mixed method qualitative and quantitative, including host communities).
- Cash and Voucher Assistance is a priority topic for stakeholders: The programme has identified that there is significant appetite from stakeholders to engage on digital financial services. This is evidenced by the interest around the programme’s publication of the Cash and Voucher Assistance (CVA) report series[1], which was launched in early April 2019 at an event in Nairobi. There were over 50 participants from five mobile network operators (MNOs) from Kenya and Somalia, as well as the Cash Learning Partnership (CALP) and various humanitarian organisations. The reports have already been downloaded / distributed 1,544 times and hosted on several websites, including the Cash and Learning Network (CaLP). This is another step in building the reputation of the GSMA’ M4H programme as a thought leader on mobile and digital solutions in the humanitarian sector, and harnessing the significant opportunities around Cash and Voucher Assistance pilots. M4H is working on various projects designed to tackle a particular challenge within the process, highlighting that it is important to build the business model beyond the digitization of cash transfers alone. The programme research has shown how important it is to consider the entire ecosystem in which the refugees live, explore the various revenue streams and expenditure patterns. Further, the local context played a crucial role in determining whether digitising CVA is appropriate. This included beneficiary awareness and acceptance of mobile phones and mobile money, as well as the investment that may need to be made in the mobile money infrastructure. Such information has enabled the programme to identify sustainable models, which are impactful on the lives of the refugees
  [1] Mobile money enabled cash aid delivery: Operational handbook for mobile money providers; Mobilising cash and voucher assistance programmes: The case for mobile money; Mobile money enabled cash aid delivery: Essential considerations for humanitarian practitioners
- Unblocking barriers to mobile usage through digital skills: Two of the five partnerships established this year prioritise addressing the digital literacy barriers that refugees face in mobile usage. This is supported by programme research in Uganda and Rwanda, which highlighted that low literacy and digital skills levels are a key barrier, limiting women’s ability to use handsets, particularly for mobile internet. The programme is therefore exploring various ways to address this gap through its work with Grameen Foundation and MTN (Uganda) and Mercy Corps (Uganda).
- Focus on data privacy and ethics: Grantees have highlighted the value of GSMA expertise regarding data privacy and sought guidance on “best-in-class” data protection for vulnerable groups. The programme is focusing more attention on developing meaningful tools for grantees on these issues, through internal collaborations (grantee workshop, collaborating with other M4D teams) and external canvasing of digital ethical tools and illustrative best practices, and co-ordinating with the International Federation of Red Cross and Red Crescent Societies (IFRC) and the International Committee of the Red Cross (ICRC) to share lessons and best practices that could inform M4H approach on this topic
- Demand for funding tailored to the stage of innovation: Feedback from Innovation Fund Round 2 and early findings from Round 3 have shown that there is demand for financing models which are structured to for different stages of innovation: adapting existing mobile enabled solutions, testing and validating new models of service delivery, and scaling solutions with proven potential for impact. Applicants in Round 3 will therefore receive appropriate funds for the stage of innovation, rather than request maximum ticket sizes.

Recommendations for the year ahead

1. Delivering impact and improving humanitarian delivery as a result of M4H partnerships between humanitarian organisations and private sector is crucial for the year ahead. As such, M4H will develop monitoring and evaluation frameworks for three partnerships in order to demonstrate the partnership outcomes and/or validate effective implementation, in view of identifying opportunities to scale. [April 2020]
2. M4H will analyse the applications received during the Round 3 window and connect with similar innovation funds such as Canadian Grand Challenges to learn and assess sector demand for tailored funding, which encourages successful existing products and services to be trialled in humanitarian contexts. The fund will also offer “scale funding” which supports models already proven in humanitarian contexts to replicate across markets and regions. The findings will inform future strategies to support innovation in the humanitarian sector. [November 2019]
3. The GSMA M4H programme will continue to have dialogue with other funds in the humanitarian innovation space including DFID funded programmes (Grand Challenges, Humanitarian Innovation Business Case), and with major humanitarian agencies, to maximise coherence and share best practice. DFID strategic partnership manager will lead on ensuring coherence with DFID humanitarian innovation programmes. [Ongoing, with updates provided to DFID in each quarterly report meeting]
4. Responding to programme learning that partnering with an external organisation to conduct webinars is an effective way to increase both readership across the globe and increase programme visibility as thought leaders, the M4H programme should partner with research organisations / think tanks to disseminate research via two webinars. [June 2020]
5. The GSMA M4H programme has submitted a recommendation for a no-cost 6-month extension to extend the programme from September 2021 to March 2022, under the current funding amount. The rationale for this is detailed further in Annex H - ‘M4H NCE_Final’. Approval of this Annual Review will trigger the extension of the relevant Accountable Grant (which also covers the M4D partnership) to March 2022. This is also referenced in the 2019 Annual Review for the Mobile for Development partnership. [August 2019]
6. DFID and GSMA will review the Surge Support model. GSMA to provide menu of options for supporting DFID Humanitarian Advisers, and DFID to present to Humanitarian cadre to agree on way forward. [September 2019]
7. GSMA to update the current output Logframe targets to reflect the overachievement of some targets in year 1 [November 2019]

## B: DETAILED OUTPUT SCORING

Output Title	Private sector and humanitarian organisations actively engage with GSMA M4H to implement programme activities.
Output number per LF		1	Output Score	A+
Impact weighting (%):		50%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of cases where the programme has engaged with programme stakeholders (excluding policy makers) to improve humanitarian delivery (cumulative)	10 (additional 6 compared to previous reporting period)	Exceeded – 17
1.2 Number of cases with evidence of partnerships established between programme stakeholders (MNOs, humanitarian organisations, donors, non-governmental organisations, private sector) to improve humanitarian delivery as a result of M4H (cumulative)	5 (additional 3 compared to previous reporting period)	Exceeded – 7
1.3 Number of cases where the programme has engaged with policy/regulatory/ international influential bodies to improve humanitarian delivery (cumulative)	5 (additional 2 compared to previous reporting period)	Exceeded – 8

Provide supporting narrative for the score

During the reporting period, the programme has increased the scale of engagement with all programme stakeholders, exceeding all of the indicators under Output 1.

1.1 Number of cases where the programme has engaged with programme stakeholders (excluding policy makers) to improve humanitarian delivery (cumulative)

The M4H programme exceeded its target under this indicator. M4H completed 13 engagements with senior officials of various stakeholders to improve humanitarian delivery over the past year. These engagements demonstrate M4H’s ability to convene senior staff from key stakeholders to address humanitarian challenges. As a result, the programme has experienced an increase in organisations looking for opportunities to collaborate with M4H in the future. These engagements resulted in the programme signing three partnerships to implement new projects (see indicator 1.2).

The programme convened its Advisory Group, with representatives from MNOs, bilateral and multilateral institutions and non-governmental organisations (NGOs), twice during the reporting period (November 2018 and February 2019). The Advisory Group remains a crucial avenue for the programme to facilitate productive dialogue between the mobile industry and the humanitarian community, facilitate partnerships between members, identify areas where there is complementary and/or duplicative efforts between organisations, and address some of the key barriers to delivering effective digital humanitarian assistance. A key outcome this year was the agreement on the vision and mission of the Advisory Group (Annex B).

The programme also organised eight workshops with representatives from MNOs, bilateral and multilateral institutions, and NGOs. At the workshops representatives were able to develop a shared understanding of emerging processes, issues, and opportunities to support deeper partnerships. Several workshops were organised in collaboration with other GSMA M4D programmes, such as Mobile Money, Connected Society and Connected Women to leverage their insights.

These include:

Mobile for Humanitarian Innovation Workshops
Digital Financial Services
Cash and Voucher Assistance (CVA) workshop, Kampala, Uganda, 12th November 2018 (In collaboration with M4D Mobile Money programme) / CVA workshop, Amman, Jordan, 25th October 2018 (In collaboration with M4D Mobile Money programme) / GSMA and CaLP workshop, Hargeisa, Somaliland, 8th April 2019 (In collaboration with M4D Mobile Money programme) / M4H implementation workshop with GiveDirectly on leveraging Mobile Money for humanitarian large cash grants, Kigali, Rwanda 11th March 2019 / GSMA, World Vision Rwanda, American Refugee Committee and MTN consortium workshop on digital and financial inclusion, Kigali, Rwanda, 13-14 March 2019
Digital Identity
Solution design workshop beneficiary verification, Hargeisa, Somaliland 5th March 2019 (In collaboration with M4D Digital Identity programme)
Gender and Inclusivity
GSMA and Grameen Foundation workshop on increasing access to financial literacy and training to female mobile agents, Kampala, Uganda 21-22 January 2019 (In collaboration with M4D Connected Women) / GSMA and Mercy Corps workshop on defeating the digital divide, Kampala, Uganda 20-21 March 2019 (In collaboration with M4D Connected Women programme)

Finally, the programme also engaged with three humanitarian forums. These include:
- Smart Communities Coalition (SCC) in Nairobi, a public private effort seeking to transform the operating model in refugee camps and settlements. The goals of the workshop were to: share lessons learned since the launch; agree upon governance and operational conditions that will drive success; and enable strengthened coordination to guide the design and implementation of activities;
- Humanitarian Private Sector Partnership Platform (HPPP) which supports systematic long-term private sector, UN, NGO, Government and community partnerships to address the impacts of natural disasters, emergencies due to conflict and complex urban and out of camp displacement situations. The programme works with HPPP in order to generate tangible and digitally supported solutions driven by the insights gathered by M4H and the HPPP research on preparedness, recovery and mitigation measures taken by Organizations and businesses in Kenya in relation to Man-made disasters and complex emergencies;
- Grand Challenges Canada (GCC), where M4H engaged frequently with the GCC team to provide project referrals, review and support fund selection processes, share insights and trends, and on joint promotions in order to maximise coherence and share best practice. Additional information is available in section G.

In addition, the programme has established a consortium with World Vision Rwanda, ARC and MTN in Rwanda as a first step towards a potential partnership. The consortium will firstly map the digital financial inclusion landscape in Rwandan refugee camps and host communities to determine the readiness of these populations to adopt digital financial services. The exercise will also determine the key conditions that need to be in place to drive the successful adoption of these services. The results of the proposed assessment will feed into the development of one or more consortium-led projects aimed at improving digital and financial inclusion among refugees and other vulnerable populations in Rwanda.

1.2 Number of cases with evidence of partnerships established between programme stakeholders (MNOs, humanitarian organisations, donors, NGOs, private sector) to improve humanitarian delivery (cumulative)

During the reporting period, the programme exceeded its target and signed five agreements with humanitarian stakeholders and MNOs to partner on projects aimed at improving humanitarian delivery:
1. Grameen Foundation and MTN in Uganda: to increase the number of female agents in Bidi Bidi camp by providing them with mobile and financial literacy skills.
2. Mercy Corps, CTen and MTN in Uganda: to improve digital literacy and skills by setting up three mobile community centres in Bidi Bidi, where refugees will be trained on topics including digital literacy, IT, and mobile money.

CARE and Telesom in Somaliland: CARE currently implements cash-based activities (conditional and unconditional cash transfers) in Somaliland. Together with the GSMA, CARE will pilot targeting a selected number of households during enrolment who will provide fingerprint biometrics as well as voice (speaking a specific word or phrase to capture the voice print). When it is time for disbursement, beneficiaries would be notified via SMS or an outbound voice message to dial a given code, which would prompt for the voiceprint. Beneficiaries would then speak the phrase used during enrolment and the platform would verify. Upon matching the voice print to stored biometric data, the platform would execute the payment via mobile wallet and the beneficiary could then access the funds. Where voice ID fails, the current disbursement and verification would be deployed as a secondary verification measure.

United Nations Office for the Coordination of Humanitarian Affairs (UN OCHA), Jazz, Telenor, Ufone and Zong in Pakistan: to provide mobile money based cash transfers to refugees and internally displaced people (IDPs). Humanitarian organisations and MNOs will work together on an exercise to map the mobile money presence and the key humanitarian activities in the 40+ most vulnerable districts identified by the National Disaster Management Authority (NDMA) of Pakistan in order to identify opportunities for collaboration between mobile network operators and humanitarian organisations.

World Food Programme (WFP) – global partnership: to build on existing research by GSMA and successful pilots by WFP to promote the use of mobile money in WFP CVA programs.

Additional information on each partnership is included in Annex C.

The programme is also scoping out possible strategic partnerships with additional partners, ranging from digitizing savings groups in refugee camps, developing payment solutions, and offering utilities via mobile money.

1.3 Number of cases where the programme has engaged with policy/regulatory/international influential bodies to improve humanitarian delivery (cumulative)

The M4H programme exceeded its target under this indicator, with five cases of engagement with policy/regulatory and other influential bodies during the reporting period. The programme’s engagement focused on highlighting the roles of MNOs and promoting advocacy messages at global platforms (e.g. the World Economic Forum in Davos, the UN General Assembly in New York, and Mobile World Congress 2019 in Barcelona), unblocking regulatory pain-points and advocating for enabling policy and regulatory environments in selected markets.

The five cases can be grouped under two categories:

Joining forces on common narratives with key partners (UN & Humanitarian actors)
  1. Operationalised the Advocacy components of the GSMA’s MoU with the UNHCR. This year saw the launch in various forums of the Displaced and Disconnected report, an in-depth research report on the policy and legal barriers that 20 host-country governments impose on MNOs in the context of offering mobile connectivity and mobile money services to refugees. This report, produced by UNHCR, in partnership with the GSMA, focuses on a relatively under-explored but nonetheless significant barrier to access among refugees and other displaced persons: legal and regulatory requirements mandating that an individual’s ID is authenticated before accessing a mobile connection, bank account or mobile money wallet. The programme presented the findings to at a UNHCR workshop in Denmark in December 2018, where 8 country offices of the UNHCR expressed an interest to collaborate on joint advocacy with the GSMA. Key messages were communicated by Kelly Clements, Assistant Secretary-General UNHCR to four refugee host-country governments at WEF in January 2019 and at MWC19 in February. Additional joint activities with UNHCR include participation in in-country workshops and joint presentations in forums including the International Telecommunications Union (ITU) World Summit on the Information Society (WSIS) in Geneva, and the UNHCR Global Virtual Summit on Digital Identity for Refugees where M4H joined panels in Canada and online.
  2. Technical Working Group (TWG), Uganda[2]. Considering the identification related policy challenges encountered by humanitarian agencies as part of humanitarian programming in Uganda as a refugee hosting country, the TWG looked at connectivity for refugees at policy, regulation and infrastructure level. The programme explored best approaches to drafting the national ‘connectivity for refugees’ strategy / plan and how to best institutionalise it in Uganda. The group considered the wider issue of connectivity for refugees from a policy, regulation and infrastructure level. They deliberated on the policy challenges relating to identification that exist in refugee hosting countries, like Uganda which would form the bases for the drafting and institutionalization of the national connectivity for refugee strategy.
    [2] Members include: United Nations High Commissioner for Refugees (UNHCR), United Nations Capital Development Fund (UNCDF), the International Rescue Committee (IRC), the United Nations Children's Fund (UNICEF), the United Nations Development Programme (UNDP), United Nations Office for Project Services, NetHope, Mercy Corps, BRAC Uganda Microfinance Ltd, The Lutheran World Federation (LWF), Finn Church Aid – Action for Human Dignity
  3. International Telecommunications Union (ITU) Global Forum on Emergency Telecommunications (GET19), Mauritius. The programme and GET19 participants made the case for partnerships, identified policy opportunities and discussed solutions to possible barriers in using mobile technologies in an emergency context. They also considered the role of regulators and mobile network operators working together on humanitarian related policy issues and explored the need for a national emergency telecommunication plan. The audience included over 180 participants from 36 Member States, representing public and private organizations, and resulted in several potential follow up activities with the Caribbean Telecommunications Union, and regulators of Trinidad and Tobago and the Benin Republic.

Delivering targeted Capacity Building course ‘Responding to Disasters and Humanitarian Crises’ to regulators
  1. Capacity Building workshop in Ghana (28-29 March 2019). The capacity building workshop, responding to disasters and humanitarian crises was delivered to regulators and policy makers in Accra, Ghana. The workshop, co-organised by Ghana Chamber of Telecommunications was attended by MNOs and representatives from 14 government offices and authorities. Attendees benefitted from a clearer understanding of current principles and practices of the role of mobile technology in disaster response. The workshop also established a starting point for future policy engagements with policy making agencies in the Government of Ghana. As part of the recommendations of the workshop, there was a public statement (also 1 and 2) where the government committed to setting up a multi sectoral team to draw an emergency telecommunications plan for Ghana.
  2. Commonwealth Telecommunications Organisation (CTO) Regulating ICTs Roundtable (1-5 April, London). This workshop brought together a mix of participants contributing scholarly and policy-focused perspectives on the problems of documentation, identification and recognition of migrants and refugees. The programme shared M4H advocacy work, policy recommendations from the publication ‘Responding to disasters and humanitarian crises’. The discussion also looked at the role of digital identity in transforming humanitarian aid delivery and the latest research on a set of 20 commonwealth countries examining the policy barriers related to SIM registration and know Your Customer / Customer Due Diligence and their impact on asylum seekers, refugees and returnees in the countries.

Lessons identified this year, and recommendations for the year ahead linked to this output
    - There are significant opportunities around Cash and Voucher Assistance pilots, and M4H is working on various projects designed to tackle a particular challenge within the process. It is important to build the business model beyond the digitization of cash transfers alone. The programme research has shown that it is important to look at the entire ecosystem in which the refugees live, explore the various revenue streams and expenditure patterns. Further, the local context played a crucial role in determining whether digitising CVA is appropriate. This included beneficiary awareness and acceptance of mobile phones and mobile money, as well as the investment that may need to be made in the mobile money infrastructure. Such information has enabled the programme to identify sustainable models, which are impactful on the lives of the refugees.
- Deepening the collaboration model with three Advisory Group members, WFP, IRC and Mercy Corps, is increasing the programme’s opportunity for impact. This is achieved by developing overarching agreements on both global and country specific projects related to the programme’s market engagement activities, research and insights and advocacy.
- The programme’s involvement with three private sector forums focused on humanitarian issues highlights the value M4H and the GSMA to such discussions as a ‘broker’ between the private and humanitarian sectors. The programme is identifying ways in which it can formalise its role within these forums in order to build long-term collaboration.
- Whilst there is interest from both MNOs and humanitarian organisations to collaborate, the programme has learnt that there are two main barriers for implementation: establishing trust and common language between private sector and humanitarian organisations and identifying project funding, especially due to the unpredictability of humanitarian crises which can be a hindrance to implement programme recommendations such as building in time and money to prepare for mobile money CVA. To address the first barrier, the programme has published research tailored for both private sector and humanitarian organisations in view of bridging the gap and speaking their language to each other, and has designed its workshops to create an environment where all participants can speak openly about their challenges and share their solutions. To address the second barrier, the programme is working with all organisations to highlight the potential of digitising humanitarian services, as well as funding technical assistance to unblock key barriers such as digital literacy and training female agents in refugee camps.

Recommendations
1. M4H will develop monitoring and evaluation frameworks for three partnerships in order to demonstrate the partnership outcomes and/or validate effective implementation, identify how innovation can be unblocked and opportunities to scale. This will include collaboration with the broader M4D team on codifying the ‘science of scaling.’ [April 2020]
2. M4H will uplift output 1 indicators in light of their achievements this year to ensure they are more stretching. [Revised Logframe to be submitted to DFID, November 2019]

Output Title	Technological innovations and business models selected and funded by the Innovation Fund
Output number per LF		2	Output Score	A+
Impact weighting (%):		30%	Impact weighting % revised since last AR?	30%

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of applications received through Innovation Fund rounds (cumulative) (disaggregated by geography)	540 (additional 80 compared to previous reporting period)	Exceeded - 687
2.2 Number of grantees of the Innovation Fund (disaggregated by geography) (cumulative)	12 (additional 7 compared to previous reporting period)	Exceeded - 14

Provide supporting narrative for the score
This Output relates to the Mobile for Humanitarian Innovation Fund, which aims to promote innovation in the use of mobile technology to address humanitarian challenges. As agreed during the creation of the original MfH logframe, this output includes the results of the first round of the Disaster Response Innovation Fund launched in September 2017 (funded under the GSMA Strategic Partnership) as well as the second round, under the M4H programme, which opened in July 2018. A supporting narrative on each of the indicators is detailed below.

2.1 Number of applications received through Innovation Fund rounds (cumulative) (disaggregated by geography)

GSMA Mobile for Humanitarian Innovation Fund – Round 3 was launched on 1 May 2019 and closed on 7 June 2019 with a total of 147 submitted applications. The third round promotes innovation in the use of mobile technology to address humanitarian challenges, specifically in complex emergencies and forced displacement contexts. Further analysis on the thematic and geographical spread of Round 3 applicants will be completed by October 2019.

Projects must be implemented through a partnership of two or more organisations and demonstrate a plan for long-term sustainability and scalability beyond the lifespan of the grant. Applicants were asked to show they have already engaged or plan to engage with one or more MNOs to support the design, implementation or future sustainability of their project.

Using learnings from rounds 1 and 2, and responding to DFID’s observation that more is needed to assist in the transition to scale for more promising innovations, the Fund re-structured slightly for Round 3 to provide a much wider stage gate approach. Additionally, efforts were taken to enhance the opportunity for organisations already operating successful M4D services in non-humanitarian contexts (i.e. PAYGO Solar systems) to adapt and test these models for humanitarian contexts. As such, Round 3 and the grants on offer were adapted to better suit the needs of the applicant(s) stage and match-funding capacity. Applicants to Round 3 can apply to 1 of 3 categories:
- Adapt existing mobile enabled solutions (up to £300,000)
- Test and validate new models of service delivery (up to £300,000)
- Scale up solutions with proven potential for impact (up to £500,000)

This represented an adaptation from Rounds 1 and 2 in the following ways:
- Reduced the minimum grant ticket size to £50,000 (previously £100,000)
- Increased the maximum grant ticket size to £500,000 (previously £300,000)
- Provided clear guidance (term sheet, infographic and videos) to help applicants select the most suitable stage and funding requirements.

The M4H Innovation Fund conducted targeted outreach to promote the call for concept notes, specifically to encourage applications with planned or existing mobile operator engagement. Outreach to date included publication on four external newsletters (GSMA IoT Innovators, ALNAP, CDACnetwork and DCHI), social media including LinkedIn and Facebook with 14,200 impressions of the hashtag #M4HInnovationFund and 106,000 views of Innovation Fund video four external webinars which attracted over 106+ mobile industry representatives, five multimedia promotional pieces: video and four infographics, and the fund web page which had been viewed 7,529 times. In addition, the M4H Fund team presented internally to GSMA on eight occasions leading to 15+ direct referrals from other M4D teams.

2.2 Number of grantees of the Innovation Fund (disaggregated by geography) (cumulative)

The M4H programme selected nine grantees under round 2 of its innovation fund:
Lead Applicant	Country / of Implementation	Project Name	Primary Thematic Focus
Danish Refugee Council	Uganda	Mobile Payments for Safe and Sustainable Water in Refugee Settlements	Mobile Enabled Utilities
American Refugee Committee	Rwanda and Uganda	Mwangaza ("Light"): Improving Refugee Access to Clean Energy	Mobile Enabled Utilities
United Healthcare Distributors	Uganda	Empowering women in Camps and Off-Grid Communities in West Nile	Mobile Enabled Utilities
Norwegian Refugee Council	Myanmar	Strengthening Digital Access to Needs-Based Protection Information for IDP Women	Gender & Inclusivity
International Rescue Committee	El Salvador and Honduras	Protecting Vulnerable Populations in El Salvador and Honduras	Gender & Inclusivity
Sesame Workshop	MENA, content distribution: Jordan Lebanon, Iraq, Syria	Sesame Seeds: An interactive mobile extension	Gender & Inclusivity
Naya Jeevan	Pakistan	My beautiful Thar: How Mobile Technology can Reduce Forced Displacement	Gender & Inclusivity / Food Security, Adaptation & Resilience to Climate Change
British Red Cross	Kenya	121 Personal Cash Aid	Digital Identity
Deutsche Welthungerhilfe e.V.	Global (data in India)	Child Growth Monitor	Food Security, Adaptation & Resilience to Climate Change

Detail of the full portfolio can be found in Annex D

Lessons identified this year, and recommendations for the year ahead linked to this output
- The programme continued engagement with other humanitarian funding bodies including StartNetwork, Humanitarian Grand Challenges, Humanitarian Innovation Fund (HIF) and WFP Innovation Accelerator. This interaction has continued to bring benefits to both the GSMA M4H Innovation Fund and its grantees and has enabled the programme to constructively contribute externally within this ecosystem. Beneficial activities include: coordinated awareness campaigns, sense-checking of new funding calls, mentoring and partnership facilitation for live grantees, collective problem solving, capacity building and capacity sharing support. The programme aims to continue building on these relationships in the coming year.
- Despite time and effort building capacity during the proposal stage of the application process, many applicants struggled to adequately complete the grantee logframe template. As such, the M4H monitoring and evaluation (M&E) have developed and integrated a series of capacity building tools and supportive techniques to better guide applicants on the process, including the development of a theory of change toolkit and a logframe webinar. In addition, the programme is arranging a capacity building workshop on grant reporting for round 2 grantees that will be held as part of the round 2 portfolio convening in Kigali in mid-July 2019, prior to the GSMA’s m360 Africa event.
- Focus on data privacy and ethics: Grantees have highlighted the value of GSMA expertise regarding data privacy and have sought guidance on “best-in-class” data protection for vulnerable groups. The programme is focusing more attention on developing meaningful tools for grantees on these issues, through the grantee workshop, collaborating with other M4D teams and co-ordinating with IFRC and ICRC to share lessons and best practices.
- Demand for adaptive funding under the Innovation Fund: Feedback from Innovation Fund Round 2 and early findings from Round 3 have shown that financing models which are structured to respond to different types of innovation are needed, for example, adaptive funding to trial existing / proven products and services in humanitarian contexts as well as scale funding for the post pilot stage.

Recommendations
1. M4H will undertake internal analysis and produce learnings from round one of the innovation fund to inform what the programme’s the engagement model with grantees will be after their grant has ended. [April 2020]
2. M4H will analyse the applications received during the Round 3 window and connect with similar innovation funds such as Canadian Grand Challenges to learn and assess sector demand for tailored funding, which encourages successful existing products and services to be trialled in humanitarian contexts, and ‘scale funding’ which supports models already proven in humanitarian contexts to replicate across markets and regions. The findings will inform future strategies to support innovation in the humanitarian sector. [November 2019]
3. The GSMA M4H programme will continue to have dialogue with other funds in the humanitarian innovation space including DFID funded programmes (Grand Challenges, Humanitarian Innovation Business Case), and with major humanitarian agencies, to maximise coherence and share best practice. [Ongoing, with updates provided to DFID in each quarterly report meeting]

Output Title	Research, insights and learning generated and disseminated to stakeholders by the programme
Output number per LF		3	Output Score	A+
Impact weighting (%):		20%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
3.1 – Usage: number of publications downloaded from the GSMA M4D website and physically distributed (content relevant to the partnership) (cumulative)	15,000	Exceeded – 22,804
3.2 – Thought leadership: Number of insights generated, (/ of which some are seminal reports[3]) that influence the industry. (cumulative)	27/3	Exceeded – 30/4
3.3 – Events: number of convenings with at least 3 different types of stakeholders and whose purpose is to disseminate learnings (cumulative)	45	Exceeded – 50
[3] A study is seminal if recognised by the humanitarian community as an important landmark in the field and is widely cited. GSMA tracks all citations related to M4H publications.

Provide supporting narrative for the score

Output 3 refers to the research, insights and learning generated by M4H and the programme’s level of success of disseminating these widely to stakeholders. Overall, the programme exceeded all milestones.[4] This was due to the programmes’ success in producing original research and generating new insights, along with strong marketing support to promote publications via social media and other channels.
[4] All figures under Output 3 are cumulative and include numbers achieved from the Strategic Partnership’s Disaster Response Programme, as agreed in the original Logframe.

3.1 – Usage: number of publications downloaded from the GSMA M4D website and physically distributed (content relevant to the partnership) (cumulative)

Reports and case studies by the M4H programme were downloaded or physically distributed a cumulative total of 22,804 times, which exceeded the Year 2 target of 15,000. The top three downloaded reports were all related to Mobile Money: Mobilising cash and voucher assistance programmes: The case for mobile money; Mobile money enabled cash aid delivery: Essential considerations for humanitarian practitioners; and Mobile money enabled cash aid delivery: Operational handbook for mobile money providers. The M4H programme distributed publications (either hard copy or USB) at wider GSMA events including MWC19, m360 Africa in Kigali, and at its Nairobi launch of the Mobile Money CVA handbook for humanitarians and MNOs with 56 attendees, including 5 MNOs from the region and other private sector players like technology service providers.

3.2 – Thought leadership: Number of insights generated, (/ of which some are seminal reports) that influence the industry. (Cumulative)

The M4H programme generated 11 reports, exceeding its target with a cumulative of 30 reports against a target of 27. Three reports have been deemed seminal:
1. Landscaping the digital humanitarian ecosystem report; this report summarises five landscaping studies commissioned by the programme to understand the promise as well as challenges of digital solutions in the humanitarian sector.
2. Bridging the mobile gender gap for refugees report; this report has been particularly well received by programme stakeholders such as UN OCHA.
3. Displaced and Disconnected report; This research is the first of its kind to systematically understand and address the barriers to access among refugees and other displaced persons: legal and regulatory requirements mandating that an individual’s ID is authenticated before accessing a mobile connection, bank account or mobile money wallet.

In addition to the 11 reports, the programme published videos on programme activities, video interviews and launched its podcast series.

The insights published are:
Reports	Other publications
Seminal reports / Landscaping the digital humanitarian ecosystem report / Bridging the mobile gender gap for refugees report / Displaced and Disconnected report / Reports / Mobile for Humanitarian Innovation 2018 Annual Report / Mobile-enabled energy for humanitarian contexts report / Recognising Urban Refugees in Jordan: Opportunities for mobile-enabled identity solutions report / Mobile money enabled cash aid delivery: Operational handbook for mobile money providers / Mobilising cash and voucher assistance programmes: The case for mobile money / Mobile money enabled cash aid delivery: Essential considerations for humanitarian practitioners / Key Trends from Round 2 of the GSMA Mobile for Humanitarian Innovation Fund report / Telesom ZAAD: Pushing the mobile money CVA frontier	Videos / Digital Identity – Video / Mobile-enabled utilities – Video / Mobile financial services – Video / Gender and inclusivity – Video / Food security and climate change – Video / GSMA interview with Ursula Mueller, Assistant Secretary-General of UN OCHA / GSMA interview with Kelly T. Clements, Deputy High Commissioner of UNHCR / Podcast / Mobile for Humanitarian Innovation Podcast – Episode 1: Gender and Inclusivity – Podcast

Finally, the programme has also established research partnerships with CARE International on female cash-transfer beneficiaries and with International Rescue Committee (IRC) on its internal transformation required to transition to private sector led digital solutions in humanitarian assistance.

3.3 – Events: number of convenings with at least 3 different types of stakeholders and whose purpose is to disseminate learnings (cumulative)

The M4H programme organised, hosted and/or participated (speaking on a panel) at 21 convenings during the reporting period. This brought the programme’s cumulative total to 50, exceeding its Year 2 target of 45.

The M4H programme engaged stakeholders and disseminated its insights and messaging at 20 conferences and external events over the reporting period. The events were organised by organisations including Mercy Corps, the Red Cross, UNHCR, World Humanitarian Forum, UNGA and more. Increasingly, the M4H programme has also been invited to deliver specific presentations at three closed door workshops – for example WFP Regional Bureau for Central and East Africa, CaLP. Please refer to Annex E for a full list of convenings hosted or attended by the M4H team during the reporting period.

The programme also engaged stakeholders via GSMA flagship events: MWC19 in Barcelona and the launch of the CVA report series.[5] In attendance were over 60 participants, five MNOs from Kenya and Somalia, CALP and humanitarian attendees, and a panel consisting of technology service provider, MNO, and humanitarian members including CaLP.
[5] This consisted of (1) Mobile money enabled cash aid delivery: Operational handbook for mobile money providers; (2) Mobilising cash and voucher assistance programmes: The case for mobile money; and (3) Mobile money enabled cash aid delivery: Essential considerations for humanitarian practitioners.

Lessons identified this year, and recommendations for the year ahead linked to this output:
- The programme delved deeper into the subject of mobile money cash and voucher assistance (CVA). Understanding the opportunities and barriers around CVA allowed the programme to start responding to its learning agenda, including which mobile/digital services could play the most transformational role in humanitarian contexts, but crucially also to provide the programme the tools to support humanitarian organisations and the private sector to shift from in-kind aid to cash, and from cash to digital payments.
- Extensive end-user research conducted this year with 3,000 refugees (in total) in Bidi Bidi Settlement (Uganda), Kiziba Camp (Rwanda), and Jordan provided insight on how digital solutions may impact end user themselves. The findings of the digital ecosystem study gave the programme first-of-its kind research on refugees’ digital needs and preferences, and identified where the programme needs to work further to fill the research gap and answer the learning agenda questions more specifically.

Recommendations
1. The M4H Insights team should design an approach to ensure the programme addresses all four learning questions[6] by September 2021. [March 2020]
  [6] 1) What is the business case for greater investment in digital humanitarian services for the mobile industry and what sustainable business models and new partnership models will unlock this? What are the biggest barriers? 2) Which mobile/digital services could play the most transformational role in humanitarian contexts – in which type /stage? What is the path to scale? 3) How will increased digital transformation in the humanitarian sector impact end-users and humanitarian organisations themselves? 4) How will the overarching policy environment affect the rollout of digital humanitarian services and how can different actors come together to advocate for more enabling environments?
2. M4H programme will aim to partner with research organisations / think tanks to disseminate research via two webinars. [June 2020]
3. Design and conduct one human centered design research project focused on refugees / IDPs’ experiences or “journeys” in receiving mobile money enabled CVA and their mobile money use. The report should build on learnings from the existing publications through in-depth vulnerable populations’ experiences with mobile money cash and voucher assistance programmes. The report will also make specific recommendations to both MNOs and humanitarian organisations who may be focusing more on the experience of the overall programme versus vulnerable people’s experience with the modality itself (i.e. mobile phone/mobile money). [May 2020]

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year

By September 2021, the Mobile for Humanitarian programme aims to impact at least 7 million people (directly and indirectly) with improved access to and use of life-enhancing mobile services during humanitarian and disaster preparedness, response and recovery context. M4H will work to accelerate the delivery and impact of digital humanitarian assistance using the following five-part model:
1. Build a learning agenda to inform the future of digital humanitarian response: Develop a research agenda to advance knowledge and understanding of where and how mobile can support across the disaster life cycle. Collect and share insights from in-country projects and partnerships to ensure awareness of lessons and critical success factors across the ecosystem.
2. Catalyse partnerships and innovation on new digital humanitarian services: Stimulate innovation (through an Innovation Fund) and facilitate matchmaking and new partnerships (through advisory support) between the mobile industry and humanitarian sector.
3. Advocate for enabling policy environments: Create a targeted narrative to reduce the regulatory barriers that may limit progress of a digital humanitarian future and foster a policy environment that ensures that those who are vulnerable to emergencies do not face additional obstacles to accessing life-enhancing mobile services
4. Monitor and evaluate Design and rollout a Monitoring and Evaluation (M&E) framework, process and tools to assess performance of various work streams on on-going basis. The M&E system will capture the lessons, successes and failures of the programme activities, ensuring that outcomes and impact are monitored on a regular basis.
5. Disseminate insights and profile achievements: Learnings will be disseminated widely throughout the industry in order to build increased understanding of the challenges and the opportunities for increased digitization of humanitarian aid, to highlight early success stories / best practice and to encourage replication. Results of the DFID-GSMA collaboration will be profiled through high-level GSMA platforms such as Mobile World Congress, regional m360s as well as other global events (WEF, UNGA, others) where appropriate.

The Theory of Change for the programme, as presented below, has not changed from the original business case with exception of the impact target increasing from 6 to 7 million beneficiaries.

Figure 1. Mobile for Humanitarian programme Theory of Change
Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead

In the period under review, the M4H programme (through the Disaster Response programme) reached 3,013,703 beneficiaries, resulting in a cumulative total of 4,018,115[7] and exceeding the milestone target of 4 million by June 2019.
[7] Impact are cumulative and include numbers achieved from the Strategic Partnership’s Disaster Response Programme, as agreed in the original Logframe.

Source	Men	Women	Total
Haiti Earthquake, Sunday 7th October 2018 / DPC requested AGERCA to work with Digicel for them to send out 3 SMS messages to the Nord-Ouest, Nord, Nord-Est, le Plateau Central et l’Artibonite areas. These messages were designed to calm the population and inform them on measures to adopt during this situation and especially with the aftershocks. / Digicel accepted to send the message to the targeted areas and 3,013,703 people received the messages.	1,506,851	1,506,852[8]	3,013,703
Total	1,506,851	1,506,852	3,013,703
[8] To calculate the gender disaggregation, the programme looked at the gender gap in Haiti is (5%) and the overall women to men ration in the population.

Impact figures from Round 1 of the Innovation Fund are counted under Strategic Partnerships Disaster Response programme.

Outcome 1: Number of cases where there is evidence that the programme insights have been used by programme stakeholders (cumulative) – Exceeded - 13 achieved, target of 10

Nine key stakeholders have cited and/or endorsed GSMA positions on Mobile for Humanitarian challenges, resulting to a cumulative total of 13 and thus exceeding the programme’s target of 10. These include:
1. Telecoms operators dial in to refugee markets, citing "Mobile is a Lifeline: Research from Nyarugusu Refugee Camp, Tanzania; and Humanitarian Payment Digitisation: Focus on Uganda's Bidi Refugee Settlement"
2. Filippo Grandi: Businesses can help refugees, citing "Mobile is a Lifeline: Research from Nyarugusu Refugee Camp, Tanzania; and Humanitarian Payment Digitisation: Focus on Uganda's Bidi Bidi Refugee Settlement"
3. IFRC World Disasters Report 2018, citing the GSMA reports Enabling Access to Mobile Services for the Forcibly Displaced.
4. Telemedia Online - Editorial article “The ultimate banking of the unbanked: working with refugees in Rwanda”, Citing Humanitarian Payment Digitisation: Focus on Uganda's Bidi Bidi Refugee Settlement
5. UNHCR article: “How to Work With Mobile Network Operators – Lessons from Tanzania”, Citing Mobile is a Lifeline: Research from Nyarugusu Refugee Camp, Tanzania;
6. Urban Institute’s Research Report: High-Tech Humanitarians. Airtel Uganda’s Partnership with DanChurchAid, Citing Humanitarian Payment Digitisation: Focus on Uganda's Bidi Bidi Refugee Settlement
7. UNHCR article: “How to (re)build connection in displacement – Lessons from Uganda”
8. Manila Island article: “Innovation: Key to disaster risk management”, Referencing the HCC’s work.
9. DevEx article: “The SDGs are on the agenda at the world's largest mobile industry event”, Citing Mobile is a Lifeline: Research from Nyarugusu Refugee Camp, Tanzania

Outcome 2: Number of new technological innovations or business models supported through the programme (cumulative) – Exceeded – 15 achieved, target of 8.
In the period under review, the M4H programme has supported nine new technological innovations or business models. This result is coming from the nine grantees of the Mobile for Humanitarian Innovation Fund round 2 shown in Table 1 below.

Table 1 M4H supported innovations
Lead Applicant	Project Title	Implementing Partners	Thematic Focus	Country of Implementation	Grant Amount	Grant Duration	Summary
Danish Refugee Council (DRC)	Mobile Payments for Safe and Sustainable Water in Refugee Settlements	Grundfos Holding A/S	Mobile Enabled Utilities	Uganda	£146,684	18 Months	Introducing a market-based approach to provide sustainable, safe and equitable water to conflict-affected populations using mobile technology.
American Refugee Committee (ARC)	Mwangaza ("Light"): Improving Refugee Access to Clean Energy	BioLite	Mobile Enabled Utilities	Rwanda and Uganda	£300,000	18 Months	The project will provide improved energy access equipment (solar light/charging and fuel efficient cook stoves) to refugees.
United Healthcare Distributors (UHD)	Empowering women in Camps and Off-Grid Communities in West Nile	Medical Teams International, VAC Solar UK Limited, Quality Medicines for all, Aptech PV, Airtel Uganda	Mobile Enabled Utilities	Uganda	£300,000	15 Months	Equipping women to access energy, create sustainable livelihoods and improve their families' health using innovative batteries and mobile phone technology
Norwegian Refugee Council (NRC)	Strengthening Digital Access to Needs-Based Protection Information for IDP Women	Koe Koe Tech, Ministry of Immigration, Labour and Populations, Statelessness Network Asia Pacific (SNAP)	Gender & Inclusivity	Myanmar	£300,000	18 Months	Provision of information on civil documents and Housing, Land and Property rights to displaced women using an existing mobile platform.
International Rescue Committee (IRC)	Protecting Vulnerable Populations	Mercy Corps, Glasswing International	Gender & Inclusivity	El Salvador and Honduras	£300,000	18 months	Providing access to protection information, safe-spaces and case management tools, to increase protection for vulnerable women and the LGBTQ community.
Sesame Workshop	Sesame Seeds: An interactive mobile extension	International Rescue Committee	Gender & Inclusivity	Jordan, Lebanon and potentially Iraq	£300,000	18 Months	Leverage the power of mobile technology and Sesame’s engaging, tested content to improve key socio-emotional outcomes among Syrian refugee families
Naya Jevaan	My beautiful Thar: How Mobile Technology can Reduce Forced Displacement	Engro, Thar Foundation, doctHERS, Telenor	Gender & Inclusivity / Food Security, Adaptation & Resilience to Climate Change	Pakistan	£300,000	15 Months	My Beautiful Thar is a multi-stakeholder collaboration that is focused on using mobile technology to increase the resilience of Tharis
British Red Cross	121 Personal Cash Aid	Kenya Red Cross, Netherlands Red Cross, Safaricom, TYKN, Disberse	Digital Identity	Kenya	£286,870	18 Months	121 connects donors directly to people in need, allowing for inclusive, fast, transparent, low cost humanitarian aid through cash.
Deutsche Welthungerhilfe / e.V	Child Growth Monitor	Action Contre la Faim (ACF) Canada, Fight Hunger Foundation (FHF) India, Bundesministerium für Wirtschaftliche Zusammenarbeit (BMZ), Deutsche Telekom	Food Security, Adaptation & Resilience to Climate Change	India	£300,000	12 Months	A game-changing app to detect malnutrition using augmented reality and AI

Outcome 3: Number of services (including technological innovations and business models) supported by the programme that are replicated in other countries / regions (cumulative) – Did not meet target – 0 achieved, target of 1.

The M4H programme was required to support or influence one service to be replicated in another country or region during the second year of implementation. Whilst the programme has made considerable progress this year in supporting new services, this target has not been met.

The programme has focused on two potential pathways for replication – through the Innovation Fund and its market engagement work stream.

As part of the implementation model of the Innovation Fund, the programme’s market engagement managers make considerable efforts to facilitate introductions and link the grantee with potential partners, as well as help grantees demonstrate the impact of their products or services. Initial signs with at least one grantee from round 1 (Sociotech Institute, also known as Lumkani) shows strong potential for scale that could materialise in the coming year.

Through the programme’s market engagement partnerships, there is also potential to support or influence services to be replicated – particularly as the programme is partnering with large international NGOs. As the partnerships are still at nascent stage, the programme has not yet been able to demonstrate successful pilots to be replicated. These efforts will continue in the coming year and M4H remains confident that it will achieve its target of three services supported or influenced by the programme that are replicated in other countries / regions by June 2020.

Outcome 4: Number of cases where there is evidence that the programme has influenced policy makers, regulators and international influential bodies (e.g. WEF, UN etc.) (cumulative) – Met – 3 achieved, target of 3.

During the period under review, two policy makers, the Ghana National Communications Authority and the Government of Uganda, and one international influential body, UNHCR, have been influenced by the programme, adding to a cumulative of four cases thus exceeding this year’s target. The cases are:
  1. UNHCR: This year the programme operationalised the Advocacy components of the GSMA’s MoU with the UNHCR. The M4H programme influenced the seminal report Displaced and Disconnected which UNHCR have been sharing and citing widely. Through the joint work on the report, the programme has been able to influence the position UNHCR has on the legal and regulatory requirements mandating that an individual’s ID is authenticated before accessing a mobile connection, bank account or mobile money wallet. These points and other key messages have been publicly communicated by Kelly Clements, Assistant Secretary-General UNHCR at WEF in Davos with 4 refugee host-country governments and MWC19.
  2. Technical Working Group (TWG) meeting in Uganda. Considering the identification related policy challenges encountered by humanitarian agencies as part of humanitarian programming in Uganda as a refugee hosting country, the TWG looked at connectivity for refugees at policy, regulation and infrastructure level. The programme joined forces in exploring best approaches to drafting the national ‘connectivity for refugees’ strategy / plan and how to best institutionalise it in Uganda.

Explain major changes to the logframe in the past year

Following the last Annual Review, the M4H programme suggested several changes to the Logframe to align the M4H reporting date to June (instead of September), matching the broader M4D partnership reporting timeframes. These were accepted by DFID on 24th April 2019 and presented below in Table 2.

Table 2. Mobile for Humanitarian Innovation Logframe Changes
Indicator	Changes and Rationale
Milestone dates	Following the Annual Review recommendations, milestone dates have been updated to align with the Strategic Partnership reporting milestones as follows: / Milestone 2: June 2019 (9 months, shortened year to align with SP) / Milestone 3: June 2020 (12 months, aligned with SP) / Target: Oct 2021 (15 months, current end of programme)
IMPACT: Number of people with improved access to and use of mobile services in humanitarian/disaster context, as a result of the activities of GSMA supported through this programme (disaggregated by gender) (cumulative)	Increase targets / In response to high impact numbers recorded thanks to Disaster Response and HCC activities, the programme is recommending to increase the targets from 6,000,000 to 7,000,000 cumulatively, as follows: / M4H YR2 target M4H YR3 target M4H YR4 target M4H YR2 target M4H YR3 target M4H YR4 target / 2,000,000 4,000,000 6,000,000 4,000,000 5,500,000 7,000,000 / Added assumption / To clarify the reporting allocation between Disaster Response and Mobile for Humanitarian, the following definition has been added: DR: HCC activities up to June 18 + Disaster Response Innovation Fund (Round 1) / M4H: All HCC activities, Innovation Fund rounds 2 and 3, Market Engagement and Advocacy activities under M4H
Outcome Indicator 1 - Number of cases where there is evidence that programme insights have been used by programme stakeholders (cumulative)	Increase targets / Increase of insights produced will support the increase in insight usage, therefore the programme is recommending to increase the targets from 15 to 20 cumulatively, as follows: / M4H YR2 target M4H YR3 target M4H YR4 target M4H YR2 target M4H YR3 target M4H YR4 target / 4 8 15 10 15 20
Outcome Indicator 2 - Number of new technological innovations or business models) supported through the programme (cumulative)	Added assumption / To clarify the reporting allocation between Disaster Response and Mobile for Humanitarian, the following definition has been added: The numbers for Outcome indicator 2 include Disaster Response grantees (but not beneficiaries, which are counted only under the Strategic Partnerships)
Outcome Indicator 3 - Number of services (inc. technological innovations and business models) supported by the programme that are replicated in other countries / regions (cumulative)	Amended definition / To align with the Strategic Partnership Logframe, the programme will also count cases where M4H influenced replication: ‘Number of services (inc. technological innovations and business models) supported or influenced by the programme that are replicated in other countries / regions (cumulative)’.
Output Indicator 2.1 - Number of applications received through Innovation Fund rounds (cumulative) (disaggregated by geography)	Increase targets / Increased interest in round 2 meant the programme has already achieved its cumulative targets. Therefore the targets are updated with actual cumulative number of applications (540), with increase in year 3 target to reflect the expected application or round 3. Revised targets are as follows: / M4H YR2 target M4H YR3 target M4H YR4 target M4H YR2 target M4H YR3 target M4H YR4 target / 200 300 300 540 620 620
Output Indicator 2.2	No changes.
Output Indicator 3.1 - Usage: number of publications' downloads from the GSMA M4D website and physical distribution (content relevant to the partnership) (cumulative)	Increase targets / Following the Annual Review recommendations and in response to high usage numbers recorded from Disaster Response publications and the new M4H publications, the programme is recommending to increase the targets from 12,000 to 23,000 cumulatively, as follows: / M4H YR2 target M4H YR3 target M4H YR4 target M4H YR2 target M4H YR3 target M4H YR4 target / 6,000 9,000 12,000 15,000 19,000 23,000
Output Indicator 3.2 - Thought leadership: Number of insights generated (of which some are seminal reports) that influence the industry (cumulative)	Increase targets / Following the Annual Review recommendations and in response to over achievement in year 1, the programme is recommending to increase the targets from 27/5 to 40/6 cumulatively, as follows: / M4H YR2 target M4H YR3 target M4H YR4 target M4H YR2 target M4H YR3 target M4H YR4 target / 17/3 22/4 27/5 27/3 34/5 40/6 / Amended definition / To align with the Strategic Partnerships definitions, the programme is recommending to update the definition of this output to: Thought leadership: publications which demonstrate new insight[9] including reports, blog posts, case studies and videos (cumulative / of which some are seminal reports). / Added footnote / Following the Annual Review recommendations the programme is adding clarification on what constitutes a seminal report: A study is seminal if recognised by the humanitarian community as an important landmark in the field and is widely cited.
Output Indicator 3.3 - Events: number of convenings with at least 3 different types of stakeholders and whose purpose is to disseminate learnings (cumulative)	Increase targets / Following the Annual Review recommendations and in response to over achievement in year 1, the programme is recommending to increase the targets from 55 to 75 cumulatively, as follows: / M4H YR2 target M4H YR3 target M4H YR4 target M4H YR2 target M4H YR3 target M4H YR4 target / 25 40 55 45 60 75
[9] New to Mobile for Development, i.e. messaging not in other M4D publications.

Describe any planned changes to the logframe as a result of this review
- It is recommended that indicator language on the Mobile for Humanitarian Innovation logframe is realigned with the new GSMA Partnership Logframe.
- GSMA to update the current Logframe targets (output and outcome targets) to reflect the overachievement of some targets in year 1 and provide more stretching targets [November 2019]

## D: VALUE FOR MONEY

Assess VfM compared to the proposition in the Business Case, based on the past year

There has been no change from the original value for money (VfM) proposition in the Business Case. The key cost drivers and performance have not changed from the business case – they remain primarily staff salaries and travel costs.

Categories	% of total budget (FY18/19)	Cost Drivers
Personnel	52%	Market value of specialist skills / Fluctuation of GBP value impact on international staff
Research and Insights	21%	Suppliers costs
Meeting and Events	5%	Suppliers costs / Marketing
Travel	8%	Flight and accommodation costs

The table below outlines how M4H is managing the key costs using the DFID 4 E’s framework.

	VfM Measures	Performance in this area
Economy – whether the project has bought inputs of the appropriate quality at the right price?	Procurement: The GSMA is governed by the GSMA Procurement Policy covering all purchasing process, whether as purchasers, negotiators or authorisers; and in all business interactions with suppliers on behalf of the GSMA. / Robust procurement process is in place, which is consistent with international good practice. Specifically, it ensures competition for all procurement over the value of £50,000 and encourages it for lower value transactions / Human resources: The GSMA has strict policies in terms of recruitment, remuneration (based on set market benchmarks) and performance appraisal. In addition, staff are generally recruited in the market / close to the market of programme focus. / Resourcing plan is built at the start of the financial year and aligned with programme future activities. During the year, potential additional resources are subject to robust business case before approval / Travel: Booked in advance and at the cost of economy fare only. The hotel and subsistence rates meet GSMA’s strict travel policy guidelines to ensure best value for money per trip.	Whilst M4H did not issue requests for large procurements (over £50k) in the period under review, it has been able to consistently identify savings through contract negotiations. Overall, the programme has identified £14.5k savings out of a budget of £122k, representing 12% savings. / The GSMA does not use derivative financial instruments to manage foreign exchange risk as the majority of GBP expenditures is funded by GBP grant income and therefore the risk is managed through internal hedging. The GSMA continues to monitor the level of exposure to foreign exchange fluctuations for grants and programme activities
Efficiency – how well the project is converting inputs into outputs? (‘Spending well’)	Input maximisation: cross-collaboration between M4D programmes to mutualise inputs ( suppliers, travels, processes, monitoring and evaluation) and maximise output impact (joint research and joint advocacy) / DFID Profiling: GSMA M4H activities have been able to leverage GSMA flagship events such as Mobile World Congress and the Mobile 360 events and high level platforms (UNGA, WEF) to profile the programme outputs / Monitoring and evaluation: constant improvement of services based on user feedback, business intelligence and monitoring and evaluation feedback. / Strengthened due diligence to mitigate risks that sub-grantees of the Innovation Fund could misuse funds	In order to maximise content synergies, reduce collaboration complexity and save budget, the M4H programme has partnered with other Mobile for Development (M4D) programmes to produce relevant content – including Mobile Money, Utilities, mAgri, Digital Identity and Gender (Connected Women). / M4H Innovation Fund uses the same processes and the same Fund Manager (Coffey) as other M4D programmes, thus increasing efficiency. In addition, GSMA negotiated a 7% reduction in fees with Coffey, resulting in £19.6k savings for M4H round 2 and 3, and £26.3k for Connected Society. / GSMA has developed a risk assessment framework to analyse country wise risk and align the sub-grant pre award due diligence and monitoring processes with the risk / The GSMA has strengthened the M&E component across the M4D programmes, by recruiting additional specialist M&E resources and introducing common M&E frameworks and systems. / The programme keeps costs down by purchasing marketing material from suppliers who offer GSMA corporate discounts and using a combination of paid and organic marketing and promotional techniques.
Effectiveness- how well the outputs produced have had the intended effect/ achieved the outcome? (‘Spending wisely’) / Cost-effectiveness - What is the project’s ultimate impact on poverty reduction, relative to the inputs that we invest in it?	Achievement and overachievements of all targets as set in the agreed Logframe	Indicators achieved. The M4H has met or exceeded all its targets for the period under review. / Strategic partnerships: The expanded partnerships with UNHCR and WFP helps the M4H programme achieve wider impact with no additional costs.
Equity - ensuring that research is inclusive and benefitting the target group	The M4H programme monitors the number of women impacted. In addition, the M4H programme works closely with the Connected Women programme, which has a specific focus on reducing the gender gap on Mobile Internet and Mobile Money.	The M4H programme monitors the number of women impacted. In addition, the M4H programme works closely with the Connected Women programme, which has a specific focus on reducing the gender gap on Mobile Internet and Mobile Money. / The M4H programme published the Bridging the mobile gender gap for refugees report, highlighting the experiences of refugee women (compared to men) with mobile technology in Bidi Bidi settlement in Uganda and Kiziba camp in Rwanda to demonstrate the value of closing the mobile gender gap. / Following the study on how mobile can act as transformative technology for people with disability in emerging markets, the GSMA has formally set up the Assistive Tech programme to drive greater digital inclusion for persons with disabilities through research and insights, innovation funding, partnerships development, advocacy, knowledge sharing and advisory to mobile operators. / In June 2019, the GSMA has adopted the UN Women’s Empowerment Principles as part of its commitment to promoting gender equality and the empowerment of women in the workplace, marketplace and community.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio

The M4H programme continues to represent value for money. Some key elements of this are as follows:
1. Increased programme targets: The programme has increased six of its logframe targets, including increasing the impact target from 6 million to 7 million beneficiaries, with no requests for additional funding.
2. Delivery: The M4H programme saw a significant scale-up of activities this year, as evidenced in section B. The programme has an ambitious pipeline of partnerships in addition to 14 innovation fund grantees and the advocacy and research work completed by the programme.
3. Innovation Fund: The innovation fund process itself is an open, competitive and transparent process, therefore driving value for money.
4. The M4H programme is also part of a portfolio of programmes funded by DFID and is leveraging the knowledge already developed in other M4D programmes.

## E: RISK

Overview of programme risk (noting the rating from p.1) and mitigation

Overall, the risk of the DFID GSMA Foundation Mobile for Humanitarian Innovation programme remains Major due to the operating environment and uncertainty around the role of market-based solutions in the humanitarian context. In the second year of operation, the programme has proved that there is a clear appetite from relevant stakeholders around humanitarian innovation, as seen from the interest in the innovation fund, the 5 signed partnerships and the pipeline of market engagement activities for the coming year. However, the following key risks remain:
- Difficult and rapidly changing contexts for operation, particularly for technology innovation and private sector;
- Extremely early stage of innovation means that the route to sustainable impact is still being established;
- The role of the private sector and the model for partnering with humanitarian actors is still emerging.

The key risks at this stage are shown in the table below and the mitigation actions have been reviewed as per this annual review. ‘↑’ indicates an increased probability or risk, ’↓’ indicates a decreasing probability or risk, and ‘-’ indicates that the level has not changed since programme inception.

Table 2: Risk Management matrix for the Mobile for Humanitarian (M4H) programme
Risks and Description	Probability (H, M, L)	Impact / (H, M, L)	Mitigating Actions
Alignment between humanitarian agencies and MNOs around partnership models	L-	M↓	Facilitation of regular dialogue between stakeholders and host convening opportunities to share best practice / Capacity building and development of tools and FAQ’s for each stakeholder group / Ongoing engagement of the M4H advisory group to steer the programme. The group includes high profile representatives from MNOs, bilateral and multilaterals
Appetite from GSMA members to engage and invest in higher-risk demonstration projects	L↓	M -	Engagement from GSMA members on identification of feasibility criteria for projects
Duplication of efforts to stimulate innovation around use of mobile in humanitarian emergencies	M -	L ↓	Close coordination with other humanitarian innovation funds such as HIF and Grand Challenges Canada and other DFID humanitarian innovation programmes, as needed / Regular engagement with focal points within innovation areas in the humanitarian community / Engagement within the advisory group to ensure clarity on digital strategies of major humanitarian players
Limitations to the ability of GSMA and its staff to engage directly in sanctioned or high-risk markets	M -	H -	Close coordination on due-diligence to ensure transparency on off-limit engagement / Cooperation with locally based implementing partners where required
The applications received and supported, and business models developed do not generate sufficient market demand to meet output and outcome indicator targets	M -	H -	Identifying a range of delivery channels and implementing partners will test multiple innovations in multiple markets before deploying significant resources to formally launch them in a market / M4H will build on the experience to date of the other GSMA Innovation Funds / Using a lean start methodology where appropriate, testing innovations will have some failures and some successes so these risks are intrinsic to this type of project and the channels and scale and spread of funding hedges these risks / Using a phased milestone approach to dispersing funds to implementing partners, ensures performance is closely monitored, limiting the disbursement of funds to channels or partners (innovations) that do not show good potential uptake by consumers and humanitarian actors
Mobile technology and business solutions supported do not directly benefit the refugees, IDPs or those in humanitarian contexts and improve delivery of humanitarian services (i.e. benefits are accrued to middle-income consumers, or do not enable operational efficiencies that will help organisations serve more customers in the near future);	M -	H -	M4H grantees must demonstrate that they are delivering services to refugees or those effected by disasters or humanitarian crisis, to the approval of the fund managers as well as the Independent Fund Panel (on which DFID is represented). / The projects supported to date under the disaster response work stream have successfully demonstrated they are serving refugees or those effected by disasters or humanitarian crisis / The formation of partnerships with established humanitarian actors is ensuring benefits in delivery of disaster preparedness, response and humanitarian assistance to the targeted groups
Market uptake of the recommendations and ideas demonstrated by the disseminated research and innovation support is less than anticipated	M -	M -	Leveraging GSMA M4D programmes, other partnerships (humanitarian agencies and through the Advisory Group) and DFID networks (incl. CHASE and country offices) engage with a range of outreach and media channels. Uptake is a critical measure of the GSMA performance with budget allocated to ensure quality and robustness of evidence, optimising uptake and results
More early stage technologies and business models will have a higher failure rate and the learnings may be less related to the use of mobile if they have not reached that point in the trial.	L -	M -	This risk reflects the early stage of many of the grantees, however it is believed that these innovations and trials have a “high-risk, high- reward” potential. Where possible, connections will be made for grantees to gain more technical expertise, such as in the area of machine-to machine communication and IoT / Strengthened M&E framework has been developed / Documentation and learning will be documented from both successes as well as failures / Strengthened criteria for assessing applications, building on learnings from rounds 1 and 2
Early stage organisations may need more business development support that is beyond the scope of our current programme.	M ↓	M -	This risk reflects the likely early stage of many of the grantees and the fact that this is new area of work for both the private sector and MNOs. Where possible, connections will be made for grantees to gain more technical expertise and business advisory support. In addition, it will build on the experience gained through other innovation funds under utilities and the eco-system accelerator e.g. boot camp for start-ups

## F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial, and financial issues

Delivery against planned timeframe
Compared to the original business case, original Logframe and original budget, the programme has been overall on track. This annual report is the report concluding the first year of implementation for the programme and:

- All output indicators (operator engagement, innovation fund and insights generation / dissemination) have been met or exceeded
- Three out of four outcome indicators have been met or exceeded. The programme is confident it will hit the missing indicator in the next reporting period
- The impact target is on target to reach its 2021 goal of 7 million beneficiaries (direct and indirect)

As underlined in section E (risks), the main risk factors that could derail the delivery against planned timeframe in the future are stakeholder appetite (MNOs and humanitarian organisations) to implement the programme’s initiatives within its timelines, uncertain environments (especially regulatory ones) and delays with sub-grantees projects. As underlined in section E, mitigations are in place for these risks.

Performance of partnership(s)

As the last review of this partnership was only undertaken in September, the M4H partnership has continued from where it left off. It is continuing to build on a strong foundation and draws on the experience of the whole team given its cross-cutting nature. DFID and GSMA have quarterly meetings, supplemented by regular informal meetings and catch-ups between the DFID partnership manager and the M4H team, particularly useful in the run up to the launch of the third round of the innovation fund. M4H team have been proactive in engaging with DFID humanitarian programmes and advisers to ensure coherence and opportunities for collaboration; for example, using the surge funding support available through this programme to partner with DFID experts in developing a solution for using GSM data to track migratory diaspora in the DRC following the Ebola outbreak (implementation still tbc). The performance of the programme and team has been very strong, establishing a solid basis both in terms of building on evidence (landscaping reports), feedback from key stakeholders through the Advisory Board as well as testing the market through the innovation fund, as well as getting a strong and experienced team in place to deliver the programme.

The team has been responsive and flexible and adapted its approach - e.g. in taking a more strategic approach to engagement with UN agencies, focus of the innovation funds. GSMA have also been proactive in managing risks, developing a risk framework and due diligence process for work in fragile and humanitarian environments, which is now being used across the GSMA DFID strategic partnership. They have also been very responsive to requests on safeguarding and further developing internal guidance and controls in this area, liaising also with DFID’s EPIC department on data ethics and privacy concerns. M4H was also presented to MoS Baldwin on her visit to the GSMA in May, with positive feedback received.

The DFID GSMA strategic partnership manager continues to play a critical role in facilitating the partnership and ensuring effective delivery and coherence with DFID humanitarian programming.

Asset monitoring and control
N/A (Round 1 Innovation Fund assets have been captured under the Disaster Response strand of the Strategic Partnership programme)

Date of last narrative financial report(s)	March 2019, / July 2019
Date of last audited annual statement (s)	June 2019

## G: MONITORING, EVIDENCE & LEARNING

Monitoring

As M4H is working with largely untested models (as is the nature of innovation projects) it is important that the programme designs and implements a robust methodology of monitoring, evaluation and continuous learning to ensure the programme is as impactful as possible.

The framework and practices put in place in the last year represent some of the most ambitious MEL activity across GSMA Mobile for Development and has been designed in an attempt to apply methodological rigour and structure to MEL for humanitarian innovation. Based on long-term outcomes of the framework’s implementation it will hopefully encourage the wider sector to follow suit.

M4H MEL operates at three levels: Programmatic (global level); Market engagement and thought leadership (country level); and Innovation fund / Strategic partnerships (project level). The key MEL activities for 2018/19 across all three levels are outlined below:

MEL Partner: In 2018, M4H appointed The Research People (TRP) to be the MEL partner for the programme. They will be responsible for (amongst other tasks): the design of the M4H MEL framework; support implementing required data collection; and conducting the base- and end-line research to evaluate the impact the programme has during its lifecycle.

M4H MEL Framework: This outlines how M4H programme activities will address its learning agenda and sets out a theoretical framework for measurement (with data collection tools). Whilst developing the framework, TRP regularly engaged with M4H staff, grantees, partners and a session with colleagues at DFID. A workshop was also held to ensure those involved understood the programme’s theory of change and were aligned to this. The framework is set up to look at evidence under four categories linked to M4H objectives (Figure 2). The data collection tools were developed to collect three different types of evidence in each of these categories: iterative evidence (informing and updating strategy decisions); evaluative evidence (demonstrating the programme’s value); and storytelling (developing a narrative around programme activities).

Figure 2. Framework evidence categories

Pathways to scaling in M4H: Work to understand the models and modalities for humanitarian innovation (both digital and otherwise) are only just emerging. Scaling mobile humanitarian innovations requires more than an understanding the potential impact of individual projects. Therefore, the M4H approach to pathways to scaling requires clear problem definition, and an analysis of the impact, risks, and wider ecosystem. M4H will take a portfolio approach to assess innovator readiness to scale on four indicators: value generation, difficulties, sustainability and variable contexts. An example of a value generation pathway to scale is provided in image 3.

Figure 3 Maximising value

Baseline report: Alongside the framework, TRP also developed a baseline assessment for M4H based on a systematic review of existing evidence around the programme’s learning agenda questions. The baseline report maps the level of evidence in each area and scores the contribution of the GSMA in developing this. As an example, for M4H learning agenda question four “How will the overarching policy environment affect the rollout of digital humanitarian services and how can different actors come together to advocate for more enabling environments?”, the baseline sets out that there is limited evidence in this space already (four out of five, where one is high) and that GSMA contribution to this evidence is low (Figure 4). When the programme ends in 2021 a similar exercise will be conducted in order to map out the impact the programme has had on sector knowledge. Hence, if in 2021 the endline says that there is now more evidence to answer learning agenda question four, and that GSMA contribution to this is ‘high’ or ‘medium’, then it could be ascertained as a success for the M4H programme. Using the same approach, the report also looks at evidence around business and scaling models for digital humanitarian innovation. Whilst this analysis was conducted after the start of the programme, only evidence that was published/available prior to the commencement of M4H was included in order to work as a genuine baseline. The report will remain internal and the findings will be published with the final end-line report at the end of the programme. The baseline report can be found here.

Figure 4. Baseline report scoring example (learning agenda question four)

M4H Team Training: After the development of the framework, tools and baseline report, training was undertaken to ensure M4H staff understood the purpose and content of the new structure.

1. Project MEL: the programme will continue to conduct MEL across its portfolio of grantees and partnerships:
  1. Theory of Change (TOC) / Log Frames: All projects are encouraged to develop a theory of change (using a MEL Framework tool). For round 3 of the Innovation Fund, all short listed applicants will be required to submit a TOC. Where it makes sense, TOC development will be included in the set-up of future strategic partnerships. All grantees have a log frame as part of their contract to monitor agreed KPIs.
  2. Regular reporting: Grantees provide regular reporting to GSMA based on agreed KPIs. Reporting covers monthly reports, milestone payment reports and quarterly financial reports. The programme is currently working on a template for end of grant reporting which will collect detailed quantitative data on these KPIs (and others) whilst also collecting rich qualitative data around grantee’s impact, innovation and journeys to scaling[10].
    [10] Much of this template is based on qualitative tools designed as part of the overarching M4H MEL Framework.
  3. Ad-hoc: Additional to the regular reporting and approved log frames, all grantees (and most strategic partnerships) are being offered an additional package of funding and technical assistance to commission and deliver a robust third-party led evaluation. Currently two suppliers have been selected for round 1 grantees (REFUNITE and Lumkani) and more are under way (Mercy Corps and Nokia). Similar packages will be offered to all Round 2 grantees in 2019 and to all Round 3 grantees in 2020.

Evidence

There have not been any major changes in evidence that would have implication for the programme, however through the work with external stakeholders this past year it was evident that there were significant knowledge gaps in the sector and that the information for people affected by crises is often non-existent. The insights provided by M4H’s work helped fill in the gap and inform stakeholders’ programmatic and advocacy work. Further, there was need to improve the quality, relevance, and use of data and statistics, which the programme has addressed via its digital ecosystems study. The programme has also learnt that there is significant appetite from stakeholders to engage on digital financial services.

In addition, the programme considers the ‘Leave no one behind’ agenda via different angles:
- Research: M4H has conducted research on the mobile gender gap in refugee contexts, publishing the and Bridging the mobile gender gap for refugees report, which highlights the experiences of refugee women (compared to men) with mobile technology in Bidi Bidi settlement in Uganda and Kiziba camp in Rwanda to demonstrate the value of closing the mobile gender gap. The programme will continue to explore this area in upcoming research including through planned female user journey case studies. In addition, the programme will explore the concept of digital privacy and informed consent.
- Joint activities with the GSMA Connected Women programme: M4H has carried out in-country workshops with programme stakeholders to provide recommendations around digital inclusion for women in humanitarian design and delivery based on the research outlined above. There are currently two active partnerships with a key gender component, and additional partnerships in the pipeline.
- The Innovation Fund is seeking mobile enabled solutions that focus on reducing the gender gap in access to digital humanitarian services and enhance equality and accessibility of assistance for vulnerable segments of the population.

Learning

Building a learning agenda is a core pillar in the M4H programme approach. Whilst the bulk of the learning agenda will be addressed through a combination of the work of the Insights Team (see Insights section of this report) and the evidence collected via the M4H MEL Framework, additional learning around how the programme is improving current practices related to evidence and evaluation will also be produced by TRP in a series of learning papers. The working topic for the first paper, expected to be shared by December 2019, is:
MEL frameworks for system change: paper outlining the M4H MEL framework and how it was designed. It would outline the four portfolios and the success measures for each.

It is important to also highlight how the MEL framework encourages wider collaboration to ‘learn through doing’ and adapt the ways in which the programme is implemented. Some examples of this are:
- Moving to theory of change (TOC): for round three of the Innovation Fund, applicants will submit a TOC (using the self-led TOC development tool from the MEL framework) as opposed to a logframe. This change was made based on the quality of initial logframes, especially at the outcome level, in previous rounds. M4H believe this will lead to higher quality indicators going forward; and
- Regular data collection: as the framework includes numerical trackers for all work streams, it means the programme is moving towards a more regular approach to collecting diverse data which may not previously have been reported.
### Progress on recommendations from previous reviews

FY2019 Annual Review Recommendation	Deliverable and Deadline	Update
M4H will adopt a strategic engagement approach with major humanitarian organisations (UN agencies and IRC), leveraging their current interest in developing organisation wide digital strategies to deepen the collaboration model and opportunity for impact.	GSMA will submit to the Advisory Group an approach on how to develop this area by Mobile World Congress in February 2019	The programme submitted two approaches to leverage the interest of major humanitarian organisations on digital strategies. / Collaborations on the CVA process and where MNOs could provide a solution using mobile technology - This approach led to discussions and and partnerships with UNCDF, WFP and Mercy Corp. / Research work with humanitarian organisations to understand their digital journeys - This approach led to a partnership with IRC to research their digital journey.
M4H will engage private sector stakeholders, especially those within the Advisory Group, to share insights, discuss strategy and identify specific collaboration opportunities. Where workshops with private sector have been held already, they have surfaced clear areas for collaboration and areas to avoid duplication of efforts.	At least 3 engagement opportunities to be scoped for the coming year by 15th January 2019	The programme has established five partnerships during the reporting period. Further information is available in annex C.
The M4H programme will produce a trends analysis of applicants to Round 2 in comparison with round 1, charting the innovation trends in mobile-enabled humanitarian assistance and response. The insight report and learnings from Round 2 will be synthesized to determine focus for Round 3.	Analysis to be completed by February 2019	Key Trends from Round 2 of the GSMA Mobile for Humanitarian Innovation Fund report; / Learning incorporated in Round 3 term sheet: / Maintain focus on forced displacement and complex emergencies / Enhance focus on MNO engagement / opportunities / Maintain thematic focus, but allow for flexibility / Enhance focus on routes to sustainability / Enhance focus on three different ‘categories’ of innovation; 1. Adapt existing mobile enabled solutions, 2. Test and validate new models of service delivery, 3. Scale up solutions with proven potential for impact. / Broaden grant size to between £50,000 - £500,000 to ‘scope’ different requirements of above 3 categories
M4H will distil and synthesise the learnings across the five landscaping reports to produce a comprehensive narrative of the current landscape of mobile services/ interventions/ opportunities in the digital humanitarian ecosystem to publish externally. This will be used to feed into the selection process for round 2 and the full design process for round 3 of the innovation fund, as well as directing the wider programme’s priorities until 2021.	Synthesis to be completed by 1st December 2018	Landscaping report published December 2018:
M4H will continue to work closely with the DFID Humanitarian Research and Innovation Team to ensure alignment with other DFID work on humanitarian innovation e.g. Grand Challenges and recently approved Humanitarian Innovation Business Case, in particular on areas such as utilities, digital identity, information services and cash transfers. The DFID GSMA strategic partnership manager will lead this.		Ongoing with two focused partners: GCC and WFP. A brief summary of how M4H has been collaborating with GCC is below: / During set up of Humanitarian Grand Challenges Round 1, GSMA M4H shared learnings and best practises on application process and scope / In June 2018 GSMA M4H hosted Humanitarian Grand Challenges, ELHRA, StartNetwork and DFID in a workshop entitled ‘Funding Humanitarian Innovation; Opportunities and Challenges’ to ensure shared learnings and collective problem solving – summary attached / GSMA M4H and Grand Challenges worked together to signpost strong candidates to respective funding opportunities where relevant, and encourage other Humanitarian Innovation funders to do the same / The M4H Fund team frequently engages with projects referred to them by Grand Challenges and vice versa / In Autumn 2018, Olly was a reviewer and Fund panellist in the Grand Challenges selection process within the connectivity and information category / In January GSMA M4H hosted Chris Houston in London to provide update on Round 1 & 2 Key Trends report / In February Grand Challenges was one of the key organisations to contribute in scoping calls around the focus of GSMA M4H Round 3 / In April, Olly contributed as an expert to the Grand Challenges report on ‘Barriers Affecting Innovations in Humanitarian Contexts’ with a focus on connectivity / Finally Grand Challenges have been very supportive in promoting the GSMA M4H Round 3 including facilitating a number of webinars this month in which GSMA M4H, Grand Challenges and ELHRA have and will discuss current funding opportunities / WFP: / Attended Innovation Accelerator ‘Pitch Night’ / Participated in WFP Humanitarian Hackathon
It is recommended that the reporting timeline of the M4H programme is aligned with the GSMA Mobile for Development Strategic Partnership reporting period (reporting in July of each year) to increase efficiencies in reporting.[[1]] This will shorten the next annual report period and logframe targets will need to be adjusted to reflect the 10-month reporting period. Additionally: / GSMA to update the current Logframe targets to reflect the overachievement of some targets in year 1 and provide more stretching targets; / GSMA and DFID to agree on beneficiary definition when it relates to national solutions supported through the Innovation Fund or systems such as Early Warning Systems, with support from the GSMA M&E lead and aligning to the approach used in the M4D programme.	Revised Logframe to be submitted to DFID by 20st December 2018	Revised Logframe approved by DFID on 24 April 2019
[[1]] This year a one month extension to the Annual Review deadline was approved to align with data collection activities, which helped provide the most up-to date results for the programme.

## ANNEXES TO BE INCLUDED WITH ANNUAL REPORT

1. Logframe
2. Advisory Group Vision and Mission
3. Partnership Briefs
4. Innovation Fund Round 2: Portfolio summary
5. M4H Logframe Evidence
6. Downstream Partner mapping
7. Financials
8. M4H NCE_Final