Title: Mobile for Humanitarian Innovation (M4H)
Programme Value £ (full life): £31 million (15.5 million Phase 1, 15.5 million Phase 2)	Review date: June 2025
Programme Code: 300446	AMP start date: / September 2017	AMP end date: / March 2027

Summary of Programme Performance
Year	2018	2019	2020	2021	2022	2023	2024
Overall Output Score	A+	A+	A+	A+	A+	A+	A+
Risk Rating	Major	Major	Major	Major	Major	Major	Major

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/33097787.odt
DevTracker Link to results framework:	Pending

A. SUMMARY AND OVERVIEW

Description of programme

The partnership between the Foreign, Commonwealth & Development Office (FCDO) and the GSMA’s Mobile for Humanitarian Innovation (M4H) programme is in its second phase (M4H 2.0). The programme works to accelerate the delivery and impact of digital humanitarian assistance by building a learning and research agenda to inform the future of digital humanitarian response; catalysing partnerships and innovation for new digital humanitarian services; and advocating for enabling policy environments.

Since the programme’s inception in 2017, the digital humanitarian landscape has shifted dramatically. Connectivity now allows crisis-affected populations to access information, connect with loved ones, and receive vital humanitarian assistance. Digital technology has changed the way people in crisis receive life-saving information and services, from digital cash programming to dissemination of early warning messages in advance of disasters. Furthermore, the scale of the humanitarian challenge is immense, with over 400 million people currently in need of assistance, and over 120 million of those forcibly displaced. The track record and credibility of the programme demonstrates a significant shift from its earlier years, when public-private partnerships and digital innovation were met with scepticism in the field of humanitarian action. It is now widely accepted that no one industry or stakeholder group can solve this challenge alone and the private sector, including mobile network operators (MNOs), is increasingly recognised as playing a vital role in emergency response.

Not only has M4H been a catalyst for this fundamental shift, its crucial role in digital humanitarian innovation is demonstrated by the leadership roles it has taken up in global humanitarian initiatives and its investment in, and support to, humanitarian solutions at scale. This annual review draws on these fundamental shifts and is centred on three themes across the programme’s delivery:

- Humanitarian Innovation: Digital solutions supported through the Innovation Fund and broader market engagement work are addressing humanitarian challenges at scale with evidence and learning shared across the humanitarian sector and mobile industry.
- Early Warning Systems: A longstanding priority of M4H, the programme was selected to play a leadership role in the UN Secretary General’s Early Warnings for All Initiative, contributing to the goal of everyone on earth being protected by an early warning system.
- Digital and Financial Inclusion for displaced communities: Based on a foundation of evidence, thought leadership, funding, and partnerships, M4H founded the Connectivity for Refugees Initiative with UNHCR and the International Telecommunication Union with an ambition of connecting 20 million refugees and the communities that host them by 2030.
Under these three strategic themes, M4H is singularly positioned to continue to enable the efficient and inclusive digital transformation in humanitarian action in partnership with the humanitarian sector and the mobile ecosystem, continuing to leverage innovation, partnerships and thought leadership to address the growing humanitarian challenge.

To realise an ambition of humanitarian impact at scale, M4H continues to prioritise diversification of its donor partners. Three new funding streams are a considerable added value to the FCDO’s investment and are providing a catalyst to the scale the programme is now delivering.

- Signed a £600k+ programme with Sida as part of M4D’s new partnership agreement
- Successfully pitched internally for a £400k+ investment from GSMA to support the programme’s early warning systems strategy.
- Delivering the humanitarian aspect of the Digital Finance for All initiative in partnership with Visa, a 10% piece of the broader 5-year partnership with other M4D programmes until 2029

Figure 1. EW4All overview

Figure 2. Connectivity for Refugees overview
Summary supporting narrative for the overall score in this review

This year’s Annual Review scores an A+ in recognition of the achievements set out in this review.

The programme exceeded all output, outcome and impact targets demonstrating its ability to deliver influence and impact on a global scale. The programme also is on track to reach its stretch impact target of twenty-two million people (directly and indirectly) in 2027.

Key achievements and highlights from this reporting period include:

- The programme continued to build on its strong track record of delivering impact, with over 5.5 million people reached with improved access to and use of mobile innovations and services in humanitarian contexts. This is the largest impact number in a reporting period in M4H’s history, demonstrating the programme is now delivering at scale, and brings the cumulative impact number of over 18 million people reached.
- £3.5m of additional funding has been raised by Innovation Fund grantees, bringing the cumulative total raised to nearly £4.4m (£2.5m private financing and £1.9m public). Three concurrent Innovation Fund rounds have continued to iterate and build on learnings, refining types of organisations targeted and tailored approaches to support humanitarian innovation at scale, leveraging the broader GSMA M4D innovation fund offer.
- M4H has been recognised as a crucial and leading player in the development and implementation of early warning systems including through the Early Warnings for All Initiative (EW4All). Impact from earlier investments is now being realised such as the replication of Sri Lanka’s DEWN system in Haiti. M4H’s approach on early warning systems is now in demand in multiple markets, with current activities across regions positioning the programme for significant impact in the coming years.
- As a leading partner in the EW4All and Connectivity for Refugees (CFR), M4H research is in high demand by broader audiences from field-based humanitarians to senior government, UN and private sector representatives. The programme is responding to increased demand for its research and evidence by refining its learning agenda, including technical publications, and expanding dissemination efforts across new and varied networks.

Major lessons and recommendations for the year ahead

Lesson-learnt	Recommendation
Partnership and Market Engagement
M4H has learned there is no “one size fits all” approach for early warning systems development and has refined its early warning systems offer based on national contexts and MNO, humanitarian and government partners. Approaches include long-term engagement, ecosystem coordination, end user and market assessment, “demo-ing” success and identification of industry champions. The early warning systems strategy will be reviewed through the programme’s MEL in the coming year. / M4H’s previous approach was to host a regional Humanitarian Connectivity Charter workshop to build relationships and then identify one country to start activities at the national level. While it has worked in bigger regions such as Asia or Africa (Pakistan and Madagascar were identified as focus markets following regional workshops), for smaller regions such as the Pacific, engagement has shown that an important first step is identifying a relationship with a regional stakeholder (in this case, the Pacific Islands Telecommunication Association) to identify a first national pilot that can be showcased to regional stakeholders in partnership with said regional body.	Provide early warning systems interventions in multiple markets where M4H is well placed to deliver, identifying appropriate interventions and strategies. Some of M4H’s key entry points include having buy-in from MNOs, gaps in expertise where M4H can support (interest in cell broadcast/location-based SMS), requests from national/regional partners and/or where M4H grantees are delivering EWS solutions. A diversified global engagement plan – supported by GSMA’s additional investments to broaden the geographical scope to on-LMICs – should deliver significant impact and scale in the coming years. (March 2026) / Replicate the Pacific model in the Southern Africa region by building trust and partnership with CRASA (the regional body for regulators) and then identify a priority market where M4H can progress development of a national EWS, showcasing this at a regional meeting. (February 2026)
Innovation Fund
Choosing a round “focus” that aligns with global humanitarian policy priorities opens opportunities for grantees. For example, early warning systems are high on the agenda of many global stakeholders including governments, UN agencies, humanitarian organisations and the private sector. This focussed interest in early warning leaves M4H grantees well placed to capitalise by forming new partnerships and receive further funding to grow and adapt their solutions.	Better leverage M4H and GSMA’s growing network in the EW4All Initiative to identify grantee opportunities at the national level; at GSMA and other EW4All events; with EW4All stakeholders and donors; and through promotion via GSMA channels (Ongoing for R5, R7, R8)
Thought Leadership and Influence
Data on connectivity to support mobile-enabled early warning systems in affected countries is not comprehensive, hindering activities to build inclusive systems and is a research gap that M4H can help to address. / Consultations with partners on the responsible use of innovative data sources in humanitarian action demonstrates a significant interest in greater M4H engagement and thought leadership on this topic, leveraging its unique position, particularly around the use of mobile big data (eg Call Detail Records, mobile money, location data), for example in tracking and responding to population displacement.	Adapt the existing GSMA CoNUA tool to support connectivity assessments to plan effective mobile-enabled early warning systems. (Mar 2026) / Develop and implement a research and engagement strategy on mobile big data in humanitarian action based on consultations with key humanitarian and industry interlocutors. (Dec 2025)

Status updates for recommendations from last year’s annual review are included in Annex A.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case

The theory of change for M4H 2.0 remains relevant in this reporting year.
The four main pathways to change continue to align with the programme’s workstreams, namely:
- Innovation: Deployment of sustainable innovative digital products and services
- Partnerships: Formation of mutually beneficial partnerships
- Policy: Improved policy and regulatory decision making
- Evidence: Use and adoption of informative, useful research and evidence

Figure 1. M4H 2.0 Theory of Change

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Impact target
M4H has made significant progress this reporting period, reaching an additional 5.5 million people (48% female) with improved access to mobile services in humanitarian settings. This brings the total impact to 18.1 million people, exceeding its 16.7 million stretch target for the reporting period.

The largest proportion – 77% (4.3 million) people – were reached through strategic partnership projects, such as M4H’s support to Digicel and Haiti’s Directorate of Civil Protection (DPC) to improve Haiti’s disaster resilience. In 2018, M4H initiated a project to replicate Sri Lanka’s Disaster and Emergency Warning Network (DEWN) mobile-based early warning system by building partnerships and buy-in with all relevant stakeholders including the National Telecommunication Council (CONATEL), the DPC, and the Emergency Telecommunications Cluster. Over seven years and despite political and security challenges, M4H continuously coordinated with and provided technical support to Digicel Haiti, other MNOs and the DPC. As a result, in August 2024, the DEWN system sent a test message through the Digicel SMS centre, with the system now live for the DPC to alert communities of an impending crisis.

Grantee projects under the GSMA Innovation Fund for Anticipatory Humanitarian Action reached close to 1.3 million people (23% of those reached in this reporting period) at grantees’ project closure. One grantee, ActionAid Cambodia, enhanced the existing “1294” Early Warning System in Cambodia by installing 12 new real-time groundwater level sensors and upgrading 20 across 11 provinces. These upgrades improved the speed and accuracy of alerts for disasters such as droughts and floods. Over 208,000 users are now registered to the platform, including 106,000 women. ActionAid Cambodia launched a widespread public information campaign through radio (12 shows) and social media, reaching over 700,000 people with early warning messaging and disaster preparedness actions and information.

A further breakdown of M4H beneficiaries is provided below:

Figure 3: Summary of beneficiaries reached (cumulative):

Number of beneficiaries

Outcome targets
The programme exceeded all five of its outcome targets during the reporting period. A summary of each outcome is provided below:

Outcome Indicator	Milestone target	Progress
Outcome 1: Number of cases where there is evidence that the programme insights have been used by programme stakeholders (cumulative)	23	Exceeded: 45 (+22)
Outcome 2: Number of new technological innovations or business models supported through the programme (cumulative)	14	Exceeded: 19 (+10)
Outcome 3: Number of services (including technological innovations and business models) supported or influenced by the programme that are replicated in other countries / regions (cumulative)	4	Exceeded: 6 (+4)
Outcome 4: Number of cases where there is evidence that the programme has influenced policy makers, regulators and international influential bodies (e.g. WEF, UN etc.) (cumulative)	4	Exceeded: 7 (+3)
Outcome 5: Scale: Amount of additional funding (£) mobilised for the services trialled through the innovation fund & strategic partnership projects (cumulative, discounted for GSMA contribution)	£2,000,000	Exceeded: / £4,371,669 / (+£3,503,932)

The annual milestone target for outcome 1 (influence) was exceeded with twenty-two new cases where M4H’s insights have been used and cited by stakeholders. Publications on language inclusion, inclusive risk communication and the ways in which displaced people utilise mobile phones have been used to inform programming by UN agencies, including within EW4All and CFR, and in academic circles.
Outcome 2 (innovation) target was also exceeded, with ten new technological innovations or business models supported by the programme through the GSMA Innovation Fund for Humanitarian Challenges:

Box 1: GSMA Innovation Fund for Humanitarian Challenges
Company of Innovative Solutions and Networks Research Pvt Ltd (CIS), Pakistan / CIS’ Aquacare project is installing IoT-based water filtration and bacterial testing units in vulnerable, flood-prone regions of Khyber Pakhtunkhwa and Punjab in Pakistan. This will minimise community exposure to contaminated water, thereby reducing the risk of waterborne disease outbreaks.
ConnectHear, Pakistan / ConnectHear is introducing AI technology tailored for at-risk individuals with hearing impairments, enabling online sign language interpretation and AI-generated sign language alerts, ensuring vital communication during crises to target disaster-prone areas.
Drop Access Limited, Kenya / Drop Access is scaling their cold chain VacciBox solution in humanitarian settlements in Turkana County, on a Cooling as a Service (CaaS) model to private and public health facilities. Health facilities will affordably access reliable cold chain equipment (hardware) and the VacciBox IoT platform (software), enabling them to store and transport vaccines and medications to remote and off-grid locations.
Exuus, Rwanda / The SAVE Score project is using alternative data driven credit scores powered by machine learning to increase access to micro-loans to unbanked refugees in informal saving groups by fintechs or informal financial service providers.
Helium Health by One Global Medical Technology Ltd, Nigeria / The HeliumDoc platform provides remote consultations and secure access to health records in Nigeria’s flood-prone regions. The platform is undergoing enhancement by integrating it with geospatial mapping, USSD functionality and robocall alerts.
Patapia, Uganda / Patapia is expanding its operations to provide micro-loans to refugees living in Rwamwanja and Kyaka II refugee settlements in Uganda. This includes providing capacity building to refugees on business planning and financial literacy. In addition, they will redesign the USSD interphase of their digital banking solution to ensure availability in Swahili language, for ease of use by the refugees.
RAAGSAN, Somalia / RAAGSAN is empowering Beledweyne communities with tailored, near real-time water and climate risk information. RAAGSAN is training primary data providers and gauge readers from the government in digitising their manual river and rainfall measurements through SMS/WhatsApp. The data collected will be integrated with existing hydromet data from NASA’s surface water and ocean topography (SWOT) data. Warnings and guidance information will be relayed to communities using the Daadihiye Citizen Engagement platform via SMS, radios and community workshops.
SmartWTI, Jordan / The “Blue Future for Schools” project is installing a water management solution in up to 40 schools based in Jordan’s refugee-hosting communities. It is utilising AI/IoT technology to enable monitoring and control of water usage in real-time allowing schools to detect and act if any potential leak occurs, avoiding the misuse and loss of water.
SOMLENG, Laos / The project is developing the Open-EWS platform, a customisable, open-source early warning system with multi-use warning, broadcast, and commercial capabilities. The project will expand its early warning system use case in southern Laos, which is prone to sudden onset disasters, most notably floods. The SOMLENG platform will be a Digital Public Good and will also have a payment module directly tied to economic incentives for early warning system maintenance and communication by the communities and caretakers.
Viamo Pakistan, Pakistan / Viamo is launching “Noor” Pakistan’s first voice-first offline Generative AI Voice Companion for disaster preparedness and response. Noor delivers lifesaving, localized disaster information in Urdu directly to basic mobile phones without the need for internet connectivity or a smartphone. Viamo’s Voice Companion will use AI to gather disaster management content in line with national curriculum of disaster management publicly available via Provincial Disaster Management Authority and National Disaster Management Authority. It is hosted on the existing Viamo Platform (toll-free nationwide SBC hotline) with MNO, Ufone.

Box 2: M4H cross-programme leverage of AI for disaster response / As artificial intelligence (AI) becomes an increasingly vital tool in humanitarian action, M4H is integrating it into solutions, services and approaches across the programme. AI offers new ways to detect hazards assess risks, delivery timely alerts, increase the effectiveness of early warning systems, improve connectivity in crisis zones, and support inclusive, tech-driven solutions for vulnerable communities. Examples in the reporting period include: / Three Innovation Fund grantees in the Innovation Fund for Humanitarian Challenges are using AI to serve disaster affected communities as evidenced in Box 1. ConnectHear is leveraging AI to bridge communication gaps for Persons with Disabilities, ensuring disaster risk information is communicated in sign-language to individuals with hearing impairments. Viamo is using Generative AI to deliver localised disaster information in Urdu to basic mobile phones, without the need for internet connectivity or a smartphone, reaching last mile communities. Smart WTI is using AI in refugee hosting schools to avoid misuse a loss of water, which is a very scarce resource in Jordan. / Disaster Connectivity Maps / DCM is a joint initiative by the International Telecommunication Union (ITU), the Emergency Telecommunications Cluster (ETC), and the M4H programme. The three organisations meet regularly to assess requests to activate the DCM for new emergencies as well as new opportunities for partners to leverage the DCM on the ground. The GSMA providers mobile operator contacts, technical support on the evolution of the tool and promotes the DCM through its networks and at GSMA events. This geospatial platform identifies where populations lack access to mobile early warning systems due to limited or no network coverage. It also assesses telecom infrastructure before and after disasters using real-time data from mobile and fixed networks, satellite imagery, and AI. By intersecting population density with network coverage, DCM identifies “coldspots” where high population density coincides with poor connectivity. It supports emergency responders by visualizing historical and near real-time connectivity to guide alert dissemination strategies. DCM has been deployed in over 50 disasters globally, including the December 2024 earthquake in Vanuatu and the March 2025 Myanmar/Thailand earthquake. / EW4All AI Sub-Group / M4H is a member of the AI Sub-Group that sits under Pillar 3 of the Early Warnings for All Initiative. The group looks at AI for hazard detection, risk assessment, and timely alert dissemination, while also helping shape global standards for responsible AI use in disaster risk reduction. M4H brings mobile industry expertise, highlights Innovation Fund grantees using AI and promotes mobile networks as critical infrastructure for early warning dissemination, especially in underserved and remote areas. For example, GSMA’s partners from WWF and Lahore University of Management Sciences (LUMS) presented their solution to the AI Sub-Group that used AI in forest fire detection in Pakistan. This opportunity helped connect WWF and LUMS to other partners in the Sub-Group to progress a pilot integration of the solution into a provincial alert system.

Outcome 3 (replication) target was also exceeded, with four technological innovations supported or influenced by the programme that were replicated in other countries.

- Replicating Sri Lanka’s DEWN system in Haiti (see summary of impact target on page 5).
- Synnefa replicated the grant-funded FarmCloud solution from Kenya to Rwanda, equipping Rwandan farmers with a custom Farmshield basic setup and integrating satellite imagery into Synnefa’s farm management platform. The solution is designed to help clients monitor essential nutrients in real-time, ensuring optimal soil health and boosting crop productivity. Further plans to provide the solution in Uganda are underway. This grant falls under the pillar of M4H’s strategy that aims to address food insecurity, a growing humanitarian challenge.
- Naxa’s Digital and Spatial Technologies for Anticipatory Action (DASTAA) grant-funded platform successfully replicated in two new markets, Democratic Republic of Congo and Bangladesh. See replication success story in box 3 for further information.
- SmartWTI has replicated its grant-funded project in Jordan that supports schools in refugee-hosting communities. The pilot project in Cote d’Ivoire aims to enhance energy and water efficiency in public buildings by deploying smart monitoring and control systems. This followed an introduction to the government by Orange Africa and will lead to deployment of their solution in a hundred government buildings if the pilot is successful. In addition, they have replicated the grant-funded project to Egypt for an agriculture use case; in partnership with the Agricultural Engineering Department, Zagazig University. This project focuses on implementing smart water management solutions using IoT and AI technologies in pivot irrigation systems for silage corn cultivation. The objective is to reduce water consumption and improve crop yields through data-driven decision-making.

Box 3: Replication success story: NAXA / GSMA, through the GSMA Innovation Fund on Anticipatory Action round provided a grant to NAXA, to enhance a disaster management platform, ‘DASTAA’ which strengthens humanitarian anticipatory efforts with accurate early warning communication and distribution of anticipatory humanitarian cash assistance to disaster affected communities in Nepal. During the grant period, DASTAA expanded from Nepal to Bangladesh and the DRC. In Bangladesh, DASTAA was piloted through the Asian Disaster Preparedness Centre’s iCARE Innovation Fund project via a grant of $240,000 which concluded successfully in January 2025. In the DRC, DASTAA is currently being piloted under the Twilio.org Climate Tech Prize project via a grant of $200,000 which commenced in February 2025. The expansion was driven by growing demand for anticipatory action tools, especially in flood, landslide, heatwave and drought prone areas where early warnings and anticipatory humanitarian assistance can significantly reduce economic losses and save lives.

Outcome 4 (policy influence) target was also exceeded, with three new cases of the programme influencing international bodies, policymakers and regulators on the issue of early warning systems. This includes influence of disaster management policies of UN Member States, research agendas of EW4All Pillar leads ITU and IFRC, and operational delivery of UN agencies and regional bodies in the Caribbean.

For the first time, M4H carried out policy engagement with ITU member states on ICT for disaster preparedness, including early warning systems. M4H submitted a joint paper to the ITU Development Sector Study Group with the ETC. The ITU meeting where M4H was invited to present the paper in Geneva in May 2025 was well attended by country delegations. Content from the M4H/ETC joint paper was incorporated into the final ITU report. M4H’s contribution in the final report of the 4-year study cycle will inform future thinking in ITU and Member States on the question of ICT for disaster preparedness and relief.

M4H’s research approaches and outcomes have influenced the research agenda of both ITU and the International Federation of Red Cross and Red Crescent Societies (IFRC). Following the launch of the M4H report on enhancing inclusion in mobile-enabled risk communications, ITU approached M4H with a request to replicate the study in multiple markets (Bangladesh, Haiti, Mozambique, Somalia, and Liberia) as part of their work in the EW4All Initiative. M4H did not have the capacity to lead on replication of the study in multiple markets, so ITU and IFRC moved forward with replicating M4H’s research methodology, with M4H acting as a key advisor.

The programme’s engagement in the Caribbean has enhanced emergency telecommunications policy and operational delivery. M4H’s investment in a regional Humanitarian Connectivity Charter (HCC) convening in November 2023 kicked off new engagements for the ETC in the region and has influenced regional actors such as the World Food Programme (WFP) and Caribbean Disaster Emergency Management Agency (CDEMA). The ETC reported to M4H that the initial convening built significant trust with the WFP country office and CDEMA, leading to increased regional operational collaboration and delivery between these partners and the ETC. As a result, ETC invested in a full-time Caribbean resource who M4H is now working directly with on the development of Dominica’s NETP.

The target for Outcome 5 (scale) was exceeded with £3.5m in additional funding raised by Innovation Fund grantees during the reporting period to bring the cumulative total to nearly £4.4m (£2.5m private financing and £1.9m public financing). At the closure of the GSMA Innovation Fund for Anticipatory Humanitarian Action, five grantees, Naxa, People in Need, Rumsan, Synnefa and Trans-African Hydro-Meteorological Observatory (TAHMO), had secured £3.3m, demonstrating the successful deployment of their solutions. In addition, two GSMA Innovation Fund for Humanitarian Challenges grantees, Drop Access and Patapia, currently implementing in Kenya and Uganda have raised £258k.

Figure 4: Additional funding raised in 2024 and 2025

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
The programme has consistently performed well across all metrics, with this reporting period marking its most impactful year to date. It is effectively demonstrating new partnership models, along with scalable and innovative tools, approaches, and business models that address global humanitarian challenges. The M4H 2.0 partnership was established with ambitious stretch targets, which continue to be met and exceeded, thanks to the programme’s increasingly scalable model.

Early investments are now yielding positive results, such as the foundational and sustained investment in supporting Haiti's early warning system, which became operational during this reporting period. M4H activities currently underway in supporting multiple countries' early warning systems position the programme to deliver significant impact for millions of people in the coming years.

Three rounds of Innovation Funding are showing promising metrics and scale potential. GSMA’s leadership in two global humanitarian initiatives enhances the programme's ability to expand its partnerships, evidence base, innovations, and technical support, thereby increasing its impact. This includes support for operational humanitarian delivery, such as the Connectivity for Refugees Initiative with UNHCR.

## C. DETAILED OUTPUT SCORING

Output Title	Governments, private sector and humanitarian organisations actively engage with GSMA M4H to implement programme activities.
Output number:	1	Output Score:	A+
Impact weighting (%):	50%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of cases where the programme has engaged with programme stakeholders (excluding policy makers) to disseminate learning and improve humanitarian delivery (cumulative)	38	Exceeded: 53 (+17)
1.2 Number of cases where the programme has engaged with policy/regulatory/influential bodies to disseminate learning and improve humanitarian delivery (cumulative)	8	Exceeded: 23 (+14)
1.3 Number of measurable action plans / partnerships agreed through GSMA convening or influence between programme stakeholders (MNOs, humanitarian organisations, donors, NGOs, private sector) to improve humanitarian delivery	10	Exceeded:18 (+9)

Briefly describe the output’s activities and provide supporting narrative for the score.

M4H exceeded its annual milestone target for output 1. M4H collaborated with humanitarian partners and MNOs in seventeen cases to improve the delivery and impact of digital humanitarian assistance (Output 1.1). Additionally, the programme engaged with policy and influential bodies in fourteen cases (Output 1.2) to share insights. The programme facilitated nine new partnerships and/or action plans between stakeholders to improve humanitarian delivery (Output 1.3). Examples of such partnerships are as follows:

Box 5: Partnerships and technical assistance for mobile-enabled early warning systems / Tanzania / M4H is leading the development of Tanzania’s early warning system, beginning by convening a national early warning systems forum and conducting a human-centred design user experience study in partnership with the Tanzania Red Cross Society. The study focused on how users in rural communities perceive early warning systems and risk communications. Based on the research findings, M4H convened all five Tanzanian MNOs, local and international organisations, the Prime Minister’s office, the regulator and the disaster management agency for a cell broadcast readiness workshop. This was a first step towards a national early warning system blueprint, with the engagement resulting in the formation of an MNO steering committee that will support the work. ITU and EW4All partners are now deploying their resources to build on this foundational work. M4H is starting replication of this approach in Nepal and Madagascar. / Pakistan / In December 2024, M4H convened a national workshop under the principles of the GSMA Humanitarian Connectivity Charter (HCC) in Pakistan, bringing together operators, humanitarian and government stakeholders to discuss emergency telecommunications and the role of digital technology. A key gap identified was the lack of standard operating procedures for emergency alerting. In response, M4H is now leading on the development of an automated early warning system messaging tool in Pakistan in collaboration with MNOs and other partners. M4H has signed a partnership agreement with Jazz Pakistan to facilitate the adoption and implementation of a Common Alerting Protocol (CAP) compliant mobile-enabled early warning system. The Government of Pakistan are looking to integrate the technology of Somleng, a grantee from the Humanitarian Challenges round. Somleng is an open-source platform designed to support the dissemination of messaging (SMS/Voice). Somleng technology is already being used in Cambodia, supporting the dissemination of flood and drought early warning messages on all three major MNO networks. This responds to the Pakistan stakeholders identifying that there is no systematic operation or standardisation of EWS message dissemination.

Box 6: New partnerships for innovation and influence / Nepal: In August 2024, M4H hosted the first national-level humanitarian positioning workshop in Nepal, bringing together government, donors, MNOs, fintech partners, humanitarian agencies and other innovators to map out opportunities for digital humanitarian solutions. One key outcome was a partnership between M4H and eSewa, a leading fintech and former GSMA Innovation Fund grantee. Working with WFP, Care, and the Nepal Red Cross Society, M4H developed a financial literacy and disaster preparedness training programme for eSewa’s mobile money agents which trained over 23,000 agents, reaching more than 116,000 people in areas prone to climate-related sudden onset crisis such as floods and landslides. / World Bank refugee engagement: M4H strengthened its relationship with the World Bank in the reporting period. For example, M4H advised the World Bank regional connectivity team in East Africa to inform inclusion of displaced populations in planned connectivity investments in Sudan, South Sudan, Ethiopia, and Somalia, under the auspices of the Connectivity for Refugees initiative with UNHCR and ITU. This engagement fed into approval by the World Bank Board of an innovative $76.3m investment in connectivity and energy in Sudan. / ASEAN NET Plan influence: Building on its longstanding expertise in National Emergency Telecommunication Plans (NETPs), M4H contributed to the ASEAN Emergency Telecommunication Network Master Plan through a dedicated high-level meeting in March 2025, with the aim of supporting better emergency planning among ASEAN members states and the regional ASEAN Coordinating Centre for Humanitarian Assistance on Disaster Management (AHA Centre).

Describe any changes to this output during the past year, and any planned changes as a result of this review.

N/A

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

Recommendation (AR 2024)	Progress
Consolidate M4H tools and technical assistance approaches into assets that can be implemented by partners with less M4H engagement. This will help to meet partner demand at scale and stimulate the replication of mobile-enabled humanitarian innovations and services in multiple markets. [March 2025]	Completed: M4H has developed the Humanitarian Positioning Solutions Platform, an internal facing/invite only tool that provides a robust set of technical assets, templates and guidance that provide concrete steps for running a humanitarian positioning process with MNOs and humanitarian organisations. The platform enables M4H to scale the positioning efforts in new markets and empower partners to play an active role in delivering this process. This year the tools will be tested through deployment in DRC, Ethiopia, Uganda, Mozambique and South Sudan. Examples of the partners engaged include Equity Bank and UNICEF in DRC, Vodacom, WFP and OCHA in South Sudan and WFP and Concern Worldwide in Somaliland.
Host HCC convenings to meet demand, and where possible do so in coalition – as the programme did in the Caribbean with ITU and WFP. Identify markets for engagement where there is a unique value add for M4H and a gap from other stakeholders. For example, in Tanzania and Pakistan – both MNOs and humanitarian agencies have specifically asked for support on early warning systems. As these are not priority countries of the EW4All, they are good locations in which M4H can take a lead. [March 2025]	Achieved and Ongoing: The programme has convened the mobile industry, humanitarian partners and governments in Tanzania and Pakistan that have led to technical support for early warning system development. The Pacific Islands has been identified as a region of opportunity with significant progress made through M4H’s leadership on development of the cell broadcast system in the Solomon Islands. The HCC Pacific workshop will take place at the end of July 2025 and will sensitise and train regional stakeholders on the cell broadcast solution. M4H has invited ITU and WFP to partner during the workshop by bringing their specific expertise and training offers.
Build engagement with partners and networks in the Pacific so that resource and engagement by the programme is impactful, complementary, and welcomed by local partners. This should include engagement with PITA, CANTO, the ETC Pacific focal point, and governments – particularly the National Disaster Management Authorities. Activities should include presenting on the HCC and early warning systems (at events such as at the annual PITA meeting); following up with the Digicel CEOs in the Caribbean in partnership with ITU on implementing early warning systems; and including a Caribbean and/or Pacific country in M4H’s upcoming MNO study on early warning systems that will demonstrate MNO engagement and best practice. [June 2025]	Completed: Successfully built partnerships with CANTO and PITA that have led to trusted relationships with the senior leadership of both organisations. / In the Caribbean, the CANTO relationship has opened doors with MNOs, regulators and governments in the region. Research and market engagement opportunities are being followed up for FY25/26. In the Pacific, the Solomon Islands was the pilot country. M4H partnered with PITA to gain buy-in from the MNO “Our Telecom”, the government and other stakeholders. M4H brought on board a technical partner, Omnitouch, and consultants. Months of work culminated in a demo of the cell broadcast solution at the PITA AGM in the Solomon Islands in April 2025. This built significant interest from other regional players, with the Cook Islands, Samoa and Kiribati interested to integrate the same solution into their markets. / With PITA’s support, M4H will conduct a regional workshop in Fiji in July 2025 and work towards a nationwide test of the Solomon Islands early warning system.

Lessons Learned:
- There is no “one size fits all” approach for early warning systems development and has refined its early warning systems offer based on national contexts and MNO, humanitarian and government partners. These approaches will be assessed in the coming year under the current MEL strategy and include:
  - Long term sustained engagement, such as in in Haiti over seven years to replicate the DEWN system in a country experiencing multiple disasters and political unrest.
  - Improving ecosystem coordination in countries where the right players are not yet working together, such as in Pakistan and Tanzania
  - Assessing end users and the current market to determine the right partners and interventions, such as in Madagascar
  - Finding industry champions to co-lead implementation, such as with the Pacific Islands Telecoms Association in the Solomon Islands
- The Pacific Islands engagement has demonstrated how identifying a pilot country in a specific region and then “demo-ing” progress to regional stakeholder can fast-track replication opportunities. M4H did this for the first time in the Solomon Islands at the AGM of the Pacific Islands Telecoms Association, leading to a surge in interest from other stakeholders and countries in the region such as the Cook Islands, Samoa, and Kiribati.

Recommendations:
- Continue to diversify the EWS engagement plan, including a mix of both national and regional interventions and different levels of engagement, ie: light touch support, single activity engagement, and leadership on EWS development. A diversified global engagement plan should deliver significant impact and scale in the coming years. (March 2026)
- Replicate the Pacific model in the Caribbean, Southern Africa and/or ASEAN by building trust and partnership with relevant regional bodies (CANTO, CRASA, ASEAN) and then by identifying one priority market where M4H can progress relatively quickly to carry out pilot and ideally technical demo at in-person meeting with regional stakeholders. One regional replication of a cell broadcast alert to be completed with government, regulatory, humanitarian and mobile industry stakeholders present. (One regional replication by February 2026)
- Incorporate early warning systems module into GSMA Capacity Building course for regulators, develop landscaping on regulatory aspects of early warning systems to inform more targeted support to governments and industry. (January 2026)

Output Title	Technological innovations and business models selected and funded by the Innovation Fund
Output number:	2	Output Score:	A+
Impact weighting (%):	30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of applications received through Innovation Fund rounds (cumulative) (disaggregated by geography)	570	Exceeded: 572 / (+16)
2.2 Number of grantees of the Innovation Fund (disaggregated by geography) (cumulative)	19	No change - 19
2.3 Percentage of grantees which have a plan for sustainability at grant close	75%	Exceeded: 100% / (100%)

Briefly describe the output’s activities and provide supporting narrative for the score.

In the reporting period, the programme closed grantee projects from the GSMA Innovation Fund for Anticipatory Humanitarian Action, which focused on delivering solutions which anticipate potential humanitarian impacts and enable effective early response, including early warning systems. At grant closure in March 2025, all eight grantees had plans to scale based on end of grant scalability interviews. Some highlights from these projects include:

Box 7: Naxa’s Anticipatory Action contributes to zero human causalities in Kanchanpur, Nepal / A significant achievement for the NAXA project occurred during a cloudburst on July 7th in Kanchanpur, Nepal. Despite severe flooding and damages estimated at NPR 1.5 billion, anticipatory actions taken through the project played a vital role in reducing the impact on communities. These efforts included the dissemination of over 30,000 IVR early warning messages and the provision of cash voucher assistance to more than 900 households in advance of the event. The floods affected around 66,000 people and the 900 households (that make up approximately 4900 people) were previously identified through NAXA’s system as the most vulnerable. NAXA’s partnership with DanChurch Aid who deliver humanitarian cash assistance enabled the delivery of this assistance to the most vulnerable in advance of the flood, enabling them to evacuate, purchase vital supplies and find temporary accommodation.

Box 8: Impactful Mobile Network Operator Partnership: People in Need (PIN) and SMART Philippines / GSMA facilitated a partnership between People in Need (PIN) and Smart Communications, a leading MNO in the Philippines, to improve the delivery of early warning messages. Partnering with an MNO was indeed crucial for PIN to create a real-time SMS alert system and ensure a wide and reliable reach of alerts across vulnerable communities. During the grant period, this system sent over 55,000 timely early warning messages to vulnerable communities, helping them better prepare for and respond to floods. M4H’S ‘Mobile solutions for flood-prone communities’ video explores how mobile-enabled solutions from Naxa, People in Need and TAHMO help vulnerable communities prepare before disaster strikes, to address flood risk and contribute to the ambition of the UN’s Early Warnings for All initiative.

In November 2024, eleven grantees have started their projects as part of the GSMA Innovation Fund for Humanitarian Challenges. This cohort of start-ups and SMEs are deploying innovations that address a range of humanitarian challenges. In-person ‘bootcamps’ took place in Nairobi in February 2025 for six Africa-based grantees and Singapore in May 2025 for five Asia-based grantees. Over the two-day bootcamps, grantees take part in learning and capacity building sessions on grant management and compliance, have an opportunity to pitch to MNOs, investors and donors from their focus region, and build networks with other grantees. Bootcamps also provide an opportunity for the M4H team to learn more about grantee projects and aspirations, leading to tailored market engagement support plans. Bootcamps also provide the chance to receive candid feedback from grantees, leading to continual iteration of the GSMA IF offer. An example of recent achievements by grantees includes the launch of ConnectHear’s AI for Inclusive Disaster Response service in March 2025. In partnership with HANDS and Ufone, this service leverages ConnectHear’s AI technology and virtual interpretation platform, enabling hearing impaired people in Pakistan to have access to life-saving information and communication during emergencies.

The third and final round of innovation funding under M4H 2.0, the GSMA Innovation Fund for Humanitarian Replication and Scale was initiated in March 2025 targeting GSMA Innovation Fund alumni to scale digital humanitarian impact in existing markets or through replication in new markets. Sixteen grantee alumni expressed interest and twelve were shortlisted, with applicants now currently in proposal phase, with panel selection planned for September 2025.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

N/A

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

All recommendations from the previous Annual Review have been completed.

Recommendation (AR 2024)	Progress
Continue to leverage the broader GSMA Innovation Fund network for humanitarian grantees, for both current and future cohorts including through bootcamps to provide important networking and learning opportunities. Hold regional focused bootcamps in Africa and Asia-Pacific, making them more relevant for grantees and supporting them to build networks and attract investors in their own regions. [December 2024]	Completed: Successfully hosted regional bootcamps in Jakarta in July 2024, Nairobi in February 2025 and Singapore in May 2025. Splitting into regional focussed bootcamps ensured that grantees were able to network and meet with more regionally appropriate investors and funders. This also meant that the team was able to deliver more regionally relevant content during the bootcamp sessions.
Refine the GSMA offer to grantees, balancing cohort-wide engagement and tailored support. Continue to build the strategy for the final round of innovation funding under M4H 2.0 that will offer grant funding and/or technical expertise. The round will focus on scale and replication and be open to previous M4H grantees and relevant M4D grantee alumni. Consultation with alumni and needs assessments will help to shape the offering. [December 2024]	Completed: Alongside portfolio engagement, tailored support has been introduced in the form of funded technical assistance for each grantee, focussing on an area of their choice to support the growth of their project. The GSMA Innovation Fund for Humanitarian Replication and Scale was launched in March 2025, open to GSMA alumni grantees only.

Lessons Learned:
- M4H aspires to maintain strong connections with its alumni to support their paths to scale with network building, technical advice and profile at events. The programme has not kept up with this ambition due to capacity and competing priorities. Launching a scale round has demonstrated the interest of alumni in continued funding and engagement with the GSMA, highlighting to the programme that the alumni engagement work needs to be prioritised and sustained.
- Choosing a round “focus” that aligns with global humanitarian policy priorities opens opportunities for grantees. For example, early warning systems are high on the agenda of many global stakeholders including governments, UN agencies, humanitarian organisations and the private sector. This focussed interest in early warning leaves M4H grantees well placed to capitalise by forming new partnerships and receive further funding to grow and adapt their solutions.
- Analysis on primary technologies shows that, alongside mobile apps, Frontier Tech/Artificial Intelligence (AI) led the way, with over 50% of applicants stating that AI made up part of their solution. AI is playing an increasingly important role in the humanitarian innovation space, with startups and SMEs now beginning to harness technology towards positive impacts in local communities, working alongside the more traditional humanitarian actors such as NGOs. The use of AI in the applications ranged from speeding up and improving once manual ’back-office’ processes to developing more sophisticated user-facing chatbots and virtual assistants.

Recommendations:
- The M4H programme has received significant interest from grantees in its scaling round for alumni, with the cohort due to be selected in September 2025. Given the high interest in receiving post grant engagement and scaling funding, it is important to build and maintain strong working relationships with alumni grantees in case of future scaling rounds. This puts further emphasis on the alumni engagement work which has received less attention due to capacity constraints. Re-establish regular check ins, invitations to appropriate events, continuation of introductions to appropriate partners and making alumni aware of new funding opportunities. (June 2026)
- Better leverage M4H and GSMA’s growing network in the Early Warnings for All Initiative by identifying grantee opportunities such as links to stakeholders focused on EWS national and regional development, through promotion with networks developed in the EW4All Initiative (Pillar 3 and High-Level Advisory Panel), through promotion of GSMA social media channels that are increasingly reaching EWS focused audiences, and through M4H EWS reports and thought leadership. (Ongoing for R5, R7, R8)
- As the use of technology in humanitarian action is changing, the programme needs to harvest important evidence on the approaches, successes and challenges these new approaches and their use in humanitarian contexts. Learning from this round of grantees, the programme should develop expertise and publish learnings on these Frontier Tech and AI approaches (December 2026)

Output Title	Research, insights and learning generated and disseminated to stakeholders by the programme
Output number:	3	Output Score:	A+
Impact weighting (%):	20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Thought leadership: publications which demonstrate new insight including reports, and case studies (cumulative).	12	Exceeded: 14 / (+4)
3.2 Dissemination: Number of cases where GSMA messages are disseminated at regional and international high-level platforms (excluding GSMA events)	25	Exceeded: 34 / (+13)

Briefly describe the output’s activities and provide supporting narrative for the score.

M4H exceeded both targets, which are focused on the programme’s research and learning activities. The programme published four thought leadership pieces and disseminated messaging at thirteen regional and/or international high-level forums. M4H focused on high quality research that resonates with key stakeholders, including early warning systems, inclusive digital innovation and public-private partnership approaches. The programme played a crucial role in building the evidence base for the design of UNHCR country activities, as part of the Connectivity for Refugees Initiative. The team focused its dissemination efforts by strategically targeting events and briefings to amplify impact and engagement at a combination of inter-governmental (ITU), technical (ETC) and high-level events (ADB Annual General Meeting) that aligned with M4H and humanitarian priority themes.

Below are highlights of thought leadership with a full list included in Annex C.

Box 9: Making Early Warnings Work for All: People Centred Design
This report offers a practical roadmap for engaging communities and applying human-centred design (HCD) research methods in designing people centred early warning systems. It shares insights from South Africa and Tanzania to illustrate some of the key principles these methods revealed for designing responsive, user friendly and contextually appropriate early warning systems solutions as well as methods and HCD tools for conducting similar research. Through such approaches, early warning stakeholders can develop systems that are not only technically sound but also socially meaningful, ultimately saving lives and enhancing climate resilience.

Box 10: India's SACHET Public Warning System: A Case Study in Mobile Alering
This report on India’s SACHET Public Warning System responds to growing demand by a variety of stakeholders for technical case studies of existing systems . Timely and effective early warning systems t (EWS) are critical for reducing the risks of disasters and saving lives. With 96% of the global population now covered by a mobile network, mobile-based EWS have become a vital tool for disseminating alerts at scale. However, the effectiveness of these systems depends on their design, deployment and operational efficiency. This report presents a case study of India’s SACHET public warning system – a valuable model for other countries seeking to enhance their public alerting capabilities. SACHET is designed to provide fast, reliable

Box 11: The GSMA Humanitarian Positioning Strategy: A Catalytic Approach to Cross-Sector Partnerships in Support of Humanitarian Assistance
The GSMA Humanitarian Positioning Strategy report explores the outcomes and impact of four M4H-supported strategies with Econet in Burundi, Safaricom in Kenya, Telesom in Somaliland and Airtel in Uganda. The report highlights how these strategies have enabled these four MNOs to engage with over 60 humanitarian partners and co-develop more than 30 innovative, mobile-enabled humanitarian projects. It also explores the motivations and benefits for MNOs in taking a more proactive role in working with the humanitarian sector – demonstrating how the mobile industry can play a powerful role in supporting communities in crisis. The report builds on foundations of the 2023 Humanitarian Partnership Framework outlining the programme’s approach to supporting cross-sector collaboration. A crucial first step in this process is the Humanitarian Positioning Strategy – a structured approach of working with mobile network operators to develop strategies for creating and expanding partnerships with local humanitarian organisations.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

N/A

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

Recommendation (AR 2024)	Progress
Build M4H’s strength through its new voice on Connectivity in Crisis. This has opened new partnerships including with the International Committee of the Red Cross. It has also led to new research initiatives, such as mapping the humanitarian coverage gap. The humanitarian coverage gap research is unique to M4H and should be built further to establish the programme as the leading voice on this evidence and approach. [November 2024]	Ongoing: M4H has pursued a focused approach to engage with key partners on Connectivity in Crisis such as the World Bank on Sudan and UNHCR on the Connectivity for Refugees initiative. As a trusted interlocutor with ICRC, M4H was invited as an observer at the International Conference of Red Cross and Red Crescent Societies in November 2024 where a resolution was passed on ICT. / The humanitarian coverage gap methodology and Connectivity Needs and Usage Assessment (CoNUA) toolkit developed by M4H have been incorporated into UNHCR’s operational planning as the Connectivity for Refugees initiative is implemented in Ethiopia, South Sudan, Iraq and Chad. M4H’s new partnership with Sida, launched in April 2025, will provide further resource to this area of work.
Leverage M4H’s increased influence and leadership in global humanitarian initiatives to advance its thought leadership. The programme should tailor research and policy initiatives based on identified gaps in these global coalitions. For example, the EW4All Initiative has a key focus on inclusion, also a priority for M4H. Research on inclusion and early warning is so far lacking and will therefore make an important contribution to the initiative, position M4H as a thought leader, and ultimately contribute to the development of inclusive early warning systems. [March 2025]	Ongoing: M4H’s publications and engagement in EW4All and the Risk Informed Early Action Partnership (REAP) at leadership and working level have solidified M4H influence on the development of inclusive early warning systems based on evidence and strong partnerships with governments and humanitarian and development stakeholders. Work to profile industry leadership in early warning systems will further develop this influence. / As a founding member of the Connectivity for Refugees initiative, M4H is influencing international and country-level planning on how to incorporate displaced people into planning for improving connectivity.

Lessons Learned:
- Partnership with UN agencies on EW4All and Connectivity for Refugees has increased M4H’s impact. However, projects that have operational dependency on UN agencies has slowed progress of M4H delivery and risked missing targets and programme spend. The programme is adapting its approach on joint projects to minimise dependency so that M4H can deliver spend and impact as planned within its financial year. In addition, M4H has developed additional ways to partner, including offering foundational research for UNHCR’s operational delivery and helping to strengthen their relationships with MNOs, leading to concrete operational plans.
- Data on connectivity to support mobile-enabled early warning systems in affected countries is not comprehensive, hindering activities to build inclusive systems and is a research gap that M4H can help to address.
- M4H is often approached for expertise on the use of mobile big data for humanitarian action which remains a gap in the programme’s expertise and delivery. The significant interest in greater M4H engagement and thought leadership on this topic has led the programme take steps to build this expertise and plan a research output in the coming year.

Recommendations:
- In the global coalitions such as EW4All and CFR, the programme should balance building partnerships that have a high dependency with other coalition partners; versus research projects that can be implemented somewhat independently that still contribute to the initiative’s aims. This approach will be incorporated into CFR-focused activities e.g. CoNUA assessment, that will be implemented with Sida funding in FY25/26. (March 26)
- Adapt the existing GSMA CoNUA tool to support connectivity assessments in order to plan effective mobile-enabled early warning systems. (March 2026)
- Develop and implement a research and engagement strategy on mobile big data for humanitarian action based on consultations with key humanitarian and industry interlocutors. (Dec 2025)

D: VALUE FOR MONEY

Key cost drivers and performance

Key Costs	% Total Budget / (Apr 2024-Mar 2025)	Cost Drivers
Innovation Fund	59%	Grantee payments; staff costs; Fund Manager costs; travel
Market Engagement	13%	Travel; staff costs; event costs
Monitoring & Evaluation	5%	External consultancy; staff costs
Analyse and Advocacy	23%	External consultancy; staff costs; travel; marketing (publication) costs

VfM performance compared to the original VfM proposition in the business case.

The original value for money as set in the business case (cost of £2.53 per person with improved access to and use of humanitarian assistance and services) has been exceeded. Based on the current impact numbers and expenditure for the reporting period, the cost per person is now £1.50, demonstrating that the M4H programme is highly cost-effective.

In summary, the VfM proposition set out in the Business Case remains valid, with the below table illustrating the M4H Programme’s continued delivery of strong value for money.

	VfM examples
Economy	Procurement: The programme continues to employ robust procurement processes such as open and competitive procurement processes to get the best price-quality ratio. The programme has sourced local suppliers in Ethiopia, Nepal, Somalia, Tanzania and the Pacific Islands, hence reducing logistical and international staffing costs. M4H always negotiates with prospective suppliers to ensure VfM. During the reporting period, M4H negotiated savings of £135k from market engagement, innovation fund and research supplier contracts. / The programme keeps costs down by purchasing marketing material from suppliers who offer GSMA corporate discounts and using a combination of paid and organic marketing and promotional techniques.
Efficiency	Digital tools: M4H has developed the Humanitarian Positioning Solutions Hub which has enabled the programme to leverage digital tools to serve MNO and humanitarian partners, reducing the amount of hands-on support needed by the M4H programme. This has streamlined the process where partners can deliver a humanitarian positioning process with lighter touch M4H engagement enabling scale and replication of the programme’s approach. / Streamlined processes: Innovation Fund uses same processes, tools and Fund Manager (Mannion Daniels) as GSMA Innovation Fund rounds, thus increasing efficiency. / Coordination with partners: M4H has coordinated with partners such as ETC, PITA, CANTO and ITU, when holding HCC convenings to provide participants with comprehensive approaches for early warning systems development. This collaboration avoids duplication and provides opportunity to share costs, technical resources and expertise across partners. / Monitoring and evaluation: constant improvement of services based on user feedback, business intelligence and monitoring and evaluation feedback. / Strengthened due diligence to mitigate risks that sub-grantees of the Innovation Fund could misuse funds. GSMA has developed a risk assessment framework to analyse country-wide risk and align the sub-grant pre-award due diligence and monitoring processes with the level of risk.
Effectiveness	Follow-on funding for Innovation Fund grantees: In addition, £3.7m raised in follow-on funding by GSMA Innovation Fund for Anticipatory Humanitarian Action grantees, with 2.4 times the amount disbursed of £1.5m for this cohort. / Reflecting successful industry engagement, the programme secured a £400k investment from the GSMA (calendar year 2025) to scale its work on early warning systems in the Pacific and carry out research on best practice of systems in Europe and Japan that can be used to develop effective systems in LMICs.
Equity	M4H recognises that the effectiveness of an early warning system is not just about the technology or the number of people it reaches, it is about its ability to drive meaningful action at the community level. To ensure early warning systems are trusted, understood, and acted upon, they must be designed with the lived experiences, preferences and challenges of communities in mind. It is for this reason that M4H conducted research and produced a report offering a practical roadmap for engaging marginalised communities and applying human-centred design (HCD) research methods in designing people centred early warning systems. It shares insights from South Africa and Tanzania to illustrate some of the key principles these methods revealed for designing responsive, user friendly and contextually appropriate early warning solutions as well as methods and HCD tools for conducting similar research.

E: RISK

Overview of risk management

The overall risk of the M4H programme remains as major, unchanged from last year. This is due to the operating environment on which M4H work is focused. The risk matrix is attached in annex D, with the top risks being:

- Operational risk - Moderate (no change): The M4H programme faces moderate risks of security issues or conflict that could restrict access and threaten staff, partners, and delivery. To address this, thorough risk assessments are done during project planning, with mitigation strategies updated as needed. Travel follows GSMA guidelines, excludes extreme-risk or sanctioned locations, and uses ISOS vetting for high-risk areas. The programme works with trusted local partners for research and monitoring, and suppliers must contractually uphold duty of care.
- Partner capacity/delivery risk – Minor (no change): Regular meetings are held with the delivery partner to closely monitor performance and address any risks in a timely manner. This allows the FCDO to shape the direction of programme components as needed. Additionally, delivery partners are required to have strong governance and management arrangements in place, along with proven expertise and track records in delivering ambitious outcomes. They work with leading sector experts, and country offices to ensure effective programme delivery.
- Management risk – Moderate (no change): The risk regarding operational complexity associated with onboarding new projects and partners remains moderate. It is important to continue to closely monitor the onboarding process to guarantee that the strategic objectives of Mobile for Development remain in line with those of the funding partners.
- Strategic & Operational – Major (change): The anticipated reduction in the UK Aid budget from FY26/27 onwards will necessitate ongoing discussions with GSMA to address the future strategic direction and priorities of the Partnership.
- Safeguarding risk – Moderate (no change): Implementing partner not adhering to FCDO safeguarding guidelines, which could lead to issues that need to be monitored and addressed to ensure the safety and well-being of beneficiaries. The FCDO continue to advise and build up GSMA expertise, so they are equipped to monitor for any safeguarding issues and raise awareness of any concerns to the M4D programme team.

GSMA continually monitors risk. The FCDO programme team and GSMA meet on a quarterly basis to formally review the programme’s progress and jointly agree actions for the upcoming quarter. This includes a discussion on risks and finances. In case of urgent issues, these are escalated to FCDO immediately.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
M4H Disbursed Cash	Year 1 / FY 19/20	Year 2 / FY 20/21	Year 3 / FY 21/22	Year 4 / FY 22/23	Year 5 / FY 23/24	Year 6 / FY 24/25
1.0	£4,197,868	£3,786,638	£2,504,865	£2,285,101	£889,694	N/A
2.0				£60,682	£2,055,662	£3,976,631

The programme has an approved budget of £31 million (£15.5 million for Phase 1 and £15.5 million for Phase 2), with £19.76 million disbursed as of March 2025. Financial performance is jointly monitored by FCDO and GSMA, ensuring adherence to the FY 2024/25 budget, which closed with a variance of just 3%.

GSMA demonstrates strong financial management, including accurate forecasting, asset tracking, and quarterly reporting of underspend to FCDO, enabling joint decisions on fund reallocation. Since 2013, GSMA has consistently submitted timely narrative reports, and annual audits by BDO have been clean for twelve consecutive years.

FCDO continues to view the partnership as transparent, responsive, and grounded in mutual trust. GSMA has remained flexible and timely in responding to evolving budget requirements and FCDO requests.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

M&E is led by GSMA’s internal team, with support from external partners as needed. External suppliers are engaged for specific tasks such as field data collection - for example, during the evaluation of Innovation Fund Round 6 grantees - or to establish baselines for new programme phases.
Where relevant, the M&E team also collaborates with MEL functions across other TIU programmes to share best practices and lessons learned.

Date of last narrative financial report		Date of last audited annual statement

Annexes
- Annex A: Update on recommendations from last year
- Annex B: M4H Logframe
- Annex C: M4H Logframe evidence
- Annex D: M4H Financial report
- Annex E: M4H Full risk matrix
- Annex F: Downstream partner mapping

Annex A: Update on recommendations from last year

Recommendation (AR2024)	Progress
Thought Leadership and Influence
Digital humanitarian action is now much higher up the humanitarian agenda since M4H’s inception with the creation in recent years of the Refugee Connectivity and Early Warnings for All Initiatives being specific examples. Therefore, the programme must align its thought leadership focus areas to these priorities, to maximise the impact and influencing opportunities. [March 2025] / In line with M4H’s research direction on Connectivity in Crisis, the programme will build a new coalition of partners on this topic. An example being collaboration with the International Committee of the Red Cross with M4H bringing a holistic framework and industry perspective, and ICRC bringing an international humanitarian law perspective. M4H will attend the RCRC International Conference as an observer for the first time in November this year. [November 2024]	Completed. M4H has pursued a focused approach to engage with key partners on Connectivity in Crisis such as the World Bank on Sudan and UNHCR on the CFR initiative. As a trusted interlocutor with ICRC, M4H was invited as an observer to engage at the International Red Cross and Red Crescent conference where a resolution was passed on ICT. / The humanitarian coverage gap methodology and CoNUA toolkit developed by M4H have been incorporated into CFR operational planning as the initiative is implemented in Ethiopia, South Sudan, Iraq and Chad.
Partnership and Market Engagement
Build on the foundational re-investment in the HCC during the reporting period. The three regional workshops held by M4H have opened national level opportunities that will lead to disaster management approaches that include telecoms, including early warning systems. The programme should focus on national level priorities to deliver specific outcomes and increase impact. [February 2025] / Further build engagement in the Caribbean and the Pacific through national and regional organisations such as PITA and CANTO. Engaging with and through these organisations will lead to better impact and acceptance of M4H’s activities in the region. [June 2025] / Consolidate M4H tools and technical assistance approaches into assets that can be implemented by partners with less M4H engagement. This will help to meet partner demand at scale and stimulate the replication of mobile-enabled humanitarian innovations and services in multiple markets. [March 2025]	Completed. HCC workshops have now been tailored to address specific needs of the stakeholders which M4H and its partner organisations can support. The HCC workshop for the Pacific Islands in 2025 will be providing capacity building for key stakeholders who are implementing cell broadcast-based early warning systems in the region. The HCC workshop planned for Ecuador will focus on the national priorities and progress made and look at supporting MNOs to play a stronger role in this process. / With this close partnership with PITA and CANTO, M4H created inroads into setting up stronger projects supporting their specific capabilities of the region. The regional cell broadcast based early warning system for the Pacific has received strong buy-in from regional stakeholders enabling it to be now replicated in 4 pacific islands. This was featured in the PITA website, showing the value they see in this approach. / The Humanitarian Solution Platform has been launched which is being tested in new markets such as DRC, South Sudan and Ethiopia, enabling the replication of M4H’s approach to be more efficient and focused.
Innovation Fund
Strategically refine M4H’s offer to grantees based on learnings from all funding rounds to date. Develop a scaling round that has a tailored approach of grant funding and technical assistance using a built-in needs assessment that will inform M4H’s offering. [December 2024] / Against the backdrop of a difficult financing landscape, continue to support grantees and alumni by sharing funding opportunities, increasing exposure through GSMA events, profiling solutions through marketing, and facilitating contacts at the country level and through GSMA organised bootcamps. Leverage the broader M4D network including through bootcamps and to promote opportunities for alumni. [February 2025] / Deepen the programme’s partnerships with other humanitarian innovation teams, sharing learnings and building complimentary approaches. Work together to ensure the pool of innovators are matched and directed to the Funds best suited to them. [June 2025]	Completed. Innovation Fund for Humanitarian Replication and Scale (R8) launched in March 2025. 16 grantees expressed interest with 12 applications shortlisted. Projects will be chosen at a fund panel in September 2025 with expectation for projects to begin in November 2025. / Multiple funding opportunities have been shared with grantees, including WFP, UNHCR, Mastercard and Internet Society Foundation. Grantees have been invited to attend and present at GSMA events, notably GSMA HCC convenings (Philippines, Pakistan) as well as other high-profile meetings such as ITU meetings. / There has been continued engagement with other humanitarian innovation programmes, notably Creating Hope in Conflict, Elhra, Innovation Norway and Response Innovation Lab. The team has contributed to several research papers and meetings, strengthening profile and visibility for grantees in the sector. Grantees have also had exposure to high profile events led by other innovators, notably the Humanitarian Innovation Forum led by ELRHA, where two grantees NAXA and Synnefa attended, sat on panels and presented their solutions at the event.