## Annual Review Template

Title: Girls’ Education South Sudan Programme Phase 2 (GESS2)
Programme Value £ (full life): £70m UK funds		Review date: 31st October covering April 2024 to March 2025
Programme Code: 300449	AMP start date: 29 March 2018	AMP end date: 30 September 2025

Summary of Programme Performance
Year	2018	2019	2020	2021	2022	2023	2024	2025
Overall Output Score	C	A	A	A	A	A	A	A
Risk Rating	Major	Major	Major	Major	Major	Major	Major	Major

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300449/documents
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0005930.xlsx

A. Summary and Overview

Description of programme.

Girls’ Education South Sudan Phase II (GESS2) is the largest education programme in South Sudan, tackling systemic barriers to education through a comprehensive, inclusive, and sustainable approach. The programme is designed to promote equity and access for all learners, especially girls and children with disabilities.

Over 7 years, the Girls’ Education South Sudan (GESS2) programme has evolved from expanding access to improving equity and sustainability. Initially focused on solely on cash transfers for girls, capitation grants, and community mobilisation, it has increasingly emphasised learning outcomes, system strengthening, and data-driven decision-making and in the last two years included children (girls and boys in recipient school years). The programme has oscillated between emergency response in early years to building resilience, integrating conflict sensitivity and inclusion for children with disabilities.

Partnerships with the Ministry of General Education and Instruction deepened through the expansion of the Education Management Information System (EMIS) and School Attendance Monitoring System (SAMS). GESS2 has also broadened engagement with communities through media communications and radio programming, promoting social norms change and ensuring national ownership for long-term education reform. The ambition of the programme while improving equity was to increase Government ownership of education programming and strengthen systems including teacher training mechanisms and data management.

During this review period (April 2024 – March 2025), GESS2 achieved notable progress in several key areas:
- Expanded Disability Inclusion – Strengthening support mechanisms for learners with disabilities.
- Enhanced Behaviour Change Strategies – Deepening community engagement and advocacy.
- Improved Data Systems – Advancing the School Attendance Monitoring System (SAMS) for better tracking and decision-making.
- Capitation Grants to Secondary Schools – A major milestone in extending financial support across education levels.

Country Context

Since the development of the programme’s business case South Sudan, still the world’s youngest nation, continues to face profound development challenges. It ranks among the lowest globally in GDP per capita and HDI, with over 80% of its estimated 13 million people living in rural areas. Persistent conflict, climate shocks, and fragile institutions have weakened public services, particularly education. Food insecurity remains severe, affecting more than half the population, while malnutrition among children continues to undermine learning and attendance. Displacement, flooding, and insecurity have closed thousands of schools, leaving nearly 3 million children out of school—one of the highest rates worldwide. Girls remain disproportionately affected by early marriage, gender-based violence, and cultural barriers. Chronic underfunding forces schools to charge fees, and teacher shortages persist, with only about one in five teachers on payroll and many classrooms staffed by unpaid or untrained personnel. Despite these challenges, partnerships with GPE, ECW, and GESS2 donors are driving system reforms, emergency education, and gender equity initiatives. In today’s context of economic uncertainty and climate vulnerability, sustained coordination and investment are critical to protect recent gains and ensure inclusive, resilient education for all.

Summary supporting narrative for the overall score in this review

The programme scores an A in this Annual Review. Reflecting strong performance across key outputs. Outputs 1,2 and 5 have either met (A) or moderately exceeded (A+) expectations while Output 3 moderately didn’t meet expectations (B) due to the lack of Government of South Sudan’s investment in Primary Capitation Grants (CGs). Due to budgetary reductions in previous years, Output 4 was not implemented in year 6 and is therefore not assessed in this review.

Key achievements in 2024/25:

In 2024/25, GESS2 achieved significant milestones across its core outputs. Community mobilisation reached 4,595 school communities, surpassing 97% of the Year 6 target. Cash transfers supported 244,000 girls and children with disabilities, including 53,237 unique learners, bringing the cumulative total to over 1.28 million beneficiaries. Capitation Grants were extended to 39 secondary schools for the first time, increasing the total to 534 schools and enabling responses to climate shocks and expanded learning spaces for displaced populations. Public Financial Management training reached 1,364 stakeholders, complemented by 247 accountability reports, strengthening governance and data reliability. Additionally, 96% of schools reported attendance through SAMS, reflecting strong system uptake.
Challenges at Output level
- Climate shocks and insecurity: Heatwaves, flooding, and conflict disrupted schooling, causing closures and relocations in multiple states.
- Capitation grant delays: Ministry of Finance failed to release primary school grants, reducing school engagement and planning.
- Teacher salary arrears: Delays of up to 12 months undermined morale and participation in programme activities.
- Exam quality concerns: Pass rates dropped from 90%+ to 60.4%, highlighting weaknesses in learning outcomes and quality assurance.
- Cash transfer withdrawal: Ending support for Primary 5 & 6 increased dropouts, emphasizing the need for conflict-sensitive approaches and social impact monitoring.
Progress against Recommendations from previous review
The previous review recommended a more targeted approach to cash transfers and analysis of the impact of withdrawing support for Primary 5 and 6, alongside extending GESS2 into early 2025/26. During the reporting period, payments were focused on upper classes (P7–Senior 4), where gender parity and transition rates were lower, and boys with disabilities were included for the first time. This strategy aimed to maximise impact in critical transition years. However, the planned analysis on the effects of withdrawing cash transfers for P5 and P6 girls was not completed and will be prioritised during the extension period, with findings due to be reflected in the Programme Completion Report (PCR).

Major lessons and recommendations for the year ahead

Lesson	Recommendation & Deadline
Systemic weaknesses undermine sustainability	Q2 2026: Lobby WB to roll out Inclusive Education Training for 8,000 teachers. End 2026: Lobby Goss to allocate 10% of budget to education.
PFM reforms need consolidation	Mid-2026: Institutionalise PFM procedures and train 300 officials. Q1 2026: Track salary payments and capitation release.
Political instability and weak fiscal commitment	Q3 2025: Streamline donor coordination meetings to strengthen advocacy.
Weak learning assessment systems	Q2 2026: Pilot LOQAs in five counties. Q4 2026: Integrate LOQA indicators into SAMS. 2027: Publish Learning Assessment Report.
Safeguarding and harmful social norms	Q1 2026: Integrate GBV modules into Education programme teacher training. 2027: Support survivor-led initiatives for community resilience.
Climate shocks disrupt learning	Q2 2026: Implement School Climate Resilience Guidelines. End 2026: Lobby to ensure 30% of new schools meet climate-resilient standards. 2027: Establish EiE focal units in all states through GPE.
Donor coordination is vital	Q3 2025: Update Joint Education Sector Plan with risk-resilience targets. 2026: Establish pooled donor funding. 2027: Strengthen civil-society participation in budgeting.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The GESS2 Theory of Change remains relevant as systemic barriers—poverty, gender norms, and disability exclusion—continue to limit access and retention. Despite funding cuts and the phasing out of quality education and research components, the programme demonstrated resilience and adaptability. Strategic adjustments, such as introducing CAPEX funding for infrastructure and expanding support to boys with disabilities, reinforced inclusivity and improved learning environments. However, withdrawal of support for Primary 5 and 6 negatively impacted retention, especially for girls, underscoring the need for sustained investment to prevent reversal of gains.
Figure 1: GESS2 Theory of Change, 2024/2025

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

GESS2 remains largely on track for its core impact—gender parity and access—despite extreme fragility and fiscal collapse. Primary-level gender parity (GPI 1.0) is a major achievement, but secondary parity (GPI 1.41) risks sustainability without structural reforms. Enrolment (2.19M) and exam pass rates are slightly off track due to insecurity, unpaid teacher salaries, and climate shocks. Learning outcomes remain weak, reflecting systemic issues beyond programme control. Continued support is essential to consolidate parity gains, address learning poverty, and adapt to rising demand from 1.1M returnees. Future actions include strengthening teacher training, integrating continuous assessments, and scaling climate-resilient infrastructure to safeguard progress.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

GESS2 remains indispensable for South Sudan’s fragile education system and should continue based on its proven impact and strategic relevance. Operating in one of the world’s most complex humanitarian contexts, the programme has reached over 1.28 million girls and children with disabilities, delivered cash transfers to reduce financial barriers, and achieved gender parity in primary education (GPI 1.0) and significant gains in secondary (GPI 1.41). Community mobilisation has transformed social norms in nearly 4,600 school communities, while PFM reforms have strengthened accountability across all ten states, training 1,364 officials and producing 240+ accountability reports.
Despite systemic challenges—teacher salary arrears, climate shocks, and fiscal collapse—GESS2 anchors the education system, contributing nearly 20% of MoGEI’s expenditure. Education outcomes remain among the lowest globally, with 70% of children out of school, underscoring the need for sustained donor engagement. Withdrawal now would reverse hard-won gains in access, gender equity, and governance, especially as 1.1 million returnees strain resources. Continued support will protect progress, expand climate-resilient infrastructure, and enable a smooth transition to Education for All South Sudan (EFASS), consolidating reforms and ensuring inclusive, equitable education for the most vulnerable learners.

## C. DETAILED OUTPUT SCORING

Output Title	Communication to girls, boys, women and men to shift attitudes and behaviours related to education of girls and children with disabilities
Output number:		1	Output Score:	A+
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1: Number of people over the age of 15 reached with radio programmes informing of the benefits of education to girls and children with disabilities / (Non- cumulative)	2.32m	2.8m (Moderately Substantially Exceeded)
1.2: Number of school communities reached with community mobilisation / (Cumulative)	4,182	4, 595 (Met)

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 1: This output is designed to deliver behaviour change messaging through nationwide radio and community outreach, promoting education rights and challenging harmful norms—especially for girls and children with disabilities.

The programme used multiple communication channels, including:
- Radio talk shows, scripted programmes, and PSAs on cash transfers, disability inclusion, and PFM.
- Six PSAs aired in 12 local languages via 26 partner stations, reaching 2.8 million people (exceeding the 2.32 million target).
- PSAs were low-cost, adaptable, and effective in reaching diverse audiences, including non-literate groups.

A Disability Inclusion Team (DIT) conducted three virtual trainings for radio presenters and producers, with an average of 29 participants per session. Materials were widely shared via CMV networks and WhatsApp, enhancing inclusivity and message quality.

Output Indicator 1.2: Community mobilisation reached 4,595 school communities, surpassing the Year 6 target of 4,182. It was designed to improve awareness and attitudes of and to the importance of inclusive education. Monitoring data shows 98% of participants had positive attitudes to girls’ and disability-inclusive education. Full target achievement was recorded in six states, with the remaining four nearing completion. However, action rates dropped in Upper Nile (64%) and Unity (68%), mainly due to economic hardship limiting families’ ability to act on awareness.
Continuous technical support to CMFPs and CMVs improved data accuracy. Minor inconsistencies from new CMVs are being addressed through mentoring and performance monitoring.

Changes and Recommendations

- No changes were made during the review period, and none are planned.
- No logframe target was set for this period, limiting measurement of incremental progress. Future programming should include updated indicators to track ongoing behaviour change outcomes.

Output Title:	Cash transfers to girls to improve enrolment, retention, transition and completion rates.
Output number		2	Output Score:			A+
Impact Weighing (%)		25%	Weight Revised since last AR?			No
Indicator(s)				Milestone(s) for this review	Progress 2024-2025
2.1: Cumulative number of (unique individuals) girls receiving cash				1,240,000	1,480,025 / Of which 53,237 in year 6 / (Substantially Exceeded)
2.2: Cumulative number of cash transfers received.				2,687,541	2,734,608 / Of which 244,230 in year 6 / (met)

Briefly describe the output’s activities and provide supportive narrative for the score
Output 2 delivers cash transfers (CTs) to eligible girls and children with disabilities in P7 to S4, aiming to boost enrolment, retention, and transition by offsetting education-related costs. The output exceeded expectations, with 1,280,025 unique learners reached (vs. 1,240,000 target), including 53,237 new beneficiaries in 2024. A total of 2,734,608 CTs were disbursed cumulatively, with 244,230 issued in 2024, surpassing targets due to stable conditions during the payment period. However, 23 schools missed payments due to insecurity and flooding; these will be covered in 2025.
Challenges included inflation, bulky cash handling, and limited currency denominations, increasing risks and verification issues. Mitigation measures like group travel and parental accompaniment were implemented, though 35 incidents were flagged to FCDO. For the first time, 530 boys with disabilities received CTs. The GPI improved from 0.67 (2014) to 1.03 (2024), reflecting increased access for girls.
In 2024 during an evaluation of support to classes from P5 to S4, classes P5 and P6 were removed from CT eligibility due to a number of factors including improved gender parity and the requirement to incentivise attendance in the latter years of school. It was assessed by the FCDO that this change was communicated effectively, and its impact is still being monitored. CT enrolment and validation were digitised using the SAMS mobile app, improving data accuracy and efficiency over previous methods.
Safeguarding was strengthened with child-friendly, community-informed reporting mechanisms integrated across programme components. Lessons learned include the need to extend CT deadlines in insecure areas and improve onboarding processes disrupted by climate shocks and conflict. Recommendations for future programmes flexible timelines and continued digital innovation to ensure no learner is left behind.

Output Title:	Capitation grants to schools to improve learning environment for all learners.
Output number		3		Output Score:		B
Impact Weighing (%)		35%		Weight Revised since last AR?		No
Indicator(s)			Milestone(s) for this review		Progress 2024-2025
3.1: Cumulative number of primary schools that are approved for Capitation grant (CG) payment by MoGEI/ GESS			6,454		6,545 (Met)
3.2: Cumulative number of qualified primary schools whose funding is released from the national Ministry of Finance and Planning (MoFP) to the state Ministry of Finance and Planning (tracking release of funds from the Ministry of Finance to state Ministry of Finance or directly to schools).			N/A		n/a GoSS took over the monitoring of this indicator, but it was agreed during the year that this indicator should be paused and no longer monitored from 2023/24 onwards as funds no longer flow from National Ministry of Finance through State Ministry of Finance to schools.
3.3: The cumulative number of primary schools that have received CG paid by MoFP (GRSS).( tracking release of funds from State MoFPs to schools)			5,116		5,093 0 (Not Met)
3.4: Cumulative number of secondary schools that have received CG by GESS / (Schools that have received capitation grants in GESS1 and now in GESS2).			275		258 (Not Met) / Of which 1 in year 6
3.5: Cumulative number of secondary schools that have received CGs by GESS for the first time / unique under GESS2.			245		276 (Moderately Exceeded) / Of which 39 in year 6
3B.1 Cumulative number of meetings held by the State Education Transfer Monitoring Committee (SETMC).			150		328 (Substantially exceeded)
3B.2 Number of accountability reports generated by the SETMC and shared to ETMC.			130		247 (Substantially exceeded)
3B.3 Cumulative number of people with PFM stakeholders involved in education policies, trained, and getting new knowledge on policy-based public finance management for education. / (Cumulative)			720		1,364 (Substantially exceeded)

Briefly describe the output’s activities and provide supportive narrative for the score
Output 3 focuses on providing Capitation Grants (CGs) to schools to improve operational capacity and learning environments. GESS2 funds secondary school CGs, while the Government of South Sudan manages primary CGs with technical support from GESS2. In Year 6, 6,545 primary schools were approved for CGs, exceeding the target, but only 34 new approvals were processed due to delays. No primary CG payments were made because of government liquidity issues, while cumulative payments reached 5,093 schools, slightly below target. Secondary CGs were paid to 258 schools under GESS1 and GESS2 and 276 under GESS2 only, meeting Year 6 targets despite banking challenges. CAPEX funding was introduced for infrastructure upgrades, and ownership verification strengthened eligibility.
Governance and PFM Strengthening
PFM reforms advanced significantly, with 328 SETMC meetings held, 247 accountability reports submitted, and 1,364 stakeholders trained—far exceeding targets. These measures institutionalised financial controls, improved transparency, and digitised attendance monitoring through SAMS (97% coverage). Despite challenges like salary arrears and limited banking infrastructure, GESS2 strengthened coordination between the Ministries of Education and Finance, laying durable foundations for accountable, data-driven governance. Lessons highlight the need to incentivise school leaders, institutionalise PFM documentation, and align donor-government planning cycles. Continued support is essential to consolidate reforms, embed accountability frameworks, and sustain progress in education system resilience.
.
Describe any changes to this output during the past year and any planned changes as a result of this review
During the reporting period, Capitation Grants (CGs) earmarked for capital expenditure continued to be paid to improve secondary school infrastructure, including classrooms, toilets, and essential equipment. Schools applied for these funds through their respective states. Additionally, a reporting error from the previous year was corrected—21 secondary schools previously misclassified as primary were updated. No further changes are planned as a result of this review.
Progress on recommendation from the previous AR.
The previous review recommended verifying school ownership to refine CG eligibility. In response, ETMC formed a sub-committee to revalidate ownership, restricting eligibility to community-owned or public schools where fee collection is prohibited.
Lessons learned this year and recommendations for the year ahead
Lessons from this year show low motivation among school leaders hindered CG processing, highlighting the need for stronger engagement and leadership stability within MoGEI. PFM reforms successfully established procedures in all ten states, trained 1,364 officials, and produced 247 accountability reports, improving transparency. However, weak budget execution and delayed fiscal transfers continue to undermine impact. Future programmes should institutionalise PFM documentation, align donor-government planning cycles, expand digital reporting via SAMS, and embed joint accountability frameworks to sustain reforms and strengthen local ownership.

Output Title:	Quality of Education, Learning Groups & Resilience to contribute to improving learning outcomes.
Output number		4	Output Score:	N/A
Impact Weighing (%)		0	Weight Revised since last AR?	No

Briefly describe the output’s activities and provide supportive narrative for the score.
Due to budget reductions in Y5, Output 4 has been paused. There were therefore no targets set for these indicators in year 6.
Output Title:	Building a knowledge base for support of girls’ education
Output number		5		Output Score:		A
Impact Weighing (%)		20%		Weight Revised since last AR?		No
Indicator(s)			Milestone(s) for this review		Progress 2024-2025
Output 5.1: Number of final drafts of studies shared with donors.			N/A		N/A
Output 5.1 B: Number of substantial reviews required for products sent to FCDO			N/A		N/A
5.2: % of schools reporting regular attendance through SAMS.			90%		96% (Moderately exceeded)
5.3: Number of research sharing/dissemination meetings held by M&E Technical Working Group (TWG)			N/A		N/A

Output 5 aimed to strengthen girls’ education by building a knowledge base through research and data collection. However, due to budget cuts in Year 6, most research and quality-focused activities were paused, limiting the programme’s ability to measure learning outcomes and improve teaching practices. The School Attendance Monitoring System (SAMS) remained operational and highly effective, achieving 97% school coverage and reducing reporting costs by over 50%. Despite this success, the suspension of core research and teacher quality initiatives narrowed the programme’s focus to access and parity indicators, leaving gaps in understanding educational quality. Future efforts under Education for All South Sudan (EFASS) must restore robust research and learning functions to inform policy and embed continuous improvement.
Attendance reporting through SAMS exceeded expectations, with 96% of schools submitting at least five reports, surpassing the 90% target and improving from 93% in the previous quarter. Strong performance was driven by staff commitment, targeted interventions, and improved stakeholder communication, with regions like Jonglei and Equatoria achieving 100% reporting. However, some areas underperformed, such as Ruweng (57%) and Northern Bahr El Ghazal (87%), highlighting the need for targeted support. External factors, including onboarding delays caused by a heatwave, disrupted the school calendar, resulting in low reporting rates early in the year. Overall, while attendance monitoring thrived, research and evaluation activities remained stalled due to funding constraints.
Describe any changes to this output during the past year and any planned changes as a result of this review.
The only changes during the past year were the phasing out of Indicators 5.1 and 5.3 due to budget reductions. No changes are planned as a result of this review.
Progress on recommendation from the previous AR.
Challenges previously identified in school attendance reporting—such as poor phone networks, unreliable electricity, staff turnover, and technical issues with the Kobo Collect app—have largely been resolved. These improvements contributed to an increase in reporting rates from 87% last year to 96% this year.
Lessons Learned this year and recommendations for the year ahead.
Introducing onboarding deadlines by MoGEI, supported by GESS2, enabled earlier completion of critical processes like CT validation and payment. Enforcing similar timelines in the future will be essential for timely data collection and effective programme delivery.

## D: VALUE FOR MONEY

GESS2 applies a defined VfM strategy, reported annually, tracking performance across the 5Es—Economy, Efficiency, Effectiveness, Equity, and Cost-effectiveness.
Key Cost Drivers and Performance
Core costs include Cash Transfers (CTs), Capitation Grants (CGs), and operations. In 2024/25, CTs accounted for £7.56 million (45% of the annual budget). Cost pressures stemmed from exchange rate volatility, insecurity, and poor infrastructure in remote areas.
Economy
Programme management costs rose to 7.84% (from 5.97%) but remained within the 8% cap. This increase reflects a smaller overall budget (£16.8m vs. £22.3m) and fixed operational costs despite a 40% reduction in CTs following withdrawal of P5 and P6. Community mobilisation costs per school dropped 68% (from £3,538 to £1,114) due to economies of scale and local procurement. Attendance reporting costs fell 41% (from £259 to £152) through SAMS upgrades, boosting reporting to 96%. Radio costs per person increased to £1.12 from £0.33 due to translation into more languages and expansion of reach but remain cost-effective compared to GESS1.
Efficiency
Efficiency measures how well inputs are converted into outputs. In Year 6, administrative costs rose from 5.97% to 7.84%, mainly due to a 23% budget reduction while fixed management and validation functions were maintained to ensure nationwide coverage. Although cash transfer disbursements fell by 40%, the same operational structure was required, increasing unit costs. Despite these pressures, efficiency remained strong: 97.5% of validated learners received payments, and management costs stayed below the 8% contractual ceiling.
Value delivered to beneficiaries was 75% of CT delivery costs—up from the 67% baseline but down from 83% in 2023—reflecting strong performance despite reduced scale. Competitive procurement and economies of scale helped offset fixed costs. Most states remained on track, with Northern Bahr el Ghazal and Warrap showing better efficiency than Eastern and Unity.
Radio programming demonstrated cost-effectiveness, with unit costs per person at £1.12—37.8% lower than the GESS1 baseline—driven by partnerships, wider reach, and economies of scale. Compared to community mobilisation (£1,114 per school), radio remains a scalable awareness tool, though less interactive. Administrative costs for school support rose to 32%, reflecting renewed investment in hard-to-reach areas and infrastructure gaps.

Effectiveness

Improved cost metrics—such as reduced mobilisation and attendance reporting costs—demonstrate better resource use. However, rising administrative costs for CTs and school support highlight areas for further efficiency improvements. Sustaining current gains will require ongoing monitoring and adaptive management in future programming.

Equity

GESS2 made significant strides in promoting equity, particularly for learners with disabilities and those in remote areas. For the first time, 2,246 learners with disabilities received cash transfers, and 53 schools used capitation grants to improve accessibility through learning aids and inclusive infrastructure. Community mobilisation reached over 42,000 individuals with disabilities, enhancing identification and inclusion. Geographic equity was also prioritised, with outreach extended to hard-to-reach areas such as Lainya, Morobo, Jur River, and Jebel Boma, which had previously been inaccessible. These efforts came with increased costs, rising to £1.37 million, but ensured that 276 secondary schools received grants. State-level progress was strong, with targets met in Jonglei, Northern Bahr el Ghazal, and Central Equatoria, while other states achieved 93–99% despite security challenges.

Cost-Effectiveness

The programme demonstrated improved cost-effectiveness through reduced costs for mobilisation and attendance reporting, reflecting better resource utilisation. However, rising administrative costs for cash transfers and school support remain areas for improvement. Sustaining these gains will require ongoing monitoring and adaptive management, as further enhancements are unlikely under current conditions. The focus moving forward will be on maintaining efficiency and equity while ensuring optimal outcomes for the resources invested.

E: RISK

Overview of risk management

The overall risk rating of GESS2 has remained as ‘Major’. This reflects the higher risk of operating in fragile, and conflict affected states. The GESS2 programme risk appetite reflects the challenging operating environment in South Sudan and the risks we will accept to be able to deliver programme objectives. The risk appetites against the seven categories have not changed since the last annual review and they are aligned with the British Embassy Juba overall risk appetites, as indicated below.

BEJ and GESS2 risk appetites.

Risk category	Strategy & / Context	Policy & Programme / Delivery	Public Service & Operations	People	Safeguarding	Financial & Fiduciary	Reputational
BEJ	Eager	Eager	Cautious	Cautious	Receptive	Receptive	Receptive
GESS2	Eager	Eager	Cautious	Cautious	Receptive	Receptive	Receptive

Risk reviews are conducted quarterly with the GESS2 team and monthly with the Senior Responsible Owner. The risk register is updated accordingly.

Top Three Risks
1. School Disruptions (Strategy & Context) Climatic shocks, violence, and flooding led to school closures, delayed capital spending, and limited access—especially in Upper Nile, Jonglei, and Unity. As a result, 23 schools missed 2024 CTs. Mitigation included fast-tracking payments and rescheduling missed disbursements for 2025.
2. Government Underfunding (Policy & Delivery) Delayed teacher salaries due to weak public financial management caused absenteeism, low morale, and high turnover, affecting learning outcomes. Mitigation includes teacher incentives, community engagement, budget advocacy, and donor coordination.
3. Fraud and Asset Loss (Financial & Fiduciary) 15 cases of theft, loss, or fraud were reported in 2024/25. Most involved negligence or planned theft. Of 64 closed cases, 16 had no loss, 14 were reimbursed, and 34 written off. Improved controls have reduced case numbers. Mitigation includes staff training, asset tracking, and community oversight.

Update on Partnership Principles

In line with FCDO partnership principles, no GESS2 funding is disbursed by or under the direct control of the Government of South Sudan (GRSS). Accordingly, the Partnership Principles are not used to manage this programme.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Delivery and Reporting
FCDO maintains a strong and collaborative relationship with MM/CE, supported by weekly and quarterly meetings. These engagements have improved coordination, risk management, and communication with State Anchors. All contractual milestones were delivered on time. MM/CE submits timely, high-quality reports across all reporting cycles. The only delay—Year 6 VfM report—was communicated in advance and resolved with agreed timelines.

Commercial Performance
In 2024/25, MM/CE delivered key commercial milestones, including:
- Contract Amendment 4: Increased contract value to £97.5m, extended the programme to June 2025, adjusted budget lines, and added capex.
- Procurement: Equity Bank South Sudan was contracted for CT disbursement.
MM/CE scored 95% on supplier KPIs, with a minor penalty for missing financial documents. They maintained 100% compliance with the Code of Conduct and used Open Book Accounting for transparency. However, GESS2 ranked third lowest (73%) among eight MM/CE projects in the Supplier Dashboard due to some poor-quality reports and missing documents in late 2024. These issues were addressed, and reporting improved from February 2025.

Financial Management
GESS2 financial management remains strong. In FY24/25, the programme spent £16.7m of a £16.8m budget (98.9% execution), improving from last year’s 1.5% variance. This was achieved through close FCDO-MM/CE coordination, quarterly planning, and securing an additional £3.53m to support increased CT beneficiaries, enabling the programme to exceed planned activities.

Activity	Budget / allocation	Total spend / FY 24/25	Variance
Programme Management	£1,327,324	£1,316,766	£10,558 (0.8%)
Behaviour change communication	£1,222,110	£1,263,702	-£41,592 (-£3.4%)
Cash transfers	£7,704,212	£7,559,396	£144,816 (1.88%)
Capitation grants	£4,580,610	£4,719,475	-£138,865 (-3.03%)
Quality, learning	£769,506	£803,764	-£34,258 (-4.45%)
Knowledge, Evidence, Research & Learning	£1,124,720	£1,097,143	£27,577 (2.45%)
Total	£16,728,483	£16,760,246	-£31,764 (-0.19%)

Asset Management

The programme maintains a detailed inventory of assets, including tablets, computers, motorbikes, vehicles, audio players, and radios. Physical spot checks were conducted in September 2024 for Mott MacDonald, Stromme, BBC MA, HARD, and WTI, while virtual checks were completed in December for ADRA, MASS, AET, and CINA.
MM/CE and State Anchors carried out regular asset verifications, with staff trained on proper handling and accountability. Asset management was aligned with programme closure to ensure a smooth handover. BEJ/FCDO also conducted independent spot checks and shared findings with MM/CE. In 2024/25, 82 assets worth £4,721.65 were written off, and 198 new assets valued at £74,727 were added to the register.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
MM/CE submits weekly context updates and monthly dashboards, supported by evidence. These are complemented by FCDO monitoring visits where feasible. While virtual monitoring for hard-to-reach areas is being considered, poor internet connectivity has delayed implementation.

In the reporting period, FCDO conducted school visits in Lakes State (Oct 23–25, 2024) and Juba, focusing on CT payments and asset checks. Meetings were held with school staff, State Ministries of Education, NGOs (Oxfam, Save the Children, ACROSS), and State Anchors, alongside focus group discussions with learners.
Key findings:
- Enrolment gains were reported, especially for girls, though rural and cattle camp attendance remains low.
- Teacher attrition persists due to unpaid salaries and better incentives in other sectors.
- School access is hindered by long distances and frequent flooding.
- Improved attitudes toward girls’ education were noted, though economic hardship continues to drive child marriage.
- Exclusion of children with disabilities from CTs was reported, as some were in ineligible lower classes.

Evidence and Learning

Findings were drawn from field visits, stakeholder meetings, and FGDs. A multi-stakeholder CT lessons learned workshop (July 2024) informed improvements in validation, procurement, and payment processes for 2025.

Successes:

- County authorities ensured safe, organised payment environments.
- Strong coordination between data and monitoring teams resolved operational issues.
- Full involvement of MoGEI at national and state levels ensured consistent policy application.
Gaps and recommendations:

- Missing beneficiaries: 25 schools in Mayom and 11 learners in Pibor were left off payment lists. Monitoring teams should escalate such cases promptly.
- Poor sensitisation: Some communities were unaware boys with disabilities were eligible for CTs, leading to refusals. State Anchors should intensify outreach.
- Limited MoGEI presence: Officials left before payments concluded. Future visits should align with payment schedules.

Bi-annual partner review meetings also contributed to programme learning. This Annual Review was based on desk analysis of reports and interviews with key stakeholders, including MoGEI and implementing partners.

Date of last narrative financial report	May 2025	Date of last audited annual statement	29 September 2025

ANNEX 1. Impact Case Studies.
Case Study 1: Behaviour Change Communication – Empowering Communities through Radio and Mobilisation
In Tonj, Warrap State, a 15-year-old girl named Aluet was enrolled in school after her mother listened to the “Our School” radio programme. This story exemplifies the transformative power of Output 1. With over 2.8 million individuals reached via radio and 4,570 school communities engaged through mobilisation, the programme achieved a cost of just £1.12 per person and £1,115 per school community—down from £2,384 at baseline. Community Mobilisation Volunteers (CMVs) and Focal Persons (CMFPs) played a pivotal role, with 83% of parents taking action to support girls and children with disabilities. The programme’s inclusive approach—broadcasting in 12 languages and using visual materials—ensured accessibility even in remote areas. Disability champions helped reach over 42,000 individuals with disabilities. These efforts not only changed attitudes but also led to tangible actions like reopening schools and increased enrolment. The strategic use of local volunteers and integration into existing community structures maximised reach and reduced costs, demonstrating strong value for money through behavioural change and inclusive education advocacy.

Case Study 2: Cash Transfers – Inclusive Support for Girls and Children with Disabilities
In Year 6, GESS2 delivered cash transfers to 244,230 learners, including 2,246 children with disabilities—marking the first time boys with disabilities were included. Despite budget constraints, the programme maintained national coverage and achieved 97.5% successful payments. The cost per recipient rose slightly due to fixed operational costs, yet administrative expenses remained below the GESS1 baseline of 33.1%, standing at 25.4%. Over six years, more than £49 million was disbursed, with over 1.2 million unique girls benefiting. In Jebel Boma, a historically inaccessible area, learners received support, showcasing the programme’s commitment to equity. Beneficiaries like Vivial shared how even modest amounts enabled them to stay in school. Strategic procurement of payment agents and robust validation processes ensured transparency and efficiency. By prioritising hard-to-reach and vulnerable populations, GESS2 demonstrated that inclusive education financing can be both impactful and cost-effective. The programme’s adaptability and focus on sustainability—through government partnerships and community involvement—further reinforced its value for money.

Case Study 3: Capitation Grants – Building Resilient School Infrastructure
Despite the government’s failure to release primary capitation grants in Year 6, GESS2 strategically invested in secondary schools, reaching 276 institutions—exceeding targets. These grants supported infrastructure improvements, including classrooms, WASH facilities, and inclusive learning environments. In Lakes State, five classrooms were renovated and one built, directly enhancing learning conditions. The programme maintained cost-efficiency, with administration costs at 32%, below the cumulative average of 39%. Schools receiving grants showed increased enrolment and retention, especially among girls and children with disabilities. Notably, 53 schools used funds to improve accessibility, demonstrating a commitment to equity. The integration of Public Financial Management (PFM) systems, including SETMC and CETMC, ensured transparency and accountability. These committees facilitated community involvement and reallocated funds to urgent needs, such as temporary learning spaces in Akoka County. Despite economic challenges, GESS2’s targeted investments delivered sustainable value, reinforcing foundational education systems and promoting inclusive development. The programme’s ability to adapt and maintain impact under financial constraints highlights its cost-effectiveness and strategic resource use.

Case Study 4: Data and Attendance Monitoring – Strengthening Education Planning
Through the School Attendance Monitoring System (SAMS), GESS2 achieved a 96.4% attendance reporting rate in Year 6—up from 83% in Year 5. The cost per school reporting attendance ≥5 times dropped to £151, down from £259, thanks to the transition to digital data collection via mobile apps. Enumerators were incentivised based on schools reached, improving efficiency and accuracy. Real-time data enabled better planning and validation for cash transfers and capitation grants. In Upper Nile, refugee schools were successfully onboarded, and in Eastern Equatoria, hard-to-reach areas were prioritised. The system also tracked 20,326 children with disabilities, informing targeted interventions. Local government officials, including Payam Education Supervisors, were engaged to ensure sustainability and reduce costs. The programme’s investment in data systems has enhanced decision-making and accountability across the education sector. By embedding SAMS within government structures, GESS2 ensured long-term benefits beyond the project’s lifespan. This output exemplifies how strategic digitisation and stakeholder engagement can deliver high-quality results at reduced costs, reinforcing the programme’s value for money.