## Annual Review
Title: Jordan Investment and Economic Reform Advisory Programme (JIERAP)
Programme Value £ (full life): £17.6m		Review date: June 2025
Programme Code : 300451	AMP start date: 7 March 2019	AMP end date: 31 March 2026

Summary of Programme Performance
Year	2020	2021	2022	2023	2024	2025
Overall Output Score	A	B	A	A	A	A
Risk Rating	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/47593290.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/57002801.xlsx

List of Acronyms
AR – Annual Review / BCG – Boston Consulting Group / CBJ – Central Bank of Jordan / CRA – Credit Ratings Agencies / DAI – Development Alternative Incorporated / Development Policy Loan - DPL / DTA – Deep trade agreement / DoS – Department of Statistics / EFF – Extended Fund Facility / EMV – Economic Modernisation Vision / FCDO – UK Foreign Commonwealth and Development Office / FTA – Free trade agreement / GoJ – Government of Jordan / IGC – International Growth Centre / IFC – International Finance Corporation / IMF – International Monetary Fund / JIERAP – Jordan Investment and Economic Reform Advisory Programme / JONEPS – Jordan National E-Procurement System / LHGP – Lion’s Head Global Partners / M&E – Monitoring and Evaluation / MDTF – Multi-donor Trust Fund / MEL – Monitoring, Evaluation and Learning / MoIN – Ministry of Investment	MoITS – Ministry of Industry, Trade and Supply / MoL – Ministry of Labour / MoPIC – Ministry of Planning and International Cooperation / MTR – Mid-Term Review / NAF – National Aid Fund / NEPCO – National Electric Power Company / NRGS - National Registry of Government Services / ONS – Office for National Statistics / PPP – Public-Private Partnership / PCR – Programme Closure Report / P4R – Programme for Results / RE – Recipient-Executed / RETF – Recipient-Executed Trust Fund / RF – Results Framework / RS – Reform Secretariat / RSF – Reform Support Fund / SC – Steering Committee / SME – Small and Medium-Sized Enterprises / TA – Technical assistance / ToC – Theory of Change / TTL – Task Team Leader / VfM – Value for money / WB – World Bank / WBG – World Bank Group

A. SUMMARY AND OVERVIEW

Description of programme
The Jordan Investment and Economic Reform Advisory Programme (JIERAP) was launched at the London Initiative on Jordan’s Growth and Opportunity in February 2019. It was originally designed as the UK’s contribution towards the World Bank Group’s (WBG) Jordan Inclusive Growth and Economic Opportunities Multi Donor Trust Fund (i.e. the Jordan Growth MDTF or MDTF), a £14m programme. The MDTF was designed to provide technical assistance (TA) and capacity building to the Government of Jordan (GoJ) to enable them to implement structural reforms through their 2018-2022 Economic Reform Matrix. The MDTF has since been adapted to align to the GoJ’s Economic Modernisation Vision (EMV), which was launched in 2022. In 2022, the end date of the MDTF was extended to 2024 to compensate for COVID 19 related delays, as was the end date of JIERAP, from March 2023 to December 2025 to allow for programme closure.

In March 2022, JIERAP was extended by cost (from £14m to £16.6m) and time (from an original March 2023 end date to December 2025) through a business case addendum. The extension included the following components:

- Macroeconomic Advisory Support (MAS). Targeted technical assistance on macroeconomic stability through DAI/ Lion’s Head Global Partners (LHGP).
- Boston Consulting Group (BCG). Technical advisory on the Aqaba Special Economic Zone (ASEZ) (completed in March 2023).
- Monitoring, Evaluation and Learning (MEL) support through the secondment of an FCDO adviser into the RS at MoPIC (completed in February 2024).

In March 2023, JIERAP was again extended to £17.6m and to March 2026 to accommodate an independent results assessment of the MDTF, and to establish an office of the International Growth Centre (IGC) in Jordan.

During the year under review, the MDTF was extended again, until December 2029. The UK considered the request to extend carefully. While the UKs commitment to Jordans reform agenda remains steadfast, the decision was taken not to sign a further extension to the MDTF in line with an internal policy and portfolio review. Therefore, the UK withdrew from the MDTF in October 2024. The UK was the first and, at the point of withdrawal, still the largest donor to the MDTF. The UK contributed £14m to date, which represents 38% of all donor commitments to the core MDTF programme, and 60% when the emergency cash transfer programme is considered (unlike the rest of the MDTF, the cash transfer programme is not a reform intervention and was funded by a separate FCDO programme, so is not assessed under the JIERAP AR). Due consideration was given to the staff resource required to effectively engage with the MDTF over the past six years and internal reprioritisation will allow us to maximise impact with limited resources going forward. It is common practice for the UK to provide seed funding to establish a MDTF and to withdraw once the mechanism is firmly established and maintained by other donors. As a founding donor, the UK considers it a success that other donors have come on board and that the Jordan Growth MDTF will continue to support the Government of Jordan in implementing its economic reform agenda post UK withdrawal.

Jordan continues to demonstrate resilience amongst regional conflict, as assessed by the International Monetary Fund (IMF) and credit rating agencies (CRAs). However, regional conflict and uncertainty around international financial assistance are exacerbating underlying structural challenges. Growth remained sluggish at 2.5% in 2024, unemployment remains high and rigid (21.5% in Q3-2024), and despite a minimum wage increase from JD260 (¬$366) to JD290 (¬$408) structural challenges persist, particularly in job creation and gender disparities. In this context, JIERAP is supporting the Government of Jordan (GoJ) to implement much needed structural reforms to progress to a sustainable and inclusive pathway to growth. The Macroeconomic Advisory Support component of JIERAP (MAS) was able to be agile to respond to changing needs, in particular in light of the pause in US international financial assistance, which proved valuable to GoJ.

Summary supporting narrative for the overall score in this review
In the year under review, based on progress against outputs, JIERAP has scored an “A” in its Annual Review. Scoring per output is indicated in the table below.

Outputs Table
Output	Weighting	Score
1A) Support capability of GoJ officials on economic management; and advise and/or introduce improved government/governance systems – MDTF	50%	A
1B) Support capability of GoJ officials on economic management; and advise and/or introduce improved government/governance systems – non-MDTF (macroeconomic stability advisory; and International Growth Centre)	10%	A
2) Laws, regulations, policies or procedures developed or strengthened on business environment and investment climate - MDTF	15%	A
3) Laws, regulations, policies or procedures developed or strengthened on labour market and social safety net system - MDTF	5%	A
4) Laws, regulations, policies and procedures developed on the energy and water (including water-efficient agriculture) sectors - MDTF	20%	A
[note] For consistency, output weightings have been maintained for this AR. Since the MDTF component has now been closed, output weightings will be adjusted to reflect this appropriately for 2025-2026.

Major lessons and recommendations for the year ahead

Major Lessons
FCDO made a concerted effort to carefully communicate the decision not to sign the extension to the MDTF to GoJ, WB, and MDTF donors, and to reiterate the UKs commitment to Jordan’s reform agenda. However, it was brought to our attention that the timing of the decision was challenging, as new partners were considering engagement with the MDTF and FCDO exit could be perceived as a lack of confidence in Jordan’s reform process and/or the MDTF as a mechanism to support the reform agenda.

Cultural change within GoJ’s civil service is best achieved by engaging at a low enough level of seniority that personnel do not change with new governments. This is a long-term process and, despite the very high English language skills within GoJ, may sometimes be best accomplished via Arabic language communication.

WB trust funds cannot be treated as a purchase of outcomes separate to broader GoJ and WB goals. Being a WB Trust Fund, the MDTF is anchored in the broader WBG engagement with the GoJ, including through a Country Partnership Framework. As a result, the establishment of the Reform Secretariat (RS) with JIERAP funding is a success and supports project implementation far beyond the MDTF. The RS provides support to several WB Program for Results programmes (PforR) and Development Policy Financing operations (DPF), and related development outcomes including reforms support, making it difficult to attribute results to the MDTF vs. core WB contributions.
Recommendations
JIERAP is in its final year of implementation and only two components remain open in 2025-2026: Macroeconomic Advisory Support and the International Growth Centre. Recommendations therefore focus on priorities for the year as well as informing future engagement beyond the lifetime of the JIERAP programme.
The MDTF was a tool to support Jordan’s reform agenda broadly and provided a key mechanism for engagement with partners, frank discussion, and a forum to agree on coordinated messaging. The internal portfolio and policy review provided an opportunity to refocus FCDO resource. The capacity that has now been freed up should be focused on engagement with GoJ and partners on areas of the reform agenda that have promise to be impactful in areas that align with FCDO priorities.

In light of substantial pressures on international financial assistance globally, FCDO will need to decide how human and financial resource can best be used to maximise impact in Jordan. Funding permitting, developing a robust evidence base to inform policy decisions and high-quality technical assistance to support the economic reforms that can have the most substantial impact should be prioritised.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

Due to the extension of the programme in 2022, the theory of change (ToC) for JIERAP was updated to reflect the evolution of the programme on the MDTF side as well as the newly added non-MDTF components (macroeconomic stability TA and IGC). The now completed components of support to the Aqaba Special Economic Zone, and MEL support to the RS were also included. The new MDTF and non-MDTF programming is fully aligned with the original objectives of JIERAP, as set out in the 2019 business case. As such, the essence of the updated ToC has not fundamentally changed since 2019.

The ToC can be summarised as: if revised laws and procedures (supported by technical assistance on best practices) are effectively implemented through capability and capacity building, and improved systems, then desired reform outcomes will be achieved. The following diagram (updated 2022 ToC) summarises the current ToC:

As noted by previous ARs, assumptions of underlying global levels of economic stability and growth and a stable national and regional security situation have been challenged. During the period under review, regional conflict continues to have impact and the pause in US international financial assistance and uncertainty around US trade and foreign policy is putting pressure on Jordans economy. There is strong complementarity between JIERAP’s technical assistance, and the support provided by the United States. The long-term sustainability of JIERAP’s impact and the effectiveness of any future programming in this area depend on stability being high enough for benefits of economic reform to be fully realised.

Last year’s AR also noted the importance of political backing from GoJ for JIERAP to be impactful. While the change of government following elections in September 2024, lead to delays in implementation while new Ministers settled in, most Task Team Leaders (TTLs) from the MDTF as well as DAI and IGC report an increase in the pace of reform over the year in review, with strong political will for change and commitment to macroeconomic stability and growth. That said, on areas such as skills, energy and competition, progress is still slow. Ultimate ownership of JIERAP’s effectiveness lies with GoJ.

The ToC’s assumption that reforms will be fully implemented implicitly includes the assumption that FCDO funding can be targeted to realise specific reforms. However, as noted above, the MDTF component of JIERAP has been delayed (even including the effect of COVID) by the need for gradual institutional adaptation to precede technical reforms. While this means that outcomes have taken longer to achieve than originally anticipated, the delivery of cultural change means the impact purchased by JIERAP has also been larger. This also applies to the trust fund structure itself: the MDTF-funded Reform Secretariat (RS) now provides support to several WB Program for Results programmes (PforR) and Development Policy Financing operations (DPF). In one sense JIERAP has subsidised these programmes, increasing cost. In another, it has bought some proportion of their impact and has increased impact beyond the MDTF itself.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
JIERAP is in its final year of implementation, with only two components remaining open (MAS and IGC). The focus for 2025-26 will be consolidating impact of the MAS component and agreeing an exit strategy, supporting IGC in disseminating research findings to maximise impact on policy making, and drawing key lessons out in the Programme Closure Report (PCR) to inform any future engagement in this area.

As reported in previous ARs, the majority of MDTF milestones are processes (GOJ adoption of outputs such as reports and policy recommendations produced by WBG), rather than outcomes. As such, they are not included in the AR. Key outcomes that were previously tracked, such as the percentage cost recovery for the water sector and reduction of cargo clearance time, are no longer being tracked in the MDTF results framework due to challenges in gathering data.

The programme is on track to contribute to the expected outcomes that we are able to continue tracking (see table below).

Outcome Indicators	Milestone(s) for this review – Feb 2025	Progress
Outcome 1.1 Increased implementation of reforms by GoJ: Cumulative number of reforms successfully supported by the Reform Secretariat related to the Reform Matrix, including reforms benefitting women (No. reforms / No. benefiting women).	The initial target for 2025 was 66/11. Since 111/27 were achieved mid-year, the target was revised upwards to 111/27. WBG adjusted this in the second half of the year to take out reforms that were not directly supported by the MDTF.	98/35 (lower than mid-year progress as a result of the removal of reforms not supported by MDTF). We comfortably consider this outcome as met in terms of progress against the initial target for 2025, which was 66/11.
Outcome 1.4 Enhanced capacity of Department of Statistics (DoS): / (1) Number of improved or finalized processes/reports/studies/plans/strategy/policy that were endorsed/approved/adopted/enacted by GoJ. / (2) Open Data Inventory (ODIN, a measure of statistical performance)	(1) NA / (2) Improvement in the Open Data Inventory (ODIN) score to 66 out of 100 points in 2022.	(2) ODIN score at 72 (2024). Due to improved data accessibility, Jordan now ranks 44th globally in the Open Data Inventory (up from 82nd in 2020). - met
Outcome 1.5 Improved access by public and businesses to improved quality infrastructure and business services from GoJ: Number of services enhanced because of the implementation of service improvement plans approved by the Office of Prime Minister.	Cumulative 2800 public services cards available.	2,730 (audited and / verified by the / audit bureau in / Jordan) - met
Outcome 1.6: Maintain Jordan’s macroeconomic stability and improve access to international finance market. / (1) IMF reviews passed successfully, indicating macroeconomic stability. / (2) Assessment of the four credit ratings agencies regarding Jordan's macroeconomic stability. / (3) Value of Eurobond issuance(s) (US$) achieved.	(1) 1st and 2nd review of IMF EFF successfully passed. / (2) 6 credit ratings completed without downgrade in assessment of Jordan's macroeconomic stability. / (3) N/A. Issuance of Eurobond or local dinar bond is yet to be decided.	(1) 1st, 2nd, and 3rd IMF EFF review successfully passed. - met / (2) Achieved, with upgrade from Moody’s in May 2024 and S&P in September 2024. – moderately exceeded / (3) No Eurobond issuance planned for the review period. Analysis and advice provided on funding strategy and debt refinancing options. - met

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
JIERAP is in its last year of implementation. Programme Closure is planned for 31 March 2026. Any future programming providing technical assistance will require some acceptance of Jordan’s geopolitical and economic risk, as well as continued political backing.

## C. DETAILED OUTPUT SCORING

Output Title	Support capability of GoJ officials on economic management; and advise and/or introduce improved government/governance systems – MDTF
Output number:		1A	Output Score:	A
Impact weighting (%):		50%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress Feb 2025
1A.1 Provide technical assistance and capacity building on reform management:
(1) Establishment and structuring of an efficient Reform Secretariat (RS).	(1) +2 RS staff hired, SS&G specialist and M&E Specialist. Overall Reform Secretariat is operating at improved capacity.	(1) 3 RS staff hired, including M&E specialist, with all roles now covered. Resignation of programme coordinator means total of 15 staff at RS. - met
2) Cumulative (i.e. since programme launch) number of consultation sessions conducted across Government ministries and other stakeholders, including private sector.	(2) 154 consultation sessions cumulatively.	(2) 91. –moderately not meeting expectations
(3) Cumulative number of GoJ ministries/agencies supported by the Reform Support Fund (RSF)	(3) 30 GoJ ministries/ agencies cumulatively supported by the Reform Support Fund RSF.	(3) 24 due to removal of any projects with standalone budget - moderately did not meet expectation.
(4) Recipient Executed Trust Fund (RETF) restructured to operate more efficiently and effectively.	(4) RETF operating more efficiently and effectively (restructure completed- % budget execution)	(4) RETF budget execution improved substantially (100% funds utilised, 23.3m approved allocation, 100% utilized, 11.5m in actual spend). – met / (Overall A, met expectations)
1A.3 Build capability of Department of Statistic (DoS) and sustainably strengthen the National Statistics System (NSS):
(1) Number of reports/studies/recommendations/plans/strategies/policies finalized/submitted by WBG. / (2) Number of training sessions conducted	(1) overall, 10 reports produced. / (2) N/A milestones for 2025	(1) 11 reports produced. / (Overall A+, met expectations)(2)
1A.4 Provide technical assistance to develop National Register of Government Services (NRGS), and enhance monitoring of GoJ service delivery:
(1) Number of knowledge-sharing events (number of individuals participated, out of which no. that are females).	(1) Hold 1 workshops / showcasing / international best / practice in developing / relevant policy / tools to monitor / service performance / standards	(1) 1 workshop held with Services and Public Administration Commission team. met.
(2) Number of reports /studies/ recommendations /plans/strategies/policies finalized/submitted by WBG.	(2) An assessment on the current state of SD / and a user manual / on effective SD / monitoring	(2) Both completed, along with a Citizen Voice Manual. - met. / (Overall A, met expectations).
1A.5 Provide technical assistance on climate responsiveness of reforms, climate governance (incl. transparency and accountability), and climate & green finance:
(1) Climate Responsiveness of Reforms: / (1a) Number of reports/ studies/ recommendations/ plans/ strategies/ policies finalized/submitted by WBG / (1b) Number of systems deployed to support climate investment. / (1c) Number of training sessions conducted (no. of individuals participated, out of which no. of females).	(1a), (1b) and (1c) N/A milestones for 2025.	(1a), (1b) and (1c) no milestones for 2025.
(2) Green Finance: / (2a) Number of reports/studies/recommendations/plans/strategies/policies finalized/submitted by WBG	(2a) 4. Ministry of Finance to formally adopt the / TOR, Debt management strategy and / Sovereign Green Financing Framework / CBJ to formally adopt the risk assessment / report	(2a) Debt management strategy published and TOR formally adopted. – moderately did not meet expectations
(2b) Number of training sessions conducted (number of individuals participated, out of which number of females).	(2b) 15 Capacity building sessions / implemented (100; with at least 25% female / participants).	(2b) 16 capacity building sessions implemented (12 workshops, 1 Presentation to CBJ on climate risk assessment, and 3 presentations on investor relations. (~100/still to be determined as of Feb 2025 SAR) moderately exceeded. / (Overall A, met expectations)
[note] In the SAR, WB/MDTF has the milestone set at 106 against which 80 consultations were achieved. There was an adjustment to how this is being measured, since in 2024 the target was 106 and 125 consultations were achieved.
[note] While the number of Gov Ministries supported by the Reform Support Fund was revised down to reflect that several projects are funded from different budgets, we recognise the positive externalities of the Reform Secretariat in supporting implementation of the reform agenda more broadly (including through WB P4Rs and DPL). With 97% of the 303 reforms under the current Reform Matrix supported, we consider this output to have overall met expectations.

Briefly describe the output’s activities and provide supporting narrative for the score.

Strengthening Reform Management (RE)
Since restructure of the RS was completed (2023-2024) and progress was made to resolve longstanding government procurement challenges, implementation of the RETF has made substantial progress. Cumulative spend has increased to US$9.3m, with the remaining US$6.5m committed.

The hiring of three staff (one part time) and the resignation of one means that the Reform Secretariat now has 16 staff. They are being used to their full extent, supporting implementation of the current Reform Matrix, the development of the second iteration of the Reform Matrix, and providing monitoring for several WB PforR programmes and DPF operations, which is a positive spillover from the investment supporting coordination and maximising impact of support channelled through the WB more broadly than the MDTF. Progress on procurement and budget execution has significantly accelerated over the last year, with almost all funding committed. The RS has been involved in 97% of the 303 reforms made under the existing Reform Matrix, which is 75% of the 403 planned reform actions. Approximately 40% of the budget for the second Reform Matrix has already been committed.

Key achievements include the creation of “Tawasul,” a public engagement portal, the operationalising of regulatory impact assessments, monitoring for MDTF BE programmes, and an increase in the proportion of GoJ projects routed through the new project concept note system. The Jordan Online E-Procurement System (JONEPS) is now used by 52% of Ministries, Departments and Agencies (MDAs), which reflects significant progress.

A Mid-Term Review (MTR) on SRM was carried out by WB in March 2024. This rated the project overall as satisfactory, with component 2 (Supporting MDAs through the Reform Support Fund) and component 3 (Strengthening PIM-PPP and Public Procurement) rated as moderately satisfactory.

Several TTLs, as well as IGC and DAI, expressed that the RS, and MoPIC more broadly, are invaluable for coordinating engagement across GoJ. However, there are potential disadvantages to the approach in that the coordinating function can be mistaken for accountability sitting with the reform secretariat and MoPIC rather than the line ministries. It is important that line ministries engage and that ownership of implementing reforms successfully sits with them.

The RE is working better as a complement to the BE component now it has capacity (given that BE can’t directly procure and GoJ is much slower at hiring). There is considerable flexibility, with some procurement needs transferred to other WB programmes. The RS is still 100% donor funded and plans to bring in more GoJ civil servants will be important for the sustainability of the FCDO’s investment.

Department of Statistics, DoS (BE)
The DoS programme strengthens Jordan’s statistical infrastructure, laying the foundation for evidence-based policy and decision making. This grant is complementary to the UK’s longstanding peer-to-peer TA to the DoS delivered by the UK’s Office of National Statistics. The DoS Task Team noted the usefulness of the RS in coordinating the various statistical support offers coming from donors.

The DoS programme has supported broader statistical reforms in Jordan, including a new Statistics Law and a new National Strategy for the Development of Statistics (NSDS). It has also helped in the ongoing development of the National Data Centre interface, an online interactive data portal, which will enable centralised data access to enhance policy coordination and improve service delivery across government institutions. Jordan’s ODIN scores have improved from 66 (2022) to 72 (2024), reflecting substantial progress. The thematic reports on gender and labour have been produced, but still not been cleared for publication by GoJ.

Service Delivery (BE)
This project is being leveraged to coordinate digital service standards work with the GoJ SANAD (official website to access government digital services and digital identity in Jordan) and the Youth, Technology and Jobs (YTJ) WB project, for which the UK is the sole donor via our Jordan Compact Economic Opportunities Programme’s contribution to the Global Concessional Finance Facility.
[note] Sanad - Homepage

The National Registry of Government Services (NRGS) which underlies SANAD was updated this year in response to feedback from government entities. This directly enhanced reporting accuracy and governance effectiveness. Training was conducted for the more than 240 government employees who are regular users of the system, resulting in successful internal rollout and public accessibility via service cards. This transition has improved efficiency by streamlining service information and increasing transparency.

There are now service cards (GoJ services which are connected to SANAD) for 2,730 services, nearly meeting the target of 2,800 set in mid-2024, accumulatively. GoJ reports there are 1.4 million digital identities on the system as of February 2025, 73% higher than in January 2024. This is, however, lower than the 3.5 million target set for 2025.
[note] EMV achieves progress in ICT sector, digital transformation – report | Jordan Times

Climate-Responsive Reforms and Green Finance (BE)
In common with several MDTF projects, the Climate Responsive Reforms and Green Finance Task Team described progress speeding up during the year in review. Jordan’s climate agenda progressed significantly, with the finalisation of the second phase of the Climate Investment Pipeline and Mobilisation Plan 2030, supporting a structured approach to mobilising climate finance and investment.

The Green Finance Programme supported the delivery of a draft for Jordan’s first Climate Risk Assessment report to CBJ, with the final report due at the time of drafting the AR. A summary report on eligible investments for a future sovereign Green Bond was due early 2025, with WB assisting MoF and line ministries in developing a pipeline of potential projects. After more than 20 consultations with MDAs, a preliminary portfolio of around one billion USD in eligible investment was drafted in the second half of 2025. Further activity on green bonds has included workshops and the planning of a potential visit to Romania to learn from their green bond experience.

Support was provided to the Climate Investment Pipeline and Mobilisation Plan 2030, and stakeholder consultations were held on Jordan’s Long-Term Strategy. The Monitoring, Reporting, and Verification (MRV) system for climate reporting advanced to publication of guidelines, supported by additional (GoJ funded) specialists at the MoE. Work continues on integrating adaptation projects into the MRV system, with the eventual hope that this will help Jordan attract international climate finance with the possibility of selling carbon credits. The Prime Ministry’s Office has also established a Disaster Risk Finance Steering Committee with MDTF to provide financial buffers from climate induced risks.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

FCDO did not opt to sign a further extension to the MDTF. From October 2024, FCDO will no longer be part of the steering committee. This output will no longer be monitored.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on recommendations from last year
With Strengthening Reform Management representing US$15.8m and 42% of Steering Committee-approved funding, the WB should consider deploying additional staff to support their Task Team Leader overseeing this grant, proportionate to the size of this grant. It is a risk and imbalanced that the largest project within the MDTF only has one dedicated staff member (excluding the cross-cutting resources such as the WB’s MDTF Secretariat, Social Safeguards Specialist, Environmental Specialist, Procurement Specialists, Financial Management Specialist etc, which are available across all projects) whereas the other, considerably smaller projects within the BETF can count on multiple.
The Task Team Leader is still the only dedicated staff member for Strengthening Reform Management project. While the usefulness of cross-cutting resources was explained as sufficient for the sub-component's needs, it is possible that extra staff would be/have been useful for some activities which have not been possible: for instance, finding a way to prioritise the order in which reforms are carried out based on potential impact.

By summer 2024 FCDO should facilitate coordination between the WB and the UK Met Office, as the latter develops the Jahez programme, so as to avoid duplications and exploit synergies, particularly with regards to the respective support by both implementing partners around climate risks.
FCDO organised an initial conversation on Jahez in July 2024, with a plan to follow up on specific areas of collaboration once the Jahez programme begins. The International Water Management Institute (IWMI) and Met Office are expected to meet with WB at some point in spring 2025.

Lessons learnt this year
One lesson learnt was that promotion of Monitoring and Evaluation within GoJ is sensitive due to nuances in language. The phrase ‘M&E’ in English was noted as being reminiscent of audit procedures rather than an ongoing attempt to focus on impact, to improve by testing what works.

The importance of in person engagements for building shared understanding of priorities and acceleration of implementation was noted by both RS and WB officials.

Recommendations for the year ahead
Since FCDO did not opt to sign a further extension to the MDTF this component was closed in October 2024. There are no recommendations for the year ahead that will be monitored within the scope of the JIERAP programme, or assessed in the next AR. However, FCDO should find appropriate avenues to ensure synergies between programmes are identified and duplication is avoided. The Jahez programme is one example, as is future climate programming, which may merit proposing a climate sector working group. Coordination on data and support to DoS can be championed through the relationship with the ONS as well as the IGC.

Output Title	Support capability of GoJ officials on economic management; and advise and/or introduce improved government/governance systems – non-MDTF (macroeconomic stability advisory; and International Growth Centre)
Output number:		1B		Output Score:		A (A for LHGP; A for IGC)
Impact weighting (%):		10%		Weighting revised since last AR?		No
Indicator(s)			Milestone(s) for this review		Progress March 2025
1B.1 Provide technical assistance/advisory to GoJ on macroeconomic stability
			(1) Credit Rating: supporting the MoF with a total of 6 credit ratings by March 2025.		(1) Total of 10 credit ratings supported by March 2025, including two upgrades. – moderately exceeded.
			(2) IMF review: Supporting the MoF with TA and advice on two IMF programme reviews by March 2025.		(2) Two IMF EFF reviews supported by March 2025 (July 2024 and December 2024), as well as the third review in April 2025. – met.
			(3) Investor Engagement: Organising and supporting the MoF and (other GoJ entities- MoPIC) with at least one investor engagement event between Jan 2025 and March 2025.		(3) GoJ requested to delay investor engagement post-election (September 2024). To meet GoJ demand and availability, investor engagement sessions were completed in April in Washington DC and may in London - moderately did not meet expectations
			(4) Following the development of the 2025 funding strategy, MAS team to provide an updated plan for potential funding options by March 2025 including Eurobonds or Local Dinar Bond subject to funding needs and market conditions.		(4) Analysis and advice provided on funding strategy and debt refinancing options. – met / (Overall A, met expectations)
1B.2 Research and policy advisory to GoJ by International Growth Centre
a. Number of reports, studies, recommendations submitted by researchers to the IGC			a. 5		a. 5: / 1. Refugee Education Decisions in the Face of Restricted Work Rights – Evidence from Jordan / 2. Fair budgets and revenue mobilisation in Jordan’s municipalities: The role of the Cities and Villages Development Bank / 3. Is Signalling the Key to Improved Matches in the Labour Market? Evidence from Jordan* 4. Jordan Labour Market Framing Paper / 5. Peer Review of the Draft Planning & Zoning By-Law for Amman City, 2024 / -met expectations
b. Number of knowledge sharing events, / training sessions, workshops, etc. conducted			b. 2		b. 2 Events hosted by IGC Jordan: / Water Roundtable: Adapting to Water Scarcity in Jordan (January 2025) / Unlocking Inclusive Growth: Jordan’s Labour Market Research Symposium (Feb 2025) –met expectations
c. (New added in 2024) Number of projects producing final outputs (reports, studies, recommendations, plans, strategies, policies, etc.) disseminated by the IGC to relevant stakeholders.			c. 3		c. 3: / 1. Refugee Education Decisions in the Face of Restricted Work Rights – Evidence from Jordan. / 2. Jordan Labour Market Framing Paper / 3. Peer Review of the Draft Planning & Zoning By-Law for Amman City, 2024 / Overall met expectations

Briefly describe the output’s activities and provide supporting narrative for the score

Macroeconomic Advisory Support (MAS)
MAS continues to provide support on the IMF EFF programme, investor engagement, and funding strategy to GoJ via Development Alternatives Inc (DAI), Lion’s Head Global Partners (LHGP), and support on credit ratings via Cygnum Capital. In preparation for Jordan’s 2025-dollar maturities, MAS advised GoJ on potential funding options. While most of LHGP’s time is spent on long term workstreams (funding strategy, IMF review and investor engagement), some is flexibly spent on requests from across GoJ, which have increased recently as a result of the USAID 90-day freeze. JIERAP’s DAI contract (subcontracted to LHGP and Cygnum Capital) is well suited to this kind of work because small requests done via other TA channels face high fixed organisational costs in funding and approval and are therefore less cost effective. Filling a critical gap left by USAID pause on monitoring progress against IMF EFF benchmarks proved valuable, both for the Ministry of Finance in continuous support on a critical policy area and to the MAS programme in strengthening engagement.

Despite there being no Eurobond issue in the year under review, LHGP continued work on engaging international investors. This is important because given the ongoing war in Gaza and the USAID freeze, lack of transparency is liable to lead to speculation amongst investors potentially putting downward pressure on Jordan’s credit rating. In this case LHGP’s and Cygnum Capital’s work are strong complements. S&P raised Jordan to BB- in Moody’s raised the Government of Jordan's long-term local and foreign currency issuer ratings toto Ba3 in May 2024, and S&P raised its rating to BB- in September 2024, , and Fitch has been stable at BB-. The rating upgrades are particularly impressive in light of regional conflict. Private ratings are sometimes capped by the government’s ratings, so these upgrades promise lower borrowing costs in Jordan’s private as well as public sector. Jordan successfully completed the first (July 2024), 2nd (December 2024), and 3rd (April 2025) review of its IMF EFF programme. The impacts of regional crisis, reducing domestic demand, and increasing debt service costs are putting pressure on Jordans fiscal space. Continuous progress on the implementation of the IMF programme is a testament to Jordans commitment to economic reform and macroeconomic stability.

Following national elections in September 2024, a new Minister of Finance was appointed. The previous Minister of Finance was the key counterpart for the MAS programme and programme delivery was supported by a close and much trusted relationship. Shortly after the election, the new Government had to navigate an IMF mission for the second IMF EFF programme review, the WB/IMF AGM annual meetings, and submission of the national budget. The MAS programme team had prepared for potential changes in Government following the election and positioned themselves well to engage with counterparts from day 1, providing support through these key events.

While the changes in Government inevitably slowed down some work as new Ministers embedded into their new roles, it also offered the opportunity to work not only to the Minister of Finance but also more directly with Jordanian civil servants, hopefully leading to longer-term upskilling and more sustainable impact. A culture shift within GoJ was noted, even over the short course of the contract, with an increased appreciation for transparency’s importance in maintaining investor confidence. This has been especially needed given the recurrent shocks Jordan’s economy has faced in the year under review and since JIERAP’s start.

International Growth Centre (IGC)
The IGC is administrated by the London School of Economics in partnership with the University of Oxford. It aims to be a bridge between government practice and academia, producing publishable research with relevance for the host country. In Jordan, they currently focus on four thematic areas: i) firms, trade and productivity, ii) state effectiveness, iii) cities, and iv) energy and environment. The IGC currently has 17 projects in progress, including 9 on firms, trade and productivity and 4 on cities. Around half are at least in part funded by other FCDO and IGC funding sources. The IGC has met its output level targets including the submission of 5 research policy papers by researchers to IGC, disseminating 3 research projects to relevant stakeholders and conducting two knowledge sharing events in January and February 2025.

The IGC country office is managing delivery of these 17 projects and building constructive relationships with Government counterparts However, IGC Jordan still does not have a full-time Country Director or Lead Academic. Hiring locally is made challenging by the overlapping requirements that any candidate be able to speak Arabic, be academically qualified and not be politically affiliated (to ensure the IGC’s independence). Another challenge is getting access to government data, which is a time-consuming process reliant on political support. However, the IGC team noted that this also increases the potential impact of their research once they have access, and that part of what they must overcome is the experience of GoJ that researchers move on after publishing rather than providing long term policy support. Building trust to counteract this will take time, but maximises benefits of IGC engagement in country by providing positive externalities for researchers in the future. IGC plan to take a long-term approach to cultural change and capacity building, focussing on relatively junior staff because they are not replaced when the government changes, and therefore provide more long-term impact.

Describe any changes to this output during the past year, and any planned changes as a result of this review

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on recommendations from last year
FCDO should be more strategic in leveraging IGC’s research network for its upcoming business cases for its new economic development programmes in Jordan.
FCDO is progressing in utilising the IGC network to inform policy and programme support to Jordan. During May 2024, FCDO met with Prof Ed Glaeser from Harvard and IGC to brainstorm water-related interventions the FCDO could support in Jordan (informed by IGC research). FCDO also provided feedback on priority areas within the water sector, including on tariffs which is also being supported by the MDTF.
FCDO facilitated connections between IGC and Ministry of Industry, Trade and Supply (MoITS), and is triangulating the following interventions:
- IGC focus on trade, through new requests from government of Jordan.
- FCDO current work with MoITS through Trade for Development Programming: technical assistance on rules of origin through the Trade Advocacy Fund (TAF2+) and export promotion support through the UK Trade Partnership Programme.
Lessons learnt this year
Routing requests for flexible support from the MAS programme across GoJ via MoPIC was found to be a more effective way of prioritising requests and managing relationships than having all line ministries directly approaching DAI. IGC also noted that MoPIC was a valuable coordinator for their engagement with GoJ.

Recommendations for the year ahead
The programme team should work with MAS implementing partners and GoJ counterparts to develop an exit strategy, balancing delivery of high-level objectives with capacity building, and ensuring impact is consolidated in 2025-26. FCDO should consider which elements of MAS drive the most impact and whether these can be built on in future programming, funding permitting.

The MAS component has proven to be good value for money. Niche expertise was able to add distinct value as a complement to other forms of TA and broader economic reform. Implementing partners have been agile and responded to impacts of cuts in US international financial assistance. To inform any future programming, cost effectiveness needs to be considered in light of reductions in support public financial management and the energy and water sectors due to reductions in US international financial assistance, which have substantial implications on debt and macroeconomic stability. Additionally, the right balance between reactive support and focused, at time propositional, strategic support would need to be considered in any future programming building on the MAS experience.

The IGC noted that as well as GoJ and civil society, donors beyond FCDO are key targets for research dissemination. The FCDO should play a convening role to support IGC in reaching a wide audience so that research can effectively feed into policy decisions.

Given the time and resource investment to establish an IGC office in country and build constructive, trusted, relationships, continuity in the IGC programme beyond JIERAP should be considered a priority for FCDO (funding permitting).

Output Title	Laws, regulations, policies or procedures developed or strengthened on business environment and investment climate - MDTF
Output number:		2	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress Feb 2025
2.1 Collect data on the impact of the licensing processes on the private sector and provide technical assistance to GoJ on business environment reforms (Investor Journey and B-Ready Indicators):
(1) B-Ready: / (a) Number of reports (studies/plans/strategy/policy) finalised.	(1a) 12 (accumulative) including: / 10 B-READY / Reform Action Plan Implementation initiated, Assessments preassessment, and Completion Report: / Gaps, Lessons and / Recommendations	(1a) Assessments pre-assessment and 10 B-READY Reform Action Plans completed. – moderately not met.
(b) Number of workshop (training sessions/knowledge sharing events/Seminar) conducted and participants (including females)	(1b) 20 workshops.	(1b) 10 awareness workshops in March 2024 and a second group of 10 in June 2024 (122 participants in March, 97 in June ). - met / Overall A (met expectations)
(2) Investor Journey Indicators: / (a) Number of reports (studies/plans/strategy/policy) finalised. / (b) Number of workshop (training sessions/knowledge sharing events/Seminar) conducted and participants (including females)	(2a) 2 sectoral / licenses / reformed. 1 Final report / delivered to GoJ and 1 / Tool developed with / MOITS to facilitate / implementation	(2a) Action plan for pipeline sectoral licensing reforms completed, updated priority list with rational for reform, high level regulatory review for sports licensing, and action plan for sports licensing reform. 3 sectoral licenses completed. –met
	(2b) 2 knowledge sharing / events with public / and private sector / to engage on / implementation	(2b) 1 meeting with / Jordan Olympic Committee for Sports Licensing Reform – moderately not met / Overall A (met expectations)
2.4 Provide Technical Assistance and Capacity Building to Strengthen Insolvency Framework:
(1) Number of reports/studies/recommendations/plans/ strategies/ policies finalised/submitted by WBG.	(1) Count =8. Details: / Final drafts of instructions ready for submission to client (Count=3) Training material / for IPs completed (Count=1), IFC will develop / 4 SOP series / targeting creditors, / debtors, judges, Ips / (Count=4).	(1) 10. / 4 draft instructions covering 5 topics completed, 1 training material for IPs completed, 1 training material for judges completed, 4 SOPs targeting creditors, debtors, judges, IPs completed. – moderately not met.
(2) Training and knowledge-sharing: / (a) Number of insolvency practitioners (IPs) trained (of which, no. Of women). / (b) Number of judges trained (of which, no. of women). (c) Number of wider knowledge-sharing events (no. of individuals attended, of which no. of women).	(2a)10 IPs/ 1 female / (2b) 20 judges/ 3 female / (2c) 4 in total. Details: / 1 Training for IPs and 1 Training for Judges 2 awareness sessions completed / (Sex disaggregated / M/F)	(2a) / 21 IPs/ 8 female / (2b) 30 judges/ 7 female / (2c) 8 in total. / 1 Training for IPs and 1 Training for Judges 5 awareness sessions completed (for lawyers, banks, accountants, Chamber of Commerce, Chamber of Industry. 1 training for CCD in Jan 2025 / (No disaggregation given for awareness sessions) – substantially exceeded. / Overall A (met expectations)
2.6 Provide technical assistance on enhancing GoJ capabilities in negotiating Deep Trade Agreements (DTAs); and on implementing trade facilitation reforms:
(2) Trade facilitation / (a) Cumulative number of reports/ studies/ recommendations/ plans/strategies/policies finalised/submitted by WBG. / and no. of individuals participated (out of which no. of females).	(2a) 15 outputs cumulatively since project start on trade facilitation WBG or supported by their TA including Two (2) reports / (assessments, surveys, / manuals, strategic / option reports) by Feb 2025.	(2a) 2 reports released in the year under review (Time release and trade and gender impact analysis). Cumulative: 13. – moderately not met.
(b) Number of training and knowledge-sharing sessions (including workshops, seminars conferences etc) conducted	(2b) N/A	(2b) No milestone for 2025 / Overall B (moderately not met expectations)

Briefly describe the output’s activities and provide supporting narrative for the score.

B-Ready and Investor Journey Indicators (BE)
The 10 B-Ready Action Plans have been finalised by the WB but not yet implemented by GoJ.. The WB has continued to run workshops on B-Ready (with 97 attending over the most recent 10) and has engaged the Jordan Olympic Committee on sports centre reform. It is up to GoJ whether or not to carry this work through to its final outcome.

The aim of the MDTF’s Investor Journey project is to collect data and information on the impact of the licensing processes on the private sector and to provide technical assistance to the GoJ with the aim of improving the ability of policymakers to identify license reform priorities.

Investor Journey reforms experienced some delays due to ministerial changes and the lack of engagement from counterparts such as the Jordan Olympic Committee (JOC), but the task team indicated that progress has recently accelerated. While not meeting its targets on report adoption, progress on the licenses themselves has accelerated. WB reports that three sectoral licenses were reformed during the period under review (reducing the logistical burden of application renewal as well as fees), bringing the total to 5 reforms, with seven new legal tools published in the Official Gazette. An action plan for prioritisation of sectoral license reform was shared with the Ministerial Committee. MoITS will no longer serve as the GoJ counterpart for sectoral licensing reforms. MoPIC has been holding the relationship while a permanent replacement is found.

Insolvency (BE)
Insolvency has not quite met its target for final drafts of instructions, but has exceeded targets for training: 21 Insolvency Practitioners (8 of whom female) and 30 judges (7 of whom female) were trained, while awareness sessions were run for lawyers, banks, accountants, Chamber of Commerce and Chamber of Industry, Companies Controller Department (CCD). This broad spread is crucial to drive understanding of and demand for the new (as of 2018) insolvency law. A 13 chapter Arabic training manual for Insolvency Practitioners was completed, 4 instructions (the third tier of law under the Jordanian legal system), and 4 SOPs have been completed, which are now with the Legal Committee with the Council of Ministers.

The Insolvency Task Team expressed that their work has become easier over time as trust has been built with GoJ counterparts. There are now more than 50 cases under the insolvency law in the courts. While just one case has reached the reorganisation stage, the Task Team noted that there are multiple outcomes from insolvency, that insolvency is a long process in all countries and that they plan to continue monitoring of the process until 2027 to understand the outcomes for businesses involved.

Trade Facilitation (BE)
Trade Facilitation is completed as of this AR. It achieved 13 cumulative outputs (reports/studies etc), slightly short of its target: 15.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

FCDO did not opt to sign a further extension to the MDTF. From October 2024, FCDO will no longer be part of the steering committee. This output will no longer be monitored.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on recommendations from last year
The WB and GoJ should monitor and widely communicate the extent to which the changes under the MDTF’s trade facilitation interventions save businesses time and costs when it comes to trade. The completion of the TRS will be an important step.
TRS has been completed, and has informed customs reform since. The results do not seem to have been widely communicated.

Recommendations for the year ahead
Since FCDO did not opt to sign a further extension to the MDTF this component was closed in October 2024. There are no recommendations for the year ahead that will be monitored within the scope of the JIERAP programme, or assessed in the next AR. However, FCDO should identify ways to continue engaging on the business environment reform and trade facilitation agenda. The Private Sector donor coordination group is a useful entry point for this.

Output Title	Laws, regulations, policies or procedures developed or strengthened on labour market and social safety net system - MDTF
Output number:		3	Output Score:	A
Impact weighting (%):		5%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress Feb 2025
3.1 Provide technical assistance to Jordanian Ministry of Social Development to expand and improve the National Aid Fund (NAF) cash transfer programme:
(1) NAF expansion and recertification of beneficiaries from the old system - number of reports/studies/recommendations/plans/strategies/policies finalised/submitted by WBG.	(1) [ Marked as completed]
(2) Status of migration of eligible old NAF programme households to new Unified Cash Transfer (UCT) programme, (indicator is not about reports/analysis etc captured above).	(2) Migration 100% completed.	(2) All eligible households migrated - met
3.2 Providing technical assistance to GoJ on how to reform the labour market and support jobseekers in finding employment:
(1) Number of reports (studies/plans/strategy/policy) finalised	1) 4 including: / -Draft supply side / labor market analysis / -Technical note / on coordination / mechanisms between / NAF and MOL on / employment support / activities / -Technical note on a / framework for a career / counselling module / -Segmentation / analysis report	1) 3. The coordination technical note was removed as a WB output in the Feb 2025 SAR. - met
(2) Number of consultation sessions with stakeholders and Number of workshop (training sessions/knowledge sharing events/Seminar) conducted	2) 3	2) Consultation with MoL on supply analysis. Moderately not met expectations.
(3) Number of participants attending workshops (Out of which are females)	3) 20. Number of individuals reached from workshops on / the Dissemination / and endorsing of the / supply analysis and / segmentation report by / December 2024	3) 20 individuals reached from workshops on / the Dissemination / and endorsing of the / supply analysis and / segmentation report. (No gender disaggregation given.) – met / Overall A (met expectations)

Briefly describe the output’s activities and provide supporting narrative for the score.

Support to NAF’s Unified Cash Transfer programme (BE)
This output aims to expand and improve the mechanism and targeting of the National Aid Fund (NAF) cash transfers. The overall aim includes the creation of a new system (with expanded eligibility), the migration of existing beneficiaries to the new system, and finally the removal of ineligible recipients. Migration is reported as 100% complete by the WB, meeting this year’s target, with the removal of ineligible recipients still to be completed. Another recent move is to improve communications to raise recipients’ economic literacy. Because many of those not eligible under current rules cannot work due to age or disability, a new law covering these groups is expected to be passed before the old system is completely shut down. Future work will also focus on making the system more shock responsive (with a focus on climate shocks), but this is not planned to be MDTF funded.

NAF had around 100 thousand recipient households before support began; it currently has 230 thousand, of whom only 40 thousand are still on the old system. Factoring in household size, those 230 thousand households represent 15% of Jordan’s population. A UNICEF survey reports payments are most often spent on food, utilities and children’s clothes.
[note] NAF_English_Report.pdf

Labour Market Assessment (BE)
This output aims to inform reforms to labour market regulations and support job seekers in finding employment.

The WB counts three reports as being finalised within the year under review: the segmentation report and supply side report covered in last year’s AR, and a technical note on career counselling. This provides recommendations for improving the national employment platform. The supply side analysis and segmentation analysis results were disseminated in 2 knowledge sharing events to a total of 20 people. A UK study tour was also held, which the WB believes was effective in engaging GoJ officials. There were also some issues: a target to produce a technical note on collaboration between NAF and MoL was removed from the WB’s objectives without explanation, and rather than 3 stakeholder consultations only one was carried out, leaving the career framework uncovered.

The flexible work bylaw was successfully amended in June 2024, providing a framework for flexible workers to gain employment rights through their contracts. Employers are not compelled to agree to a flexible work contract, and the NGO Phenix Center has called for more effort from GoJ to encourage take-up of the new system. Amendments to the labour law and the Social Security Corporation law have also been endorsed by the Cabinet. These aim to establish uniform maternity leave across the public and private sectors, introduce more flexible termination regulations, prevent the dismissal of pregnant employees and remove the legal requirement that any employment relationship last for 16 days or more.
[note] Jordanian Labor Watch: Mechanisms to implement the amended flexible work system are still weak

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The WB removed the technical paper on coordination mechanisms between NAF and MOL as a target for this year. The target for NAF migration was increased from 80% to 100%.

FCDO did not opt to sign a further extension to the MDTF. From October 2024, FCDO will no longer be part of the steering committee. This output will no longer be monitored.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on recommendations from last year
FCDO should explore whether the UK Office of National Statistics could work with the Jordanian Department of Statistics through their existing partnership, to revise the definition of head of household from being male by default, in order to facilitate greater women’s access to the UCT. FCDO should also explore whether its Strengthening Societal and Economic Resilience in Jordan (SSERJ) programme could be used as a vehicle to support women’s access to other universal social protection benefits.
The DoS task team explained that the definition of head of household is governed by Jordanian law and would require an act of parliament to be changed. In relation to NAF, the NAF task team described a number of measures to prevent female headed households, including married women whose husbands cannot fill in the forms, from unfairly missing out on social protection. Each married household now has an “other representative,” who is by default female, who can apply for NAF. Other problems of eligibility such as the children of Jordanian women with non-Jordanian men not contributing towards payments (because under Jordanian law they are not citizens) would again require more fundamental reform by an act of law.
By June 2024, following the finalisation of the labour market supply analysis through the MDTF, FCDO should explore how it can build on the complementary findings between this analysis and the recent refugees skills audit FCDO commissioned.
Recommendations for the year ahead
Since FCDO did not opt to sign a further extension to the MDTF this component was closed in October 2024. There are no recommendations for the year ahead that will be monitored within the scope of the JIERAP programme, or assessed in the next AR. However, labour market reform and the strengthening of social safety nets remain critical areas for FCDO engagement, both for humanitarian and any future economic development programming. FCDO technical advisers are well placed to invest in key relationships with WB and GoJ counterparts and play a convening role when further coordination can add value.

Output Title	Laws, regulations, policies and procedures developed on the energy and water (including water-efficient agriculture) sectors. - MDTF
Output number:		4	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress Feb 2025
4.1 Provide technical assistance on water sector financial sustainability, and water-efficient agricultural reforms:
(2) Agriculture sector reforms (to develop a roadmap for reforms to water subsidies and identify an incentive framework to support the agriculture and food sector's inclusive and sustainable growth path.)	(1) N/A (project completed)	(1) N/A (project completed)
(2a) Number of reports (studies/plans/strategy/policy) finalised	(2a) 2. / 1- Technical Inputs into / Agricultural Extension / Plan / 2- Technical Inputs into / Veterinary Services Plan	(2a) 2. - met
(2b) Number of finalised reports (studies/plans/strategy/policy) that got (endorsed/approved/adopted/enacted)	(2b) Technical committee / approves both plans on / Technical Inputs into / Agricultural Extension Plan / and Veterinary Services Plan	(2b) 2. Both reports approved. - met
Provide technical assistance on energy sector reforms: / (1) Reports/studies/recommendations/plans /strategies/policies supported by WBG	(1) 3 outputs completed. / Studies on Energy Storage, E-mobility and Green / Hydrogen. / The key findings and / recommendations have been presented to Jordanian stakeholders, informing policy.	All 3 studies underwent QER processes. Additionally, a technical report and study trip were organised on green hydrogen in Europe, along with a two-day workshop on energy storage with a focus on pumped hydro. - met

Briefly describe the output’s activities and provide supporting narrative for the score.

Water-efficient agricultural reforms (BE)
This sub-component has met its targets for the year under review, with technical inputs provided and technical committee approval given to both the Agricultural Extension Plan and the Veterinary Services Plan. Sustainable practices are also to be promoted via a water saving loan, which is currently being rolled out (non-MDTF funded). The main objectives of the Plan (from the UN Environmental Programme) are to “develop a more integrated and efficient agricultural extension system [...] (ii) enable inclusive participation in extension services through demand-driven training programs for youth, women, and marginalized groups [...] (iii) promote the adoption of modern, climate-smart technologies [...] (iv) enhance institutional and individual capacities.”

Energy (BE)
There are three studies being prepared on the energy sector. These are on Energy Storage, E-Mobility (transport) and Green Hydrogen. All 3 underwent Quality Enhancement Review in the last year and are expected to be finalised in Q1 2025. Draft copies have been circulated with GoJ entities including NEPCO (the energy company) and MEMR.

The green hydrogen study is focused on establishing a regulatory framework for future production. A study tour to Europe was organised for 13 high level figures from MDAs and stakeholders to see Green Hydrogen production in practice.

The energy storage study is looking at business models that could work in Jordan as well as how the electricity law could be amended to cover distributed energy storage. A two-day workshop on energy storage was held, with a particular focus on pumped storage. This involved over ten multilateral and multilateral development partners and built upon a previous report suggesting the construction of a project around the Mujib dam.
[note] (PDF) Pumped Hydro Storage Contributions To Achieve Jordan Energy Strategy 2020-2030

Time of use tariffs, applying lower prices during periods of lower usage, were extended in January 2025 to banks, private hospitals, water pumping, and hotels, meeting the target of 15% of consumption covered by July 2024. GoJ is therefore on track for its target of 30% coverage by January 2025 (data not yet published). The WB is merging electricity data with other administrative datasets to inform future tariff adjustments and target household support under NAF. The WB’s reporting confirms that slow approvals from GoJ have delayed progress on this output – not uncommon in complex reform processes.
[note] Incentive electricity tariffs during off-peak times for vital productive sectors | Jordan Times

Describe any changes to this output during the past year, and any planned changes as a result of this review.
FCDO did not opt to sign a further extension to the MDTF. From October 2024, FCDO will no longer be part of the steering committee. This output will no longer be monitored.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on recommendations from last year
FCDO should ensure that the World Bank and the IWMI coordinate to exploit synergies between the MDTF’s water-efficient agricultural work, and Jahez’s planned work on nature-based water solutions, including for agricultural production.
FCDO organised an initial conversation between the Jahez programme team and a WB Senior Agricultural Economist in June 2024. Further meetings are anticipated when the Jahez programme progresses.

Recommendations for the year ahead
Since FCDO did not opt to sign a further extension to the MDTF this component was closed in October 2024. There are no recommendations for the year ahead that will be monitored within the scope of the JIERAP programme, or assessed in the next AR. However, FCDO will continue to support water sector efficiency through IGC research to influence policy decisions and future climate programming. Similarly, energy sector financial stability is critical to macroeconomic stability and growth in Jordan and should be considered as a key area if technical assistance can be provided to GoJ in the future (funding permitting).
## D: VALUE FOR MONEY

Key cost divers and VfM performance compared to the original VfM proposition in the business case

Economy
Economy refers to the cost paid for components.

MDTF: The original JIERAP Business Case anticipated that the transition from BE to greater levels of RE activities would drive down WBG management fees from the 17% fee for BE towards the 5% fee for RE as the RE proportion increased over the programme lifetime. This argument remains valid in line with previous ARs. The Strengthening Reform Management RETF continues to account for the largest budget share of the MDTF ($23.3m, or ¬46% of the overall Steering Committee-approved core program funding). Strengthening reform management spent $3.7 million in the year under review. The Programme Management and Administration budget comes to another 5% for the year in review.

MAS: The DAI contract continues to provide good value for money for the impact achieved, with £369,000 budgeted for FY 24/25. DAI note that FCDO’s rates are lower than other donors in Jordan.

IGC: Forecast FCDO funding for IGC in FY 24/25 is £500,000, indicating that it is now running at full capacity. This is fully in line with the business case addendum for IGC.

Effectiveness
Effectiveness refers to how well the money spent has contributed to a programme’s outcomes.

MAS: As in last year’s AR, the clearest results were achieved through the Macroeconomic Advisory Programme. S&P and Moody’s both raise Jordan’s credit rating despite impacts of regional conflict. This is a testament to GoJs commitment to macroeconomic stability and economic reform, and helps maintain access to borrowing and reduces borrowing costs for both GoJ and Jordanian business.

MDTF: Cultural change has also been a key outcome of JIERAP, more than the original business case anticipated. One example is an increase in internal (to GoJ) and external transparency, noted by both the DoS Task Team and MAS. Appreciation for the benefits of reform has been spearheaded by the RS’ high profile, and the adoption of this system by a new government represents the passing of a major hurdle.

MDTF: In terms of reformed systems, the completion of NAF migration, the increased usage of SANAD, the expansion of ToU tariffs and the increase in cases passing through the new insolvency system are all successes.

Efficiency
Efficiency refers to how well the money spent has contributed to a programme’s outputs.

MAS: The MAS component is the most clear example of high efficiency, with a small investment ensuring support is provided across a wide variety of outputs. The new government have continued to rate the service highly, with support requested and provided for an IMF engagement within the first week following the election in September 2024.

IGC: IGC’s individual project costs are low for the level of academic quality they represent. The most expensive JIERAP funded project is on remote work adoption, at £58,190.

MDTF: BE projects are also reasonably low cost for the amount of work done. The only projects over £1 million in lifetime cost are DoS, B-Ready and Climate Mainstreaming. It is not entirely clear why these projects were chosen to receive more investment, which ties in with the general problem that reforms have not been prioritized according to the impact they can have. It should also be noted that where outputs take the form of recommendations (such as B-Ready), impact will come only if GoJ has sufficient will to pass the reforms.

MDTF: The RETF has generally poor reporting on outputs, a concern that has been raised by FCDO for several years.

Equity
Equity refers to how the benefits of a programme are distributed across a recipient country’s society.

IGC’s projects are the most clearly related to underprivileged groups within Jordan. Of their 17 current projects, 7 are marked as 100% gender focused, and 7 are marked as 100% marginalised groups focused. This also has the potential for wider economic benefits, given Jordan’s very low female labour force participation (14%).
[note] Labor force participation rate, female (% of female population ages 15+) (modeled ILO estimate) - Jordan | Data

A highpoint in the MDTF is NAF support, which clearly targets (and now better targets after the reform) the very poorest in Jordan. Some MDTF projects involving workshops could do better at disaggregating their participants by gender.

Assessment of whether the programme continues to represent value for money
The programme team continues to be confident that there is sufficient evidence that JIERAP represents good value for money. IGC and MAS are low-cost interventions that demonstrate good value for money on delivered outputs. While the results assessment made some progress towards this, there is still a need for more evidence on outcomes and impact of the more mature MDTF component.

E: RISK

Since inception, the overall risk rating for JIERAP has been assessed as ‘moderate’, and remains so, in line with the UK’s risk appetite for Jordan. The risk register is updated on a quarterly basis and was last updated in February 2025.

Following the UK decision to exit the MDTF in October 2024, the JIERAP programme team streamlined the number of risks that are related to the MDTF component and are actively monitored. There are currently nine active risks under JIERAP. Six risks have a residual risk of Moderate and three risks has a residual risk of Minor. The table below reflects the current risk register, which also outlines the post-mitigation residual risk rating and updates on each risk.

Risk Description	Residual (Post-Mitigation) Rating	Review comments
Policy & Programme Delivery
Macroeconomic Advisory Support -MAS contract fails to meet the expectations of Government of Jordan.	Moderate	The implementing partners through DAI/LHGP are meeting expectations. GoJ through the Minister of Finance and Minister of Planning and International Cooperation are providing positive feedback to FCDO.
International Growth Centre struggles to gain traction in Jordan and fails to produce relevant research/policy advice that will be implemented.	Moderate	IGC continue to gain traction in Jordan for their second year and are working across a number of key entities including MoPIC, MoWI, DoS and others. IGC first Symposium event was conducted in February 2025 with a good number of attendees from GoJ and researchers and quality discussions. Additional research projects are in the pipeline.
Lack of coordination between MoPIC and other Government ministries and stakeholders (implementing partners and donors).	Moderate	Coordination between MoPIC, Government Ministries and implementing partners is well maintained, MoPIC continues to be at the centre of the coordination process.
Lack of climate change focus and specific actions through the JIERAP	Minor	JIERAP components have embedded climate and environment considerations where feasible, including new research initiatives by the IGC focusing on climate.
Strategy & Context Risk
UK economic and political context changes adversely affect JIERAP.	Moderate	Residual risk downgraded from major to moderate over the past year. The risk remains due to uncertainty around 2024 UK general elections, and any subsequent implications.
People Risk
FCDO staff turnover leads to internal capacity and capability gaps.	Minor	The risk remains relevant but declining. Risk was downgraded to minor. following MDTF Exit, advisory requirements for JIERAP are reduced, IGC and MAS require less advisory work and similar PM engagement.
Financial & Fiduciary Risk
Misuse of Trust Funds through fraud and corruption	Moderate	This risk is well controlled on MDTF, IGC and MAS components. Annual Statement of Progress are conducted by FCDO annually and FRAs every three years.
Safeguarding Risk
Risk of exploitation or abuse of beneficiaries through the JIERAP initiatives	Moderate	FCDO centrally revisits its Central Assurance Assessment, which covers safeguarding, with the WB every three years. Due diligence and contracts for other JIERAP implementing partners address safeguarding. Safeguarding issues are discussed with all partners at regular intervals and Partners Engagement Day. No safeguarding cases have been reported to date across JIERAP.
Reputational Risk
Poor performance of JIERAP initiatives reflect badly on the UK as a donor.	Moderate	The likelihood for activities under the MDTF that are poorly performing, that may cause reputational risk, is relatively low, especially following the UK decision to exit from the MDTF in Mid-2024. The other JIERAP components (IGC and MAS) are relatively small, enabling easier monitoring by FCDO.

The JIERAP risk register, British Embassy Amman portfolio and country risk registers, monthly embassy Delivery Board meetings, and quarterly cross-embassy senior leadership Country Board meetings provide effective systems for escalating risks within the British Embassy Amman.

Update on Partnership Principles

The FCDO Partnership Principles underpin the aid relationship between the UK and a host country. The four principles are:

1. A commitment to reducing poverty and achieving the Sustainable Development Goals.
2. A commitment to respecting human rights and other international obligations.
3. A commitment to strengthening financial management and accountability and reducing the risk of funds being misused through weak administration or corruption.
4. A commitment to strengthening domestic accountability.

JIERAP is relevant to all the Partnership Principles. The economic reforms are intended to promote sustainable and inclusive growth in the long-term. The MDTF support to the National Aid Fund is intended to mitigate negative impacts on the poorest and most vulnerable.

The macroeconomic stability advisory component of JIERAP strengthens the financial management of GoJ, by supporting GoJ with its negotiations with the IMF, and meeting the requirements of the credit ratings agencies. These are particularly relevant to the third and fourth Partnership Principles.

Concerns have not led to any suspension of disbursements, and the UK judgement is that a sufficiently credible commitment to the Partnership Principles exists to allow the aid relationship to continue.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.
JIERAP is overseen by the Economic Advisor at Jordan’s Economy and Prosperity team, who is the Senior Responsible Owner (SRO). The SRO is supported by wider members of the Economic Development team including a Senior Programme Manager who is the Programme Responsible Owner (PRO), a private sector development adviser, and a cross-cutting Monitoring, Evaluation and Learning (MEL) Adviser. Multi-disciplinary advisory support (including governance, social development, humanitarian, conflict) from across the British Embassy Amman is also sought as and when required to review MDTF and non-MDTF project proposals and quality assure the JIERAP Annual Review.

MDTF
FCDO Jordan made its final payment to the MDTF in November 2021, bringing the FCDO’s total financial contribution to £14m overall since the start of the programme in 2019. The FCDO remains the largest contributor to the MDTF having provided 38% of the total available funding to date for the core programme (60% when the UK’s contribution to the emergency cash transfer programme is included).

The MDTF “end disbursement date” was planned on 31st December 2025 per the Administrative Agreement and respective amendments. FCDO aim was to continue the support for Jordan reform agenda until the planned end date via the MDTF to finalise the old legacy portfolio and work on designing new economic portfolio post December 2025 that aligns with the FCDO Jordan and supports Jordan’s Economic Modernization Vision.

During 2024, the Government of Jordan and World Bank agreed a MDTF extension by an additional four years from 2025 to 2029. The World Bank informed FCDO that the ‘closing date’ and related ‘end disbursement date’ of the MDTF cannot be extended without the agreement of all donors, as all Administrative Agreements are structured the same. Since FCDO had decided not to sign a further MDTF extension, FCDO withdrew from the MDTF agreement before other MDTF donors signed the Amendment and extend the end disbursement date.

Non-MDTF
The remaining active non-MDTF components under JIERAP are 1- Macroeconomic stability advisory to GoJ through an FCDO contract with DAI and sub-contractors (Lion’s Head Global Partner,LHGP, and Cygnum Capital) and 2- Establishing the International Growth Centre (IGC) office in Jordan through an accountable grant.

Macroeconomic stability advisory: the contractors continued to demonstrate satisfactory performance for the second year, delivering against the terms of reference and agreed workplan. The quality of work was affirmed by Government of Jordan’s positive feedback, as a direct beneficiary of the services provided. The contractors engaged with FCDO and government counterparts, meeting FCDO requirements of reporting, both financially and technically. The financial performance of the second year is fully aligned with the agreed forecasts, which reflects a commendable level of foresight and financial management and is consistent with the first-year forecasting vs spending accuracy.

In late 2024, FCDO team agreed with the contractor to extend the contract for an additional year, following the continued demand from Ministry of Finance and successful results of the first two years. The contract extension is yet to be signed, which will raise the total value to £1.165 M up from £777K, and the end date by March 2026.

IGC: The centre’s second year has witnessed progress and improvements in comparison to the year of establishment, in terms of number of active research projects, engagement with key counterparts and operational activities. IGC managed to utilise the second-year budget of £500k as forecasted, bringing up the total utilised close to £780K. During the second year, the accountable grant agreement has been extended as a ‘no cost extension’ to run until September 2025. The plan following September 2025 is to consider the continuation of the IGC office in Jordan via the Green and Inclusive Growth Centre of Expertise at the FCDO central team.

The IGC team in London provides strategic oversight, as well as financial management and monitoring and evaluation. Both the London hub, and in-country team have been fully engaged with FCDO, continuously updating the budget forecast and providing quarterly narrative reports in high quality and depth.

The Delivery Chain Risk Map for the programme is outlined below reflecting both the MDTF component (showing the main line ministries within the GoJ that the MDTF is engaged with) and the non-MDTF components under the cost extension.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
Throughout the review period, JIERAP’s monitoring and evaluation (M&E) activities were conducted through regular quarterly meetings with key stakeholders, including implementation partners and the Government of Jordan. These meetings served as a platform to assess programme performance, gather feedback from the Government of Jordan, and ensure alignment with strategic priorities. The MDTF component concluded with the final Steering Committee meeting attended by FCDO in May 2024 following the UK’s decision not to extend support. Previous evaluations of the MDTF component played a critical role in shaping programme priorities. Notably, assessments of two key economic areas—Public-Private Partnerships (PPP) and the business environment—provided valuable insights which were taken into consideration previously. Additionally, the World Bank's mid-term review further informed programme direction in 2023. For the non-MDTF components, including the Macroeconomic Advisory Support Programme (MAS) and the International Growth Centre (IGC), M&E efforts primarily relied on quarterly progress reviews and direct engagement with key government counterparts. This included regular discussions with the Ministry of Finance on the MAS component and coordination with the Ministry of Planning and International Cooperation (MoPIC) on both the MAS and IGC activities.

Evidence
As the MDTF component formally closes this year, following FCDO’s decision not to sign an extension, there are no significant changes to the evidence base for this component. For the IGC, evidence generation continues through ongoing research activities focused on Jordan’s key economic priorities, including the labour market, water, and urban development. While findings are still being developed, early outputs include a ‘labour market framing paper’, which has been shared with the Government of Jordan. Additionally, discussions held during the Labour Market Symposium in February 2025 highlighted the importance of improved data collection and disaggregation for policy development. A notable initiative is the partnership between the Department of Statistics (DoS) and the World Bank through the MDTF aiming to enhance data management and utilisation through national data centres to support evidence-based policymaking.

Learning
In the programme’s final year, the focus will be on consolidating lessons from both MDTF and non-MDTF components to inform the design and implementation of FCDO Jordan’s future programmes, particularly the planned support to macroeconomic stability and research. Additionally, a key learning point is around the potential impact of IGC’s work and how FCDO can leverage IGC’s academic network and research expertise to support FCDO programmes. This has been communicated to the IGC central team to consider as the IGC work will be only via the central team from September 2025.

Date of last narrative financial report	February 2025	Date of last audited annual statement	December 2024