## Annual Review Template

Title: Global Finance Programme (GFP)
Programme Value £ (full life): 69 million		Review date: 28 July 2025
Programme Code: 300452	AMP start date: March 2018		AMP end date: December 2045

Year	2018/19	2019/20	2020/21	2021/22	2022/23	2023/24	2024/2025
Overall Output Score	A	A	A+	A+	A	A	A
Risk Rating	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	Original Business Case | 2024 Addendum
DevTracker Link to results framework:	Logical Framework https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300452/documents

A. SUMMARY AND OVERVIEW

Summary
The Global Finance Programme has been assessed as meeting expectations, scoring an A for the 2024 to 2025 review period. Delivery across the programme’s core technical assistance components largely met expectations, with some milestones exceeding expectations.

The GFP funds the Financial Services Centre of Expertise (FSCOE) – a facility providing technical assistance and capacity building to emerging market developing economies (EMDEs) from across the UK public, private and academic-sectors. The GFP also includes our support for local currency through The Currency Exchange Fund (TCX).

Overall, the GFP remained responsive to demand from Foreign, Commonwealth and Development Office (FCDO) posts and partner governments. Within the FSCOE, the Bank of England continued to deliver high-quality support to central banks, while the Cambridge Centre for Alternative Finance (CCAF) met all log frame targets and maintained its position as a leading provider of digital regulatory tools and insights. TheCityUK and the Green Finance Institute (GFI) progressed their pilot engagements in Vietnam, Nigeria, Indonesia and the Philippines, contributing to financial sector reform and climate finance mobilisation.

For TCX, the fund delivered a second consecutive record year in hedging volumes and expanded its engagement with institutional investors and policymakers. Some sectoral and geographic targets were not met, reflecting structural constraints and market conditions in TCX geographies.

Description of programme
The Global Finance Programme is the UK’s flagship centrally managed programme for financial sector development. It aims to strengthen financial systems and unlock investment in emerging and developing economies by drawing on the UK’s comparative advantage in financial services, regulation and market infrastructure.

Within the GFP, the Financial Services COE provides access to TA and capacity building, delivered by a range of flagship UK agencies with a strong reputation in the financial sector. The FS COE was launched as a pilot in 2023, and has already demonstrated its value as a flexible, demand-led platform for deploying UK public, private and academic-sector expertise.

In 2024, the FSCOE partnerships included:

Bank of England (BoE)
Cambridge Centre for Alternative Finance (CCAF)
Green Finance Institute (GFI)
TheCityUK
- Consultative Group to Assist the Poor (CGAP) - pilot
- Alliance for Financial Inclusion (AFI) - pilot

In addition to the FSCOE, GFP support to TCX is aimed at helping to build sustainable capital markets by deepening the use of local currency in EDMEs. TCX offers innovative financial solutions such as hedging products to manage FX risks, as well as advocacy to promote the use of local currency in MDBs, DFIs and across the financial sector.

The programme delivered across four thematic pillars:

Improving Financial Sector Stability: Delivered primarily through the Bank of England, this pillar supports central banks and regulators to strengthen monetary policy frameworks, supervisory capacity and financial stability infrastructure. In 2024 to 2025, the Bank of England delivered thirty-nine formal activities, including deepened engagements in Ethiopia, Kenya, Nigeria and Bangladesh.

Increased Access to Global Capital Markets: This pillar supports the development of deeper, more accessible and more resilient capital markets in partner countries. It includes support for local currency financing through The Currency Exchange Fund (TCX), and new programming focused on financial centre development and sustainable finance. TheCityUK is supporting the development of international financial centres in Vietnam and Nigeria, including strategy design, legislative reform and institutional capacity building. In parallel, the Green Finance Institute (GFI) is working with governments in Indonesia and the Philippines to identify barriers to investment in priority sectors, co-develop financial instruments and strengthen enabling environments for climate-aligned capital mobilisation.

Promotion of Financial Technology: Led by CCAF, this pillar supports digital financial innovation, regulatory capacity building and knowledge exchange. CCAF delivered all agreed outputs, including the second State of SupTech report, expansion of the Regulator Knowledge Exchange platform and the first cohort of the Cambridge Open Banking and Open Finance Programme.

Banking: This pillar supports strategic engagement with financial institutions, regulators and market actors to promote inclusive and sustainable finance. While no longer a standalone delivery stream, banking sector engagement continues through the Bank of England’s technical assistance to central banks, and through TheCityUK’s work on financial centre development and investment promotion. CCAF also contributes to this pillar through its work on Open Frameworks, including Open Banking and Open Finance, which aim to improve interoperability, competition and consumer choice in digital financial services across emerging markets.

Programme Developments

After a period of transition, the programme is now delivered through two key channels, the Financial Services Centre of Expertise (COE) and The Currency Exchange Fund (TCX). Other components of GFP, including the partnership with the IMF Financial Sector Stability Fund (FSSF) and the Catalyst Fund ended this year as planned, enabling the programme to focus on development of the FS COE and retaining our support to TCX.

Two pilot partnerships with the World Bank’s Consultative Group to Assist the Poor (CGAP) and the Alliance for Financial Inclusion (AFI) were tested this year as part of the FS COE. However, as set out in Section C, it has been decided these pilots will not continue next year. While both pilots delivered on expectations, various factors (e.g. alignment of overarching GCAP results with the Global Finance Programme, and hurdles on the rapid deployment of technical assistance through AFI) mean there is a limited case for scaling up these pilots into FY25/26.

During the year, a new partnership with the Financial Conduct Authority (FCA) has been established. This will form part of the FS COE and will complement GFP’s offer to EDMEs on financial regulation and enhancing market integrity.

GFP Business Case Addendum
A new business case addendum is planned to extend the budget headroom for the programme and to enable continued delivery of the FSCOE under the Global Finance Programme. This will include increased ability for Posts to buy-in to the Centre of Expertise, in line with a wider shift across FCDO towards a re-defined central offer.

Review Score & Summary

This is GFP’s seventh Annual Review and covers activity and results from April 2024 to March 2025. The overall Output Score is A, meaning that the programme is meeting expectations.

FCDO Annual Review Scoring Rubric
Score Assessment	Threshold For Score
Outputs substantially exceeded expectation (A++)	>137.5
Outputs moderately exceeded expectation (A+)	>112.5
Outputs met expectation (A)	>87.5
Outputs moderately did not meet expectation (B)	>62.5
Outputs substantially did not meet expectation (C)	<62.5

Output	Output Description	Weighting (%)	Output Performance	Impact Weighted Score
1	Promotion of Financial Technology: / Cambridge Centre for Alternative Finance (CCAF)	20%	A	20
2	Promotion of Financial Technology: / Catalyst Fund (CF)	5%	A	5
3	Improving Financial Sector Stability: / Bank of England (BOE) Technical Assistance Partnerships	20%	A+	25
4	Improving Financial Sector Stability: / IMF Financial Sector Stability Fund (FSSF)	5%	A	5
5	Strengthening Capital Markets: / The Currency Exchange (TCX)	20%	B	15
6	Strengthening Capital Markets: / TheCityUK	10%	A+	12.5
7	Strengthening Capital Markets: / Green Finance Institute	10%	A+	12.5
8	Pilot partnerships: / Consultative Group to Assist the Poor (CGAP) / & Alliance for Financial Inclusion (AFI)	10%	A	10
	All Outputs	100%		105 (A)

There have been minor adjustments to the output weightings for this AR, specifically: i) reducing Catalyst Fund from 5% to 0%; ii) previous pilots from a collective from 10% to 20% (10% each); and iii) Including pilot partnerships with CGAP and AFI at a combined 10%. These adjusted weightings better reflect the activity and budget in the review period.

As noted in the previous annual review, this will be the final year of reporting for Catalyst Fund and the IMF FSSF.

Major lessons and recommendations for the year ahead

- Bank of England:
  - Continue working with the BoE to ensure strategic allocation of capacity across partnerships.
  - Explore opportunities to deprioritise or close weaker or underperforming relationships, reallocating resources to regional platforms (e.g. SADC, ASEAN, WAMU/BCEAO) where appropriate.
- Cambridge Centre for Alternative Finance (CCAF):
  - Engage early with CCAF to accommodate internal planning cycles and ensure timely agreement of activities and log frame.
  - Ensure future research and technical assistance are appropriately scoped to regional contexts and aligned with FCDO priorities.
  - Identify opportunities for follow-on engagement or peer learning where initial technical assistance has generated strong interest.

- The Currency Exchange:
  - FCDO should review the results framework with TCX, to ensure it accurately reflects FCDO priorities and TCX activity
  - FCDO should seek to leverage TCX’s expertise to support FCDO’s advocacy efforts to promote local currency finance solutions, including with respect to MDB reforms.
- General Programme Management:
  - Build out options to increase the utilisation of the FSCOE offer by developing a more where Posts can more easily ‘buy-in’ to the advice available through GFP partners
  - Strengthen results frameworks to reflect new programming and partner transitions.
  - Continue to align technical assistance more closely with FCDO’s private capital mobilisation agenda.
  - Capture and disseminate lessons from FSCOE partnerships to inform future Centre of Expertise development.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The GFP’s Theory of Change remains broadly valid, although the programme’s transition to focus on the FSCOE as the primary delivery vehicle means that the programme’s delivery model is evolving to reflect a more flexible, demand-led approach to deploying UK financial sector expertise. The programme continues to focus on strengthening financial systems and unlocking investment in emerging and developing economies, with an emphasis on upstream engagement, institutional capacity building, and enabling environments for inclusive and sustainable finance.

GFP delivers on the Theory of Change through the following channels:

Financial Stability: Stable financial systems are a prerequisite for inclusive growth and investment. The GFP’s financial stability pillar is grounded in the belief that upstream support to central banks and regulators can strengthen institutional resilience and reduce vulnerability to shocks. By improving monetary policy frameworks, supervisory capacity and crisis response mechanisms, the programme helps partner countries build the foundations for credible and effective financial governance. This work is particularly important in contexts where macroeconomic volatility and institutional fragility threaten development progress.

Capital Markets: Deep and resilient capital markets are essential for mobilising long-term investment and expanding access to finance. The GFP supports partner governments and market actors to strengthen enabling environments, improve regulatory frameworks and design financial instruments that attract private capital. This includes work on financial centre development, green finance architecture and blended finance solutions. The programme also recognises the importance of local currency finance in reducing exposure to exchange rate risk and enhancing financial system stability—especially in low-income and frontier markets.

Digital Finance: Digital financial infrastructure and innovation are increasingly central to financial sector development. The GFP promotes inclusive digital finance by supporting regulators, supervisors and market participants to adopt enabling technologies and frameworks. This includes work on open finance, supervisory technology (SupTech), and digital asset regulation. The programme’s approach combines research, peer learning and technical assistance to help partner countries build secure, interoperable and consumer-friendly digital ecosystems that expand access and improve efficiency.

Banking and Financial Sector Partnerships: The GFP continues to engage with financial institutions and sector stakeholders to promote inclusive and sustainable finance. While no longer a standalone delivery stream, this work is embedded across the programme’s pillars—particularly through central bank engagement, investment promotion, and support for open frameworks. These partnerships help align financial sector development with broader economic and social goals.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme remains on track to deliver against its intended outcomes. Most components met or exceeded expectations, with delivery aligned to the programme’s Theory of Change and evolving FSCOE structure.

CCAF delivered strongly across research, technical assistance, and peer learning. While some training programmes underperformed on completion rates, CCAF’s overall contribution to regulatory capacity building and digital infrastructure development remained significant. A new alumni impact survey and refinements to the mentorship model are expected to strengthen future delivery.

Catalyst Fund concluded all activities in March 2025. Loan reflows were managed in line with compliance standards, and the programme will no longer be reported on in future reviews.

The Bank of England continued to deliver high-quality technical assistance, with strong demand from partner central banks and high satisfaction scores. Engagements supported reforms in monetary policy, financial stability, and payments infrastructure. The Bank also began internal work to prioritise partnerships and manage strategic exits.

The IMF FSSF successfully concluded Phase I, meeting all agreed outputs. While no new funding is planned, the Fund’s diagnostics and follow-up TA contributed to strengthened financial stability frameworks in multiple jurisdictions.
TCX continued to perform strongly, with record hedging volumes and expanded advocacy efforts. While no new funding was disbursed, TCX remains on track to contribute to the programme’s long-term objectives on local currency finance and financial system resilience.

TheCityUK and Green Finance Institute (GFI) transitioned from pilot to core FS COE partners and moderately exceeded expectations. Both delivered credible, multi-country engagements that advanced national strategies and institutional reforms. While it is too early to assess long-term impact, early signs suggest strong alignment with the programme’s objectives on capital mobilisation and enabling environments.

CGAP and AFI completed short-term pilot partnerships. Both delivered on agreed outputs, with CGAP contributing to global guidance on open finance and women’s financial inclusion, and AFI producing regionally grounded diagnostics on SupTech and digital infrastructure. While both pilots delivered on expectations, no further work is anticipated for these partnerships. Team will keep opportunities for future engagement with CGAP and AFI under review.

Looking ahead, the programme will focus on refining its results framework, aligning delivery with FS COE priorities, and ensuring that new and existing partnerships are strategically targeted to maximise impact.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The programme should continue. It remains strategically relevant, technically sound, and well-positioned to respond to partner demand for financial sector expertise. Delivery across core and pilot components has been consistently strong, continuing to play a critical role in helping partner countries strengthen financial systems, mobilise investment, and manage economic shocks. Its upstream, demand-led model allows for agile, context-specific support, and its focus on institutional capacity building and enabling environments remains central to long-term development impact.

As the only centrally managed programme of its kind in HMG’s toolkit, the GFP offers a unique platform for deploying UK public, private and academic expertise in support of financial sector reform. It continues to deliver good value for money and remains in high demand across the FCDO network.

## C. DETAILED OUTPUT SCORING

Output Title	Promotion of Financial Technology: Cambridge Centre for Alternative Finance (CCAF)
Output number:		1	Output score:	A
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicator(s)		Milestone(s) for this review	Progress
Objective 1: Research & Advocacy Activities
Digital Public Infrastructure & Digital Financial Services: Regulatory Considerations Report		Publication of the report	Met expectation (Published)
Global Cryptoasset Regulatory Landscape Study - Emerging Practices and Early Lessons Learned		Publication of the report	Met expectation (Published)
State of Suptech Report		Publication of the report	Moderately did not meet expectations / (In progress, 95% complete, awaiting final data)
Objective 2: Regulator Knowledge Exchange (RKE) development
RKE Onboard Globally Influential Network	1 network onboarded	Met Expectations (Completed – GFIN onboarded)
Institutional Collaborations	2 EMDE institutions onboarded	Moderately Exceeded Expectations (Completed – 4 institutions onboarded)
Women’s Regulator Network	Network established	Met Expectations (Launch delayed, but number of partnerships & planned events exceed expectations
RKE Live Events	2 regional events delivered	Met Expectations (Completed – Singapore, Kigali)
Open Banking & Open Finance Readiness Assessment Tool	Tool launched	Met Expectations (Completed)

Objective 3: Capacity Building and Education
Cambridge Fintech and Regulatory Innovation Accelerator (CFTRI-A)	Train 82 learners, NPS ≥ 65	Moderately Did Not Meet Expectations (82 signed up, 76 completed, NPS 70)
Cambridge Open Banking and Open Finance Programme (COBOF)	Train 57 learners, NPS ≥ 65	Substantially Did Not Meet Expectations (48 signed up, 38 completed, NPS 68)
SupTech Frontiers	Train 57 learners, NPS ≥ 65	Substantially Did Not Meet Expectations (57 signed up, 45 completed, NPS 52)
Cambridge Digital Assets for Regulators (CDAR)	Train 110 learners, NPS ≥ 65	Moderately Did Not Meet Expectations (106 signed up, 98 completed, NPS 73)

Objective 4:
State Bank of Pakistan – Capacity Building	Train 30 SBP staff across 5 courses	Met Expectations (Completed)
State Bank of Pakistan – Technical Assistance	Deliver 3 workshops + follow-on TA	Moderately Exceeded Expectations (Completed – 6 workshops + research paper)
COMESA Business Council – Regulatory Gap Analysis	Deliver 2 gap analysis reports	Met Expectations (Completed)
Ukraine – Digital Assets Regulatory Framework Support	Deliver full TA workshop series	Met Expectations (Completed)

Note: FCDO and CCAF agree a fresh results framework at the beginning of each financial year for the forthcoming 12 months, reflecting the evolving nature of CCAF’s activity.

Briefly describe the output’s activities and provide supporting narrative for the score.

Objective 1: Research and Advocacy Activities
CCAF delivered two of three planned research outputs during the review period. The Digital Public Infrastructure & Digital Financial Services: Regulatory Considerations report and the Global Cryptoasset Regulatory Landscape Study were both finalised and disseminated. These reports contribute to the global evidence base on regulatory approaches to digital finance, with a particular focus on emerging markets and developing economies.

The State of SupTech 2024 report was not completed by year-end but is 95% finalised and expected to be published in early Q2 2025. CCAF describes this as the most comprehensive global assessment of supervisory technology to date. Collectively, these outputs are intended to support regulators in strengthening digital financial infrastructure and supervisory frameworks, in line with FCDO’s objectives on financial innovation and private capital mobilisation.

Objective 2: Regulator Knowledge Exchange (RKE) Development
The RKE platform continued to expand its reach and functionality, with membership growing to over 3,000 regulators globally. The onboarding of GFIN and four new institutional partnerships exceeded the year’s targets and reflects the platform’s growing role in facilitating peer learning and regulatory coordination. The RKE Live events in Singapore and Kigali were well attended, with participation significantly above the 50-person target, and provided opportunities for dialogue on topics such as digital assets and sustainable finance.

While the formal launch of the Women’s Regulator Network was delayed, CCAF established a strong foundation through partnerships with CGAP, Women’s World Banking, and WIRI, and has planned a series of events for the coming year. These activities contribute to the development of more inclusive and collaborative regulatory ecosystems.

Objective 3: Capacity Building and Education
CCAF’s four flagship training programmes attracted strong enrolment, but all fell short of their completion targets. While the CFTRI-A and CDAR courses achieved relatively high completion rates and strong Net Promoter Scores, the SupTech Frontiers course underperformed on both metrics. CCAF has taken steps to address these challenges, including refining its mentorship framework and implementing new scholarship management processes.

The launch of an alumni impact survey in June 2025 is a positive development and may help inform future improvements. These programmes remain a key mechanism for strengthening regulatory capacity in FCDO priority markets, and the integrated model — combining training with technical assistance — continues to offer a pathway to institutional impact.

Objective 4: Technical Assistance
CCAF delivered all planned technical assistance activities in Pakistan, COMESA, and Ukraine. In Pakistan, CCAF supported the State Bank of Pakistan with a two-phase programme covering sandboxes, digital assets, and open banking. The engagement included both workshops and written feedback and was supported by senior leadership at SBP. In COMESA, CCAF completed a regulatory gap analysis focused on consumer protection, data privacy, and KYC/AML, which was validated by the regional working group. In Ukraine, CCAF delivered a tailored workshop series on digital assets, including sessions on market monitoring, global regulatory practices, and EU legislation. These engagements were well aligned with FCDO priorities and demonstrate CCAF’s ability to respond to country-specific needs in support of regulatory reform and financial sector development.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

None.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The programme team should engage early with CCAF to accommodate the internal processes of partner institutions. It should also work with CCAF to ensure research and technical assistance are appropriately scoped and tailored to regional contexts and identify opportunities for follow-on engagement or peer learning where initial technical assistance has generated strong interest.

Output Title	Promotion of Financial Technology: Catalyst Fund (CF)
Output number:		2	Output score:	A
Impact weighting (%):		0	Weighting revised since last AR?	Yes – revised down as all tracked indicators were completed

Briefly describe the output’s activities and provide supporting narrative for the score.

As stated in the previous annual review, Catalyst Fund had achieved all of its milestones by the end of the FY2022–23 review period. From its inception to the conclusion of FCDO-funded activities, the programme supported 65 early-stage ventures across 14 emerging markets, reaching over 18 million users and catalysing more than $810 million in follow-on investment. Of these, 30 fintechs were accelerated with FCDO support between 2019 and 2022, raising $187.6 million and reaching 1.8 million users, over 550,000 of whom were active.

In FY2024–25, Catalyst Fund’s only remaining activity was the management of loan reflows under Catalyst 2.0. Twelve startups received zero-interest loans of approximately $100,000 each. By the end of the loan period, two companies had fully repaid, one had partially repaid, and three closed with no repayments. Six companies did not raise funding during the loan term. While repayment performance was low—reflecting persistent challenges in the fundraising environment—Catalyst Fund continued to provide investor engagement and visibility support. A total of $240,000 in reflows was redeployed to cover loan management and venture-building activities, with the remaining $960,000 written off in line with compliance standards. With the grant cycle concluding in March 2025, the loan component of the programme will now be formally closed.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

As noted in the previous annual review, this will be the final annual review reporting on the activities of Catalyst Fund, as all indicators pertaining to Catalyst Fund 2.0 have now been completed, and the Global Finance Programme has not funded Catalyst Fund 3.0.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

None.

Output Title	Improving Financial Sector Stability: Bank of England (BoE) Technical Cooperation with Central Banks
Output number:		3	Output score:	A+
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Objective 1: Outreach of activities
1.1. Number of delegates who took part in the activity	36.2 (last year’s average number of participants)	Moderately exceeded expectations (40.775)
1.2. Number of departments who took part in the activity	3	Moderately exceeded expectations (3.667)
1.3. Number of central banks who took part in the activity (regional only)	12.9 (last year’s number of participating central banks)	Moderately did not meet expectations (11)
1.4. Proportion of female staff taking part in the activity (%)	40	Met expectations (44.2)
1.5. Proportion of senior staff (Head of Division or above) (%)	25	Met expectations (27.179)
1.6. Proportion of participants from low income or fragile countries (%)	20	Moderately exceeded expectations (26.429)

2.1 Products of activities (delivered during/immediately after the activity)	Descriptive indicator	Met expectations / (TA products used in partner reforms incl. Ethiopia, Egypt, SADC)

3.1. Overall rating of the TA/training event by delegates (%)	75	Moderately exceeded expectations (89.649)
3.2. Relevance of the material/topic(s) covered (%)	75	Moderately exceeded expectations (92.111)
3.3. Extent to which the event(s) match their announced objectives (%)	75	Moderately exceeded expectations (88.973)
3.4. Extent of BoE experts' knowledge and command of their topic(s) (%)	75	Moderately exceeded expectations (94.486)

Briefly describe the output’s activities and provide supporting narrative for the score.

The indicators show that the Bank is successfully delivering its mission to change central banks’ behaviours so that they make more effective and credible central bank policy, in turn leading to improved monetary and financial stability as well as providing a supportive environment for private capital markets to develop. This year’s delivery reflected a mature and responsive programme, with the Bank adapting to new political contexts, deepening engagement with reform-minded institutions, and embedding its support in areas of strategic importance to both partner countries and the UK.

Objective 1: Outreach of Activities
The Bank’s outreach activities moderately exceeded expectations, with over 1,100 delegates engaged across 39 events. The programme expanded its reach to new partners including Ethiopia, Kenya, Bangladesh, and Nigeria, while maintaining strong engagement with traditional counterparts. Participation from low income and fragile states remained high, and departmental diversity and seniority of delegates met or exceeded targets.

The Bank’s ability to convene senior stakeholders and deliver peer-to-peer engagement was central to its impact. In several cases, outreach directly supported reform momentum, such as in Egypt where the Bank was entrusted to review a pre-publication monetary policy report, and in SADC where a crisis simulation exercise led to a Governor-level Lessons Learnt Report. These examples reflect the Bank’s credibility and its ability to deliver inclusive, strategically aligned outreach that supports institutional effectiveness.

Objective 2: Products of Activities
The Bank’s technical assistance products met expectations and were used strategically by central banks to support reform implementation. These included monetary policy models, supervisory frameworks, legal reviews, and strategic diagnostics. In Ethiopia, BoE input informed the design of the new Financial Stability Committee and contributed to the draft central bank proclamation. In Bangladesh, the Bank supported the implementation of a Prompt Corrective Action Framework. In Morocco, a jointly developed CBDC (Central Bank Digital Currency) model is being used to simulate macro-financial scenarios and inform policy design. Products were also reused across regional platforms such as ASEAN and SADC and were often co-produced with local counterparts to enhance ownership. Their uptake in IMF Board discussions and UK diplomatic engagements further demonstrates their relevance and influence.

Output 3: Engagement / Satisfaction of Recipient Staff
The Bank’s technical assistance continued to receive high satisfaction ratings, with all engagement indicators moderately exceeding expectations. Participants consistently rated the relevance, clarity, and delivery of sessions highly, with particular appreciation for the depth of expertise and the peer-to-peer format. These engagements often involved strategic dialogue with senior officials and covered complex topics such as inflation targeting, seigniorage accounting, and financial stability governance. Feedback indicated that the Bank’s support enhanced participants’ confidence and capability to enact change, with many reporting that the content would directly influence their department’s future work. The Bank’s ability to deliver trusted, high quality, and context specific support continues to underpin its reputation as a leading provider of central banking technical assistance.

Some common key themes from these activities include:

- Strengthening monetary policy frameworks, particularly in newer partnerships. The Bank supported transitions toward inflation targeting in Bangladesh, Egypt, Kenya and Nigeria, and provided modelling, forecasting and communications support aligned with central bank reform agendas.
- Reforms to payment systems, a growing area of demand. The Bank supported the development of a cross-border payments roadmap for SADC, advised on fast payment systems in Kenya, and continued its work with ASEAN and Bank Al-Maghrib on CBDC design and interoperability.
- Enhancing financial stability and crisis management, including support to establish new financial stability functions in Ethiopia and the Philippines, delivery of a crisis simulation exercise for 14 SADC central banks, and ongoing regional supervision work led by the Bank of Ghana.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

None

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on last year’s recommendations:
In line with the recommendations of last year’s annual review, FCDO has worked with the BOE to be aware of opportunities for additional impact (e.g. inputting into IMF missions with the lessons learned from activities undertaken through its partnerships). The BOE has also begun an internal exercise to understand how to assess which partnerships would be most appropriate to close should the need present itself.

For the year ahead:
The FCDO programme team should work with the BOE to continue exploring the strategic allocation of BOE partnerships and identify opportunities to:
- Deprioritise or close weaker or underperforming relationships,
- and (accordingly), reallocate resources to an increased focus on regional platforms (e.g. SADC, ASEAN, WAMU/BCEAO).
Output Title	Improving Financial Sector Stability: IMF Financial Sector Stability Fund (FSSF)
Output number:		4	Output score:	A
Impact weighting (%):		5%	Weighting revised since last AR?	Yes – in line with the end of Phase I.

Indicator(s)	Previous Year	Progress
Objective 1: Diagnostic and Reform Planning
Number of financial sector stability review (FSSR) diagnostics completed	2, with 2 in progress	3, more diagnostics completed under Phase II but not FCDO funded
Number of FSSR missions participated in	2	6
Objective 2: Implementation of Reform and Technical Assistance
Number of FSSR follow-up technical assistance (TA) projects progressed	12 with 3 in preparation	12 / 7 completed and 5 extended into Phase 2) / 4 new Phase II projects not counted
Number of Long-term experts engaged	7	7
Objective 3: Capacity Building and Data Strengthening
Number of financial soundness indication (FSI) TA missions conducted	9	3, more completed for Phase II
Number of balance-sheet approach (BSA)-related TA missions conducted	12	3
Number of participants reached through online or face to face training (not including country specific TA).	4,399 (2500 BIS-IMF Supervisory and Regulatory Online Course, 1,799 Cyber Risk Supervision Online Course, 100 Annual Cybersecurity Supervision Workshop)	2,069 / 522 BIS-IMF Supervisory and Regulatory Online Course, / 1,450 Cyber Risk Supervision Online Course, / 97 the Annual Cybersecurity Supervision Workshop

Briefly describe the output’s activities and provide supporting narrative for the score.

The IMF’s Financial Sector Stability Fund (FSSF) continued to deliver high-quality, timely support to strengthen financial stability frameworks in low- and lower-middle-income countries, through completion of its Phase I activities. All outputs under this review period were assessed as having been met (A).

Objective 1 (Diagnostic and Reform Planning), the FSSF completed three FSSR diagnostics during the review period, exceeding the previous year’s milestone of two. The IMF’s Statistics Department (STA) participated in six FSSR missions, up from two the previous year, ensuring that statistical capacity development was embedded from the outset. This reflects strong demand for diagnostic engagement and effective coordination between the IMF’s Monetary and Capital Markets (MCM) and Statistics (STA) departments.

Objective 2 (Implementation of Reform and Technical Assistance), the FSSF maintained momentum in delivering follow-up technical assistance. Twelve FSSR follow-up TA projects were progressed, with seven completed and five extended into Phase II. The number of long-term experts engaged remained steady at seven, ensuring continuity and deep engagement with country authorities. This sustained delivery is notable given the wind-down of Phase I and the absence of new contributions from members in FY24.

Objective 3 (Capacity Building and Data Strengthening), the Fund delivered three FSI TA missions and three BSA-related TA missions within the Phase I window. While lower than the previous year, this reflects a natural tapering as Phase I concluded. Importantly, 2,069 participants were reached through multi-country training activities, including the BIS-IMF Supervisory and Regulatory Online Course, the Cyber Risk Supervision Online Course, and the Annual Cybersecurity Workshop. These activities continue to build foundational knowledge and support follow-up TA missions.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Phase I concluded in December 2024. FCDO has decided not to continue with the FSSF, making this the final time it is reported in a GFP annual review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

None

Output Title	Strengthening Capital Markets: The Currency Exchange (TCX)
Output number:		5	Output score:	B
Impact weighting (%):		20	Weighting revised since last AR?	Yes – revised down due to removal of the IFC Facility

Indicator(s)	Milestone(s) for this review (target/delivered)	Progress
Objective 1: Expanding Local Currency Hedging and Market Reach
Total volumes of new hedging capacity created (attributable to FCDO investment)	N/A
Maturity of hedging contracts written by TCX	3.5	Moderately exceeded expectations (3.7)
Volume of hedging contracts written in lower to lower-middle income countries	70%	Moderately did not meet expectations / (Least developed countries: 11.5% / Lower middle-income countries: 41% / Total: 52.5% [following DAC list])
Number of local currency bonds issued (off and on-shore) to free up capacity and develop local capital markets	40	Moderately exceeded expectations (47)
Objective 2: Supporting Sectoral Diversification and Development Impact
Sector diversification of new production (/business): SME finance allocation[1]	30%	Met expectations (32.6%)
Sector diversification of new production (/business): SE4ALL / Climate or sustainable projects allocation	5%	Substantially did not meet expectations (3.8%)
Sector diversification of new production (/business): Other infrastructure allocation[2]	5%	Met expectations (5.2%)
[1] Refers to proportion of new TCX business that is for SME financing. TCX have sought to diversify their business away from the heavy reliance on MSMEs towards larger financial institutions and others.
[2] Refers to proportion of new TCX business for non-renewable/green infrastructure which are reliant on hard currency, such as housing, social infrastructure and transport.

Briefly describe the output’s activities and provide supporting narrative for the score.

TCX remains a core GFP investment, supporting local currency finance and capital market development in frontier and emerging markets. In 2024, TCX delivered a second consecutive record year in hedging volumes and expanded its engagement with institutional investors and policymakers. While some sectoral and geographic targets were not met, this reflected structural constraints and market conditions in TCX geographies. The results framework is being reviewed to better reflect TCX’s evolving activities and FCDO priorities, including the growing importance of sovereign hedging, bond issuance, and advocacy.

Objective 1: Expanding Local Currency Hedging and Market Reach
In 2024, TCX hedged 2.76 billion US dollars, a 20 percent increase from 2.3 billion in 2023, marking the highest annual volume in its history. This growth was supported by improved global capital markets and the full deployment of the EU’s original Pricing Facility, which helped unlock demand in higher-risk jurisdictions. The weighted average maturity of contracts rose to 3.7 years, up from 3.6 years last year and exceeding the FCDO’s 3.5-year benchmark. TCX also supported 47 local currency bond issuances, up from 41 in 2023, and on-sold 1.7 billion US dollars in currency risk to private investors, compared to 1 billion the previous year. These activities contributed to freeing up balance sheet capacity and deepening local capital markets.

However, the share of hedging in least developed and lower-middle income countries declined to 52.5 percent, down from 59.1 percent in 2023 and below the FCDO’s 70 percent target. This shortfall was driven by flat activity in Sub-Saharan Africa, where macroeconomic fragility and high interest rates continued to suppress demand, while growth was concentrated in Asia (up 93 percent), Latin America (up 88 percent), and the Middle East and North Africa (up 68 percent). TCX’s regional diversification reflects both opportunity and constraint, and the fund’s continued ability to on-sell risk to private investors demonstrates its growing credibility in global markets.

Objective 2: Supporting Sectoral Diversification and Development Impact
TCX’s performance on sectoral diversification was mixed. The SME finance allocation rose to 32.6 percent in 2024, up from 23.6 percent in 2023 and well above the FCDO’s revised 30 percent target. This reflects continued demand from financial institutions serving micro and small enterprises, particularly in Asia and Latin America, and builds on TCX’s longstanding strength in this segment. However, the share of hedging allocated to climate-aligned projects fell to 3.8 percent, down from 4.5 percent last year and below the 5 percent target, while infrastructure rose modestly to 5.2 percent from 3.7 percent, just meeting the revised target but still below the 10 percent ambition set in 2023. These shortfalls reflect limited borrower demand and structural barriers in these sectors, including the need for concessional finance, complex structuring, and regulatory uncertainty.

TCX’s own reporting notes that while it has expanded its offering to include sovereign transactions and deliverable products, uptake in climate and infrastructure remains constrained. To address this, TCX has stepped up its advocacy and market-building efforts, including participation in the G20, IMF and World Bank meetings, and the launch of new EU-backed Pricing and Capacity Facilities under EFSD+. These facilities, totalling 400 million euros, are designed to support greater uptake in high-risk and climate-aligned sectors and are expected to play a more prominent role in 2025 and beyond.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This output’s weighting has been revised down to reflect the closure of the IFC Facility noted in the previous annual review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

For the year ahead, the team should continue to support TCX as it seeks to grow. Leverage TCX’s expertise to support FCDO’s advocacy efforts to promote local currency finance solutions, including with respect to MDB reforms.

The team should also review the results framework with TCX, to ensure it accurately reflects FCDO priorities and TCX activity, and so that it includes an indicator tracking loan interest payments.

Output Title	Strengthening Capital Markets: TheCityUK
Output number:		6	Output score:	A+
Impact weighting (%):		10%	Weighting revised since last AR?	Yes – revised up, in line becoming a core partner.

Indicator(s)	Milestone(s) for this review	Progress
Objective 1: Vietnam International Financial Centre
Final strategy and Politburo approval	Strategy submitted; Politburo decision	Moderately exceeded expectations (Approved Nov 2024; dual-city model agreed)
Stakeholder consultations and Resolution development	Consultations held; Resolution drafting initiated	Moderately exceeded expectations (Consultations completed; drafting began mid-2024; legislative sub-group formed)
Capacity building and additional engagement	One FDI training; initial workshops	Moderately exceeded expectations (Two FDI trainings; 100% reported ≥70% knowledge gain; extra sessions delivered)
Objective 2: Nigeria International Financial Centre
Working group and sub-working groups established	Main working group formed	Moderately exceeded expectations (Main group + 3 sub-groups formed; 2–3 meetings each)
Final report and educational engagement	Report submitted; initial workshops	Moderately exceeded expectations (Report approved; extra materials and sessions delivered)
Federal-level engagement and strategic integration	Initial federal outreach	Moderately exceeded expectations (Presidential Advisor support; Executive Order signed; IFC in national plans)

Briefly describe the output’s activities and provide supporting narrative for the score.

TheCityUK moderately exceeded expectations in delivering targeted support to Vietnam and Nigeria on international financial centre (IFC) development. Both strands of work advanced strategic milestones, demonstrated strong partner engagement, and aligned with UK objectives on trade and investment. Delivery was timely, adaptive, and well-coordinated, justifying an overall output score of A+ (moderately exceeding expectations).

Objective 1: Vietnam – International Financial Centre
TheCityUK’s Phase III support to the Government of Vietnam moderately exceeded expectations. The final strategy was approved by the Politburo ahead of schedule, with agreement on a dual-city IFC model. Consultations with senior stakeholders were extensive, and the drafting of the Resolution began significantly earlier than planned, supported by the formation of a legislative sub-working group. Two FDI trainings were delivered in the UK, with all participants reporting strong knowledge gains, and additional capacity-building sessions were held. The programme also adapted effectively to institutional restructuring within the Vietnamese government, maintaining delivery momentum and reinforcing UK-Vietnam economic cooperation.

Objective 2: Nigeria – International Financial Centre
TheCityUK’s Phase I engagement in Nigeria also moderately exceeded expectations. A main working group and three sub-groups were established, enabling structured engagement across key themes. The final report was approved by the Lagos International Financial Council (LIFC) and complemented by additional educational materials and workshops to address stakeholder knowledge gaps. The project secured high-level political support, including from a senior Presidential Advisor, and the LIFC was formally integrated into national and state development plans. These achievements reflect a well-executed first phase, with strong alignment to Nigeria’s reform agenda and UK strategic interests.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Recognising that TheCityUK’s had successfully operated as an FSCOE pilot partner through the two years, we have considered them a core partner of the FSCOE since the start of FY25.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

None

Output Title	Strengthening Capital Markets: The Green Finance Institute
Output number:		7	Output score:	A+
Impact weighting (%):		10%	Weighting revised since last AR?	Yes – revised up, in line becoming a core partner.

Indicator(s)	Milestone(s) for this review	Progress
Objective 1: Indonesia
Workstream 1: Sustainable Finance Committee (SFC) institutionalisation	White Paper finalised and disseminated; SFC governance inputs reflected in draft regulation	Moderately exceeded expectations (White Paper finalised and shared with MoF, OJK, and BI; used as reference for upcoming regulation; high-level alignment secured)
Workstream 2: PT SMI Trust Fund design	Advisory delivered on fund structure, risk-sharing tools, and pipeline development	Met expectations (Credit risk frameworks revised; blended finance models scoped; initial project pipeline identified)
Objective 2: Philippines
Workstream 1: Sectoral finance diagnostics (transport and waste)	Diagnostics completed; financial interventions prioritised; pilot opportunities identified	Moderately exceeded expectations (Diagnostics completed; 40+ consultations; validation event held; pilot pathways scoped)
Workstream 2: Green Force evolution support	Technical input provided to align sector pilots with Green Force platform	Met expectations (Recommendations informed Green Force reform planning; coordination with BCG-led platform ongoing; publication delayed due to political transition)

The Green Finance Institute moderately exceeded expectations in delivering targeted support to the Philippines and Indonesia on sustainable finance architecture and sectoral capital mobilisation. In both countries, GFI demonstrated strong institutional engagement, deepened public–private dialogue, and delivered credible, context-specific recommendations. Overall, progress was assessed as justifying an overall output score of A+ (moderately exceeding expectations).

Objective 1: Indonesia
The Green Finance Institute’s engagement in Indonesia moderately exceeded expectations. Building on last year’s pilot, GFI finalised and disseminated the Sustainable Finance Committee (SFC) White Paper, which is now being used as a reference for forthcoming government regulation. High-level alignment was secured with the Ministry of Finance, Bank Indonesia, and the Financial Services Authority. In parallel, GFI delivered institutional advisory support to PT SMI, revising credit risk frameworks and advancing the design of a blended finance Trust Fund. Sectoral coalitions were initiated in green building, transport, and waste, with strong backing from industry groups and government stakeholders. These activities reflect a maturing programme of work that is shaping national sustainable finance infrastructure and enabling scalable investment pathways.

Objective 2: Philippines
The Green Finance Institute’s work in the Philippines also moderately exceeded expectations. Stage 1 diagnostics were completed for the waste and transport sectors, supported by over 40 stakeholder consultations and a high-level validation event co-hosted with the Department of Finance and Climate Change Commission. The resulting recommendations informed the government’s planning for Green Force reform and laid the groundwork for pilot financial interventions. While formal publication of the report was delayed due to a cabinet reshuffle, GFI maintained momentum through interim outputs and continued engagement. The programme’s sector-specific approach and early alignment with government priorities have positioned it well for implementation in the next phase.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Recognising that The Green Finance Institute had successfully operated as an FSCOE pilot partner through the two years, we have considered them a core partner of the FSCOE since the start of FY25.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

None

Output Title	Pilot Partnerships: The Consultative Group to Assist the Poor (CGAP) & Alliance for Financial Inclusion (AFI)
Output number:		8	Output score:	A
Impact weighting (%):		10	Weighting revised since last AR?	No

Note: As these two small interventions were established at pace during the review period and are designed to inform potential design of the FS CoE, formal results frameworks were not finalised prior to work commencing. Instead, deliverables were agreed upon, against which these delivery partners are measured below. The FS COE will continue testing new partnerships in this manner in order to broaden its development toolkit and expand its offer.

Briefly describe the output’s activities and provide supporting narrative for the score.

Two pilot partnerships were delivered in FY24/25 with CGAP and the Alliance for Financial Inclusion (AFI). Both met expectations, delivering timely outputs and demonstrating strong alignment with FCDO priorities. Each pilot laid a credible foundation for future collaboration and contributed to the FS CoE’s strategic aims around inclusive finance, digital transformation, and regulatory innovation.

Pilot 1: CGAP
CGAP’s pilot partnership met expectations. The initiative advanced thought leadership across key themes including open finance, climate resilience, women’s financial inclusion, and outcome measurement. Highlights included the launch of global guidelines on open finance, the development of the Impact Pathfinder platform, and a new whole-of-market approach to women’s financial inclusion piloted in India and Morocco. CGAP also deepened its work on inclusive climate finance and digital consumer protection, with frameworks now being tested in Rwanda and Peru. The partnership demonstrated CGAP’s continued relevance and influence in shaping inclusive finance agendas globally.

Pilot 2: AFI
AFI’s pilot partnership also met expectations. The project delivered two regionally grounded diagnostics and implementation roadmaps—one focused on SupTech infrastructure in the Pacific, and the other on inclusive digital infrastructure in South Asia. Both components were co-developed with member institutions and validated through regional workshops and training sessions. Despite a compressed timeline, all deliverables were completed and endorsed, with strong member engagement and institutional ownership. The pilot has positioned AFI and its regional platforms (PIRI and SARFII) for a next phase focused on implementation and regulatory reform.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

While both pilots delivered on expectations, various factors (e.g. alignment of overarching GCAP results with the Global Finance Programme, and hurdles on the rapid deployment of technical assistance through AFI) mean there is a limited case for scaling up these pilots into FY25/26. No further work is therefore currently anticipated for these partnerships, althoughopportunities for future engagement with CGAP and AFI will be kept under review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

None. Pilots will not be taken forward in FY25/26

## D: VALUE FOR MONEY

Key cost drivers and performance

VfM performance compared to the original VfM proposition in the business case

To assess the ongoing value for money of the Global Finance Programme, the basis used is the PrOF Guide on Value for Money, including its ‘five Es’ model:

Economy: Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency: How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness: How well are the outputs having the intended effect? (‘Spending wisely’)
Equity: How fairly are the benefits distributed? (“spending fairly”)
Cost-Effectiveness: What is the intervention’s ultimate impact on our foreign policy objectives, relative to the inputs that we or our agents invest in it?

An overview is given below for components of the programme in the context of this guide.

Economy
The programme continues to demonstrate strong economy by sourcing high-quality inputs from UK public institutions (e.g. Bank of England, Cambridge University), academic centres, and not-for-profit organisations. These partners offer globally respected expertise at a fraction of the cost of commercial alternatives. The use of FCDO staff for programme management — rather than outsourcing — ensures alignment with HMG remuneration and travel policies and avoids unnecessary overheads. Co-funding arrangements, such as the Gates Foundation’s $990,000 investment in CCAF’s Regulatory Knowledge Exchange (RKE), has further leveraged FCDO’s resources. Across the programme, delivery partners have delivered within budget, and there is no evidence of waste or excessive input costs. The lean delivery model used by GFI and TheCityUK in Nigeria and Vietnam — leveraging pro bono expertise and in-kind support — also reflects strong economy.

Efficiency
Efficiency has been strengthened through adaptive delivery, strategic targeting, and the use of scalable platforms. The Bank of England’s triaging system ensures that technical assistance is directed to reform-minded institutions, while regional platforms (e.g. SADC, ASEAN) allow for economies of scale. CCAF’s digital-first tools — including the RKE, online training, and toolkits — enable broad reach at low marginal cost, with over 3,000 regulators now engaged globally. GFI and TheCityUK delivered multi-country engagements within tight timeframes, despite political transitions and institutional restructuring. CGAP and AFI delivered regionally grounded diagnostics and roadmaps with limited funding and short lead times. Across the programme, delivery partners have shown the ability to convert inputs into outputs efficiently, with minimal resource wastage and strong responsiveness to evolving demand.

Effectiveness
Most components met or moderately exceeded expectations, with clear evidence that outputs are contributing to intended outcomes. The Bank of England delivered 39 formal activities, with high satisfaction scores and documented uptake of its technical assistance in central bank reforms in Ethiopia, Egypt, Bangladesh, and Nigeria. CCAF met or exceeded most of its logframe targets, with its research, technical assistance, and training programmes supporting regulatory innovation in Pakistan, Ukraine, and COMESA. GFI’s work in Indonesia and the Philippines informed regulatory reforms and pilot investment pathways in climate-aligned sectors. TheCityUK’s work in Vietnam and Nigeria led to the approval of a dual-city IFC strategy and integration of IFC development into national and state plans. CGAP’s work on open finance and women’s financial inclusion, and AFI’s diagnostics on SupTech and digital infrastructure, also contributed to institutional change. The programme’s ability to adapt to shifting political contexts and maintain delivery momentum has been a key factor in its effectiveness.

Equity
The programme maintains a strong equity focus, ensuring that benefits reach underserved populations and institutions. CCAF’s RKE platform is accessible to regulators in developing countries, with 75% of members from EMDEs and 45% women. The Bank of England’s outreach included a high proportion of participants from low-income and fragile states, and its regional workshops enabled participation from smaller central banks. CGAP’s pilot of a whole-of-market approach to women’s financial inclusion in India and Morocco, and AFI’s training on cybersecurity and consumer protection, addressed the needs of vulnerable groups. GFI’s work in the Philippines and Indonesia targeted underserved sectors such as waste and transport, and supported inclusive green finance. Across the board, delivery partners have demonstrated a commitment to inclusive engagement and equitable access to knowledge, tools, and policy influence.

Cost-Effectiveness
The programme continues to represent good value for money. It delivers strategic impact across financial stability, fintech, capital markets, and climate finance, with relatively modest budgets and a lean delivery model. Most components are achieving their output indicators and contributing to FCDO’s development strategy and White Paper commitments. The Bank of England’s peer-to-peer model and CCAF’s digital platforms offer high-impact, scalable delivery at low marginal cost. TheCityUK and GFI delivered credible, multi-country engagements that are already influencing policy and institutional reform. The programme also delivers diplomatic benefits, strengthens UK institutional partnerships, and remains in high demand across the FCDO network. Its flexible, upstream engagement model allows for tailored support that maximises impact per pound spent, and its internal governance and delivery structures continue to support disciplined, results-focused implementation.

Assessment of whether the programme continues to represent value for money

The GFP continues to offer strong value for money. Delivery has been consistently high across core components, with most partners meeting or exceeding expectations. The programme maintains low delivery costs, leverages co-funding and pro bono support, and delivers strategic impact across financial stability, fintech, capital markets, and climate finance. It remains well-aligned with FCDO priorities, in high demand across the network, and continues to deliver both development and diplomatic returns at modest cost.

E: RISK

Overview of risk management
The Risk Register has been updated to reflect current considerations.

The overall programme risk remains moderate, consistent with previous years. Resourcing (People) continues to impact delivery and remains a significant risk. Recruitment is underway, however timely onboarding processes will mean capacity constraints will continue for some time. The limited headroom in the Business Case (Programme Delivery) presents a major risk, with mitigation in place to control in-year costs and assess opportunities in line with strategic priorities. a A Business Case addendum is being developed to support the FS CoE and enable greater post buy-in. The programme team continue to work alongside delivery partners to mitigate risks and reduce the likelihood of risks occurring.

Risk Category	Current Appetite Level (Residual Risk)	Description
Strategy and Context	Receptive (Moderate)	Effective financial sector development is aided, among other things, by domestic political will, financial stability, sensitivity to the local context, a stable macroeconomic environment (including debt sustainability), and a recognition by local stakeholders that activity in this space (such as regulatory reforms) deliver impact with a lag. Many of these factors are outside of the programme’s control, and so a receptive level of risk appetite is considered appropriate. The team seeks to mitigate these risks through networking including with FCDO Posts, specifically on CoE buy-in, and adopting a diverse portfolio of programming to minimise exposure to macroeconomic shocks in a particular country or region. The residual risk is moderate.
Policy and Programme Delivery	Cautious (Moderate)	This category refers to the potential for the programme, or components of it, to underperform due to factors such as poor programme design, weakness in implementation, commercial mismanagement, a lack of resourcing, or inadequate oversight. There has been a lack of resources in the Programme team to improve performance and increase ambition, however the programme team is working to ensure high impact interventions are completed with value for money a priority. The residual risk is moderate.
Public Service Delivery and Operations	Cautious (Minor)	This programme focuses on delivering development impact through allocation and use of ODA. Operational risks may arise within FCDO support functions such as Finance or service providers assisting with e.g. disbursement of funds. This is mitigated through FCDO’s usual processes, including training courses, updated guidance and updated systems.
People	Cautious (Moderate)	The programme is dependent on having the necessary personnel both among the programme team and delivery partners. Recruitment is ongoing and the FCDO programme team will have increased capacity and resources in the coming year but for this review period the risk appetite remains cautious. The residual risk is moderate.
Financial and Fiduciary	Cautious (Moderate)	Risks covered here include financial mismanagement or fraud by programme stakeholders including implementing partners, as well as budget and funding uncertainties. Due diligence has been completed for all delivery partners, with each partner holding the relevant policies and processes in place. The programme team frequently discuss the zero tolerance to inaction on fraudulent behaviour. Risks around budgets remain elevated, however, the programme team is mitigating this through clear communication and expectation management with implementing partners and developing country counterparts. The residual risk is moderate.
Safeguarding	Cautious (Moderate)	This category refers to risks arising from failure to establish and maintain strong safeguards to prevent harm to the programme team, programme beneficiaries, implementing partner staff, local communities, the environment, or others. The programme has a cautious appetite regarding these risks. While these risks remain present, they are minimised somewhat by the upstream nature of much of the programme’s activities. The team ensures implementing partners have appropriate policies in place regarding SEAH and whistleblowing and monitors this issue closely. The residual risk is moderate.
Reputational	Cautious (Minor)	This category refers to risks arising from programme failures or actions that could damage FCDO’s or the UK’s reputation. The programme has a cautious appetite for reputational risk. The residual risk is minor.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The Global Finance Programme continues to operate as a standalone programme under FCDO since funding ceased under the Prosperity Fund on 31st March 2021. This reporting period has seen the programme extend agreements with the Bank of England and the Cambridge Centre for Alternative Finance as well as respond to cross-FCDO work on Centres of Expertise – an initiative designed to respond to demands of the network and partner countries. The programme received additional RDEL funding to spend across core activities and interventions through the financial services pillar of the COEs.

An initial process of early engagement was completed with priority posts, as defined by FCDO’s Economic Development and Partnerships Directorate, to understand areas of interest. There were challenges onboarding delivery partners due to the mid-year confirmations of interventions creating tight time frames. Delivery partners responded well to the delays and ensured they were ready to action plans once agreements were signed. CCAF also welcomed the additional demands from post through the CoE and remained flexible despite the challenges of delays and approval chains.

As was the case in FY24, the programme team had resource and capacity changes throughout the year due to staff turnover, in turn shifting the management of relationships with partners. Work is in progress on a new business case to deliver further technical assistance in future years, although the timeline for this is dependent on factors including programme team resources and outer year budgets.

The Bank of England partnership (Memorandum of Understanding) is funded through payments made quarterly in arrears and based upon an agreed invoicing schedule. The project is overseen by a steering committee comprised of BOE and FCDO staff, which meets quarterly.

University of Cambridge partnership, acting through CCAF, is funded through an Accountable Grant Agreement. Payments are made quarterly in arrears and reporting has been generally timely and detailed. CCAF maintains a proactive dialogue on risk and incorporates any updates to their delivery chain map in quarterly reports. CCAF has been very responsive to shifting priorities and budget changes.

TheCityUK partnership is funded through an Accountable Grant Agreement. Payments are made quarterly in arrears, with financial and narrative reporting submitted in line with FCDO requirements. TheCityUK has maintained timely reporting and demonstrated strong responsiveness to evolving programme & post priorities.

The Green Finance Institute is funded through an Accountable Grant Agreement. Payments are made quarterly in arrears, with regular reporting on delivery, risk, and financial performance. GFI has provided timely and detailed updates, adapted effectively to political and institutional changes in delivery countries, and maintained close coordination with FCDO throughout the review period.

The IMF Financial Sector Stability Fund is run as a multi-donor fund under the IMF’s Framework Administered Account for Selected Fund Activities. The basis for the financial arrangements between FCDO and the IMF is a Letter of Understanding, and HMG’s contribution is subject to standardised terms and conditions.

TCX: In 2019 FCDO made a £31 million development capital investment in TCX in the form of a convertible subordinated loan. TCX received no additional programmatic spend this period. FCDO’s subordinated convertible loan to TCX represents an asset for FCDO, requiring annual valuation. We are working on providing future valuations within a department-wide contract. TCX continues to pay FCDO the interest income as stipulated in the subordinated convertible loan agreement in a timely manner. The programme team will continue to monitor these interest payments alongside FCDO Finance. These reflows score as negative RDEL and are non-ODA.

Catalyst Fund programme was funded through an Accountable Grant between Rockefeller Philanthropy Advisers (RPA) and FCDO. There has been no funding dispersed during this review period, and no further funding is anticipated. The project was previously overseen via quarterly meetings comprised of RPA, Catalyst Fund, FCDO staff and co-funder JPMC. As the projects reporting ended in December 2024, engagement will conclude as of this annual review.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring and Evaluation: Monitoring activities were embedded across all programme components and informed both strategic decisions and delivery adjustments. The Bank of England maintained quarterly steering committee meetings and used participant feedback to refine its technical assistance model. CCAF collected performance data across its training and technical assistance engagements, including launching an alumni impact survey in June 2025.

TheCityUK and the Green Finance Institute conducted extensive stakeholder consultations and validation events in Vietnam, Nigeria, Indonesia and the Philippines, which shaped programme design and ensured alignment with national priorities.

CGAP and AFI pilots were monitored through deliverable-based frameworks, with regional workshops and member feedback informing outputs. The Annual Review process included inputs from across the FCDO programme team, delivery partners, and relevant posts, with scoring informed by logframe data and partner reporting.

Evidence: The programme continued to generate and apply evidence to inform delivery. CCAF published two major research reports—on digital public infrastructure and cryptoasset regulation—and nearly completed its State of SupTech 2024 report. These outputs contributed to the global evidence base on digital financial regulation and were used to inform technical assistance in Pakistan, COMESA and Ukraine.

CGAP launched global guidelines on open finance and piloted new approaches to women’s financial inclusion, while AFI delivered regionally grounded diagnostics on SupTech and digital infrastructure. Across the programme, evidence was used to refine interventions, support policy dialogue, and inform future programming. Monitoring data was disaggregated where possible, and inclusive finance remained a cross-cutting priority.

Learning: Learning was captured through partner reporting, stakeholder engagement, and internal programme reflection. CCAF’s alumni survey and mentorship review informed improvements to its training model. The closure of underperforming components prompted lessons-learned exercises to inform future programming.

The Bank of England initiated an internal review of partnership prioritisation, and results frameworks are being revised to better reflect FCDO priorities. CGAP and AFI pilots provided insights into rapid deployment models and regional engagement strategies. These learning processes have shaped recommendations for the year ahead, including refining results frameworks, aligning activities with FCDO priorities, and exploring strategic exits from underperforming partnerships.

Learning Aims for the Year Ahead: In the coming year, the programme will focus on:
- Build out options to increase the utilisation of the FS CoE offer by developing a more where Posts can more easily ‘buy-in’ to the advice available through GFP partners
- Strengthening results frameworks to reflect new programming and partner transitions.
- Continue to align technical assistance more closely with FCDO’s private capital mobilisation agenda.
- Enhancing the strategic allocation of resources across delivery partners.
- Capturing and disseminating lessons from FSCOE partnerships to inform future Centre of Expertise development.

Date of last narrative financial report	N/A. Received quarterly.	Date of last audited annual statement	25/09/2025