## Annual Review Template

Title: Better Assistance in Crises (BASIC)
Programme Value £ (full life): £20,500,000.00		Review date: November 2025
Programme Code: 300467	AMP start date: 30 October 2018	AMP end date: 31 March 2026

Summary of Programme Performance
Year	2019	2020	2021	2022	2023	2024	2025
Overall Output Score	A	A	A	B	A	A+	A
Risk Rating	Moderate	Moderate	Major	Major	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/44086905.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0005744.xlsx

A. SUMMARY AND OVERVIEW
Description of programme

The Better Assistance in Crises (BASIC) programme aims to help poor and vulnerable people cope better with crises and meet their basic needs through more effective social assistance in contexts of recurring shocks, protracted conflict and forced displacement. The programme supports new and/or improved use of social protection approaches during crisis by providing expert advisory, capacity-building, learning, coordination, high-level policy influencing and research services.

Since the programme’s inception, levels of humanitarian need and the frequency of crises have increased. Crises are most often protracted or recurrent, whilst humanitarian financing and delivery models are mainly short-term and reactive. Humanitarian finance is also oversubscribed with demand for assistance far exceeding available resources. Social protection offers a critical tool to bridge the gap to humanitarian assistance, both by responding to needs as well as building resilience in crisis contexts. Seven years of the BASIC programme has positioned the FCDO as a thought leader on social protection in crisis settings and offers a template for catalysing change with relatively small, targeted resources. The programme has now delivered a comprehensive catalogue of evidence and resources on the benefits and rationale of social protection in fragile contexts, and supported partners with timely, expert technical assistance to inform and strengthen social protection approaches in crisis contexts across the world. However, social protection continues to be underutilised globally, particularly in crisis contexts often due to political economy challenges, compounded by a substantial financing gap of $1.4 trillion annually for low and middle-income countries (ILO, 2024).

BASIC is designed to tackle bottlenecks at global and country levels through three inter-related components:

Research to strengthen global and country-specific evidence on using social protection approaches to build resilience and respond to crises, in different contexts, for different vulnerable groups, and the costs and benefits of such approaches. The research does this through global level questions, in-depth research in four focus countries (Lebanon, Niger, Nigeria and Yemen) and research uptake. It is delivered through a framework agreement contract (International Multi-Disciplinary Programme (IMDP)) with the Institute of Development Studies (IDS)

Technical assistance for country support, capacity building, learning, coordination, and policy influencing across multiple countries and at the global level has been delivered by the Social Protection Technical Assistance, Advice and Resources Facility (STAAR) since September 2021, managed by DAI Global UK. Specific humanitarian expertise is provided through the Humanitarian and Stabilisation Operations Team database (HSOT, managed by Palladium).

Evaluation to ensure that the programme is achieving its outputs and contributing to the desired outcomes and impact. An independent performance evaluation (baseline, midline, interim and endline) is assessing the effectiveness of BASIC and generating learning for FCDO, governments and partners that provide technical assistance, research and capacity strengthening on what works to influence policy, programme and systems-level change. This is being delivered through a framework contract Global Evaluation Framework Agreement (GEFA) with Integrity Global.

A new fourth component was introduced during the reporting period:

Catalytic finance to the World Bank to build capacity and test approaches to strengthen social protection operations in fragile and conflict settings. The FCDO has worked in partnership with the World Bank to launch a new Fragility, Conflict and Violence (FCV) window through the World Bank Social Protection Response Umbrella Trust Fund (SPR). It provides small catalytic grants to country and global teams, alongside funding for social protection and FCV consultants to support delivery of the window.

Despite reductions in Official Development Assistance (ODA) during the programme lifespan, minimal changes have been made to the total BASIC budget, with the main structural change during the reporting period being the inclusion of the new World Bank component. A contract amendment in March 2025 aimed to extend the STAAR technical assistance facility to March 2026, with an uplift in budget. However, due to timings and reduction of ODA, the facility was awarded a no cost extension to December 2025, bringing it in line with the timeline for the BASIC-Research component.

Summary supporting narrative for the overall score in this review

The BASIC programme has scored an A in this annual review, covering 12 months from October 2024 to end September 2025, with all four outputs scoring an A. Key achievements for the year have included:

- Output 1 scored an A. BASIC-Research has continued to produce robust academic and non-academic outputs to expand the evidence base for social protection in crises and presented findings at a range of different events including delivering the end of programme BASIC conference at IDS on “Social and Humanitarian Assistance in Crises” in September 2025 which convened nearly 100 academic practitioners, donors and multilateral representatives.
- Output 2 scored an A. STAAR continued to deliver new technical assistance assignments across a range of fragile contexts including Nigeria, Sudan, Yemen and OPTs, and in new countries such as South Africa and Haiti. STAAR also supported delivery of critical global events such as the October 2024 Global Forum on Social Protection in Conflict and Fragility and provided the secretariat to the UK co-chaired High-Level Panel on Social Protection in Fragile and Conflict Settings. Through provision of both long-term support and more responsive short-term inputs, demand from non-FCDO users has continued (albeit at lower levels than FCDO users), including from partner governments, with an average of 96% reporting that assignments sufficiently met expectations.
- Output 3 scored an A. Coordination between BASIC-Research and STAAR has shifted to focus on maximising dissemination and uptake opportunities in the final year of the programme, with both partners exceeding milestones on the number of events delivered and presented at. Integrity is on track on deliver the first draft of the evaluation endline in February 2026, which will be reported in detail in the PCR.
- Output 4 scored an A. This is a new output for the reporting period, so this review assessed the mobilisation and inception of the new Fragility, Conflict and Violence window that the FCDO is supporting the World Bank to deliver through the Social Protection Response Umbrella Trust Fund (SPR). The new window has demonstrated substantial demand for this type of funding opportunity and will provide lessons for the upcoming refresh of the World Bank’s FCV Strategy.

Output Scores

Output	Weighting (%)	Score
1. High quality, policy relevant, inclusive research in different contexts generated and effectively disseminated	35 %	A
2. High quality technical assistance provided for the design and delivery of country plans, policies, programmes and systems	35%	A
3. Greater awareness, knowledge and learning generated across countries and agencies on social protection approaches in crises	20%	A
4. Increased provision of high-quality assistance on social protection in fragile and conflict contexts in World Bank projects	10%	A

Major lessons and recommendations for the final months ahead

The key recommendations are as follows, with a full list in Annex 1:

Recommendation	Timing	Who responsible
BASIC-Research to continue to maximise dissemination and uptake until the end of their contract and consider recording/producing any final standalone non-academic outputs that could be pre-emptively developed to support upcoming publications.	By 31 December 2025	BASIC-Research
STAAR to continue to maximise dissemination and uptake until the end of their contract and consider recording any final standalone webinars or podcasts that would support upcoming publications.	By 31 December 2025	STAAR
FCDO should hold a joint meeting with BASIC-Research and STAAR to track any outstanding joint actions on dissemination and uptake before contracts close.	By 31 December 2025	FCDO
Given short timelines and anticipated progress on the 7 grantees after the BASIC programme has closed, the World Bank SPR and FCDO teams should maintain close engagement to ensure the impact of the FCV window is maximised and to galvanise other donors to scale up support.	Ongoing	WB and FCDO

Wider reflections, including for the PCR and future work
- STAAR’s capacity and expertise has sustained the FCDO’s leadership and ability to deliver across a range of high-profile social protection priorities despite a period of significant change in the international aid landscape.
- It can take longer than expected to build both demand for, and trust in, technical expertise services amongst targeted stakeholders, thereby backloading activity in the later years of the programme.
- In crisis contexts, there is need for flexible technical assistance to respond to new demands and opportunities that emerge. Balancing the demand between core priorities and responsive opportunities would benefit from early and clear agreement between FCDO and the partner on a planned division of labour.
- Embedded advisers offer an effective mechanism for addressing institutional change but then also require appropriate management and support to manage the new or different political contexts in which they are situated. Expectations need to be realistic on what is feasible to achieve in the relatively short timelines that individuals are embedded into agencies.
- Embedded advisers also bring substantial contribution to outcome level change, but similar value can also be achieved by sequencing support under certain conditions. National consultants enable continuity and sustainability by preserving institutional knowledge and expertise, even when in between assignment funding.
- BASIC-Research has supported uptake by strengthening guidance on working papers to ensure clear policy recommendations and executive summaries, though have not been able to track user satisfaction and impacts of these changes. Future programmes could consider designing new metrics or follow up tools specifically around user uptake from inception.
- Discussions around the proposed cost-extension in the final year of the programme absorbed programme management bandwidth which then did not come to fruition. However, this is a risk at any stage of the programme lifecycle and STAAR was able to draw on good relationship management to implement the no-cost extension with their delivery chain.
- Both the FCDO and the STAAR Facility reflected on the high administrative burden of the Facility, which was partially because of changes in FCDO personnel in key programme roles and reduced STAAR technical leadership, partially because of the Facility design, and contrasting approaches between STAAR and FCDO around financial management, especially forecasting which ran the risk of impacting strategic decision making.
- BASIC-Research and STAAR have been able to work closely during the reporting period and provide complementary perspectives in joint uptake sessions, setting out research findings alongside policy implications. Despite underlying tensions with the original programme design and evolving global context affecting social protection policy priorities, partners have continued to demonstrate a coordinated approach.
- There is huge demand for the FCV window funding within World Bank teams, so securing additional donor funding to increase the overall size of the window could yield greater impact, as well as administration efficiencies. Given the relatively limited funding available through the window at present, both FCDO and World Bank expectations need to be managed on what can be achieved.
- Given the nascency of the FCV window, the programme team should consider how to establish reporting arrangements that are sustained after the end of the programme lifecycle to support with monitoring and maximising the impact of these catalytic investments.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

BASIC aims to help poor and vulnerable people cope better with crises and be able to meet their basic needs through more efficient and effective social assistance in contexts of recurrent shocks, protracted conflict and forced displacement. It is premised on the idea that high-quality advice, greater awareness, knowledge and learning, targeted capacity development, high-quality, policy-relevant evidence combined with new or strengthened relationships and strategic partnerships across the humanitarian, climate resilience and social protection sectors will lead to strengthened policies, systems, plans and programmes; greater capability; more coordination and coherence and increased political commitment. It is anticipated that the programme will contribute to longer-term sustainable gains by strengthening systems through which domestic resources and donor funding will be spent more efficiently and effectively.

Whilst the World Bank component has been added to the programme during this reporting period, the Theory of Change has not been updated during the reporting period, meaning this Annual Review will assess this new fourth component against the existing outcomes and impact indicators.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

This Annual Review’s assessment of outcomes is based on partner reporting. The endline evaluation for the BASIC programme, led by Integrity, will inform overall outcome assessment in the Project Completion Review (PCR) in 2026. A major change during the reporting period has been the announcement of reductions in ODA globally, with assumed negative impacts on global appetite to engage in and absorb new evidence and technical expertise from the BASIC programme. The criticality of political commitment for social protection is outlined in the Theory of Change and has been implicitly strengthened through the range of high-level international events during the reporting period, but would be helpful for the PCR to consider additional inputs that could be constructively included in any future social protection offer as part of comprehensive efforts to increase social protection coverage and strengthen systems. This includes balancing effort between activity in a set of focus countries and themes, alongside flexibility to respond to emerging strategic opportunities.

Partner reporting this year has broadly demonstrated a continued positive trend of transitioning from outputs to outcomes with a significant uptick in policy and systems strengthening, although longer term impacts are less clear. The inclusion of a new component with the World Bank offers the programme scope to accelerate social protection in crises objectives with one of the biggest donors in the social protection sector. The UK has played a “first mover” role on the FCV window, providing critical seed funding. The new FCV window was oversubscribed by World Bank teams thus highlighting the potential scope for impact in influencing the World Bank’s approach to FCV, though the focus of this initial window is relatively limited. Grants have recently started implementation so output 4’s progress will be reported in more detail in the PCR.

As the programme is nearing its end, the endline evaluation and final partner reports should review how effective the actions taken by partners have been at developing and maintaining capacity and capability of national systems and how viable this is in the future for achieving programmes outcomes and impacts.

Outcome 1: New or strengthened country and global plans, policies, programmes and systems designed and implemented (bilaterals, multilaterals, Governments, FCDO)

The BASIC programme has continued to demonstrate good progress towards outcome 1 during the reporting period. BASIC-Research in coordination with STAAR has worked to influence the approach and policies of governments and IFIs, increasingly focusing on how social assistance should be provided in crises and the practicalities of sustaining and adapting systems under conflict, displacement and compound shocks. BASIC-Research has achieved this through lived-experience research which informs accountability practices; country-evidence shaping policymaking; and influencing the global agenda on social protection in conflict. STAAR has been able to expand reach and influence both in responding to the 2024 call for proposals and through delivery of last year’s Global Forum on Social Protection in conflict which both highlighted STAAR’s offer to an international audience. This then led to the ongoing High-Level Panel on Social Protection in Fragile and Conflict Settings including its public enquiry. BASIC-Research and STAAR plan to conclude pending assignments, publish the pending pipeline of outputs, and support final dissemination and uptake activities which are intended to contribute to further outcome-level change.

Country Level

In Uganda, BASIC-Research on inclusion supported government thinking. BASIC-Research shared evidence on the barriers faced by young women and other marginalised claimants which catalysed discussion on the government’s role in delivering inclusive programme design to improve social protection coverage of marginalised groups. As a result, the government invited BASIC Researchers into senior-level dialogues, recognising the work as “critical” for making interventions responsive to marginalised groups. A STAAR workshop in May 2025 helped kickstart a stalled agenda on social protection in Sudan, bringing together Sudanese practitioners, academics, donors and experts and led to formation of a Sudanese-led Alliance for Social Protection. This coalition now meets regularly, has established working groups and developed an engagement strategy to facilitate priorities.

Global Level

STAAR has led and contributed to several processes to strengthen policies and systems at the global level which have galvanised international attention, however it is too early to assess whether these processes have led to wider change in how policies and programmes are implemented. A key focus has been building and strengthening the narrative and coordination of social protection in fragile and conflict settings, starting with successful delivery of the Global Forum on social protection in conflict in October 2024 in Rome which was co-hosted by WFP, UNICEF, BMZ and USAID. During the close of the Forum, a new High-Level Panel (HLP) on Social Protection in fragile and conflict settings was announced, co-chaired by the UK and Somalia. STAAR also progressed the UK’s multilateral priorities during the reporting period, supporting the secretariat for South Africa as chair of the G20 Development Working Group, providing drafting, negotiation and technical support, and contributing to social protection’s successful inclusion in the ministerial declaration. An assignment nearing conclusion on potential virtual mechanisms for social protection financing was also referenced as a future deliverable in a Brazil co-sponsored Sevilla Platform for Action at FFD4 in July on better integrated financing for SDGs 1 and 2. More details on this assignment will be included in the PCR.

Meanwhile BASIC-Research has supported improvements in global practices and policies of some of the FCDO’s major partners, including WFP and the World Bank, as well as working closely with STAAR, as part of the secretariat supporting the Global Forum, and also supporting the HLP. BASIC-Research’s analysis of accountability in conflict settings contributed to WFP’s review of complaints and feedback mechanisms with explicit focus on the interface between social protection and humanitarian. New evidence and academic outputs have also contributed to ongoing policymaking in the global social protection community, such as informing the World Bank’s new approach paper on social protection in FCV. BASIC-Research’s focus on social protection in conflict has helped shift perceptions and demonstrate this is a policy problem that can be addressed through country operations. BASIC also reported a degree of challenge in accessing the right policy spaces and external interlocutors in order to effect change, and their dependence on FCDO teams including overseas posts in facilitating such dialogue.

Outcome 2: Improved cross-sector human and institutional capability and capacity (Governments, local actors, multilaterals, bilaterals, FCDO)

There has been a continued positive trend in improving national and global capability and capacity on social protection during the reporting period. BASIC-Research and STAAR have embedded expertise and processes into national systems, which has enabled systems to have the capacity to support social protection. This includes through STAAR’s embedded advisory capacity to support social protection systems which provides continuity to support sustained reform, such as in Yemen and Palestine which in turn supported greater capacity and capability within national contexts. At a global level, STAAR’s technical assignments have influenced key institutions such as the World Bank, enabling greater capability uptake. Meanwhile, BASIC-Research has supported both formal and informal knowledge channels to support global capability, specifically through the development of e-learning and communities of practice respectively.

Country Level

STAAR has engaged in a range of contexts to support capability and capacity strengthening of a variety of actors. In Haiti, STAAR worked with WFP to strengthen advocacy for integrating displaced populations into social protection systems and to move beyond emergency aid. This work is expected to contribute to greater change over time, with STAAR exploring potential to use the flexible pool to provide further support to WFP in the final months of the BASIC programme. In South Sudan, STAAR supported the World Bank to strengthen institutional capacity and capability around humanitarian-social protection linkages through the development of an options note which helped to reactivate the national social protection working group. This has led individuals to take forward recommendations and provided space for structured discussion on social protection.

In Yemen, BASIC-Research supported a national researcher who is now part of a STAAR supported donor coordination function. The researcher has been able to use capacities, knowledge and evidence developed from her work with BASIC to inform how donors respond to the current situation. In Nigeria, BASIC-Research supported capacity building through support to crises-trajectory workshops in Borno, which precipitated immediate state-level action and referral of cases to courts for prosecution, thus showcasing how recommendations from BASIC-supported findings are embedded into national institutions.

Global Level

At the global level, STAAR has played a role in connecting practitioners with conceptual tools and framing to support research, analysis and delivery – particularly at the intersection of humanitarian assistance and national systems. Through the provision of shared language and frameworks, STAAR’s work has led to strengthened capacity of actors. Examples include the World Bank’s Social Protection Assessment Resource Kit for Systems (SPARKS), work on the TRANSFORM training on social protection in fragile and conflict settings which will support global capacity beyond the BASIC programme’s lifecycle, and ODI’s Climate-responsive Social Protection Primer for Philanthropy, which draw directly from STAAR’s “solar system” framing.

Meanwhile BASIC-Research findings provided the backbone of a new e-learning course on Social Protection in Crises, which launched in September 2025, supporting global capability on social protection. Furthermore, BASIC-Research are supporting informal global networks of social protection capability and capacity through a community of practice which emerged following the Rome forum and has since met at the IDS conference. Whilst the true impact of this community is difficult to measure, online communities on sp.org and on WhatsApp are supporting global discussions about policy debates at global, regional and country level. At the regional level, the Rome forum led to the mapping of efforts to coordinate social protection and humanitarian cash in the Middle East and North Africa, which ILO are taking forward in the next reporting period. These informal networks support and complement more formal processes such as SPIAC-B.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The BASIC programme will come to a planned close by the end of March 2026, with the BASIC-Research and STAAR components due to close by the end of 2025. It is clear from partner reports and accompanying discussions that the programme has broadly achieved output level objectives and made good progress on transitions towards outcome-level change but given the scale of fragility and humanitarian need globally, there is need to continue efforts towards the overall impact of ensuring vulnerable people cope better with crises. Given the limited time left to deliver the BASIC programme, and the anticipated gap in programming on this agenda, there is risk of a backslide in momentum towards the high level of ambition set out in the programme’s Theory of Change (at outcome and impact level). Partners and the FCDO programme team should consider how to embed sustainable exits from existing work and how any future programming (by FCDO or others) could build on the strong foundation established by BASIC.

The programme has provided a comprehensive range of research to justify continued investment in support for social protection in crisis settings. A natural result of the BASIC programme’s maturity, as well as the FCDO Gender-Responsive Social Protection programme, is that external interlocutors have also become increasingly aware of and interested in the FCDO’s technical expertise offer on social protection. In this final year of the programme, STAAR particularly has therefore been able to leverage previous assignments such as those in Yemen, or access new spaces for influence such as the World Bank. The positive feedback from users on both BASIC-Research and STAAR outputs; the capability this has provided the FCDO in then using these outputs to inform and accelerate international momentum on social protection through embedded advisors as well as set-piece global events; and the new strategic opportunity of the thematic window with the World Bank, demonstrates the inherent value of the programme. Lesson learning from the programme indicates the necessity of planning sufficient time for technical expertise and research processes to develop and build trust and access with key interlocutors and points to the merits of having a joint technical assistance facility between two programmes that can share capacity and capability which may not have otherwise been available with a standalone facility. However, the design of the current programme does highlight some areas for improvement. This includes earlier sequential integration of partners; designing a mechanism that offers more efficiencies for FCDO administration time but likely more political brokering; and initiating catalytic multilateral finance earlier to ensure that results are fully captured within the programme’s lifecycle.

## C. DETAILED OUTPUT SCORING

Output Title	High quality, policy relevant, inclusive research in different contexts generated and effectively disseminated
Output number:		1	Output Score:	A
Impact weighting (%):		35%	Weighting revised since last AR?	Yes, down from 40%
Indicator(s)			Milestone(s) for this review	Progress
1.1 Number of high-quality open access academic outputs on critical global themes and from focus countries (e.g. peer reviewed journal articles, working papers, and book chapters which meet FCDO research quality standards) published or accepted for publication (cumulative)			68	Not Met / 65 (20 new outputs during reporting period)
1.2 No. of non-academic research outputs on critical global themes and in focus countries (e.g. blogs, articles, presentations) and policy outputs (e.g. policy briefs, rapid response briefs, presentations to policy audiences) (cumulative)			90	Exceeded / 99 (25 new outputs during reporting period)
1.3 Number of operational and policy recommendations specifically about gender, age, disability and intersecting vulnerabilities (cumulative)			22 recommendations across 50% of non-inclusion theme reports	Exceeded / 41 (23 outputs during reporting period)
1.4 Number of people (disaggregated by country) engaging with research communications through webpages and/or social media (cumulative)			14,000 visits to IDS BASIC webpage, 30,000 visits to BASIC blogs (disaggregated by country) / 80% increase in external stakeholders engaged by research communication activities/events from Milestone 1	Partially Met / 13,137 page views / 28,112 blog visits / 6,919 engagements (220% increase from Milestone 1) / 4,901 LinkedIn followers (362% increase from Milestone 1) / 1,722 stakeholders attended event and meetings (1048% increase from Milestone 1)
1.5 Increased capacity of southern researchers/research organisations working in crisis contexts to conduct, direct, interpret and use BASIC-Research (e.g. use research/research processes to position themselves and to advocate/influence others)			18 partners in BASIC focus countries either publish new academic outputs or present new research to in-country audiences or institutions	Exceeded / A total of 46 (28 new partners during the reporting period)

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 1, led by the Institute of Development Studies (IDS), highlights a core function and value of the BASIC programme in delivering robustly researched outputs to strengthen the global evidence base on social protection in crises, particularly protracted crises - known as BASIC-Research. Now in its fifth year, BASIC-Research has published a large body of work and still has a pipeline of new academic outputs pending publication. BASIC-Research will be focused on maximising dissemination and uptake activities in the final months of the programme. The FCDO should explore whether the evaluation endline or economic analysis can assess the impact of this output’s balance of effort between operational research and uptake.

Output 1 overall scores an A, as all indicators were either not met, partially met or exceeded. BASIC-Research has made strong progress during the reporting period, responding to recommendations from the 2024 annual review and delivering planned outputs on time, including presenting evidence at a range of different events and delivering a major IDS conference supported by the BASIC programme in September 2025 which convened nearly 100 academic practitioners, development partners and multilateral representatives. Other events included a workshop in Ethiopia with policy makers, academics, government and NGOs to feed into discussions concerning the evolving policy agenda around safety nets; convening a panel to discuss BASIC-Research on frontline capacities at the Development Studies Association (DSA) conference; and webinars on the launch of new papers such as financing. Indicators are focused on IDS’s immediate production of academic and non-academic outputs, and engagement with them, rather than on metrics to assess how this evidence is then used in practice by other agencies, though this year BASIC-Research has been able to gather high level demographic data as a result of updates to the IDS and OpenDocs websites.

Output indicator 1.1 has been not met
This reporting period has been more conducive for operational research than previous years of the programme, with less disruption arising from contextual or environmental risks. The milestone was not met however some outputs are pending publication and will be reported in the PCR. During this reporting period 17 new working papers were released, plus a journal special issue drawing on papers from the Social Protection conference in 2023 and 2 other Journal articles focusing on Nigeria, Ethiopia, Lebanon, Yemen, Sudan, Niger and Iraq. Output themes included social assistance in protracted crises; political economy; limits and exclusions around cash transfers; financing and climate resilience. BASIC-Research received positive feedback on new papers with users noting work on Yemen “provides a wealth of information and “explores a critical and timely topic…the rigor in amplifying these distant voices is commendable”. To manage ongoing discussions balancing IDS’s role and expertise as an academic institution and the need for policy-focused recommendations, IDS has strengthened guidance for its researchers to ensure more proactive consideration of policy recommendations so that academic outputs can be operationalised more effectively.

Output indicator 1.2 has been exceeded
BASIC-Research delivered 25 new non-academic research outputs, including 14 policy and research briefings and 11 other outputs such as blogs, videos and podcasts, exceeding the target by 9 additional outputs. There is country and thematic coherence on the focus of these non-academic outputs alongside the outputs produced under indicator 1.1, with the addition of Syria and focus on the role of social protection in post-conflict transition. Public engagement with these outputs is challenging to track, as the quantitative data of downloads does not provide detail on who it was that engaged, or for what purpose. Timely outputs relating to global issues can generate engagement with short-form content but not necessarily the underlying research i.e. a blog about social protection in Syria has been the best performing blog on the IDS website this year.

Output indicator 1.3 has been exceeded
BASIC-Research produced 23 recommendations, predominantly on Gender Equality and Social Inclusion (GESI). Recent examples include “Social Assistance and coping with crises in Nigeria” (GESI focus); “Can Social Protection Programmes Promote Livelihoods and Climate Resilience in Conflict-affected Settings?” (GESI; age-related; intersecting vulnerabilities); and “Reframing the Accountability of Social Assistance in Crises” (people with disabilities; GESI; intersecting vulnerabilities). BASIC-Research’s “lived experiences” work in Iraq has shifted to a GESI-transformative stage, drawing on participatory research processes and influencing key stakeholders to deliver an inclusive refresh of the social protection legal framework. More than half (57%) of the 23 recommendations were from non-inclusion theme reports.

Output indicator 1.4 has been partially met
Engagement has continued to grow during the reporting period, such as posting content 68 times through the BASIC-Research LinkedIn page which achieved over 110,000 impressions (visibility/reach) and more than 1500 engagements (interactions with content/posts). BASIC-Research has included engagement through LinkedIn within the milestones, as recommended during the 2024 annual review, which provides more holistic data on their engagement and reach. Outputs that generate the most engagement include podcasts, shorter briefings and synthesis papers which cater for wider audiences, with demographic data tracking non-profit organisations, research services and international affairs as the three largest audiences by group. It’s not possible however to monitor and track wider impacts of audiences engaging with these types of outputs.

Output indicator 1.5 has been exceeded
BASIC-Research has supported 28 national researchers, exceeding this review’s milestone of 18. This further increase is due to country partners being involved in a wide range of dissemination activities as well as co-authoring BASIC-Research outputs. Working with national researchers is standard good practice for IDS and can be considered to contribute to equity of the wider programme through its focus on national ownership and input to new research.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
All milestones were adjusted following the 2024 annual review; however, some targets could have been more stretching.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation from 2024 Annual Review	Progress to date
BASIC-Research to review what more can be built into research writing and QA processes to ensure recommendations in academic research clearly outline who they target, to do what and when (i.e. are SMART), and complement existing country stakeholder mappings and engagement plans with power analyses to identify priority institutions and individuals to target to leverage policy uptake [Action: by March 2025]	BASIC-Research continued to work with researchers across the consortium to ensure that outputs are relevant to policy and influence key stakeholders through communication, dissemination and research uptake efforts. They circulated guidance on ensuring policy relevance to lead researchers, adapted the working paper format to include policy focussed executive summaries and prioritised the publication of short policy briefs as well as longer working papers. BASIC-Research have also developed guidance on research recommendations that ensure the suggestions are specific, relevant and measurable.
BASIC-Research to conduct further analysis to understand who is being reached by online content and outputs and the impact of this engagement with research online [Action: by March 2025]	The BASIC communications team review demographic data and social media engagement quarterly to track which content is most effective. The most engaged posts were those that had a call to action or for people to get involved in discussion, as well as shorter, targeted blogs and events.
BASIC-Research to review whether adequate human/financial resource is dedicated to planning around dissemination and uptake and consider with FCDO whether this needs to be revised or research ambitions reduced to make room for stronger uptake of activities [Action: by January 2025]	BASIC has conducted a review and have a costed plan for dissemination and uptake activities which has been reviewed and agreed with FCDO.
BASIC-Research to ensure higher quality proofing and consideration over audience of reports. [Action: ongoing]	BASIC continue to review, edit and proofread outputs according to academic standards, and have also updated their guidance for working papers to give greater consideration for audiences from the outset, and updated guidelines on ensuring policy recommendations are specific, measurable and relevant.

Lessons learned this year
- BASIC-Research has supported uptake by strengthening guidance on working papers to ensure clear policy recommendations and executive summaries, though have not been able to track user satisfaction and impacts of these changes. Future programmes could consider designing new metrics specifically around user uptake and consider feasibility of tracking progress over the lifetime of the programme in agreed locations.
- Policy briefings are a useful tool for highlighting key findings and repackaging research outputs into more useable formats for non-academic audiences, particularly when provided as supporting material for a webinar or event.
- BASIC-Research has improved the visibility of GESI recommendations as seen firstly in their internal capability to implement a GESI strategy and then incorporating transitions from GESI-aware to GESI-sensitive and even GESI-transformative as seen in Iraq.
- Online engagement figures have limited value as proxies for understanding the programme’s impact, as they do not convey how products are then absorbed and used. However, there has been demonstrable participation through the webinars, conferences and face to face events, proving audiences value participatory engagement.
Recommendations for the year ahead
- BASIC-Research to continue to maximise dissemination and uptake until the end of their contract and consider recording/producing any final standalone non-academic outputs that could be pre-emptively developed to support upcoming publications [by 31 December 2025]
- FCDO to consider how to support engagement around new publications where these take place after BASIC-Research’s contract has ended i.e. through FCDO-hosted events in 2026 [by 31 March 2026]
- FCDO to explore whether the endline evaluation or economic analysis can assess the impact of this output’s balance of effort between operational research and uptake [by 31 March 2026]

## C. DETAILED OUTPUT SCORING

Output Title	High quality technical assistance provided for the design and delivery of country plans, policies, programmes and systems
Output number:		2	Output Score:	A
Impact weighting (%):		35%	Weighting revised since last AR?	Yes, down from 40%
Indicator(s)			Milestone(s) for this review	Progress
2.1 Use of BASIC technical assistance by FCDO, governments, agencies, and other donors: / Number of BASIC assignments that have been completed and/or moved from scoping to delivery (cumulative) / Number of countries supported by BASIC assignments (cumulative) / Number of non-STAAR/FCDO users (non-cumulative) / Number of national/local consultants as TL or deputy TLs on STAAR assignments (non-cumulative)			90 / 57 / 10 / 5	Exceeded / 101 (19 new + 8 assignments not included in previous AR) / 61 (3 new) / 10 / 7
2.2 Quality of BASIC technical assistance and delivery / % of STAAR assignments commissioned by non-STAAR users with a client satisfaction score of 4 or higher out of 5 (cumulative) / % of STAAR assignments commissioned by non-STAAR users achieving stated objectives set out in original or revised ToR, with a score of 4 or higher out of 5 (cumulative) / Number of STAAR assignments commissioned by non-STAAR users that have moved from agreed ToR to delivery of agreed workplan (kick-off call within 4 months) (non-cumulative)			90% / 90% / In all but one case	Not met / 86% / 83% / One case (Iraq)
2.3 Knowledge and learning produced and disseminated by BASIC technical assistance / Number of BASIC technical assistance high-quality knowledge and learning products (cumulative) / Media and social media outreach: / i)Total no. output views disaggregated by output type – papers, blogs, digital assets / ii) Number of LinkedIn followers to STAAR page			157 / i) 8000 output views disaggregated by output type – papers, blogs, digital assets / ii) 2500 LinkedIn followers	Exceeded / 182 / i) 9233 output views disaggregated by output type: / - papers = 4846 views / - blogs = 1782 views / - evidence digests = 474 views / - digital assets = 2131 views / ii) 3418 LinkedIn followers

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 2, implemented by DAI, highlights another core function of the BASIC programme in delivering the STAAR Technical Assistance Facility, which supports FCDO posts, partner governments and multilateral agencies by providing timely expertise to strengthen implementation of social protection systems in crises. Output 2 overall scores an A, as indicators were either exceeded or not met. Following the previous annual review, STAAR agreed with FCDO to focus on the uptake and sustainability of work already generated through the Facility, with workstreams to focus on climate; conflict sensitivity; coherence; local actors and financing. January to March 2025 was a particularly busy period for STAAR, with the highest volume of work of any quarter to date, driven in part by the contract amendment running concurrently. With the existing contract due to end 31 March 2025, there was a significant risk of no extension being granted. Subsequently, assignments were placed under huge pressure to finish by 31 March 2025.STAAR continued to deliver new technical assistance assignments across a range of fragile contexts including Nigeria, Sudan, Yemen and OPTs. Through provision of both long-term support and more responsive short-term inputs, demand from non-FCDO users such as UN agencies has continued to grow, reinforcing STAAR’s role as a trusted and responsive technical assistance facility.

For STAAR this reporting period began with delivery of the Forum on Social Protection in Fragility and Conflict which took place in Rome in October 2024 and brought together more than 150 participants from over 40 countries. The forum aimed to raise ambition and ability to use social protection approaches in situations of acute, rapid onset and protracted conflicts, and resulted in a Charter for Action as well as the announcement of the UK co-chaired High Level Panel (HLP) on Social Protection in Fragile and Conflict Settings which intended to contribute to broader political commitment to invest systematically in social protection systems in these contexts. STAAR has provided critical technical expertise and secretariat support to the HLP, supporting the launch event in May 2025, the review and synthesis of 78 submissions to the public enquiry in June 2025; a subsequent panel meeting in September 2025 and at the time of writing this annual review continues to work closely with the panel to finalise the recommendations which will be launched at the Second World Summit for Social Development in Doha in November 2025. STAAR’s support to the HLP has contributed to wider momentum and impact of the BASIC programme.

More generally, the STAAR team commented on the benefits that a shared Facility across the BASIC programme and Gender-Responsive Social Protection Programme (GSP) has had on their ability to deliver, especially at outcome-level where there are shared objectives. For example, DAI commented on the greater ability of their team to support more disability inclusion because of the expertise available on the GSP outputs / outcomes. The PCR may therefore wish to consider how any design activities may want to consider the co-benefits of a joint technical assistance facility in future.

Output indicator 2.1 has been exceeded.
STAAR delivered more assignments than originally planned, driven in part by high demand from the 2024 open call for assignments and the October 2024 Forum, increased conflict following, and interest from actors in Syria, Armenia, Latin America and the MENA region. Assignments ranged from short-term technical inputs to embedded advisory roles in agencies. Delivery included secretariat support to the UK co-chaired High-Level Panel (HLP) on Social Protection in Fragile and Conflict settings (FCAS) including its public enquiry; setting out the role of social protection for the Fund for responding to Loss and Damage thus strengthening the intersection of social protection with climate resilience; development of a conflict sensitivity operational diagnostic for UNICEF and WFP Sahel teams; and supporting South Africa with technical expertise to deliver ambitious priorities on social protection through the G20 Development Working Group this year. This broad range of assignments highlights the criticality of having a resourced expert technical assistance facility to leverage global moments in order to progress social protection objectives. Although falling just outside this review period, an executive summary of the assignment on loss and damage will be presented in October 2025 at the Board meeting of the Loss and Damage Fund, demonstrating both the potential impact and influence of STAAR assignments and critical role that technical expertise can play in navigating complex political processes.

During the programme’s lifetime, STAAR has supported 61 countries in total, exceeding the milestone. New countries supported during the reporting period included Haiti, Syria, and South Africa for the G20. STAAR’s technical expertise has largely been accessed by FCDO staff and posts, but 10 assignments were requested by non-FCDO users, including i repeat requests from UN agencies such as WFP. All new in-country specific assignments this year have included national consultants in lead or deputy roles, which enables assignment teams to quickly adapt to local dynamics. National consultants also enable continuity during periods without specific assignment funding, and preserve institutional knowledge, whilst also supporting equity through building more diverse and local capacity. In Haiti, the national consultant strengthened the team’s ability to quickly locate local stakeholders and supported with Creole when required.

Output indicator 2.2 has been not met.
During the reporting period, STAAR has concentrated on consolidating existing partnerships, fostering trust through the quality of the technical assistance provided to users. Client satisfaction has fallen slightly from last year, scoring four out of five on satisfaction of 86% rather than 90% target across assignments (and less than the 93% reported in the 2024 annual review), with lower scores reported on assignments relating to the Sahel and East Africa. Satisfaction levels dropped slightly when scoring whether objectives were met, with 83% scoring four out of five compared to the 90% target, but rose to 97% if including scoring of three out of five which indicates that support met expectations sufficiently. Satisfaction with international events scored highly however, such as the October 2024 Forum with one user noting “the forum delivered effectively through advice and framing of issues by STAAR”. One assignment in Iraq did not progress within required timelines during the reporting period and was subsequently cancelled.

Output indicator 2.3 has been exceeded.
To date, STAAR has produced 182 learning and knowledge products such as blogs and evidence digests, exceeding the milestone by 25 products. Recent examples include blogs and papers on pre-arranged financing in Malawi, Jamaica and Mozambique; maintaining and strengthening social assistance systems in conflict settings, with focus on Sudan and Armenia; and the role of local actors in social protection in crisis contexts. The dissemination of these outputs has contributed to STAAR exceeding social media outreach milestones, with cumulative results of 9233 output views and more than 3400 LinkedIn followers on the STAAR page. The most engaged paper was “forum on social protection: building and protecting social protection systems through the humanitarian-development-peace nexus” with 1,151 views; whilst the most viewed digital asset was “responsive social protection systems: an explainer” with 1,119 views.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
Milestones were adjusted for output indicators 2.1 and 2.2 as these were met or exceeded in the 2024 annual review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation from 2024 Annual Review	Progress to date
STAAR to develop, share and agree with FCDO a BASIC portfolio plan for the final phase of the programme that considers the best mix of models (e.g. long-term advisers, draw down support), thematic priorities likely to get traction in the global policy landscape, and geographic priorities (including whether to widen focus from Africa and MENA to Asia and others) [Action: by March 2025]	Workstream planning was conducted and submitted to FCDO by mid-February. The reduction in funding meant further planning was required. This has been done in partnership with FCDO and BASIC-Research.
FCDO and STAAR to agree maximum time for ToR approval and put logframe metrics in place to measure it, and STAAR to ensure it has the right range of support functions in the wider team rather than relying too narrowly on and overburdening a few individuals [Action: by January 2025]	A new logframe metric was not added to measure ToR approval. But STAAR has adjusted internal tasking so that Facility Manager tasks are now shared across two key team members rather than resting on one individual, supported by an experienced, separate member of staff to lead on other workstreams that arise beyond the standard portfolio.
FCDO and STAAR should ensure there is appropriate allocation in budgets and planning to support learning and uptake at outcome level in the final phase and consider reducing ambition on assignments to make room for stronger uptake activities if necessary [Action: by March 2025].	Allocations for uptake were included for the final phase of the programme, and additional flexibility is provided through the flexible pool through the STAAR core team. The reduced funding for the uptake workstreams were ultimately not used for uptake and instead supported new assignments.
STAAR to ensure there is adequate Technical Senior Leadership Team (TSLT) support to quality assure assignments and build consultant capacity, particularly where local researchers lead research or act as team leaders [Action: ongoing].	TSLT support is now integrated in each assignment team and receives positive feedback from users.
STAAR to set out how it can strengthen post-assignment support within its processes, e.g. through TSLT or additional time for consultants to support uptake of recommendations and in seeking commitments from users from the outset to (as a minimum) facilitate relationships at the country level for research/KIIs and help organise a roundtable with policy maker to discuss recommendations as a prerequisite to an assignment being approved [Action: by March 2025].	Terms of reference templates have been updated to include a sustainability and uptake dimension. / Flexible pool time through core is used to encourage further uptake of assignments.
STAAR to assess the VFM of supporting embedded advisors and whether this is an effective approach to strengthening impact and uptake of recommendations [Action: by March 2025].	STAAR has developed a paper assessing the role of embedded advisors which is currently under quality assurance. Initial findings suggest that embedded advisers bring substantial contribution to outcome level change under certain conditions, but that similar value can be approximated with sequenced support under certain conditions.
STAAR to ensure higher quality proof reading and consideration over audience of reports. FCDO would welcome sight of assignment reports before submission too [Action: ongoing]	All materials are quality assured, proof-read and approved by users prior to publication.

Lessons learned this year
- STAAR’s capacity and expertise has sustained the FCDO’s leadership and ability to deliver across a range of high-profile social protection priorities despite a period of significant change in the international aid landscape.
- It can take longer than expected to build both demand for, and trust in, technical expertise services amongst targeted stakeholders, thereby backloading activity in the later years of the programme.
- In crisis contexts, there is need for flexible Technical Assistance to respond to new demands and opportunities that emerge. Balancing the demand between core business and responsive opportunities would benefit from early and clear agreement between FCDO and the partner on a planned division of priorities.
- Embedded advisers offer an effective mechanism for addressing institutional change but then also require appropriate management and support to manage the new or different political contexts in which they are situated. Expectations need to be realistic on what is feasible to achieve in the relatively short timelines that individuals are embedded into agencies.
- Discussions around the proposed cost-extension in the final year of the programme absorbed programme management bandwidth which then did not come to fruition. However, this is a risk at any stage of the programme lifecycle and STAAR was able to draw on good relationship management to implement the no-cost extension with their delivery chain.
- Embedded advisers also bring substantial contribution to outcome level change, but similar value can also be achieved by sequencing support under certain conditions. National consultants enable continuity and sustainability by preserving institutional knowledge and expertise, even when in between assignment funding.
Recommendations for the year ahead
STAAR to continue to maximise dissemination and uptake until the end of their contract and consider recording any final standalone webinars or podcasts that would support upcoming publications [by 31 December 2025]

## C. DETAILED OUTPUT SCORING

Output Title	Greater awareness, knowledge and learning generated across countries and agencies on social protection approaches in crises
Output number:		3	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	No
Indicator(s)			Milestone(s) for this review	Progress
3.1 Knowledge and learning events organised or presented at by BASIC-Research or TA: / Number of events targeting external audiences organised by supplier (cumulative) / Quality of events organised by supplier (% of events with average participant feedback score above midpoint score) (non-cumulative) / Number of events presented at by supplier technical assistance (cumulative)			BASIC R – 39 (6 new) / STAAR – 54 / BASIC R – 80% / STAAR – 80% / BASIC R – 38 (7 new) / STAAR - 50	Overall: Exceeded / BASIC R: Exceeded / STAAR: Exceeded / BASIC R - 52 (19 new) / STAAR – 68 (20 new) / BASIC R - 100% / STAAR – 100% / BASIC R - 42 (11 new) / STAAR – 57 (16 new)
3.2 Delivery of BASIC knowledge management and learning strategy: / Delivery of jointly organised learning events, including those between suppliers (KELU quarterly meetings and follow-up discussions on opportunities for information sharing/strengthened collaborative approaches) those targeting external stakeholders (non-cumulative) / Qualitative examples of where coordination between STAAR and BASIC-R on specific assignments, research/non-academic outputs, influencing activities or monitoring/evaluation efforts has strengthened quality (non-cumulative) / ToRs and plans shared as relevant between BASIC-R and STAAR (non-cumulative)			6 shared learning events delivered / 32 opportunities qualitative examples where coordination has led to improved products or efficiencies with no examples of missed opportunities / 8 emails (4 STAAR to BASIC-R and 4 from BASIC-R to STAAR)	Met / 7 events / 42 (19 new) / 10 further examples in this reporting period
3.3: Timely and high-quality delivery of the evaluation of BASIC			Midline refresh report recommendations to be delivered. / KPI measures on quality and timeliness fulfil full payment / Endline review to be delivered on time	Met / Yes / Yes / On track

Briefly describe the output’s activities and provide supporting narrative for the score.
This output captures BASIC-Research and STAAR’s individual learning events and joint efforts to coordinate dissemination of knowledge as well as monitoring Integrity’s progress in delivering the final evaluation of the BASIC programme in 2026. Overall, output 3 scores an A as all indicators were met or exceeded. At the beginning of the reporting period, coordination between BASIC-Research and STAAR initially focused on the October 2024 Forum. Coordination between partners then shifted to focus on maximising dissemination and uptake opportunities in the final year of the programme, with joint planning on key themes as evidenced by workshops in November 2024 and August 2025 to agree final activities. Integrity is on track on deliver the first draft of the endline review in February 2026, which will be reported in detail in the PCR.

Output indicator 3.1 has been exceeded.
This engagement has taken place against a backdrop of shifting international donor priorities which presented unforeseen challenges in terms of both accessing, and the appetite of, influential partners in the development and humanitarian sectors to absorb and implement new evidence and policy recommendations. Despite these challenges, BASIC-Research exceeded the milestone for organising events (52 cumulative, 19 new during the reporting period exceeding the milestone of 6 new) and presenting at events (42 cumulative, 11 new – not including presentations by BASIC Researchers at the BASIC programme conference). Organised events included online and hybrid webinars, roundtables, conference panels and the end of programme BASIC conference in September 2025 on “Social and Humanitarian Assistance in Crises”. 11 of the 19 events were planned jointly with STAAR, including webinars on “Social Protection in a post-USAID world” and “the role of localisation in delivering more effective social protection in crises”. BASIC also presented at 11 non-BASIC organised events such as the March 2025 DEEP International Conference on Poverty Evidence and regional events including the National Policy Dialogue “Promoting Universal Social Protection in Lebanon”, also in March 2025.

STAAR exceeded the milestone for organising events (68 cumulative, 20 new) and presenting at events (57 cumulative, 16 new) to support knowledge exchange. Events included webinars and facilitated workshops, though the major deliverables during the reporting period were the October 2024 “Forum on Social Protection in Fragility and Conflict” and the High-Level Panel on Social Protection Fragile and Conflict Settings, which met in both May and September 2025. STAAR also presented at other events such as the G20 Development Working Group meeting in May 2025 and the Social Protection podcast in September 2025 on social protection in Gaza.

Both BASIC-Research and STAAR exceeded the milestone for participant feedback with 100% average feedback scores above midpoint, such as the webinar on “Reflections from the Forum on Social protection in Fragility and Conflict” which received average scores of 4.6/5. Feedback was primarily secured after set-piece events or webinars. STAAR received most positive feedback for the events that focused on broader messages around social protection in fragile and conflict settings, whereas events that were tailored to a specific context received marginally less positive feedback. BASIC-Research noted that feedback was “overwhelmingly positive” to both webinars and the end of BASIC programme conference in September 2025. Whilst helpful for providing a snapshot of scale, it remains challenging to gather feedback from participants/viewers of online events and the current indicators mask the variance of effort in delivering different types of events i.e. a conference is weighted the same as a webinar despite the different in resourcing and delivery requirements.

Output indicator 3.2 has been met.
STAAR and BASIC-Research met the target to hold 6 joint learning events during the reporting period, delivering 7 joint internal events during the reporting period. This included two Knowledge, Evidence, Learning and Uptake (KELU) sessions; the first focusing on next steps from the October 2024 Global Forum on Social Protection, and the second on the politics of social protection which led to a useful discussion around priority audiences for the emerging key messages and how to engage audiences. Other events included engagement planning workshops on key messages for social protection priorities and a country-specific session on Ethiopia.

Partners exceeded the target to demonstrate opportunities where coordination has improved efficiency or quality, with 19 new examples during the reporting period (42 cumulative). Examples are predominantly technical exchanges and reviews of assignments and participation and/or joint work to develop new proposals or events such as two proposals that were then accepted for the March 2025 Humanitarian Networks and Partnerships Week. Partners have also slightly exceeded the milestone to share key documents to ensure coordination, evidencing ten separate occasions during the reporting period where they shared updates on project plans, country mapping in Lebanon and Yemen, plans for thematic working groups and final engagement plans.

This indicator has required greater FCDO engagement to ensure that partners were sufficiently integrated in planning and understood FCDO strategic priorities for dissemination and uptake, in order to deliver final activities for the remainder of the programme.

Output indicator 3.3 has been met.
Integrity was contracted by FCDO in October 2020 to undertake an independent performance evaluation of BASIC at three points during its delivery – baseline (2021), midline (2022) and endline (2025). Integrity delivered an additional refresh of the midline review recommendations in October 2024 to support the 2024 annual review. Findings were discussed between the FCDO with partners in a joint meeting in November 2024. Integrity fulfilled nearly all KPI measures for payment with exception of August 2025 which was delayed to September, at Integrity’s request. The evaluation endline is currently underway and is expected to be delivered on time in 2026. There has been a small change of personnel in the Integrity team during the reporting period so continued close engagement with the FCDO will be required to ensure that it remains on track.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
Milestones were increased for indicator 3.1.a; 3.1.c; 3.2.a and 3.2.b following the 2024 annual review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation from 2024 Annual Review	Progress to date
STAAR and BASIC-Research to share and discuss their revised individual uptake strategies for the remainder of the programme and agree priority events and stakeholders for targeted joint uptake and influencing, and work with Integrity and FCDO to agree how to prioritise outputs to achieve outcome-level change [Action: by March 2025]	Partners participated in a workshop in November 2024 to agree in principle how to increase likelihood of achieving change at the outcome level. This was followed by a January 2025 workshop where partners explored potential themes for collaboration in dissemination and developed work plans. This was accompanied by further close work with FCDO to ensure clear deliverables were identified and agreed for uptake.
FCDO to carefully consider its own channels and strategy for championing social protection and dissemination of outputs internally, e.g. through the Social Protection Community of Practice, engagement with other key directorates centrally, and with posts [Action: by February 2025]	FCDO channels for disseminating outputs internally include: the FCDO Social Protection community of practice holds regular sessions with differing topics which have good engagement. A monthly social protection bulletin is disseminated and highlights key reports/articles and podcasts which prompts engagement from different teams around FCDO. Through our climate policy workstream we have sustained and deepened engagement on social protection across a range of teams, for example Loss and Damage and Adaptation teams. On fragility, there has been increased internal collaboration including with IFI teams ahead of the World Bank’s refreshed FCV strategy. Joint BASIC-R and STAAR uptake sessions have also been delivered for a range of FCDO advisory cadres.
STAAR and to develop a joint plan for conducting and supporting uptake of research in overlapping focus countries (e.g. in Lebanon and Yemen, as was done for Sudan), e.g. jointly undertaking KIIs where the same individuals at country levels are targeted. [Action: by February 2025]	This has continued on an ongoing basis, with joint work and approaches developed where possible. STAAR and BASIC researchers have taken part in planned uptake events and joint uptake focused projects, such as the inclusion of STAAR in BASIC-planned events in Lebanon, Amman and Nigeria.
STAAR to document and compile learning on the effectiveness of modalities (e.g. technical assistance mechanisms modelled through STAAR and ‘free to user’ model) used in the BASIC programme to feed into discussions on a successor programme, and to generate learning for other donors considering similar technical assistance programmes [Action: by March 2025]	STAAR has developed a paper assessing the VfM of embedded advisors which is currently undergoing quality assurance. / Ongoing KML processes will capture learning, as well as an assignment which focused on a mentorship model between CashCap and UNICEF, should also further this learning.

Lessons learned this year
- BASIC-Research and STAAR have been able to work closely during the reporting period and provide complementary perspectives in joint uptake sessions, setting out research findings alongside policy implications. Despite underlying tensions with the original programme design and evolving global context affecting social protection policy priorities, partners have continued to demonstrate a coordinated approach.
- There is questionable utility of the current indicators tracking the number of events rather than impact, which masks resource costs and does not distinguish between immediate impact of different types of events. Alternative metrics should be explored in future uptake frameworks, particularly if there are priority countries or themes where longer-term change could be tracked, including drawing on political reporting from post.
Recommendations for the year ahead
FCDO should hold a joint meeting with BASIC-Research and STAAR to track any outstanding joint actions on dissemination and uptake before contracts close [by 31 December 2025]

## C. DETAILED OUTPUT SCORING

Output Title	Increased provision of high-quality assistance on social protection in fragile and conflict contexts in World Bank projects
Output number:		4	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	N/A – new indicator
Indicator(s)			Milestone(s) for this review	Progress
4.1 Timely and high-quality delivery of the Fragility, Conflict and Violence window: / Call for proposals / Global activity / Social protection and FCV consultants			Call for proposals completed by April 2025 / Plan for global activity set out by December 2025 / Two consultants in place by June 2025	Met / a) Met – Call for proposals successfully launched. 7 grants allocated from 24 high-quality proposals, exceeding available funding. Grants will finance work in Afghanistan, Burkina Faso, Republic of Congo, Somalia, South Sudan, Ukraine and the West Bank and Gaza. b) On track to be met / c) Met (one full time consultant, and WB staff at 25%-time allocation)
4.2 Number of social protection and FCV knowledge and learning events held for/with WB staff, clients, and partners			2	Met / 2
4.3 Evidence of the Fragility, Conflict and Violence window having wider effects on WB social protection and FCV activity and/or approaches			Three examples	On track / Two examples including shaping the WB FCV strategy.

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 4, which is a new addition to the programme during this reporting period, focuses on a new thematic window delivered by the World Bank through the Social Protection Response Umbrella Trust Fund (SPR). The new Fragility, Conflict and Violence (FCV) window will award grants for global and country level work on social protection in FCV contexts, drawing on a UK contribution of £3 million. This annual review focuses largely on the mobilisation and inception phase of the window, and the Project Completion Review will assess progress of awarded grants. The World Bank is one of social protection’s largest donors, providing $29.5 billion in financing through their live portfolio including $15.5 billion through IDA for social protection as of April 2025. At the 2024 Spring Meetings, President Ajay Banga announced a new target for the World Bank to reach at least 500 million people with social protection by 2030. The World Bank has also positioned their ambition as a key contribution to the G20 Global Alliance, which seeks to address hunger and poverty.

Output 4 overall scores an A, as all indicators were either met or on track, however due to the rapid pace of work during the review period, some targets have been set within 6 months of this annual review. The FCV window aims to deepen World Bank engagement and capacity on the social protection in crises agenda, which is critical if increased social protection coverage is to reach those most in need. The window’s flexible funding will enable World Bank teams in FCV settings to pilot new approaches and strengthen their evidence base on social protection. The thematic window offers a route to support not only the World Bank to catalyse progress towards where and how their 500m target is delivered, but also to support the outputs of other components in the BASIC programme translate to outcome-level change through the read across to influencing the World Bank’s own organisational policies and approach. Successful grants have only recently started implementation and therefore longer-term impact and influence on the World Bank’s institutional approach to social protection in FCV settings cannot yet be known, but it offers a compelling and strategic opportunity. The SPR as an instrument has scope to both influence wider World Bank practice by providing case studies of innovative interventions in social protection in FCV. However, the relatively limited scope of funding with an initial 7 grants which have only recently started implementation, alongside funding for global-level activity and personnel to support delivery of the window, caps likely wider impacts including on the World Bank’s revised FCV strategy that will launch later in 2025.

Output indicator 4.1 has been met.
The World Bank launched the new FCV window during the reporting period, with a call for expressions of interest that received 24 proposals. Following technical assessment, 7 grants were awarded ranging between $200,000-$400,000USD for work in Afghanistan, Burkina Faso, Republic of Congo, Somalia, South Sudan, Ukraine and the West Bank and Gaza. Grants will enable World Bank teams to leverage wider lending by providing more flexible funding; for example, in Somalia the grant will support the transition to a government-led social protection system and in Ukraine, the grant will leverage digital technologies and public-private partnerships to support employment outcomes. Implementation began as of late September/early October 2025, and grants will last for up to 24 months. In addition to the 7 grants, the World Bank has also made provision for a global activity to support wider activity, which is still under consideration but may include a knowledge review which was helpful in the Rapid Social Response Multi-Donor Trust Fund (precursor to the SPR) Gender window. To support institutional capability on FCV and social protection in the World Bank, a new community of practice on social protection and labour in FCV contexts has been established. This will provide a platform to share evidence and support the operationalisation of the World Bank’s forthcoming social protection and labour in FCV approach paper. Additional capacity has also been recruited or re-allocated within the World Bank to support delivery of the FCV window and capacity and learning.

Output indicator 4.2 has been met.
The World Bank met the milestone, holding two learning events during the reporting period. Both events took place in September 2025; one to launch the new community of practice on social protection and labour in FCV and the other for the seven grantees under the FCV window to exchange information and share information protocols. Grantee teams will share quarterly updates with the SPR team in the World Bank to enable close tracking of progress and lessons.

Output indicator 4.3 is in progress and on track.
The World Bank is in the process of revising their FCV strategy which is expected to launch later in 2025. The new FCV strategy will set the World Bank’s approach to engagement in FCV contexts as well as strategic opportunities and sectors, such as social protection. A new Social Protection and Labour in FCV Approach Paper is also in development which highlights the World Bank’s internal efforts to support coherence between social protection and FCV strategies. There is scope for the FCV window’s 7 grants and global-level learning to inform ongoing implementation of the Approach Paper. The call for proposals for the thematic window was oversubscribed demonstrating strong interest across the World Bank FCV priority contexts to access flexible funding to test and explore new approaches to social protection in crisis settings. This annual review comes too soon after initial implementation to provide meaningful assessment on wider impacts and influence of the new window on World Bank institutional processes, however the organisational demand, plus development of the new Approach Paper and the upcoming FCV strategy highlight wider institutional engagement on the intersection of FCV and social protection.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
This output is new for the reporting period, following agreement with the World Bank in February 2025. There are no planned changes as a result of this review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
This is a new output from the previous year so there were no recommendations in the 2024 annual review.

Lessons learned this year
- There is huge demand for the FCV window funding within World Bank teams, so securing additional donor funding to increase the overall size of the window could yield greater impact, as well as administration efficiencies. Given the relatively limited funding available through the window at present, both FCDO and World Bank expectations need to be managed on what can be achieved.
- The World Bank often faces a challenge of differing mandates when collaborating with other actors. The requirement to work with partners on the ground has been delegated to the 7 grants but will need to be monitored closely through progress updates.
Recommendations for the year ahead
Given short timelines and anticipated progress on the 7 grantees and global activity after the BASIC programme has closed, the World Bank SPR and FCDO teams should maintain close engagement to ensure the impact of the FCV window is maximised and to galvanise other donors to scale up support [ongoing]
## D: VALUE FOR MONEY

Key cost drivers and performance

The initial Value for Money (VfM) of BASIC was achieved through the competitive procurement of the BASIC-Research, BASIC TA/STAAR and BASIC Evaluation contracts. In early 2025, the World Bank was added as a new programme partner through funding for a new FCV window of the SPR Trust Fund, which offers a mechanism to strategically partner with a large funder in the social protection sector and thus support the World Bank to strengthen their activity and further prioritise activity in fragile and conflict settings.

The original business case outlines the main cost drivers as daily fee rates, travel and subsistence costs. This includes security related costs and duty of care expenses when working in fragile and conflict settings. A no-cost extension was approved for BASIC in February 2025 to extend the programme’s end date to March 2026. This was accompanied by no-cost extensions to the contracts for BASIC-Research and STAAR until December 2025.

These no-cost extensions have been critical to enable partners to deliver final activities and targets, including dissemination and uptake of new research and technical advice. Most progress on the World Bank’s new FCV window will take place after BASIC closes, with the successful grants under the April 2025 call for proposals having started implementation in September/October 2025.

A midline review of BASIC was conducted in October 2024 and concluded that the programme represents good VfM across the 5Es. VfM performance in this review period has improved with partners continuing to implement strong cost-containment measures and largely either meeting or exceeding agreed deliverables.

VfM performance compared to the original VfM proposition in the business case

Economy
The main metric for BASIC-Research is the ‘proportion of administrative costs versus programme costs consistent with that of other similar research programmes’. Data for April 2025 to December 2025 (Year 5) shows 14.5% of the budget was spent on administrative costs, and by the end of the programme BASIC-Research is forecast to spend 13.2%, which represents good VfM. The BASIC-Research contract was drawn down from the IMDP framework meaning fee rates have already been competitively negotiated by the FCDO and remained unchanged during the last contract amendment in November 2024.

The main economy metric for STAAR is ‘proportion of administrative costs versus programme costs’. Data covering October 2024 to September 2025 demonstrates that the administrative costs have been 13% of the total budget spent. Other metrics focus on the delivery and costs of assignments, covered by the percentage of assignments designed and implemented economically (within budget and with competitive cost). Within the reporting period, 100% of assignments that were completed were within budget, which is consistent with the previous year. The ‘average daily fee rate on TA assignments’ has remained well below the maximum fee rate of £800, at £624 across the reporting period. This is lower than last year’s average daily fee rate of £633. To address the challenges raised in the previous annual review around underspend, STAAR has changed its approach to planning assignments. This contributed to a much lower underspend in 24/25 (of 1.36%) with STAAR demonstrating economic delivery of a large assignment budget.

Efficiency
The main metric for BASIC-Research focuses on the production and communication of high-quality research, measured by costs per output. Other metrics include cost per output, communication campaigns and events. The 2024 annual review reported an increase in VfM due to an overall reduction in cost per unit. This remains the same for this reporting period. The cost per unit has declined from £42,811.98 to £36,011.97 which indicates that over the lifetime of the programme, BASIC-Research has been able to deliver work more efficiently by leveraging their network of researchers and co-delivering events and presentations with other agencies to reduce costs. In addition, within this reporting period, the volume of outputs i.e. publications and events have increased but the underlying costs have not, contributing to the reduced cost per unit. The PCR should consider analysing the overall impact of such activities.

The main metrics for STAAR are the ‘number of countries receiving advisory services’ and the ‘quality of advisory products and satisfaction from users’. Cumulatively, STAAR has provided advisory services to 59 countries, with additional countries supported since last year. On the quality of advisory services, 86% of assignments scored 4 or higher out of 5 for client satisfaction and 83% scored 4 or higher out of 5 for meeting the original objectives as agreed in the Terms of Reference. Both these figures fell from the previous year (from 93% and 86% respectively) indicating a reduction in VfM.

Effectiveness
The main metrics for BASIC-Research consider the ‘timeliness and quality of evidence produced’ and the adoption of its ‘research findings into policy and practice’. Reporting shows that BASIC-Research is being presented and discussed internationally. For example, BASIC-Research was used in Nigeria to inform in-country policy dialogues and reframe discussions from a technical perspective to focus on political economy. BASIC-Research reported challenges around the sustainability of influencing at the national level during the reporting period as a result of FCDO staff changes at posts, which hindered progress in engaging international stakeholders.

The main metric for STAAR is the percentage of assignments that were suggested to have informed a change in country plans, policies, programmes or systems. There has been positive progress during the reporting period, including strengthening social protections systems in Yemen and Sudan and encouraging the EU’s decision to fund a donor coordination post in Lebanon. As noted in the 2024 annual review and in recent discussion with STAAR, there continue to be significant challenges in maintaining effectiveness due to wider external factors such as political instability which influences partner engagement.

Equity
The key indicator for BASIC-Research is the ‘number of operational and policy recommendations specifically about gender, age, disability and intersecting vulnerabilities’. BASIC-Research have exceeded the target with 23 new recommendations within this reporting period. 57% of these recommendations were in reports with research themes other than inclusions.

The main metric for STAAR is the ‘% of workstreams that transition from an international to a national lead’. Throughout the review period, the percentage of assignments with national consultants has been above 50%, with 100% of assignment consultants in Q3 of FY2425 at a national level. Working with national consultants supports sustainability of STAAR operations and preserves institutional knowledge, such as through the national leads in STAAR assignments in Yemen, Syria and Sudan. STAAR has also improved its disability focus across assignments since the previous reporting period. STAAR has a framework which provides guidance on how to include disability across the portfolio and is reflected in their engagement with countries such as Haiti and Ethiopia. This is also included as part of the package of key policy messages around FCAS.

Equity is not an explicit metric for the World Bank, but it is embedded in their approach to their FCV grants. As the World Bank was added as a new partner during the reporting period and grants have only recently begun, VfM evidence remains limited.

Assessment of whether the programme continues to represent value for money
Partner reporting demonstrates that BASIC has continued to perform well across most VfM measures during the reporting period. STAAR has continued to inform policy and practice at the country and global level, providing critical technical advisory services and expertise to accelerate social protection priorities and galvanise international momentum. Now in the final year, BASIC-Research has delivered a range of robust research findings which are starting to influence at global and national levels. There is evidence of improved synergies between the different programme components, for example BASIC-Research has informed the World Bank’s emerging approach to social protection in fragile and conflict settings, whilst in turn BASIC-Research has incorporated STAAR guidance into research projects in Yemen.

The no-cost extensions of the BASIC-Research and STAAR contracts until 31 December 2025 will support partners to complete their activities, deliver their results and secure maximum VfM before the programme ends on 31 March 2026. It is not possible to include a comprehensive assessment of the VfM of the World Bank’s new FCV window through the SPR Trust Fund as they are in the early stages of activity. The PCR should consider progress and assess the VfM of the grantees as these will have moved beyond inception to implementation by spring 2026.

E: RISK

Overview of risk management
The overall risk rating for BASIC has remained moderate. As was the case during the last reporting period, heightened instability in regions such as the Middle East and Ukraine impacted travel, stakeholder engagement and ability to conduct research in certain contexts. This risk was known to all partners delivering as part of BASIC due to the nature of the crisis contexts the programme operates in. All partners engaged with stakeholders in-country to anticipate, monitor and manage risks, leaning on security specialists to support with safeguarding staff, managing crisis preparedness and safety and security training for researchers and consultants. BASIC-Research noted that in Niger, for example, specific context risks meant that research was impacted. They responded by redesigning their research methodology to enable work to continue.

During the review period the FCDO and its partners experienced changes in both the internal and external operating environment, with announcements and implementation of reductions in global (and UK) ODA. This prevented the signing of a cost-extension for the STAAR Facility and meant that a no-cost extension was approved instead, thus requiring extensive re-planning and impacting on the creation and dissemination of some products. The contract amendment process in Q4 of FY2526 posed a major risk for the programme and the STAAR TA facility given its proximity to the end of the DAI contract end date. BASIC-Research also experienced minor delays to delivery due to funding uncertainty.

As well as the programme management and financial implications of the change to a no-cost extension, both partners noted that global ODA reductions may result in decreased uptake of outputs, despite also seeing an increase in demand for assistance by the most vulnerable populations. Whilst there have been concerns from partners about reduced uptake due to global challenges, they noted that there had been successes in highlighting the effectiveness and cost-efficiency of social protection strategies in addressing needs within this context, as can be evidenced during the Financing for Development Forum (FFD4). It can therefore be seen that whilst uptake could be impacted by external factors, BASIC’s work to showcase the impact of social protection in fragile contexts can act as a mitigation.

Both the STAAR Facility and BASIC-Research noted that as the programme moved into its final stage, there was a risk of limited uptake of learning and results due to the short time remaining on contracts to deliver final activities. Both partners collaborated to consider how they could transition from outputs to outcomes, with an increased effort by FCDO to encourage partners to work together on policy recommendations. The STAAR Facility noted they mitigated the risk of reduced uptake by focusing on embedding uptake considerations into output design, leveraging global platforms to disseminate key messages and focusing on developing thematic workstreams.

The evaluation endline could consider the risk of the programme’s achievements not being sustained, notably in the absence of a successor offer. Whilst the programme has made some strong progress against its outcomes in this reporting period, given the programme is closing in March 2026, with STAAR and IDS contracts ending December 2025, and global risks of increasing fragility and humanitarian needs, there will be a gap in social protection evidence and technical advisory services focused on crisis contexts after 31 December 2025 unless other development partners step into this space. Additionally, there may be potential loss or erosion of institutional knowledge across key agencies, which is a wider risk for progress towards the overall intended impact of ensuring vulnerable people can better cope with their basic needs in crises.

All live major and moderate risks (ratings are residual)

There are currently no major risks for the programme.

Moderate risk – External Humanitarian and development actors’ appetite for reform is low. This may lead to low uptake and limited policy influence.
Mitigation - Selection of deep engagement countries has been informed by assessments of government engagement and appetite for reform, for both Research and STAAR as well as both interventions looking at what works in terms of government engagement. The programme will utilise existing in country relationships with FCDO posts as well as STAAR assignment consultants at national level (where possible). The STAAR capacity development plan will also look to test what works with government interventions and influencing. Midline evaluation identified that influence of government is lower than influence of FCDO policy and programme at country level and acknowledges that government influence may take some time, this will be assessed again at endline. FCDO driving the SPIAC-B working group on linking humanitarian assistance with social protection, including developing common principles on linking and working with the Global Cash Advisory Group to build trust and understanding. FCDO is driving efforts (Global Forum and High-Level Panel) to raise the profile of social protection in crises contexts, and as part of the humanitarian-development-peace nexus. BASIC SRO to engage with humanitarian policy colleagues to ensure social protection remains central to its crisis prevention and humanitarian reform work. Lead Adviser will review how influencing will continue and how it will feed into the BASIC Endline Evaluation and PCR.

Moderate risk – Change in context (e.g. new shock) in a priority or deep engagement country could cause delays or disruption to research and other activities leading to work no longer being feasible or may require adaptation of activities.
Mitigation - Delivery partners are maintaining oversight of situations in deep engagement countries, as well as FCDO SPT engaging with FCDO post colleagues to ensure early identification of potential issues. The list of these countries will remain flexible, but an assessment will be made depending on the nature of the shock and potential benefits of continued engagement given the nature of the programme. Both partners are aware and continue to plan accordingly, updating FCDO in good time.

Moderate risk - Fraudulent activity from downstream delivery partners either as a result of deliberate fraud or poor management results in funds being used for unintended purposes.
Mitigation - All contracts set out the requirement for immediate reporting to FCDO of any suspicion of fraud. Maintaining specific partner delivery chain maps and a BASIC programme level one helps to track funding through the beneficiary level. All agreements with partners stipulate that suspicions of fraud need to be reported to the FCDO reporting line and that any funding lost as a result of fraud is reimbursed to FCDO. Due diligences on all partners have taken place, providing assurance of adequate financial management systems. On submission of invoices the programme team continue to interrogate these against the proforma to ensure funding is allocated appropriately. Monitoring of financial documentation with each partner will check that financial management processes are in place and that all staff working on the BASIC programme are aware of the requirement to report fraud. The programme has not had any cases of fraudulent activity to date.

During the reporting period, a number of programme risks reduced, including the risk of underspend by STAAR, and the risk of poor communication between suppliers impacting delivery and influencing power of the programme. These reductions are the result of a number of changes in management of the BASIC programme including (but not limited to) the change from quarterly to monthly invoicing and the appointment of a HSOT Advisor to lead on a joint engagement/influencing strategy across both partners. SEAH and safeguarding monitoring is ongoing, and the programme has no active concerns currently.

Risk management
The FCDO team discusses risk in bi-monthly internal programme meetings. Monthly partner meetings and quarterly reporting allow FCDO to stay abreast of any changes. The AMP risk register is discussed within the entire programme team and updated quarterly by the Programme Manager and PRO.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL and FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues

BASIC-Research – IDS
The contract with IDS for the BASIC-Research component started in 2020 and has undergone four contract amendments to date reflecting changes to research plans and budgets. IDS reflected that this delayed some engagement around outputs, but they were able to manage this to avoid adverse impact.

BASIC-Research report on ten KPIs, three of which are used within a payment by results (PBR) process and the rest are monitored within the logframe, evidenced within quarterly and annual reports, and in the VfM framework and risk management processes. The payment method is hybrid, with 70% of fees based on inputs and the remaining 30% linked to PBRs on timeliness of output delivery, accuracy of financial forecasts and quality of research products. BASIC-Research has performed well against its PBR KPIs in the last year, with all PBRs met and all KPIs are on track or exceeding for this period. BASIC-Research forecasting for FY24/25 was extremely accurate, with final spend 0.06% under the total budget. In FY25/26, 27% of the budget was spent by end September 2025 and the BASIC-Research remain on track to spend the remaining budget.

FCDO’s relationship with BASIC-Research is very positive, with good communication on both sides. Monthly meetings are scheduled between the programme teams, and the research leads that cover each aspect of the programme. During the contract amendment period, communication between FCDO and BASIC-Research increased, enabling action to be taken quickly where required. Reporting is of high quality and on time, with minimal queries from the FCDO team.

In last year’s annual review, there was a recommendation to ‘ensure partner delivery chain maps, risk registers are reviewed and updated regularly, with specific focus on partners increasing communication of increased risks to operational delivery and research dissemination’. BASIC-Research have adhered to this recommendation and implemented the necessary steps to ensure information is shared with FCDO.

STAAR Facility - DAI
The Social Protection Technical Assistance, Advice and Resources (STAAR) Facility contract started in September 2021, and is delivered by DAI Global UK Ltd. The first contract amendment was completed in March 2024 which increased the overall STAAR contract value by £3 million (for separate activity funded under an FCDO Ukraine humanitarian programme). During the reporting period, FCDO and DAI worked through a further contract amendment to extend delivery, initially to March 2026 and then revised to December 2025. It was noted by both parties that the process of finalising this contract amendment was challenging, initially due to delays in the process (which started in October 2024) which risked the amendment not being approved on time, compounded by the announcement of UK reductions to its ODA budget in February 2025 and the subsequent pause on contract amendments. This led to a period of uncertainty for the STAAR Facility which they responded to by putting a stop order on work to avoid incurring further costs whilst budgets were unconfirmed. This slowed down delivery, and a knock-on impact was subsequently felt through delayed invoices for deliverables.

DAI report on sixteen KPIs linked to core fees on a quarterly basis and has performed well against all indicators during the reporting period. 98% of the KPIs have been met, with the 2% unmet being one KPI in the first quarter of the reporting period relating to forecast variance.

DAI produce quarterly reports covering assignment progress, risk and risk management, and finances. STAAR Facility forecasting for FY24/25 remained inconsistent with monthly forecasts not showing spend to date. FCDO regularly discussed this to improve accuracy. The individual assignment budget forecasting was more accurate, but inaccuracies continued throughout the reporting period, with final spend 1.36% under total budget. In FY25/26 38% of the budget has been spent by September 2025. Spend has been slow due to delays in invoicing, but FCDO expect spend to increase significantly during Q3. As part of the contract amendment DAI proposed moving underspend from previous financial years into FY25/26 in addition to making use of a £660k budget uplift available within the contract. The uplift was not granted given the announcement of reductions to the UK ODA budget. DAI noted that this posed a challenge as they had foreseen the budget would have been available for FY25/26. In response, DAI changed its approach to managing resources. They ensured that TSLT were engaged in strategic functions on a task-specific basis, whilst flexible resource was deployed to mobilise onto priority work. As a result, and in response to the recommendation from last year’s Annual Review,[1] STAAR have been able to minimise delays to assignments, though delays to programme management processes remain, as outlined below. A key change since April 2025 has also been the loss of the STAAR BASIC Technical Lead on Crisis which has resulted in less strategic oversight of and direction to the STAAR BASIC portfolio, including the planned uptake workstreams that ultimately did not progress.
[1] A recommendation from last year’s Annual Review noted that STAAR should review staffing support to minimise assignment and PM delays, and FCDO/STAAR to closely prioritise assignments to maximise the potential for impact.

The administrative burden of programme reporting remained high during this review period, partially because of changes in FCDO personnel in key programme roles and reduced STAAR technical leadership, partially because of the Facility design. Both FCDO and DAI noted differences in approach to forecasting, resulting in extensive communications between FCDO programme manager(s) and the DAI programme team. The Facility’s approvals process, which requires FCDO approval for assignment spend, also drives a high administrative burden. FCDO noted in the previous Annual Review that invoices should be submitted monthly. As a direct result of the no cost extension in March 2025, invoicing changed from quarterly to monthly ensuring spend could be more accurately tracked. It has also been noted that the quarterly reports submitted by DAI to FCDO have required significant review and comments on occasion, leading to delays in finalising reports and submitting invoices.

Whilst communication between the FCDO and DAI has been regular, with monthly check ins scheduled, some of the challenges noted above have dominated discussions between the Facility Manager, Project Manager(s) and the FCDO programme management team. FCDO noted that there were sometimes discrepancies between FCDO and DAI’s understanding of specific costs to be invoiced by DAI, with decision sometimes being made without FCDO consultation. The PCR may wish to consider how to address the high administrative burden that the STAAR Facility has placed on both FCDO and DAI, including the decision thresholds for individual budgetary decisions, and how this may be mitigated in any future technical assistance facilities.

Fragility, Conflict and Violence (FCV) Window – World Bank
Given that the FCDO and World Bank have only recently established the FCV Window, there is limited delivery and/or programme management to assess. The FCDO anticipates that it will receive quarterly reporting from the World Bank in a similar format to that which they receive for the Gender Window under the GSP programme, covering methodology, main findings, synthesis of key learning and recommendations. The financial statement shared suggest that the World Bank have a good track record of delivering within their budgets. FCDO communication with the World Bank has been positive to date. Given this Window was established late in the BASIC programme’s lifecycle, the PCR may wish to consider how these reporting arrangements will be implemented to ensure that the FCV Window can be monitored and its impact maximised.

FCDO team
Over the reporting period there have been some changes to team resourcing. The senior programme manager left the team, with the existing programme manager (PM) taking on their responsibilities. Partners commented on the smooth transition between the senior PM and existing PM, given the PM’s experience to date on the BASIC programme.

There were also changes in advisory and SRO roles within the team, as the previous SRO left the team in April 2025, being replaced by the Social Protection Team Leader, and the PRO was replaced by a programme funded role already working on the BASIC programme. Partners commented on how, like the transition of programme management responsibilities, the movement of the SRO role was relatively smooth given the experience of the Team Leader on the programme, which ensured a good degree of continuity and understanding of the programme as it heads into its final months.

Partners noted, however, that other resource changes to HSOT resourcing and changes in advisors at post made some engagement more challenging. BASIC-Research noted that high turnover of staff in country made some dissemination more challenging, whilst quick turnover of HSOT resourcing brought in between May and August 2025 meant that whilst progress was made, continuity was low.

Furthermore, given the change in resources over this reporting period, engagement from the SPT in monthly meetings has varied outside of the programme manager. Any future successor programme should consider the design of the programme, and how FCDO staffing and responsibilities could best support partners to deliver maximum outputs and outcomes.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
The plans for managing, monitoring and reporting programme performance across BASIC-Research and STAAR were developed during the inception phase of the programme. The World Bank was added as a new partner during this reporting period, and they have their own system for managing multi-donor trust fund performance. This is reflected in their most recent annual report FY25/26. BASIC-Research and STAAR provide quarterly reports that detail further information on the agreed outputs and financial reports. Both partners also participate in monthly meetings with the FCDO and engage on an ad hoc basis when necessary. The BASIC programme has also contracted Integrity Global to evaluate the overall BASIC programme and provide evidenced key findings and recommendations to the FCDO.

To inform this annual review, partner submissions have been used, complemented by partner interviews and reviews of quarterly documents across the reporting period. It also used the finalised midline refresh report by Integrity Global and interviews with the FCDO programme team. In the previous reporting period, FCDO requested a refresh of Integrity’s midline review to inform the 2024 annual review. The report assessed uptake and progress against the midline review, achievements, VfM and contributions to outcomes. The findings confirmed that there was improved coherence across the workstreams and provided recommendations on how to achieve outcome-level results.

Evidence
The evaluation endline review is currently underway and is expected to be finalised in early 2026. BASIC is moving into the last phase of implementation with the addition of the World Bank as a partner. In the last year of the programme, the focus has been on capitalising on the recommendations and learning from the previous reporting period to enhance delivery and contribute to wider impact. Interviews with partners suggest positive changes after implementing the recommendations. The coordination between STAAR and BASIC-Research has improved as seen through their joint planning on dissemination, uptake and approach to events. In this reporting period, STAAR have delivered and contributed to high-profile international and multilateral engagement e.g. with the ILO, World Bank, WFP, to accelerate the transition from output to outcome level change. BASIC-Research have increased the visibility of their GESI recommendations and have worked with STAAR to translate their research into policy recommendations – making them more specific to their target audience. The World Bank has commenced activities this year, with grants beginning implementation towards the end of this reporting period, and therefore there is no significant evidence to report yet, but to note there is substantial demand for this type of funding in the World Bank with the FCV window oversubscribed. The PCR will provide a more detailed assessment of output 4.

Learning
BASIC-Research, STAAR and the World Bank have individual MEL plans and processes. These are supplemented by the BASIC Evaluation conducted by Integrity Global. This sits within the overarching KELU strategy for BASIC agreed in 2022. Some key lessons identified in the current period include:

- The importance of partners working closely together to maximise and translate the research into practical application via the technical assistance and policy briefs; however, this remains challenging to execute in terms of sequencing coordination.
- The recruitment of national consultants and researchers overseeing inclusion themes can maximise the impact of those themes beyond inception activities and influencing the wider programme when those individuals are allocated future assignments/research.
- Embedding national consultants into STAAR’s assignments has helped translate outputs to outcomes by enabling the right people to access the work and helping to navigate the political context to generate buy-in.
- Ensuring partners and FCDO teams are sufficiently resourced to provide consistent and clear strategic direction to maximise impact.

The programme is in the final year so these lessons could be further analysed in the PCR. The PCR could also explore how to effectively create synergies between programme workstreams, in the early stages of developing a programme like BASIC to maximise efficiencies for partners and the FCDO. It could also explore how partners have leveraged technical expertise to incorporate key inclusion themes across its processes as well as outputs.

Date of last narrative financial report	DAI – October 2025 / IDS – October 2025 / World Bank – August 2025 / Integrity – September 2025	Date of last audited annual statement	DAI – December 2023 / IDS – December 2024 / World Bank – June 2025 / Integrity – January 2025

ANNEX A - List of Acronyms

BASIC – Better Assistance in Crises
BmZ - Federal Ministry of Economic Cooperation and Development (Germany)
DRF - Disaster Risk Financing
EACDS - Expert Advisory Call-Down Service
FAO - Food and Agriculture Organization
FCDO - Foreign, Commonwealth and Development Office
FY - Financial Year
GEFA - Global Evaluation Framework Agreement
GESI - Gender Equality and Social Inclusion
GIZ - German Development Agency (Gesellschaft für Internationale Zusammenarbeit)
GSP - Gender Responsive Social Protection Programme
HSOT - Humanitarian and Stabilisation Operations Team
ICF - International Climate Finance
IDS - Institute of Development Studies
IFIs - International Financial Institutions
IMDP - International Multi-Disciplinary Programme Framework Agreement
KEL - Knowledge, Evidence and Learning
KELU - Knowledge, Evidence, Learning and Uptake
KML – Knowledge Management and Learning
KPIs - Key Performance Indicators
ODA - Official Development Assistance
PFP - Programme Funded Post
PSNP - Productive Safety Net Programme
SPACE - Social Protection Approaches to COVID-19 Expert advice
SPIAC-B - Social Protection Inter-Agency Cooperation Board
SPT – Social Protection Team
STAAR - Social Protection Technical Assistance, Advice and Resources Facility
TA - Technical Assistance
TAF - Technical Assistance Facility
ToR - Terms of Reference
TSLT – Technical Senior Leadership Team
UN - United Nations
UNICEF - United Nations Children's Fund
USAID - United States Agency for International Development
VFM - Value for Money
WFP – World Food Programme

Annex B: BASIC Programme 2025 Annual Review Recommendations

- BASIC-Research to continue to maximise dissemination and uptake until the end of their contract and consider recording/producing any final standalone non-academic outputs that could be pre-emptively developed to support upcoming publications. [by 31 December 2025]
- FCDO to consider adding the risk of the programme not achieving its impact given the high ambition of the programme to its risk register and consider a mitigation plan for the final months of the programme (as outlined through some of the below recommendations). [by 31 December 2025]
- FCDO to consider how to support engagement around new publications where these take place after BASIC-Research’s contract has ended i.e. through FCDO-hosted events in 2026. [by 31 March 2026]
- STAAR to continue to maximise dissemination and uptake until the end of their contract and consider recording any final standalone webinars or podcasts that would support upcoming publications. [by 31 December 2025]
- FCDO should hold a joint meeting with BASIC-Research and STAAR to track any outstanding joint actions on dissemination and uptake before contracts close [by 31 December 2025]
- Given short timelines and anticipated progress on the 7 grantees and global activity after the BASIC programme has closed, the World Bank SPR and FCDO teams should maintain close engagement to ensure the impact of the FCV window is maximised and to galvanise other donors to scale up support [ongoing]
- Partners and the FCDO programme team should consider how they will embed sustainable exits from existing work and ensure that a future programme could build on the strong foundation established by BASIC [by 30 June 2026]

Annex C: Possible recommendations to consider in the BASIC Programme PCR (due 30 June 2026)

FCDO should use the PCR to assess:
- The BASIC programme’s design, with specific focus on
  - i) the division of functions across different implementing partners, and whether that has aided effective coordination.
  - ii) the administrative burden of the Technical Assistance Facility on both FCDO and DAI, and the extent to which value for money has both been delivered and hindered as a result of the Facility’s current operating model. This includes balancing effort between core business in a focus set of countries alongside flexibility to respond to emerging strategic opportunities; and
  - iii) minimum levels of FCDO staffing and engagement including through the post network to deliver outcome-level change.
- The risks in a gap in social protection technical advisory services after 31 December 2025, and risks of loss of institutional knowledge across key agencies.

ANNEX D – Recommendations from 2024

Recommendation	Progress to date

BASIC-Research to review what more can be built into research writing and QA processes to ensure recommendations in academic research clearly outline who they target, to do what and when (i.e. are SMART), and complement existing country stakeholder mappings and engagement plans with power analyses to identify priority institutions and individuals to target to leverage policy uptake [Action: by March 2025]	BASIC-Research continued to work with researchers across the consortium to ensure that outputs are relevant to policy and influence key stakeholders through communication, dissemination and research uptake efforts. They circulated guidance on ensuring policy relevance to lead researchers, adapted the working paper format to include policy focussed executive summaries and prioritised the publication of short policy briefs as well as longer working papers. BASIC-Research have also developed guidance on research recommendations that ensure the suggestions are specific, relevant and measurable.
BASIC-Research to conduct further analysis to understand who is being reached by online content and outputs and the impact of this engagement with research online [Action: by March 2025]	The BASIC communications team review demographic data and social media engagement quarterly to track which content is most effective. The most engaged posts were those that had a call to action or for people to get involved in discussion, as well as shorter, targeted blogs and events.
BASIC-Research to review whether adequate human/financial resource is dedicated to planning around dissemination and uptake and consider with FCDO whether this needs to be revised or research ambitions reduced to make room for stronger uptake of activities [Action: by January 2025]	BASIC has conducted a review and have a costed plan for dissemination and uptake activities which has been reviewed and agreed with FCDO.
BASIC-Research to ensure higher quality proofing and consideration over audience of reports. [Action: ongoing]	BASIC continue to review, edit and proofread outputs according to academic standards, and have also updated their guidance for working papers to give greater consideration for audiences from the outset, and updated guidelines on ensuring policy recommendations are specific, measurable and relevant.
STAAR to develop, share and agree with FCDO a BASIC portfolio plan for the final phase of the programme that considers the best mix of models (e.g. long-term advisers, draw down support), thematic priorities likely to get traction in the global policy landscape, and geographic priorities (including whether to widen focus from Africa and MENA to Asia and others) [Action: by March 2025]	Workstream planning was conducted and submitted to FCDO by mid-February. The reduction in funding meant further planning was required. This has been done in partnership with FCDO and BASIC-Research.
FCDO and STAAR to agree maximum time for ToR approval and put logframe metrics in place to measure it, and STAAR to ensure it has the right range of support functions in the wider team rather than relying too narrowly on and overburdening a few individuals [Action: by January 2025]	A new logframe metric was not added to measure ToR approval. But STAAR has adjusted internal tasking so that Facility Manager tasks are now shared across two key team members rather than resting on one individual, supported by an experienced, separate member of staff to lead on other workstreams that arise beyond the standard portfolio.
FCDO and STAAR should ensure there is appropriate allocation in budgets and planning to support learning and uptake at outcome level in the final phase and consider reducing ambition on assignments to make room for stronger uptake activities if necessary [Action: by March 2025].	Allocations for uptake were included for the final phase of the programme, and additional flexibility is provided through the flexible pool through the STAAR core team. The reduced funding for the uptake workstreams were ultimately not used for uptake and instead supported new assignments.
STAAR to ensure there is adequate Technical Senior Leadership Team (TSLT) support to quality assure assignments and build consultant capacity, particularly where local researchers lead research or act as team leaders [Action: ongoing].	TSLT support is now integrated in each assignment team and receives positive feedback from users.
STAAR to set out how it can strengthen post-assignment support within its processes, e.g. through TSLT or additional time for consultants to support uptake of recommendations and in seeking commitments from users from the outset to (as a minimum) facilitate relationships at the country level for research/KIIs and help organise a roundtable with policy maker to discuss recommendations as a prerequisite to an assignment being approved [Action: by March 2025].	Terms of reference templates have been updated to include a sustainability and uptake dimension. / Flexible pool time through core is used to encourage further uptake of assignments.
STAAR to assess the VFM of supporting embedded advisors and whether this is an effective approach to strengthening impact and uptake of recommendations [Action: by March 2025].	STAAR has developed a paper assessing VfM which is currently under quality assurance. Initial findings suggest that embedded advisers bring substantial contribution to outcome level change under certain conditions, but that similar value can be approximated with sequenced support under certain conditions.
STAAR to ensure higher quality proof reading and consideration over audience of reports. FCDO would welcome sight of assignment reports before submission too [Action: ongoing]	All materials are quality assured, proof-read and approved by users prior to publication.
STAAR and BASIC-Research to share and discuss their revised individual uptake strategies for the remainder of the programme and agree priority events and stakeholders for targeted joint uptake and influencing, and work with Integrity and FCDO to agree how to prioritise outputs to achieve outcome-level change [Action: by March 2025]	Partners participated in a workshop in November 2024 to agree in principle how to increase likelihood of achieving change at the outcome level. This was followed by a January 2025 workshop where partners explored potential themes for collaboration in dissemination and developed work plans. This was accompanied by further close work with FCDO to ensure clear deliverables were identified and agreed for uptake.
FCDO to carefully consider its own channels and strategy for championing social protection and dissemination of outputs internally, e.g. through the Social Protection Community of Practice, engagement with other key directorates centrally, and with posts [Action: by February 2025]	FCDO channels for disseminating outputs internally include: the FCDO Social Protection community of practice holds regular sessions with differing topics which have good engagement. A monthly social protection bulletin is disseminated and highlights key reports/articles and podcasts which prompts engagement from different teams around FCDO. Through our climate policy workstream we have sustained and deepened engagement on social protection across a range of teams, for example Loss and Damage and Adaptation teams. On fragility, there has been increased internal collaboration including with IFI teams ahead of the World Bank’s refreshed FCV strategy. Joint BASIC-R and STAAR uptake sessions have also been delivered for a range of FCDO advisory cadres.
STAAR and to develop a joint plan for conducting and supporting uptake of research in overlapping focus countries (e.g. in Lebanon and Yemen, as was done for Sudan), e.g. jointly undertaking KIIs where the same individuals at country levels are targeted. [Action: by February 2025]	This has continued on an ongoing basis, with joint work and approaches developed where possible. STAAR and BASIC researchers have taken part in planned uptake events and joint uptake focused projects, such as the inclusion of STAAR in BASIC-planned events in Lebanon, Amman and Nigeria.
STAAR to document and compile learning on the effectiveness of modalities (e.g. technical assistance mechanisms modelled through STAAR and ‘free to user’ model) used in the BASIC programme to feed into discussions on a successor programme, and to generate learning for other donors considering similar technical assistance programmes [Action: by March 2025]	STAAR has developed a paper assessing the role of embedded advisors which is currently under quality assurance. Initial findings suggest that embedded advisers bring substantial contribution to outcome level change under certain conditions, but that similar value can be approximated with sequenced support under certain conditions. / Ongoing KML processes will capture learning, as well as an assignment which focused on a mentorship model between CashCap and UNICEF, should also further this learning.

Annex E – BASIC Technical Assistance Outputs

Output 2.1 Use of BASIC technical assistance by FCDO, governments, agencies, and other donors

Annex 1 - EACDS, HSOT and STAAR Technical Assistance Assignments

#	Code	Title	Country or Global	Lead User	Stage	How well did the assignment achieve objectives?	How satisfied were you with the quality of the service and assignment?
EACDS
1		Support to BASIC Reporting	Global	FCDO	Closed
2		Support for BASIC Knowledge Management and Learning	Global	FCDO	Closed
3	B001	Linking Social Protection Systems and Humanitarian Cash Transfers in Nigeria	Nigeria	FCDO	Closed
4	B002	Facilitation of a workshop on linking humanitarian cash transfers with social protection (Grand Bargain Workshop)	Global	SPIAC-B	Closed
5	B003	Review of Cash Programming and Linkages to Social Protection in Lebanon	Lebanon	FCDO	Closed
6	B004	Mozambique Humanitarian Cash and Social Protection Advisor	Mozambique	FCDO	Closed
7	B005	Framework Development for Linking Humanitarian Cash and Social Protection in Yemen	Yemen	FCDO	Closed
8	B006	Review and Analysis of Identification and Registration systems in protracted and recurrent crises (MIS in Crises)	South Sudan	FCDO	Closed
9	B007	Action Framework Development for DFID Afghanistan in the Humanitarian Aid and Social Protection Nexus	Afghanistan	FCDO	Closed
10	B008	Grand-Bargain Sub-Group on Linking Humanitarian Cash and Social Protection Facilitation	Global	SPIAC-B	Closed
11	B009	Part-Time Multi-Donor Cash Adviser for the WFP Multi-Purpose Cash Programme in Lebanon	Lebanon	FCDO	Closed
12	B010	Yemen Social Protection and Humanitarian Cash Linkages Donor Coordinator	Yemen	FCDO	Closed
13	B011	Strategic Advice to DFID to strengthen the reach of the social protection system in Jordan	Jordan	FCDO	Closed
14	B012	Support to Developing the Government of Sudan National Social Protection Strategy	Sudan	Government	Closed
15	B013	Social Protection Approaches to COVID-19 Expert advice helpline (SPACE)	Global	FCDO	Closed
16	B014	Grand-Bargain sub-group on linking humanitarian cash and social protection. Knowledge Management and Learning (KML)	Global	SPIAC-B	Closed
17	B015	Social Protection Approaches to COVID-19 – Expert advice (SPACE) Phase 2	Global	FCDO/Multi	Closed
18	B017	Political Economy Analysis to inform BHC Pakistan’s Current and Future Programmes on Resilience Building and Climate Adaptation	Pakistan	FCDO	Closed
19	B018	Social Protection Approaches to COVID-19 Expert advice helpline (SPACE) - Humanitarian	Global	FCDO/Multi	Closed
HSOT
20		Humanitarian and Stabilisation Operations Team support to BASIC Inception 1	Global	FCDO	Closed
21		Humanitarian and Stabilisation Operations Team support to BASIC Inception 2	Global	FCDO	Closed
22		Humanitarian and Stabilisation Operations Team support to BASIC Inception 3	Global	FCDO	Closed
23		Humanitarian and Stabilisation Operations Team support to SPACE	Global	FCDO	Closed
24		Humanitarian and Stabilisation Operations Team support to SPACE-H	Global	FCDO	Closed
25		Humanitarian and Stabilisation Operations Team support to SPACE-Phase 2	Global	FCDO	Closed
26	B036	Humanitarian and Stabilisation Operations Team support to Nigeria	Nigeria	FCDO	Closed
27	B037	Humanitarian and Stabilisation Operations Team support to the Democratic Republic of Congo.	DRC	FCDO	Closed
28	B038	Humanitarian and Stabilisation Operations Team support to Somalia	Somalia	FCDO	Closed
29		Humanitarian and Stabilisation Operations Team support to the OPTs	OPTs	FCDO	Closed

STAAR
30	B016	REAP COP 26	N/A	FCDO	Concluded	N/A	N/A
31	B019	Lebanon Donor Coordinator	Lebanon	FCDO	Concluded	4	5
32	B021	Supporting social protection at the onset of extreme crisis and insecurity	Ethiopia	FCDO	Concluded	4	4
33	B022	Strengthening humanitarian-social protection linkages in the Ukraine regional refugee response	Ukraine	FCDO	Concluded	4	4
34	B024	Links between social protection and preventing deforestation/protecting biodiversity	Zambia	FCDO	Concluded	5	4
35	B032	Donor Coordination for Food Security and Social Safety Nets Programme	Yemen	FCDO	Implementation	Ongoing	Ongoing
36	B033	Ukraine Cash Working Group	Ukraine	Cash Working Group	Concluded	5	5
37	B034	Review of VSLAs and Self-Help Group programming within FSSN	Yemen	FCDO	Concluded	4	4
38	B039	Climate Lead	N/A	STAAR	Concluded	N/A	N/A
39	B043	Linking Shock-Responsive Social Protection with Disaster Risk Financing Assignment	N/A	FCDO	Concluded	Not provided by user.	Not provided by user.
40	B044	Digital cash transfers and transitioning from humanitarian cash to social protection	N/A	FCDO	Concluded	5	5
41	B046	Government TA for Shock Responsive Social Protection Systems	Mozambique	FCDO	Concluded	Not provided by user.	Not provided by user.
42	B047	VfM analysis of activities in FSSN from different partners, and modelling of how FDCO Yemen could optimise VfM and localisation of its funding.	Yemen	FCDO	Concluded	3	4
43	B051	Programming options for Kismayo Somalia	Somalia	GiZ	Concluded	5	5
44	B052	Strategic roadmap for the National Cash Transfer Office	Nigeria	Government	Concluded	5	5
45	B059	Conflict-sensitive social protection scoping study	Somalia	WFP	Concluded	Not provided by user.	Not provided by user.
46	B073	World Bank global partnership (through core)	N/A	FCDO	Concluded	Not required.	Not required.
47	B074	Roadmap for incoming SDA's engagement on SP	Sudan, South	FCDO	Concluded	2	3
48	B075	Making the case for climate financing social protection	N/A	FCDO	Concluded	5	4
49	B078	SPIAC B: Common principles for linking humanitarian assistance and social protection	N/A	SPIAC B/Grand Bargain	Concluded	4	5
50	B082	Kismayo, Shock Responsive Social Protection	Somalia	GIZ	Concluded	4	4
51	B086	Jordan Humanitarian Business Case	Jordan	FCDO	Concluded	5	5
52	B087	National Cash and Voucher Assistance Policy - Needs Assessment	Nigeria	Government	Concluded	Not provided by user.	Not provided by user.
53	B088	Maintaining social protection systems in response to conflict	N/A	FCDO	Concluded	Not provided by user.	Not provided by user.
54	B090	Nigeria UNICEF embedded SP in crises advisor	Nigeria	UNICEF	Implementation	4	4
55	B093	Comparative analysis East Africa	N/A	FCDO	Concluded	3	3
56	B094	Sahel Adaptive Social Protection Programme: Climate influence	"Sahel"	World Bank	Concluded	3	3
57	B097	The role of social protection in preventing and managing food crises	N/A	FAO	Concluded	Not required.	Not required.
58	B098	Synthesising lessons and promising practices for country-level coordination in the delivery of joined-up humanitarian cash and social protection.	N/A	SPIAC B/Grand Bargain	Concluded	4	4
59	B101	TRANSFORM: Social Protection in Fragile and Conflict settings	N/A	WFP	Implementation	Ongoing	Ongoing
60	B106	BASIC Learning Journey inputs	N/A	FCDO	Concluded	Not required.	Not required.
61	B107	Technical Assistance to support FCDO-World Bank Partnership on Linking Humanitarian Assistance and Social Protection in South Sudan	Sudan, South	World Bank	Concluded	Not provided by user.	Not provided by user.
62	B114	IMF program for Sri Lanka (through core)	Sri Lanka	FCDO	Concluded	Not required.	Not required.
63	B117	ADB Social Protection Conference	N/A	FCDO	Concluded	Not required.	Not required.
64	B152	Centre for Social Protection International Conference: Reimagining Social Protection in a time of Global Uncertainty	N/A	BASIC Research Team	Concluded	Not required.	Not required.
65	B158	Fragility Forum with BASIC Research	N/A	STAAR	Concluded	Not required.	Not required.
66	B160	Climate links with social protection on productive inclusion programmes in the Sahel	"Sahel"	World Bank	Concluded	3	3
67	B165	Social Health Protection document for SFD	Yemen	Local civil society organisations including coalitions of local actors and women’s groups.	Concluded	Not provided by user.	Not provided by user.
68	B173	Somaliland SRSP Review	Somalia	WFP	Concluded	Not provided by user.	Not provided by user.
69	B176	Analysis of the impact of SRSP on vulnerable groups in Haiti	Haiti	WFP	Concluded	4	5
70	B200	Scoping review on innovative climate financing for social protection in rural areas.	N/A	FAO	Implementation	Ongoing	Ongoing
71	B204	Social Protection and conflict - Response to the White Paper	N/A	FCDO	Concluded	5	5
72	B205	Coordination support to the social protection and cash and voucher technical working group for the Occupied Palestinian Territories	Occupied Palestinian Territories	ILO and CWG	Implementation	5	5
73	B219	Brazil Food Insecurity	Brazil	Government	Concluded	5	5
74	B220	Food Security Commission	N/A	FAO	Concluded	Not provided by user.	Not provided by user.
75	B221	Zambia response to the crop failure due to El Nido	Zambia	Government	Concluded	5	5
76	B223	Climate - Loss and Damage - Supporting work, feeding into the development around the fund.	N/A	FCDO	Implementation	Ongoing	Ongoing
77	B226	Ethiopia embedded advisor to the CWG	Ethiopia	Cash Working Group	Concluded	5	5
78	B229	Donor roundtable on conflict (through B204)	N/A	FCDO	Concluded	Not required.	Not required.
79	B231	Roundtable discussion on climate finance and social protection during the SBs in Bonn (through core)	N/A	FCDO	Concluded	Not required.	Not required.
80	B234	FCDO Economics conference (October 2024) (through core)	N/A	FCDO	Concluded	Not required.	Not required.
81	B235	UNICEF and CashCap mentorship pilot review	N/A	UNICEF	Concluded	Not provided by user.	Not provided by user.
82	B238	High level panel on Social Protection in Conflict	N/A	FCDO	Concluded	Ongoing	Ongoing
83	B239	Identifying Building Blocks and Enablers for Social Protection in Syria	Syria	FCDO	Implementation	Ongoing	Ongoing
84	B245	Ethiopia - Emergency Food Preparedness and Response Plan Review (through core)	Ethiopia	FCDO	Concluded	Not required.	Not required.
85	B246	Input to the CLEAN Guidance (through core)	N/A	FCDO	Concluded	Not required.	Not required.
86	B247	Sahel - Conflict Sensitive Operational Diagnostic	"Sahel"	WFP	Implementation	Ongoing	Ongoing
87	B248	Social Protection: Towards a Virtual Pooling Facility / Funding Mechanism	N/A	FCDO	Implementation	Ongoing	Ongoing
88	B278	UN Special Rapporteur on extreme poverty and human rights (through core)	N/A	OHCHR	Concluded	Not required.	Not required.
89	B281	STAAR support to the South African G20 presidency	South Africa	Government	Concluded	5	5
90	B286	Sudan - Building on what we know	Sudan	FCDO	Concluded	Pending	Pending
91	B288	FCDO Zambia: Clinic Call (through core)	Zambia	FCDO	Concluded	Not required.	Not required.
92	B293	Committee on World Food Security Side event (through core)	N/A	WFP, FAO and FCDO	Implementation	Not required.	Not required.
93	B295	Sudan Social Protection Alliance	Sudan	FCDO	Implementation	Ongoing	Ongoing
94	B300	FCDO Cadre Meetings (through core)	N/A	FCDO	Implementation	Not required.	Not required.
95	S009	TSLT support to FCDO during STAAR inception	N/A	FCDO	Concluded	N/A	N/A
96	S013	Disability Lead	N/A	STAAR	Concluded	N/A	N/A
97	S026	Scoping of the Ukraine refugee regional response	"Regional Ukraine Response"	FCDO	Concluded	5	5
98	S041	Strengthening the role of local actors in social protection in crisis contexts: supporting improved outcomes, including in gender equality and social inclusion	N/A	FCDO	Concluded	5	5
99	S043	Strengthening social protection programming for inclusive climate action in rural settings.	N/A	FAO	Implementation	Ongoing	Ongoing
100	S058	Enhancing the focus of gender responsive crisis-sensitive social protection on SocialProtection.org	N/A	FCDO	Concluded	Ongoing	Ongoing
101	S059	WFP Strategic Plan Review (through core)	N/A	WFP	Concluded	Not required.	Not required.

Annex 2 - EACDS, HSOT and STAAR Technical Assistance Assignment Countries

Key:
 * New for BASIC STAAR this year
+ Repeat user of BASIC STAAR this year

	Country	SPACE	BASIC through EACDS	STAAR BASIC	STAAR	Other e.g. HSOT	BASIC Reporting	Repeat user this year
1	Afghanistan	3	1		1		5
2	Armenia			1			1
3	Brazil	2		1			3
4	Cambodia	3					3
5	Cameroon	1					1
6	Chad			3			3	+
7	Colombia	1					1
8	Democratic Republic of the Congo	3				1	4
9	Ethiopia	2		3			4	+
10	Fiji	3					3
11	Ghana	3					3
12	Haiti			1			1	*
13	Indonesia	4					4
14	Iraq	2					2
15	Jamaica			1			1
16	Jordan	4	1	1			6
17	Kenya	4			1		5
18	Kiribati	3					3
19	Kyrgyzstan	1					1
20	Lebanon	4	2		1		7
21	Lesotho	1					1
22	Liberia	1					1
23	Madagascar	2					2
24	Malawi			1			1
25	Mali	1					1
26	Mauritania	1		3			4	+
27	Moldova			1			1
28	Mozambique	2	1	1			4
29	Myanmar			2	1		3
30	Nepal	2			1		3
31	Niger	1		3			4	+
32	Nigeria	7	1	3		1	12	+
33	OPT	3		1			4	+
34	Pakistan	4		1			5
35	Papua New Guinea	1					1
36	Peru	3					3
37	Philippines					1	1
38	Poland			1			1
39	Romania			1			1
40	Rwanda	1					1
41	Sierra Leone	2					2
42	Somalia	6		4		1	11
43	South Africa			1			1	*
44	South Sudan	5	1	2			8
45	Sri Lanka			1			1
46	Sudan	6	1	2	1		10	+
47	Syria			1			1	*
48	Tajikistan	2					2
49	Timor-Leste	3					3
50	Tonga	1					1
51	Turkey	5					5
52	Uganda	3					3
53	Ukraine			2			2
54	Venezuela	1					1
55	Yemen	3		3			6	+
56	Zambia	2		3			5	+
57	Zimbabwe	3					3
Regions
58	Caribbean	1					1
59	Overseas Territories	2					2
60	Sahel	1					1
61	Southern Africa	1					1

Annex 3 – Output 2.2 Quality of BASIC technical assistance and delivery
Output 2.2a. % of STAAR assignments commissioned by non-STAAR users with a client satisfaction score of 4 or higher out of 5 (cumulative) and Output 2.2b. % of STAAR assignments commissioned by non-STAAR users achieving stated objectives set out in original or revised ToR, with a score of 4 or higher out of 5 (cumulative)
Assignment	Was the support you received timely?	How well do you think this assignment achieved its intended objectives	How satisfied were you with the quality of the service and assignment as a whole?
B047_Framework for a localisation shift within the Yemen Humanitarian Portfolio	3	3	4
B204_Forum on social protection in fragility and conflict: Building and protecting social protection systems through the Humanitarian-Development-Peace nexus	5	5	5
B219_G20 Task Force for the establishment of a Global Alliance Against Hunger and Poverty: Social protection and food security specialist	5	5	5
B093_East Africa Comparative Analysis	3	3	3
B221_Zambia drought response preparation through social protection and cash programming	3	5	5
B094_Strengthening linkages between social protection & climate in the World Bank’s Sahel Adaptive Social Protection Programme	3	3	3
B160_Strengthening linkages between social protection & climate in productive inclusion programmes in the Sahel	2	3	3
S041_Role of Local Actors in Social Protection	5	5	5
B176_Analysis of how social protection can meet the needs of vulnerable groups in Haiti	5	4	5
B226_Ethiopia nexus and conflict sensitivity coordinator	5	5	5
B281_South Africa G20 Presidency Social Protection Specialist	5	5	5

Output 2.2c - Number of STAAR assignments commissioned by non-STAAR users that have moved from agreed ToR to delivery of agreed workplan (kick-off call within 4 months) (non-cumulative)

Assignment code	Assignment title	User
B032	Donor Coordination for Food Security and Social Safety Nets Programme	Yemen
B033	Ukraine Cash Working Group	Ukraine
B101	TRANSFORM: Social Protection in Fragile and Conflict settings	N/A
B165	Social Health Protection document for SFD	Yemen
B176	Analysis of the impact of SRSP on vulnerable groups in Haiti	Haiti
B200	Scoping review on innovative climate financing for social protection in rural areas.	N/A
B223	Climate - Loss and Damage - Supporting work, feeding into the development around the fund.	N/A
B235	UNICEF and CashCap mentorship pilot review	N/A
B238	High level panel on Social Protection in Conflict	N/A
B239	Identifying Building Blocks and Enablers for Social Protection in Syria	Syria
B247	Sahel - Conflict Sensitive Operational Diagnostic	"Sahel"
B281	STAAR support to the South African G20 presidency	South Africa
B286	Sudan - Building on what we know	Sudan
B295	Sudan Social Protection Alliance	FCDO

Annex 4 - Output 2.3 Knowledge and learning produced and disseminated by BASIC Technical Assistance
Output 2.3a - Total number products generated and disseminated under BASIC TA (this reporting period)

	Product	Product type	Date
1	Disability inclusive social protection in fragile and conflict-affected settings	Blog	11/10/2025
2	How to do political economy better in conflict settings	Blog	22/10/2025
3	STAAR Evidence Digest (Issue 20)	Evidence Digest	Nov 2024
4	Forum on social protection in fragility and conflict: Building and protecting social protection systems through the Humanitarian-Development-Peace nexus	Paper	Oct 2024
5	STAAR Evidence Digest (Issue 21)	Evidence Digest	Nov 2024
6	Digitising Social Protection in contexts of fragility and conflict – reflections from the recent Forum	Blog	10/12/2024
7	Emerging lessons on pre-agreed financing for shock-responsive social protection in Jamaica	Paper	16/01/2025
8	Emerging lessons on pre-agreed financing for shock-responsive social protection in Malawi	Paper	16/01/2025
9	Emerging lessons on pre-agreed financing for shock-responsive social protection in Mozambique	Paper	16/01/2025
10	Making Social Protection Shock-Responsive through Disaster Risk Finance Mechanisms: Synthesis Report	Paper	16/01/2025
11	STAAR Evidence Digest (Issue 22)	Evidence Digest	Jan 2025
12	Maintaining and strengthening social assistance systems in conflict settings: Yemen case study	Paper	26/02/2025
13	Maintaining and strengthening social assistance systems in conflict settings: Ethiopia case study	Paper	05/03/2025
14	STAAR Evidence Digest (Issue 23)	Evidence Digest	05/03/2025
15	Social protection in crisis: a myth buster	Paper	24/03/2025
16	Maintaining and strengthening social assistance systems in conflict settings: Sudan case study	Paper	25/03/2025
17	Maintaining and strengthening social assistance systems in conflict settings: Armenia case study	Paper	25/03/2025
18	Shock-responsive social protection in a world gone mad	Blog	27/03/2025
19	Maintaining and strengthening social assistance systems in conflict settings: Sahel case study (Niger & Burkina Faso)	Paper	07/04/2025
20	STAAR Evidence Digest (Issue 24)	Evidence Digest	07/04/2025
21	Value for Money Analysis of Emergency Multi-Purpose Cash Assistance Delivery Models in Ukraine	Paper	10/04/2025
22	A review of the shock-responsive social protection system in Mauritania	Paper	15/04/2025
23	A review of the shock-responsive social protection system in Kenya	Paper	15/04/2025
24	Comparative analysis of shock-responsive social protection systems	Paper	15/04/2025
25	Synthesising lessons and promising practices for country-level coordination in the delivery of joined-up humanitarian cash and social protection	Paper	15/04/2025
26	Maintaining and strengthening social assistance systems in conflict settings: Somalia case study	Paper	21/04/2025
27	STAAR Evidence Digest (Issue 25)	Evidence Digest	06/05/2025
28	Social Protection Explainer	Digital tool	05/2025
29	Maintaining and strengthening social assistance in conflict settings: Synthesis note	Paper	04/06/2025
30	The role of social protection in preventing and managing food crises – Climate-driven hunger	Blog	05/06/2025
31	The role of social protection in preventing and managing food crises – Nutrition	Blog	05/06/2025
32	The role of social protection in preventing and managing food crises: an emerging convergence	Blog	05/06/2025
33	Executive summary - Maintaining and strengthening social assistance in conflict settings: Synthesis note	Paper	05/06/2025
34	The role of social protection in preventing and managing food: Women’s and girls’ climate resilience	Blog	05/06/2025
35	The role of social protection in preventing and managing food crises - Conflict, Fragility, and Political Settlements	Blog	05/06/2025
36	The role of social protection in preventing and managing food crises: Urbanisation	Blog	05/06/2025
37	The role of social protection in preventing and managing food crises: Food systems, food markets and trade	Blog	05/06/2025
28	The role of social protection in preventing and managing food crises: new ideas, and some old ones that are worth repeating	Blog	05/06/2025
39	STAAR Evidence Digest: Issue 26	Evidence Digest	23/06/2025
40	Social Protection: The SDG Game-Changer We Can't Afford to Ignore	Blog	27/06/2025
41	Charting a Course for Social Protection in Sudan: Bridging Research and Policy	Paper	21/07/2025
42	The Role of Local Actors in Social Protection in Crisis Contexts	Paper	21/07/2025
43	The Role of Local Actors in Social Protection in Crisis Contexts: ANNEX COMPENDIUM	Paper	21/07/2025
44	The Role of Local Actors in Gender Responsive and Inclusive Social Protection Systems: ANNEX COMPENDIUM	Paper	21/07/2025
45	The Role of Local Actors in Gender Responsive and Inclusive Social Protection Systems	Paper	21/07/2025
46	Strengthening the Role of Local Actors in Social Protection in Crisis Context: Policy Brief	Paper	21/07/2025
47	Strengthening the Role of Local Actors in Gender- Responsive and Inclusive Social Protection (GRISP): Policy Brief	Paper	21/07/2025
48	STAAR’s “Back-to-School” Reading List…	Evidence Digest	09/09/2025

Output 2.3b - Media and social media outreach and Output 2.3bi Total number of output views disaggregated by output type – papers, blogs, digital assets (Data collected on 24/09/2025.)

	Title	Link	Number of views
Papers
1	Forum on social protection in fragility and conflict: Building and protecting social protection systems through the Humanitarian-Development-Peace nexus	https://socialprotection.org/discover/publications/forum-social-protection-fragility-and-conflict-building-and-protecting-social	1151
2	Emerging lessons on pre-agreed financing for shock-responsive social protection in Jamaica	https://socialprotection.org/discover/publications/emerging-lessons-pre-agreed-financing-shock-responsive-social-protection	187
3	Emerging lessons on pre-agreed financing for shock-responsive social protection in Malawi	https://socialprotection.org/discover/publications/emerging-lessons-pre-agreed-financing-shock-responsive-social-protection-0	183
4	Emerging lessons on pre-agreed financing for shock-responsive social protection in Mozambique	https://socialprotection.org/discover/publications/emerging-lessons-pre-agreed-financing-shock-responsive-social-protection-1	184
5	Making Social Protection Shock-Responsive through Disaster Risk Finance Mechanisms: Synthesis Report	https://socialprotection.org/discover/publications/making-social-protection-shock-responsive-through-disaster-risk-finance	236
6	Maintaining and strengthening social assistance systems in conflict settings: Yemen case study	https://socialprotection.org/discover/publications/maintaining-and-strengthening-social-assistance-systems-conflict-settings	171
7	Maintaining and strengthening social assistance systems in conflict settings: Ethiopia case study	https://socialprotection.org/discover/publications/maintaining-and-strengthening-social-assistance-systems-conflict-settings-0	77
8	Social protection in crisis: a myth buster	https://socialprotection.org/discover/publications/social-protection-crisis-myth-buster	238
9	Maintaining and strengthening social assistance systems in conflict settings: Sudan case study	https://socialprotection.org/discover/publications/maintaining-and-strengthening-social-assistance-systems-conflict-settings-1	159
10	Maintaining and strengthening social assistance systems in conflict settings: Armenia case study	https://socialprotection.org/discover/publications/maintaining-and-strengthening-social-assistance-systems-conflict-settings-4	63
11	Maintaining and strengthening social assistance systems in conflict settings: Sahel case study (Niger & Burkina Faso)	https://socialprotection.org/discover/publications/maintaining-and-strengthening-social-assistance-systems-conflict-settings-2	209
12	Value for Money Analysis of Emergency Multi-Purpose Cash Assistance Delivery Models in Ukraine	https://socialprotection.org/discover/publications/value-money-analysis-emergency-multi-purpose-cash-assistance-delivery-models	124
13	A review of the shock-responsive social protection system in Mauritania	https://socialprotection.org/discover/publications/review-shock-responsive-social-protection-system-mauritania	55
14	A review of the shock-responsive social protection system in Kenya	https://socialprotection.org/discover/publications/review-shock-responsive-social-protection-system-kenya	118
15	Comparative analysis of shock-responsive social protection systems	https://socialprotection.org/discover/publications/comparative-analysis-shock-responsive-social-protection-systems	243
16	Synthesising lessons and promising practices for country-level coordination in delivery of joined-up humanitarian cash and social protection	https://socialprotection.org/discover/publications/synthesising-lessons-and-promising-practices-country-level-coordination	485
17	Maintaining and strengthening social assistance systems in conflict settings: Somalia case study	https://socialprotection.org/discover/publications/maintaining-and-strengthening-social-assistance-systems-conflict-settings-3	185
18	Maintaining and strengthening social assistance in conflict settings: Synthesis note	https://socialprotection.org/discover/publications/maintaining-and-strengthening-social-assistance-conflict-settings-synthesis	308
19	Executive summary - Maintaining and strengthening social assistance in conflict settings: Synthesis note	https://socialprotection.org/discover/publications/executive-summary-maintaining-and-strengthening-social-assistance-conflict	112
20	Charting a Course for Social Protection in Sudan: Bridging Research and Policy	https://socialprotection.org/discover/publications/charting-course-social-protection-sudan-bridging-research-and-policy	159
21	The Role of Local Actors in Social Protection in Crisis Contexts	https://socialprotection.org/discover/publications/role-local-actors-social-protection-crisis-contexts	29
22	The Role of Local Actors in Social Protection in Crisis Contexts: ANNEX COMPENDIUM	https://socialprotection.org/discover/publications/role-local-actors-social-protection-crisis-contexts-annex-compendium	17
23	The Role of Local Actors in Gender Responsive and Inclusive Social Protection Systems: ANNEX COMPENDIUM	https://socialprotection.org/discover/publications/role-local-actors-gender-responsive-and-inclusive-social-protection-systems	13
24	The Role of Local Actors in Gender Responsive and Inclusive Social Protection Systems	https://socialprotection.org/discover/publications/role-local-actors-gender-responsive-and-inclusive-social-protection-systems-0	44
25	Strengthening the Role of Local Actors in Social Protection in Crisis Context: Policy Brief	https://socialprotection.org/discover/publications/strengthening-role-local-actors-social-protection-crisis-context-policy-brief	21
26	Strengthening the Role of Local Actors in Gender- Responsive and Inclusive Social Protection (GRISP): Policy Brief	https://socialprotection.org/discover/publications/strengthening-role-local-actors-gender-responsive-and-inclusive-social	29
27	How social protection can better meet the needs of the most vulnerable in Haiti: the case of internally displaced persons	https://socialprotection.org/discover/publications/how-social-protection-can-better-meet-needs-most-vulnerable-haiti-case	37
28	Comment la protection sociale pourrait mieux répondre aux besoins des plus vulnérables en Haïti : le cas des personnes déplacées internes	https://socialprotection.org/fr/discover/publications/comment-la-protection-sociale-pourrait-mieux-r%C3%A9pondre-aux-besoins-des-plus	9
Blogs
29	Disability inclusive social protection in fragile and conflict-affected settings	https://socialprotection.org/discover/blog/disability-inclusive-social-protection-fragile-and-conflict-affected-settings	115
30	How to do political economy better in conflict settings	https://socialprotection.org/discover/blog/how-do-political-economy-better-conflict-settings	124
31	Digitising Social Protection in contexts of fragility and conflict – reflections from the recent Forum	https://socialprotection.org/discover/blog/digitising-social-protection-contexts-fragility-and-conflict-%E2%80%93-reflections-recent	339
32	Shock-responsive social protection in a world gone mad	https://socialprotection.org/discover/blog/shock-responsive-social-protection-world-gone-mad	234
33	Displacement Crisis in Haiti: A Call for Inclusive Social Assistance	https://socialprotection.org/discover/blog/displacement-crisis-haiti-call-inclusive-social-assistance	104
34	The role of social protection in preventing and managing food crises – Climate-driven hunger	https://socialprotection.org/discover/blog/role-social-protection-preventing-and-managing-food-crises-%E2%80%93-climate-driven-hunger	59
35	The role of social protection in preventing and managing food crises - Nutrition	https://socialprotection.org/discover/blog/role-social-protection-preventing-and-managing-food-crises-nutrition	56
36	The role of social protection in preventing and managing food crises: an emerging convergence	https://socialprotection.org/discover/blog/role-social-protection-preventing-and-managing-food-crises-emerging-convergence	69
37	The role of social protection in preventing and managing food: Women’s and girls’ climate resilience	https://socialprotection.org/discover/blog/role-social-protection-preventing-and-managing-food-women%E2%80%99s-and-girls%E2%80%99-climate	62
38	The role of social protection in preventing and managing food crises - Conflict, Fragility, and Political Settlements	https://socialprotection.org/discover/blog/role-social-protection-preventing-and-managing-food-crises-conflict-fragility-and	86
39	The role of social protection in preventing and managing food crises: Urbanisation	https://socialprotection.org/discover/blog/role-social-protection-preventing-and-managing-food-crises-urbanisation	142
40	The role of social protection in preventing and managing food crises: Food systems, food markets and trade	https://socialprotection.org/discover/blog/role-social-protection-preventing-and-managing-food-crises-food-systems-food-markets	80
41	The role of social protection in preventing and managing food crises: new ideas, and some old ones that are worth repeating	https://socialprotection.org/discover/blog/role-social-protection-preventing-and-managing-food-crises-new-ideas-and-some-old-ones	152
42	Social Protection: The SDG Game-Changer We Can't Afford to Ignore	https://socialprotection.org/discover/blog/social-protection-sdg-game-changer-we-cant-afford-ignore	109
43	STAAR’s “Back-to-School” Reading List…	https://socialprotection.org/discover/blog/staar%E2%80%99s-%E2%80%9Cback-school%E2%80%9D-reading-list%E2%80%A6	51
Evidence Digests
44	Evidence Digest 19	https://socialprotection.org/discover/publications/staar-evidence-digest-issue-19	92
45	Evidence Digest 20	https://socialprotection.org/discover/publications/staar-evidence-digest-issue-20	79
46	Evidence Digest 21	https://socialprotection.org/discover/publications/staar-evidence-digest-issue-21	78
47	Evidence Digest 22	https://socialprotection.org/discover/publications/staar-evidence-digest-issue-22	64
48	Evidence Digest 23	https://socialprotection.org/discover/publications/staar-evidence-digest-issue-23	36
49	Evidence Digest 24	https://socialprotection.org/discover/publications/staar-evidence-digest-issue-24	40
50	Evidence Digest 25	https://socialprotection.org/discover/publications/staar-evidence-digest-issue-25	59
51	Evidence Digest 26	https://socialprotection.org/discover/publications/staar-evidence-digest-issue-26	26
Digital assets
52	Responsive social protection systems: an explainer	https://staarexplainer.socialprotection.org/	1,119
53	Interactive Gender Guidance Note	https://a-socialprotectiondev.vev.site/gender	45
54	STAAR web page	https://staar.socialprotection.org/	967

Annex 5 Output 3.1 Knowledge and learning events organised or presented at by BASIC Technical Assistance
Output 3.1a - Number of events targeting external audiences organised by supplier (cumulative)
	Event name	Date
1	Using social assistance to promote climate resilience [in fragile and conflict contexts] – webinar	10/8/2024
2	Forum on Social Protection in Fragility and Conflict: Building and protecting social protection systems through the Humanitarian-Development-Peace nexus	15-17/10/2024
3	Complexities and explore practical solutions for making social protection information systems more flexible and effective	8/11/2024
4	STAAR long-term adviser learning group – forum reflections and discussions	21/11/2024
5	Reflections from the Forum on Social Protection in Fragility and Conflict - webinar	26/11/2024
6	Maintaining and sustaining social protection in conflict and fragile settings – webinar	14/01/2025
7	B220- Food Security Commission Final Workshop	Feb-25
8	The role of localisation in delivering more effective social protection in crises – webinar	27/02/2025
9	Social Protection in Conflict and Protracted Crisis Series Ep. 1 | Women and Other Marginalised Groups in Fragile Contexts	28/02/2025
10	Validating Research Findings on Conflict-Sensitive Social Protection in Ethiopia – workshop	Mar-25
11	STAAR long-term adviser learning group – Sahel and World Bank deep dive	6/3/2025
12	Humanitarian Networks and Partnership Week Session 1: Why Should Humanitarians care about social protection	24/03/2025
13	Humanitarian Networks and Partnership Week Session 2: Localising social protection in crisis response: the case for empowering local actors	25/03/2025
14	Social Protection in Conflict and Protracted Crisis Series Ep. 2 | Localisation and local social protection systems in conflict and crisis	28/03/2025
15	Social Protection in Conflict and Protracted Crisis Series Ep. 3 | Humanitarian, Development & Peace Nexus Approach	30/04/2025
16	Charting a Course for Social Protection in Sudan: Bridging Research and Policy workshop	22-23/05/2025
17	High Level Panel meeting 1
18	Brown Bag Session - High-Level Panel on Social Protection in FCAS	17/07/2025
19	Learning event to FCDO colleagues on the Comparative analysis of shock-responsive social protection systems	5/12/2025
20	High-Level Panel meeting 2	19/09/25

Output 3.1b - Quality of events organised by supplier (% of events with average participant feedback score above midpoint score) (non-cumulative)

	Event	Feedback score
1	Using social assistance to promote climate resilience [in fragile and conflict contexts] What do we know and what needs to change – webinar	4.4
2	Forum on Social Protection in Fragility and Conflict: Building and protecting social protection systems through the Humanitarian-Development-Peace nexus	4.5
3	Reflections from the Forum on Social Protection in Fragility and Conflict – webinar	4.6
4	Maintaining and sustaining social protection in conflict and fragile settings – webinar	4.6
5	The role of localisation in delivering more effective social protection in crises – webinar	4.2
6	Learning from Ukraine: Leveraging the Social Protection System to Respond to the Full-Scale Invasion - webinar	4.2
7	Charting a Course for Social Protection in Sudan: Bridging Research and Policy workshop	4.1
8	Brown Bag Session - High-Level Panel on Social Protection in FCAS	4.5

Output 3.1c - Number of events presented at by supplier technical assistance (cumulative)

	Name of event	Date of event
1	STAAR gender lead moderating SP.org webinar on 5 December on Harnessing social protection for gender equality, resilience and transformation	Dec 24
2	The Climate Lead presented at the FCDO SDA PDC	Jan 25
3	B107 Zoirjon Sharipov presentation for the CWG /PSPWG/NSPWG South Sudan on Options Paper	Feb 25
4	B160 STAAR presentation of findings on climate change adaptation opportunities for Hodh el Chargu to World Bank Economic inclusion Group	April 2025
5	B281 G20 South Africa – STAAR attended the DWG3 meeting (24-28 May) where the Draft 1 was presented and STAAR (Senzelwe and Lauren) gave a presentation on our proposed actions for the current and new commitments for the Accountability Framework	May 2025
6	Age-Sensitivity of Social Assistance in the Kingdom of Eswatini – STAAR asked to present by DPMO	May 2025
7	Amman Donor Coordination for Cash and Social Protection Programming presentation	Jul 25
8	Anna McCord and Katerine Cooke at British Expertise International on B200 Scoping review (climate financing for SP in rural areas)	Sep 25
9	Carla Lacerda was invited as a Guest on the Social Protection Podcast to speak about B205	Sep 25
10	Ric participated in the Resilience and Adaptation Fund FCDO post-network call	Sep 25
11	Edward Archibald presenting on political economy at the IDS - BASIC Research conference on ‘Social and Humanitarian Assistance in Crises’	Sep 25
12	Carla Lacerda presenting B205 at IDS - BASIC Research conference on ‘Social and Humanitarian Assistance in Crises’ conference – Palestine OPT	Sep 25
13	Ric presenting B093 comparative analysis at IDS - BASIC Research conference on ‘Social and Humanitarian Assistance in Crises’	Sep 25
14	Valentina presented B088 maintenance systems in conflict at IDS - BASIC Research conference on ‘Social and Humanitarian Assistance in Crises’	Sep 25
15	Laura Phelps presented B098 coordination across the nexus at IDS - BASIC Research conference on ‘Social and Humanitarian Assistance in Crises’	Sep 25
16	Strengthening social protection programming for inclusive climate action in rural settings	Sep 25

Output 3.2 Delivery of BASIC knowledge management and learning strategy (BASIC Technical Assistance)

Output 3.2a - Delivery of jointly organised learning events, including those between suppliers (KELU quarterly meetings and follow-up discussions on opportunities for information sharing/strengthened collaborative approaches) those targeting external stakeholders (non-cumulative)

	Name of event	Date of event
1	Webinar: Using social assistance to promote climate resilience [in fragile and conflict contexts] What do we know and what needs to change?	08/10/24
2	Webinar: Reflections from the Forum on Social Protection in Fragility and Conflict	26/11/24
3	Webinar: Maintaining and sustaining social protection in conflict and fragile settings	14/01/25
4	Webinar: The role of localisation in delivering more effective social protection in crises	27/02/25
5	Event: HNPW: Why should humanitarians care about social protection	March 2025
6	Event: HNPW: Localising Social Protection in Crisis Response: the Case for Empowering Local Actors	March 2025
7	KELU Meeting:	10/12/25
8	KELU Meeting:	17/06/25

Output 3.2b Qualitative examples of where coordination between STAAR and BASIC Research on specific assignments, research/non-academic outputs, influencing activities or monitoring/evaluation efforts has strengthened quality (non-cumulative)

	Example	Date
1	Rachel and Jeremy Lind met Lili Mohidin and Chachi Bezuneh in Addis (STAAR consultants preparing the conflict sensitivity study)	Oct-Dec 2024
2	Jeremy Lind joined two calls with STAAR to plan the sp.org hosted joint STAAR/BASIC webinar on climate	Oct-Dec 2024
3	Becky Carter had meetings with STAAR to coordinate the studies on Sudan and to begin thinking about a Sudan engagement event proposed be Ed Barney	Oct-Dec 2024
4	Paul Harvey had discussions with STAAR to coordinate roles in planning and contributing BASIC-R and STAAR insights to the proposed high-level panel	Oct-Dec 2024
5	There have been calls between BASIC R and STAAR(Sophie and Gabrielle) to get their insights into the World Bank approach paper country studies	Oct-Dec 2024
6	Paul had further discussions with STAAR on his work on the World Bank approach paper to support their work on Ukraine. (January)	Jan-Mar 2025
7	The BASIC R Climate Global Review paper has been reviewed by Anna McCord of STAAR. Anna also joined an internal BASIC webinar to explore key findings from the Global Review. This session highlighted emerging messages and insights on how international actors’ mainstream climate challenges in their social protection work.	Jan-Mar 2025
8	Alan Stanley met with Charlotte and other STAAR colleagues to share information and coordinate planning around engagement and uptake plans and activities. In this quarter these meetings focused on planning and coordination around the sp.org webinar series and podcast and the two HNPW sessions. BASIC R also shared information on country engagement plans and updates stakeholder mappings along with a draft communications workplan, which documents planned BASIC R engagement activities and outputs with expected dates.	Jan-Mar 2025
9	Jeremy Lind reviewed the STAAR Ethiopia shock responsive paper by Daniel Hailu.	Jan-Mar 2025
10	Calum McClean has fed BASIC-R findings on interoperability into his STAAR role on donor coordination in Yemen.	Jan-Mar 2025
11	There was a joint STAAR/BASIC R meeting with FCDO Yemen on 11th February following on from which a joint summary of key messages was produced for FCDO highlighting Yemen research across both parts of the programme.	Jan-Mar 2025
12	BASIC R and STAAR liaised to submit joint proposals for panels at HNPW – two panels were accepted.	Jan-Mar 2025
13	Rebecca Holmes (STAAR) reviewed the BASIC-R Targeting synthesis paper.	Apr-Jun 2025
14	Jackie Shaw (BASIC-R) liased with STAAR about joining with them on engagement and uptake plans with government officials in Uganda.	Apr-Jun 2025
15	BASIC R and STAAR have collaborated around global review webinars (accountability, politics, climate)	Jul-Sep 2025
16	BASIC R and STAAR collaborated on planning joint presentations for FCDO cadres	Jul-Sep 2025
17	Paul Harvey has been coordinating with STAAR on an a possible approach to engaging with Gulf States on our research findings. STAAR have now approved the work on Gulf State donors. Paul will be contributing to a piece of work with STAAR focussed on better understanding the role that Gulf State donors are playing in supporting social protection in crises and using that to discuss with Gulf State donors in a workshop looking at how BASIC research and STAAR findings can inform their approaches.	Jul-Sep 2025
18	Anna McCord at STAAR has reviewed the Climate, Social Protection and Conflict: From past trends and crises to future storylines Working paper written by RCCC.	Jul-Sep 2025
19	Valentina Barca of STAAR reviewed the Targeting Global Review working paper.	Jul-Sep 2025

Output 3.2c Terms of Reference and plans shared as relevant between BASIC-Research and STAAR (non-cumulative)

	Example	Date

1	BASIC-R emailed STAAR with the quarterly project update detailing all project plans and methodology and update on current project activities for Q2 2024/25.	Oct-Dec 2024
2	Sophia Swithern and Paul Harvey have had multiple calls and emails with STAAR colleagues to discuss the financing work – to share a draft concept note and coordinate plans for a possible phase 2 of the research	Oct-Dec 2024
3	January 2025 BASIC-R emailed STAAR with the quarterly project update detailing all project plans and methodology and update on current project activities for Q3 2024/25.	Jan-Mar 2025
4	BASIC-R shared its stakeholder mapping on Lebanon and Yemen in February	Jan-Mar 2025
5	STAAR shared details of thematic working groups following the engagement workshop in January.	Jan-Mar 2025
6	Shared the BASIC-R final year uptake and engagement strategy with STAAR in May. This was then used for the background of discussions at the June KELU meeting.	Apr-Jun 2025
7	Emails between Megan Smith and Ollie Burch clarifying planned country engagement activities and opportunities for including STAAR identified stakeholders.	Apr-Jun 2025
8	April 2025 BASIC-R emailed STAAR with the quarterly project update detailing all project plans and methodology and update on current project activities for Q4 2024/25.	Apr-Jun 2025
9	July 2025 BASIC-R emailed STAAR with the quarterly project update detailing all project plans and methodology and update on current project activities for Q1 2025/26.	Jul-Sep 2025
10	In advance of the meeting with FCDO in early August STAAR and BASIC shared key messages and current engagement plans	Jul-Sep 2025

ANNEX F – BASIC Research Outputs
Annex 1 – Output 1.1 Number of high-quality open access academic outputs on critical global themes and from focus countries (e.g. Peer reviewed journal articles, working papers, and book chapters which meet FCDO research quality standards) published or accepted for publication (cumulative)

	Name of BASIC Research Academic document	Type of document (journal, working paper)	Citation link
1	Those with Big Phones have the Upper Hand’: Political, Gender and Digital Exclusions in Cash and Voucher Assistance in North East Nigeria	Working Paper 25	https://www.ids.ac.uk/publications/those-with-big-phones-have-the-upper-hand-political-gender-and-digital-exclusions-in-cash-and-voucher-assistance-in-north-east-nigeria/
2	Social Assistance and Coping with Crises in Borno, Nigeria	Working Paper 31	https://www.ids.ac.uk/publications/social-assistance-and-coping-with-crises-in-borno-nigeria/
3	The Politics of Social Assistance in Lebanon: Social Protection, Sectarianism, and Lebanon’s Fragmented Social Contract	Working Paper 32	https://www.ids.ac.uk/publications/the-politics-of-social-assistance-in-lebanon-social-protection-sectarianism-and-lebanons-fragmented-social-contract
4	The Role of Social and Humanitarian Assistance for Supporting Lives and Livelihoods During the 2021‒22 Tigray Crisis	Working Paper 33	https://www.ids.ac.uk/publications/the-role-of-social-and-humanitarian-assistance-for-supporting-lives-and-livelihoods-during-the-2021%E2%80%9222-tigray-crisis/
5	A Bridge to Those in Need’ Frontline Provider Perspectives on the Accountability of Social Assistance in the Kurdistan Region of Iraq	Working Paper 34	https://www.ids.ac.uk/publications/a-bridge-to-those-in-need-frontline-provider-perspectives-on-the-accountability-of-social-assistance-in-the-kurdistan-region-of-iraq/
6	Poverty Dynamics and Social Assistance Amidst Intersecting Crises in Nigeria	Working Paper 35	https://www.ids.ac.uk/publications/poverty-dynamics-and-social-assistance-amidst-intersecting-crises-in-nigeria/
7	Towards Inclusive Social Assistance for Marginalised People in East and Northeast Uganda	Working Paper 36	https://www.ids.ac.uk/publications/towards-inclusive-social-assistance-for-marginalised-people-in-east-and-northeast-uganda/
8	Can Social Protection Programmes Promote Livelihoods and Climate Resilience in Conflict‑Affected Settings? Evidence from Ethiopia’s Productive Safety Net Programme	Working Paper 37	https://www.ids.ac.uk/publications/can-social-protection-programmes-promote-livelihoods-and-climate-resilience-in-conflict%e2%80%91affected-settings-evidence-from-ethiopias-productive-safety-net-programme/
9	Fragmented Power, Access and Legitimacy: The Politics of Social Assistance in Yemen’s Conflict (2014-2024)	Working Paper 38	https://www.ids.ac.uk/publications/fragmented-power-access-and-legitimacy-the-politics-of-social-assistance-in-yemens-conflict-2014-24/
10	Reframing the Accountability of Social Assistance in Crises: Emerging Evidence and Promising Practices	Working Paper 39	https://www.ids.ac.uk/publications/reframing-the-accountability-of-social-assistance-in-crises-emerging-evidence-and-promising-practices/
11	Supporting Mutual Aid in Sudan: Conflict-Sensitive Approaches to Risk and Accountability	Working Paper 40	https://www.ids.ac.uk/publications/supporting-mutual-aid-in-sudan-conflict-sensitive-approaches-to-risk-and-accountability/
12	Financing Social Protection in Protracted Crises	Working Paper 41	https://www.ids.ac.uk/publications/financing-social-protection-in-protracted-crises/
13	The Political Economy of Lebanon’s Financial Crisis	Working Paper 42	https://www.ids.ac.uk/publications/the-political-economy-of-lebanons-financial-crisis/
14	A Global Review of Climate Change and Social Protection in Protracted Crisis Contexts	Working Paper 43	https://www.ids.ac.uk/publications/a-global-review-of-climate-change-and-social-protection-in-protracted-crisis-contexts/
15	Institutional Perspectives on Targeting in North East Nigeria in the Humanitarian and Social Protection Sectors	Working Paper 44	https://www.ids.ac.uk/publications/institutional-perspectives-on-targeting-in-the-humanitarian-and-social-protection-sectors-in-north-east-nigeria/
16	Local social solidarity and mutual assistance mechanisms in Niger : a rich and varied repertoire for resilience and crisis response.	Working Paper 46	https://www.ids.ac.uk/publications/local-social-solidarity-and-mutual-assistance-mechanisms-in-niger-a-rich-and-varied-repertoire-for-resilience-and-crisis-response/
17	Social protection and resilience in protracted crises. International Social Security Review, 78: 173–190	Journal Article	https://doi.org/10.1111/issr.70000
18	Social protection in times of conflict: Evidence from Ethiopia	UNU WIDER Working Paper 2025/9 (co-branded BASIC Research output)	https://www.wider.unu.edu/publication/social-protection-times-conflict
19	The limits to cash-plus provision in protracted crises	Journal Article	https://doi.org/10.1111/dpr.70020 https://opendocs.ids.ac.uk/articles/journal_contribution/The_Limits_to_Cash-plus_Provision_in_Protracted_Crises/29412947/1?file=55677965
20	Reimagining Social Protection, IDS Bulletin Vol 55 No. 2	Journal Special Issue	https://doi.org/10.19088/1968-2024.115

Annex 2 – Output 1.2 No. of non-academic research outputs on critical global themes and in focus countries (e.g. blogs, articles, presentations) and policy outputs (e.g. policy briefs, rapid response briefs, presentations to policy audiences) (cumulative)

	Name of BASIC Research Non-Academic document	Type of document (journal, working paper)	Citation link

1	Mind the gap – What forms of social protection might replace subsidies in post-Assad Syria?	Blog	https://www.ids.ac.uk/opinions/mind-the-gap-what-forms-of-social-protection-might-replace-subsidies-in-post-assad-syria/
2	Reimagining Social Assistance in the Kurdistan Region of Iraq: The Vital Role of Local Organisations	Blog	https://socialprotection.org/discover/blog/reimagining-social-assistance-kurdistan-region-iraq-vital-role-local-organisations
3	How to finance social protection finance in protracted crises: Five lessons	Blog	https://www.ids.ac.uk/opinions/how-to-finance-social-protection-finance-in-protracted-crises-five-lessons/
4	2. Financing for social protection in 2025 and beyond: anyone any clearer?	Blog	https://www.ids.ac.uk/opinions/financing-for-social-protection-in-2025-and-beyond-anyone-any-clearer/
5	Gaps in Lebanon’s social assistance for IDPs during the recent Israeli war	Blog	https://www.ids.ac.uk/opinions/gaps-in-lebanons-social-assistance-for-idps-during-the-recent-israeli-war/
6	How can we reimagine social protection in an uncertain world? IDS ‘Between the Lines podcast. Rachel Sabates Wheeler	Podcast	https://www.ids.ac.uk/events/podcast-s06-ep7-how-can-we-reimagine-social-protection-in-an-uncertain-world/
7	Fred Merttens participated in the Impact & Beyond podcast by Dr Michele Binci on Ethiopia Social Protection and Humanitarian assistance	Podcast	https://michelebinci.substack.com/p/the-fred-merttens-one
8	Women and Other Marginalised Groups in Fragile Contexts Rachel Sabates Wheeler took part in the first episode of a three-part podcast series on "Social Protection in Conflict and Protracted Crisis", produced by socialprotection.org in partnership with FCDO & STAAR	Podcast	https://socialprotection.org/learn/podcasts/social-protection-conflict-and-protracted-crisis-series-ep-1-women-and-other
9	Reimagining social security in fragile and conflict-affected settings. Philip Proudfoot in conversation with Cynthia Saghir (Oxfam Lebanon), produced by Development Pathways	Podcast	https://open.spotify.com/episode/1tAIxYUqeLleIkjFrpASI4
10	Intersecting Exclusion in Digital Cash and Voucher Assistance in Nigeria	Policy Briefing 04	https://www.ids.ac.uk/publications/intersecting-exclusion-in-digital-cash-and-voucher-assistance-in-nigeria/
11	The Politics of Social Assistance in Lebanon	Policy Briefing 05	https://www.ids.ac.uk/publications/the-politics-of-social-assistance-in-lebanon/
12	Designing Social Assistance Programmes for Displaced People	Policy Briefing 06	https://www.ids.ac.uk/publications/designing-social-assistance-programmes-for-displaced-people/
13	Supporting Mutual Aid in Sudan	Policy Briefing 07	https://www.ids.ac.uk/publications/supporting-mutual-aid-in-sudan/
14	Tackling Political Barriers to Effective Social Assistance in Nigeria	Policy Briefing 08	https://www.ids.ac.uk/publications/tackling-political-barriers-to-effective-social-assistance-in-nigeria/
15	Social Assistance and Poverty Reduction Amidst Multiple Crises	Policy Briefing 09	https://www.ids.ac.uk/publications/social-assistance-and-poverty-reduction-amidst-multiple-crises/
16	Local Solidarity Mechanisms for Resilience and Crisis Response in Niger	Policy Briefing 10
17	Growth from Below: Poverty Reduction beyond Social Protection in Nigeria	Policy Briefing 11
18	Climate Change and Social Protection in Protracted Crises	Policy Briefing 12	https://www.ids.ac.uk/publications/climate-change-and-social-protection-in-protracted-crises/
19	Protecting the Gains: using social protection to sustain progress in protracted crises.	Research Briefing
20	Is Poverty Underestimated Because Males and Females Report Food Security and Food Expenses Differently?	Research Briefing 4	https://www.ids.ac.uk/publications/is-poverty-underestimated-because-males-and-females-report-food-security-and-food-expenses-differently/
21	Climate Change, Conflict, Food Security and Social Protection in Niger	Research Briefing 5	https://www.ids.ac.uk/publications/climate-change-conflict-food-security-and-social-protection-in-niger/
22	Graduation from Social Protection: Removed, Ready or Rotated?	Research Briefing 6	https://www.ids.ac.uk/publications/graduation-from-social-protection-removed-ready-or-rotated/
23	Compilation video featuring Julie Lawson McDowall, Charis Reid, Getu Demeke Alene & Dr Tahir Zaman promoting the IDS Social Protection Bulletin	video	https://www.linkedin.com/feed/update/urn:li:activity:7257370093397946368
24	Dr Tahir Zaman reflection on the evolving role of the humanitarian sector	video	https://www.linkedin.com/feed/update/urn:li:activity:7267915214329667585
25	Syria in Transition: What's Happening to Social Protection in Syria?	Proximity Research Briefing	https://f7a63f40-0af6-472c-b6b6-76fe93263b1c.usrfiles.com/ugd/f7a63f_b91909688a3f426ea4522b2a3d4c671e.pdf

Annex 3 – Output 1.3 Number of operational and policy recommendations specifically about gender, age, disability and intersecting vulnerabilities (cumulative)

	Output containing recommendations	Detail	Theme

1	Social Assistance and Coping with Crises in Borno, Nigeria (Working Paper 31)	Complement social assistance with insurance products Insurance mechanisms can also help complement and improve the effectiveness of social assistance. Like most part of Nigeria, insurance services are largely absent in Borno state. Accurately estimating the risk in conflicts situation is difficult, and given high levels of poverty and low financial inclusion, this could make private financial systems reluctant to provide such services due to multifaceted risks such as migration and insecurity. Insurance programmes by the federal government such as NIRSAL have limited coverage. Climate financing options face similar challenges. To address the challenges posed by climate shocks on food security and poverty, it is crucial to strengthen climate-resilient insurance products as well. This would include insurance to guard against asset loss prevalent in the two LGAs, credit insurance to guard against potential debt spirals from loans, and weather indexed insurance to mitigate the profound negative effects of climate-related disasters on agricultural production. Ensuring that women farmers are able to benefit from these products is important given the negative gendered effects of drought on agricultural production identified in the analysis. Crop and livestock insurance can also be important in ensuring that conflict does not have profoundly negative effects on agricultural production. Learnings from index-based livestock insurance and weather-based insurance should be carefully considered in design of such programmes to ensure that both supply-side and demand-side challenges are overcome	Inclusion
2	Politics of SA in Lebanon	Establish mechanisms to monitor implementation of the NSPS, ensuring transparency and accountability. Civil society can act as a watchdog to prevent corruption and ensure that reforms benefit the most vulnerable populations.	Politics
3	BASIC Research Working Paper 35. Poverty Dynamics and Social ‍Assistance Amidst Intersecting Crises in Nigeria	Promote equity-centred economic policy responses: Reducing the impacts of inflation on poor households can be supported by intervening in key markets and imposing price controls for goods commonly consumed by poor households during periods of heightened crises, and mitigating its impact through social protection. It will also be critical to ensure that more micro-level economic promotion policies are directed to youth and women	Inclusion
4	BASIC Research Working Paper 35. Poverty Dynamics and Social ‍Assistance Amidst Intersecting Crises in Nigeria	Address underlying structural challenges: This includes the need for better infrastructure (such as roads, water supply, and electricity) in disadvantaged regions, and providing free or subsidised health care and measures to support user costs of education for children from poor households. If effectively implemented through a focus on risk and equity, these interventions could reduce poverty by addressing the root causes of crises and vulnerabilities that they may otherwise amplify.	Inclusion
5	BASIC Research Briefing 4. Is poverty underestimated because males and females report food security and food expenses differently?	The findings suggest that social protection programmes, like the PSNP, will benefit from a gender-sensitive design in terms of targeting, distribution and evaluation. Data collection for purposes of poverty measurement must consider who is the most appropriate and knowledgeable respondent as doing so will have significant impacts on the lives of the poorest households	Climate
6	BASIC Research Briefing 4. Is poverty underestimated because males and females report food security and food expenses differently?	Improved household survey design on food security and consumption to account for gender-specific differences in reporting. Including both male and female respondents in food security surveys could prevent gendered under- or over-reporting.	Climate
7	BASIC Research Briefing 4. Is poverty underestimated because males and females report food security and food expenses differently?	Holistic understanding of food expenditure and consumption to account for how gender roles shape the division of labour and responsibilities within households and the wider food environment, which extends to how food consumption and expenditure are perceived and reported. Further studies should focus on the drivers of gendered differences in food reporting.	Climate
8	BASIC Research Briefing 4. Is poverty underestimated because males and females report food security and food expenses differently?	Gender-sensitive food security programmes since women are more attuned to moderate food insecurity. Such programmes could benefit from focusing on women’s unique coping strategies and perceptions to ensure a more nuanced understanding of household vulnerabilities. If women employ self sacrificing strategies to shield their children from food scarcity (Piperata et al. 2013), this is likely to appear in their assessments of household-level food insecurity.	Climate
9	BASIC Research Briefing 4. Is poverty underestimated because males and females report food security and food expenses differently?	Rethinking poverty metrics. On average, taking a male respondent’s view on household food expenditures and food security would underestimate the poverty ranking of that household relative to others. In other words, higher male reported expenditures mean the household would be ranked as richer compared to others. This could result in the exclusion of households from poverty assistance programmes. In contrast, had the females responded to the targeting surveys, the same households would more likely be recognised as eligible for assistance.	Climate
10	BASIC Research Working Paper 39. Reframing the Accountability of Social Assistance in Crises: Emerging Evidence and Promising Practices	Support collective approaches to accountability and learning that are not project specific (so inclusive approaches become systemic rather than projected)	Inclusion
11	BASIC Research Working Paper 39. Reframing the Accountability of Social Assistance in Crises: Emerging Evidence and Promising Practices	Put the basics in place: In too many crises, people still have limited awareness about what assistance is available, who is eligible, and how to complain or provide feedback if there are problems with eligibility or delivery.	Inclusion
12	BASIC Research Working Paper 39. Reframing the Accountability of Social Assistance in Crises: Emerging Evidence and Promising Practices	Accountability, genuine participation and trust need to be built through presence and face-to-face communication: Digital channels for communication such as hotlines must be complemented by a focus on in-person discussions with people, communities and local authorities.	Inclusion
13	BASIC Research Working Paper 39. Reframing the Accountability of Social Assistance in Crises: Emerging Evidence and Promising Practices	Involve affected people in decision-making: Clarify participation processes, and ensure transparency in decisions regarding social assistance delivery.	Inclusion
14	BASIC Research Working Paper 39. Reframing the Accountability of Social Assistance in Crises: Emerging Evidence and Promising Practices	Focus on front-line decision-making: To better support and devolve decision-making to front-line workers and organisations with a presence in conflict-affected areas where assistance is most needed	Inclusion
15	BASIC Research Working Paper 39. Reframing the Accountability of Social Assistance in Crises: Emerging Evidence and Promising Practices	Invest in better locally led, contextual political analysis to design accountable social assistance programmes, especially at scale: Comprehensive political economy and context analysis will enable donors and aid agencies to engage more effectively with crisis-affected governments and broader civil society.	Inclusion
16	BASIC Research Working Paper 39. Reframing the Accountability of Social Assistance in Crises: Emerging Evidence and Promising Practices	Focus on the roles that wider civil society, media and the private sector – not just NGOs – play in accountability: Stronger and more direct support to local implementing organisations is part of the agenda, but this support must be rooted in broader accountability initiatives. Other civil society actors such as women-led organisations, disability and minority rights groups, media, the private sector and community organisations all have vital roles to play in establishing greater accountability for assistance and could be more engaged with and better supported in providing the necessary countervailing power for social assistance in crises.	Inclusion
17	BASIC Research Working Paper 40. Supporting Mutual Aid in Sudan: Conflict-Sensitive Approaches to Risk and Accountability	Strengthening protection for community responders on the front line, through advocacy with parties to the conflict to recognise the humanitarian activities of mutual aid groups, support to human rights documenters, and practical support on protection and security for local groups. (This operational recommendation is relevant for GESI as women responders face specific risks such as sexual and gender-based violence).	Systems
18	BASIC Research Working Paper 40. Supporting Mutual Aid in Sudan: Conflict-Sensitive Approaches to Risk and Accountability	Continuing to adapt funding modalities and modes of engagement to support the priorities and leadership of community initiatives, through empowering approaches. (This is relevant for GESI because it entails responding to the needs of women initiatives and engaging them in humanitarian forums).	Systems
19	BASIC Research Working Paper 40. Supporting Mutual Aid in Sudan: Conflict-Sensitive Approaches to Risk and Accountability	Working closely with diaspora supporters and organisations, as well as new philanthropic initiatives, on support to local initiatives, given their long-standing relationships with community groups and critical support to them during the conflict.(Many of these diaspora and philanthropic initiatives have a GESI focus)	Systems
20	BASIC Research Working Paper 42. The Political Economy of Lebanon’s Financial Crisis	FCDO should continue to encourage reforms that build life-cycle social insurance systems, with poverty targeted approaches being only a safety net of last resort.	Systems
21	BASIC Research Working Paper 38. Fragmented Power, Access and Legitimacy: The Politics of Social Assistance in Yemen’s Conflict (2014-2024)	Redefine and rescope social assistance interventions given expanding multi-dimensional poverty	Politics
22	BASIC Research Working Paper 37. Can Social Protection Programmes Promote Livelihoods and Climate Resilience in Conflict‑Affected Settings? Evidence from Ethiopia’s Productive Safety Net Programme	Strengthen the integration of the PSNP with complementary sectors particularly health, business planning and skills development. There is a need to further define the complementarity of CBHI and the PSNP, identifying linkages that would improve the effectiveness of both.	Climate and Livelihoods
23	BASIC Research Working Paper 37. Can Social Protection Programmes Promote Livelihoods and Climate Resilience in Conflict‑Affected Settings? Evidence from Ethiopia’s Productive Safety Net Programme	Trends associated with rural transformation and associated dynamics are also strongly gendered and defined by age-related differences. Whereas landlessness for young people and women is an urgent problem in many areas, the focus on gender and age of many rural development and extension efforts is generic (ibid.), with inadequate attention given to intersectionality (by wealth, marital status, access to land and so forth	Climate and Livelihoods

Annex 4 – Output 1.5 Increased capacity of southern researchers/research organisations working in crisis contexts to conduct, direct, interpret and use BASIC Research (e.g. use research/research processes to position themselves and to advocate/influence others).

	Examples	Type	Country

1	Louis Hodey presented the Targeting project findings to a CALP Network regional webinar focussed on feedback mechanism and accountability in Nigeria	Presentation	Ghana
2	Yihunbelay Teshome presented at the African Studies Association UK (ASAUK) annual conference on the Ethiopia research under the Livelihood and Climate Resilience project	Presentation	Ethiopia
3	Ibrahim Jalal was an expert speaker at a NatCen International and Shabaka hosted roundtable: ‘Sudan Crisis Series Session Two - Humanitarian Diplomacy in the Sudan Crisis: Insights from Outside the Formal Humanitarian Architecture’.	Presentation	Yemen
4	Abeer Al Absi presented the BASIC Yemen research as part of the socialprotection.org webinar ‘The role of localisation in delivering more effective social protection in crises’ 27/2/25	Presentation	Yemen
5	Hassan-Alattar Satti took part in the BASIC R panel at HNPW ‘Localising social protection in crisis response: the case for empowering local actors’ 25/3/25	Presentation	Sudan
6	Muhammad Ayub Jan (Pakistan), Nadine Khayat (Lebanon), Rouba Mhaissen (Lebanon), Shahida Aman (Pakistan) all presented as part of the BASIC panel at the IASFM conference in Indonesia in January	Presentation	Pakistan and Lebanon
7	Hassan-Alattar Satti took part in the FCDO Sudan meeting in Nairobi, Kenya, on 21-22 May, sharing BASIC-R research findings and helping facilitate a session on conflict sensitive and politically informed social protection.	Presentation	Sudan
8	Hassan-Alattar Satti presented research findings from the BASIC-R study on Supporting Mutual Aid in Sudan at the Humanitarian Xchange Kampala: Advancing Locally Led Response in East Africa event in Kampala, Uganda on 26-27 May.	Presentation	Sudan
9	Abeer Alabsi was a discussant in a DSA Conference roundtable Investing in frontline capacities for social protection in deepening crises on 25 June.	Presentation	Yemen
10	Judith-Ann Walker was part of a BASIC/DEEP panel presenting research from the Nigeria Lived Experience project at the Nigeria Economic Society Scientific Conference, Sep 8-11, 2025, Abuja	Presentation	Nigeria

	Four BASIC researchers presented papers based on their respective research projects at the BASIC conference in September:
11	Hassan-Alattar Satti Sudan project	Presentation	Sudan
12	Adedeji Adeniran Nigeria Lived Experience project	Presentation	Nigeria
13	Victor Ogharanduku Nigeria Targeting project	Presentation	Nigeria
14	Nadine Khayat Geography of Social Assistance in Lebanon project	Presentation	Lebanon

	CO-AUTHORS
1	Harem Karem was a co-author of BASIC Research Working Paper 34 ‘A Bridge to Those in Need’ Frontline Provider Perspectives on the Accountability of Social Assistance in the Kurdistan Region of Iraq	Co-author	Iraq
2	‘Gbenga Sesan was a co-author of BASIC Research Working Paper 25 ‘Those with Big Phones have the Upper Hand’: Political, Gender and Digital Exclusions in Cash and Voucher Assistance in North East Nigeria	Co-author	Nigeria
3	Multiple members of the Nigerian team (Adedeji, A.; Nwosu, E.; Obaniyi, F. and Udora, C.) co-authored BASIC Research Working Paper 31 Social Assistance and Coping with Crises in Borno, Nigeria	Co-author	Nigeria
4	Sami Zoughaib co-authored BASIC Research Working Paper 32: The Politics of Social Assistance in Lebanon: Social Protection, Sectarianism, and Lebanon’s Fragmented Social Contract	Co-author	Lebanon
5	Judith-Ann Walker and Adeniran Adedeji co-authored BASIC Research Working Paper 35: Poverty Dynamics and Social Assistance Amidst Intersecting Crises in Nigeria	Co-author	Nigeria
6	Ben Boham Okiror co-authored BASIC Research Working Paper 36: Towards Inclusive Social Assistance for Marginalised People in East and Northeast Uganda	Co-author	Uganda
7	Yihunbelay Teshome was a co-author of BASIC Research Working Paper 37. Can Social Protection Programmes Promote Livelihoods and Climate Resilience in Conflict‑Affected Settings? Evidence from Ethiopia’s Productive Safety Net Programme	Co-author	Ethiopia
8	Ibrahim Jalal Fakirah authored BASIC Research Working Paper 38. Fragmented Power, Access and Legitimacy: The Politics of Social Assistance in Yemen’s Conflict (2014-2024)	Co-author	Yemen
9	Hassan-Alattar Satti was a co-author of BASIC Research Working Paper 40. Supporting Mutual Aid in Sudan: Conflict-Sensitive Approaches to Risk and Accountability	Co-author	Sudan
10	Hassan-Alattar Satti was a co-author of BASIC Research Policy Briefing 7: Supporting Mutual Aid in Sudan	Co-author	Sudan
11	Judith-Ann Walker, Kareem Abdulrasaq and Michael Turnwait were co-authors of BASIC Research Policy Briefing 9: Social Assistance and Poverty Reduction Amidst Multiple Crises	Co-author	Nigeria
12	Judith-Ann Walker, Kareem Abdulrasaq and Michael Turnwait were also co-authors of BASIC Research Research Briefing 5: Climate Change, Conflict, Food Security and Social Protection in Niger	Co-author	Nigeria
13	Bozari Mamane and H.A-A Taffa co-authored BASIC Research Working Paper 46. Local social solidarity and mutual assistance mechanisms in Niger: a rich and varied repertoire for resilience and crisis response.	Co-author	Niger
14	Bozari Mamane and H.A-A Taffa co-authored BASIC Research Policy Briefing 10. Local Solidarity Mechanisms for Resilience and Crisis Response in Niger.	Co-author	Niger

Annex 5 – Output 3.1 Knowledge and learning events organised or presented at by BASIC Research
Output 3.1a Number of events targeting external audiences organised by supplier (cumulative)

	Event	Date

1	Webinar: Reflections from the Forum on Social Protection in Fragility and Conflict	Nov-24
2	Webinar: Using social assistance to promote climate resilience [in fragile and conflict contexts] What do we know and what needs to change?	Oct-24
3	BASIC Research were heavily involved in the Global Forum on building and protecting social protection systems in fragile and conflict settings through the Humanitarian-Development-Peace nexus, 15-17 October.	Oct-24
4	Conference side event: Supporting and Sustaining Social Protection during Conflicts: Insights from Current 'Better Assistance in Crises' (BASIC) Research	Nov-24
5	Meeting: Dissemination exercise of the research titled "Poverty Dynamics and Social Protection Amidst Complex Crises in Nigeria	Nov-24
6	Meeting: Presenting Ethiopia work to range of donors and stakeholders (PSNP Donor Working Group) in Addis Ababa	Nov-24
7	Webinar: Social protection in a post-USAID world: an open discussion on key implications	Feb-25
8	Webinar: Maintaining and sustaining social protection in conflict and fragile settings	Feb-25
9	Webinar: The role of localisation in delivering more effective social protection in crises	Feb-25
10	BASIC Panel: Why should humanitarians care about social protection? Session at the Humanitarian Networks and Partnerships Week 2025, 17-28 March	Mar-25
11	BASIC Panel: Localising social protection in crisis response: the case for empowering local actors. Session at Humanitarian Networks and Partnerships Week 2025, 17-28 March	Mar-25
12	Webinar: Gender-responsive social protection in crises: reaching and supporting marginalised groups	Apr-25
13	Webinar: Financing Social Protection in Protracted Crises	Jun-25
14	Workshop: Saving Lives and Building Livelihoods Through Crisis: Evidence from Ethiopia	May-25
15	World Bank - Nigeria Bureau of Statistics Roundtable held at dRPC office on 12th December 2024	Dec-24
16	BASIC Conference ‘Social and Humanitarian Assistance in Crises: agendas, ambitions and aspirations for more effective intervention’ 16-18 September	Sep-25
17	Webinar: Investing in local social protection workers in protracted crises	Jul-25
18	Webinar: Reframing the accountability of social assistance in crises. BASIC Global Review roundtable	Sep-25
19	Webinar: Social protection and climate change in protracted crisis contexts. BASIC Global Review roundtable	Sep-25

Annex 6 - Output 3.1c Number of events presented at by BASIC Research (cumulative)

	Event	Date

1	Meghan Bailey; Vidya Diwakar and Jeremy Lind provided written contributions to a UN Special Rapporteur on extreme poverty and human rights online Roundtable	Oct-Dec 24
2	Rachel Sabates-Wheeler presented and participated in an ARI/ DRC conference on the 6th November - ‘Supporting SP during conflicts in the MENA region’. She was invited to so due to her work on BASIC. She was also invited to become part of the advisory committee for the Arab Region SP hub of ARI. An advisory meeting was held on the 8th November	Nov-24
3	Philip Proudfoot presented at the Share End-of-Project Conference: Strengthening Social Protection, Security And Welfare In The Middle East And North Africa Region - Key Findings And Recommendations For Research And Practice	Nov-24
4	Dolf te Lintelo and Nadine el Khayat presented at the Policy Dialogue 1 - National Policy Dialogue Series on “Promoting Universal Social Protection in Lebanon”, the Arab Reform Initiative (ARI) and the International Labor Organization (ILO), with the support of the United Kingdom and the European Union, Lebanon, Wednesday, March 12th, 2025	Mar-25
5	Paul Harvey, Louisa Seferis, Carolina Holland-Szyp, Becky Carter, Rachel Slater, Sarah Blin, Abeer Al-Absi, Jackie Shaw presented at the DSA Conference 2025	Jun-25
6	Vidya Diwakar presented at the DEEP International Conference on Poverty Evidence	Jun-25
7	Becky Carter, Hassan Alattar-Satti and Paul Harvey presented at the STAAR, DAI and Rift Valley Institute, Nairobi workshop on 'Charting a Course for Social Protection in Sudan: Bridging research and policy'	May-25
8	Michael Collyer presented at the FCDO Migration Roundtable	Apr-25
9	Alexandrine Dupras and Rachel Slater presented as part of the Social Assistance Schemes in Syria, 2011-2024, Institut Francais du Proche-Orient (IFPO) webinar	May-25
10	Dolf te Lintelo and Nadine el Khayat presented at the event: Sustainability of the Social Assistance System and Linkages with the Humanitarian Assistance System, hosted by the Arab Reform Initiative (ARI) and the International Labor Organization (ILO), with the support of the United Kingdom and the European Union	Apr-25
11	Tahir Zaman gave an online presentation to Pakistan FPDS & Trade Desk, Global Affairs Canada, Government of Canada, presenting an overview of displacement and development context in Khyber Paktunkhwa.	Jun-25

Annex 7 – Output 3.2 Delivery of BASIC knowledge management and learning strategy

Output 3.2a Delivery of jointly organised learning events, including those between suppliers (KELU quarterly meetings and follow-up discussions on opportunities for information sharing/strengthened collaborative approaches) those targeting external stakeholders (non-cumulative)

	Event	Date

1	A workshop was convened by Integrity in November 2024 involving BASIC R, STAAR and FCDO to discuss and agree in principle on where and how to a) build on existing results and b) prioritise/adapt planned activities to increase the likelihood of achieving change at the outcome level.	Nov-24
2	KELU meeting 10th December – Nick Moore presented on next steps following on from the November workshop; discussion of plans for additional stakeholder mapping; discussion of next steps following on from Global Forum. Also plenary discussion of relevant policy processes and upcoming events to feed BASIC-R and STAAR research into; collaboration opportunities on specific research or research uptake activities and assignments; Identifying key areas of shared interest in terms of policy influencing; opportunities for reaching BASIC-R and STAAR target audiences across regions we agreed to focus on at Integrity Workshop: MENA, the Sahel, and Ethiopia	Dec-24
3	Ethiopia engagement planning workshop (16th Jan 2025). This was an online workshop attended by STAAR and BASIC people. Harri Lee joined and Tom Russell joined for a while. In total there will about 10 of us. We spent time sharing findings and brainstorming ideas for engagement, and face to face workshops. A substantial amount of time was spent populating a mural board to help crystallise ideas for policy messages and who to target with these messages.	Jan-25
4	BASIC R staff joined STAAR’s engagement workshop on 22nd and 23rd January where STAAR mapped its policy engagement activities against themes.	Jan-25
5	KELU Meeting 17th June. Main areas of discussion were a deep dive on the Politics of Social Protection work and a discussion of country and thematic engagement plans and opportunities for intersections.	Jun-25
6	1st May – bilateral meeting with BASIC and STAAR to discuss changing engagement priorities and possible areas for joint uptake activities including the High-Level Panel.	May-25
7	Planning meeting for FCDO Social Protection Team workshop on 5th August to agree key messages around 3 central themes and mapping engagement targets and opportunities	Aug-25

Output 3.2b Qualitative examples of where coordination between STAAR and BASIC Research on specific assignments, research/non-academic outputs, influencing activities or monitoring/evaluation efforts has strengthened quality (non-cumulative)

	Example	Date

1	Rachel and Jeremy Lind met Lili Mohidin and Chachi Bezuneh in Addis (STAAR consultants preparing the conflict sensitivity study)	Oct-Dec 2024
2	Jeremy Lind joined two calls with STAAR to plan the sp.org hosted joint STAAR/BASIC webinar on climate	Oct-Dec 2024
3	Becky Carter had meetings with STAAR to coordinate the studies on Sudan and to begin thinking about a Sudan engagement event proposed be Ed Barney	Oct-Dec 2024
4	Paul Harvey had discussions with STAAR to coordinate roles in planning and contributing BASIC-R and STAAR insights to the proposed high-level panel	Oct-Dec 2024
5	There have been calls between BASIC R and STAAR(Sophie and Gabrielle) to get their insights into the World Bank approach paper country studies	Oct-Dec 2024
6	Paul had further discussions with STAAR on his work on the World Bank approach paper to support their work on Ukraine. (January)	Jan-Mar 2025
7	The BASIC R Climate Global Review paper has been reviewed by Anna McCord of STAAR. Anna also joined an internal BASIC webinar to explore key findings from the Global Review. This session highlighted emerging messages and insights on how international actors’ mainstream climate challenges in their social protection work.	Jan-Mar 2025
8	Alan Stanley met with Charlotte and other STAAR colleagues to share information and coordinate planning around engagement and uptake plans and activities. In this quarter these meetings focused on planning and coordination around the sp.org webinar series and podcast and the two HNPW sessions. BASIC R also shared information on country engagement plans and updates stakeholder mappings along with a draft communications workplan, which documents planned BASIC R engagement activities and outputs with expected dates.	Jan-Mar 2025
9	Jeremy Lind reviewed the STAAR Ethiopia shock responsive paper by Daniel Hailu.	Jan-Mar 2025
10	Calum McClean has fed BASIC-R findings on interoperability into his STAAR role on donor coordination in Yemen.	Jan-Mar 2025
11	There was a joint STAAR/BASIC R meeting with FCDO Yemen on 11th February following on from which a joint summary of key messages was produced for FCDO highlighting Yemen research across both parts of the programme.	Jan-Mar 2025
12	BASIC R and STAAR liaised to submit joint proposals for panels at HNPW – two panels were accepted.	Jan-Mar 2025
13	Rebecca Holmes (STAAR) reviewed the BASIC-R Targeting synthesis paper.	Apr-Jun 2025
14	Jackie Shaw (BASIC-R) liased with STAAR about joining with them on engagement and uptake plans with government officials in Uganda.	Apr-Jun 2025
15	BASIC R and STAAR have collaborated around global review webinars (accountability, politics, climate)	Jul-Sep 2025
16	BASIC R and STAAR collaborated on planning joint presentations for FCDO cadres	Jul-Sep 2025
17	Paul Harvey has been coordinating with STAAR on an a possible approach to engaging with Gulf States on our research findings. STAAR have now approved the work on Gulf State donors. Paul will be contributing to a piece of work with STAAR focussed on better understanding the role that Gulf State donors are playing in supporting social protection in crises and using that to discuss with Gulf State donors in a workshop looking at how BASIC research and STAAR findings can inform their approaches.	Jul-Sep 2025
18	Anna McCord at STAAR has reviewed the Climate, Social Protection and Conflict: From past trends and crises to future storylines Working paper written by RCCC.	Jul-Sep 2025
19	Valentina Barca of STAAR reviewed the Targeting Global Review working paper.	Jul-Sep 2025

Annex 9 - Output 3.2c Terms of Reference and plans shared as relevant between BASIC Research and STAAR (non-cumulative)

	Example	Date

1	BASIC-R emailed STAAR with the quarterly project update detailing all project plans and methodology and update on current project activities for Q2 2024/25.	Oct-Dec 2024
2	Sophia Swithern and Paul Harvey have had multiple calls and emails with STAAR colleagues to discuss the financing work – to share a draft concept note and coordinate plans for a possible phase 2 of the research	Oct-Dec 2024
3	January 2025 BASIC-R emailed STAAR with the quarterly project update detailing all project plans and methodology and update on current project activities for Q3 2024/25.	Jan-Mar 2025
4	BASIC-R shared its stakeholder mapping on Lebanon and Yemen in February	Jan-Mar 2025
5	STAAR shared details of thematic working groups following the engagement workshop in January.	Jan-Mar 2025
6	Shared the BASIC-R final year uptake and engagement strategy with STAAR in May. This was then used for the background of discussions at the June KELU meeting.	Apr-Jun 2025
7	Emails between Megan Smith and Ollie Burch clarifying planned country engagement activities and opportunities for including STAAR identified stakeholders.	Apr-Jun 2025
8	April 2025 BASIC-R emailed STAAR with the quarterly project update detailing all project plans and methodology and update on current project activities for Q4 2024/25.	Apr-Jun 2025
9	July 2025 BASIC-R emailed STAAR with the quarterly project update detailing all project plans and methodology and update on current project activities for Q1 2025/26.	Jul-Sep 2025
10	In advance of the meeting with FCDO in early August STAAR and BASIC shared key messages and current engagement plans	Jul-Sep 2025