Annual Review BEPAC 2026 (reporting year 2025)

Programme Title: Building an Evidence Base on Humanitarian Protection of People Affected by Conflict (BEPAC)
Programme Value (£): £18.1m
Programme ID: 300484
Review Date: 29 April 2026
AMP Start Date: 02 February 2019
AMP End Date: 31 March 2027

Programme Performance

Year	2019	2020	2021	2022	2023	2024	2025	2026
Overall Score	A	A	A	A	A	A	A	A
Risk Rating	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

Devtracker links to other key Programme files

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/programme/GB-GOV-1-300484/documents
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/programme/GB-GOV-1-300484/documents

Section A. Overview and link to wider Portfolio

Description of programme

The ‘Building an Evidence Base on Humanitarian Protection of People Affected by Conflict’ (BEPAC) programme is designed to improve understanding of protection risks faced by conflict-affected people, particularly in regard to increasing challenges to international humanitarian norms, and to identify what can be done to reduce and mitigate these risks. Overall, the evidence base for humanitarian protection is still considerably weaker than other areas of humanitarian action. All BEPAC research projects are focussed around six aspects of improving humanitarian protection: International Humanitarian Law (IHL) violations; protection programming; restraint; local protection mechanisms; recognition; and targeting.
[note] Physical and mental health risks and risks to legal rights.
[note] The six themes were arrived at after consultation during the design of the Business Case.

BEPAC has three active component projects and a fourth previously completed.

1: Researching the Impacts of Attacks on Healthcare (RIAH) began in 2019. RIAH is an interdisciplinary research programme investigating the nature, frequency, and scale of attacks on healthcare in armed conflict and aims to improve the methodologies employed to measure their impacts. Direct and indirect impacts include harm to civilians and health workers, undermining health systems, and worsening overall broader public health and human development outcomes. RIAH has conducted research in Colombia, Afghanistan, Central African Republic (CAR), Democratic Republic of Congo, Myanmar and Nepal, as well as historical research, and supports data collection on attacks on heath care by Insecurity Insight. It is delivered by a multi-institution consortium led by the University of Manchester (UoM).
[note] In February 2024 RIAH was extended to 31 March 2026, with an additional £0.5m to enable more dissemination and uptake of research, and an additional £0.25m agreed with FCDO in late 2024. Currently budgeted at £3.99m.
[note] Manchester’s Humanitarian and Conflict Response Institute (HCRI) leads the consortium, which includes Johns Hopkins University, Geneva Centre of Humanitarian Studies (formerly CERAH), and Insecurity Insight; with support from the University of California-Berkeley, and Chatham House (the Royal Institute for International Affairs).

2: The Humanitarian Protection Initiative (HPI) began at the end of 2023, with the Abdul Latif Jameel Poverty Action Lab (J-PAL). Implemented by J-PAL and Innovations for Poverty Action (IPA), the programme conducts Randomised Controlled Trials (RCTs) on humanitarian protection themes. The aim is to equip humanitarian actors with a deeper understanding of cost-effective, scalable, and context-sensitive solutions for preventing and mitigating physical, psychological, social, and legal harm against conflict-affected populations.
[note] £3.3m over 4 years.

3: The Beyond Compliance Consortium (BCC) began in March 2024 following a competitive grant process. The programme aims to identify legal and extra-legal strategies, including armed actors’ compliance with international humanitarian law (IHL) and international human rights law (IHRL), to prevent, reduce, and respond to harm and need in war. BCC co-produces work with local partners and researchers in nine countries: Afghanistan, Colombia, the Democratic Republic of Congo, Myanmar, Somalia, South Sudan, Syria, Ukraine, and Yemen. It is delivered by a multi-institution consortium (including leading humanitarian and human rights organisations) led by the University of York (UoY).
[note] £5m over 3-4 years.
[note] As well as the University of York the consortium includes the University of Glasgow and Utrecht University, and six humanitarian and human rights organisations: Watchlist on Children and Armed Conflict, War Child Alliance, the International Humanitarian Law Centre, Center for Civilians in Conflict, Centre on Armed Groups, and Fight for Humanity.

4: The Collaborative humanitarian protection research programme ended in March 2024. It was run with the UK Arts and Humanities Research Council (AHRC) and consisted of 12 protection research grants awarded to academic partners through a competitive open call for proposals.
[note] Approximately £2.9m.

Supporting narrative for the overall score in this review

Overall programme performance is strong and scores A. In this reporting period, all three component projects have delivered well against their respective outputs and outcomes and, in several areas, exceeded expectations – combining high-quality evidence generation with active, credible engagement to drive uptake.

During the last year, RIAH completed its planned publications and shifted effectively to dissemination and influence, substantially exceeding public engagement targets and strengthening global understanding of the impact of attacks on healthcare as part of respect for humanitarian norms. Its data methodologies are increasing the visibility and verifiability of violations and are being used in UN and leading INGO products, supported by sustained engagement with influential actors (including participation in senior IHL expert fora). Emerging capacity-building partnerships with major medical INGOs should leave a lasting legacy for data quality and use.

HPI is on track across outputs, consolidating momentum through a final funding round that produced a robust pipeline of policy-relevant research aligned to BEPAC learning priorities and practitioner demand. Improvements to proactive project development, capacity-building and delivery systems have increased efficiency and ensured funds were allocated and disbursed to timeline. Signs of emerging progress towards outcomes are visible and partnerships with ICRC, UNHCR, IRC and others have matured into structured collaboration on evaluation design, learning and dissemination. This strengthens the likelihood of sustained evidence use beyond programme end and thus increasing the odds of outcome to impact level progress.

BCC has met and exceeded annual output targets within its empirically grounded approach to IHL violations and wider civilian harms. Data collection has covered over 600 participants across nine case study countries, while quantitative data was coded into an innovative database linking IHL compliance and civilian harm. This was complemented by an active dissemination strategy (academic and policy outputs, multimedia products, a blog symposium and the co-produced BEYOND Serious online game). Outcomes are beginning to be seen within the consortium and there is a plausible path to achievement of outcomes outside the consortium in future. A key achievement this year was providing written evidence in response to the House of Commons International Development Committee’s inquiry on humanitarian access and adherence to international humanitarian law and being widely cited in the report.
[note] Protection not permission: The UK’s role in upholding international humanitarian law and supporting the safe delivery of humanitarian aid. The report also mentions RIAH’s evidence submitted to the enquiry.

Taken together, the components demonstrate clear delivery, effective management and credible pathways to influence, with outcomes providing confidence in the likelihood of continued progress through closure and into post-programme uptake.

Fitness for Purpose in the wider Portfolio

Fit with FCDO priorities: The global international development environment has changed substantially and rapidly. UK commitment to international development is demonstrated through a modernised approach and four key shifts that incorporate a refreshed focus on partnerships and greater activism as a key shareholder in the multilateral system. The Foreign Secretary made it clear in March 2026 that humanitarian response remains a top FCDO priority and UK development support will prioritise supporting fragile and conflict affected areas and those with greatest humanitarian need, including a focus on prevention of conflict and atrocities. Humanitarian protection is a policy priority for FCDO, and promoting humanitarian protection has been an under-researched topic within humanitarian policy. BEPAC contributes to evidence to support people in contexts of great humanitarian need, facing significant risks. Component projects work with local partners to help build local capacity and knowledge, supporting the shift from international interventions to local expertise and solutions where possible. Seven years on from its inception, BEPAC remains strategically and policy relevant.
[note] Thinking as an investor rather than a donor; supporting systems rather than delivering services; providing expertise rather than grants; and championing local solutions where appropriate over international interventions.
[note] The Rt Hon Baroness Chapman of Darlington, ‘Four Shifts’, in Wood, I and Coolin, G (2025) Promising Development: The future of aid in an uncertain world. Fabian Ideas No. 670, pp. 6-7.
[note] Written Statement made by: Secretary of State for Foreign, Commonwealth and Development Affairs (Yvette Cooper) on 19 Mar 2026, House of Commons: Written Statement (HCWS1425); Foreign, Commonwealth and Development Office, The Rt Hon Yvette Cooper MP, and The Rt Hon Baroness Chapman of Darlington, ‘Foreign Secretary sets out new innovative development reforms’, Press release 19 March 2026.
[note] See for example the UK Humanitarian Framework (publishing.service.gov.uk)

Fit with Research portfolio: The programme supports the FCDO’s Global Research and Technology Development portfolio, which will invest in high potential R&D to tackle shared global challenges. Emerging research priorities are likely to include investing in research on forecasting and anticipatory action, new tech and innovation for humanitarian response, inclusive AI innovation, and what works in health, education, livelihoods, food security and economic systems. This prioritises ODA-funded research and development where high-quality evidence, science and innovation can deliver the greatest impact for people most in need, and where the UK has a clear strategic role to play. Learning from BEPAC will help drive new, problem-focused humanitarian research within a ‘whole of UK’ approach, where quality FCDO-funded research is used to inform UK policy and influence international policy.
[note] Written Statement made by: Secretary of State for Foreign, Commonwealth and Development Affairs (Yvette Cooper) on 19 Mar 2026, House of Commons: Written Statement (HCWS1425).

Fit with policy and geographic priorities and humanitarian needs: BEPAC’s independent and rigorous research is valued by FCDO’s humanitarian protection policy team and coordinated with them and their policy priorities, and with other relevant teams across FCDO including the Humanitarian Directorate, and the UK IHL Committee. The learning from this programme on humanitarian protection will help provide an evidence base for effective delivery. Within the wider humanitarian ecosystem protection remains a challenging area for good evidence of effectiveness, and the past year has seen global withdrawal of humanitarian research funding within a context of the increasing humanitarian need discussed above. This makes maximising learning on protection from BEPAC even more vital to help support good decision-making by humanitarian actors at all levels within the humanitarian ecosystem, well beyond HMG. BEPAC partners have good links into the wider humanitarian system at many levels.

Section B. Learning and Recommendations

Learning

There are five main areas of design and delivery learning through the BEPAC programme this year, which tie to specific recommendations following.

L1. Developing a robust Theory of Change in an area as complex as reinforcing global norms, promoting respect for IHL, and the protection of civilians in armed conflict, continues to be challenging. This is magnified as respect for humanitarian norms has been declining in BEPAC’s last two to three years – an unexpected development that has further complicated the ToC. The ToC does not sufficiently capture how the programme can help the humanitarian system to have a clearer understanding of how to reduce and mitigate protection risks to civilians presented in particular by increasing challenge to or erosion of global norms and IHL. This also means the programme level logframe does not sufficiently capture measurement of outcome achievements and progress towards impact. Capturing the contribution of, for example, RIAH, in terms of reinforcing global humanitarian norms during a period when those norms are increasingly challenged is complex. More sophisticated approaches will be needed to assess and evaluate BEPAC’s contribution to its outcome and impact goals as it comes to its end. More broadly, this could assist wider organisational learning around humanitarian norms and protection of civilians. (See Recommendation 1.)

L2. Learnings from logframe reporting outlined in Section D, along with RIAH coming to an end and HPI and BCC entering their final 12-15 months, mean that the output level of component and programme logframes need revision. This will ensure realistic but stretching final milestones are set for partners and that the most appropriate output indicators from component logframes are reflected in the programme logframe. (See Recommendation 2.)

L3. The contours of a follow-on research agenda from BEPAC (which has been groundbreaking in terms of new forms of evidence on humanitarian protection) are becoming clearer, for example the need for a clearer focus on using combinations of quantitative and qualitative research to establish the most effective ways of engaging with armed actors to promote restraint and compliance with IHL. (See Recommendation 3.)

L4. Uptake in FCDO of BCC’s Research Line offer has been good in this reporting year but obtaining meaningful feedback from busy FCDO stakeholders has been challenging, presenting difficulties in assessing value of this service to the organisation (see also discussion of indicator 5.1 in Section D). (See Recommendation 4.)

L5. Delivery risks are not always well assessed and flagged to FCDO by partners as clearly or as promptly as needed. A learning this year is that partners can have a tendency towards optimism, but this hopefulness should be tempered to avoid standing in the way of preparation and communication around risk. (See Recommendation 5.)

Recommendations

R1. SRO should assess feasibility of using programme underspend towards services of a MEL consultant, contracted and administered through a BEPAC partner, or another mechanism, to deliver:
1. A revised BEPAC Theory of Change that can inform wider organisational thinking about global norms.
2. A proposal for strengthened approaches to demonstrating outcome assessment and pathways to impact from research programmes in this area.
3. By programme closure review, an assessment of BEPAC’s contribution to its outcome and impact goals.
(Action: SRO lead with support of BEPAC partners, by December 2026 (1 and 2 complete and 3 in progress).)

R2. The output levels of the remaining two component logframes and the BEPAC programme logframe should be revised. (Action: BEPAC partners for component logframes; PRO for programme logframe, agreed by July 2026.)

R3. BEPAC partners should each draft a summary for FCDO of what they see as being the most important outstanding research questions remaining as their projects near completion. (Action: BEPAC partners, by December 2026.)

R4. BCC designs a draft feedback mechanism for the Research Line offer (which provides on-demand support for FCDO) and shares this with FCDO. (Action: BCC by June 2026 for the design; implemented from July.)

R5. BEPAC partners swiftly and clearly flag risks to FCDO so that mitigations can be discussed as soon as possible. There should be no incidents of delayed or unreported risks. Partners must report all possible delivery implications with assessment of likelihood and potential impact. (Action: BEPAC partners, with immediate effect.)

Response to last year’s recommendations:

R1. The BEPAC Theory of Change should be re-assessed, with a particular focus on setting realistic impact indicators and agreeing any consequent adjustments to programme activities in particular on dissemination and uptake. The logframe should then be revised, including revision to outcome indicator 3 to ensure better assessment of the programme’s conceptual impact. (Action: FCDO/SRO and BEPAC partners, by September 2025.)
Not met. The ToC has proven challenging and is still under review, with a new provisional change idea under development (see below). As such, outcome indicator 3 has not yet been revised.

R2. BCC to conduct a series of seminars on IHL for FCDO humanitarian and conflict advisers to promote professional learning and help build the recognition and trust in FCDO for the BCC research line offer. (Action: BCC by end November 2025.)
Met. The Research Line has actioned this recommendation by completing five seminars (‘thematic briefings’), by the end of December 2025. The topics of the briefings were decided in consultation with FCDO colleagues (through the intermediary of the SRO) to ensure their response to their interests/needs. The BCC and RL team have continued to raise wider awareness within the FCDO about the existence of the BCC, the BCC RL specifically and its offerings, and to build direct relationships with desks and country teams to ensure take-up. As such, all CRU leads reached out to FCDO contacts in the nine case study countries, and a number of follow-up meetings were organised.

R3. Where relevant and useful for protection outcomes, the FCDO SRO and DPM to cultivate more linkages across BEPAC partners (throughout and by December 2025).
Met. DPM established links across partners during the reporting period and partners are in contact.

R4. FCDO to develop a VFM workplan for partners to ensure that qualitative and quantitative metrics are linked to logframe outputs and documented in greater detail. (Action: FCDO DPM by June 2025.)
Met. BCC has produced a detailed VFM framework using the FCDO template. J-PAL have not used the template itself, however, they have used the guidance to produce detailed examples of VFM metrics with the same end result as the template. RIAH have consistently provided helpful VFM examples and will continue to consider this as we approach the PCR.

Section C. Theory of Change and Outcome Review

Theory of Change Review

BEPAC’s theory of change is that high-quality research on the effectiveness of protection interventions, and the factors that either promote or reduce rights violations, will contribute to more effective programming and policies for FCDO and the wider humanitarian system. Previous FCDO-funded research on a similar topic by the International Committee of the Red Cross (ICRC) (Roots of Restraint) demonstrates this is possible.

The ToC diagram below remains in place for BEPAC at present. The assumptions driving production of outputs have been shown to hold, and high-quality programme outputs continue to be produced by implementing partners. The assumptions underpinning outputs to outcomes in the causal chain have also largely been shown to hold but achievement of the outcome goal across the programme remains uneven as of the date of this review, despite indicators being exceeded (and component projects are at very varying stages). Achievement of the impact goal remains out of reach. However, given the ambitious nature of the outcome and impact statements for this programme and the long and complex causal chains involved, this is no surprise. It was acknowledged in last years’ annual review that the impact statement is too ambitious for what a research programme can achieve and that a more realistic (yet still very challenging) impact goal might be positively influencing humanitarian norms at global and local levels.

Work to revise the programme’s ToC (along with impact statement, outcome indicators and logframe) is still ongoing but in light of progress over the year under review, the FCDO programme team believe that some of the complexity involved could be spelled out in more detail. The output to outcome and in particular, the outcome to impact steps should be theorised more explicitly, with attention paid to normative change: including the role that data, analysis, research and evidence play in normative change and how this may lead to the promotion of protection outcomes. Initial thinking is presented below.

An emerging role for BEPAC is to improve understanding of how international humanitarian norms interact with the abuse of civilians by armed actors – so the humanitarian system has a clearer understanding of how to reduce and mitigate protection risks to civilians presented in not insignificant part by increasing challenge to or erosion of these norms. The FCDO team has developed the below statement as a starting point for a revised ToC discussion.

If international humanitarian norms are made salient, embedded in institutions, and backed by credible incentives, monitoring, and social pressure, then armed actors will increasingly see restraint as both expected and advantageous – leading, over time, to fewer abuses of civilians.

In other words, as violations are made more visible and verifiable, combined with continued international advocacy and pressure, this may help to raise the cost of such attacks at least for armed actors seeking international legitimacy: even actors who don’t ‘believe’ in the norms may comply when costs of violation rise and benefits of restraint become clearer. Thus, we could theorise a feedback loop between norm entrepreneurship, norm diffusion, monitoring, and documentation (in all of which there is a role for R&D as BEPAC is demonstrating) and increasing the incentives for compliance and restraint and the costs for violation – potentially shifting both interests and self-understandings of armed actors. There are, of course, counter-arguments to this which could be presented, which will need to be explored and included into a revised ToC.

Over the next few months of the programme the FCDO team will work with partners and, if possible, an external MEL consultant to explore the above idea, what the steps and feedback loops involved might be and how the programme could contribute to this (see Recommendation 1).

Impact statement
Humanitarian protection outcomes are improved

Assumptions
- Practitioners and policy makers have appetite and resources to use evidence in policy making and programme design.
- Better evidence is vital for designing and implementing effective programming.

Outcome Statement
Humanitarian protection policy and operations are improved through better evidence of protection risks/mitigations and evidence of what works.

Assumptions
The programme strengthens capacity of partners to measure their impact.
- The programme produces high quality evidence that improves understanding of protection risk and outcomes.
- Channels exist to communicate research results and findings to the right audience.

OUTPUT 1
Improved understanding of the type, scale and impacts of attacks on healthcare
OUTPUT 2
Improved evidence of the impact of protection interventions

OUTPUT 4
Improved evidence on the drivers for restraint and compliance with IHL by armed actors
OUTPUT 3
Improved understanding of the drivers of protection risks

Assumptions
- It is logistically possible to access the necessary research in contexts affected by conflict related humanitarian emergencies.
- It is possible to apply rigorous research methodology in contexts affected by conflict related humanitarian emergencies.
- Research capacity exists to implement research in conflict and fragile affected states and humanitarian emergencies.

Impact Review

Note that the BEPAC logframe is composed of indicators from each component project’s logframes. These component indicators are referenced in the Impact and Outcome Indicator Review tables below and the Output Indicator Tables in Section D.

Impact Statement

Humanitarian protection outcomes are improved.

Impact Indicator Review

Impact indicator	Milestone (Partner)	Progress towards indicator achievement in the last year
1: Number of IHL duty-bearer and non-state actor commitments to protect healthcare / (RIAH Impact Indicator 2)	Increase in frequency and strength of statements indicating commitment to IHL on protecting healthcare (RIAH)	Substantially Exceeded / 2025 calendar year: / 1,489 IHL duty-bearer commitments / 0 non-state actor commitments
2: Number of times evidence or case studies used demonstrating uptake by policy makers or practitioners / (RIAH Outcome Indicators 1, 2, 3; BCC Impact Indicator 2; AHRC Impact Indicator 1.1)	170 (+50) (RIAH) / 4 (BCC) / 0 (AHRC)	Moderately Exceeded / RIAH / Substantially exceeded: 348 (+133) / BCC / Not met: 3 / The BCC conceptual framework directly influenced the framing of the IHL Centre’s preliminary assessments around IHL (reported in IHL Centre Quarterly Report). / Influence on design of the IHL Centre’s Stockholm Manual. / Influence on ToC and wider design of proposed FCDO humanitarian programming in one of the BCC case study countries. / AHRC / 1 / (See Collaborative Humanitarian Protection Research Programme impact story below)

BEPAC Impact Indicator 1 (number of IHL duty-bearer and non-state actor commitments to protect healthcare – see Annex 14):

A key impact milestone for this year is an increase in frequency and strength of statements indicating commitment to IHL on protecting healthcare. For IHL duty-bearers the 1,489 new commitments in 2025 represent a significant increase on the 840 seen in 2024 and 381 seen in 2023, but no new commitments from non-state armed groups related to healthcare were made in 2025 compared to one in 2024 and one in 2023.

Additionally, 16 United Nations resolutions addressed directly the necessity to respect and protect healthcare in armed conflict, which is an increase from 13 in 2024. These included:
- Seven United Nations Security Council Resolutions
- Nine United Nations General Assembly resolutions

Whether BEPAC Impact Indicator 1 is a helpful indicator against the current impact statement (‘humanitarian protection outcomes are improved’) will be looked at as part of the ToC and outcome/impact assessment review discussed earlier in this section and at Learning 1 and Recommendation 1.

BEPAC Impact Indicator 2 (number of times evidence or case studies used demonstrating uptake by policy makers or practitioners):

RIAH’s contribution to Impact Indicator 2 is a composite of Outcome Indicators 1, 2 and 3 – see Outcome Review section for detailed reporting.

Beyond the impact targets for the reporting year, the now closed Collaborative Humanitarian Protection Research Programme (run through the AHRC) illustrates how impact from research programmes emerges after the end of programme funding (although not captured by Impact Indicator 2 milestones).

The Data and Displacement project examined the practical and ethical implications of targeting humanitarian protection through data, surfacing key operational and ethical challenges in data-driven humanitarianism. Findings have been used in some training by humanitarian organisations (e.g., ICRC and IRC) and cited in sector publications. Since project end, follow-on impact funding supported development of a practitioner training tool to strengthen data literacies through shared learning with affected communities, and further funding for validation and trial in 2026-27 (DLiD+ project). The current global funding reduction has compromised some of this trialling but there remains a potential pathway to incorporation into International Organization for Migration’s standard training, which would be high impact if agreed. This example illustrates the benefit obtained through additional impact funding and how the greatest impact emerges after programme closure but also shows how unpredictable global events can slow uptake. We remain engaged with the research team and continue to follow progress with interest to assess whether this project contributes to Impact Indicator 2 in future.
[note] The New Humanitarian ‘On our radar’ for 2023 report; K4D Knowledge, Evidence and Learning for Development September 2022 issue on ‘Monitoring Inclusion in Crises’ and K4D Humanitarian Evidence and Discourse Summary of May 2025; the CSRF Conflict Sensitivity Resource Facility South Sudan update 05.25.
[note] See project webpage for publications arising. There has also been an additional peer-reviewed research piece from the project, published during this reporting year: V Squire and B Jones (2025), ‘You Already Know Enough: Certainty and Ignorance in Data-Driven Humanitarianism’, Geopolitics, Vol. 30, No. 3, pp. 1101–1124: https://doi.org/10.1080/14650045.2025.2463005.

The example detailed in the story box below (included in the Impact Indicator 2 count above) shows a BEPAC key research output informing practitioner guidance and policy work.

Collaborative Humanitarian Protection Research Programme (AHRC) Impact Story:
Project: From Words to Deeds

Problem
Armed non-State actors (ANSAs) shape the conduct of contemporary armed conflicts and have significant impacts on civilians. International humanitarian law (IHL) binds all parties to armed conflict but ANSAs’ own perspectives on humanitarian rules – how they understand and translate them into internal policies and behaviour – have been insufficiently explored. The project addressed this evidence gap to better explain when and why humanitarian commitments lead (or do not lead) to restraint in practice, aiming to provide tools and evidence to support engagement with ANSAs and improve humanitarian protection.

Research
From 2020–2022, From Words to Deeds used mixed qualitative methods: analysis of 500+ ANSA-produced documents; desk-based literature review; and more in-depth comparative case studies supported by field research and semi-structured interviews with armed-group leaders and relevant stakeholders (desk-only for Al Qaeda and Islamic State for security reasons). Case studies covered ANSAs in eight countries. The project examined ANSA positions on ten core humanitarian norms. Key findings include that many ANSAs engage on humanitarian issues (though unevenly); positions can shift over time with political strategy and legitimacy concerns; ‘entry points’ such as protection of health care may be more workable than others; compliance is strongly shaped by capacity and command-and-control, knowledge, and enforcement; and sustained engagement is valuable.

Use
Since the project was closed and last reported on in the Annual Review for 2024, its findings and case studies have continued to inform practitioner-facing negotiation and protection guidance and policy work, including outputs by Centre of Competence on Humanitarian Negotiation, International Committee of the Red Cross, Global Coalition to Protect Education from Attack, Geneva Call, PeaceRep, and an FCDO/MoD Conflict, Hunger and IHL practitioners’ legal handbook. Other INGOs are currently using research methodologies that extensively draw on this project’s work.

Result: change in the world so far
The project produced an accessible, consolidated evidence base and practical tools for engagement with ANSAs. It has been demonstrably integrated into policy/practitioner products shaping how humanitarian actors and states approach armed-group engagement.

For the BCC project, this is the first reporting year where impact milestones were set. BCC and FCDO have now together concluded that BCC Impact Indicator 2 has proven to be unhelpfully largely duplicative of BCC Outcome Indicator 2 and needs to be revised as part of wider logframe changes. See Recommendation 1.

Outcome Review

Outcome Statement

Humanitarian protection policy and operations are improved through better evidence of protection risks/mitigations and evidence of what works.

Outcome Indicator Review

Outcome indicator	Milestone (Partner)	Progress towards indicator achievement in the last year
1: Cumulative number of citations of project outputs in relevant high-level reports, policy papers or project documents / (RIAH Outcome Indicator 1; BCC Outcome Indicator 1)	120 (+40) (RIAH) / 7 (+7) (BCC)	Substantially Exceeded / RIAH / Substantially exceeded: 272 (+116) / (see Annex 1) / 111 citations of 11 RIAH research products in academic journal articles. / Five citations of RIAH-supported work in publications from a range of policy and advocacy organisations. / BCC / Substantially exceeded: 18 (+15) / (see Annex 9)
2: Cumulative number of grants/awards/engagement which has informed or changed the work of the government or UN agency or local community / armed actors or NGO implementing partner on the evaluation/research (i.e. instrumental impact) / (RIAH Outcome Indicator 3; HPI Outcome Indicator 2; BCC Outcome Indicator 2)	17 (+3) (RIAH) / 1 (+1) (BCC) / 1 (+1) (HPI)	Moderately Exceeded / RIAH / Substantially exceeded: 31 (+7) / (See Annex 3) / HPI / Not met: 0 / BCC / Moderately exceeded: 4 (+2) / Two evidenced examples (one internal to BCC member organisation the IHL Centre and one FCDO team): / Influence on design of the IHL Centre’s Stockholm Manual (see Annex 10). / Influence on ToC and wider design of proposed FCDO humanitarian programming in one of the BCC case study countries
3: Cumulative number of research studies/grants/awards assessed as making a significant contribution to national or international policy debates (i.e. conceptual impact). / (RIAH Outcome Indicator 2)	33 (+7) (RIAH)	Moderately Exceeded / RIAH / Exceeded: 39 (+9) / (See Annex 2)
[note] RIAH’s systematic review of the literature on violence against healthcare in conflict is the most heavily cited (65 times in academic papers and once in a policy paper), followed by a qualitative study of Myanmar (13 times). The Systematic Review, published in Conflict and Health in May 2021, has been accessed 27,000 times and appears in 198 Mendeley libraries.

The programme has exceeded all three outcome targets both annually and cumulatively this year (but see the preceding ToC discussion).

BEPAC Outcome Indicator 1 (cumulative number of citations of project outputs in relevant high-level reports, policy papers or project documents):

RIAH and BCC both show significant and increasing citations of their outputs in relevant arenas and wider engagement with their work.

BEPAC Outcome Indicator 2 (cumulative number of grants/awards/engagement which has informed or changed the work of the government or UN agency or local community / armed actors or NGO implementing partner on the evaluation/research, i.e. towards instrumental impact):

BCC and HPI are naturally at an earlier stage than RIAH, which is ending. BCC is showing promising progress, as shown in the table above and BCC Progress Story at Annex 10. HPI shows some early results from grants awarded to research teams, beginning to contribute to shifting the work of some organisations. The clearest example so far is the Burkina Faso prevention of sexual exploitation pilot study (funded in the previous reporting year), Sextortion and Entrepreneurship. Building on this, the implementing partner (Empow’Her) has shown strong interest in increasing capacity to expand their training programmes and embed the gender-based violence module co-created in this pilot into their training, to expand this approach to Cote d’Ivoire, and to apply for J-PAL Crime and Violence Initiative funding for a larger scale RCT in the two countries.

RIAH’s research and data have made an important contribution to the global understanding of trends in and the specific impact of attacks on healthcare. Their evolving reach and status as experts in this field as the is now giving them increasing opportunities to influence at the international level. RIAH’s contribution can be seen in a range of ways. The uptake of their data and wider evidence have contributed to international policy debates and increased public awareness. Data uptake alongside engagement and consultations with influential global actors and INGOs have helped inform the approach of these actors to data collection on healthcare attacks and show signs of influencing policy. For example, RIAH-supported data is being drawn on in UN and key INGO reports relating to protection of civilians, which are used to shape and reinforce humanitarian norms (see Annex 2). RIAH Consortium members are invited to present data to humanitarian organisations and advise on data collection and to contribute to policy fora, events and debates (see Annex 3).

During 2025, RIAH conducted a study that produced a mapping report on actions and plans by states and civil society to protect health in conflict, including any plans for advocacy in 2026 (a key year due to the 10th anniversary of UN Security Council Resolution 2286). The work identified barriers to coordination and opportunities for action, generated recommendations, surfaced gaps in awareness and created new stakeholder connections. Interviews with state actors helped prompt a high-level briefing in New York hosted by Denmark’s UN Mission, facilitated links among NGOs and ministries, and led to RIAH participation in a high-level UN retreat on International Humanitarian Law focused on protecting health in conflict. This process has already strengthened networks and spurred concrete follow-on collaboration, including ongoing coordination around 2026 UN-focused activities. A more significant longer-term impact, however, would be the establishment of an international structure to enhance shared communication and collaboration on actions to protect health (which RIAH’s report proposes states, humanitarian and civil society actors work towards). The connections made and awareness raised during the development of this report continue to be built on towards this end. The connections and awareness raising RIAH has facilitated in this reporting year have been enabled by the additional dissemination and uptake funding FCDO granted the project in the contract extension, indicating the value of such a focus on uptake and impact at the end of a project.

BEPAC Outcome Indicator 3 (cumulative number of research studies/grants/awards assessed as making a significant contribution to national or international policy debates, i.e. towards conceptual impact):

In last year’s review, FCDO noted that Outcome Indicator 3 was not proving useful in assessing results contributing towards conceptual impact and recommended that this change as part of a wider ToC review. The quantitative description and milestone here are not as effective as FCDO would like and a better and more qualitative way of assessing conceptual impact needs to be found. This will be addressed as part of the wider ToC and outcome/impact review – see Learning 1 and Recommendation 1.

Section D. DETAILED Programme Scoring

Output Number: 1
Output/Performance Area: Improved understanding of the type, scale and impact of attacks on healthcare (RIAH)
Score: A
Impact Weighting (%): 20%
Weighting revised since last AR?: No
Delivery Partner(s): University of Manchester

Indicator	Milestone (March 2026)	Progress
1.1 Number of reports produced including recommendations of impact analysis methodologies (RIAH 2.3)	1	Met / 1
1.4 Number of evidence-based synthesis of impact case studies (RIAH 4.4)	1	Met / 1
1.5 Number of public engagements (e.g. conferences, workshops, forums) to promote research or policy findings (RIAH 5.5)	8	Substantially exceeded / 15
1.6 No. and type of research outputs available on project websites (RIAH 5.8)	1	Moderately exceeded / 2
1.7 Number of policy-relevant materials available on websites (RIAH 5.9)	TBC	80
1.8 Total number of (externally) peer-reviewed publications (RIAH 5.10)	1	Met / 1

Summary of output/performance area activity and justification of score

As previously noted, output reporting for RIAH in this annual review covers up to end of March 2026 as the project is ending then, not just calendar year 2025 as with the rest of BEPAC.

BEPAC indicator 1.1: The Impact Methods Paper, ‘Methodologies for Evaluating Impacts of Attacks on Health in Conflict’, was published on the RIAH website this year. It outlines RIAH’s methodological approaches, lessons learned, and conceptual issues in evaluating the impacts of attacks on health. The paper summarises qualitative and quantitative methods, their strengths and limitations in leveraging health impact analysis for better accountability and protection, then sets out next steps.

BEPAC indicator 1.4: The synthesis paper was due last reporting year but was delayed because the Afghanistan papers were not yet complete. FCDO and RIAH agreed this would be carried over as a milestone for this reporting period as an outstanding action. Subsequently, the decision was taken to proceed with the paper without including Afghanistan case study data, due to an insurmountable personnel challenge. Despite numerous and repeated attempts to gain access to the Afghanistan data, the researcher who led the data collection and analysis has not shared the files, so a line had to be drawn under this for RIAH to complete delivery by programme closure (see Recommendation 5). RIAH presented the synthesis findings at the International Studies Association (ISA) in March 2025 and have since revised based on feedback. RIAH completed the paper by the project end date and expect to submit to target journal Global Public Health in April 2026.

BEPAC indicator 1.5: RIAH public engagements this year:
- 18 January: International Committee of Military Medicine Workshop on Military Medical Ethics – Legal and ethical considerations of forced medical evacuations.
- 21 February: Webinar – Bombing into submission: Russian targeting of civilians and infrastructure in Ukraine.
- 5 March: Organised and presented on a panel at the International Studies Association Convention in Chicago (Healthcare under attack: Interdisciplinary approaches to understanding the implications of attacks on health).
- 25 March: Global Health Partnership talk: From misinformation to clarity: Enhancing knowledge sharing for humanitarian action in Myanmar.
- 19 May: Protection of Civilians event hosted by Poland and Spain - Protection of Healthcare and Tech.
- 23 May: World Health Assembly side event presenting the CAR research.
- 27/28 May: International Committee of the Red Cross expert meeting on restoration of IHL on interpretation and civilian protection measures.
- 11 June: University of Geneva event: Attacks on Healthcare: From the Syrian civil war to Gaza and Khartoum.
- 12 June: International Council of Nurses Congress - Violence against healthcare during insecurity - strategies for supporting staff and health systems.
- 16 June: Safeguarding Health in Conflict Coalition Launch Webinar for the newly released global report: Epidemic of Violence.
- 12 September: Humanitarian Studies Centre – Normative States.
- 10 October: Global Frontiers conference – Casualties of war: what can be done to protect healthcare facilities, health professionals & civilians?
- 19 November: Invited talk at the Refugee Studies Centre, University of Oxford, ‘Attacking Health’.
- 19 January: Global Interagency Security Forum Community of Practice presentation on International Medical Corps collaboration.
- 4 March: Presentation at Humanitarian Networks and Partnerships Week on Security Risk Management for Health.

BEPAC indicator 1.6: RIAH research outputs added to the website this year:
[note] Additionally, the peer-reviewed study on CAR reported against indicator 1.8 was also added to the RIAH website this year.
- What works and who knows? The importance of community and health worker perspectives in defining solutions to attacks on healthcare
- Normative States: Successes, failures, and Lessons for protection of healthcare.

BEPAC indicator 1.7: RIAH policy-relevant materials added to the website this year (between January 2025 and March 2026, available on Policy Reports page of RIAH website):
- Myanmar Health News Briefs [22]
- OPT Health News Briefs [22]
- Sudan Health News Briefs [22]
- Drone Guidance Myanmar [4]
- Social Media Monitoring reports [2]
- Myanmar Regional Health Guides [7]
- Mapping Report [1]

BEPAC indicator 1.8: Externally peer reviewed publication published this year (see Annex 4):
All the academic journal publications are Open Access, with the exception of the British Medical Journal article that used RIAH-supported Insecurity Insight data.
[note] W Stahl‑Timmins, E Mahase, M Hutcheson and M‑K Looi (2025), ‘How Attacking Healthcare Has Become a Strategy of War’, British Medical Journal Vol. 391: r2153. doi:10.1136/bmj.r2153.

Case study research has concluded. The final publication based on the CAR case study was published in August 2025.
Healthcare under fire: quantifying the impact of violence on medical services in facilities supported by International Medical Corps in three prefectures of Central African Republic, 2016–2020

RIAH have also been working with Tribhuvan University on a study to examine impact of regulatory and bureaucratic impediments to relief work. The report will be published on the RIAH website as a partner contribution.

Additional detail on RIAH progress in this reporting period can be obtained from progress on the outputs from the RIAH-specific logframe. Some key updates are recorded below:

The RIAH oral histories collection contains interviews with individuals from several organisations and institutions (ICRC, MSF, WHO, Insecurity Insight, Johns Hopkins, and the Harvard Humanitarian Initiative), including key figures in the development of significant data and advocacy initiatives on attacks on healthcare. The collection is available from the Humanitarian Archive at the John Rylands University Library. In 2025, nine additional testimonies were finalised; the collection now totals 33 testimonies.

Significant RIAH-Supported Data Collection & Media Attention

RIAH supported the data collection for the 2024 Safeguarding Health in Conflict Coalition (SHCC) report, collating data from calendar year 2024 to record more than 3,623 (up from 2,562 in 2023) incidents of violence against health in 36 countries and territories in conflict. The report is widely read and cited in many news outlets with 40,801 downloads.

Insecurity Insight continued to produce the global bi-monthly news briefs with funding from the RIAH project. They also produce regular reports on the most affected countries (Myanmar, OPT and Sudan), regional reports, drone guidance and social media monitoring in Myanmar. Audience figures have reached 112,564.

After USAID ended support for Insecurity Insight’s data work, RIAH resumed investment in IT development to boost data collection efficiency and information access. Leveraging improvements in automated open-source information gathering, RIAH advanced user-focused data sharing through a global map for the 10th anniversary of UN Security Council Resolution 2286. FCDO funding supports a dedicated version to highlight trends since Resolution 2286, adding new analytical categories.

The Normative States report (April 2025) heavily influenced the approach to the mapping project. The report has been opened over 250 times to date, and cited in several significant policy reports, including MSF’s recent report Medical Care in the Crosshairs.

RIAH members are working to implement the methodological innovations of the project related to impact reporting, which includes collaborating with two major international medical NGOs to pilot a new approach to impact analysis via routine health and security data collection, an approach used in both the CAR and DRC case studies. This work is ongoing. RIAH members participated in a GISF Community of Practice webinar in January 2026 to discuss the pilot projects and will be part of a GISF HNPW session on March 4 to report on preliminary findings.

Output Number: 2
Output/Performance Area: Improved evidence on the impact of protection interventions (HPI)
Score: A
Impact Weighting (%): 40%
Weighting revised since last AR?: Yes (up from 20%)
[note] Output number 4, which brought together communications outputs from all the research projects, has been removed for this AR. This decision was made in June 2025. Comms activities are now reported on within the output reporting from each of the three components. This approach provides a more accurate measure of individual project progress. This has simplified the logframe and made it more accurate. As Output 4 was removed, the relative output weightings needed to be reconsidered. Because there was a large budgetary increase this year for J-PAL, as it commissioned more RCTs and pilot studies, JPAL’s output weighting was increased from 20% to 40%.
Delivery Partner(s): J-PAL

Indicator	Milestone (December 2025)	Progress
2.1 Number of grants awarded for high-quality, policy-relevant research proposals that address HPI priority questions (JPAL 1.1)	3 RCT / 3 Pilot	Substantially exceeded / 5 RCT / 6 Pilot
2.2 Number of HPI-funded projects that include at least one academic from traditionally underrepresented groups as co-PI, namely: / i) co-PIs who are from or based in an LMIC as measured by current university affiliation or having a high-school and/or undergraduate alma mater in an LMIC; / ii) co-PI who identifies as female, non-binary, or agender (JPAL 3.2)	5 / 5	Substantially exceeded / 9 / 9
2.3 Number of HPI Scholar teams who: / i) are paired with a mentor (current J-PAL affiliate or invited researcher) and / ii) complete the mentorship accompanying the implementation of their award. / iii) become Invited Researcher as a result of HPI (JPAL 3.1)	i) 2 / ii) 2 / iii) 2	Moderately not met / 2 / 2 / 0
2.4 Cumulative number of public engagements (e.g. conferences, workshops, forums) to promote research or policy findings (JPAL 2.3)	20	Substantially exceeded / 50
2.5 Number of open access products showcasing FCDO-funded work as part of HPI (e.g. research project descriptions, blog posts, policy insights, evaluation summaries) on J-PAL and IPA's websites: Materials showcasing research outputs (JPAL 2.2 i)	2	Substantially not met / 0
2.6 Number of open access products showcasing FCDO-funded work as part of HPI (e.g. research project descriptions, blog posts, policy insights, evaluation summaries) on J-PAL and IPA's websites: Materials showcasing other policy-relevant outputs (JPAL 2.2 ii)	0	Substantially exceeded / 4

Summary of output/performance area activity and justification of score

BEPAC indicator 2.1: HPI grant awarding achieved in 2025:
- HPI Round Two funded two full RCTs in Myanmar and the Democratic Republic of Congo. (See full list of RCTs and pilots in Annex 7).
- HPI Round Three (July 2025) awarded funding to three full RCTs in Somalia, DRC, and Colombia. [Five total in reporting year.]
- HPI Round Two funded three pilot studies in Afghanistan, Colombia, and Haiti. A fourth off-cycle pilot proposal after completion of second round was funded in Afghanistan, enabling the team to align their research with the timing of the humanitarian program.
- HPI Round Three initially awarded funding to three pilot studies in Myanmar, Egypt, and Niger. The Niger pilot did not proceed due to lack of government buy-in, meaning two pilot studies in Round Three. [Six total in reporting year.]
- Two exploratory proposals were also funded in Round Two in Nigeria, both from HPI scholars.

HPI team support for funding applications:
- Ahead of Round Three, the team held 43 project development meetings with key humanitarian actors and researchers, including IRC, WFP, Oxfam, ICRC, Plan International, Give Directly. From these meetings, 13 resulted in applications to the final funding round.
- In April 2025, a Humanitarian Action Research Incubator was hosted at IPA Philippines, with the goal of developing projects and funding opportunities for HPI in tandem with the Displaced Livelihoods Initiative. Five protection-focused teams from Myanmar, Indonesia, Bangladesh, and the Philippines were invited. Participants strengthened capacity to conduct randomised evaluations, laying the groundwork for future collaborations with researchers seeking impact evaluation funding. Three of the teams applied for research funding under HPI RFP III; one project by Stop Online Harm received pilot funding to evaluate their project on Technologically-Facilitated Gender-Based Violence.

Pilot studies and full RCT projects are ongoing, meaning there are as yet no peer-reviewed publications, journal submissions, or working papers (but see Annex 8 for list of blog and policy briefs).

BEPAC Indicator 2.2: In the HPI RFP II and HPI RFP III, 12 out of 13 research teams included at least one researcher based in or from an LMIC and/or a researcher who identifies as female. Among the HPI-funded projects with LMIC-based Co-PIs are Somalia, DRC, Egypt, Myanmar, Afghanistan, Colombia, and Nigeria. Research projects involving at least one academic from traditionally underrepresented groups as co-PI make up 92% of overall funded projects.

BEPAC Indicator 2.3: During the second RFP round, 14 scholars submitted an expression of interest with nine full proposals. In the third round, six scholars submitted their expression of interest, followed up by two full proposals. Two scholars were paired with a mentor this year and two completed their mentorship. There was no scholar project in the third round, due to: (1) the limited scope of most proposals; (2) insufficient time for further project development, and (3) in the final round, full RCTs and pilot studies were prioritised for funding over exploratory proposals, which were the primary type of applications submitted.

BEPAC Indicator 2.4: In 2025, HPI staff participated in 50 engagements with policymakers and practitioners to motivate evidence generation and evidence use. Engagements included 43 meetings dedicated to advancing the HPI project and partnership development, three events and conferences aimed at building connections for project development and evidence dissemination, and four evidence dissemination sessions.

Key project and partnership development meetings:
- IPA met with leaders from Stop Online Harm, a survivor-led organisation aimed at reducing and responding to technology-facilitated gender-based violence in Myanmar. The team joined the Research Incubator in Manila and were awarded funding for a pilot study.
- IPA met with Plan International’s Child Protection team to discuss programs that could be suited for an evaluation. This led to arranging a virtual workshop for January 2026 with their team to understand the evidence base and increase evidence use.
- J-PAL and IPA met with the International Rescue Committee team to discuss potential programs that could apply for HPI round III evaluation funding; two pilot proposals were subsequently submitted and considered.
- J-PAL met with the director of the International Security and Development Center (ISDC) to discuss future collaborations.

Key events and conferences:
High-Level Engagement with WFP Leadership and the UN ecosystem in Rome
- Closing Conversation and Senior Leadership Engagement at the Global UN Impact Evaluation Forum: Prof. Abhijit Banerjee's keynote address.
- Participation in the Global UN Impact Evaluation Forum included a set of publicly accessible content pieces to extend reach beyond the in-person audience and amplify core thematic messages on evidence use in humanitarian settings:
1. Cost-Effectiveness in Humanitarian Settings
2. Future of Humanitarianism
3. Lessons from Local Research Partnerships.
- High-Level Panel on Evidence for Saving Lives in Humanitarian Contexts: J-PAL Europe convened an event examining how impact evaluations can inform lifesaving and protection interventions.
- Riyadh Humanitarian Forum (KSRelief): J-PAL co-organised and contributed to a high-level panel on ‘The Role of Evidence Generation in Driving Impact for Humanitarian Action’.

Key evidence dissemination sessions:
- HPI met with ICRC and UNHCR to present J-PAL’s The Evidence Effect: Evidence for action in conflict and crisis.
- Global UN Impact Evaluation Forum panel on ‘Decision-Making during the Humanitarian Reset’: HPI co-hosted this panel with WFP, bringing together researchers and practitioners to explore how rigorous evidence can inform humanitarian action.
- Climate-Conflict Nexus: A Crisis that Demands Innovation: On the margins of the UN General Assembly, IPA and IRC co-hosted a roundtable on the climate-conflict nexus to identify and align the next generation of research questions.

BEPAC Indicator 2.5: The funded project webpage provides an overview of all projects that have received HPI funding, allowing researchers and practitioners to see what work is currently in the pipeline. As most projects are ongoing, there are no materials showcasing research outputs.

BEPAC Indicator 2.6: Products showcasing policy-relevant outputs, including how FCDO-funded projects are situated within the existing literature (Annex 8):
- Preventing Violence Against Women and Girls: What we’ve learned in the 30 years since the Beijing Declaration
- Driving Innovation amidst Crisis: The Humanitarian Action and Displacement Response Research Incubator in Asia
The Evidence Effect Campaign is a key example of distilling insights from existing evidence. It led to clear recommendations for practitioners via 1) a broad overview and 2) a focused synthesis which explored the protective potential of perspective-taking programs:
- The Evidence Effect: Evidence for action in conflict and crisis
- From bias to belonging through perspective-taking

Describe any changes to this output during the past year, and any planned changes as a result of this review.

For public engagements (Indicator 2.4) the performance this year suggests that the target may not have been ambitious enough. HPI has now proposed milestone targets for their final year of delivery, which will be reviewed by FCDO to ensure they are stretching but achievable (see Recommendation 2).

Output Number: 5
Output/Performance Area: Improved evidence on the drivers for restraint and compliance with IHL by armed actors (Beyond Compliance)
Score: A+
Impact Weighting (%): 40%
Weighting revised since last AR?: No
Delivery Partner(s): University of York

Indicator	Milestone (December 2025)	Progress
5.1 Percentage of requested written submissions and oral briefings provided to the FCDO through the Research Line that fall within the scope of the Beyond Compliance Component (BCC 2.1)	70%	Moderately exceeded / 100%
5.3 Percentage of outputs 5.7 and 5.8 co/authored by women (BCC 1.6)	50%	Moderately exceeded / 76% / Annual total: 13 out of 17 outputs 5.7 and 5.8.
5.4 Percentage of outputs 5.7 and 5.8 co/authored by Global South researchers. (NB Global South researchers are defined as those from ODA recipient countries. These include all the 9 case study countries of the BCC programme) (BCC 1.7)	40%	Moderately exceeded / 59% / Annual total: 10 out of 17 outputs 5.7 and 5.8.
5.5 Number of regional and local workshops conducted by BCC and addressed to local community actors seeking to disseminate programme findings, share experience, bridge capacity on restraint, compliance, protective environment and facilitate co-production and operationalisation of tools (BCC 3.2)	1	Substantially exceeded / 7
5.6 Number of engagements with humanitarian, human rights, peacebuilding, development actors through events and other public engagement opportunities that facilitate dissemination of BCC research (BCC 4.3)	6	Substantially exceeded / 23
5.7 Number of policy briefs and blog symposium articles (excluding Research Line) (BCC 1.2)	9	Moderately exceeded / 15
5.8 Number of original peer-reviewed publications produced by BCC and submitted for publishing in open access format (BCC 1.1)	2	Met / 2

Summary of output/performance area activity and justification of score

BEPAC Indicator 5.1: The Research Line received seven requests from the FCDO during this reporting period. The BCC delivered six responses: four written briefs and two oral briefings. The Sudan request fell outside the geographical scope of the BCC but the Research Line was able to leverage the expertise of the IHL Centre (on a pro-bono basis) and provide a response (seven total).

1. Written brief ‘What are the most pressing historic, and/or ongoing violations of IHL that are having the most significant impact on the current humanitarian landscape, as of January 2025?’ (January 2025).
2. Oral briefing ‘North East Syria: detention camps and protection of children’ (March 2025).
3. Written brief ‘Opportunities and challenges in designing interventions that integrate humanitarian and human rights approaches in Myanmar’ (July 2025).
4. Oral briefing ‘Behaviour analysis of HTS’ (August 2025).
5. Written brief ‘The What, Who and How of Compliance and Restraint by Non-State Armed Groups: A Snapshot of Behavioural Variation’ (November 2025).
6. Written brief ‘Assessment Thresholds, Ethnic Violence and Identification of Serious Violations of IHL: El Fasher, Sudan’ (November 2025).
7. Additional: written brief ‘Myanmar’s Armed Conflict and Earthquake: Compounded Harm & Need’ (May 2025) – proactively produced by BCC; not requested by FCDO.

As noted in Section B, it has proven difficult to obtain much meaningful feedback from FCDO users of Research Line products. This year, BCC sought to address this concern by soliciting more informal comments via email or in conversations and organising a small number of qualitative follow-up interviews, though this also proved challenging. Whilst 100% of FCDO respondents (3 out of 3) rated the analysis provided in these briefings as either ‘excellent’ or ‘good’, and 67% of FCDO respondents (2 out of 3) indicated the ‘output holds potential to influence policy’, this is a low number of responses so is not strong evidence for learning and adaptation purposes. See Recommendation 4 on this. However, it is notable that one brief was drawn on to support programme design of humanitarian programming an FCDO country team was developing (see Indicator 2 in the earlier Outcome Indicator Review). Further, the written brief on non-state armed groups led to subsequent engagement with the FCDO policy team who lead on HMG engagement with non-state armed groups, including extensive expert feedback from BCC researchers on an FCDO policy paper, which was valued by the policy team.

BCC also delivered five oral thematic briefings on: cross-border and cross-line operations; inclusion gaps in humanitarian response; roles and responsibilities of non-state armed groups; the strategic and tactical use of IHL within humanitarian programming and advocacy; and conduct of hostilities and the balance between military necessity and humanity.

BEPAC Indicator 5.5: BCC regional workshops in 2025:
3x BCC workshops engaging local actors and armed and governance actors (45 total participants):
  - BCC DRC workshop with external stakeholders on validation of findings, Goma (June).
  - BCC Colombia data sharing and validation workshop, jointly with the Agencia para la Reincorporación y la Normalización (Agency for Reincorporation and Normalisation) with demobilised FARC fighters, Cali (October).
  - Regional BCC Serious Game Co-design Workshop; external participants including policymakers and members of local communities working in human rights and humanitarian fields, Nairobi (November).
4x BCC workshops with participation of BCC members’ local staff and local partner organisations:
  - BCC Yemen CRU workshop with Fight for Humanity and three local researchers from the Yemen Policy Group, Amman (April).
  - BCC Somalia CRU workshop series with BCC researchers on Somalia (Centre on Armed Groups and BCC Somalia researcher) and BCC local partner organisation, Elman Peace, Mogadishu and online (April-May).
  - BCC Colombia data analysis and reflexivity workshop with Fight for Humanity, University of York, local partner organisation Indepaz and the Indigenous community Resguardo Indígena de Huellas Caloto, Bogota (October).
  - BCC DRC and South Sudan data analysis workshop with War Child DRC and South Sudan researchers, IHL Centre Nairobi office, and University of York, Nairobi (November).

BEPAC Indicator 5.6: BCC engagements:
Academic conferences with BCC participation included flagship events such as the International Studies Association annual conference, the International Political Science Association World Congress, and an event organised by the American Academy of Sciences and Arts.

Engagement highlights include (see Annex 12 for full list):
1. BCC-organised public roundtable ‘Harm + Need in Armed Conflict: What to Expect from Law, Policy and Practice in 2025?’, with 92 participants.
2. Watchlist on Children and Armed Conflict Policy Workshop hosted a BCC panel on 'Beyond Compliance: Exploring a Harm and Need Approach to the Protection of Children in Armed Conflict'. BCC research findings shared with 50 participants from diplomatic missions, humanitarian and human rights organisations and academia.
3. BCC High-Level Ministerial Dinner on Children and Armed Conflict on the margins of the UN General Assembly High-Level in September, with representatives from a range of countries.
4. Geneva Peace Week, as part of the panel ‘Beyond Compliance in a Chaotic World: Achieving Full(er) Protection in Armed Conflict’, BCC researchers from Fight for Humanity, the University of York, Utrecht University, CIVIC and the Centre for Armed Groups presented early empirical findings to an audience of 105.
5. BCC researchers from Glasgow, CIVIC, IHL Centre, and Elman Peace Somalia designed and co-hosted a booth at the first-ever ‘Solutions Showcase’ at the 5th International Conference on the Safe Schools Declaration (SSD) event. This gathered research and practitioner organisations to demonstrate how they are innovating in order to better protect children in armed conflict. Over 400 participants attended from 57 governments, UN agencies, civil society organisations, academia, and children and youth advocacy groups.

Additional opportunities to engage policy audiences were pursued in 2025 through written submissions. In February, BCC submitted written evidence in response to the House of Commons International Development Committee’s inquiry on humanitarian access and adherence to international humanitarian law. The IDC report extensively cited the BCC submission. BCC also responded to a call for submissions from the UN Special Rapporteur on the situation of human rights in Myanmar in December, using conceptual and empirical data.

BEPAC Indicator 5.7: 15 blog articles (see Annex 11 for full list).

BEPAC Indicator 5.8: BCC academic articles:

1. Abikar and Jackson’ article (both Centre on Armed Groups): ‘Social Infrastructures of Protection: Civilian Protective Agency and Community‑Led Harm Reduction in Somalia’ with empirical findings on harm + need submitted and discussed at the workshop Gender, Peace and Security: Resistance and Resilience, Nairobi, December 2025, to be included in an edited book by the same name (publication date TBC).
2. ‘Reconciling proportionality in attack with a decolonial approach to mental harm’ submitted to the International Review of the Red Cross in May 2025 (accepted for publication in September 2025 and forthcoming in summer 2026).

A more comprehensive picture of BCC progress can be obtained from progress on the outputs from the BCC-specific logframe. Some key updates are recorded below:

In July 2025 the quantitative research team finalised the pilot phase of the IHL database and the pilot codebook. The Quants + IHL team held a Review Workshop that month; after revising the codebook following workshop feedback, coders completed the data collection phase in December 2025. The database provides systematically collected, micro-level data on armed actors’ conduct across violent events in Somalia, South Sudan, and Myanmar. The data and codebook will be shared in an interactive, open access format: the Beyond Data Hub.

The Beyond Compliance Blog Symposium (see Annex 8) engages practitioners and scholars on BCC concepts and emerging empirical findings. A booklet of blog contributions has been widely circulated at BCC events in 2025 and a selection of articles have been translated into Arabic and Spanish. In 2025, there were 4,101 page views of the Blog Symposium webpage on the BCC and Armed Groups and International Law blog landing pages.
[note] More broadly, BCC overall receives good engagement on LinkedIn, with 551 new annual followers against a target of 400. The newsletter has 204 subscribers against a target of 75.

Beyond Compliance: In Conversation podcast series has produced 14 episodes (7 this calendar year), spanning two different seasons (see Annex 11). In the first season, the podcast explored the theme of civilian agency by having conversations across disciplines, whilst the second season focuses on ‘Harm + Need – People’s Lives during Conflict’. There have been 2,442 cumulative total downloads of all 13 released episodes published on streaming apps by the end of 2025 and the podcast has generated positive feedback. The podcast has over 1000 followers on Spotify and 10 reviews, all of which are 5-star.

BCC have developed a Beyond Compliance Paper Series (see Annex 11). The first publication of October 2025 presents the state of the art on compliance and restraint by armed actors and the second in November 2025 maps trends of harm + need in Myanmar drawing on quantitative data.

Data analysis and reflexivity workshops were used to support Country Research Units to review their emerging fieldwork findings and ensure consistent quality across different case study contexts (e.g. DRC, Somalia, South Sudan, Yemen). Validation workshops were used to iteratively test how key stakeholders (especially local actors) engage with the conceptual and empirical findings of the research. Regional co-design workshops in Nairobi (November 2025) and Amman (January 2026) were used for the development of the BEYOND 2D Game, inviting participants to draw on research material, professional experiences of protection, and lived experience of conflict. BCC Country Research Units were able to present and integrate emerging field research findings from Colombia, DRC, Myanmar, Somalia, South Sudan, Syria, and Yemen.

The BEYOND Game seeks to harness emotions, immersive learning, and game mechanics to enhance understanding about harm + need experienced in conflict and compliance + restraint as strategies for fuller protection. In 2025, the BCC developed an original co-design process for the new BEYOND 2D. The co-design approach, which draws on the experience of Rebecca Sutton’s (CoI, Glasgow) CEASEFIRE! prototype co-design process was piloted in the two in-person co-design sprints in Nairobi and Amman. The game will be substantially completed by the end of March 2026.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Output Indicator 5.8 currently encompasses academic papers submitted for peer review/publication, which has been a useful way of assessing progress in this reporting year. However, as we move into BCC’s final 15 months of delivery, this indicator will be adjusted to set realistic but stretching targets for achievement by programme end of published, or accepted for publication, peer-reviewed academic papers that will help support outcome achievement.

In this reporting year, BCC has substantially exceeded targets for regional and local workshops (Output Indicator 5.5) and public engagements/events with humanitarian, human rights, peacebuilding and development actors to disseminate BCC research (Indicator 5.6). This suggests that targets could be more ambitious for the final year, with attention paid to how to ensure these outputs help drive outcome achievement.

As the BCC project is now much more advanced and entered its final 15 months of operation, the indicators from the BCC project logframe that the BEPAC master logframe draws on will be reviewed and revised, to ensure they accurately reflect the stage the project is at and focus on higher value outputs to drive achievement of outcomes.

See Recommendation 2.

Section E. Programme Management Review

Risk

Overview of risk management

The risk appetite for the programme is Cautious. In the last reporting period, the overarching post-mitigation risk for the programme remains at a Moderate level.

Strategy & Context	Policy & Programme Delivery	Public Service & Delivery Operations	People	Financial & Fiduciary	Safeguarding	Reputational	Overall
Moderate	Moderate	Minor	Minor	Moderate	Moderate	Minor	Moderate

Strategy and Context

The fragile and volatile contexts in which much of our partners’ work takes place present logistical and potentially ethical challenges for conducting research. Fielding research teams in these contexts is often costly; constantly shifting states of political and social stability require high levels of flexibility. This can delay or prevent research implementation.

Our partners conduct detailed feasibility and risk assessments in the planning phase and monitor this throughout the project lifecycle. They adopt contingency planning where needed, such as focussing on desk-based research or conducting interviews remotely or in neighbouring countries. Partners are regularly in touch with FCDO to inform and consult on developing situations and planning, often informed by on-the-ground local expertise. When data collection is not possible at certain times, partners’ efforts can be redirected to activities such as analysis and dissemination.

BCC has a budget for unforeseen emergency expenses that takes into account the nature and context of the field research. J-PAL’s Policy Advisory Group supports decision-making by providing input on the ethical considerations of working in certain contexts and any context-specific risks on the ground. IPA has implemented an ‘Outside of Country Office’ policy to assess potential engagements by level of risk, strategic value, and operational feasibility. J-PAL and IPA's wide research networks can advise new researchers on almost any context. As J-PAL expand into new geographies, IPA has implemented an ‘Outside of Country Office’ policy to assess potential engagements by level of risk, strategic value, and operational feasibility.

Policy and Programme Delivery

The risk around the RIAH Afghanistan case study emerged as an active issue as it remained delayed and subsequently could not be delivered. This was initially flagged to FCDO in June 2023. It is important that, going forwards, partners clearly flag the severity of risks when such issues arise, so mitigations for the possible consequences can be discussed as soon as possible. Additionally, FCDO needs assurance that partners are carrying out extensive downstream partner due diligence, including an examination of duty of care protocols to their researchers and research subjects. See Recommendation 5.

There is a J-PAL risk of insufficient relevant high-quality proposals received to comply with annual spending targets. This was mitigated through extensive project development prior to the launch of the request for proposals for Round II and III. Many of the projects that were funded were sourced through training and project development meetings. HPI team provided research support to researchers via an innovative Research Quality Support system. HPI staff will support through tailored research support meetings to guide and advise on the development of their proposed projects.

Public Service and Delivery Operations

The primary risk operationally is that policy makers do not use evidence generated by the programme, thus limiting impact. This is especially pronounced if there is high staff turnover. J-PAL and IPA have well developed policy engagement strategies before, during, and after production of new research. The Board members of HPI evaluate proposals based on policy impact (among other criteria). The HPI team will track the number of projects that have a government partner on the evaluation, or have concrete policy influence, under the assumption that a government is more likely to take up research results if they are involved in designing and conducting the intervention. HPI staff and funded researchers also frequently connect with policymakers (governments, NGOs, funders, and others) via one-on-one meetings, seminars, and sectoral conferences to disseminate findings of HPI-funded research. J-PAL has an ‘Evidence to Scale’ vertical focused on supporting the adaptation and uptake of evidence in new and existing contexts. RIAH have a small working group who ensure that research results are implemented as widely as possible.

People

The HPI team have demonstrated a strong ability to quickly adapt to changes in staffing as various team members have departed and new team members have been brought onboard. J-PAL and IPA intentionally hire a mix of staff who are both sector experts as well as policy generalists so that, as staffing changes occur, it is relatively easy to transfer staff between teams if needed to supplement team capacity as new staff are brought onboard.

There is risk of staff turnover within the large BCC consortium due to the number of actors involved – this has been met with drawing on expertise from other members of the consortium and the associated organisations. There have been examples of departing staff being contracted to the project as consultants including in-kind contributions from new employers.

Financial & Fiduciary

Over the course of this reporting period, the main financial risks to BEPAC have been related to under/overspend by partners. This has been mitigated through ongoing monitoring and communication with FCDO and partners as well as an approach that allows partners to vire between budget lines with FCDO approval.

There is a risk with J-PAL having moved the bulk of spend for the year into Q4, that invoices will not be submitted on time by partners. The result of this will be financial liability for J-PAL possibly beyond the allocated £200k for next year, and an over-accrual by FCDO. FCDO is in regular contact with J-PAL about this concern, and they assure us that they continue to remind partners of the importance of timely invoicing and are largely confident that this will be achieved.

All programme partners host regular meetings with funders and consortium members / partners to establish whether resources and spending are on track with research objectives. Mitigation processes include extensive due diligence before funds are committed, regular and robust performance and financial reporting, invoice spot checks, and payment milestones which enable timely corrective action.

As the project draws to a close, JPAL have intensified follow-up with sub-grantees (monthly milestone tracking for higher-risk projects), re-phased workplans to prioritise core deliverables, and prioritised projects most likely to be completed within the timeframe.

Safeguarding

The primary safeguarding risk for the programme is the safety of the researchers as they conduct the research for the different projects that make up BEPAC. BCC engages with state and non-state armed actors, but the physical and mental wellbeing of their researchers is paramount. There is a risk of sexual exploitation, abuse and harassment (SEAH) in academia and research, due primarily to the inherent power imbalance between parties.

To mitigate this, all partners have strong policies and robust reporting procedures to escalate potential risks of this nature to the first-tier partner, as well as escalated to FCDO Reporting Concerns so that suitable action can be taken immediately.

BCC is mitigating against the risk of SEAH by ensuring that all partners adhere to the IASC Minimum Operating Standards on PSEA and/or the Core Humanitarian Standard on Quality and Accountability. Further mitigation has been achieved through applied ethics trainings with researchers. BCC member organisations were also asked to fill out safeguarding self-assessment forms to inform them on strengths and any areas for reinforcement or further training/support. The BCC organised an online training session for researchers and local partners on vicarious trauma and wellbeing provided by specialist trainers in Nov. 2025.

At J-PAL, MIT have guidelines on vetting partnerships based on ethical concerns. To ensure that ethical standards are upheld, JPAL have implemented the Research Quality Support process to oversee funded teams. These steps help ensure that J-PAL is not inadvertently working with or funding countries or partners that may be engaged in systematic human rights violations. Applicants are part of universities that require research to undergo internal ethical review boards before it goes forward. All staff are required to undergo a training on working with human subjects and referrals for psychological support are offered if required.

RIAH conduct research with the appropriate ethical clearance led by the UoM University Research Ethics Committees (URECs). The Code of Practice for Investigating Concerns outlines the process followed if allegations of research misconduct are received.

Reputational

Given the nature of BEPAC’s humanitarian work, there are risks surrounding research ethics and around findings that challenge the humanitarian system as it currently functions.

To mitigate, applicants need to prove that their project can be delivered to the highest ethical standards. The initiative’s scope and focus on humanitarian settings necessitates a heightened investment in ethical research design and implementation as well as robust due diligence procedures. FCDO accept the risk of system challenge as an important part of any research that aims to intervene and make change in the world.

J-PAL and IPA share proposals with FCDO country offices, enabling them to flag any concerns before they are reviewed by Review Boards. Review Boards take into consideration potential ethical and reputational risks of conducting research, which they factor into their award decisions.

Value for Money

Key cost drivers and performance

Key cost drivers from the Business Case remain valid and currently are the cost of research personnel to deliver high quality impact evaluations and case studies (70-80% of overall costs). The cost of research uptake (outreach activities), capital expenditure, management costs, the costs of providing operational support to programme teams, and monitoring costs make up the remaining key cost drivers.

VfM performance compared to the original VfM proposition in the business case

Economy

RIAH aims to leverage established platforms (like DHIS2 for reporting or DisasterReady for training) rather than building bespoke systems from scratch. This offers cost savings by avoiding duplication of tools and infrastructure. The mapping project drew on interviews across governments, civil society groups, and researchers who gave their time freely. The time of IMC and MSF staff who are collaborating with RIAH are giving their time pro bono. Insecurity Insight has received complementary funding that contributes to the same incident-recording infrastructure used for RIAH data collection. This co-funding helps maintain and improve the data systems while reducing RIAH’s direct costs and expands the range of activities.

J-PAL’s establish funding caps for different proposal types, for instance travel and pilot grants are capped at US$10,000 and US$75,000 respectively. This ensures HPI can economise FCDO funds and obtain research results for reasonable cost. J-PAL and IPA have an established local presence in over 30 countries employing policy staff with deep knowledge of local contexts. This enables HPI to benefit from economies of scale with respect to the cost of implementing field research.

BCC uses the same country case studies for qualitative and quantitative data collection, the Research Line, dissemination, and uptake, which ensures that the same teams will be involved in most aspects of the research. This keeps staffing, management, travel, and fieldwork costs to a minimum. BCC has leveraged savings through an in-kind contribution of staff time from DEval and the IHL centre.

Efficiency

RIAH’s research protocols used for the qualitative case studies have proven adaptable to different conflict contexts. Publication of the methods paper will ensure that the most important elements of methodological innovation are captured for policy and academic audiences to ensure research can be replicated and scaled in future projects or new contexts. Investment into Insecurity Insight’s data-collection process allows their outputs to be delivered with less staff time.

By building on best practices from similar initiatives such as GCCI, HPI funds projects that build upon and complement each other. J-PAL implements HPI in accordance with financial regulations which draw from MIT’s financial procedures. These are built specifically to efficiently manage large-scale research efforts while providing reasonable oversight and control. HPI was able to efficiently use staff time to ensure project development via matches made between implementing partners and relevant researchers, drawing on J-PAL and IPA’s growing connection to humanitarian organisations.

By benefiting from the knowledge of country-based, established staff, BCC has ensured an efficient and smooth delivery of research as the project scales. BCC seeks to ensure efficiency through complementarity of skills and expertise across the work packages. BCC expects that by the end of the programme all CRUs will have worked across all three BCC work packages. Efficiency is also seen through leveraging the complementarity of skills and expertise within and across the work packages, for instance involvement of field researchers in co-production of the Beyond game.

Effectiveness

RIAH’s outputs allow for more informed data collection and analysis of what works in the protection space, as well as development of new methodologies to inform key health, protection, and diplomatic actors’ decision-making and policy. Uptake of the data collection and analysis methodologies has and will continue to contribute to generating more robust evidence to support advocacy for policy change and future funding for resilient health programming in conflict contexts.

HPI funding is directed towards key priorities for policy relevant research. Proposals are evaluated against standardised criteria, ensuring an effective process that holds all submissions to the same high standards. As part of the review process, proposals receive comments and feedback from top academic and policy experts in this thematic focus, helping to further develop the field and improve the quality of proposals. J-PAL and IPA are well positioned to engage in effective, results-oriented policy outreach given their longstanding, trusted partnerships with many governments and multilateral organisations.

BCC Output indicators for delivery, for example the Blog Symposium, Podcast Series, and public events demonstrate good uptake in activities so far. The podcast series has gained public traction with 2,422 total downloads of the 13 episodes published and there have been 4,101 page views to the BCC blog symposium webpage. Research Line thematic briefings have been consistently well-attended with 40-60 participants each session.

Equity

RIAH’s activities are led by or include contributions from colleagues at organisations in LMICs in countries such as Nepal, South Sudan, Myanmar, Afghanistan, CAR, and the DRC. There are seven named researchers in the project, three of which are women (including the PI). 100% of publications include female authors.

The inclusion of gender as a cross-cutting theme in HPI original design has continued to promote equity in research. In 2025, 9 co-PIs from HPI-funded project identified as female, non-binary, or agender, exceeding the milestone of 5. In 2025, 9 co-PIs from HPI-funded projects were based in an LMIC. These grants have increased the diversity and inclusion of researchers attending leading economics conferences by extending accessibility to scholars from low- and middle-income countries studying governance topics.

The BCC programme has a commitment to gender equity. This is evidenced by the makeup of the leadership team, which is 80% women – with a female principal investigator. In 2025 76% of academic publications, policy briefs, and blog articles were coauthored by women and 59% by Global South researchers. The BCC is actively working with colleagues across different career levels and with research partners from indigenous and minoritised communities, with a focus on increasing research capacity.

Assessment of whether the programme continues to represent value for money

Across the outputs and outcomes, our partners have met and regularly exceeded expectations for value for money. As the JPAL and BCC projects reach scale, FCDO expects to see additional valuable insight into humanitarian protection research from partners. All three projects benefit from academic oversight as well as benefitting from in-country global networks which facilitate Southern partner engagement. The programme involves collaboration between academics and key humanitarian actors in the NGO and multilateral space, advancing conceptual and instrumental impact in humanitarian protection.

In this reporting period RIAH saw the highest annual increase (116) in academic and policy citations, showing the growing visibility of the project. The number of engagements with organisations which have informed / altered their approach to data collection on attacks has risen by 8 in 2025, and the number of references to project outputs, findings and deliverables in statements or reports by member states, UN agencies, international organisations, and NGOs has risen by 9, demonstrating RIAH’s commitment to raising the profile of attacks. For BCC, there were 18 citations of project outputs in relevant high-level scholarly outputs, inter-, non- and governmental reports, policy papers or project documents in 2025, exceeding the target of 7. Similarly, there were 6 cases where BCC research directly or indirectly influences policy, programme design or implementation by FCDO/HMG, by BCC member organisations, and other humanitarian, human rights and development actors, far surpassing the target of 1. Early results from grants awarded to research teams have begun to shift the work of the government, UN agency, or NGO implementing partner on J-PAL evaluations. These will be explored further in the PCR but demonstrate the efficacy of the RCTs at a local level.

Finance and Commercial

All partners on the BEPAC programme engage with FCDO on a regular basis and have been attentive to requests for additional information. Effective negotiations have meant that sound agreements are in place for all components of the project, and through regular engagement with partners we ensure bookkeeping is open and transparent.

All three partners engage with an annual external audit, the results of which are reported to the FCDO. RIAH provided their audit report signed off in January 2026 reporting no instance of material misstatement and JPAL provided their report signed off in June 2025 stating the same. BCC’s report was submitted without issue in September 2025.

During this reporting year, accountable grant amendments were submitted for all three partners. For RIAH, this involved an increase in budget of £0.25m in January 2025 for additional dissemination and uptake activities. For the BCC, this involved a shift in annual allocations, moving money from 26/27 into 25/26. These costs related to the BEYOND 2D mobile game and the historical database, as planned activities started earlier for these two outputs. In February 2026 an AG amendment was signed with J-PAL extending the project until December 2026, moving £200k into FY26/27 due to delays in the commencement of the project caused by postponement of the grant signature.

The programme delivery team has now recruited a PRO who joined in November 2025.

Financial Performance

Please note, forecast figures and variance for each quarter have not been included here due to the accountable grant amendments which were made during the year. Considering these amendments, variances would appear overstated and thus paint an inaccurate picture of partners’ financial management.

	Spend (£)
Partner	Q4 - Actual	Q1 - Actual	Q2 – Actual	Q3 - Forecast	Forecast Total
RIAH	55,051.94	62,879.00	84,934.22	265,792.03	468,657.19
J-PAL	96,153.00	164,844.00	272,888.00	1,521,881.00	2,055,766.00
BCC	429,983.03	426,480.14	506,167.16	615,724.70	1,978,355.03

All three partners invoice the FCDO in quarterly in arrears. Expenditure reports and forecasts are sent to FCDO on a quarterly basis, and partners flag any significant budget virements of more than 10% in value. Financial reports are monitored against the agreed budget and checked to ensure that costs are realistic and represent value for money.

The University of York programme team managed the funds in a responsive and agile way, reallocating funds between member organisations as need arose. For example, funds that were not being used for impact-related staffing at one BCC member organisation, were put towards the development of impact-generation tools (e.g. the Beyond game), ensuring VFM.

FCDO is going to pursue the recovery of costs spent on the RIAH Afghanistan research which did not lead to published outputs due to the personnel issue detailed in Output 1. FCDO is engaging with the project team at the University of Manchester to agree this.

MEAL

The main reporting period for this review is calendar year 2025. This applies to programme components 2 (HPI) and 3 (BCC). Component 4 (AHRC) concluded before this reporting period and as such outputs from this component are not being reported against in this review. Component 1 (RIAH) reporting year was agreed to be 15 months – January 2025 up to end of March 2026 – as this component comes to an end 31 March and its final milestones were agreed for the 15-month period when the last funding extension was agreed in late 2024.

This Annual Review was written by the Humanitarian Research DPM and PRO drawing upon information provided by the partners of the programme. FCDO has discussed this review with key partners during Q3 meetings, who have been obliging in answering queries and providing additional information. Partners provided references to outputs where appropriate enabling these to be checked and tallied within the report.

Additionally, the PRO attended the RIAH component’s two-day project end meeting in Geneva in March 2026 and extensively discussed lessons learned from the project and future plans with core members of the consortium. The PRO also met with a member of the BCC consortium in Geneva and discussed progress and initial ideas for course correction to obtain more fruitful feedback from FCDO stakeholders on the project’s Research Line offer in the next year (see Recommendation 4).

Programmes apply a robust monitoring approach to monitor the performance and effectiveness of grants. FCDO and partners have been in frequent contact over the course of the reporting period, both for exchanges on the research and to discuss progress on deliverables, finances, and risks. Quarterly meetings are scheduled to discuss the projects and their progress. Each partner’s performance is tracked through a logframe, these are then combined into the wider programme level logframe to gauge overall performance.

For this reporting period RIAH, BCC, and two projects from the Collaborative Humanitarian Protection Research Programme (which ended in March 2024) were asked to send in detailed outcome/impact stories (case studies) as part of their reporting. AI tools were used by FCDO to improve the efficacy of some of these reports for inclusion in the review text, to highlight key achievements.

The learning driver of the programme is to increase the understanding, knowledge of, and evidence base around protection. This is achieved primarily through the key areas captured in the logframe such as producing learning materials, making academic outputs widely available, and hosting public engagements. In accordance with the ToC, as long as the assumptions hold, it is expected that these learning products will go on to improve humanitarian protection policy and operations through better evidence. However, this will be reviewed as part of the wider ToC review (see Recommendation 1).

RIAH continues to contribute to the evidence base on attacks on healthcare by capturing more fully the nature, frequency, and scale of attacks in conflict and to improve the methodologies employed to measure the impact of the problem. Where possible and where suitable, disaggregated information by protected characteristics is captured and utilised to strengthen the outputs of the programme, which means the BEPAC programme is actively supporting the ‘leave no one behind’ agenda.

During the reporting period J-PAL organised four evidence dissemination events focused on summarising protection-related research and three conferences aimed at building connections for future project development. These are discussed in detail in Output 2.

BCC has gained traction with their blog symposium and podcast series which are accessible ways for people to access information on the protection space and understanding of IHL. BCC document any informal feedback from participants at events or related to outputs such as the podcast series which they receive on email, social media, in testimonials, or as anecdotes orally. BCC continues to circulate surveys for Research Line written submissions and thematic briefings and post-event evaluation surveys for BCC public events. They also track website traffic and analytics, as well as social media statistics.

BCC has worked together with a group of 7 postgraduate students at the University of York to gain some initial MEL insights. As part of their academic course, pursuant to training and ethics approval, the students held interviews with 18 individuals across the BCC’s member and local partner organisations, some FCDO staff, and a limited number of other stakeholders. Their report evaluates aspects of the research and some outputs (e.g. the impact of the podcast), whilst providing a set of suggestions and recommendations on how to broaden and deepen impact. BCC member organisations and local partners also complete on a bi-annual basis narrative reporting forms and internal workshops, where they report on research progress, identify challenges, and share lessons learnt. BCC has incorporated feedback from member organisations to better facilitate access to findings and lessons learned from the country research units.

Compliance checklist

Gender Equality and / Public Sector Equality Duty	This programme contributes to improving our understanding of how gender affects protection risks and protection outcomes. The programme complies with the Gender Equality Act and will also support commitments in the UK’s Women Peace and Security National Action Plan (UNSCR 1325) to improve evidence and country-level data on women and conflict. / There are seven named researchers in the RIAH project, three of whom are women (including the PI). 100% of publications include female authors. In 2025, nine co-PIs from HPI-funded project identified as female, non-binary, or agender, exceeding the milestone of five. In 2025, nine co-PIs from HPI-funded projects were based in an LMIC. The BCC leadership team is 80% women – with a woman principal investigator. In 2025 76% of academic publications, policy briefs, and blog articles were coauthored by women and 59% by Global South researchers.
Counter-Terrorism	The risk of resources being used to fund terrorism is low. Research is however conducted in areas where terrorist organisations operate. The programme follows UK guidelines on the Counter Terrorism and Security Act 2015 to have due regard to the need to prevent people from being drawn into terrorism. We ensure that all implementing partners are aware of the UK’s policy and funding rules regarding counter terrorist financing, and that FCDO staff check compliance at regular review meetings. FCDO conducted Due Diligence assessments on all top tier delivery partners, which includes a review on partners Anti-terrorism processes, and we ensure that those partners carry out due diligence on their downstream partners.
Safeguarding Considerations	In line with FCDO standards, we applied the following principles in relation to assessing the safeguarding procedures of partners. We expect our partners to apply these principles in their work and through their delivery chains. The safeguarding principles that will underpin all due diligence are as follows: / Everyone has responsibility for safeguarding / Do no harm / Organisations have a safeguarding duty of care to beneficiaries, staff and volunteers, including where down-stream partners are part of delivery / This is also true of children and vulnerable adults in the community who are not direct beneficiaries but may be vulnerable to abuse / Act with integrity, be transparent and accountable / All activity is done in the best interests of the affected person / A child is defined as someone under the age of 18 regardless of the age of majority/consent in country / All affected persons shall be treated equally, irrespective of race, gender, religion/or none, sexual orientation or disability / Organisations that work with children and vulnerable adults should apply a safeguarding lens to their promotional communications and fundraising activities / These principles are aligned with the UN Convention on the Rights of a Child (UNCRC). / All partners have strong policies and robust reporting procedures to escalate potential risks of this nature to the first-tier partner, as well as escalated to FCDO Reporting Concerns so that suitable action can be taken immediately. / BCC is mitigating against the risk of SEAH by ensuring that all partners adhere to the IASC Minimum Operating Standards on PSEA and/or the Core Humanitarian Standard on Quality and Accountability. Further mitigation has been achieved through applied ethics trainings with researchers. At J-PAL, MIT have guidelines on vetting partnerships based on ethical concerns. To ensure that ethical standards are upheld, JPAL have implemented the Research Quality Support process to oversee funded teams. All staff are required to undergo a training on working with human subjects and referrals for psychological support are offered if required. RIAH conduct research with the appropriate ethical clearance led by the UoM University Research Ethics Committees (URECs). The Code of Practice for Investigating Concerns outlines the process followed if allegations of research misconduct are received.
Climate and Environment: / -Paris Alignment / -Environmental Protection / -International Climate Finance (ICF)	In light of the fact that this is a research programme, environment impact will be kept to a minimum, especially with partners favouring regional workshops or online events and having a strong international on-the-ground local presence which mitigates the need for excessive air travel.
Nutrition	N/A for research programme on protection.

Annex 1: Outcome Indicator 1 RIAH
Number of citations in academic/policy publications (Y8 target 40)

Target exceeded: to date in Y8 RIAH products have 116 citations in academic/policy publications.

Scientific journal article citations between Jan 2025 and Feb 2026 are summarised below (111 total):

Violence against healthcare in conflict: a systematic review of the literature and agenda for future research	65
Using Data to Create Change? Interrogating the Role of Data in Ending Attacks on Healthcare	3
Underestimating attacks: comparing two sources of publicly-available data about attacks on health care in 2017	7
‘There is a fear that you will be attacked just for the act of working in health’: a survey of experiences of violence against healthcare in Colombia	1
Caring Under Fire Across Three Continents: The Hadfield-Spears Ambulance, 1941–1945	4
Impacts of attacks to female health care workers in three territories of Colombia	7
Intimacy and the gendering of war healthcare: women’s experiences of insurgency war in Nepal (1996–2006)	1
‘I will take part in the revolution with our people’: a qualitative study of healthcare workers’ experiences of violence and resistance after the 2021 Myanmar coup d’etat	13
‘It’s normal to be afraid’: attacks on healthcare in Ouaka, Haute-Kotto, and Vakaga prefectures of the Central African Republic, 2016–2020	6
Have attacks on healthcare become the new normal? a public health call to action for armed conflicts before it is too late	2
Healthcare under fire: quantifying the impact of violence on medical services in facilities supported by International Medical Corps in three prefectures of Central African Republic, 2016–2020	2
TOTAL:	111

(Note: citation information is not consistently available, so we are unable to add this information for articles published in the journal Humanity.)

Policy Publication citations (5 total):

Product cited	Date	Policy Publication
SHCC Report	24/03/2025	Physician advocacy, international humanitarian law, and the protection of health care workers in conflict zones
Incident Data Myanmar	May 2025	Advocacy materials for Global Health Partnerships
Systematic Review paper	04/07/2025	Violence against healthcare workers in Nepal: a system dynamics perspective on a growing crisis
Multiple	22/07/2025	BMA report: Medicine under attack: the increasing assault on healthcare in conflict zones
SHCC data	15/10/2025	Care amongst the chaos: The voices of nurses working in conflict

Annex 2: Outcome Indicator 2 RIAH
Number of references to project outputs, findings and deliverables in statements or reports by member states, UN agencies, international organisations and NGOs (Y8 target of 7)

Target exceeded: To date project outputs were referenced in the following statements/reports (total 9):

1. In May, for the second-year running, Insecurity Insight data, including data on explosive weapons and attacks on healthcare, was used in the Explosive Weapons Monitor Annual report.
2. In April, for the second year running, Insecurity Insight data on healthcare were used in Watchlist’s ‘A Credible List’ Report that includes Recommendations for the Secretary- General’s 2025 Annual Report on Children and Armed Conflict.
3. In May, for the fourth year running, Insecurity Insight global data on violence against healthcare and the damage caused by explosive weapons was cited by the UN Secretary General’s Report on the Protection of Civilians.
4. In May, for the second year running, Insecurity Insight was used in the data for the UK Health Partnership for Myanmar’s annual report.
5. In June, Insecurity Insight and RIAH contributed evidence to the International Development Committee report: Protection not permission: The UK’s role in upholding international humanitarian law and supporting the safe delivery of humanitarian aid
6. In September, the WHO Health Cluster Coordinator for Myanmar used Insecurity Insight data in their Health Cluster Bulletin.
7. In October, RIAH Insecurity Insight data were used in a British Medical Journal special report: How attacking healthcare has become a strategy of war
8. In December, for the second year running, Insecurity Insight data on healthcare was used in IRC’s 2026 Emergency Watchlist report.
9. In January 2026, MSF’s advocacy report Medical Care in the Crosshairs: The attack on humanity used Insecurity Insight and SHCC datasets.

Annex 3: Outcome Indicator 3 RIAH
Number of engagements/consultations with other organisations that have informed or changed the approach to data collection on attacks on healthcare (Y8 target 3)

Target exceeded: 7 key engagements are listed below.

In May consortium members participated, and SHCC co-sponsored a Protection of Civilians side event: Leveraging New Technologies for the Protection of Healthcare: Advancing Prevention and Accountability. Organised by the permanent missions of Poland and Spain with co-sponsors Denmark, Egypt, Japan, Uruguay, the EU, IRC, PHR, MSF and WHO.

RIAH’s work, in particular the Security Risk Management (SRM) for Health manual, has directly informed the creation of a GISF Community of Practice around the issue. The group convenes regularly and has a working action plan amongst GISF members. Multiple types of NGOs that are interested in delivering guidance on SRM, and it is clear that SRM must be embedded in institutional systems rather than left to individual health workers.

In September and October 2025 RIAH consortium members were consulted as experts to inform a report commissioned by the Dutch government relating to domestic legislation for the protection of aid workers in conflict. The report is expected to be published in Q1 of 2026 and be used in the parliamentary decision-making process.

In November several RIAH members attended a roundtable about IHL and the protection of healthcare, organised at the request of the Danish Mission in NY – elected to a current term on the Security Council (2025-2026). This stock-take meeting was intended to deepen their understanding of key issues related to the protection of the medical mission in armed conflict, in advance of the 10 year anniversary of UN Security Council Resolution 2286. The senior humanitarian policy advisor has since confirmed that this meeting ‘helped our internal thinking and culminated in a strong case to the Danish government’.

As a result of consistent RIAH support to Insecurity Insight and the regular collection of instances data, the WHO requested that RIAH members assist with a preliminary comparison of the WHO Surveillance System on Attacks on Healthcare (SSA) data and Insecurity Insight data, for several countries. The comparison was presented at an internal WHO meeting to discuss the SSA and future plans, given overall restructuring at WHO.

Building on RIAH Consortium member engagement with the 2024 World Innovation Summit on Health (WISH) report focused on protection of healthcare, RIAH and the Qatar-based WISH asked RIAH to co-host a workshop to discuss strengthening data and evidence related to attacks on healthcare. This workshop will extensively feature RIAH data and case study methods, and will convene key Geneva-based and other State and NGO stakeholders focused on protection of healthcare. In addition, WISH and RIAH have secured co-sponsorship for this workshop from the Office of the High Commissioner for Human Rights (OHCHR) and the International Federation of the Red Cross and Red Crescent Societies.

Based on the RIAH ‘mapping report’, funded as part of its uptake and dissemination activities, several RIAH Consortium members have been invited to speak at an the upcoming annual Greentree retreat for all UN SC members and sponsored by the Spanish Mission in NY and the ICRC. The theme for this year is protection of healthcare.

Annex 4: RIAH Peer-Review Journal Articles (previous years greyed out)

Date	Journal	Title
07 May 2021	Conflict and Health	Violence against healthcare in conflict: a systematic review of the literature and agenda for future research | Conflict and Health | Full Text
26 May 2022	International Studies Review	Using Data to Create Change? Interrogating the Role of Data in Ending Attacks on Healthcare | International Studies Review | Oxford Academic
30 January 2023	Conflict and Health	Underestimating attacks: comparing two sources of publicly-available data about attacks on health care in 2017 | Conflict and Health | Full Text
09 April 2023	Social History of Medicine	Caring Under Fire Across Three Continents: The Hadfield-Spears Ambulance, 1941–1945 | Social History of Medicine | Oxford Academic
12 June 2023	Conflict and Health	The crisis of maternal and child health in Afghanistan | Conflict and Health | Full Text
24 October 2023	Conflict and Health	‘There is a fear that you will be attacked just for the act of working in health’: a survey of experiences of violence against healthcare in Colombia | Conflict and Health | Full Text
3 April 2024	Conflict and Health	Impacts of attacks to female health care workers in three territories of Colombia
22 April 2024	Humanity	Project MUSE - ‘Like a Yam Between Two Stones’: Remembering Healthcare at War in Nepal (1996–2006)
22 April 2024	Humanity	Project MUSE - Introduction: History Writing and Attacks on Healthcare
12 July 2024	International Feminist Journal of Politics	Intimacy and the gendering of war healthcare: women’s experiences of insurgency war in Nepal (1996–2006)
20 August 2024	Conflict and Health	‘I will take part in the revolution with our people’: a qualitative study of healthcare workers’ experiences of violence and resistance after the 2021 Myanmar coup d’etat
27 August 2024	Conflict and Health	‘It's normal to be afraid’: attacks on healthcare in Ouaka, Haute-Kotto, and Vakaga prefectures of the Central African Republic, 2016–2020
5 August 2025	Conflict and Health	Healthcare under fire: quantifying the impact of violence on medical services in facilities supported by International Medical Corps in three prefectures of Central African Republic, 2016–2020 | Conflict and Health | Springer Nature Link

Annex 5: RIAH Other Publications (previous years greyed out)

Title	Document Type	Publication Date	URL
Impact Methods Meeting Summary	Thematic Summary	13 February 2020	2019-Panels-Summary-for-Website.pdf
Health workers at risk: Violence against health care	Report	2020	SHCC2020final.pdf
Conceptual issues and methodological approaches to evaluating the wider and longer-term impact of attack on healthcare in conflict	Working Paper	December 2020	Impact-Methods-Working-Paper-min-1.pdf
Case Study: Exploratory Analysis of Publicly Available Data on Attacks on Health in Colombia	Case Study	22 April 2021	RIAH-Columbia-Online-Surveillance-WebCopy.pdf
No Respite: Violence Against Healthcare in Conflict	Report	2021	SHCC 2021 Report No respite Violence against health care in conflict.pdf
Afghanistan Interview Guides	Protocol	2021	Afghanistan Interview Guides – RIAH – Researching the Impact of Attacks on Healthcare
Unrelenting Violence: Violence Against Healthcare in Conflict	Report	2022	SHCC%202021%20Unrelenting%20Violence2%20FINAL.pdf
Accounting for gender when it is not counted Highlighting the importance of sex-disaggregated data in understanding the impacts of attacks on healthcare	Briefing	February 2022	HCRI_Policy_Brief_Gender-_25.02.22.pdf
Gendered health impacts of civil war in Nepal	Briefing	January 2023	RIAH-Policy-Brief-Nepal-gender-Jan-2023-FINAL.pdf
What do we Learn from the History of Attacks on Healthcare?	Briefing	May 2023	Research-Brief-05.23-What-do-we-learn.pdf
Ignoring Red Lines: Violence Against Healthcare in Conflict	Report	2023	SHCC-Report-Ignoring-Red-Lines.pdf
Have attacks on healthcare become the new normal? a public health call to action for armed conflicts before it is too late	Discussion Paper	6 December 2023	Have attacks on healthcare become the new normal? a public health call to action for armed conflicts before it is too late | Conflict and Health | Full Text
The impact of violence against health care on the health of children and mothers a case study in three health zones in Eastern DRC	Case Study	April 2024	ERSP UCB RIAH IRC - ATTACKS AGAINST HEALTHCARE DRC.pdf
Critical Condition: Violence Against Healthcare in Conflict	Report	2024	2023-SHCC-Critical-Conditions.pdf
Security Risk Management for Health Care Handbook	Handbook	2024	Security Risk Management for Health Care Security Risk Management for Health Care Security Risk Management for Health Care - Insecurity Insight
HUMVI: A Multilingual Dataset for Detecting Violent Incidents Impacting Humanitarian Aid	Article	15 October 2024	2410.06370
What works and who knows? The importance of community and health worker perspectives in defining solutions to attacks on healthcare	Comment	24 July 2025	What works and who knows? The importance of community and health worker perspectives in defining solutions to attacks on healthcare
Normative States: Successes, Failures, and Lessons for Protection of Healthcare	Paper	April 2025	RIAH-Normative-States-FINAL-photo-credit-amended-4.pdf

Annex 6: RIAH Media Mentions (see Excel spreadsheet)

Annex 7: HPI Funded Projects (all three rounds – previous years greyed out)

Full RCTs
1. Growing Stronger Together: A Family Strengthening Approach to Reduce Child Engagement with Armed Forces in Central African Republic - Amber Peterman (University of North Carolina at Chapel Hill, UNC), Kathryn Falb (Johns Hopkins Bloomberg School of Public Health), Yvonne Agengo (IRC), Camille Fabbri (London School of Hygiene and Tropical Medicine), Clement Bicaba (IRC); with the International Rescue Committee (IRC). This study aims to reduce child engagement in armed forces through an innovative approach that combines curriculum- and group-based effective parenting programming with tailored support for families who have had children engaged in or at risk of recruitment into armed groups.
2. The Value of Landmine Awareness Programs in Conflict Settings: Evidence from Myanmar - Travis Baseler (University of Rochester), Sutirtha Sinha Roy (World Bank), Roy Van der Weide (World Bank). The study is testing whether targeted educational interventions can, in addition to reducing landmine-related accidents, also improve livelihoods by improving mobility.
3. Civilian Protection by Direct Combatant Interventions: What works and what Doesn’t? A Field Experiment leveraging combatant incentives through IHL training and combatant empathy through perspective taking - Raul Sanchez (University of Chicago), Lewis Dunia Butinda (UC Berkeley), Hilary Yu (UC Berkeley). The project aims to answer the following questions: Does training in IHL among combatants protect civilians? Is its effect amplified by a values-based intervention? Can perspective-taking, designed to promote empathy, reduce civilian abuse?
4. Caregiver Mental Health and Early Childhood Development in Conflict-Affected Settings: At- Scale Experimental Evidence from Colombia - Andres Moya (Universidad de Los Andes), Bilge Erten (Northeastern University), Pinar Keskin (Wellesley College), Camila Galindo (Universidad de los Andes). This project evaluates the scale-up of Semillas de Apego, a community-based psychosocial program designed to restore caregiver mental health and protect early childhood development in conflict-affected and displaced communities.
5. Fostering economic and psychosocial resilience among conflict-affected women to tackle GBV in Somalia - Julia Smith-Omomo (IOM), Kathryn Falb (Johns Hopkins University), Julia Smith-Omomo, Theresa Maclay (IOM), Balint Nemeth (IOM). The study aims to answer the following questions: the following questions: Can simultaneous investments in livelihoods and MHPSS improve resilience while reducing the risks of GBV among displacement-affected women? Can such interventions be effectively delivered by trained and supervised lay personnel under a task-shifting model?
6. Advancing Screening for and Access to Mental Health Services in Eastern Democratic Republic of Congo - Peter Van der Windt (New York University), Andres Moya (Universidad de Los Andes), Lelys Dinarte-Diaz (World Bank), Igor Asanov (University of Kassel), Emmanuel Kandate (Director of RISD), Toan Do (World Bank). This study assesses the potential transformative role of digital tools for screening and delivering mental health services in conflict-affected regions.
Pilot Studies
1. Sextortion and entrepreneurship in Burkina Faso - Oana Borcan (University of East Anglia); Doris Aja-Eke (Dublin City University, DCU); Robert Gillanders (Dublin City University, DCU); W. H. Eugenie Maiga (Université Norbert Zongo, Burkina Faso), with IPA and Empow’Her. This pilot study of interventions to prevent sexual exploitation of female entrepreneurs in Burkina Faso. This pilot study investigates if a training and peer support intervention for IDP women entrepreneurs in Burkina Faso can protect women against sextortion, which is particularly prevalent in business registration and financing offices.
2. Layperson first responder trainings to improve trauma care for civilian casualties of explosive violence in Burkina Faso - Nicolas Meda (Co-PI, Government of Burkina Faso / Université Joseph Ki-Zerbo); Hannah Wild (University of Washington) Moumini Niaone; with the Mines Advisory Group. This pilot project seeks to improve laypersons’ ability to respond to physical trauma of civilian victims in the immediate aftermath of mine explosions and enhance coordination between the UN Humanitarian Cluster System’s Health and Protection Clusters to reduce preventable deaths and injuries in armed conflict zones.
3. YY Enhancing Resilience and Agency through Remote Education for Afghan Girls: A Pilot in Providing Foundational Numeracy and Literacy - Michael Callen (LSE), Oeindrila Dube (University of Chicago), Noam Angrist (What Works Hub - University of Oxford). The study assesses whether interactions with peers and teachers enhance social inclusion and well-being. They also aim to test for impacts on spillovers on learning and empowerment outcomes of siblings, as well as long-run impacts.
4. YY Preventing Sexual Violence through Training: A Pilot Study in Colombia’s Military Academies - Michael Weintrub (Universidad de los Andes). The project investigates how preventative education may reduce sexual violence in conflict zones. The pilot phase will refine the intervention, develop and test survey instruments, and collect qualitative data at a single training academy to prepare for randomisation and scale-up.
5. YY The adaptation of a remote preschool program for use in active conflict contexts - Florencia Lopez Boo (New York University), Kate Schwartz (New York University), Pedro Carneiro (University College London). The specific aims of this pilot are to understand: 1) interest in the program; 2) the validity and reliability of a remotely adapted child development measure; and 3) barriers to and facilitators of successful implementation.
6. YY Digital Education Tools in Crisis Environments - Hila-Nawa Alam (Uplift Afghanistan), Dana Burde (NYU), Cyrus Samii (NYU), Heddy Lahmann (NYU). This study aims to assess the feasibility as well as potential benefits and limitations of two innovative educational technologies—Ideas Cube and Kajou Cards—distributed by Bibliothèques Sans Frontières (BSF) for children aged 6 to 12 in Afghanistan.
7. YY Online Ambulance – Empowering Women and Girls Against Technologically-Facilitated Gender-Based Violence (TFGBV) in Myanmar - Sajai Liangpunsakul (Stop Online Harm), Alexandra Hartman (UCL). The pilot assesses which Online Ambulance services—such as digital safety support and psychosocial support can be scaled and rigorously evaluated, and the modalities for measuring impact.
8. YY Monitoring for Protection: Reducing Workplace Sexual Violence Against Sudanese Refugees in Egypt - Suzanna Khalifa (Sciences Po), Laura Munoz Blanco (University of Exeter), Karmini Sharma (Imperial College). Sudanese refugees in Egypt—particularly women—are highly vulnerable. Many are employed informally in domestic work, where they are isolated, face little to no labor protections, and are often subject to exploitation. The study evaluates whether third-party monitoring can reduce sexual violence at work.
Exploratory studies
1. Fostering peaceful behaviours among farmers and herders: Impacts of community-driven initiatives and edutainment (Nigeria). This project, aimed at fostering peaceful behaviours among farmers and herders through community-driven initiatives and edutainment, directly addresses this policy issue by promoting conflict resolution and enhancing social cohesion.
2. The impacts of safe spaces on network creation and gender-based violence among conflict-affected displaced women (Egypt). This project aims to evaluate how social network interventions in safe spaces can protect displaced women from gender-based violence (GBV) and mitigate its psychological and socioeconomic impacts.
3. Safe Spaces and Internal Displaced Women’s and Girls' Wellbeing (Burkina Faso): The project aims to address GBV issues in conflict-affected areas of Burkina Faso by implementing two interventions: the creation of safe spaces offering support, awareness, and empowerment activities for displaced women and girls, and a home-based outreach programme to engage the broader community in GBV prevention and response efforts.
4. Improving Adolescent Outcomes in Conflict Settings (Ethiopia). The proposed pilot research lays the groundwork for a rigorous randomised evaluation of timely and policy-informed multi-level, multi-faceted programming aimed at the reduction of GBV and support for GBV survivors in conflict-affected settings in Ethiopia. The eventual full evaluation will fill existing evidence gaps on the effectiveness of combinations of policies shown to work in other settings but not proven in regions affected by conflict.
5. Explaining and Preventing Environmental Conflict in the Amazon (Brazil). This project aims to generate rigorous empirical evidence on the rising but understudied violence against land and environmental defenders while evaluating mechanisms to protect remote, vulnerable communities from harm. By addressing gaps in data and understanding, it seeks to inform more effective prevention and protection strategies.
6. Violence and Mental Health of Women in Internally Displaced Camps: Experimental Evidence from Nigeria - Emeka Eze (Michael Okpara University of Agriculture, Umudike), Eleanya Nduka (University of Warwick). This study aims to answer the following questions: Does access to mental health counseling services in IDP camps improve the mental health of women who have experienced violence? Does access to mental health counseling services help to integrate these women back into society?
7. Engaging internally displaced women in Nigeria in smart agriculture to minimise vulnerability to sex and gender based violence - Joseph Amuka (University of Nigeria, Nsukka), Ambrose Omoje (University of Nigeria, Nsukka). The objective of this study is to examine if training the women in IDP camps in smart agricultural practice will minimise their vulnerability to these sex and gender based violence, as they will be able to have a source of income to buy some of their family's needs while in the IDP camps.

Annex 8: J-PAL Publications (previous years greyed out)

Date	Publication Type	Title	Country	J-PAL/IPA Website link
13/02/2024	Blog	New Humanitarian Protection Initiative Will Help Reduce Harm to People Affected by Conflict	Global	https://poverty-action.org/new-humanitarian-protection-initiative-will-help-reduce-harm-people-affected-conflict
15/07/2024	Policy Brief	Preventing Individual-Level Violence in Conflict Settings	Global	https://poverty-action.org/sites/default/files/2024-07/Humanitarian-Protection%20Policy-Brief%231%20%283%29.pdf
14/02/2024	Policy Publication	Request for Proposal Document	Global	https://www.povertyactionlab.org/sites/default/files/HPI_RFP%201_Feb2024.pdf
19/12/2024	Blog	In conversation with Norwegian Church Aid: Understanding the catalyzing effect of J-PAL humanitarian trainings	Global	https://www.povertyactionlab.org/blog/12-19-24/conversation-norwegian-church-aid-understanding-catalyzing-effect-j-pal-humanitarian?lang=fr
3/26/2025	Blog	Preventing Violence Against Women and Girls: What we’ve learned in the 30 years since the Beijing Declaration	Global	https://poverty-action.org/preventing-violence-against-women-and-girls-what-weve-learned-30-years-beijing-declaration
6/12/2025	Blog	Driving Innovation amidst Crisis: The Humanitarian Action and Displacement Response Research Incubator in Asia	Global	https://poverty-action.org/driving-innovation-amidst-crisis-humanitarian-action-and-displacement-response-research-incubator
7/1/2025	Policy publication, blog	The Evidence Effect: Evidence for action in conflict and crisis	Global	https://www.povertyactionlab.org/blog/7-21-25/evidence-effect-evidence-action-conflict-and-crisis
7/1/2025	Policy publications	From bias to belonging through perspective-taking	Global	https://www.povertyactionlab.org/evidence-effect/bias-to-belonging-through-perspective-taking

Annex 9: Beyond Compliance Outcome Indicator 1 for 2025
Cumulative number of citations of project outputs in relevant high-level scholarly outputs, inter-, non-and governmental reports, policy papers or project documents.

Target exceeded: to date BCC products have 18 citations in academic/policy publications (target of 7), with 15 occurring this year. This year’s citations, listed in chronological order:

Citation in ABILA International Law Weekend Panel Blog Reflection by audience member (January 2025), https://www.ila-americanbranch.org/ilw24-panel-reflection-beyond-compliance-reflections-on-a-protective-environment/
Citation in Humanitarian Evidence and Discourse Summary (January 2025), https://opendocs.ids.ac.uk/articles/report/K4DD_Humanitarian_Evidence_and_Discourse_Summary_June_2025/29476400?file=55980161
Extensive references to BCC work in House of Commons, International Development Committee, Protection not permission: The UK’s role in upholding international humanitarian law and supporting the safe delivery of humanitarian aid, Fifth Report of Session 2024–25, HC 526 (June 2025), https://committees.parliament.uk/publications/48324/documents/252895/default/
Citation in Humanitarian Evidence and Discourse Summary (June 2025), https://opendocs.ids.ac.uk/articles/report/K4DD_Humanitarian_Evidence_and_Discourse_Summary_June_2025/29476400?file=55980161
Citation of the BCC conceptualisation in academic article by Andrew Clapham 'Liability for killing in war and why there is no “licence to kill”’ in Netherlands Quarterly of Human Rights (July 2025), https://journals.sagepub.com/doi/10.1177/09240519251363038
Reference to the BCC by Dr. Alessandra Spadaro, ‘All Wars Matter? On a Different Way for International Lawyers to Engage with Armed Conflicts’, in Opinio Juris (July 2025), https://opiniojuris.org/2025/07/11/all-wars-matter-on-a-different-way-for-international-lawyers-to-engage-with-armed-conflicts/
Citation of BCC blog article on mental harm in academic article by Giulia Bosi ‘The Protection of Mental Health under International Humanitarian Law’ in Journal of International Humanitarian Legal Studies (August  2025), https://brill.com/view/journals/ihls/aop/article-10.1163-18781527-bja10121/article-10.1163-18781527-bja10121.xml
Citation of several Beyond Compliance: In Conversation podcast episodes in Creating Safer Spaces project news item (August 2025), https://creating-safer-space.com/css-researchers-in-podcast-on-civilian-agency-armed-groups-and-international-law/
Citation of BCC conceptualisation in academic article by Katharine Fortin ‘Classifying the Armed Conflict in Gaza’ in Revue belge de droit international (September 2025) https://research-portal.uu.nl/ws/files/276498635/Scanned_Fortin_Classifying_the_armed_conflict_in_Gaza.pdf
Citation of two Beyond Compliance: In Conversation podcast episodes in The Netherlands Institute of Human Rights Newsletter, Summer 2025 Issue, https://mailings.uu.nl/i/82tFHvES1hET4JEe8h1bJwm67_ODCPUYOXHC4i-OO_wBaRJUMe7fqw
Citation of two Beyond Compliance: In Conversation podcast episodes, Fall 2025 Issue, https://mailings.uu.nl/i/nCIEb8qx0u7709U4Zx03dLtoStnhayyFJTJ1M0S8ES5uERTCBQ8XhQ
BCC citation in article by Thomas Evans, ‘Goodbye is the hardest part: why is ending violence so difficult for non-state armed groups?’ in Humanitarian Law and Policy, the ICRC blog (October 2025), https://blogs.icrc.org/law-and-policy/2025/10/09/goodbye-is-the-hardest-part-why-is-ending-violence-so-difficult-for-non-state-armed-groups/
BCC citation in article by Manuel Galvis and Marko Milanovic, ‘Improving Fact-Finding for IHL and Harnessing Modern Technology’ in in EJILTalk, the European Journal of International Law blog (October 2025), https://www.ejiltalk.org/improving-fact-finding-for-ihl-and-harnessing-modern-technology/
Citation of BCC empirical findings in article by Lauren Spink ‘Drones are Changing How Wars Harm Civilians’, in Just Security (November 2025), https://www.justsecurity.org/123474/drones-are-changing-how-wars-harm-civilians/
BCC citation in Humanitarian Evidence and Discourse Summary (December 2025), https://opendocs.ids.ac.uk/articles/report/K4DD_Humanitarian_Evidence_and_Discourse_Summary_December_2025/31099780?file=61224460

Annex 10: BCC Progress Story: The IHL Centre’s Stockholm Manual

Problem
Humanitarian practitioners often need to judge whether observed civilian harm reflects breaches of international humanitarian law (IHL), but many are not legal specialists. Practice can swing between over-claiming violations (undermining credibility) or avoiding legal assessment altogether (weakening protection advocacy).

Research
Through co-produced, socio-legal research and sustained reflective engagement with consortium members, including the International Humanitarian Law Centre (IHL Centre), BCC developed the ‘Beyond Compliance “harm + need” conceptual framing. A key insight of this approach is to move away from the standard legal doctrinal approach, which ignores harm that is not fully captured by rules and assumes that all harm is most effectively addressed through legal compliance. Instead, this approach starts from the empirical reality of the types of harm civilians experience and practitioners observe, and maps this onto legal rules and extra-legal strategies.

Use
The IHL Centre implemented aspects of this framing in their design of the Stockholm Manual, organising practitioner guidance on IHL assessments and advocacy around categories of civilian harm rather than legal provisions, to help non-specialists move from observation → assessment → advocacy. This has potential to improve the quality and consistency of humanitarian advocacy. The IHL Centre reports the Manual is being used by Oxfam and local partners in Ukraine, and by Insecurity Insight to inform data collection.

Result: change in the world so far
At the date of this review, a nascent path to wider conceptual and instrumental impact can be seen. The influence of the BCC ‘harm + need’ approach within the consortium itself can be seen clearly with the implementation of the approach in the IHL Centre’s Stockholm Manual, discussed here. Downstream conceptual and instrumental impact from the Manual, external to the consortium, is emergent and it is plausible that BCC’s conceptual framing may have a significant impact in the wider sector in future, subsequently contributing to improved advocacy effectiveness that leads to changes in direction, policy or practice. We will continue to follow BCC’s progress with this.

Annex 11: Beyond Compliance Research Outputs (previous years greyed out)
Blog Symposium: How to prevent harm and need in conflict

Date	Title	Author
18 December 2025	‘Child Soldiers’ Recruitment in the Democratic Republic of Congo – Harm and Obstacles to Breaking Intergenerational Norms’ Available online	Zawadi Gasindikira Jael
4 December 2025	‘Harm by Overcompliance to Unilateral Sanctions - The Paradigm of Syria’ Available online	Mohammad Kanfash
17 November 2025	‘Armed Groups without Armed Conflict - Reflecting on the Thresholds of Violence and Protection’ Available online	Ezequiel Heffes
16 October 2025	‘How Conflict and Climate Change Deepen Child Malnutrition in Sub-Saharan Africa’ Available online	Oche Joseph Otorkpa
23 September 2025	‘Before compliance – ex-ante decision making in the design of military AI capabilities and the need to unravel the private technology sector’s role’ Available online	Yiokasti Mouratidi
31 July 2025	‘Sanctions and Silence - Intergenerational Trauma and Legal Gaps’ Available online	Konstantina Karagkouni
15 July 2025	‘Between Aftershocks & Airstrikes in Myanmar - Accounts of Compounding Harm + Need’ Available online	Lway Mownt Noon, Samantha Holmes, Chris Rush and Florian Weigand
8 July 2025	‘Widening the legal lens from within IHL and beyond: ‘Special or ad hoc agreements’ as an expandable resource for restraint’ Available online	Aristide Evouna Evouna
19 June 2025	‘Recommitting to Compliance and Restraint to Reverse the Unprecedented Trends of Harm and Need Experienced by Children in Armed Conflict’ Available online	Bethany Ellis and Patrick Kumi
5 June 2025	‘What is needed to reduce the risk of violence faced by communities during armed conflict’ Available online	Gemma Davies, Leigh Mayhew
29 April 2025	‘Legal Frameworks by Non-State Armed Groups in Syria – Drivers or Constraints of Harm to Children?’ Available online	Anki Sjöberg and Yousef Wehbe
8 April 2025	‘Beyond the State- The Role of Armed and Political Movements in Implementing the Women, Peace, and Security Framework in Yemen’ Available online	Anki Sjöberg, Wameedh Shakir, Yousef Wehbe, and Véronique Dudouet
30 January 2025	‘Extracting Lessons from the Russia-Ukraine War to Improve Civilian Protection’, Beyond Compliance Symposium, Articles of War. Available online.	Lauren Spink
28 January 2025	‘Investigating Civilian Harm in an Era of Western Remote Warfare’, Beyond Compliance Symposium, AGIL. Available online.	Lauren Gould
21 January 2025	‘Broadening the Lens: Rethinking Civilian Harm within International Humanitarian Law’, Beyond Compliance Symposium, Articles of War. Available online.	Stephen Wilkinson, Yvette Issar, Emilie Fitzsimons, Matias Thomsen, and Alice Priddy
19 December 2024	‘The UN Children and Armed Conflict agenda as an accountability mechanism’, Beyond Compliance Symposium, AGIL. Available online.	Rocco Blume and Samantha Holmes
17 December 2024	‘Providing a Framework for NATO’s Human Security Approach’, Beyond Compliance Symposium, Articles of War. Available online.	Alexander Gilder and Daniel Linsdell
10 December 2024	Research Consultations with Non-State Armed Groups’, Beyond Compliance Symposium, AGIL. Available online.	Pascal Bongard and Anki Sjoeberg
5 December 2024	‘Quantifying Compliance: Challenges of Measuring Compliance with International Humanitarian Law’, Beyond Compliance Symposium, Articles of War. Available online.	Christoph Dworschak and Hyunjung Park
26 November 2024	‘Recognising and Addressing Harm to Children Caused by Explosive Weapons’, Beyond Compliance Symposium, AGIL. Available online.	Bethany Ellis
19 November 2024	‘Towards the full protection of civilians’, Beyond Compliance Symposium, Articles of War. Available online.	Simon Bagshaw
12 November 2024	‘Buddhism's Psycho-ethics of Non-Harm and Restraint for All Sentient Beings During Armed Conflict’, Beyond Compliance Symposium, AGIL. Available online.	Andrew Bartles-Smith
5 November 2024	‘The Harm Mitigation Holarchy: Human Security, Protection of Civilians, and Civilian Harm Mitigation and Response’, Beyond Compliance Symposium, Articles of War. Available online.	Dan E. Stigall
29 October 2024	‘Security beyond the physical – Addressing the Nasa Indigenous people’s spiritual harm in armed conflict’, Beyond Compliance Symposium, AGIL. Available online.	Piergiuseppe Parisi
22 October 2024	‘Systemic impacts of war in protracted conflicts’, Beyond Compliance Symposium, Articles of War. Available online.	Joshua Joseph Niyo
15 October 2024	‘Beyond Compliance Symposium: War is not skin deep – International Humanitarian Law and mental health’, Beyond Compliance Symposium, AGIL. Available online.	Samantha Holmes
10 October 2024	‘Armed Groups, Compliance and International Law: There is more than meets the eye’, Beyond Compliance Symposium, AGIL. Available online.	Ezequiel Heffes
3 October 2024	‘A rights-based approach to addressing harm and need in armed conflict?’, Beyond Compliance Symposium, Articles of War. Available online.	Rocco Blume
3 October 2024	‘Practical Measures to Prevent and Mitigate Conflict-induced Food Insecurity’, Beyond Compliance Symposium, AGIL. Available online.	Katherine Kramer
2 October 2024	‘Redressing Civilian Harm and Going Beyond International Humanitarian Law Compliance’, Beyond Compliance Symposium, Articles of War. Available online.	Luke Moffett
26 September 2024	‘Strategies for reducing harm and need in war through a decolonial and intersectional lens’, Beyond Compliance Symposium, AGIL. Available online.	Samantha Holmes
25 September 2024	‘Why armed actors should pay more attention to civilian self-protection efforts’, Beyond Compliance Symposium, Articles of War. Available online.	Marc Linning
24 September 2024	‘Beyond typologies of actors: ambiguous boundaries in non-international armed conflicts’, Beyond Compliance Symposium, AGIL. Available online.	Anastasia Shesterinina
18 September 2024	‘Compliance + Restraint Towards Full(er) Protection in War’, Beyond Compliance Symposium, Articles of War. Available online.	Ioana Cismas and Anastasia Shesterinina
18 September 2024	‘What’s in a Frame? Understanding Everyday Lived Experiences of Armed Conflict Through a Lens of ‘harm + need’’, Beyond Compliance Symposium, AGIL. Available online.	Katharine Fortin and Rebecca Sutton
17 September 2024	‘Why and How to Go ‘Beyond the Law’ to Address Negative Lived Experiences of Armed Conflict’, Beyond Compliance Symposium, Articles of War and AGIL. Available online.	Katharine Fortin, Ezequiel Heffes, Ioana Cismas and Jennifer Maddocks

Academic articles

Date	Title & Journal	Author
February 2026	‘The Beyond Compliance Approach: Centring Harm + Need Towards Full(er) Protection in Armed Conflict’, Columbia Journal of Transnational Law, Volume 64, pp.	Ioana Cismas, Katharine Fortin, Rebecca Sutton, Ezequiel Heffes and Anastasia Shesterinina
Accepted for publication, Forthcoming July 2026	‘Reconciling proportionality in attack with a decolonial approach to mental harm’ Submitted to the International Review of the Red Cross	Samantha Holmes
Submitted	‘Social Infrastructures of Protection: Civilian Protective Agency and Community‑Led Harm Reduction in Somalia’ – submitted and discussed at the workshop ‘Gender, Peace and Security: Resistance and Resilience’, Nairobi, December 2025, to be included in edited book by the same name (publication date TBC).	Rahma Abikar and Ashley Jackson

Policy documents

Date	Title	Author
15 December 2025	‘Accountability for everyday harm + need and grave human rights violations in Myanmar’, Written submission for the UN Special Rapporteur on Myanmar on accountability	Authored by Samantha Holmes with input from Lway Mownt Noon, Ioana Cismas, Florian Weigand and Chris Rush
12 February 2025	‘Strengthening compliance with international humanitarian law and improving humanitarian access - Building evidence and strategies for action and change’. Submission to the UK Parliament’s International Development Committee in response to the inquiry on ‘Humanitarian access and adherence to international humanitarian law’ Available online	Ioana Cismas, Katharine Fortin, Emilie Fitzsimons, Ezequiel Heffes, Stephen Wilkinson, Rocco Blume and Rebecca Sutton

Beyond Compliance Paper Series & Symposium Booklet
Date	Title & Publication	Author
November 2025	Data Brief: Mapping Trends on Harm + Need in Myanmar - Beyond Compliance Paper Series, issue no. 2.	Christoph Dworschak, Hyunjung Park, Rob Grace and Konstantina Karagkouni
October 2025	The What, Who and How of Compliance and Restraint by Non-State Armed Groups - Beyond Compliance Paper Series, issue no. 1	Anastasia Shesterinina, Ezequiel Heffes, Anki Sjöberg and Konstantina Karagkouni
March 2025	Beyond Compliance Symposium – How to prevent harm and need in conflict, Booklet. Available online / A selection of blog articles from the booklet have been translated into Spanish and Arabic	Curated by Samantha Holmes and co-edited with Konstantina Karagkouni

Podcasts

Date	Title	Speakers
8 January 2026 (released deliberately after holiday period for traction)	Beyond Compliance: In Conversation Podcast: Season 2 Episode 2 ‘Famines & Starvation’ Available online	Hosts: Katharine Fortin, Florian Weigand, / Speakers: Alex de Waal (World Peace Foundation and Fletcher School, Tufts University) and Yousuf Syed Khan (Legal Action Worldwide - LAW in Geneva, Atlantic Council’s Strategic Litigation Project, International Centre for Counter-Terrorism, The Hague)
18 November 2025	Beyond Compliance: In Conversation Podcast: Season 2 Episode 1: Civilian Protection & the Legacies of the War in Afghanistan Available online	Hosts: Katharine Fortin, Florian Weigand / Speakers: Sharhazad Akbar (Rawadari Organisation, former Chair of the Afghanistan Independent Human Rights Commission, and Honorary Fellow at Wolfson College, University of Oxford) and Thomas Gregory (University of Auckland, New Zealand)
14 July 2025	Beyond Compliance: In Conversation Podcast Series 1: Episode 12 ‘Civilian Agency in the Digital Realm’ Available online	Hosts: Katharine and Florian Weigand / Speakers: Oona A. Hathaway (Yale Law School, Yale University Department of Political Science, Faculty at the Jackson School of Global Affairs, Yale Law School Center for Global Legal Challenges) and Taras Fedirko (School of Social and Political Sciences, University of Glasgow, Institute for Human Sciences in Vienna)
17 June 2025	Beyond Compliance: In Conversation Podcast Series 1: Episode 11 ‘Civilian Self-Protection and Land’ Available online	Hosts: Katharine Fortin and Florian Weigand / Speakers: Marwan Darweish (Center for Peace and Security at Coventry University, UK) and Piergiuseppe Parisi (Centre for Applied Human Rights and the York Law School, University of York, UK)
26 May 2025	Beyond Compliance: In Conversation Podcast Series 1: Episode 10: ‘Strengthening Civilian Protection’ Available online	Hosts: Katharine Fortin and Florian Weigand / Speakers: Rev Peter Tibi (Imatong Bible College in Juba, Sudan, and RECONCILE, International), Leigh Mayhew (ODI’s Global Risks and Resilience programme, The Centre on Armed Groups) )and Gemma Davies (Humanitarian Policy Group at ODI)
3 April 2025	Beyond Compliance: In Conversation Podcast Series 1 Episode 9: ‘Gender & Civilian Agency’ Available online	Hosts: Katharine Fortin and Florian Weigand / Speakers: Shalaka Thakur (Danish Institute for International Studies-DIIS) and Helen Kinsella (University of Minnesota, Twin Cities, Department of Gender, Women & Sexuality Studies, the Hubert H. Humphrey School of Public Affairs, the Human Rights Center at the Law School, and the Interdisciplinary Center for the Study of Global Change and at the Senator George J. Mitchell Institute for Global Peace, Security and Justice, Queens University, Belfast, Northern Ireland )
6 February 2025	Beyond Compliance: In Conversation Podcast Series 1: Episode 8 ‘Peacebuilding from Below’. Available online.	Hosts: Katharine Fortin and Florian Weigand / Guests: Dr. Véronique Dudouet (Berghof Foundation, Berlin, Germany) and Urko Aiartza Azurtza (member of the Gipuzkoa Bar, Co-President of the European Lawyers Association for Democracy and World Human Rights, and OCHA’s Humanitarian Negotiation Unit and Centre on Armed Groups).
29 November 2024	Beyond Compliance: In Conversation Podcast Series 1: Episode 7 ‘Victimhood & Everyday Peace’. Available online.	Hosts: Katharine Fortin and Florian Weigand / Guest: Kieran McEvoy (the Senator George J. Mitchell Chair of Peace, Security and Justice and Leverhulme Major Research Fellow) and Roger Mac Ginty (School of Government and International Affairs and the Durham Global Security Institute, Durham University).
15 November 2024	Beyond Compliance: In Conversation Podcast Series 1: Episode 6 ‘Armed Groups and Counter-Terrorism’. Available online.	Hosts: Katharine Fortin and Florian Weigand / Guests: Sophie Haspeslagh (Department of War Studies at King’s College London) and Gloria Gaggioli (Geneva Academy, Law Faculty of the University of Geneva)
1 November 2024	Beyond Compliance: In Conversation Podcast Series 1: Episode 5 ‘Decision Making in Armed Conflict’. Available online.	Hosts: Katharine Fortin and Florian Weigand / Guests: Mara Revkin (Duke University, and the Democracy, Conflict and Governance Program at the Carnegie ) and Justin Schon (the Migration Analysis Center within the Office of Homeland Security Statistics at the Department of Homeland Security)
18 October 2024	Beyond Compliance: In Conversation Podcast Series 1: Episode 4 ‘Negotiating with Armed Actors’. Available online.	Hosts: Katharine Fortin and Florian Weigand / Guests: Riyad Anwar (the Centre for Advocacy and Legal Consultation at the University of Hasanuddin), Ashley Jackson (Centre on Armed Groups) and Abellia Anggi Wardani (Faculty of Humanities, Universitas Indonesia, Indonesia and Exploring Community Perceptions and Coping Strategies on Violence in Rakhine State – Myanmar)
4 October 2024	Beyond Compliance: In Conversation Podcast Series 1: Episode 3 ‘Mexico – Civilian Agency Outside of War Zones’. Available online.	Hosts: Katharine Fortin and Florian Weigand / Guests: Anjan Sundaram (independent author, journalist, academic and activist) and Chiara Redaelli (Diakonia IHL and Catholic University of Lille Lille University and La Saban University in Colombia).
20 September 2024	Beyond Compliance: In Conversation Podcast Series 1: Episode 2 ‘Civilian Agency in Violent Settings’. Available online.	Hosts: Katharine Fortin and Florian Weigand / Guests: Emily Paddon Rhoads (Swarthmore College) and Juan Masullo (the Institute of Political Science, Leiden University)
9 September 2024	Beyond Compliance: In Conversation Podcast Series 1: Episode 1 ‘Engaging Armed Groups’. Available online.	Hosts: Katharine Fortin and Florian Weigand / Guests: Matthew Bamber-Zryd (ICRC’s Adviser on Armed Groups, based in the Geneva headquarters) and Dr Tilman Rodenhäuser (thematic legal adviser at the International Committee of the Red Cross’ headquarters in Geneva, Switzerland)

Annex 12: Number of engagements with humanitarian, human rights, peacebuilding, development actors through events and other public engagement opportunities that facilitate dissemination of BCC research

1x BCC Public roundtable: ‘Harm + Need in Armed Conflict: What to Expect from Law, Policy and Practice in 2025?’.  With the participation of Advisory Board members: Andrew Bartles-Smith (Independent consultant, formerly with the ICRC), Emiliano Buis (University of Buenos Aires), Gemma Davies, (Humanitarian Policy Group at ODI), Helen Kinsella (University of Minnesota), Shelly Whitman (Dallaire Institute for Children, Peace and Security). Introductory remarks by Ioana Cismas (University of York) and moderation by Katharine Fortin (Utrecht University).
1 x Submission of evidence to the UK Parliament’s International Development Committee in response to the inquiry on ‘Humanitarian access and adherence to international humanitarian law’ (Feb. 2025).
1 x Attendance at FCDO Conflict Conference + Market Place presentation (March 2025).
1x OCHA-led Protection of Civilians Working Group presentation of the harm + need approach towards fuller protection (Feb 2025).
1x South Sudan CRU meeting with GREDO with regards to data collection in Pibor and Akobo (Feb 2025).
1 x Watchlist Annual Policy Workshop, New York (Jan 2025).
1 x BCC attendance at Protection of Civilians Week, New York (May 2025).
1 x Meeting with Danish Refugee Council (June 2025).
1 x Meeting with the Permanent Mission of Germany in New York: Introducing BCC concept and blog symposium (June 2025).
1x Series of meetings with Geneva-based child rights partners: Introducing BCC concept and preparation for Geneva CAAC Policy Workshop Session on BCC June-August 2025).
1x Meeting with the British Red Cross’ NGO-Military Contact Group (NMCG) (June 2025).
1 x Presentation for session on children and armed conflict during the American Red Cross' Leadership Training: ‘Upholding Humanitarian Principles in Modern Armed Conflict’ (July 2025).
1 x meeting with FCDO staff in Glasgow at Advanced Research Centre (August 2025).
1 x Watchlist Children and Armed Conflict policy workshop in Geneva, including a panel discussion on 'Beyond Compliance: Exploring a Harm and Need Approach to the Protection of Children in Armed Conflict'; findings shared from BCC desk-research and Myanmar fieldwork (Aug. 2025).
1 x series of 3 preparatory meetings for the FCDO 'Deep Dive' on Protection (connected to the 'Humanitarian Re-Set') (June – Aug. 2025)
1x UN General Assembly High-Level Week Side Event: ‘Beyond Compliance: Protecting Children in the Face of Intensifying Conflict.’ (September 2025)
1x Attendance at Expert Group Meeting: Economic, Social and Cultural Rights and Armed Conflict (BCC member attendance, Geneva Academy, (Sept. 2025)
1 x Attendance/ BCC panel presentation at Geneva Peace Week (Oct. 2025).
1 x Attendance at FCDO Deep Dive on Protection (Oct. 2025).
1 x Attendance/BCC presentation at FCDO 'Lunch and Learn' sharing fieldwork findings from Myanmar, Ukraine and Somalia, at FCDO Glasgow office and remote (Oct 2025).
1 x meeting at the Netherlands Marine Establishment (Oct. 2025).
1 x attendance at Fifth International Conference on the Safe Schools Declaration: BCC hosted a ‘Solutions Showcase’ booth, Nairobi (Nov. 2025).
1 x Submission in response to the call of the UN Special Rapporteur on the situation of human rights in Myanmar (Dec. 2025).

Annex 13: Peer-reviewed articles from AHRC (previous years greyed out)

Date	Title	Journal
17 Feb 2022	‘One Man’s Meat Is Another Man’s Poison’: Marungi and Realities of Resilience in North-West Uganda	Civil Wars
June 2022	The Cultural Problematic in Narratives of Violence against Women and Girls in South Sudan	Journal of Asian and African Studies
March 29 2023	Coloniality and frictions: Data-driven humanitarianism in North-Eastern Nigeria and South Sudan	Big Data and Society
26 April 2023	Data gathering and utilization: humanitarian targeting and ethical issues in northeastern Nigeria	Journal of Humanitarian action
21 March 2023	‘These people are lying to us’: Mutating Vaccine Fears and Colonial Histories in Arua, North-West Uganda	Medical Anthropology Quarterly
June 2023	‘All in good faith?’ An ethno-historical analysis of local faith actors’ involvement in the delivery of mental health interventions in northern Uganda	Transcultural Psychiatry
August 2023	‘I embroider the beauty that is my head and not the dead trees around me’ art heritage and resilience in South Sudan: a gendered view	Journal of Humanities and Applied Social Sciences
Jan 2024	Conceptualising and challenging child neglect in humanitarian action: Protecting displaced children in Jordan and Palestine	Child Abuse and Neglect
Jan 2024	Longitudinal Impact of Conflict-Related Sexual Violence Experienced by Men in Detention Since the Onset of the Syrian Conflict	eClinical Medicine (Lancet)
April 2024	Parenting and family interventions in lower and middle-income countries for child and adolescent mental health: A systematic review	Comprehensive Psychiatry
October 2024	Engaging Data Literacies in Displacement	Journal of Humanitarian Affairs
2025	‘You already know enough: Certainty and Ignorance in Data-Driven Humanitarianism’	Geopolitics

Annex 14: Number of IHL duty-bearers and non-state actors’ commitments to protect healthcare in 2025, disaggregated by nature of commitments (RIAH report)

Summary
In 2025, 1,489 IHL duty-bearer commitments to protect healthcare were made. Like the previous year, there was an increase in the number of commitments and statements on the protection of healthcare.

16 United Nations resolutions directly addressed the necessity to respect and protect healthcare in armed conflict:

1. The United Nations Security Council adopted Resolution 2773 on condemning ongoing offensives by the 23 March Movement (M23) in Eastern Democratic Republic of the Congo which condemned all attacks against the civilian population, including United Nations and associated personnel, humanitarian personnel, and medical personnel and facilities.
2. The United Nations Security Council adopted Resolution 2779 on extension of the mandate of the UN Mission in South Sudan (UNMISS) which stressed the obligation to respect and protect all medical and humanitarian personnel, their means of transport and equipment as well as hospitals and other medical facilities.
3. The United Nations Security Council adopted Resolution 2781 on the renewal of sanctions imposed by Security Council Resolution 2428 (2018) until 31 May 2026 and the extension of the mandate of the Panel of Experts on South Sudan until 1 July 2026 which expressed alarm and concern over continued violence against medical personnel and urged all parties to the conflict to allow and facilitate safe, rapid, and unhindered humanitarian access.
4. The United Nations Security Council adopted Resolution 2793 on the authorisation to Member States to form a Gang Suppression Force (GSF) in Haiti for an initial period of 12 months and on the establishment of the UN Support Office in Haiti (UNSOH) which expressed concern over the deterioration of the security situation and humanitarian crisis and called for the GSF to provide security for critical infrastructure including hospitals.
5. The United Nations Security Council adopted Resolution 2808 on the extension of the mandate of the UN Organisation Stabilisation Mission in the Democratic Republic of the Congo (MONUSCO) which demanded that all parties respect and protect all humanitarian personnel, including national and locally recruited personnel, and medical personnel, their means of transport and equipment, as well as hospitals and other medical facilities.
6. The United Nations Security Council adopted Resolution 2802 on the extension of the mandate of the UN Interim Security Force for Abyei (UNISFA) which expressed concern at the deteriorating humanitarian situation and insufficient access to food, medical care, and other essential services.
7. The United Nations Security Council adopted Resolution 2800 on the extension of the mandate of the UN Multidimensional Integrated Stabilisation Mission in the Central African Republic (MINUSCA) which condemned attacks by armed group against the civilian population, humanitarian and medical personnel and the obstruction to humanitarian access.
8. The United Nations General Assembly adopted Resolution A/RES/79/264 on the promotion of durable peace through sustainable development in Africa which condemned violent attacks and threats directed against medical personnel and facilities.
9. The United Nations General Assembly adopted Resolution A/RES/79/317 on the situation in Afghanistan which called for the Taliban to reverse their decision to suspend women’s and girls’ access to education in private and public medical institution and called for equal access to basic services, including public health services.
10. The United Nations General Assembly adopted Resolution A/RES/80/77 on the operations of the United Nations Relief and Works Agency for Palestine Refugees in the Near East which called for the unhindered provision of basic services and humanitarian assistance, as well as medical supplies and medical care to Palestinians in the Gaza Strip.
11. The United Nations General Assembly adopted Resolution A/RES/80/112 on the safety and security of humanitarian personnel and protection of United Nations personnel which condemned the high number of attacks against national and locally recruited medical and humanitarian personnel, as well as their means of transport and equipment, medical facilities and medical and relief supplies.
12. The United Nations General Assembly adopted Resolution A/RES/80/116 on the advisory opinion of the International Court of Justice on the obligations of Israel in relation to the presence and activities of the United Nations and third States in, and in relation to the Occupied Palestinian Territory which recalled and affirmed the requirement for Israel to fulfil its obligation under international humanitarian law to ensure the population of the Occupied Palestinian Territory has essential supplies for daily life, including medical supplies and services and to respect and protect all relief and medical personnel and facilities.
13. The United Nations General Assembly adopted Resolution A/RES/80/211 on the protection of and assistance to internally displaced persons which called for the respect and protection of medical personnel and humanitarian personnel engaged in medical duties, their means of transport and equipment, as well as hospitals and other medical facilities.
14. The United Nations General Assembly adopted Resolution A/RES/80/220 on the situation of human rights in the Democratic People’s Republic of Korea which noted the exacerbation of the humanitarian situation and governments restriction on international staff of humanitarian agencies and the effect these restrictions may have on levels of malnutrition and access to health services.
15. The United Nations General Assembly adopted Resolution A/RES/80/221 on the situation of human rights of Rohingya Muslims and other minorities in Myanmar which expressed alarm over the continued attacks on medical and humanitarian personnel, lack of basic healthcare and lifesaving assistance and the denial of safe, rapid and unhindered humanitarian access.
16. The United Nations General Assembly Resolution A/RES/80/223 on the situation of human rights in the temporarily occupied territories of Ukraine, including the Autonomous Republic of Crimea and the city of Sevastopol which condemned deliberate attacks against critical energy infrastructure and attacks impacting medical facilities.

We also noted seven additional statements from UN or international entities on the protection of healthcare:

1. The World Health Organisation released a statement on 29 October 2025 condemning killings of patients and their companions and the abduction of six health workers, on 28 October from the Saudi Maternity Hospital in El Fasher, Sudan. It called for an immediate end to hostilities in El Fasher and all of Sudan and for the protection of civilian, humanitarian workers, and health care.
  [note] World Health Organisation. WHO condemns killings of patients and civilians amid escalating violence in El Fasher, Sudan. 29 October 2025. Available at https://www.who.int/news/item/29-10-2025-who-condemns-killings-of-patients-and-civilians-amid-escalating-violence-in-el-fasher--sudan
2. The Special Rapporteur on the right of everyone to the enjoyment of the highest attainable standard of physical and mental health and the Special Rapporteur on the situation of human rights in the Palestinian territories occupied since 1967 released a statement on 13 August 2025 accusing Israel of deliberately attacking and starving health care workers, paramedics and hospital to wipe out medical care in the Gaza Strip. It stated that the targeted destruction of Gaza’s healthcare system by the Israel Defense Forces amounted to ‘medicide’. It called for deliberate attacks on health and care workers and health facilities to stop and stated at States have failed in their duty to end attacks and Palestinian trapped in Gaza are paying the ultimate price for that failure and indifference.
  [note] United Nations Human Rights. UN experts appalled by relentless Israeli attacks on Gaza’s healthcare system. 13 August 2025. Available at: https://www.ohchr.org/en/press-releases/2025/08/un-experts-appalled-relentless-israeli-attacks-gazas-healthcare-system
3. In a briefing to the Security Council on the provision of healthcare in Gaza the United Nations High Commissioner for Human Rights called for the protection of hospitals during warfare and condemned the destruction of hospitals across Gaza which goes beyond depriving Palestinians of their right to access adequate healthcare. It also stated that intentionally directing attacks against hospitals and places where the sick and wounded are treated, provided they are not military objectives, is a war crime and the deliberate destruction of healthcare facilities may amount to a form of collective punishment.
  [note] United Nations Human Rights. Israel’s attacks have devastating impact on Gaza’s hospitals, Türk tells Security Council. 03 January 2025. Available at: https://www.ohchr.org/en/statements-and-speeches/2025/01/israels-attacks-have-devastating-impact-gazas-hospitals-turk-tells
4. The International Council of Nurses issued an updated policy statement on health care in conflict, reaffirming its commitment to supporting nurses and ensuring their safety. It acknowledged a disturbing increase in conflicts and wars and called for peace and compliance with international humanitarian law.
  [note] International Council of Nurses (ICN). ICN issues updated statement on health care in conflict, calling for peace and compliance with international humanitarian law. 24 February 2025. Available at: https://www.icn.ch/news/icn-issues-updated-statement-health-care-conflict-calling-peace-and-compliance-international
5. The Royal College of Emergency Medicine issued a position statement on the targeting of healthcare facilities and workers during conflict calling for respect for international humanitarian law, the restoration of emergency medicine services impacted by conflict, the protection of healthcare workers and the safe release of all healthcare workers.
  [note] Royal College of Emergency Medicine. Targeting of healthcare facilities and workers during conflict – position statement by the Royal College of Emergency Medicine. 05 November 2025. Available at: https://rcem.ac.uk/news/targeting-of-healthcare-facilities-and-workers-during-conflict-position-statement-by-the-royal-college-of-emergency-medicine/
6. The British Medical Association (BMA) issued a press release on 22 July 2025 urging organisations around the world, including governments, the United Nations, NGOs and medical representative groups to play a role in taking action against attacks on healthcare staff, patients and facilities, and public health more widely, in global conflicts.
  [note] British Medical Association (BMA). BMA urges global co-operation and action against attacks on healthcare in conflict zones. 22 July 2025. Available at: https://www.bma.org.uk/bma-media-centre/bma-urges-global-co-operation-and-action-against-attacks-on-healthcare-in-conflict-zones
7. The Australian Nursing & Midwifery Federation launched a petition on 17 October 2025 calling for the Australian government to take stronger action on the protection of healthcare workers in conflict zones, where they are increasingly coming under attack.
  [note] Australian Nursing & Midwifery Federation. ANMF launches petition calling for protection of healthcare workers in conflict zones. 17 October 2025. Available at: https://www.anmf.org.au/media/media-releases/anmf-launches-petition-calling-for-protection-of-healthcare-workers-in-conflict-zones/

Additionally, the European Commission presented an EU action plan aimed at bolstering the cybersecurity of hospitals and healthcare providers, an initiative seen as an important step in shielding the healthcare sector from cyber threats to create a safe and more secure environment for patients and health professionals.
[note] European Commission. Commission unveils action plan to protect the health sector from cyberattacks. 15 January 2026. Available at: https://ec.europa.eu/commission/presscorner/detail/en/ip_25_262

In 2025, five conferences held events dedicated to the protection of health care in armed conflict. Similar to previous years, the Protection of Civilians Week 2025 held two events on the protection of healthcare. The ICRC held the Global IHL Initiative which involved two state consultations on the protection of hospitals in armed conflict, whilst the World Health Assembly held a side-event, organised by the WISH/Qatar Foundation and Central African Republic on the exploring ways to strengthen reports, analysis and responses to attacks on healthcare and encourage cooperation for a coordinated global response. Additionally, Queen Mary, University of London held two public panel events on the impact of attacks on healthcare in conflict zones and on violence against healthcare in conflict.