Title: Africa Food Trade and Resilience Programme
Programme Value (full life): £35 million		Review date: / 28 September 2025
Programme Code: 300489	AMP start date: / 28 September 2018	AMP end date: / 31 March 2026

Summary of Programme Performance
Year	2019	2020	2021	2022	2023	2024	2025
Overall Output Score	A	A	A	A	A+	A	A
Risk Rating	Major	Major	Major	Major	Major	Moderate	Major

DevTracker Link to Business Case:	https://devtracker.FCDO.gov.uk/ / /GB-GOV-1-300489/documents
DevTracker Link to results framework:	https://devtracker.FCDO.gov.uk/projects/GB-GOV-1-300489/documents

## A. SUMMARY AND OVERVIEW

Description of programme

The Africa Food Trade and Resilience (AFTR) programme was established as a five-year programme (2018-2023) funded by Africa Programme and Expertise Department (APEX). In 2023, a two-year no cost extension was granted taking the programme end date to March 2025, with a further no-cost extension granted in 2024 taking the programme end date to March 31st, 2026. The programme aims to stimulate an increase in regional food trade in Sub-Saharan Africa through partnerships with African Institutions including the African Union (AU) Commission, Regional Economic Communities (RECs), and with agri-businesses. The AFTR programme also generates knowledge, evidence and analysis for policy makers and businesses. This contributes towards generating more rural jobs, improved climate resilience and income for farmers. The programme is delivered via AGRA.
[note] Formerly Alliance for a Green Revolution in Africa: About Us - AGRA

The AFTR programme achieves its aims by a) improving the transparency and predictability of government policies to unlock regional food trade, b) supporting evidence-based decision-making, and c) working with companies that source, process, and trade food in the region, to maximize investment, coordination, and benefits to poorer farmers. The programme integrates climate resilience and gender as cross-cutting elements.

Summary supporting narrative for the overall score in this review

The overall score is. A. Outputs meets expectation.

The challenges of La Niña-induced droughts and floods, and the lingering effects of El Niño-induced droughts created both challenges and opportunities for the AFTR Programme. Some countries witnessed >50% reduction in crop yields due to droughts and floods. Against a background of limited fiscal headroom, and emergent food sovereignty concerns, several affected countries elected to impose ad hoc bans on grain exports as they struggled to balance national food self-sufficiency with regional trade. Through AGRA, this programme has been able to further focus efforts to support national governments with accurate data, analytics, and evidence-based advice to make informed policy decisions.

The programme has increasingly strengthened its partnership with the African Union. The programme has provided both financial and technical support to the new Kampala Declaration’s ten-year Comprehensive Africa Agriculture Development Programme (CAADP) Strategy and Action Plan, Africa Fertiliser and Soil Health Summit activities and Action Plan, and the Africa Continental Free Trade Area (AfCFTA) Agri-trade Action Plan. At the level of Regional Economic Communities (RECs), the programme continued to deepen and strengthen relationships, especially with the Common Market for Eastern and Southern Africa (COMESA) and Economic Community of West African States (ECOWAS). Two senior specialists were recruited to strengthen these partnerships. Currently, the AFTR Programme Management Unit in AGRA is comprised of ten staff.
Table 1: Summary of Output Assessment

	Output	Assessment	Score
1	Up to date market and political economy analysis of regional food trade flows informs selection of opportunities for policy reform and demand led regional food market development	The programme responded to regional challenges by pivoting investments to support emergent policy-related needs. In doing so, the programme surpassed all Output 1 targets for Year 7. Much of this investment has been to better understand the food-security related challenges facing national governments and the search for regional solutions. The creation and dissemination of knowledge management products continued to be critical in supporting evidence-based decision-making.	A+
2	More predictable, private sector and climate friendly government interventions reduce obstacles to regional food trade	The programme continued to prioritise the workstream on policy predictability. AGRA delivered a cumulative 58 policy interventions in various countries, against a target of 59. The programme is supporting COMESA to expand the number of countries both supplying data and using the Regional Food Balance Sheet, as well as the range of commodities reported. The programme also strongly supported COMESA’s workstream on Mutual Recognition Agreements (MRAs). The MRA between Malawi and Zambia was officially cleared, and preparations for signing have commenced. The MRAs for Malawi and Zimbabwe; and Zambia and Zimbabwe have also been successfully developed and negotiated and are just waiting for clearance by Zimbabwe.	A
3	Improved coordination and investment in regional food value chains, with commercial companies supported to efficiently engage and service smallholders, based on actionable data-driven insights and advice	One Output 3 target was achieved, and 3 were narrowly missed. This was due to the programme’s pivot towards policy and data/evidence generation/collation, and over-ambitious targets for ongoing small and medium-sized enterprises (SME) investments. There were no new market shaping investments during the reporting year. / FCDO’s contribution to the ‘Financing for Agriculture Small and Medium Enterprises in Africa’ (FASA) programme helped leverage wider donor commitments.	B
4	More resilient SHF accessing better services, new markets, advice, and finance through integration in regional food value chains	Whilst some progress was made, AGRA failed to achieve Output 4 targets. This was primarily due to operational delays with the Chinyanja Phase II, and COMESA East Africa Horticulture Accelerator (CEHA) projects, and the fact that no new market shaping investments were made in the reporting year.	B

Major lessons and recommendations for the year ahead

Major lessons

In a world of scarce donor resources, there is a need to develop partnerships to build on lessons learned and to scale the pioneering initiatives piloted under this programme. Any follow-on Programme should partner with development partners, Development Finance Institutions, and key public and private sector actors to crowd-in investment to take these initial investments to scale. RECs could be developed into centres of excellence in various value chains, e.g., ECOWAS for rice, COMESA for horticulture, and SADC for soya.

AGRA has evolved significantly during the past seven years and has built a strong reputation on regional trade. Because of this, it is becoming increasingly critical in supporting the adoption/alignment (i.e. “domestication”) of strategic continental agendas within national policy processes on both trade (AfCFTA), and agriculture (CAADP).
Major Recommendations
This AR makes the following recommendations:

- Recommendation 1: AGRA should work with the AU’s AfCFTA Secretariat, and Agriculture, Rural Development, Blue Economy, and Sustainable Environment (ARBE) to strengthen collaboration on progressing the domestication of AfCFTA, and CAADP across target African countries. This should be delivered by 31st January 2026.
- Recommendation 2: AGRA should determine the optimal use of policy coalitions. This should be completed by 31st December 2025.
- Recommendation 3: AGRA should develop an action plan for taking key pilot investments (such as RFBS, MRAs, Food Corridors) to scale. This should be delivered by 31st December 2025.
- Recommendation 4: AGRA should consolidate and align partners’ support and commitments towards ensuring sustainability of strategic on-going investments. This should be delivered by 31st January 2026.
- Recommendation 5: AGRA to consider what lessons have been learned through their support of commercial companies and develop case studies to share that learning more widely.
- Recommendation 6: Future reviews should amend the Effectiveness VfM indicator to ensure it captures work done by AFTR this Financial Year.
- Recommendation 7: VfM indicators should be evaluated at the project as well as programme level in any successor programme to AFTR.
- Recommendation 8: An assessment of programme cost-efficiency should be included in the Programme Completion Review and considered in the design of any successor programme.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

1. The programme’s Theory of Change is that greater predictability, and efficiency of government interventions in regional food markets, and improvements in market facilitation, value chain coordination, will together lead to increased business and investor confidence. In turn, investors will inject much-needed capital to facilitate growth of the sector. This should raise agricultural productivity, production, and processing, and create profitable market linkages, especially for Small Holder Farmers (SHFs). By generating evidence on opportunities for viable investment, the programme will reduce risk perceptions and ultimately catalyse greater financing into the sector, which should lead to more jobs, increased cross-border food trade, increased availability of affordable nutritious food and improved farmers’ resilience. Overall, the programme continues to have the same indicators that were identified in the original business case.
2. No changes were made to the impact and outcome indicators from the original business case. The programme continues to track 4 impact indicators and 7 outcome indicators that were identified in the original business case. However, the programme has not been tracking impact indicator 2 (Enabling the Business of Agriculture Index - Food Trading Score) due to lack of data, as World Bank discontinued the publication of the Enabling Business of Agriculture Reports in 2021.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Whilst the Programme continues to make a significant contribution to regional food trade and food and nutritional security in Africa, mapping these against both Impact and Outcome indicators is difficult. Where reliable data exists, logframe outcome data suggests that there is a positive trend in African regional food trade; for instance, on Outcome 1, the total additional volume of food traded by supported firms is 451,392 metric tons (MT – mainly to new buyers), with 336,776 MT in domestic trade and 114,616 MT in regional trade. The AFTR programme has also improved the availability of nutritious foods, such as beans and soybeans, trading 52,800 MT over six years through supported companies.

In many respects, the key strength of the Programme, and AGRA as FCDO’s implementing partner, is the capacity to crowd-in public sector actors at continental, regional and national levels, as well as development partners and private sector companies and trade organisations, into the regional food trade and food and nutrition security space, around data/analytics/evidence, policy support, and economic growth potential, especially around food corridors. A review of the Programme’s Theory of Change by EQUALs, undertaken in June 2025, confirmed that most of the assumptions made, along with the identified risks and mitigation measures, remained relevant, especially at the policy and systems level.

The Programme provides financial and technical support to supply and demand-side initiatives, which aim to secure regional food and nutrition security and enhanced food trade.

In the year ahead, the Programme will continue providing financial and technical support to the African Union Commission forn the process of domesticating the AU-Kampala CAADP Strategy and Action Plan, AU Fertiliser and Soil Health Action Plans, and the AU-AfCFTA’s Agri-trade Initiative Action Plan. We will continue to support evolving work on food corridors to better connect Africa's agricultural production basins to both regional and international markets. We will also drive market shaping activities through the creation of food corridors, improving coherence and access across Eastern and Southern Africa. At a regional level, the Programme will continue supporting COMESA’s RFBS, MRA, and CEHA workstreams, as well as the ECOWAS Rice Observatory (ERO).
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio.

The programme should continue. It is a key enabler of intra-African food trade and is a major contributor to food system transformation in Africa, which is critical for delivering food and nutrition security. The programme is meeting expectations and, in some cases, exceeding them. The programme is providing information and analytics that supports evidence-based decision making by governments and private sector, and the delivery team are seen as influential in shaping the continental agenda. The programme continues to provide thought leadership and crowd-in other development partners to support demand-side interventions. The programme also plays a key role in building climate resilience.

## C. DETAILED OUTPUT SCORING

Output Title	Up to date market and political economy analysis of regional food trade flows informs selection of opportunities for policy reform and demand led regional food market development
Output number:		1	Output Score:	A+
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Cumulative Milestone(s) for this review	Progress
1.1 Number of country-influencing strategies on food trade where priorities are informed by political economy analysis (PEA) and country engagement started	24	26
1.2 Number of coordinated initiatives and/or systems for monitoring food trade trends/flows developed, strengthened and or consolidated at regional level (i.e., food demand projections, price monitoring systems, trade monitors, production forecast system among others)	20	21
1.3 Number of agricultural policies and initiatives following 1.1 and 1.2 above completing policy development stages (i.e., analysis, stakeholder consultation, public/private dialogue)	20	21
1.4 Number of knowledge management products that are produced on regional food trade	182	212

Briefly describe the output’s activities and provide supporting narrative for the score

1. Output 1 aims to identify potential high impact entry points for evidence-based regional food trade and policy reform and to initiate policy engagements. The programme has moderately exceeded expectations. The overall output rating for Output 1 is A+.
2. Output 1.1 This year, the programme initiated four new country-influencing strategies on trade, taking the total to 26, against a target of 24.
3. One PEA study and influencing strategy has been initiated on monitoring food policy and trade developments in Southern and West Africa. Another PEA study focused on the Food Baskets/Corridors Initiative, which informed the design of the Food Corridors Initiative.
4. Two country level studies were initiated. One study assessed the impact of fiscal measures on agricultural value chains in Kenya. The second study assessed the impact of Ghana’s export restrictions on cereals. The outcome of these studies will identify key areas, entry-points, and approaches for the programme to design nimble policy influencing activities in the respective geographies.
5. Output 1.2 This year the programme launched a new coordinated initiative for monitoring food trade trends/flows at the regional level, taking the cumulative total to 21, against the target of 20. This initiative monitors food policy and trade developments in Southern and West Africa. This initiative is designed to gather real-time insights into food security policy, as well as formal and informal trade in and movement of food commodities in countries that have been hard-hit by climate change related adverse weather, which have significantly affected agricultural production and created food deficits in many countries. By generating reliable, timely, and Africa-sourced data, the initiative strengthens governments and regional bodies’ capacity to make decisions based on homegrown evidence rather than external reports. This builds trust and legitimacy in African data systems. FCDO will continue to work with AGRA to embed these data systems within existing African institutions (e.g., RECs like COMESA, ECOWAS, EAC, and AU organs), to strengthening their technical and analytical capacities to manage and sustain a continent-wide early warning system for food security.

1. Output 1.3 The programme initiated one policy initiative. Building on evidence generated by the COMESA Regional Food Balance Sheet, Market Information System, and leveraging the Food Trade Coalition for Africa, AGRA successfully facilitated resolution of the mutually imposed, and potentially highly disruptive, trade issues arising between Tanzania and Malawi. This targeted initiative brings the cumulative total to 21, against a target of 20.
2. Output 1.4 During the period under review, a cumulative total of 212 Knowledge Management Products/events were delivered against a cumulative target of 182. These include 11 Food Security Monitors, 1 peer reviewed journal article on “Embracing the African Continental Free Trade Area: Unpacking Malawi’s Economy Response to Trade Liberalization”, 12 policy briefs, and a range of awareness materials, technical guides, success stories, technical guides, learning events, and dialogue sessions (held on the sidelines of the Africa Food Systems Forum in Rwanda, 2024).
Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no specific changes to the output during the period under review. However, output targets 1.2, 1.3, and 1.4 were increased due to AGRA’s over-achievement in the previous year’s Annual Review. Even though the target for output 1.1 wasn’t increased, AGRA still managed to surpass the target.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

A status report on last year’s recommendations is in Annex 1.
Lessons and Recommendations
Lesson 1: This year continued to demonstrate the importance of AGRA’s responsiveness to live policy issues; for example, when AGRA successfully resolved the mutually imposed, and highly disruptive, trade restrictions between Tanzania and Malawi. AGRA should continue to demonstrate being proactive and consider using programme and policy levers at their disposal when dealing with emerging issues. To this end, AGRA should develop an end-to-end case study of this engagement to help FCDO and partners understand and learn from this dispute and inform how similar disagreements might be resolved in future.
Recommendation 1: AGRA should work with the AU’s AfCFTA Secretariat, and Agriculture, Rural Development, Blue Economy, and Sustainable Environment (ARBE) to strengthen collaboration on progressing the domestication of AfCFTA, and CAADP across target African countries. This should be delivered by 31st January 2026.

Output Title	More predictable, private sector friendly and climate friendly government interventions reduce obstacles to regional food trade.
Output number:		2	Output Score:	A
Impact weighting (%):		40%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review (Cumulative)	Progress
2.1 Number of food trade initiatives including business-led advocacy for cross-border food trade completing policy development stages (Total 2.1 i-iv + 2.1b)	59	58
(i) Validation	17	18
(ii) drafting /revision	15	16
(iii) Approval (legislation/regulatory)	12	11
(iv) effective implementation	10	10
2.1 (b) Number of Mutual Recognition Frameworks developed and negotiated by COMESA member states	5	3
2.2 (a) Number of food trade policy coalitions champions identified and engaged	57	57
2.2 (b) Number of policy coalitions launched	7	7
2.2 (c) Number of strategic engagements on food trade policies and investments organized or co-organized by the programme	46	57

Briefly describe the output’s activities and provide supporting narrative for the score

Output 2 aims to facilitate growth and predictability in regional food trade through building and driving coalitions of action. On the whole, the programme has met expectations. The overall output rating for this output is A.

Output 2.1 AGRA supported a cumulative total of 58 policy interventions in various countries, against a target of 59. In line with expectation, two of the achievements were at the policy approval and implementation stages. These were the MRA between Malawi and Zambia, which was approved over the period of this AR and was signed after the reporting period, and resolution of the mutually imposed trade restrictions between Tanzania and Malawi. Only one new initiative, the AU AfCFTA Agri-trade Action Plan was reported at the validation stage. It is expected that most of the remaining policies and initiatives will be approved and implemented by the end of the programme.

Output 2.1 (b) Following a series of bilateral negotiation meetings and follow ups with senior government officials in the targeted countries, the Mutual Recognition Agreement between Malawi and Zambia was cleared. This agreement was signed in August 2025. Implementation of this MRA is expected to significantly contribute to easing barriers to trade by reducing trading costs in terms of eliminating multiple testing and grading of the six commonly traded stapple food commodities namely, rice, maize, beans, soya beans, groundnuts and sorghum. The MRAs for Malawi and Zimbabwe, and Zambia and Zimbabwe have also been successfully developed and negotiated and are waiting for clearance by the Government of Zimbabwe. MRA negotiations are ongoing between Kenya and Uganda, and Uganda and Rwanda. COMESA is leaning into the MRA processes to ensure that at least some of the MRAs are signed, and in the process of implementation, by the end of the Programme.

Output 2.2 (a) No additional food trade policy coalitions champions were identified and engaged this year. This output indicator remains on target given achievements beyond milestone targets in previous years. This year, the Food Trade Coalition for Africa has undergone a strategic refresh. Existing champions are expected to lean into key Programme priority areas, such as the RFBS and MRA workstreams.

Output 2.2 (b) No further policy coalitions were launched this year. This output indicator remains on target given achievements beyond milestone targets in previous years, as such no notable progress was expected on this output indicator. During the reporting period, the Food Trade Coalition for Africa facilitated the second round of negotiations on the Simplified Trade Regime (STR) between the Republic of Malawi and the United Republic of Tanzania on the sidelines of the Africa Food Systems Forum (AFSF) which was held in September 2024, in Kigali, Rwanda. The STR framework has now been cleared by the Government of Tanzania and is awaiting clearance from the Government of Malawi before proceeding to signing. The Food Trade Coalition collaborated with EAGC and TradeMark Africa to convene the Eastern and Southern Africa Private Public Policy Dialogue (PPD) and Business-to-Business (B2B) Forum, in Nairobi, Kenya from December 16 - 17, 2024, to discuss and exchange ideas on strengthening policy frameworks, fostering collaboration, and addressing the shared challenges within the region’s grain value chain. The forum was convened to agree on solutions and approaches to address trade bottlenecks as well as provide a platform for business networking. The B2B session, conducted alongside the PPD, yielded 31 non-binding contracts. The agreements encompassed a total of 132,776 metric tons of grains, valued at approximately $41.79 million committed to trade in the current and upcoming seasons for 14 different commodities (see Output 2.2(c) below).

Output 2.2 (c) The Programme achieved a cumulative total of 57 strategic engagements on food trade policies and investments organized or co-organized by the programme, against a target of 46.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
As a result of this review, the FCDO plan to approve refreshed output targets for Year 8 of the AFTR programme, noting the extension to March 2026.
Lessons and Recommendations

Lesson 2: AGRA has evolved significantly during the past seven years and has built a strong reputation on regional trade. Because of this, it is becoming increasingly critical in supporting the adoption/alignment (i.e. “domestication”) of strategic continental agendas within national policy processes on both trade (AfCFTA), and agriculture (CAADP).
Lesson 3: In the case of the trade dispute between Malawi and Tanzania, data/evidenced-based facilitation proved critical in resolving political stalemates.
Lesson 4: Getting to the point of signature for MRAs requires commitment to both technical details and political expediency, whilst not underestimating the importance of post-signing implementation.
Recommendation 2: AGRA should determine the optimal use of policy coalitions. This should be completed by 31st December 2025.

Output Title	Improved coordination and investment in regional food value chains, with commercial companies supported to efficiently engage and service smallholders, based on actionable data-driven insights and advice
Output number:		3	Output Score:	B
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review (cumulative)	Progress (cumulative)
3.3 (a) [AGRA] Investment leveraged in inclusive regional value chains (aggregation, post-harvest, primary processing, structured trade, services to farmers) (US$ million)	35	34.3
3.3 (b) [AGRA] Of which investments are eligible under International Climate Finance (ICF) Key Performance Indicator (KPI) 12	11.8	10.01
3.4 (b) Number of technical assistance projects supported by AGRA	9	7
3.4 (d) Amount of finance (US$ million) leveraged from other partners in support of Regional Food Trade initiatives as a result of the FCDO programme	30	33.9 / [FCDO design funds played a leveraging role in the US$200m FASA programme.]
[note] ICF KPI 12: Volume of private finance mobilised for climate change purposes because of ICF funding.

Briefly describe the output’s activities and provide supporting narrative for the score

1. The overall output rating for this output is B.
2. Output 3 aims to improve coordination and investment in regional food value chains, with companies supported to efficiently engage and service SHFs, based on actionable data-driven insights and advice.
3. Output 3.3 (a) No new achievements were reported during the reporting period in line with expectation. The total cumulative investment leveraged still stands at USD 34.3 million and USD 10.1 million for ICF investments, against a target of USD35 million and 11 million respectively. This is due to the Programme’s pivot towards policy and data/evidence generation/collation. It is possible that the CEHA initiative will meet the current targets by the end of the Programme in March 2026. However, during the reporting year, the Programme continued to invest in strengthening platforms that would facilitate market shaping activities, for which there is a time lag for results. Some of the anticipated results will come onstream in the 2025-26 financial year, and beyond. This includes: 1) support to CEHA to trigger the implementation of the CEHA Matching Grant Facility to support SMEs in the horticulture sector, and 2) increased investment in ACE - Malawi to support enhancement of technology applications in rural warehouses to integrate more smallholder farmers in structured trade through the commodity exchange.
4. Output 3.3 (b) As referenced in 3.3(a) above there were no new market shaping investments making contributions during the past reporting year, therefore no further progress was made on this indicator.
5. Output 3.4 (b) This year no new technical assistance projects were supported by the Programme, maintaining the cumulative total of 7, against a target of 9. As two new technical assistance projects on accessing UK markets for high-value African fruit and vegetables get underway, the target of 9 is expected to be met before the close of the Programme.
6. Output 3.4 (d) This year, an additional USD9 million was leveraged by AGRA from other partners for FCDO priority workstreams, taking the total to USD33.9 million against a target of USD 30 million. USD5 million was leveraged from the Gates Foundation to support the establishment and implementation of a Matching Grants Facility targeting SMEs in the horticulture sector across Kenya, Tanzania, Uganda, Rwanda, and Ethiopia. The facility is designed to catalyse private sector investment by requiring participating SMEs to contribute 50% co-financing, thereby reinforcing the sustainability and ownership of the initiative. A total of USD 4 million of the newly approved Gates Foundation rice project was secured by AGRA in partnership with GIZ, JICA and local Rice chapters of ECOWAS Rice Observatory.
7. The AFTR programme also made a £1m contribution to FASA programme, a multi-donor fund-of-funds that will address the financing gap and capacity building needs within food systems. It will provide catalytic capital and technical assistance to support investment funds (IFs) that will lend to, or invest in, agri-SMEs across Africa. The AFTR contribution was able to leverage and facilitate other donors’ funding by providing design funds and support for the wider monitoring, evaluation and learning elements of FASA.
8. To include the FASA leverage in the progress section of these indicators would skew the calculations, however considerable leverage was achieved as the new investment vehicle progressed towards its US$ 200 million investment target.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

Given that IDH is officially no longer a programme partner, Outputs 3.1, 3.2 are no longer reported, only AGRA’s contribution to Outputs 3.3a, and 3.3b are reported.
Lessons and Recommendations
Lesson 5: Many of the Programme’s investments have been relatively pioneering and innovative in nature – food baskets/corridors, COMESA’s Regional Food Balance Sheet (RFBS), MRAs, etc. In a world of scarce donor resources, there is a need to develop partnerships to build on lessons learned and to scale these pioneering investments. Any follow-on Programme should partner with development partners, Development Finance Institutions, and key public and private sector actors to crowd-in investment to take these initial investments to scale. RECs could be developed into centres of excellence in various value chains, e.g., ECOWAS for rice, COMESA for horticulture, and SADC for soya.
Recommendation 3: AGRA should develop an action plan for taking key pilot investments (such as RFBS, MRAs, Food Corridors) to scale. This should be delivered by 31st December 2025.
Recommendation 4: The AFTR team should consolidate and align partners’ support and commitments towards ensuring sustainability of strategic on-going investments. This should be delivered by 31st January 2026.

Output Title	More resilient smallholder farmers accessing better services, new markets, advice, and finance through integration in regional food value chains
Output number:		4	Output Score:	B
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 Number of SHFs disaggregated by sex, other dimensions / (b) accessing better set of intervention packages from extension, financial services through AGRA / c) supported to cope with the effects of climate change / d) Number of smallholders reached by new and/or strengthened aggregation arrangements established with support of the programme.	335,000 of which 155,000 female / 80,000 / 210,000	333,971 / (of which 136,832 are female) / 72,438 / 202,058

Briefly describe the output’s activities and provide supporting narrative for the score

1. Output 4 aims to support the equitable integration of SHFs into structured and climate resilient regional food systems. TA providers are encouraged to target commodity aggregators that already provide financial and technical support to SHFs and support further scaling of approaches that deliver greater stability, profitability, and resilience of farm-level production. The overall output rating for this output is B.
2. Output 4.1 (b) The cumulative achievement of this output is 333,971, against a target of 335,000. Of this number, 136,832 were female, against a target of 155,000. This shortfall is primarily due to operational delays with the Chinyanja Phase II project. However, this indicator remains on track and should be achieved before programme closure. Whilst the overall target is likely to be met, the number of females is likely to remain below target. This is due to the fact that AGRA’s sub-grantees work directly with aggregators and processors, and not directly with farmers. This limits AGRA’s sub-grantee’s ability to influence the selection of individual farmers and farmer groups.
3. Output 4.1 (c) Under this output, AGRA aims to support SHFs to cope with the effects of climate change. AGRA reached 72,438 SHFs, narrowly missing a target of 80,000 farmers. As above, this shortfall is primarily due to operational delays with the Chinyanja Phase II project. However, this indicator remains on track and should be achieved before programme closure.
4. Output 4.1(d) AGRA established or strengthened the aggregation arrangements of 202,058 SHFs, against a target of 210,000. This shortfall is primarily due to operational delays with the Chinyanja Phase II, and CEHA projects. However, this indicator remains on track and should be achieved before programme closure.
Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]
Given that IDH is officially no longer part of the Programme, Output 4.1a is no longer reported, and only AGRA’s contribution to Output 4.1c is reported.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
There were no recommendations for Output 4 from the previous annual review.
Lessons and Recommendations

Lesson 6: Most agri-business investments are time sensitive, and any operational delays affects results reporting due to time-lag. For example, operational delays in Chinyanja Triangle Phase 2 project means that performance and impact of the Warehouse Monitoring System can only be reported after project closure as next harvest system is in May-June 2026.

Recommendation 5: AGRA to consider what lessons have been learned through their support of commercial companies and develop case studies to share that learning more widely.

D: VALUE FOR MONEY

As set out in its Business Case, AFTR measures VfM using the following benchmarks, corresponding to 4 of the 5Es:
- Economy: percentage of budget used on administrative costs (“Administrative Cost Ratio”)
- Effectiveness: amount of investment generated from the initial funding by FCDO (“Investment Leverage Ratio”)
- Efficiency: £s spent on smallholder farmer engagement projects per farmer engaged (“Smallholder Farmer Engagement Ratio”)
- Equity: proportion of smallholder farmers engaged which are female (“Female Smallholder Engagement Ratio”)
1. Two out of four benchmarks increased their level of VfM in the previous Annual Review, one benchmark remained stable, and one benchmark saw decreased VfM (reflecting a different type of project attempted)
2. FCDO together with AGRA has sought to make improvements on the VfM performance of the programme. AGRA seeks to help downstream partners to improve their VfM and includes a VfM analysis section in their final project completion reports. All new grantees for on-boarding in 2024 have been supported to include a VfM section in their proposals as part of the requirements for approval.
Economy – Administrative Cost Ratio
The key metric to measure economy is the Administrative Cost Ratio. This metric is tracked how it trends over time to ensure the programme’s economy does not change notably. AGRA report that their cumulative spend on administrative costs for the lifetime of AFTR has been £680,154 out of £15,482,582, or 4.4%. The table below shows the comparative figure throughout the lifetime of the programme. The administrative cost ratio is comfortably below guidelines set by FCDO and provides good value for money.
Metric	Partner	2019	2020	2021	2022	2023	2024	2025
Administrative cost ratio	AGRA	6%	4.8%	5%	5%	5.9%	5.0%	4.4%

Effectiveness – Investment Leverage Ratio
The Investment Leverage Ratio is calculated by comparing the operational costs of technical assistance (TA) provided to grantee partners to the investments leveraged by the grantee partners as a result of this TA. As the table below illustrates, the ratio in 2024 is unchanged from the previous year, for the third year in a row. This ratio offers good value for money; this is an extremely high ratio and compares favourably to similar TA projects.
Metric	Partner	2020	2021	2022	2023	2024	2025
Investment leverage ratio	AGRA	N/A	£1: £18	£1: £32	£1: £27	£1: £27	£1:£27

1. This lack of change is mainly due to there not being any additional spend on TA over the course of this Annual Review period, resulting in the Investment Leverage Ratio staying at the same level.
2. This metric no longer provides a meaningful measure of progress during this Annual Review period. Given that no further TA is planned between now and the closure of the AFTR programme, the programme team should consider broadening this VfM indicator to include more potential methods in which AFTR leverages investment.
Recommendation 6: Future reviews should amend the Effectiveness VfM indicator to ensure it captures work done by AFTR this Financial Year.
Efficiency – Smallholder Farmer Engagement Ratio
The Smallholder Farmer Engagement Ratio measures the ratio of funds disbursed and the reported number of SHFs benefitting from grantee-based projects, showing the number of pounds spent for one SHF to be engaged. The smaller the ratio, the more efficiency the programme demonstrates. As the table below indicates, there has been an increase in this ratio (indicating less efficiency). Efficiency is now at its lowest rate since 2020.
Metric	Partner	2020	2021	2022	2023	2024	2025
Smallholder engagement rate	AGRA	£4.26:1	£1.94:1	£4:1	£3.75:1	£3.73:1	£4.19:1

1. While this would be expected to demonstrate a reduction in project efficiency, this increased SHF engagement ratio is primarily due to the current project having a different scope and location to projects in previous years. The current project is providing focussed, high-intensity training to upskill aggregators and input suppliers, centred around the (relatively small number) of SHFs using warehouses in the Chinyanja Triangle in Malawi. This training is more impactful and has a broader scope than training provided on earlier projects, which classed SHFs as “reached” with the provision of basic informational.
2. This metric highlights a weakness in setting cumulative indicators at a programme level; while this can be a useful abstraction for overall analysis, it can obscure trends within the individual projects that make up AFTR. The Chinyanja Triangle project was started during this Annual Review period, so no year-on-year efficiency analysis is currently possible; however, the Programme Completion Report will be able to compare efficiency with the results of this Annual Review.
3. The table below displays the project-level SHF Engagement Ratio, showing the variance between projects. The Chinyanja Triangle project is the first one on the list.
4. Variation between projects over the lifetime of the programme is to be expected, given the different goals, geographies, operating environments, and challenges in any given context. Indeed, the lower figures from earlier in the programme may reflect an over-reliance on two projects with an extremely strong smallholder farmer engagement ratio. This demonstrates the importance of keeping project-level figures, and the programme team may wish to consider project-level VfM indicators as well as overall figures in any future programme design.
Recommendation 7: VfM indicators should be evaluated at the project as well as programme level in any successor programme to AFTR.
Smallholder Farmer Engagement Ratio – Cumulative values (Year 7)
Total cumulative disbursements (£)	Total Farmers reached (cumulative)	Ratio
180,004.00	6,692	26.8
177,693.00	168,192	1.06
225,500.00	43,255	5.21
167,246.00	58,115	2.88
200,000.00	30,262	6.61
356,162.76	24,960	14.27
107,416.21	6,053	17.75
1,414,021.97	337,529	4.19

Equity – Percentage of Female SHFs
The key metric to measure equity is the percentage of females SHFs among smallholders supported by the programme. This year, this ratio improved to 45.1%, demonstrating a significant improvement in equity. This is a strong performance, and is significantly closer to the 50% benchmark suggested for programmes.

Metric	Partner/AR Year	2020	2021	2022	2023	2024	2025
% SHFs engaged that are female	AGRA	31%	30%	39%	41%	41%	45%

This result should also be seen in conjunction with the benchmark on efficiency, reflecting the fact that both benchmarks are linked into programme support for SHFs. In this instance, while efficiency is decreasing due to the change in project type, equity is significantly increasing in that same intervention, suggesting that this work done in the Chinyanja Triangle project is of good quality.
Cost-Efficiency
Notably, there is no cost-efficiency indicator currently in place for this programme. While the programme is nearing the end of its lifespan, this is an important indicator for both this and any future successor programmes.
Recommendation 8: An assessment of programme cost-efficiency should be included in the Programme Completion Review and considered in the design of any successor programme.

E: RISK

Overview of risk management
1. The risk level for the AFTR is currently assessed as Major. This is an increase from its level at the last Annual Review, which was Moderate, and a return to the programme’s risk level for the majority of its life. The increase in risk level reflects a difficult financial context (both internal to the FCDO and external), which has posed additional challenges to programme delivery.
2. AFTR has had long-running risks around the potential for climate, security and fraud issues to disrupt delivery; all three of these phenomena could jeopardise FCDO investments and reduce the capacity of delivery partners to implement projects, but were mitigated against. However, over the period in question for this Annual Review, significant developments put additional risk onto the implementation of a programme focussing on encouraging the removal of barriers to free trade across Africa.
- Firstly, the imposition of tariffs on global trading partners by the USA created a more hostile policy environment for the AFTR, with African countries potentially encouraged to apply their own tariffs to recover revenue, therefore restricting cooperation with the AFTR by policymakers.
- This was enhanced by the related rise in global economic instability, which risks limiting the capacity of policymakers and reducing their willingness to engage with AFTR’s delivery partners. Key partners, such as the AUC Commission for Agriculture and AGRA, also underwent leadership changes, creating further uncertainty and reducing institutional capacity to navigate these shocks.
- These two aspects combined to increase the overall risk profile of AFTR, providing additional high-risk hurdles that could potentially derail delivery.
AFTR currently has the following appetites for risk:
Risk Appetite Category	Level
Strategy & Context	Receptive
Policy & Programme Delivery	Receptive
Safeguarding	Cautious
Public Service Delivery & Operations	Cautious
Financial & Fiduciary	Cautious
Reputational	Cautious
People	Cautious

1. One risk appetite was changed since the previous Annual Review; the Safeguarding risk appetite was increased from Minimal to Cautious. This reflected feedback from central risk experts that Minimal was inappropriately low and based on a misunderstanding of what a zero-tolerance policy should look like in a risk appetite; the level of Safeguarding risk in the programme has not increased.All risk appetites are now set at suitable levels which reflect the programme’s capacity to tolerate risk.
2. There is currently one risk which is outside of appetite; a reputational risk, considering the reputational damage of FCDO withdrawal from the sector, and the efforts being taken to mitigate it. As outlined in the Business Case, the FCDO team maintains an AFTR programme oversight level Risk Register, which is updated every six weeks in line with FCDO best practice.
3. AGRA undertakes its own risk management processes, where it identifies risks within each of projects and mitigating actions taken. Details of these risks are presented and discussed with the FCDO team at Quarterly meetings.
4. AGRA conducts due diligence into downstream partners before entering into agreements, making them aware of reporting mechanisms and providing staff training There were no suspicions or allegations of fraud, terrorist financing, money laundering, bribery, corruption, or sexual exploitation, abuse or harassment (SEAH) involving any AGRA staff member or partner (or downstream delivery partners) during the reporting period for this Annual Review.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

1. AFTR has one implementing partner, AGRA. AGRA has signed an accountable grant agreement with FCDO. AGRA in turn have a number of downstream partners.
2. Delivery to date has met expectations – indeed, AGRA have had to revise targets upwards to take strong historic performance into account. AGRA is a professional and well-established partner who display a strong convening power and track record of delivery, including through several long-standing policy products. AGRA are aware of FCDO monitoring and reporting requirements and meet programme management deadlines; where deadlines are not met, this is communicated in advance. AGRA deserve particular commendation for their flexibility with an uneven funding model, responding at pace to fluctuations and uncertainty in budget allocations. FCDO has worked with AGRA over this Annual Review period to focus delivery in priority areas, such as contributions to system-level transformation of intra-African food trade (Outputs 1 and 2).
Project example / In January 2025, the African Union adopted the CAADP Kampala Declaration, Strategy, and Action Plan, which aims to transform Africa’s agri-food systems. The Action Plan focuses on six strategic commitment areas, which include intensifying sustainable food production, agro-industrialization, and trade; boosting investments and financing for agrifood systems transformation; ensuring food and nutrition security; advancing inclusivity and equitable livelihoods; building resilient agrifood systems and strengthening agrifood systems governance.

1. AFTR had a final spend for the 24-25 FY of £6.6m – £5.6m to AGRA, and £1m to the FASA Fund, an initiative created in 2023 by USAID and the Norwegian development agency, Norad, which aims to catalyse US$ two hundred million in investment for small and medium sized agricultural businesses in Africa.
2. The programme-funded secondee based in AGRA continued to provide results. The secondee returned to FCDO in January 2025. Since then, AGRA has experienced a large number of vacancies, which weakened the timeliness and quality of programme and financial documents; this gap highlights the importance of continued FCDO capacity building. AGRA has now recruited staff to fill these vacancies; however, these staff will undoubtedly require additional time to gain familiarity with their role, making the retention of current AGRA expertise vital.
3. AGRA completed their audit for 2024 in July 2025. This audit was viewed and approved by FCDO. The audit concluded that project financial reporting was accurate in all material respects and was in compliance with grant agreement between AGRA and FCDO. Some minor weaknesses in internal control were identified, which did not impact overall AGRA financial performance and have been addressed.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

1. This Annual Review was led by a member of the Africa Economic Development Group with support from a member of APEX’s Operational Excellence Group. Partner reporting formed the basis of the Output reporting, supplemented but questionnaires and programme visits.
2. AFTR does not have a dedicated monitoring, evaluation and learning (MEL) supplier. Monitoring is instead conducted by the programme team directly, with additional verification being conducted through discrete monitoring deliverables commissioned from the APEX-wide Third-Party Monitoring Programme (TPM). The most recent commission from TPM was in FY 21-22. TPM ended in December 2024, although a successor programme is currently being procured.
3. As part of their roles, FCDO programme staff frequently travel to the sites of AFTR investments, providing assurance on the veracity and effect of FCDO investments. FCDO and AFTR also meet quarterly for a programme progress discussion, with monthly meetings around the finance component.
4. The programme SRO visited Kampala as part of the AU’s Kampala Summit given FCDO support and in conjunction with the PRO made two additional visits during the period to West Africa. The first was to Cote d’Ivoire where they visited and engaged cashew value chain actors. They also met food trade partners during the AfDB Annual meetings. They later visited Ghana to Chair the Partnership for Inclusive Agricultural Transformation in Africa (PIATA) in-person partners meeting and engaging with the ERO national chapter partners to understand their work programme and visited rice millers.
5. Programme management staff visited AGRA’s headquarters in March 2025, where they discussed key features of programme implementation with AGRA’s procurement, monitoring and evaluation and financial management staff. They also met with staff leading programme delivery and some downstream partners, where they received briefings on each of the major workstreams.
6. This Annual Review was created as a desk-based Annual Review, with no specific visits for field verification of work being done.

Date of last narrative financial report AGRA	Jan - June 2024 Financial Report & Annual narrative report
Date of last narrative financial report IDH	Jan - March 2021 (no funding beyond that date)
Date of last audited annual statement	Annual audited statements covering up until 31 Dec 2023 for AGRA

Glossary of Terms
AD	Africa Directorate
AfCFTA	Africa Continental Free Trade Area
AFSF	Africa Food Security Forum
AFTR	Africa Food Trade and Resilience Programme
APEX	Africa Programmes and Expertise Department
ARBE	Agriculture, Rural Development, Blue Economy, and Sustainable Environment
AU	African Union
B2B	Business-to-Business
CAADP	Comprehensive Africa Agriculture Development Programme
CEHA	Comesa East Africa Horticulture Accelerator
COMESA	Common Market for Eastern and Southern Africa
ECOWAS	Economic Community of West African States
ERO	ECOWAS Rice Observatory
FASA	Financing for Agricultural Small-and-Medium Enterprises in Africa
FCDO	Foreign, Commonwealth and Development Office
ICF	International Climate Finance
KPI	Key Performance Indicator
MEL	Monitoring, evaluation and learning
MRA	Mutual Recognition Agreement
PPD	Eastern and Southern Africa Private Public Policy Dialogue
PEA	Political economy analysis
PIATA	Partnership for Inclusive Agricultural Transformation in Africa
REC	Regional Economic Commission
RFBS	Regional Food Balance Sheet
SEAH	Sexual exploitation, abuse and harassment
SHF	Smallholder farmer
SME	Small and medium-sized enterprises
STR	Simplified Trade Regime
TA	Technical assistance
TPM	Africa Programmes and Expertise Department Cross-Portfolio Third Party Monitoring Programme

Annex 1: Progress on Recommendations from Annual Review 2024

Recommendation	Progress
[Programme level] Given the considerable disruptions experienced by the programme (including the COVID pandemic, lockdown interruptions to activities and budget uncertainties), the FCDO team should consider whether to put in place a further no-cost extension to the programme lifetime to give implementing and downstream partners more time to deliver the Outputs, Outcomes and Impacts expected under the original business case.	Achieved. A 12-month No-cost extension was approved by FCDO which extended the programme implementation period to March 31st, 2026.
[Output 1] Noting the significant achievements already made under this Output, AGRA should undertake a review of the log frame indicator milestones for the remainder of the programme lifetime and agree with FCDO appropriate new targets which are both realistic and stretching. Consider and agree new targets by 31st December 2024.	In progress. A Target Adjustment Proposal was developed by AGRA and discussed with FCDO in March 2024. Although the recommendation was specific to output 1, AGRA took the opportunity to review all targets in the AFTR log-frame to align them with current achievements. With guidance from FCDO, the official submission of the revised log-frame to FCDO for approval was put on hold awaiting formal approval of pipeline projects and Year 8 budget.
[Output 2] AGRA should produce two knowledge management products, which provide a detailed examination of what has worked and what hasn't worked vis-a-vis the MRA and RFBS sub-grants. This should inform explicit changes in how to approach these technically and politically complex mechanisms. This should be completed by March 31st, 2025.	Achieved. Two products were created: / 1) Technical Brief: Pilot Phase of the Digital Regional Food Balance Sheet (RFBS) in Eastern and Southern Africa: Achievements, Lessons Learnt and Recommendations for Scaling in Future. / 2) Policy Brief: Documenting the Process and Lessons from Implementing Mutual Recognition Agreement (MRA) in Agricultural Trade in the COMESA region.
[Output 3] Applying lessons from the IDH endline evaluation, AGRA should outline an effective strategy to disseminate knowledge products to a varied (and relevant) base of users. Where appropriate, this strategy should make use of informal and face-to-face interactions to teach users how to get the most out of the knowledge products. This should be completed by December 31st, 2024.	Achieved. A Knowledge Management Strategy for the AFTR programme that was developed in 2022 was updated during the period under review. The strategy specifically includes an action plan for generation and dissemination of Knowledge Management Products for the AFTR programme during the period of April 2025 – March 2026.
[Output 4] Multiple projects utilise radio stations for marketing or disseminating information. However, interviews conducted as part of this annual review highlighted a lack of effort to create feedback loops to measure the effectiveness of this approach. AGRA should encourage projects using radio as means of marketing to develop methods of measuring its effectiveness – such as surveys. This should be done in time for the next annual review.	Not started. Currently there are no projects that utilize radio stations for marketing or dissemination of information funded by FCDO or any other DONOR. However, if any project of such nature will be designed in future regardless of which Donor, AGRA will put mechanisms to measure effectiveness of using radio or any mass media channel for dissemination of information.
[Output 4] AGRA should develop a plan for increasing SHF’s resilience to the effects of climate change in future projects. This should be completed by March 31st, 2025.	Achieved. The AFTR programme already has a Climate resilience framework for the Regional Food Trade and Resilience Programme which was developed in 2022. Recently, under its AGRA 3.0 strategy, AGRA has committed to integrating climate change adaptation and mitigation across all areas of its work. This integration will primarily occur through its core business lines, each addressing critical components of the food system that must adapt to climate change. These range from promoting drought-resistant seed varieties and regenerative farming practices to leveraging markets for climate-friendly goods and influencing government policy and investment decisions. This climate-focused work is anchored within the Sustainable Farming business line, where it is treated as a cross-cutting theme