## Annual Review – Lafiya Nigeria

Title: LAFIYA - UK Support for Health in Nigeria
Programme Value £ (full life): up to £235 million		Review date: 26/10/2025
Programme Code: 300495	AMP start date: 26/10/2018	AMP end date: 17/02/2027

Summary of Programme Performance
Year	2019	2020	2021	2022	2023	2024	2025
Overall Output Score	A	A	B	A	A	A+	A+
Risk Rating	Moderate	Moderate	Major	Major	Major	Major	Major

DevTracker Link to Business Case:	Business case and summary
DevTracker Link to results framework:	Logical Framework

A. SUMMARY AND OVERVIEW

Description of programme

Lafiya is FCDO Nigeria’s flagship health systems strengthening programme, due to run until 2026/27. The programme has three core aims: (1) catalyse the Government of Nigeria’s (GoN) political and financial commitment to health, particularly for the poorest; (2) improve basic health and nutrition service provision through upstream systems strengthening; and (3) increase the proportion of Nigerians using modern contraceptives, particularly women of reproductive age.

Lafiya focuses its delivery against three goals from Nigeria’s Country Business Plan (CBP) and four of the priorities set out by the Foreign Secretary for FCDO. Lafiya’s work on health system strengthening in partnership with the Government of Nigeria delivers on Goal 4 of the CBP “Strengthening Nigerian institutions through technical co-operation’ and the FCDO Priority 6 on Development. Lafiya’s work to support the Government develop its local health commodities manufacturing capabilities and to achieve benefits from demographic transition deliver on Goal 1 of the CBP “More Mutual Growth” and FCDO Priority 1 on Growth. Lafiya’s collaboration with the UK’s Department of Health and Social Case (DHSC) on health workforce migration contributes to Goal 4 of the CBP “Managed Migration and Borders” and FCDO Priority 5 on Migration. Lastly, the innovative work FCDO is supporting on Climate and Health – developing health adaptation plans, integrating health into Nigeria’s Nationally Determined Contribution 3.0, and developing a framework to improve the resilience of health infrastructure – is delivering outsized impact and aligns with FCDO’s 5th Priority on Climate and Nature.

1. Lafiya takes a ‘thinking and working politically’ approach to delivering these aims. It works with State and Federal government Ministries, Departments and Agencies (MDAs) to identify high potential policy windows for reform and provides demand-led technical assistance (TA) to catalyse progress. This is designed to work flexibly and adaptively to respond to shifts in country priorities and is explicit about ‘how political change happens’. This approach to partnership is based on mutual accountability – with Lafiya supporting the challenges and priorities identified by GoN, delivering under their leadership and direction, and ensuring we can hold each other to account for delivering jointly agreed goals.
2. Lafiya is pivotal to the UK’s bilateral health partnership with Nigeria, together with the wider programme portfolio and policy engagement. This includes expert and senior engagement in established fora, including: the Health Sector Wide Approach, Health Development Partners Group (HDPG); WASH DPG; Nutrition DPG; Demography DPG; Nigeria DPG; Key Political Partners Group (KPPG); and FCDO Nigeria’s Mutual Accountability Frameworks (MAFs) with partner States. Lafiya works closely with programme offers from other FCDO Nigeria Teams, such as the FCDO governance programme Partnership for Agile Governance and Climate Change (PACE) to maximise ability to identify and engage with policy windows, and Partnership for Learning for All in Nigerian Education (PLANE) on health and education issues such as engaging with state level budget processes and safeguarding in schools. Lafiya also collaborates and coordinates across over 15 centrally managed programmes covering health system strengthening, climate and health, Sexual Reproductive Health and Rights (SRHR) and demography (particularly with the Women’s Integrated Sexual Health Dividend Programme – WISH-D), nutrition and water, sanitation and hygiene (WASH), and health investments by the Department of Health and Social Care (DHSC) and UK Health Security Agency (UKHSA), to maximise the collective UK impact on health outcomes in Nigeria. This supports coherence across all the UK’s work in health, enabling us to present a coherent offer to Nigeria.

Lafiya also plays a key role in the wider UK-Nigeria relationship. Health exemplifies the overlap between Nigeria’s asks of the international community and the UK’s comparative advantage. The UK and Nigeria have also built up a strong relationship of trust over more than 20 years of unbroken UK health programming and engagement. As a result, health is consistently in the top three asks State governors make of the UK, and is a major component of our engagement at the Federal level. The UK’s commitment to support the implementation of President Tinubu’s Health Sectoral Renewal Investment Initiative was part of the Nigeria-United Kingdom Strategic Partnership developed in November 2024. These relationships not only underpin the high ‘Value for Money’ (VfM) of Lafiya, but also support the wider UK-Nigeria relationship – to the benefit of both countries.

Lafiya currently has three core components through which it delivers its aims:
1. ‘Health systems strengthening’ contract with Palladium: Delivering Technical Assistance to Federal, State and local government area (LGA) partners covering 138 LGAs in five focus States (Kaduna, Kano, Jigawa, Borno and Yobe), but with a wider lighter offer in several other States for catalytic and transformational support.
2. Global Financing Facility (GFF) MoU through an administrative agreement: providing funding into a multi-donor trust fund to the World Bank ‘HOPE PHC’ programme which has been set up to support the Health Sector Wide Approach in Nigeria.
3. ‘Family planning’ Memorandum of Understanding (MoU) with UNFPA: supporting the procurement of contraceptives through a basket fund approach. There is no allocated budget for this component, but as a high value investment, it is activated to enable rapid high impact spend where additional funding becomes available.
Changes in the operating context
The implementation of the new Health Sector Wide Approach (SWAp) has enabled better coordination by the Government of development partners to increase collaboration and alignment. The SWAp approach is Minister Pate’s leading reform. It aims to bring Government and development partner resources together under one health plan. It is leading to more effective and efficient use of limited resources, with more focused delivery against government target outcomes. This has required a strategic shift from Lafiya during the past two years, where it has supported key elements of the SWAp including: establishment and staffing of the SWAp Coordination Office; inauguration of its Technical Working Groups; and the development and funding of pooled financing mechanisms for TA and outcome based programming under the leadership of GoN. Moreover, it has demanded a much more collaborative approach by Lafiya both across Development Partners and with government at National and State level. FCDO’s Co Chairing of the Health Development Partners Group was a pivotal role in the SWAp, which was directly enabled by Lafiya.

The exit of USAID and reduction in development partner ODA have had a major impact on Nigeria’s health sector. Under the leadership of the Coordinating Minister for Health and Social Welfare, Professor Muhammad Ali Pate, Nigeria responded positively and nimbly to these unprecedented changes compared to many regional peers. However, there are significant impacts on delivery – particularly for HIV, Tuberculosis and Malaria service provision and prevention (though the Nigerian Government has approved $200m to procure commodities to fill some of this gap). The scale back in US funding has been compounded by announcements by other donors of planned reductions in ODA. This is leading to a new approach in development support, where government leadership must come to the fore and active planning for self-reliance is at the heart of government decision making and resource allocation. Early signs are that Nigeria, and in particular the health sector, are in a strong position to address this challenge. However, they will require support in the short term to manage this transition.

The UK is planning for the change in ODA from a commitment of 0.5% of UK GNI in FY 2025/26 to 0.3% from FY 2026/27. This will have an impact on the UK’s development portfolio in Nigeria. Given more constrained development partner funding, FCDO and Lafiya are working to maximise the impact of Government spend, particularly by positioning and pooling our resources behind the Government’s HOPE PHC programme (funded through a World Bank loan and Development Partner funding) which principally utilises disbursement linked indicators to incentivise Government delivery at Federal and State level. The Lafiya programme is also refocusing on areas of priority for the GoN, which are aligned with the HOPE PHC programme and identified through consultation with GoN partners.

The Government of Nigeria has stated a strong commitment to increased local manufacturing of health commodities. This policy has been backed up with legislative changes to enable stronger local investment in manufacturing, with tough decisions made in government procurements to stimulate local markets. This policy also aligns with the UK Government and British High Commission focus on growth. Lafiya has already started to shift its work portfolio through its support for the Presidential Initiative for Unlocking Value Chain (PVAC) to open private sector markets and strengthen local manufacturing, as well as collaboration with the UK National Institute for Health and Care Excellent (NICE) supporting the National Health Insurance Agency (NHIA) to build its capacity on Health Technology Assessment.
Partner Performance
Lafiya implementing partners continue to deliver strong results, demonstrating flexibility and technical excellence in adapting to evolving sector priorities. Their focused support to the Coordinating Minister of Health and Social Welfare’s Health Sector Renewal Investment Initiative and the Sector-Wide Approach has been widely acknowledged by government stakeholders. Feedback from federal and state partners, as well as community and civil society beneficiaries, consistently highlights Lafiya-Palladium’s responsiveness and the high calibre of its technical personnel.

The Lafiya programme is consistently recognised as a visible and credible channel of UK support to Nigeria’s health sector. At both federal and state levels, the main implementing partner, Palladium, has actively promoted UK engagement—ensuring attribution is clear and serving as a trusted advocate across government structures.

Palladium continues to be recognised as a strategic and responsive partner across federal, state, and local levels. Their ability to adapt to shifting government priorities and support the Health Sector Strategic Blueprint delivered through the SWAp framework has been commended throughout the Annual Review. Despite modest state-level funding, Lafiya-Palladium consistently delivers beyond expectations and was rated satisfactorily in the June 2025 FCDO Supplier Relationship Management (SRM) scorecard.

The UNFPA-managed basket fund continues to play a role in supporting family planning commodity procurement and advocacy across Nigeria. With the government’s plan to adopt pooled procurement via PVAC and the renewed focus on financing under the FCDO-supported HOPE-PHC programme, there are important implications for UNFPA’s operational model that warrant consideration in future programming. UNFPA has consistently maintained high performance throughout the life of the Lafiya programme, contributing meaningfully at both federal and state levels.

The Government of Nigeria’s HOPE PHC programme, is financed through a World Bank loan and partner contributions. Utilising the Global Financing Facility (GFF), it is the main mechanism through which development partners can pool financing behind GoN health sector reform plans. The UK has already committed £15.8million through this mechanism, including £4.4million to support a TA Pooling and Coordination Mechanism, which will be jointly led by Government and Development Partners. While financial reporting is pending due to delays in the external borrowing plan’s approval through Government of Nigeria systems, much of the ‘readiness’ work that was planned for the first year of the programme has already been achieved. We will be tracking progress closely with government and partners and aligning Lafiya support to help government meet the Disbursement Linked Indicator targets. This will deliver a health sector transformation with direct impact on the health and life expectancy of women and children.
FCDO management of the programme
Strategic direction and leadership of Lafiya is led by the programme SRO, the senior health adviser, who reports to the Human Development and Demography Block (HDDB) Lead. The SRO is supported by a (Lafiya) programme-funded health adviser, an (Ending Preventable Deaths Support) programme-funded health adviser, a programme manager, deputy programme manager, and two programme officers.

Quarterly performance review meetings are held with the FCDO programme management team, and the Lafiya programme implementing team to review progress against performance indicators, finance profile, and to identify and discuss challenges and opportunities for the delivery of the programme. FCDO also has quarterly performance review meetings with Palladium.

At the sub-national level, Lafiya has been a key part of the Mutual Accountability Framework (MAF) approach with States. This has been critical in both delivering on the priorities set out in the MAF, and also in maintaining and sustaining strong relationships with our State government partners. The FCDO Nigeria sub-national team has also been important in supporting the programme through its established presence and relationships at the State level. Over the past 12 months, there have been regular and proactive interactions between the Lafiya programme and the sub-national team. The sub-national team have also been part of all FCDO field visits and performance review meetings related to Lafiya.

The consolidated risk register is reviewed quarterly at a dedicated internal session as part of risk management processes. Additionally, risk status and mitigation actions are reviewed quarterly with Palladium. Day to day risk management is coordinated by FCDO programme management staff, with risks escalated as required.

Summary supporting narrative for the overall score in this review

Lafiya continues to perform at a high level. FCDO has remained a steady and reliable partner to the Nigerian Government during a period of significant reform and transition. Whilst this year has seen significant upheaval and a scale back of Development Partner support (most significantly USAID withdrawal), FCDO’s leadership and consistent engagement has been critical, which has been enabled through the Lafiya programme. Lafiya’s top achievements this year include: continuing and scaling up support for the design and implementation of the Sector-Wide Approach (SWAp); helping states improve planning and resourcing via the Annual Operation Plan process; strengthening civil society organisations to improve health budget transparency and accountability; scaling up ethical financing institutions to provide community level financing; supporting the National Health Insurance Agency (NHIA) with health technology assessments through collaboration with UK’s National Institute of Health and Care Excellence (NICE); advancing local manufacturing ambitions through support to PVAC; supporting Nigeria’s drive on climate and health resilience and sustainably; and navigating political systems to establish state-level Centres for Disease Control (CDCs).

Lafiya’s flexible support to Minister Pate and the Government has made it a valued and effective partner. This aligns with the UK’s approach to modern development partnerships. During the Annual Review, Stakeholders engaged at both federal and state levels underscored Lafiya’s adaptability and strategic alignment with government-led initiatives, which significantly accelerated the achievement of targeted outcomes. At the Federal level, Lafiya’s support for the Minister’s vision of a Sector Wide Approach (SWAp) has been instrumental in the design, operationalisation and implementation. UK expertise and Lafiya’s perceptive approach have enabled support in areas where other partners are less engaged, such as climate and health (elevating the impact and value for money of Centrally-Managed Programme investments), improving NHIA’s value-for-money approach, and building domestic capacity for procurement and manufacturing through PVAC.

The programme retains a privileged position of trust, particularly in Kano, Kaduna and Jigawa, where it is the latest health development offer building on over two decades of uninterrupted UK support. Additionally, Lafiya remains one of the few bilateral health system strengthening programmes in Borno and Yobe. While support in these states is modest, Lafiya’s influence is significant, and results, particularly in Yobe, are delivering well beyond the size of our investments.

This review period has seen the Lafiya programme further strengthen partnership working with FCDO centrally managed programmes (CMP), driving stronger impact delivery and value for money. Lafiya is now the vehicle of delivery for investments by the Climate and Health CMP. This builds on work over the past two years, where Lafiya supported parallel investments by the CMP to ensure impact at the country level. Lafiya is also working across FCDO and UK Department for Health and Social Care (DHSC) investments in Human Resources for Health (HRH) to develop a joined-up UK offer in this space. The Women's Integrated Sexual Health Dividend (WISH-D) CMP is building on Lafiya's developed networks at a Federal and State Level to deliver TA on SRHR and demography.

Looking ahead, Lafiya should focus on implementation as Minister Pate shifts fully into delivery mode. With elections expected in March 2027, there is still a key window to achieve impact. Lafiya will continue supporting SWAp operationalisation, acting as the primary contributor to the SWAp TA pool to show proof of concept and attract investments from other bilateral and multilateral partners. It will work with Federal and State governments to ensure success of HOPE PHC and to unlock disbursement-linked indicator incentives. Lafiya will also support demand-side financing to expand health insurance coverage and increase value-for-money through Institutional building in NHIA and partnership work with NICE on health technology assessment. Lafiya will continue to build on the impressive progress made through its support to PVAC, work to establish and strengthen State level Centres for Disease Control and Preventions, and the scale up and delivery on the Climate and Health agenda.

Lafiya has performed well across all output measures. Three of the five outputs scored an A+ ‘moderately exceeded expectations’, and the remaining two Outputs scored an A ‘met expectation’. There were elements of ‘exceptional performance’, namely output 4.1, reflecting the critical and highly impactful role of Lafiya in both the establishment, and institutional and capacity building of Kano, Jigawa and Kaduna Centres for Disease Control. The overall score for this AR is therefore A+: moderately exceeded expectations.

Output	Impact weighting	Score
1. Strengthened governance for the delivery of integrated health and nutrition services	25%	A+
2. Strengthened health financing, including use of Basic Health Care Provision Fund (BHCPF) and innovative financing approaches	25%	A+
3. Strengthened health workforce and health information systems, including use of data for decision-making	20%	A
4. Improved health security through a One Health approach, including response to emergencies	15%	A+
6. Improved access to sexual and reproductive health and rights, including strengthened access and demand in north-east Nigeria, and support to accelerate the demographic transition	15%	A

Output 1: Lafiya sustained a strong performance on ‘Strengthened governance for the delivery of integrated health and nutrition service’, maintaining the gains of the previous year, and driving greater impact. It supported the Federal Ministry of Health in developing policy instruments to guide the scale-up and sustainability of subnational Departments of Family Health (DFHs), enabling their establishment in 10 states. Of particular note, Lafiya facilitated DFH approval in Kaduna. Targeted technical assistance advanced SWAp governance through the development of key instruments and thematic working groups. Subnational support improved stakeholder understanding of HOPE-PHC operations and positioned states to begin to meet Disbursement Linked Indicator (DLI) participation criteria and access associated funding.

Output 2: Lafiya continues to make remarkable progress on ‘Strengthened health financing, including use of Basic Health Care Provision Fund (BHCPF) and innovative financing approaches’, leveraging budget analysis and Civil Society Organisations (CSO) engagement to influence health sector improvements, including budget allocations. All supported states, except Jigawa, met the Abuja Declaration target, with Yobe achieving a 98% release rate – this is exceptional performance. Ethical Health Financing committees have been institutionalised in 87% of Lafiya LGAs, mobilising over ₦1 billion (£481, 927), for infrastructure, workforce expansion, and improved access to care. Lafiya has also supported health insurance reforms, enabling enrolment of over 218,000 vulnerable individuals. These efforts align with national priorities and are driving more equitable, transparent, and results-oriented financing for health.

Output 3: Lafiya met expectations on output 3 “Strengthened health workforce and health information systems, including use of data for decision-making’. During this review period, Lafiya has proactively engaged with the FCDO and DHSC Global Health Workforce Programme which, supported the development of the Federal Health Workforce Migration Policy and the Health Workforce Migration Policy implementation plan. Lafiya’s partnership with DHSC and WHO built on their long-standing relationships in states to help deliver FCDO’s Equipment Support for Health Training Institutions (ESHTI) programme. Lafiya has also been instrumental in Human Resources for Health (HRH) data collection, collation, and automation in several States, which has been critical for State and LGA level resource planning and allocation.

Output 4: Lafiya has performed very strongly again this year on ‘Improved health security through a One Health approach, including response to emergencies’, moderately exceeding expectations. Notable successes this year include securing executive approvals to establish Kaduna and Jigawa Centre for Disease Controls (CDCs) and facilitating lesson learning from Kano State CDC to other Lafiya states. The FCDO team in Nigeria, with support from the centrally managed ‘Climate and Health’ Programme and Lafiya, are the Government of Nigeria’s key development partner on climate and health. With their expertise (unavailable elsewhere) and small amounts of funding they have supported the government to integrate health sector ambitions into their Nationally Determined Contribution 3.0 (NDC 3.0), to develop Nigeria’s first Climate Vulnerability Assessment Report, and to draft National and State Climate and Health Adaptation Plans. This is in addition to supporting the institutionalisation of the FCDO Climate Resilient Infrastructure for Basic Services (CRIBS), which supports the renovation of health and education facilities to be climate resilient.

Output 5: Lafiya has performed well on ‘Improved access to sexual and reproductive health and rights, including strengthened access and demand in north-east Nigeria, and support to accelerate the demographic transition’, meeting expectations. Our investments in the United Nations Population Fund (UNFPA) administered basket fund to supply family planning commodities remains excellent value for money. There is an expected increase in financing for family planning commodities over the next year both from government ($6m) and donors ($21m). This is a tremendous and welcome increase in family planning commodity financing. Lafiya will have less need to ‘fill gaps’ in commodity financing going forward, and will need to adjust its offer to enabling access to procured commodities. There is an opportunity for Lafiya to work with the Government and other development partners to ensure effective last mile distribution of commodities during the next review period. During this review period, Lafiya-Palladium has spearheaded efforts on increasing access to contraceptives for people with disabilities. They have also continued supporting step down training on demographic dividend to states.
Major lessons and recommendations for the year ahead

A summary of the key lessons and recommendation are detailed below (note: there is a more comprehensive set of lessons and recommendations in section C)

Lesson 1: PVAC’s progress underscores that unlocking Nigeria’s healthcare value chain requires not only investment and infrastructure but also sustained technical assistance, policy reform, and capacity building—particularly at subnational levels where implementation bottlenecks persist.

Recommendation 1: Lafiya should deepen collaboration with PVAC through targeted support in regulation, workforce development, and procurement systems; advancing PVAC’s goals while contributing to the UK Government’s growth agenda through improved health outcomes, job creation, and expanded local manufacturing linked to UK investment opportunities in health.

Lesson 2: Institutionalising Health Technology Assessment (HTA) in Nigeria is critical for evidence-based decision-making, but current capacity gaps, particularly in data systems, regulatory alignment, and technical expertise, limit NHIA’s ability to implement HTA effectively and sustainably.

Recommendation 2: Lafiya to sustain collaboration with NICE in delivering targeted technical assistance, capacity building, and policy support to NHIA, focusing on regulatory harmonisation, data systems strengthening, and stakeholder engagement. This partnership will help operationalise HTA, and improve health system efficiency by enabling transparent, evidence-driven health investments and expanding opportunities for UK-linked innovation and partnerships.

Lesson 3: Nigeria’s Nationally Determined Contributions (NDC) 3.0 marks the first-time health sector ambitions were integrated into Nigeria’s NDC and also marks the country out as a global leader in this respect. Moreover, the development and launch of Nigeria’s first Climate and Health Vulnerability and Adaptation Assessment and its first Health National Adaptation Plan (HNAP) followed by extensive work across States to develop their own Climate and Health Adaptation Implementation Plans, presents a strategic opportunity to mobilise climate financing (Green Climate Fund, Adaptation fund, HOPE PHC DLIs etc) for health sector investments in climate adaptation and mitigation. Increased Lafiya support working with the FCDO PACE programme can play a catalytic role in operationalising these ambitions by strengthening systems, enhancing coordination, and building capacity at subnational levels.

Recommendation 3: Lafiya to collaborate with FCDO’s PACE programme to deliver technical assistance and policy support essential for mobilising climate and global health funding needed to support implementation of Nigeria’s NDC 3.0 and HNAP, advancing climate-resilient health systems and national commitments under the Paris Agreement and SDGs.

Lesson 4: Lafiya’s support to civil society organisations in advocating for improved health sector allocations and transparency in fund utilisation is delivering results. However, poor budget performance and low releases at the subnational level persist, largely due to limited technical capacity in budget planning, weak intersectoral coordination, and insufficient advocacy for health prioritisation during budget cycles.

Recommendation 5: Lafiya should support subnational governments by facilitating joint planning with finance and planning ministries, further strengthening budget advocacy and execution capacity, and promoting real-time budget tracking.

Lesson 6: Lafiya’s support in establishing coordination mechanisms—through the SWAp Coordinating Office and Technical Working Groups—is helping to unify fragmented health financing efforts. This underscores the importance of strong institutional frameworks and committed leadership as foundations for sustainable financial reform.

Recommendation 6: Lafiya should continue supporting the SWAp Coordination Office to sustain coherence in health financing but also assess how the SWAp mechanism translates to tangible improvements in the transparency, efficiency and equity of health financing flows.

Lesson 7: In 2025, Government and Development Partner commitments for family planning commodities rose to $6m and $21m respectively, with procurements currently in progress. The Government’s $6m pledge will unlock $5m via HOPE PHC Disbursed Linked Indicators (FCDO has already committed £15.8million to HOPE PHC and is a member of the National Steering Committee for the SWAp/HOPE-PHC). These commitments help close the funding gap, but success depends on timely procurement and efficient distribution.

Recommendation 7: Lafiya partners should collaborate with the Federal and state governments and development partners to ensure effective last mile distribution. They should also support states in addressing stockout data issues and build capacity for data collection where needed.

Lesson 8: There is the risk of a delay in distribution of family planning commodities, due to the e Government’s plan to only procure through government procurement channels.

Recommendation 8: UNFPA, Lafiya-Palladium, and partners should support PVAC to ensure timely procurement and avoid stockouts. Lafiya-Palladium should also assess how state procurement aligns with the Federal PVAC system.

Lesson 9: The Coordinating Minister for Health and Social Welfare has driven real transformation in the health sector, and the UK is seen as a trusted and consistent partner. Through its expertise, flexible funding and leadership, the UK has demonstrated commitment to health sector reform through the SWAp and should remain a reliable partner in the short and medium term.

Recommendation 9: Given the scale of reform and the UK’s longstanding role in Nigeria’s health sector, the Lafiya programme should consider options for an extension beyond its current programme close date.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

The Lafiya log-frame has undergone multiple revisions since the original business case, with the most significant changes following the 2022 Annual Review. Subsequent adjustments have been minimal, affecting five output indicators—specifically Output 5 and Indicator 1.4 due to the closure of the HERON service delivery component, and Indicators 1.2, 1.3, and 2.4, which required updates following a 100% achievement of their respective milestones. The table below provides a summary of the outcome indicators, which reflect global norms where possible (e.g. SDG indicators or WHO Global Reference List of 100 Core Health Indicators).
Table 1: Summary of Lafiya Programme Outcome Indicators
Substantially increased health financing (SDG 3.c)	Outcome Indicator 1.1 / Current expenditure on Primary Health Care as a percentage of Current Health Expenditure (CHE) (national and State level) (under SDG 3.c) / (Source - FMoH National Health Accounts)
	Outcome Indicator 1.2 / General government expenditure on health as a percentage of total government expenditure (national level) (under SDG 3.c) / (Source - State-level budget and expenditure reports)
Improved coverage of integrated essential health services and health emergency preparedness (SDG 3.8 and SDG 3.d)	Outcome Indicator 2.1 / Proportion of births attended by a skilled birth attendant (national and State level: Kano, Kaduna, Jigawa, Borno, Yobe) (SDG 3.1.2) / (Source – MICS/NDHS Report)
	Outcome Indicator 2.2 / Proportion of women in targeted States who have a postnatal check during the first two days after birth. / (Source – MICS/NDHS Report)
	Outcome Indicator 2.3 / Proportion of LGAs with functional EPR committees in focus States (Kano, Kaduna, Jigawa, Borno, Yobe) / (Source – Program data)
Improved access to sexual and reproductive health services (SDG 3.7)	Outcome Indicator 3.1 / Proportion of women aged 15-49 who have their need for family planning satisfied with modern methods (national and State level: Kano, Kaduna, Jigawa, Borno, Yobe) (SDG 3.7.1) / (Source – MICS/NDHS Report)
	Outcome Indicator 3.2 / Adolescent birth rate (per 1000 women) (national and State level: Kano, Kaduna, Jigawa, Borno and Yobe) (SDG 3.7.2) / (Source – MICS/NDHS Report)

The impact indicators for Lafiya reflect standard metrics used in health systems strengthening programmes and align with the UK’s commitment to ending the preventable deaths of mothers, babies and children. However, these indicators should be interpreted within the broader determinants of health—including nutrition, WASH, education, income, and the socio-environmental context. Over the life of the programme, trends in the following indicators should be viewed through this lens:
    1. Maternal mortality ratio (MMR) (SDG 3.1.1)
    2. Under 5 mortality rate (U5MR) (SDG 3.2.1)
    3. Neonatal mortality rate (NMR) (SDG 3.2.2)
    4. Out of pocket expenditure on health, as a percentage of Current Health Expenditure (under SDG 3.c)

The revised 2023 Theory of Change (ToC) presented in Figure 1 below reflects the Lafiya programme’s strategic potential within the constraints of reducing UK ODA.

Figure 1: Lafiya theory of change (2023)

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

In November 2024, the National Demographic and Health Survey (NDHS) Key Indicators’ Report was released, with the final comprehensive version expected later in 2025. While some indicators fell short of targets—largely due to the ambitious benchmarks set in national and state Strategic Health Development Plans—measurable progress was recorded across core health indicators in most Lafiya-supported States compared to the 2018 baseline. Skilled birth attendance improved across all Lafiya States, with Yobe, Borno, and Kano demonstrating consistent gains across all outcome indicators. Borno and Jigawa achieved exceptional improvements in postnatal care, exceeding the national average by 43% while the national adolescent rate declined by 27% (See illustrations in Figure 1 indicative of percentage point changes in outcome indicators based on NDHS findings from 2018 to 2024)

Figure 1: Table Illustrating Percentage Point Changes in Outcome Indicators from the NDHS Survey Report (2018–2024)

Government health expenditure reflects its commitment to Universal Health Coverage and improved public health outcomes. Nigeria’s 2022 National Health Accounts show that current expenditure in Primary Health Care accounts for 44.46% of Current Health Expenditure (CHE), while General Government Health Expenditure (GGHE) represents only 7.4% of General Government Expenditure (GGE).This places Nigeria below many African countries of similar context, where GGHE ranges from 2.1% to 12%, with only South Africa meeting the Abuja Declaration target of 15%. This underscores both the opportunity and constraint for Lafiya implementation, highlighting the need for continued strategic alignment with national priorities, advocacy for efficient resource use, and strengthened coordination to maximise impact within a constrained fiscal space.
[note] WHO African Region Health Expenditure Atlas 2023

Table 2 presents progress against outcome indicator milestones, where data is available,

Indicator(s)	Baseline (2021)	Milestone(s) for / this review / (2024)	Progress
Outcome Indicator 1.1 / Current expenditure on Primary Health Care as a percentage of Current Health Expenditure (CHE) / (national and state level) / (under SDG 3.c) / (Source - State Health Accounts)	National - 55.5% Kaduna - 33% / Kano - 47%	National – 61.5% / Kaduna - 41% / Kano - 53%	Off track: / National – 45.46% (2022) / Kaduna - 16% / Kano -29.4% / (Review date: 2017-2022)
Outcome Indicator 1.2 / General government expenditure on health as a percentage of total government expenditure (national level) (under SDG 3.c) / (Source - State-level budget and expenditure reports)	4.5%	6.0%	On track / 7.4% (2022)
Outcome Indicator 2.1 / Proportion of births attended by a skilled birth attendant (national and state level:Kano, Kaduna, Jigawa, Borno, Yobe) (SDG 3.1.2) / Source – MICS (Baseline) and DHS surveys) / NDHS 2023-24 Report	National - 50.7% / Borno - 32.3% Jigawa - 22.2% / Kaduna - 42.7% / Kano - 27% Yobe - 47.5%	National – 51.8% / Borno - 61.7% / Jigawa - 27.9% / Kaduna - 47.2% / Kano - 34.6% / Yobe - 51.2%	Off track / National – 45.9% / Borno - 37.7% / Jigawa – 24.6% / Kaduna – 35.6% / Kano – 36.3% / Yobe – 35.4%
Outcome Indicator 2.2 / Proportion of women in targeted states who have a postnatal check during the first two days after birth. / Source – MICS (Baseline) and DHS surveys) / NDHS 2023-24 Report	National - 61.4% Borno - 38.7% Jigawa - 26.2% / Kaduna - 55.1% / Kano - 61.8% Yobe - 47.1%	National - 69.6% / Borno - 40.9% / Jigawa - 28% / Kaduna - 62.4% / Kano - 63.4% / Yobe - 50.5%	Mixed progress / National - 42.3% North West - 23.9% North East - 35.4% / Borno - 45% / Jigawa - 41.4% / Kaduna - 23.6% / Kano - 30.1% / Yobe - 33%
Outcome Indicator 2.3 / Proportion of LGAs with functional Emergency Preparedness and Response (EPR) committees in focus states / (Kano, Kaduna, Jigawa, Borno, Yobe) / (Source – Program data)	Borno - 15% / Jigawa - 0% / Kaduna - 0% / Kano - 0% / Yobe – 0%	All LGA EPR committees implement at least 50% activities from the EPR committee plans in line with the State Action Plan for Health Security	On track / ALL (average) - 100% Borno - 100% / Jigawa - 100% / Kaduna - 100% / Kano - 100% / Yobe - 100%
Outcome Indicator 3.1 / Proportion of women aged 15-49 who have their need for family planning satisfied with modern methods (national and state level: Kano, Kaduna, Jigawa, Borno, Yobe) (SDG 3.7.1) / Source – MICS (Baseline) and DHS surveys) / NDHS 2023-24 Report	National - 39.9% Borno - 38.2% / Jigawa - 9.5% / Kaduna - 36.6% / Kano - 37.4% Yobe - 37.7%	National - 40.2% / Borno - 40.9% / Jigawa - 12.1% / Kaduna - 40.9% / Kano - 43% / Yobe - 41.5%	Off track / National - 43.7% North East - 34.9% North West - 30.2% / Borno - 25.9% / Jigawa - 19.1% / Kaduna - 36.6% / Kano - 28.5% / Yobe - 22.9%
Outcome Indicator 3.2 / Adolescent birth rate (per 1000 / women) (national and state level: Kano, Kaduna, Jigawa, Borno and Yobe) / (SDG 3.7.2) / Source – MICS (Baseline) and DHS surveys) / NDHS 2023-24 Report	National - 75 / Borno - 100 / Jigawa - 156 / Kaduna - 103 / Kano - 93 / Yobe – 76	National - 66 / Borno - 92 / Jigawa - 148 / Kaduna - 83 / Kano - 78 / Yobe - 33	Off track / National - 77 / Data available only at national level

Whilst the performance against outcome indicators is poor, there is recognition that delivering progress on outcome level indicators is outside the direct influence of the programme. Outcome indicators require long term continued strategic engagement. Nevertheless, performance against the output indicators has been very positive, demonstrating Lafiya’s ability to manage multiple pressures, react to a changing and complex environment and still deliver at the Federal and State level across a diverse set of measures. According to the mid-term evaluation report (MTR) of Lafiya published in January 2025, the program has proven to be a resilient, catalytic force in Nigeria’s health sector, delivering strategic reforms and fostering inclusive, sustainable health systems. The MTR stated that to continue delivering value for money and positive health impacts, Lafiya must now scale smartly, deepen partnerships, and align more closely with emerging national priorities such as the Sector-Wide Approach (SWAp), MAMII, and HOPE PHC initiatives —especially at the local level—while maintaining its core strengths in adaptability, equity, and systems thinking. Key opportunities include expanding support to additional states, strengthening governance at the increasingly autonomous LGA level, enhancing workforce development, reinvigorating private sector engagement, and supporting health security through subnational CDCs. By leveraging its flexible model, strategic partnerships, and community-driven approaches, Lafiya can continue to deliver sustainable reforms and support the improvement of health outcomes for Nigeria’s most vulnerable populations.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
The Lafiya programme continues to demonstrate strong value for money, with notable flexibility in aligning with government priorities and adapting to Nigeria’s evolving health context. Since the introduction of the Health Sector Wide Approach (SWAp), Lafiya has played a pivotal role in supporting the design and implementation of this new framework. The Lafiya team recognise the need for deeper systemic reforms to accelerate progress and improve health outcomes for Nigerians. Lafiya directly supports federal and state health sector ambitions and remains responsive to emerging priorities such as HOPE PHC, Health Technology Assessment, PVAC, and climate-health policy, financing and delivery. Sustained stakeholder engagement and government ownership further enhance the programme’s effectiveness and likelihood of achieving its intended results.

From a UK strategic alignment perspective, the Lafiya programme continues to advance the Foreign Secretary’s priorities on inclusive growth and development, and personifies a ‘modern development partnership’. It supports Nigerian-led reforms and systems strengthening for a transition to self-reliance, while promoting rights, equality, and the empowerment of women and girls. Lafiya also contributes to key development outcomes, including: accelerating demographic transition through support for sexual and reproductive health and rights; addressing drivers of instability by improving basic service delivery; enhancing climate resilience via strengthened and adaptative health systems; improving domestic resource mobilisation through the Basic Health Care Provision Fund (BHCPF) and ethical health financing at the subnational level; and driving economic growth through investments in human capital.

The programme continues to strengthen system-wide change across federal, state, LGA, facility, and community levels, promoting sustained coordination and reform. Lafiya has supported technical and administrative processes enabling states to access funding through the Basic Health Care Provision Fund (BHCPF), while complementing this with efforts to mobilise private sector and philanthropic resources through pioneering the Ethical Health Financing Initiatives such as the Waqf. This initiative is driving insurance enrolment for vulnerable groups, scholarships for community health workers, and capital investments—laying the groundwork for long-term self-reliance. Lafiya also provides technical assistance to advance the Sector-Wide Approach (SWAp), with notable progress including the operationalisation of governance structures (SWAp Coordination Office, TWGs) and development of key documents (ToRs, Code of Conduct, SWAp playbook), which have strengthened coordination, accountability, and integrated service delivery. Its embedded partnerships, upstream policy influence, and value-for-money orientation have positioned it as a trusted and impactful actor in Nigeria’s health sector.

Over the reporting period, Lafiya has actively supported FCDO centrally managed programmes (CMPs) and other UK government department (OGD) initiatives to maximise their impact at country level. This has involved strategic relationship management with government and partners, and flexible resource deployment to accelerate progress and address operational bottlenecks - particularly in climate and health. As the designated ‘docking’ programme for UK health ODA in Nigeria, Lafiya plays a central coordinating role across a broad portfolio, covering UK bilateral and centrally managed programmes. It has also become a key enabler of strategically important multilateral health funding, particularly where there is limited in country presence, most notably GAVI and the Global Fund. This integrated approach has significantly enhanced coordination, delivery, and the strategic positioning of UK health investments in Nigeria.

The strong recommendation emerging from this Annual Review is the continued positioning of the Lafiya programme as the central pillar of the UK’s health partnership with Nigeria. Its strategic role in driving system-wide reforms, coordinating health ODA, and delivering impactful results across priority areas reinforces its value as a flagship platform for advancing shared UK–Nigeria health objectives. The programme should be extended to consolidate current gains achieved so far and reinforce the UK’s position as a reliable partner to the Nigerian government.

## C. DETAILED OUTPUT SCORING

Output Title	Strengthened governance for the delivery of integrated health and nutrition services
Output number:		1	Output Score:	A+
Impact weighting (%):		25%	Weighting revised since last AR?	Yes, previously 20%

Indicator(s)	Milestone(s) for this review	Progress
1.1 Targeted policy windows where technical assistance could catalyse health governance reform at Federal and State level identified, discussed with FCDO, implemented, and evaluated (Palladium)	Policy advocacy and TA provided to establish State Departments of Family health (DFH) in at least two Lafiya supported States.	Score: A+ exceeded expectation / With support from the Lafiya programme, Kaduna State secured formal approval to establish a Department of Family Health (DFH), increasing the number of Lafiya-supported states with DFH structures (Jigawa, Yobe, and Kaduna) to three out of five receiving federal-level assistance. / Borno has appointed a focal person to oversee RMNCAEH+N initiatives, with the DFH proposal currently pending approval. / Lafiya health governance reform impact went well beyond milestone, also making significant contributions and achievements in the delivery of the SWAp, supporting PVAC agenda and setting up HTA.
1.2 Proportion of LGAs in target States with functional RMNCAH+N coordination committees (Kano, Kaduna, Jigawa, Borno, Yobe) (Palladium)	ALL (average) - 100% / Borno - 100% / Jigawa - 100% / Kaduna - 100% / Kano - 100% / Yobe - 100%	Score: A met expectation / ALL (average) - 100% / Borno - 100% / Jigawa - 100% / Kaduna - 100% / Kano - 100% / Yobe – 100%
1.3 Proportion of LGAs in target States with functional primary health care (PHC) advisory committee (Kano, Kaduna, Jigawa, Borno, Yobe) (Palladium)	ALL (average) - 100% Borno - 100% / Jigawa - 100% Kaduna - 100% / Kano - 100% / Yobe - 100%	Score: A met expectation / ALL (average) – 100% / Borno – 100% / Jigawa – 100% / Kaduna – 100% / Kano –100% / Yobe – 100%

Briefly describe the output’s activities and provide supporting narrative for the score.

Lafiya has performed well in this output area. Lafiya supported the Federal Ministry of Health in developing policy instruments to guide the scale-up and sustainability of subnational Departments of Family Health (DFHs) and Reproductive, Maternal, Neonatal, Child, Adolescent, and Elderly Health and Nutrition (RMNCAEH+N) multi-stakeholder coordination platforms. These tools enabled DFH establishment in 10 states, laying the foundation for dedicated budget lines and expanded service delivery.

At the state level, Lafiya facilitated DFH establishment in Jigawa, secured DFH approval in Kaduna, and supported the appointment of a RMNCAEH+N Coordinator in Borno. Lafiya has also facilitated cross-state learning among newly established DFHs in target and non-target states. These subnational structures are critical to driving, institutionalising and sustaining RMNCAEH+N coordination at the state level. Lafiya’s support has contributed to measurable improvements in maternal health outcomes, as reflected in quarterly scorecard ratings.

Lafiya continues to support LGA Primary Health Care Advisory Committees across the five Lafiya states. While implementation of LGA financial autonomy appears to have slowed due to resistance at various levels, the Supreme Court ruling remains in effect. In anticipation of future operationalisation, these committees are well-positioned to address challenges in PHC delivery.

Targeted technical assistance has advanced SWAp governance, including development of Terms of Reference, a Code of Conduct, and a SWAp playbook. These efforts have strengthened coordination, accountability, and integrated service delivery. Lafiya helped establish TWGs on Monitoring and Evaluation, Human Resources for Health, Health Security, and Resource Coordination. At the subnational level, Lafiya supported SWAp secretariats to enhance stakeholder understanding of HOPE PHC operations and Disbursement Linked Indicators (DLIs) and contributed to the development of Annual Operational Plans (AOPs) aligned with the 2024–2027 Health Sector Strategic Blueprint. This support enabled states to meet participation criteria for a HOPE DLI and contributed to the first-ever harmonised National Health Sector AOP.

In line with its flexible delivery model, Lafiya collaborated with the National Institute of Clinical Excellence (NICE) UK to support the National Health Insurance Authority (NHIA) in institutionalising Health Technology Assessment (HTA) within Nigeria’s health system. To guide implementation, Lafiya supported the development of an HTA Roadmap and a draft National HTA Framework, now ready for finalisation. This initiative aims to strengthen evidence-informed decision-making, optimise resource allocation, and enhance the quality and efficiency of healthcare services with the aim of realising Universal Health Coverage for the Nigerian population.

Lafiya is actively supporting the Presidential Initiative for Unlocking the Value Chain (PVAC) through embedded technical assistance. This engagement focuses on strengthening Drug Management Agencies (DMAs) in procurement, logistics, and manufacturing readiness, aligning with the Medipool strategy and contributing to curriculum development for the proposed manufacturing academy. Looking ahead, Lafiya will support PVAC in advancing both Nigeria’s and the UK’s mutual growth agenda by strengthening Nigeria’s health market and promoting inclusive economic development. Through policy, regulatory, and coordination support, Lafiya aims to de-risk investments, accelerate local manufacturing, and promote inclusive economic development—positioning Nigeria as a regional health hub and fostering UK-linked partnerships.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Since the last annual review, output indicators 1.2 and 1.3 have achieved 100% completion. Ahead of the next review period, FCDO and partners will reassess these indicators to ensure they continue to drive ambitious performance and maintain programme relevance and impact.

Progress on previous AR recommendations

Following recommendations from the last annual review, Lafiya conducted a diagnostic to assess the immediate and long-term implications of Local Government budget autonomy on primary healthcare delivery. Lafiya-supported state level dialogues that revealed critical issues including lack of clarity on Local Government roles, limited state-level commitment to decentralization, and slow federal implementation. Lafiya has continued to support LGAs through targeted capacity building, advocacy for harmonized funding mechanisms, and promotion of integrated service delivery models to mitigate risks and optimize the benefits of a potential autonomy transition.

A key recommendation was for the FCDO Health and Governance teams to convene a joint session with leads from the new FCDO governance programme (PACE) and the Lafiya programme to identify opportunities for collaboration. Whilst this proposed engagement is still to happen, Lafiya continues to engage closely with the PACE team at the subnational level, complementing efforts to support government through collaboration on the Kaduna State Climate Change Bill, the Medium-Term Expenditure Framework, and budget tracking initiatives.

The other key recommendation from the last annual review was for Lafiya and FCDO to revise Output Indicator 1.2 to reflect a stronger focus on supporting the functionality, sustainability, and effectiveness of RMNCAH+N coordination committees. In response, Lafiya has proposed the development of Capacity Development Plans and the introduction of an Organizational Capacity Assessment (OCA) tool to track progress, with quarterly reporting through case studies. A similar ‘stretch’ approach has been proposed for Output Indicator 1.3, aimed at further strengthening the RMNCAEH+N committees to sustain delivery at scale. FCDO and Lafiya must prioritise the review of these indicators within the next six months to ensure timely alignment with programme objectives and prevent delays in implementation.
Lessons learned and recommendations for year ahead
Lesson 1.2: PVAC’s progress underscores that unlocking Nigeria’s healthcare value chain requires not only investment and infrastructure but also sustained technical assistance, policy reform, and capacity building—particularly at subnational levels where implementation bottlenecks persist (such as weak institutional capacity to manage procurement and logistic, limited technical capacity and resistance to reform).

Recommendation 1.2: Lafiya should deepen collaboration with PVAC through targeted support in regulation, workforce development, and procurement systems—advancing PVAC’s goals while contributing to the UK Government’s growth agenda through improved health outcomes, job creation, and expanded local manufacturing linked to UK investment opportunities in health.

Lesson 1.3: Institutionalising Health Technology Assessment (HTA) in Nigeria is critical for evidence-based decision-making, but current capacity gaps—particularly in data systems, regulatory alignment, and technical expertise—limit NHIA’s ability to implement HTA effectively and sustainably.

Recommendation 1.3: Lafiya to sustain collaboration with NICE in delivering targeted technical assistance, capacity building, and policy support to NHIA—focusing on regulatory harmonisation, data systems strengthening, and stakeholder engagement. This partnership will help operationalise and institutionalise HTA, and improve health system efficiency by enabling transparent, evidence-driven health investments and expanding opportunities for UK-linked innovation and partnerships.

Lesson 1.4: Reductions in programme scope driven by ODA funding cuts and strategic reprioritisation have heightened the importance of managing expectations among stakeholders.

Recommendation 1.4: Lafiya to proactively strengthen stakeholder engagement and communication with government and other partners to mitigate reputational risks linked to the programmes’ narrowing scope. This will involve a clear and transparent communication of the factors driving the reduced scope and a demonstration of how remaining interventions align with national health priorities.

Output Title	Strengthened health financing, including use of Basic Health Care Provision Fund (BHCPF) and innovative financing approaches
Output number:		2	Output Score:	A+
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Targeted policy windows where technical assistance could catalyse improvements in health financing at Federal and State level identified, discussed with FCDO, implemented, and evaluated (Palladium)	TA provided civil society and non-state actors to conduct evidence-informed advocacy (e.g. using health budget analysis) to increase and sustain health budgets as reflected in the FCDO MAF agreements with partner states.	Score: A+ (Exceeded expectations) / Lafiya produced and presented the 2024 FGN Health Sector Budget Brief and Budget Analysis to the Development Partners’ Forum. / Lafiya supported Annual Operation Plan refinement, as well as accountability efforts, contributing to notable health budget increases in Yobe (15.2%), Kano (15.18%), Borno (15.3%) and Kaduna (16.1%) States. / Quarterly performance reviews were facilitated to strengthen planning and ensure adequate budget provisions for achieving Disbursement Linked Indicators (DLIs).
2.2 Proportion of designated BHCPF facilities that receive direct facility financing disbursements on time in line with the BHCPF operational guidelines (Kano, Kaduna, Jigawa, Borno, Yobe) (Palladium)	All (average) - 100% / Kano - 100% / Kaduna -100% / Jigawa - 100% / Yobe - 100% / Borno - 100%	Score: A (met expectations) / All (average) – 100% / Kano – 100% / Kaduna – 100% / Jigawa – 100% / Yobe – 100% / Borno – 100%
2.3 Proportion of LGAs that have implemented ethical financing to support basic service delivery (Kano, Kaduna, Jigawa, Borno, Yobe) (Palladium)	ALL (average) - 80% / Borno - 80% / Jigawa - 80% / Kaduna -80% / Kano - 80% / Yobe - 80%	Score: A+ (Moderately exceeded expectations) / ALL (average) – 87% / Borno – 100% / Jigawa – 81% / Kaduna – 82% / Kano – 81.8% / Yobe – 88%

Briefly describe the output’s activities and provide supporting narrative for the score.

Lafiya continues to perform strongly on this indicator, leveraging opportunities to engage on budget analysis to influence sector improvements, and sustaining advocacy through enabling stronger CSO engagement. All Lafiya-supported states, except Jigawa, have met the Abuja Declaration target of 15% health budget allocation, with Yobe achieving a 98% release rate in 2024 – an impressive result. Further analysis is required to assess budget performance rates in Borno, Jigawa, Kano, and Kaduna to ensure allocations translate into actual disbursements.

Lafiya’s support to civil society has strengthened state-level accountability through targeted advocacy capacity building, with notable success in mechanisms like the Kano State Ministry of Health, in collaboration with the Kano State-Led Accountability Mechanism (KanSLAM). By enabling CSOs and community structures to engage in budget processes and service delivery tracking, the programme has increased health sector ambition across focal states. As SWAp implementation progresses, sustaining civil society engagement will be critical to ensuring transparency, responsiveness, and improved health outcomes.

Lafiya continues to support facility-level planning and access to BHCPF disbursements through quarterly business and improvement plans, enhancing service delivery, and data use. At the national level, Lafiya has supported the BHCPF Ministerial Oversight Committee (MOC) Secretariat in reviewing and validating the BHCPF 2.0 guidelines, now approved for dissemination. As momentum builds for increased BHCPF allocation from the Consolidated Revenue Fund, Lafiya will need to work with the Ministerial Oversight Committee (MOC) Secretariat to prioritise resource allocation for maximum impact on service delivery and health outcomes.

Lafiya has supported the scale-up and institutionalisation of Ethical Health Financing (EHF) committees across 87% of its 138 LGAs, surpassing the 80% target. Through strategic collaboration with the International Institute of Islamic Banking and Finance (IIBF), the programme is advancing knowledge management and sustainable investment models. This support has mobilised over ₦1 billion (£481,927), enabled infrastructure development, expanded the health workforce, and improved access to care for vulnerable populations—particularly on maternal and child health. Lafiya is further embedding sustainability by integrating EHF into university training programmes, positioning the initiative for long-term delivery and impact.

Lafiya has supported health sector reform aligned with the Coordinating Minister’s vision by strengthening resource coordination at the Federal level under the SWAp framework and enhancing transparency in financing across government tiers. At the State level, Lafiya assisted contributory health insurance agencies in adapting the NHIA Act and developing strategic plans to expand coverage. In Kaduna, this included developing an Informal Sector Framework, leading to the enrolment of 5,000 vulnerable persons and a ₦745.5 million approval to enrol 70,000 more. In Jigawa, Lafiya supported the launch of the J-Basic Health Programme, an initiative aimed at providing free and accessible healthcare to the poorest and most vulnerable citizens, enabling the enrolment of 143,500 individuals across all wards.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Output Indicator 2.2 has reached 100% achievement. Considering this, FCDO and the Lafiya team to review to ensure it continues to drive programme performance ahead of the next review period. While Lafiya has suggested retaining the indicator due to its role as a payment milestone, an additional indicator is being proposed; tracking the proportion of states that have enrolled at least 80% of their target beneficiaries. This aims to sharpen focus on underperforming areas and incentivize targeted interventions to improve enrolment and service delivery.
Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead

Progress on previous AR recommendations

In response to the last AR recommendation, Lafiya collaborated with Federal and State agencies to strengthen civil society engagement within accountability frameworks. CSOs were integrated into SWAp orientations and key planning processes, including roadmap development and the 2025 Annual Operational Plan. Additionally, State Led Accountability Mechanisms (SLAMs) conducted independent BHCPF facility spot checks, enhancing transparency and accountability in the implementation of BHCPF, Drug Revolving Fund (DRF), and related health interventions.

Another recommendation was for Lafiya to ensure timely BHCPF support to facilities and enhance impact. Lafiya supported states in conducting monthly programme monitoring visits. These visits improved service quality, enabled in-situ mentoring—reducing the need for refresher trainings -and provided real-time data to state gateways, facilitating responsive decision-making and strengthening accountability in BHCPF implementation.

To sustain progress monitoring of supported Ethical Health Financing (EHF) Committees, Lafiya developed and deployed an EHF tracker, maintained by each committee’s M&E focal person. With ongoing mentorship from LGA facilitators, committees now regularly update the tracker, strengthening oversight of ethical financing practices and enhancing accountability in health service delivery.
Lessons learned and recommendations for year ahead

Lesson 2.1: Lafiya’s support to civil society organisations in advocating for improved health sector allocations and transparency in fund utilisation is moving at pace. However, poor budget performance and low releases at the subnational level persist, largely due to limited technical capacity in budget planning, weak intersectoral coordination, and insufficient advocacy for health prioritisation during budget cycles.

Recommendation 2.1: Lafiya should support subnational governments by facilitating joint planning with finance and planning ministries, strengthening budget advocacy and execution capacity, and promoting real-time budget tracking.

Lesson 2.2: Lafiya’s support in establishing coordination mechanisms, through the SWAp Coordinating Office and Technical Working Groups, is helping to unify fragmented health financing efforts. This underscores the importance of strong institutional frameworks and committed leadership as foundations for sustainable financial reform.

Recommendation 2.2: Lafiya should continue supporting the SWAp Coordination Office to sustain coherence in health financing but also assess how the SWAp mechanism translates to tangible improvements in the transparency, efficiency and equity of health financing flows.

Lesson 2.3: States often face challenges accessing innovative financing mechanisms like the HOPE PHC DLIs, Climate financing and the Child Nutrition Fund due to limited awareness, weak technical capacity, and fragmented coordination across MDAs

Recommendation 2.3: Lafiya should support states by strengthening their capacity to identify, engage with, and meet eligibility requirements for key financing opportunities.

Output Title	Strengthened health workforce and health information systems, including use of data for decision-making
Output number:		3	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Targeted policy windows / where technical assistance could catalyse improvements / in health workforce and / health information systems at federal and state level identified, discussed with / FCDO, implemented, and / evaluated (Palladium)	Policy collaboration with UK DHSC (Department of Health and Social Care) and WHO to catalyse HRH reforms and TA provided to implement the state HRH policy to improve HRH in the supported states as outlined in the FCDO MAF agreements with partner states.	Score: A (met expectations) / Facilitated the alignment of strategies between FCDO and DHSC health workforce initiatives, promoting unified action including: / Supporting the engagement of Kano, Jigawa, and Kaduna States in the FCDO’s Equipment Support for Health Training Institutions (ESHTI) programme. / Providing pivotal support for the drafting and validation of Nigeria’s health workers migration policy. Working alongside WHO and UK DHSC.
3.2 Number of supported states that maintain an updated Health Workforce Registry (Palladium)	All Lafiya supported states	Score: A (met expectations) / Supported Jigawa, Yobe, Kaduna and Borno for the update of their Health Workforce Registry and the development of HRH dashboard.
3.3 Proportion of designated BHCPF facilities that meet the minimum national data quality standards / requirements for submission of complete and timely health / information through DHIS2 / (Kano, Kaduna, Jigawa, Borno, Yobe) (Palladium)	At least 80% in Kano, Kaduna, Jigawa and at least 70% in Yobe and Borno	Score: A+ (moderately exceeded expectations) / ALL (average) – 91% / Average across Borno and Yobe - 92% / Jigawa, Kano and Kaduna – 91% / Borno - 91% / Jigawa - 100% / Kaduna - 80% / Kano - 93% / Yobe - 93%
3.4 Proportion of LGAs in target states that use data for decision-making and planning through Lafiya support (Palladium)	ALL - 100% / Kano - 100% / Kaduna - 100% / Jigawa - 100% / Yobe - 100% / Borno - 100%	Score: A (met expectations) / ALL – 100%

Briefly describe the output’s activities and provide supporting narrative for the score.

Health workforce continues to be the number one challenge for health service delivery in Nigeria. Challenges include workers that are overworked and poorly motivated. Others are high absenteeism, lack of access to basic equipment, poor and/or unsafe working environment, and poor training. Resolving these challenges is difficult due to poor data availability and a lack of coordination between different levels of governance to improve provision of human resources for health (HRH).

Lafiya supported efforts to improve health workforce data and its use in the planning process. At the Federal level, Lafiya contributed to the review and enhancement of the national health workforce tool, aligned with the 2021-2025 National HRH Policy. Ten (10) HRH officers were trained in how to use the tool, subsequently conducting Organisational Capacity Assessments across Lafiya’s five focal states. Lafiya also supported validation of updated National Health Management Information System tools.

At the state level, Lafiya supported the development and automation of HRH dashboards – improving data accuracy and accessibility. Specifically, Jigawa, Yobe, Kaduna and Borno were supported to update their Health Workforce Registries, which is critical to enabling workforce planning, deployment and advocacy for budget releases.

Lafiya states were supported in improving data quality through a number of areas of activity. This included: automation of Jigawa’s RMNCAEH+N and BHCPF Assessment reports into quality assurance platforms; supporting Kaduna’s Health Facility Census to generate critical baseline data on indicators such as workforce, essential medicines, and clinical equipment; facilitating targeted data cleaning and harmonization across Yobe’s Health Facility Registry and District Health Information Systems 2 (DHIS2) platforms.

Lafiya, in collaboration with UK DHSC and WHO, has supported workforce retention efforts through development on the Federal Health Workforce Migration Policy and the Health Workforce Migration Policy implementation plan. Lafiya-Palladium ensured the policy was co-created with Lafiya states and have since initiated collaboration with the National diaspora commission.

FCDO’s Equipment Support for Health (ESHTI) programme funded the procurement and distribution of training aids and equipment for nursing and midwifery training institutions in Nigeria. This is a key necessary investment in the expansion of training capacity and associated accreditation – critical to enabling the development of more nursing grade staff. Lafiya leveraged on its partnership with UK DHSC and WHO in Lafiya supported States to maximise the potential impact of ESHTI by working across focal training institutions to ensure their engagement and to identify opportunities to add value.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes to this output during the past year.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on previous recommendations

The key recommendation was for Lafiya to continue direct advocacy with government and support civil society efforts, using HRH data to push for increased recruitment and training intake. In Kaduna, Lafiya engaged with the Open Government Partnership (OGP), positioning it as a driver to unlock health budgets and address sector priorities. In Kano, with FCDO’s education programme PLANE, supported KanSLAM (Kano Sate Accountability Network) to assess the reversal of the service elongation law (which had extended potential for clinical staff employment beyond their retirement age) – resulting in increased 2025 budget allocations for health worker recruitment.

An additional recommendation advised Lafiya to examine the potential impacts of the Supreme Court’s decision on local government autonomy on HRH in the primary healthcare system. It recommended engaging with the Association of Local Governments of Nigeria (ALGON). In response, Lafiya led a series of consultations with federal legislators from the House of Representatives, the national leadership of ALGON, and ALGON chairpersons from all 36 states. Lafiya identified a lack of independence of ALGON from state governors and turned its engagement to other groups such as Nigeria Union of Local Government Employees. Through these efforts, Lafiya ensured that local government reform discourse included strong voices for accountability and transparency. This will be crucial in monitoring the impact of local government autonomy (when implemented in the future) on HRH provision.
Lessons learned and recommendations for the year ahead

Lesson 3.1: With Lafiya support all focal states are maintaining workforce registries. This data can be used to understand the most pressing health workforce gaps (by population, geography, disease burden) and support evidence-based planning and advocacy.

Recommendation 3.1: Lafiya should continue and scale up support to States to assess their health workforce needs, centred around the analysis of health workforce registries. This will complement the Lafiya supported Organisational Capacity Assessments which were conducted by federal level officers. The assessments can be used both by government and the CSOs in their advocacy efforts.

Output Title	Improved health security through a One Health approach, including response to emergencies
Output number:		4	Output Score:	A+
Impact weighting (%):		15	Weighting revised since last AR?	Yes, previously 10%

Indicator(s)	Milestone(s) for this review	Progress
4.1 Targeted policy windows where technical assistance could catalyse improvements in health security at Federal and State level are identified, discussed with FCDO, implemented, and evaluated (Palladium)	Policy advocacy and TA provided to establish dedicated departments or agency for disease control in line with NCDC subnational health security strengthening agenda.	Score: A++ (exceeded expectation) / The Executive Governor of Kano has given his assent to the law establishing the Kano CDC. Lafiya has supported the institutional building of Kano CDC, and the development and implementation of its operational guidelines. / The Executive Governor of Kaduna has assented a Public Health Law and approved establishment of a state Centre for Disease Control. / With Lafiya support, there is progress in passing the CDC bill in Kaduna and Jigawa and in developing the CDCs’ operational guidelines and workplan.
4.2 Number and percentage of targeted States that have domesticated and are implementing the action plan on health security in line with national guidelines (Kano, Kaduna, Jigawa, Borno, Yobe) (Palladium)	Kano, Kaduna, Jigawa and Yobe States (80% of targeted States) have successfully domesticated the Nigeria National Action Plan for Health Security (NAPHS)	Score: B (moderately did not meet expectation) / Kano, Kaduna, and Jigawa states (60% of targeted states) have successfully domesticated the NAPHS and have implemented key activities from the plan. / In Yobe and Borno States, the Joint External Evaluation (JEE) - a critical prerequisite for NAPHS domestication has been completed.

Briefly describe the output’s activities and provide supporting narrative for the score.

Lafiya has exceeded expectations in this output. Lafiya’s adaptive approach has been pivotal in the support they have provided to the Federal level and in their work to step down health security reforms to the subnational level. All Lafiya states have undergone the International Health Regulations (IHR) process of Joint External Evaluations (JEE) of their health security capabilities, supported by a conglomerate of partners including Lafiya. Lafiya has also supported Kano, Kaduna and Jigawa to domesticate the National Action Plan for Health Security (NAPHS) and are working to finalise this in Yobe and Borno.

Lafiya-Palladium continues its support to establish and make operationally effective state level CDCs across Lafiya focal States. Lafiya’s ‘thinking and working politically’ approach has been crucial to securing support to establish CDCs. Kano CDC has been the outstanding State level success across Nigeria, and the learning from the approach to delivering an operationally effective CDC at State level is being shared across Lafiya focal States and well beyond. In Kaduna and Jigawa, executive approvals to establish a Kaduna CDC and Jigawa CDC have been secured and Lafiya is supporting development of an implementation roadmap. Yobe and Borno, with the support of Lafiya, are amending laws which established the State Agency for Control of AIDS and expanding the scope so they can serve as the State Centre for Disease Control. This approach could provide a more cost-effective model for other states to establish their CDCs.

FCDO and Lafiya have worked with the Federal Government to establish and operationalise the Health Security TWG as part of the SWAp approach. This will act as a dedicated Governance mechanism for coordinating health security efforts. Moreover, Lafiya will support the NCDC to maximise the delivery and impact of the soon to be effective World Bank funded regional Health Security Programme (HeSP) – this is a critical funding source to transform health security capacity at the national and subnational level.

1. The UK is seen by the Government of Nigeria as their key partner on climate and health. Lafiya now directly manages funding from the FCDO climate and health CMP, to deliver against jointly agreed delivery objectives with Government of Nigeria and Development Partners. FCDO’s technical leadership and funding support, has been critical in the achievement of several key delivery milestones: the development of Nigeria’s first Climate and Health Vulnerability and Adaptation Assessment; the development of the Health National Adaptation Plan for Nigeria; the integration of four disbursement linked indicators in the national HOPE PHC programme to incentivise a shift in ambition for the delivery of climate resilient and sustainable interventions across Nigeria; the integration of the Climate resilient Infrastructure for Basic Services methodology into national government primary health care revitalisation programmes; and the integration of health to be at the centre of Nigeria’s Nationally Determined Contribution 3.0, among much more. This progress has put Nigeria at the forefront of action on climate and health globally. FCDO’s expertise and leadership on climate and health has enabled the UK, with support through Lafiya, to help Nigeria to move from commitments to build a climate resilient and sustainable (low carbon) health system in 2021 at COP26 to delivery at scale and pace that is an example to other countries in Africa and across the global.
2. Lafiya’s support for the climate and health agenda is central to its integration into health security initiatives such as the development of an integrated climate, environment and health early warning system and the inclusion of climate shocks into public health emergency preparedness and response mechanisms. Lafiya should work with the UK’s PACE programme and government partners to unlock multilateral financing on climate to deliver on climate and health security objectives.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes to this output during the past year. The logframe should be reviewed to include milestones from the emerging priorities on climate and health, and health security.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on previous recommendations

Lafiya was previously advised to support network learning among Lafiya states planning to establish their own CDCs. Kano led this effort though learning sessions on setting up sub-national CDCs and developing essential strategic documents such as roadmaps, legislative bills, and operational guidelines. This initiative helped accelerate CDC development in Kaduna and Jigawa, which are now building their own CDC structures based on insights from Kano’s model and experience.
Lessons learned and recommendations for the year ahead

Lesson 4.1: Nigeria’s Nationally Determined Contributions (NDC) 3.0 marks the first time health sector ambitions were integrated into the national climate strategy, with the Health National Adaptation Plan (HNAP) positioning climate-resilient health systems as a central pillar of climate action. This presents a strategic opportunity to mobilize climate financing for health sector improvements. Increased Lafiya working with the UK PACE programme can play a catalytic role accessing climate financing and supporting delivery at pace and scale at both federal and sub-national levels.

Recommendation 4.1: Lafiya to collaborate with FCDO’s PACE programme to support government of Nigeria to ‘unlock’ climate financing to help realise the ambitions set out Nigeria’s NDC 3.0 and HNAP.

Lesson 4.2: Significant progress has been made in establishing state-level CDCs, including investments in infrastructure such as new buildings, wards, and laboratories, as well as the development of staffing plans. However, there is a risk of delays in transitioning from legal establishment to full operationalisation. Operational plans must also carefully consider the impact of recruiting health workers from existing hospitals and institutions to avoid weakening other parts of the health system.

Recommendation 4.2: Lafiya should use their trusted position to continue advocating for the operationalisation of state-level CDCs to ensure that government investments deliver value for money across the whole health system at the sub-national level.

Output Title	Improved access to sexual and reproductive health and rights, including strengthened access and demand in north-east Nigeria, and support to accelerate the demographic transition
Output number:		5	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
5.1 Targeted policy windows where technical assistance could catalyse improvements in sexual and reproductive health and rights, and accelerating the / demographic transition, are identified, discussed with FCDO, implemented, and evaluated (Palladium/World Bank)	TA provided to states to harmonise the SRH services and product and institutionalise them in the established Department of Family Health.	Score: A+ (moderately exceed expectations) / Kaduna State Government launched a ₦30 billion (£14.5 million), three-year (2025–2027) strategic plan aimed at enhancing Sexual and Reproductive Health and Rights (SRHR) services for persons with disabilities. / Jigawa State developed procurement guidelines for state-funded family planning commodities. / Kaduna State has integrated the National Demographic Dividend (DD) Roadmap into its development planning framework.
5.2 Annual reporting from UNFPA Basket Fund on family planning commodities submitted on time, and discussed with FCDO (UNFPA)	Report submitted on time and discussed with FCDO	Score: A (met expectations) / Annual report (for Year 5) has been submitted and review meeting held with FCDO.

Briefly describe the output’s activities and provide supporting narrative for the score.

UNFPA and Lafiya-Palladium have met expectations for this output. UNFPA received £2.7m from FCDO between December 2023 and March 2025 for procurement through the UNFPA administered basket fund to supply family planning commodities in 2024 and 2025. Our investments represent excellent value for money. We procured 1,250,469 Couple Years of Contraception Protection for the period under review – which is associated with 405,000 unintended pregnancies averted, 87,440 unsafe abortions averted, and 1,593 maternal deaths averted.

1. However, the availability of modern contraception is still not meeting demand. There are anecdotal reports that demand is increasing due to household budget constraints felt after recent economic reforms. In 2023-24, only 15% of married women aged 15 – 49 were using modern methods and 21% had unmet need for contraception (NDHS 2023-24). In 2024, over 40% of service delivery points reported stocks out of contraceptives in the last three months (from when they were surveyed). The termination of USAID has impacted commodity availability and data collection and validation on stockouts. However, there has been a recent scale up in ambition and commitment by government of Nigeria and development partners on family planning commodity financing and supply. In 2024 the Government of Nigeria released $4m for family planning commodities, which unlocked $2m in match funding from UNFPA. This has been further stepped up through commitments from CIFF, and strong incentives for family planning commodity financing through HOPE PHC. This will likely mean that 2026 will see by far the largest procurement of family planning commodities in Nigeria for many years.
2. Lafiya, working with the FCDO WISH Dividend programme, and other partners will need to focus on supporting last mile distribution and matching supply with demand to realise the potential of increased commodity supply. It will also be critical to collect and collate evidence on the impact of such significant investments to drive advocacy for increasing ambition in this area.

Furthermore, Lafiya-Palladium has spearheaded efforts to increase access to family planning for persons with disabilities across Lafiya states. Lafiya support to the development of Kaduna’s Inclusive SRH Policy and accompanying strategic plan led to the launch of Kaduna’s N30 billion (£14.5 million) three-year Strategic Plan to strengthen SRHR for people with disabilities. In Kano, advocacy supported by Lafiya led to the creation of a dedicated Persons with Disabilities Department in the State Government.

Working with FCDO’s education programme PLANE and Save the Children International, Lafiya-Palladium advanced adolescent and school safety through a package of safeguarding interventions including training healthcare providers and establishing safeguarding platforms in 6 LGAs in Jigawa. This led to work by the World Bank’s education programme AGILE, to map and link girls’ secondary schools to Primary Health Care facilities. This is critical to understanding and addressing access issues for girls and promoting their ongoing engagement in education.

Over the review period, Lafiya-Palladium continued its efforts on demography and stepping down the national demographic dividend to states. They supported a high-impact workshops on the Demographic Dividend agenda convening Federal Commissioners, religious and traditional leaders, CSOs, and state representatives in the five Lafiya states. The workshop catalysed actionable strategies for implementation at the state and community level, including: Kaduna integrating the Demographic Dividend roadmap into the states planning framework; Yobe State developing a strategic Demographic Dividend workplan, and establishing a multi-sectoral steering committee and a Human Capital Development and Demographic Dividend Council; and in Kano, the appointment of dedicated demographic dividend focal points in key MDAs. These are key strategic interventions which will help enable consideration of demography in State level planning and decision making.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

Our support to the Health Resilience in Northern Nigeria Programme (HeRON) ended in May 2024. Therefore, we are no longer using indicators 6.3 or 6.4 which assessed performance of HeRON supported facilities.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on previous recommendation

The previous recommendation was for Lafiya Partners (Lafiya-Palladium and UNFPA) to work with WISH Dividend (new FCDO regional programme that will provide Technical Assistance on SRHR and Demography) and other partners to motivate states to increase their family planning finance to unlock HOPE-PHC disbursement. Joint planning across these programmes is now embedded in ways of working, facilitated by the FCDO Demography Adviser, and the inclusion of a specific agenda item on integration and collaboration across the programmes in Lafiya’s quarterly performance management committee.
Lessons learned and recommendations for the year ahead

Lesson 5.1: In 2025, Government and Development Partner funding commitments for family planning commodities have increased an expected to $6m and $21m respectively – procurements are ongoing with commodities expected to arrive in country in 2026. The Government’s unprecedented $6m commitment for FY2025 will unlock a further $5m from the HOPE PHC Disbursement Linked Indicators. The FP commodity commitments will meaningfully reduce the gap in financing for family planning. However, impact will depend on timely and cost-effective procurement and efficient last mile distribution.

Recommendation 5.1: Lafiya and WISH Dividend should work with development partners and state and Federal Government, to ensure effective last mile distribution of family planning commodities. They should also work with state governments to understand issues with data on stockout levels at PHCs and support capacity building on data collection and recording where appropriate.

Lesson 5.2: One potential delay to family planning commodity distribution, is the Government’s ambition to procure directly for the first time, through the Presidential Initiative for Unlocking the Healthcare Value Chain (PVAC). Development partners, including UNFPA, are working with PVAC to accelerate the process however it is unclear whether procurement will occur at the necessary pace to prevent further stockouts at the facility level.

Recommendation 5.2: UNFPA, with Lafiya-Palladium and other development partners, should support PVAC and Government of Nigeria to procure family planning commodities in time to avoid exacerbating stock out issues. Lafiya-Palladium should work with their states to understand how state level procurement mechanisms fit in with the Federal PVAC mechanism.

Lesson 5.3: Nigeria is currently developing its National Development Plan for the period 2026 to 2030. The National Development Plan should include planning for population trends and determine necessary policies (including health and education investments) to benefit from a demographic dividend.

Recommendation 5.3: Lafiya-Palladium is well-positioned to contribute to this planning process, given its trusted role and strong connections across various arms of state government. It should collaborate with WISH Dividend and UNFPA to advocate for the integration of demographic dividend analyses into the development plans. This includes leveraging available data from the State/LGA National Population Commissions and the National Bureau of Statistics.
## D: VALUE FOR MONEY

Key Cost Drivers and Performance

The programme’s primary cost drivers include personnel expenses, travel and logistics, training, procurement of supplies, and office operational costs. They have remained consistent with those identified in the original Business Case.

Technical assistance (TA), which has been predominantly delivered through Lafiya-Palladium has represented excellent value for money by sustainably building capacity of partners at Federal, State, LGA, and facility level. The work at LGA, and facility level has helped to ensure disbursements of government financing through the Basic Health Care Provision Fund (BHCPF). The work with local communities to develop Ethical Health Financing Committees has been critical in enabling locally led health financing fund flows which are in addition to partner and government funds and focused on local needs. Moreover, the work to establish and make functional the RMNCAEH+N Coordination platforms and establish Departments of Family Health, has been key to enabling integration of services into a package of care which addresses individual and community needs. This will also lead to more efficient use of resources with higher impact with less spend. As demonstrated in the achievement of corresponding output indicators, the Lafiya-Palladium have delivered strong performance, often exceeding expectations.

The primary cost driver for the UNFPA MoU is the cost of commodities, which is influenced by both the mix of commodities procured and their respective unit prices. UNFPA Nigeria sources these commodities through the UNFPA Supply Chain Management Unit (SCMU), which oversees the procurement of contraceptives and related products for 55 beneficiary countries under the UNFPA Supplies Partnership.
VfM performance compared to the original VfM proposition in the business case
The VFM proposition in the original Lafiya business case focuses on interventions to support the Government of Nigeria to increase investments in health, to improve effectiveness of public and private basic health services, and to increase contraceptive prevalence rate. The original cost effectiveness analysis showed that the Lafiya programme was expected to deliver excellent value for money with investment cost per disability adjusted life year (DALY) of around £128, and a cost per life saved of around £4,273. This exceeds the value for money investment targets set by the WHO to deliver cost effective health interventions. During this Annual Review period, we expect the programme’s performance to remain stable. Despite operating with significantly reduced funding, it continues to focus on delivering strategic, high-impact, and value-driven interventions.

A VfM Equity Case Study was completed, focusing on Lafiya’s support for Ethical Health Financing (EHF). The final report highlighted EHF’s contribution to health systems strengthening in Lafiya states by empowering communities to invest in their own health infrastructure and allocate resources where they are most needed. The EHF model promotes self-reliance and local ownership of healthcare financing, complementing government efforts and reinforcing the broader health system. By aligning with cultural and religious practices, EHF ensures the sustainability of health financing within the local context, leveraging capacity within existing community institutions.

A formal annual VfM self-assessment is currently underway, and programme staff received targeted training to enhance internal VfM capacity.
Economy
The programme’s Cost Savings Log, maintained over the past three years, recorded total VfM savings of GBP 190,527 for the reporting year—equivalent to 3% of total programme expenditure. These savings were achieved through strategies such as efficient supply chain management, resource sharing, local sourcing, collaborative training delivery, lean event planning, bulk procurement, and reuse of programme materials. All savings were reinvested to expand the programme’s reach and impact.

Progress against key VfM economy indicators, benchmarked against programme targets, is summarised below.
Indicator	Performance
Administration and management expenditure as a proportion of total programme expenditure	3.4 % of the overall programme expenditure was spent on administration and management. This benchmarks well against previous years and comparator programmes e.g. UK Maternal, Newborn and Child Health Programme (MNCH2)
Expenditure on reimbursable as a percentage of total expenditure	The programme recorded a 100% spend of the FY24/25 funding allocation, with all its state locations and cost centres achieving between 99% - 101%. Expenditure on reimbursables as a percentage of total expenditure was 27%.
VFM Savings as a percentage of reimbursable expenditure	During the review period savings were made at HQ and State level on data charges, fuel usage and co-locating office sites etc. Savings are being tracked in a Savings Log. The total savings for the year equate to £190,527 which is 12% of total expenditure on reimbursables in the reporting period. This benchmarks well against comparator programme e.g. MNCH2

Efficiency

The programme management team conducts thorough monthly and quarterly reviews of programme expenditures to ensure that implementing partners remain within budget and, where possible, achieve cost savings across targeted output areas. The programme consistently meets—and often exceeds—its workplan targets while staying within allocated financial resources. Overall, programme management assesses the efficiency of implementation as strong.

Palladium has consistently demonstrated a high level of performance in its role as the Lafiya TA supplier. They have shown a strong commitment to delivering results, with at least 90% of agreed deliverables completed on time.

UNFPA leverages a pooled procurement mechanism and works exclusively with pre-qualified vendors. This approach has ensured access to high-quality pharmaceutical and contraceptive commodities while achieving cost efficiencies through bulk purchasing and negotiated pricing. UNFPA consistently secures prices for quality-assured products that are equivalent to or better than those listed by internationally recognized pricing benchmarks, including USAID’s published prices (see table below) and the Management Sciences for Health’s International Drug Price Indicator Guide.
Unit cost of family planning commodities compared to catalogue list price

Commodity	Total Quantity procured in 2024/25	Total cost($)	Unit Cost US$ UNFPA 2024	Unit cost US$ (USAID commodities catalogue 2024)
Depo-Provera	738,600	509,634.00	0.69	0.76
Jadelle	100,000	850,000.00	8.50	8.50
Implanon	61,920	563,320.00	8.5	8.5
Microgynon	160,272	144,480.00	0.22	0.66
Female Condom	20,000	10,000.00	0.5	0.5
Levoplant	60,000	402,200.00	6.7	6.9

Effectiveness

1. Despite operating within a constrained annual budget compared to the original business case, the Lafiya programme has demonstrated high effectiveness, as evidenced by its consistent achievement of output indicators. Moreover, the programme has added value beyond the core deliverables.
2. Lafiya–Palladium employs an evidence-based approach to delivering catalytic funding that supports sustainable health system strengthening. Programme activities are grounded in international best practices and are subject to rigorous quality assurance. This is ensured through oversight by technical leads within partner organisations and by FCDO Lafiya programme advisers—including a senior health adviser, a health adviser, and an additional adviser focused on nutrition and WASH. Despite challenging macroeconomic conditions, Lafiya–Palladium have effectively managed the programme budget, ensuring continuity and impact. Notably, FCDO and Lafiya team leveraged substantial central investments in global health initiatives – such as the Global Financing Facility – to amplify results at the Federal and State levels and enhance the visibility of UK funding.

The UNFPA basket fund, which primarily supports the procurement and distribution of family planning commodities, delivers high-impact interventions with strong value for money. UNFPA estimates that each Disability Adjusted Life Year (DALY) averted through access to family planning commodities costs just £13—making it a highly cost-effective investment.
Equity
Lafiya integrates a strong equity focus throughout its programme design and implementation, prioritising support for populations with the greatest need, least access to resources, and poorest health outcomes:
- A key example of this is its backing of the Ethical Health Financing (EHF) model, which empowers communities to invest in their own health infrastructure and direct resources to where they are most needed. The review of its support for the ethical health financing model conducted in 2024 highlighted the model’s significant contribution to health system strengthening in Lafiya-supported states. It emphasised the value of self-reliance and community-led ownership in healthcare financing, often complementing government resources and reinforcing the broader health system.
- Support for civil society organisations targeting advocacy to State government to increase the access and quality of health services for underserved and vulnerable populations.
- Support to understand health care worker distribution (e.g. developing and maintain health workforce registries) to address inequity in supply.
- UNFPA during its life cycle has supported the last mile distribution of contraceptives to 7 (44%) of 16 priority states (as determined by FCDO/UNFPA) which matches with the 44% VfM proposition intended.
Assessment of whether the programme continues to represent value for money.
The Lafiya programme continues to deliver strong performance and impact, even within a constrained financial framework, offering excellent value for money. Its flexibility—alongside that of its implementing partners—has proven advantageous, enabling agile responses to the evolving health sector transformation led by the Coordinating Minister of Health and Social Welfare.

Lafiya is also actively collaborating with centrally managed programmes under FCDO. These partnerships are helping to align and coordinate activities and provide on-the-ground expertise and adaptable resources. This integrated approach presents a cohesive UK health sector offer to the Government of Nigeria.
E: RISK

Overview of risk management

The overall risk rating for Lafiya remains Major and the risk appetite threshold for the programme is Receptive, remaining unchanged since the last Annual Review. During this Annual Review period, the FCDO programme management team have continued to review the risk management framework and update of the risk register on the Aid Management Platform (AMP) in line with PrOF rules. The risk register and risk appetite statement have been reviewed and updated in line with the current risk profile of the programme in the reporting year.

Risk management is well established in the programme through regular identification, assessment, and escalation protocols, where necessary. The programme governance structure feeds risks through quarterly programme management committee (PMC) delivery meetings, checking to evaluate the effectiveness of mitigation strategies, monitoring emerging risks to ensure accountability. These risks are updated at the component and the portfolio levels of the programme. Lafiya approach to risk management is proactive, with mitigation strategies regularly developed and implemented to safeguard programme outcomes.

Key risks this year:

- Challenging macroeconomic conditions: Key developments—including the removal of fuel subsidies and the floating of the naira by the new administration—led to heightened inflation, diminished purchasing power, and widespread economic hardship. This has also had implications for programme planning which has been impacted by rapid inflation but also increased buying power of the pound against the Naira – this has substantial impact on ability to accurately plan programme activities against budgets. Lafiya implementing partners have worked with FCDO Programme Management team to regularly review programmes of work and budgets to respond in an agile and timely way to continue to deliver value for money, impact and spend profiles in line with programme output and outcome expectations.
- Ongoing insecurity: such as kidnappings, communal violence, and political unrest, particularly in Borno and Kaduna states. These factors posed considerable threats to programme implementation. During the period of this AR, implementing partners have been able to (with robust risk mitigation in place) operate in these geographies. While duty of care remains the responsibility of the supplier, FCDO and relevant UN agencies have shared information on security with our suppliers and other development partners, particularly in the north east. This has been critical to informing risk mitigation practices and safety of supplier staff working in insecure regions. This is now a well-established approach to risk mitigation in the Lafiya programme.
- Fiduciary and safeguarding risks: Lafiya continues to maintain a strong controls environment and set of mitigating actions to address the high potential for aid diversion in its delivery context. Whilst it is a key concern, there were no reported incidents of fraud, corruption or safeguarding issues during the review period. Lafiya has implemented robust financial controls and anti-fraud systems aligned with a zero-tolerance policy. FCDO works closely with programme partners to ensure a zero-tolerance position for sexual exploitation, harassment, and abuse is maintained. All programme staff have undertaken the mandatory Sexual Exploitation Abuse and Harassment (SEAH) as well as code of conduct training. Refresher trainings are conducted periodically, and Palladium includes updates on these in their quarterly reports to FCDO. During the reporting period partners have reviewed and reported full compliance with FCDO safeguarding policies.
- Reputational risk: The narrowing of programme scope resulting from ODA funding cuts and strategic reprioritisation continues to represent a reputational risk for FCDO with government partners, development partners, CSOs, communities and beneficiaries. This has been managed through focusing and proactively prioritising communication and consistent stakeholder engagement, which have been instrumental in managing expectations and maintaining stakeholder confidence and trust.
- Climate and Environmental risk: Lafiya conducted a reassessment of its climate and environmental risk exposure in response to previous year’s recommendation - to complete a formative climate risk assessment to further inform programme design and activities, ensuring alignment with the Paris Climate Agreement. Although the programme’s direct environmental footprint remains minimal, climate-related disruptions—such as flooding, drought, and desertification—continue to pose risks, particularly in target states. These risks have been mitigated by integrating climate resilience into its planning processes, updating workplans and strategies to reflect climate priorities, actively engaging key decision makers. Lafiya also collaborated with local governments and NGOs to support climate adaptation and environmental sustainability efforts. Regular training sessions on climate change and health were conducted for staff and government partners to strengthen awareness and preparedness. In response to the flooding in Maiduguri and the resulting damage to programme assets, Lafiya management is implementing proactive disaster risk reduction measures. These include the continuous monitoring of weather forecasts and rainfall volumes during peak seasons, as well as the establishment of early warning systems. To further safeguard operations and ensure continuity, the programme relocated its office to a safer, flood-resilient area. This relocation aims to provide a secure working environment, minimizing future disruptions caused by natural disasters.

The key risks above, and the wider set of programme risks identified, have remained within appetite and will be monitored to ensure that mitigation measures remain appropriate and proportionate. All risks considered to be above appetite are escalated to the Development Director through the Lafiya Programme SRO and Human Development Block Lead in consultation with the Integrated Strategy and Delivery Unit of the British High Commission in Nigeria. The programme’s risk escalation process is laid out in the programme’s risk appetite statement.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Palladium remains a highly effective implementing partner, consistently delivering impactful results despite operating within a significantly reduced budget. Palladium has reliably met its output targets across a broad thematic and geographic scope, maintaining strong financial and programme management throughout. Its ability to adapt, innovate, and remain flexible has been instrumental in ensuring the programme achieves its objectives and maintains high standards of delivery—even in a challenging operational environment. Palladium currently has 13 female members of staff out of 47, including senior positions working at the regional and Federal levels.

Similarly, UNFPA has demonstrated strong effectiveness in managing the Basket Fund for family planning commodity delivery. It has consistently absorbed FCDO allocations in accordance with the Memorandum of Understanding and has shown responsiveness and cost-efficiency. However, with increased focus on family planning financing through the World Bank’s HOPE PHC programme, PVAC’s medipool framework, and the emergence of the Sector-Wide Approach (SWAp), UNFPA is reviewing its operating model to ensure continued alignment with government and partner strategies. FCDO’s investment through UNFPA in the context of much increased family planning commodity financing is likely to have much less impact, and a renewed focus should be placed on last mile distribution and timely supply to the most vulnerable.
Financial Performance
As of September 2025, the programme has spent £79.3million out of the original £235 million budget allocated since inception. The FCDO team has worked closely with Lafiya to ensure timely submission of forecasts and adherence to spending targets. Overall, programme expenditure remains on track to meet the UK’s Official Development Assistance (ODA) target for Nigeria.

Implementing partners have submitted regular monthly forecasts, which are reviewed by FCDO. These routine engagements, alongside active oversight by the FCDO programme management team, have helped ensure that spending stayed aligned with expectations throughout the year. Lafiya successfully met the UK ODA benchmark of 81% spend by the end of Quarter 3 and achieved full budget utilisation of £14.4m by the end of the 2024/25 financial year.

The table below summarises cumulative programme spend up to August 2025 and also summarises the budget allocation for the period under review. The total expected expenditure by the end of FY25/26 is £95.4 million, representing 41% of the approved business case value (£235 million).
Overview of Lafiya spend by programme component
Component	Partner	FY 24/25 budget	Cumulative Total Spend
UK Support for Health in Nigeria	Palladium	5,875,860.38	38,988,008.19
Programme Funded Adviser	FCDO	114,365.90	293,846
Procurement of Family Planning Commodities by UNFPA	UNFPA	955,659.80	12,658,659.80
Monitoring, Evaluation and Learning (DELVe)	Ecorys	-	680,433
WB Recipient Executed Trust Fund - Global Financing Facility (GFF) administrative agreement	GFF/ World Bank	7,535,000.00	7,535,000
Totals		14,480,886.08	60,155,946.99
[note] This mechanism enables investment in a multi-donor trust fund to the World Bank ‘HOPE PHC’ programme which has been set up to support the Health Sector Wide Approach in Nigeria. FCDO began disbursements in October 2024.

Programme financial audit
FCDO commissioned an independent financial audit of Lafiya-Palladium, covering the period of April 2023 – March 2024. The audit returned an unqualified opinion, affirming sound financial practices. Recommendations from the audit have been adopted, contributing to strengthened accountability and continued improvements in financial management. Another audit is currently being commissioned, and this will cover April 2024-August 2025.

In line with existing framework agreements, the UNFPA progress and financial report for March 2023 to February 2025 was reviewed and found to be satisfactory, with no issues requiring further action.
Assets monitoring and management
FCDO has established robust procedures for managing programme assets in collaboration with Palladium and in alignment with its best practice standards, the Lafiya programme maintains comprehensive asset registers to ensure accurate tracking and accountability. As part of the annual financial audit process, FCDO conducts asset verification exercises to confirm the integrity and proper management of these assets. The 2024 Lafiya programme audit included a detailed asset verification, which recommended the disposal of unserviceable, damaged, and surplus assets. This recommendation aims to ensure that all programme assets are put to productive use and to free up critical office space required for ongoing and future programme activities, enhance operational efficiency and maintain a safe, functional working environment.

In September 2024, severe flooding in Maiduguri caused significant damage to the Lafiya office, resulting in the loss of assets, structural damage, and temporary disruption of programme activities. Recovery efforts were swiftly mobilised, with support from the former HeRON project and reallocation of underutilised resources from other Lafiya sites. A new office space has since been secured and is now fully operational.
Compliance with the supply partner code and Supplier Relationship Management (SRM) scorecard assessment
In the latest Supplier Relationship Management (SRM) scorecard, Palladium’s performance on the Lafiya programme was rated as “Good,” with the assessment noting steady improvements across reporting periods. The programme has successfully met its contractual Key Performance Indicators (KPIs), delivering in line with agreed milestones and terms. It has also remained fully compliant with FCDO’s Supply Partner Code and transparency requirements, including the use of Open Book Accounting.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

Over the review period, the Lafiya programme has deepened its collaboration with FCDO sub-national teams, particularly those based in focal states. This closer working relationship has greatly enhanced visibility, insight, and oversight at the point of implementation, positioning FCDO more prominently as the commissioning body for Lafiya. Sub-national teams have actively contributed to quarterly programme management review meetings, bringing valuable local perspectives into strategic discussions. Their involvement has strengthened programme responsiveness and accountability.

Lafiya operates a dynamic monitoring, evidence, and learning framework that supports adaptive management and strategic alignment. Regular financial and programme reviews—including weekly expenditure tracking and quarterly performance assessments—have ensured that delivery remains on track, risks are proactively managed, and innovations are integrated in real time. This adaptive approach has enabled Lafiya to respond effectively to shifting priorities within Nigeria’s health sector. The programme’s flexibility and resilience have proven critical in navigating fiscal constraints and operational challenges, while maintaining high-quality delivery and strategic relevance.

A thorough and inclusive approach was adopted for the Annual Review during this reporting period. Led by the Demographic Adviser and EPD Health Adviser, with the Lafiya Programme Management Team, a detailed assessment of programme activities and outputs was conducted, engaging a broad spectrum of stakeholders to gather diverse perspectives on performance. Key informant consultations included representatives from federal and state governments, implementing partners, UN agencies, facility-level managers and health workers, civil society organisations, and community members. As part of the review, field visits were conducted in two focal states (Kano and Kaduna) to assess delivery on the ground and identify challenges and opportunities for the upcoming programming year. Beyond the concentrated engagement during the Annual Review, FCDO’s programme management team and specialist health advisers maintained regular interaction with Lafiya’s implementing partners and beneficiaries throughout the year. These ongoing exchanges provided valuable insights that further enriched the findings and recommendations of the review

Evidence

Lafiya employs a rigorous, data-driven approach to reach Nigeria’s most underserved populations, continuously analysing intervention data and refining strategies to improve outcomes. While delays in national health surveys and limitations in data quality—particularly with platforms like DHIS-2 —have posed challenges, the programme has remained responsive through adaptive planning aligned with the demands of the health Sector-Wide Approach (SWAp).

The Mid-Term Review (MTR) of the Lafiya programme, completed during the reporting period, reaffirmed Lafiya’s good performance and strong value for money. The programme successfully delivered 100% of its milestones, demonstrating its ability to adapt to Nigeria’s evolving health landscape while maintaining high-quality, sustainable outcomes for vulnerable populations. Lafiya showcased strategic agility in navigating complex political, economic, and health system transitions. It excelled in key areas such as health financing and institutional coordination, and resilience in conflict-affected regions.

The MTR highlighted notable achievements including expanded access to the Basic Health Care Provision Fund (BHCPF), support for state-level health insurance schemes, the rollout of innovative Ethical Health Financing models across 90 Local Government Areas, institutionalising coordination platforms for RMNCAEH+N and supporting the establishment of State Centres for Disease Control (CDCs). While the review acknowledged persistent challenges—such as delays in funding flows, shortages in human resources, and supply chain inefficiencies—it also provided strategic recommendations to deepen impact, broaden reach, and enhance alignment with national health priorities. These findings reinforce Lafiya’s position as a transformative and responsive force within Nigeria’s health sector.

Learning

Lafiya continues to maintain a strong commitment to continuous learning and evidence-informed programming. Through routine monitoring, targeted reviews, and collaborative learning processes, the programme captures insights that shape interventions and improve performance. Monitoring data is actively used to assess progress and refine strategies, ensuring responsiveness to evolving needs.

The development and implementation of the Sector-Wide Approach (SWAp) has provided a valuable platform for documenting lessons that inform future programming. In the year ahead, a key learning priority for the Lafiya programme will be to systematically capture insights and experiences from the implementation of the Health Sector-Wide Approach (SWAp) across federal, state, and local government levels. This includes documenting lessons from the rollout of the Health National Adaptation Plan (HNAP), Health State Adaption Plans (HSAP), and the Health System Performance (HeSP) programme.

Additional key learning processes and lessons from the review period includes:

- Using the evaluation of the Ethical Health Financing model to strengthen Lafiya’s approach. The EHF model has gained traction, with local committees now initiating capital projects and scholarship schemes, demonstrating growing ownership and sustainability.
- Establishing a Community of Practice that brought together Commissioners of Health and Planning Directors to foster peer exchange and institutional learning.
- Engaging directly with LGAs, CSOs and States to understand the impact of the Supreme Court ruling on Local Government budget autonomy on health.
- Civil society organisations have proven essential for promoting transparency and accountability, and their integration into the Sector-Wide Approach (SWAp) remains a priority.
- Efforts to establish Departments of Family Health (DFH) at the state level have highlighted the need for sustained federal mentorship to ensure operational effectiveness.
- Kano’s Centre for Disease Control (CDC) has emerged as a national learning hub, supporting replication of State CDCs across Nigeria.

These learnings will be essential for informing current and future programming, while also contributing to broader knowledge generation for FCDO and its partners. To maximise the value of these insights, Lafiya will need to continue proactive engagement with the FCDO Nigeria communications team, ensuring that evidence of impact and lessons learned are widely disseminated and leveraged to enhance the overall return on investment.
Date of last narrative financial report	30 June 2025	Date of last audited annual statement	17 February 2025