ADDENDUM TO BUSINESS CASE

INCLUDING SCALE-UP COST EXTENSIONS

SUMMARY INFORMATION
Project Name	Tax Transformation Programme (TSTP)
Country or region targeted	Ethiopia
Type of cost extension (if applicable)	Time
Original project budget	£35 million
Original project start and end dates	April 2018 - March 2024 (extended to 31 March 2026)
Cost extension value (if applicable)	N/A
New reduced budget (if applicable)	£24 million
New project end date (if applicable)	30 June 2028
Business Case Quest Document No.	45010791

INFORMATION
What is the project’s purpose?
To transform Ethiopia’s tax system so that the Ethiopian Government can fund more services for its population from its own revenues and become less dependent on aid. It takes an accelerated ‘delivery approach’ to tax reform that will reduce compliance costs for taxpayers, support a better environment for businesses by improving clarity and increase the fairness of the tax system for businesses and investors. In doing so, it will create a platform for further sustainable increases in tax revenue and improve the Government's ability to assess the distributional impacts of its tax policies, particularly on the poor and other vulnerable groups. In doing so it will contribute to a more sustainable macro-economic environment, reduce economic shocks and support long-term growth and poverty reduction.
What is the objective of the cost extension or other changes?
This twenty-seven month extension to the TSTP (extending it until 30 June 2028, to align with the end of an IMF Extended Credit Facility, World Bank DPO series and a National Medium Term Revenue Strategy – all agreed during July and August 2024) will allow: / Deepening the impact of the programme and securing the long-term sustainability of revenue improvements: / in key deliverables around the maintenance and upgrading of critical IT infrastructure, continuation of Business Process Transformation, and / Beginning the implementation of the Ministry of Revenue (MoR) Reform Strategy and Roadmap, co-developed by the TSTP supplier and the Ministry Of Revenue, and approved in the week of 6 July 2025 / Supporting the achievement of domestic resource mobilisation (DRM) targets set out in the National Medium Term Revenue Strategy (NMRTS) and IMF Extended Credit Facility (ECF) / Draft key tax legislation in order to meet tax policy changes agreed to under the WB Development Policy Operation. / The UK to play a convening role in the tax space: / using our incumbent position to continue to coordinate donors as they begin to reengage (e.g. the World Bank); / aid the MOR to help them be good partners with donors, with clear communications, requests and a roadmap for reforms (note the MOR Reform Roadmap is a critical step in this process). / working to influence donors to ensure we are more than the sum of our parts. / Pivot our engagement to: / support equitable and transparent taxation of international investors, protecting and supporting Ethiopia’s investment climate at a time of high revenue pressure, including supporting the establishment of an international tax department, which will allow reform of Ethiopia’s tax treaty framework and / advocate for careful policy analysis of revenue measures to protect vulnerable groups, especially women. / Ensure sustainable withdrawal: / Transfer of donor coordination responsibilities to create ownership, supported by tools, capacity development, and transitional advisory input across the group. / Finalisation of monitoring and evaluation systems to sustain performance tracking post-programme impact and its attribution.
What is the additional and total support the UK will provide?
This extension does not involve an additional cost over the original BC value of £35 million. / After some years of annual budget reductions, in late 2023 an amendment was approved that lowered the budget to £17 million, with a possibility to spend up to £18.4 million. This amendment also extended the lifetime of the programme to 2025. This extension does involve increasing the total support above this amended level, to £24 million. In the context of falling aid budgets for Ethiopia, efforts to raising revenue become ever more important as the government takes up a large share of spending on critical services and investment. / The TSTP was originally envisaged as a £35 million programme to support a Government of Ethiopia policy priority. It faced a rapidly changing and challenging operating environment. Large shocks, including the covid-19 pandemic and Tigray War, caused frequent shifts in GOE priorities, and triggered a macroeconomic crisis. UK Government reductions in ODA following the pandemic caused disruptions to planned annual budgets. The main delivery partner, Cowater Sogema (hereafter Cowater), has displayed considerable adaptability to this shifting environment. / With this extension the programme will only spend 64.3% of the originally envisaged £35 million. / Cowater initially had a contract of £27.2 million. In advance of this amendment they are expected to spend £18 million over the lifetime of the programme to date. This leaves £8.8 million of headroom for Cowater compared to the original contract value, of which up to £2.8 million will be utilised under this amendment. / TSTP had monitoring and evaluation supplied by IPE Global Limited. During the last amendment in 2023 we moved them from a drawdown to a deliverables approach, focused on providing detailed annual reports. Input from IPE has been extremely valuable, informing programme adaptations. We will look to maintain this support.
What are the expected results?
TSTP will continue to respond flexibly to GOE reform plans and support implementation of i) the new Ministry of Revenue Reform Roadmap, ii) the National Medium Term Revenue Strategy (NMTRS), iii) the reforms agreed by the GOE in the IMF Extended Credit Facility (ECF) and two World Bank Development Policy Operations (DPO) and iv) engagement with the tax measures in the World Bank Governance Modernisation Programme. / Under the IMF ECF and NMRTS listed in point 1, Ethiopia has significant revenue targets. TSTP plays a key role in helping the GOE meet these. Alongside this, TSTP has begun a process of conducting regular taxpayer surveys, helping the GOE identify challenges in the investment climate from the renewed efforts on tax mobilisation. / In this extension TSTP will respond flexibly to accommodate new sources of support to the GOE. Key results will remain: / Ensuring the stability of the core IT system (SIGTAS), without which Ethiopia’s revenue system will collapse. / Ensuring databases remain stable and developing data recovery plans. / Providing the IT support to new business processes that reduce compliance costs and supporting policy work through the supply of data. / Support a new reform strategy that involves efforts to modernise the management and HR functions in the MOR. / Provide leadership on modernisation of the MOR Tax Training Centre, ensuring work from TSTP, and other donors, can be sustained after the end of the programme. / Ensure that a raft of tax policy reforms, required under the World Bank Development Policy Operation, are well drafted and passed by the House of Peoples’ Representatives. This support is critical, and the World Bank have been clear on how fundamental TSTP support is to secure these changes. / Providing a donor coordination function to the MOR, which will be used to avoid duplication, align with a revenue improvement strategy, disseminate evidence, and provide a forum for taxpayer representatives to speak to MOR officials / Develop a robust exit strategy, accounting for the changes to the MOR, that allows the functions of the TSTP to be accommodated within the MOR under the new MOR reform strategy (which TSTP co-developed with the MOR).
What is the approach to implementation?
The TSTP is implemented via long-term embedded advisers in the Tax Transformation Office (TTO) now located in the Ministry of Revenue. Most of these advisers are focused on information technology support, maintaining the core IT system and upgrading systems to improve business efficiency. This became the core of TSTPs approach of patient, trusted, flexible, technical assistance. / A legal adviser is embedded in the tax policy unit of the Ministry of Finance. They draft the legal documents that facilitate policy changes and provide training on key areas of concern, such as international taxation matters. This support has been critical in meeting a range of commitments in the IMF Extended Credit Facility, approved in July 2024, and two World Bank Development Policy Operations, approved in July 2024 and July 2025. / Since the start of 2024, Cowater have increased their management capacity, recruiting a new programme director, a respected tax expert, adding a Project Manager based in Addis, and a new Project Officer and Project Director. Costs have been managed well within set contractual limits. / These new positions have supported Cowater to manage a scale up of the TSTP activities over the past 18 months. This was a busy period, in which TSTP embedded advisers provided critical support to the GOE in their successful negotiations with the IMF and World Bank on new programmes and supported the GOE to meet the requirements of early reviews of these programmes. / Revenue reform requirements of the new IMF and WB programmes have dramatically increased political support for tax administration reforms. TSTP has responded quickly to this, co-developing (with Ministerial approval from the GOE Ministries of Revenue and Finance) a Revenue Administration Reform Strategy and Roadmap. These comprehensive documents are the first sequenced and prioritised plans for reforms to tax administration. Cowater have consulted widely with other partners, including the IMF and WB, gaining a reputation for leadership in the sector.
Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work?
The scale and scope of this programme has shifted in response to huge disruptions in the external environment and FCDO budgets. However, throughout the purpose of the programme has remained constant: to support a sustainable revenue system for Ethiopia. / Tax Transformation Programme (TTP): Adapting to external and FCDO shocks 2018-2023 / The TSTP was informed by earlier work on domestic revenue mobilization (DRM) undertaken as part of the first phase of the Ethiopian Advisory Facility (EIAF), 2015 – 2021. This identified opportunities for additional tax revenues. TSTP, was developed to try and realise these opportunities. / Following a competitive procurement, a 5-year contract for the TSTP was awarded to Cowater Sogema International Inc (henceforth Cowater) on 13 March 2019 for GBP 27,167,193. This contract specified an optional two-year extension. / TSTP was delivered in a context of acute social, political and economic crisis. Multiple shocks affected Ethiopia, being with drought in 2019, Covid in 2020, and commodity price shocks in 2022. Several internal conflicts have broken out, including the two-year Tigray War, which started in 2020. Ethiopia’s macroeconomy slid into crisis. Accelerating inflation and a growing exchange rate overvaluation led to a default on debt and significant erosion of real wages and social sector spending. / While the scope and budget of TSTP were restricted during implementation due to FCDO budget cuts, a team of long-term advisers, embedded in the Ministries of Revenue and Finance, were maintained throughout, developing excellent relationships with senior officials and Ministers. / The work of the embedded advisers focused on IT support, keeping an ailing and vulnerable core IT system operational, strengthening database security and recovery plans, and preparing for the procurement of a new central IT system via public procurement. / Extension in December 2023: Responding to huge risks and challenges / During 2023, against a background of growing macroeconomic crisis, the TSTP supported the GOE with preparation for public procurement of a new Integrated Tax Administration System. The competitive procurement was cancelled shortly before the release of tender documents, in favour of a platform built in-house by the GOE body INSA. This decision almost certainly resulted from the acute foreign exchange shortages that were affecting the country. Several stakeholders raised concerns about the ability of the GOE to deliver a new IT system and it became clear support to the existing system would be needed beyond March 2024, the original TSTP end date. / At the end of 2023 we agreed a two-year extension to TSTP to provide this support, during which the FCDO planned to consider its work on tax reform. / New incentives for reform from significant IMF and World Bank programmes / Since 2023 the TSTP has been central in support the Government of Ethiopia’s ambitious macroeconomic reform agenda to move to a more sustainable fiscal position so that it can support it’s own services and the investment needed to drive long-term growth and poverty reduction. / In response to conflict in Ethiopia, development partners withdrew support for economic development, focusing instead on humanitarian assistance. A peace agreement in November 2022, ending the war in Tigray, was a necessary but not sufficient step to a shift in this position. This picture gradually shifted through 2023. The UK supported the start of new negotiations with the IMF and World Bank (WB), but progress was slow. / In the first quarter of 2024 discussions about an IMF and WB package appeared to halt, with limited engagement from the GOE. But in the second quarter, after TSTP had been extended, there was a surge of activity. The key issues for the GOE were how resolve the large spread between the official and parallel exchange rates and how to sustainably raise domestic revenue, which had fallen to below 7% of GDP. Uncertainty persisted into June. / On the 29 July 2024 the GOE floated the Birr, leading to a 100% devaluation over August and a unification of the parallel and official ER. This devaluation facilitated a big increase in trade taxes in the subsequent year, due to the change in valuations. But sustaining tax increases in the later years needs much more careful assistance. / Two hours after the devaluation, the IMF Board approved a USD 3.4 billion Extended Credit Facility (ECF). The following day, the WB Board approved the first in a series of four complementary Development Policy Operations (DPOs), expected to provide a total of USD 3.7 billion. / This breakthrough was very uncertain even in May 2024, shortly after the two-year extension envisaged in the original contract started. Political fractures in Ethiopia, a fragile and conflicted affected state, made prediction extremely challenging. Contacts in the IMF and WB were unsure when or if a deal might get done. Political analysts advised that the GOE were highly unlikely to agree to external programmes that held the GOE to account. / Such a low level of domestic revenue mobilization meant it was clear that if a deal was agreed it would involve revenue targets – as IMF programmes commonly do. But it was not possible to predict how the GOE would respond to these, for example whether they would increase aggressive revenue collections or commit to significant reforms. / Both the ECF and DPO include results targets on revenue mobilization, covering tax policy and administration. These dramatically increased incentives for tax reforms in Ethiopia due to funding disbursements being linked to revenue increases and legislative reforms. But neither the ECF nor DPO includes the depth and persistence of technical assistance required to support the achievement of these results, which demand a much higher degree of implementation capacity than the relevant GOE Ministries have. / In August 2024, the Government of Ethiopia committed to a National Medium-Term Revenue Strategy (NMTRS). This covers a range of policy and administrative reforms, aimed at increasing revenues by 4 percentage points of GDP over 4 years. But the NMTRS lacks a coherent strategy that sequences and prioritizes reforms. / In the event, following the agreement on these programmes, political momentum behind revenue reforms have dramatically increased. Demands on the TSTP have increased along with it. Since November 2024, GOE requests for support have grown considerably. Taxation is deeply political and trusted relationships – such as those the UK has supported - are essential. / In response to requests from the GOE, we prioritized the TSTP embedded adviser time towards supporting the negotiations of these programmes and then meeting the high demands of the programmes in the past year. TSTP advisers have built deep trusted relationships with senior officials and Ministers. This is a significant asset and presents an opportunity to drive further impact and value for money on the UK investment in TSTP. / While other donors, including the WB, are currently developing or launching projects in the tax space, they have done so in coordination with the TSTP, which is completing the role intended in the 2024 extension of coordinating donors. WB and IMF programmes provide finance in return for reforms but only limited technical support to the reform delivery. Neither have mechanisms to embed long-term technical advisers. As a result, TSTP activities are highly complementary to these wider efforts, supporting value for money more broadly. / This support from TSTP is ideal for the new ODA environment, representing modest expenditure to support a tried and tested project that we know is crucial to helping the government raise the finances it needs to take on the funding burden from donors in key sectors like health and education.
[note] Cowater Sogema (hereafter referred to as ‘Cowater’) are the main implementing partner for the Tax Systems Transformation Programme. Cowater won a competitive tender to be contracted to implement the programme.
[note] Ethiopia floated its currency on 29 July 2024. Two hours later the IMF Board approved the ECF. The next day the WB Board approved the first in a series of DPOs.