## TTP Logframe (October 2025)
PROJECT TITLE | Ethiopia Tax Transformation Programme (TTP) | [7 empty] | Assumptions | Sep 2021 Revisions Based on Budget Cut for FY 21/22 or additional information received |  | Milestone 1 Actuals updated end of EFY 2013 (July 2021)
IMPACT | Impact Indicator 1 |  | Baseline: July 2020 (end of 2012 Ethiopian Fiscal Year - EFY) | Baseline: July 2024 (end of 2016 EFY) | Milestone 5 FY4Q3 (31 Dec 2024) (31 Dec 2017EFY) | Milestone 5 end FY4Q4 (31 Mar 2025) (31 Mar 2017EFY) | Milestone 6 - End FY5 Q1 (30 June 2025) (30 June 2017 EFY) | Milestone 6 - End FY5 Q4 (31 Mar 2026) (31 Mar 2018 EFY) | Unless otherwise stated, the focus of the programme until end FY3 will be on the LTO. From FY4Q1 until end of programme (FY5Q4) both the LTO and MTO will be reported on. This programme would only focus on the STO in Addis Ababa (AA) East , North West and West branches as they are the only federal STO offices.
GOE is able to self-finance its development through increased, sustainable revenue collection | Tax revenue collected by federal government | Planned | 9.2% | N/A | ETB 347 billion | ETB 347 billion | ETB 900,266 billion | ETB 1.28 Trillion | Milestones/targets for this indicator reflect the MoR's own strategic plan and represent the results of contributions by multiple actors. Cowater will report the progress of these indicators, however, is only responsible for the results of specific activities, upon which the programme is focusing. (Not sure we need to add what is highlighted in red - that's the purpose of Impact Indicators) | Baseline figure updated - Initial value for impact indicator 1.1 were estimates (forecasts), while the recent figure is based on final figures from the NBE (National Bank of Ethiopia) |  | Still TBC
|  | Achieved | 10.5% | N/A | TBD | ETB 587,164 billion | ETB 900,217 billion | TBD
Source
Annual Performance Report
OUTCOME 1 | Outcome Indicator 1.1 |  | Baseline: July 2020 (end of 2012 Ethiopian Fiscal Year - EFY) | Baseline: July 2024 (end of 2016 EFY) | Milestone 5 FY4Q3 (31 Dec 2024) (31 Dec 2017EFY) | Milestone 5 end FY4Q4 (31 Mar 2025) (31 Mar 2017EFY) | Milestone 6 - End FY5 Q1 (30 June 2025) (30 June 2017 EFY) | Milestone 6 - End FY5 Q4 (31 Mar 2026) (31 Mar 2018 EFY) |  | Baseline and Milestones were initially set based on the 10-year strategic plan of MoR, which provides only net tax revenue targets (excluding non-tax revenue and other revenues). In order to align with the annual plan of the MoR revenue targets for EFY 2012, 2013 and 2014 are replaced with the actual targets and collection. Estimates from EFY 2015 onwards are still based on 10 year targets and will be gradually refined. Note that the revenue targets are based on the Ethiopian fiscal year (e.g. EFY 2014 is the period from July '21 to June '22, these targets are taken for the TTP current year plan - April '21 to March '22.) |  | The amount indicated reflects actuals as of end of EFY 2013, as in the AR only a predicted amount was included which was ETB 261.8 billion by July 2021 (domestic: ETB 149.5 billion and customs: ETB 112.3 billion) - the actual surpassed this prediction
Improved voluntary compliance | No. of active taxpayers as % of total number in the register Inactive Indicator with historic data - not being monitored for Milestones 5-6. | Planned |  | N/A - Baseline
|  | Achieved |  | LTO = ACTIVE (758) / TOTAL (759) = 99.9% MTO = ACTIVE (8,358) / TOTAL (8,375) = 99.8% STO = ACTIVE (50,884) / TOTAL (55,605) = 91% | Not active indicator | Not active indicator | Not active indicator | Not active indicator
Source
SIGTAS/Registration Directorate
| Outcome Indicator 1.2 |  | Baseline: July 2020 (end of 2012 Ethiopian Fiscal Year - EFY) | Baseline: July 2024 (end of 2016 EFY) | Milestone 5 FY4Q3 (31 Dec 2024) (31 Dec 2017EFY) | Milestone 5 end FY4Q4 (31 Mar 2025) (31 Mar 2017EFY) | Milestone 6 - End FY5 Q1 (30 June 2025) (30 June 2017 EFY) | Milestone 6 - End FY5 Q4 (31 Mar 2026) (31 Mar 2018 EFY)
| % of tax collected from filings/returns vs debt to total domestic tax revenues | Planned |  | N/A - Baseline | 84% | Filing/Returns: 87.5% Debt: 12.5% | Filing/Returns: 90% Debt: 10% | Filing/Returns: 90% Debt: 10%
|  | Achieved |  | 84.7% | 84.7% | Filing/Returns: 81.2% Debt: 18.8% | On-track | TBD
Source
MoR Planning Directorate - may use SIGTAS reports
| FCDO (£) |  |  | Govt (£) | Total (£) | Total (£)
FCDO (FTEs)
| Outcome Indicator 1.3 |  | Baseline: July 2020 (end of 2012 Ethiopian Fiscal Year - EFY) | Baseline: July 2024 (end of 2016 EFY) | Milestone 5 FY4Q3 (31 Dec 2024) (31 Dec 2017EFY) | Milestone 5 end FY4Q4 (31 Mar 2025) (31 Mar 2017EFY) | Milestone 6 - End FY5 Q1 (30 June 2025) (30 June 2017 EFY) | Milestone 6 - End FY5 Q4 (31 Mar 2026) (31 Mar 2018 EFY)
| % of Taxpayers with improved perception of the tax administration system, indicating neutrality and fairness | Planned |  | N/A | TBD | TBD upon integration of Taxpayer Survey Findings | N/A - Baseline | Very Unfair = 25.00% Unfair = 14.67% Neutral = 23.33% Fair = 21.67% Very Fair = 15.33%
|  | Achieved |  | N/A | TBD | TBD upon integration of Taxpayer Survey Findings | Very Unfair = 30.00% Unfair = 16.67% Neutral = 23.33% Fair = 16.67% Very Fair = 13.33% | TBD
Source
TTP Project Taxpayer Survey Report
| Outcome Indicator 1.4 |  |  | Baseline: July 2024 (end of 2016 EFY) | Milestone 5 FY4Q3 (31 Dec 2024) (31 Dec 2017EFY) | Milestone 5 end FY4Q4 (31 Mar 2025) (31 Mar 2017EFY) | Milestone 6 - End FY5 Q1 (30 June 2025) (30 June 2017 EFY) | Milestone 6 - End FY5 Q4 (31 Mar 2026) (31 Mar 2018 EFY)
| % of tax revenue paid on time (Disaggregated by VAT and CIT) | Planned |  | N/A - Baseline | VAT: 80% CIT: 55% | VAT: 80% CIT: 55% | VAT: 95% CIT: 75% | VAT: 95% CIT: 75%
|  | Achieved |  | VAT: 77% CIT: 51% | VAT: 77% CIT: 51% | VAT: 87.96% CIT: 65.8% | VAT: 94.96% CIT: 91.8% | TBD
Source
SIGTAS
OUTCOME 2 | Outcome Indicator 2.1 |  | Baseline: July 2020 (end of 2012 Ethiopian Fiscal Year - EFY) | Baseline: July 2024 (end of 2016 EFY) | Milestone 5 FY4Q3 (31 Dec 2024) (31 Dec 2017EFY) | Milestone 5 end FY4Q4 (31 Mar 2025) (31 Mar 2017EFY) | Milestone 6 - End FY5 Q1 (30 June 2025) (30 June 2017 EFY) | Milestone 6 - End FY5 Q4 (31 Mar 2026) (31 Mar 2018 EFY)
A tax environment that encourages business | % of taxpayers using e-filing for VAT and Corporate Income Tax disaggregated by: Large/Medium/Federal Small Tax Office in Addis Ababa | Planned |  | N/A - Baseline | VAT: LTO: 99.59% (maintained) MTO: 99.86% (maintained) STO: 95% CIT: LTO: 97% MTO: 95% STO: 60% | VAT: LTO: 99.59% (maintained) MTO: 99.86% (maintained) STO: 95% CIT: LTO: 97% MTO: 95% STO: 60% | VAT: LTO: 99.59% (maintained) MTO: 99.86% (maintained) STO: 96% CIT: LTO: 98% MTO: 96% STO: 70% | VAT: LTO: 99.59% (maintained) MTO: 99.86% (maintained) STO: 96% CIT: LTO: 98% MTO: 96% STO: 70% |  | Milestone 2 changed to N/A as no work on customs this year | Wording of Outcome 2 changed to accommodate the addition of outcome indicator 2.4 (previously output 4.3) | N/A
|  | Achieved |  | VAT LTO: EFILERS (737) / TOTAL FILERS (740) = 99.59% MTO: EFILERS (7,126) / TOTAL FILERS (7,136) = 99.86% STO: EFILERS (18,291) / TOTAL FILERS (19,717) = 92.77% CIT LTO: EFILERS (173) / TOTAL FILERS (179) = 96.65% MTO: EFILERS (731) / TOTAL FILERS (775), = 94.32% STO: EFILERS (1,071) / TOTAL FILERS (2,079) = 51.52% | VAT LTO: EFILERS (737) / TOTAL FILERS (740) = 99.59% MTO: EFILERS (7,126) / TOTAL FILERS (7,136) = 99.86% STO: EFILERS (18,291) / TOTAL FILERS (19,717) = 92.77% CIT LTO: EFILERS (173) / TOTAL FILERS (179) = 96.65% MTO: EFILERS (731) / TOTAL FILERS (775), = 94.32% STO: EFILERS (1,071) / TOTAL FILERS (2,079) = 51.52% | VAT: LTO: 98.4% MTO: 99.57% STO: 93.86% CIT: LTO: 95.35% MTO: 97.54% STO: 86.35% | VAT: LTO: 98.4% MTO: 99.57% STO: 93.86% CIT: LTO: 95.35% MTO: 97.54% STO: 86.35% | TBD
Source
SIGTAS/ Filing Directorate
| Outcome Indicator 2.2 |  | Baseline: July 2020 (end of 2012 Ethiopian Fiscal Year - EFY) | Baseline: July 2024 (end of 2016 EFY) | Milestone 5 FY4Q3 (31 Dec 2024) (31 Dec 2017EFY) | Milestone 5 end FY4Q4 (31 Mar 2025) (31 Mar 2017EFY) | Milestone 6 - End FY5 Q1 (30 June 2025) (30 June 2017 EFY) | Milestone 6 - End FY5 Q4 (31 Mar 2026) (31 Mar 2018 EFY)
| The time taxpayers take to file taxes | Planned |  | N/A | TBD | N/A | N/A - Baseline | LTO: 6.25 Days MTO: 4.14 Days STO: 3.00 Days |  | Changed to quantitate and new milestones set due to reduced resourcing. It is assumed that the work the program is doing through Wassihun will have at least one policy related impact that can be described. Future milestones may need to be revised depending on resources
|  | Achieved |  | N/A | TBD | N/A | LTO: 6.47 Days MTO: 4.34 Days STO: 3.32 Days | TBD
Source
TTP Project Taxpayer Survey
| Outcome Indicator 2.3 |  | Baseline: July 2020 (end of 2012 Ethiopian Fiscal Year - EFY) | Baseline: July 2024 (end of 2016 EFY) | Milestone 5 FY4Q3 (31 Dec 2024) (31 Dec 2017EFY) | Milestone 5 end FY4Q4 (31 Mar 2025) (31 Mar 2017EFY) | Milestone 6 - End FY5 Q1 (30 June 2025) (30 June 2017 EFY) | Milestone 6 - End FY5 Q4 (31 Mar 2026) (31 Mar 2018 EFY)
| The time taxpayers take to pay taxes | Planned |  | N/A | TBD | N/A | N/A - Baseline | 0-15 Mins: LTO: 8% MTO: 9% STO: 23.0% 16-30 Mins: LTO: 18% MTO: 28% STO: 33% 31-60 Mins: LTO: 29% MTO: 25 STO: 17% Over 60 Mins: LTO: 45% MTO: 38% STO: 27% |  | Changed to quantitative and new milestones set due to reduced resourcing. It is assumed that the work the program is doing through Wassihun will have at least one policy related impact that can be described. Future milestones may need to be revised depending on resources
|  | Achieved |  | N/A | TBD | N/A | 0-15 Mins: LTO: 6.67% MTO: 7.92% STO: 22.2% 16-30 Mins: LTO: 16.67% MTO: 26.73% STO: 31.89% 31-60 Mins: LTO: 30% MTO: 25.74 STO: 17.2% Over 60 Mins: LTO: 46.67% MTO: 39.6% STO: 28.71% | TBD
Source
TTP Project Taxpayer Survey
INPUTS (£) | FCDO (£) |  |  | Govt (£) |  | Total (£) | FCDO Share (%) | FCDO Share (%)
| 18005643 |  |  |  |  | 18005643 | 100% | 100% |  | This was previously Output Indicator 4.3 but has been moved to outcome level given that the programme now has less control over this.
INPUTS (HR) | FCDO (FTEs)
FCDO TO INPUT
OUTPUT 1 | Output Indicator 1.1 |  | Baseline: July 2020 (end of 2012 Ethiopian Fiscal Year - EFY) | Baseline: July 2024 (end of 2016 EFY) | Milestone 5 FY4Q3 (31 Dec 2024) (31 Dec 2017EFY) | Milestone 5 end FY4Q4 (31 Mar 2025) (31 Mar 2017EFY) | Milestone 6 - End FY5 Q1 (30 June 2025) (30 June 2017 EFY) | Milestone 6 - End FY5 Q4 (31 Mar 2026) (31 Mar 2018 EFY) |  | Kept Milestone 2 as forecasting has already been done and collection underway but Milestone 3 changed to N/A as there will be no support on forecasting this year. |  | As of end of EFY 2013 figure is 3.6%
SIGTAS system is enhanced, and data quality is strengthened. (Enhancement = both improving modules, and incorporating customised business processes (originally designed for ITAS) | Number of BPT SoPs developed, agreed and implemented for enhanced SIGTAS functionalities | Planned |  | N/A | 2 | 2 | 4 | 4
|  | Achieved |  | 0 | 0 | 0 - On track with delays. Submission of SOPs delayed by MoR input. | 2 | TBD
Source
Project Documentation (from BPT expert reports)
| Output Indicator 1.2 |  | Baseline: July 2020 (end of 2012 Ethiopian Fiscal Year - EFY) | Baseline: July 2024 (end of 2016 EFY) | Milestone 5 FY4Q3 (31 Dec 2024) (31 Dec 2017EFY) | Milestone 5 end FY4Q4 (31 Mar 2025) (31 Mar 2017EFY) | Milestone 6 - End FY5 Q1 (30 June 2025) (30 June 2017 EFY) | Milestone 6 - End FY5 Q4 (31 Mar 2026) (31 Mar 2018 EFY)
| Percentage of SIGTAS blocking and critical issues resolved relative to total number of issues in hand during period | Planned |  | N/A - Baseline | 70% | 70% | 80% | 80%
|  | Achieved |  | Opening Balance (Number of cases) = 25 New Cases in Year = 43 Resolved in Year = 43 ; % = 43/(43+25) = 63.2% | 77% (Opening Stock=25, New Cases=10, Resolved= 27) | Opening Balance (Number of cases) = 25 New Cases in Year = 18 Resolved in Year = 30 % = 30/(18+25) = 69.8% | Opening Balance (Number of cases) = 25 New Cases in Year = 18 Resolved in Year = 30 % = 30/(18+25) = 69.8% | TBD
Source
|  | Data IT (TTP) / Data Centre | [7 empty] | Milestone 2 changed to N/A as no work on organisational health this year. | Output 4 is therefore not captured this year - hence why we have changed the language of Outcome 2 to try to capture equity considerations (it also has an additional output - previous 2.4 to capture equity)
| Output Indicator 1.3 |  | Baseline: July 2020 (end of 2012 Ethiopian Fiscal Year - EFY) | Baseline: July 2024 (end of 2016 EFY) | Milestone 5 FY4Q3 (31 Dec 2024) (31 Dec 2017EFY) | Milestone 5 end FY4Q4 (31 Mar 2025) (31 Mar 2017EFY) | Milestone 6 - End FY5 Q1 (30 June 2025) (30 June 2017 EFY) | Milestone 6 - End FY5 Q4 (31 Mar 2026) (31 Mar 2018 EFY)
| Number of improved SIGTAS reports: i) # reports produced and used in practice ii) # reports improved | Planned |  | N/A - Baseline | i) 2 new types of reports produced and used ii) 0 - N/A | i) 2 new types of reports produced and used ii) 0 - N/A | i) 60 new types of reports produced and used ii) 45 reports improved | i) 60 new types of reports produced and used ii) 45 reports improved
|  | Achieved |  | 0 | i) 45 new types of reports produced and used ii) 20 | i) 45 ii) 20 | i) 51 ii) 35 | TBD
Source
|  | SIGTAS + Annual Management Survey | [7 empty] | Milestone 2 changed to N/A as this was not completed due to competing priorities of senior management and we are trying to hand over to tax dev.
| Output Indicator 1.4 |  | Baseline: July 2020 (end of 2012 Ethiopian Fiscal Year - EFY) | Baseline: July 2024 (end of 2016 EFY) | Milestone 5 FY4Q3 (31 Dec 2024) (31 Dec 2017EFY) | Milestone 5 end FY4Q4 (31 Mar 2025) (31 Mar 2017EFY) | Milestone 6 - End FY5 Q1 (30 June 2025) (30 June 2017 EFY) | Milestone 6 - End FY5 Q4 (31 Mar 2026) (31 Mar 2018 EFY)
| Improved capacity of Ministry of Revenues IT Officers measured by: i) Number of staff trained (disaggregated by gender); ii) % satisfied with training; iii) Average % improvement in pre-post test | Planned |  | N/A - Baseline | i) 28-33 IT Officers trained ii) 95% iii) 15% | i) 28-33 IT Officers trained ii) 95% iii) 15% | i) 28-33 IT Officers trained ii) 95% iii) 15% | i) 28-33 IT Officers trained ii) 95% iii) 15%
|  | Achieved |  | i) Total = 31 (Male = 21 (68%) // Female = 10 (32%)) ii) % Satisfied with training = 98% iii) N/A - pre & post tests not given for baseline year | i) 30 IT Officers trained (22M / 8F) ii) 100% iii) N/A% | i) 30 IT Officers trained ii) 100% iii) 15% | i) 30 IT Officers trained ii) 100% iii) 15% | TBD
IMPACT WEIGHTING (%) |  | Source
50% |  | TTP Training Database (for i) + Feedback Forms (for ii) + Participant PP Tests/Trainer Reports (for iii)
INPUTS (£) | FCDO (£) |  |  | Govt (£) |  | Total (£)
9002821.5
INPUTS (HR) | FCDO (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline: July 2020 (end of 2012 Ethiopian Fiscal Year - EFY) | Baseline: July 2024 (end of 2016 EFY) | Milestone 5 FY4Q3 (31 Dec 2024) (31 Dec 2017EFY) | Milestone 5 end FY4Q4 (31 Mar 2025) (31 Mar 2017EFY) | Milestone 6 - End FY5 Q1 (30 June 2025) (30 June 2017 EFY) | Milestone 6 - End FY5 Q4 (31 Mar 2026) (31 Mar 2018 EFY)
An improved robust and high-functioning Tax administration system | Number of LTO audit cases started/completed with audit expert support | Planned |  | N/A - Baseline | 2 | 2 | 2 | 2 | 100
|  | Achieved |  | 0 | 0 | 2 | 1 | TBD
Source
Audit Expert and Audit Director (Shared Report)
| Output Indicator 2.2 |  | Baseline: July 2020 (end of 2012 Ethiopian Fiscal Year - EFY) | Baseline: July 2024 (end of 2016 EFY) | Milestone 5 FY4Q3 (31 Dec 2024) (31 Dec 2017EFY) | Milestone 5 end FY4Q4 (31 Mar 2025) (31 Mar 2017EFY) | Milestone 6 - End FY5 Q1 (30 June 2025) (30 June 2017 EFY) | Milestone 6 - End FY5 Q4 (31 Mar 2026) (31 Mar 2018 EFY)
| Number of tax forms revised and/or rationalised | Planned |  | N/A - Baseline | 2 | 2 | 2 | 14 |  | Moving forward this will be estimated as share of domestic tax revenue from filing to total domestic tax revenue adjusted for the impact of debt revenue. See indicator detail sheet for full details. |  | 83% based on revised methodology
|  | Achieved |  | 0 Tax Forms | 0 | 2 | 14 | TBD
Source
Project Documentation (Registration Expert)
| Output Indicator 2.3 |  | Baseline: July 2020 (end of 2012 Ethiopian Fiscal Year - EFY) | Baseline: July 2024 (end of 2016 EFY) | Milestone 5 FY4Q3 (31 Dec 2024) (31 Dec 2017EFY) | Milestone 5 end FY4Q4 (31 Mar 2025) (31 Mar 2017EFY) | Milestone 6 - End FY5 Q1 (30 June 2025) (30 June 2017 EFY) | Milestone 6 - End FY5 Q4 (31 Mar 2026) (31 Mar 2018 EFY)
| Improved capacity of Large Taxpayer Office auditors measured by: i) Number of staff trained (disaggregated by gender); ii) % satisfied with training; iii) Average % improvement in pre-post test | Planned |  | N/A - Baseline | i) 20-25 Trained ii) 95% iii) 15% | i) 20-25 Trained ii) 95% iii) 15% | i) 20-25 Trained ii) 95% iii) 15% | i) 20-25 Trained ii) 95% iii) 15% |  |  |  | As of end of EFY 2013 figures are: 93%,61%,14%
|  | Achieved |  | 0 - No Audit training taken place | i) 0 Trained ii) 0% iii) 0% | i) 11 Trained ii) 100% iii) N/A% (not yet completed) | i) 22 Trained ii) 83.4% iii) N/A | TBD
IMPACT WEIGHTING (%) |  | Source
30% |  | TTP Training Database (for i) + Feedback Forms (for ii) + Participant PP Tests/Trainer Reports (for iii) | [7 empty] | Indicator and methodology changed as previous methodology did not effectively capture what we were trying to. New milestones added based on this. Please see indicator details sheet for full details.
INPUTS (£) | FCDO (£) |  |  | Govt (£) |  | Total (£)
5401692
INPUTS (HR) | FCDO (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline: July 2020 (end of 2012 Ethiopian Fiscal Year - EFY) | Baseline: July 2024 (end of 2016 EFY) | Milestone 5 FY4Q3 (31 Dec 2024) (31 Dec 2017EFY) | Milestone 5 end FY4Q4 (31 Mar 2025) (31 Mar 2017EFY) | Milestone 6 - End FY5 Q1 (30 June 2025) (30 June 2017 EFY) | Milestone 6 - End FY5 Q4 (31 Mar 2026) (31 Mar 2018 EFY)
Strengthened tax policy analysis and legislative drafting capacity in the Ministry of Finance & Ministry of Revenue | Number of pieces of tax policy analysis delivered and accepted by counterparts | Planned |  | N/A - Baseline | 2 | 2 | 2 | 2
|  | Achieved |  | No tax policy analysis delivered in year | 2 | 2 | 2 | TBD
Source
|  | TTP Reporting (Reports from Tax Policy experts); Tax Policy Director | [7 empty] | Milestone 2 adjusted based on reduced LoE and disaggregation set for all milestones to capture element of equity here.
| Output Indicator 3.2 |  | Baseline: July 2020 (end of 2012 Ethiopian Fiscal Year - EFY) | Baseline: July 2024 (end of 2016 EFY) | Milestone 5 FY4Q3 (31 Dec 2024) (31 Dec 2017EFY) | Milestone 5 end FY4Q4 (31 Mar 2025) (31 Mar 2017EFY) | Milestone 6 - End FY5 Q1 (30 June 2025) (30 June 2017 EFY) | Milestone 6 - End FY5 Q4 (31 Mar 2026) (31 Mar 2018 EFY)
| Improved capacity of Ministry of Finance and Ministry of Revenue operational staff measured by: i) Number of staff trained (disaggregated by gender); ii) % satisfied with training; iii) Average % improvement in pre-post test | Planned |  | N/A - Baseline | i) 55-65 legislative drafters trained ii) 95% iii) 15% | i) 55-65 operational staff trained ii) 95% iii) 15% | i) 55-65 operational staff trained ii) 95% iii) 15% | i) 55-65 operational staff trained ii) 95% iii) 15%
|  | Achieved |  | N/A - Baseline | i) 45 legislative drafters trained (28 M / 17 F) ii) N/A iii) N/A | i) 45 various operational staff of the proclamations, regulations and directives trained ii) 100% iii) N/a % Challenges in applying test to the officers meant results could not be captured. Change to approach means the data will be available in future training. | i) 45 operational staff trained ii) 100% iii) N/a % Challenges in applying test to the officers meant results could not be captured. Change to approach means the data will be available in future training. | TBD
Source
TTP Training Database (for i) + Feedback Forms (for ii) + Participant PP Tests/Trainer Reports (for iii)
IMPACT WEIGHTING (%) | FCDO (£) |  |  | Govt (£) |  | Total (£)
10% | 1800564.3
INPUTS (£) | FCDO (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline: July 2020 (end of 2012 Ethiopian Fiscal Year - EFY) | Baseline: July 2024 (end of 2016 EFY) | Milestone 5 FY4Q3 (31 Dec 2024) (31 Dec 2017EFY) | Milestone 5 end FY4Q4 (31 Mar 2025) (31 Mar 2017EFY) | Milestone 6 - End FY5 Q1 (30 June 2025) (30 June 2017 EFY) | Milestone 6 - End FY5 Q4 (31 Mar 2026) (31 Mar 2018 EFY)
Programme is managed effectively and plays a central role in supporting donor coordination on tax | % progress of planned initiatives Green - on track Yellow - delayed Red - Not on track | Planned | Green: 74% Yellow: 5% Red: 21% | N/A - Baseline | Green: 85% Yellow: 10% Red: 5% | Green: 85% Yellow: 10% Red: 5% | Green: 90% Yellow: 5% Red: 5% | Green: 90% Yellow: 5% Red: 5% | 100
|  | Achieved |  | Green: 93.3% Yellow: 0% Red: 6.7% | Green: 94.7% Yellow: 5.3% Red: 0% | Green: 90% Yellow: 10% Red: 0% | Green: 90% Yellow: 10% Red: 0% | TBD
Source
Transformation Dashboard; Workplan; TTP Project Documentation
| Output Indicator 4.2 |  | Baseline: July 2020 (end of 2012 Ethiopian Fiscal Year - EFY) | Baseline: July 2024 (end of 2016 EFY) | Milestone 5 FY4Q3 (31 Dec 2024) (31 Dec 2017EFY) | Milestone 5 end FY4Q4 (31 Mar 2025) (31 Mar 2017EFY) | Milestone 6 - End FY5 Q1 (30 June 2025) (30 June 2017 EFY) | Milestone 6 - End FY5 Q4 (31 Mar 2026) (31 Mar 2018 EFY)
| Effective donor coordination, measured by: a) Quarterly sharing of information b) Number of meetings convened | Planned |  | N/A - Baseline | a) 2 reports shared b) 2 meetings held in the year | a) 2 reports shared b) 2 meetings held in the year | a) 2 reports shared b) 2 meetings held in the year | a) 4 reports shared b) 2 meetings held in the year
|  | Achieved |  | No Baseline data available | a) 1 report shared b) 1 meeting held in the year | a) 1 reports shared b) 1 meetings held in the year | a) 1 reports shared b) 1 meetings held in the year | TBD
Source
TTP Project Documentation; Meeting Minutes
| Output Indicator 4.3 |  | Baseline: July 2020 (end of 2012 Ethiopian Fiscal Year - EFY) | Baseline: July 2024 (end of 2016 EFY) | Milestone 5 FY4Q3 (31 Dec 2024) (31 Dec 2017EFY) | Milestone 5 end FY4Q4 (31 Mar 2025) (31 Mar 2017EFY) | Milestone 6 - End FY5 Q1 (30 June 2025) (30 June 2017 EFY) | Milestone 6 - End FY5 Q4 (31 Mar 2026) (31 Mar 2018 EFY)
| Workplan Agreed | Planned |  | N/A - Baseline | Yes | Yes | Yes | Yes
|  | Achieved |  | Yes | Yes | Yes | Yes | TBD
Source
Documentation of agreement with counterparts/FCDO
| Output Indicator 4.4 |  | Baseline: July 2020 (end of 2012 Ethiopian Fiscal Year - EFY) | Baseline: July 2024 (end of 2016 EFY) | Milestone 5 FY4Q3 (31 Dec 2024) (31 Dec 2017EFY) | Milestone 5 end FY4Q4 (31 Mar 2025) (31 Mar 2017EFY) | Milestone 6 - End FY5 Q1 (30 June 2025) (30 June 2017 EFY) | Milestone 6 - End FY5 Q4 (31 Mar 2026) (31 Mar 2018 EFY)
| Number of minuted SteerCo meetings held annually | Planned |  | N/A - Baseline | 2 | 2 | 2 | 2
|  | Achieved |  | 2 | 1 | 2 | 0 | TBD
IMPACT WEIGHTING (%) |  | Source
10% |  | TTP Project Documentation; Meeting Minutes
INPUTS (£) | FCDO (£) |  |  | Govt (£) |  | Total (£)
1800564.3
INPUTS (HR) | FCDO (FTEs)
100

## Indicator Details (Updated)
| Indicator Name | Detailed Description of Indicator | Assumptions | Cowater's suggestions for IPE Global's scope of work
Impact Indicators |  |  | Note 1: Unless otherwise stated, the focus of the programme until end FY3 will be on the LTO. From FY4Q1 until end of programme (FY5Q4) both the LTO and MTO will be reported on. This programme would only focus on the STO in AA East and West Branches as they are the only federal STO offices.
Impact Indicator 1 | Tax revenue collected by federal government | This indicator represents the total nominal amount of tax revenue collected by the government. Targets given are a floor, meaning that these are the minimum values that the government aims to collect.The source of data for this should be the government's Medium-Term Revenue Strategy, which is updated periodically. Data for this indicator can then be used to give the Tax-to-GDP ratio, which was the previous inidcators representing the Goverrnment of Ethiopia's target ratio according to the Prosperity Plan of the ratio of tax revenue as a percentage of GDP. Data from the National Planning Commission indicates that GDP will grow by 10% on average. Therefore, assuming that tax will be elastic to the growth of GDP, it is estimated that tax will contribute 16.2% to GDP, by 2025. | Data from Medium-Term Revenue Strategy is available, and updated on a timely basis.
Outcome Indicators
Outcome 1 | Voluntary tax compliance increased | This outcome represents quantitative indicators which measure the potential to increase tax revenue. It is best practice in tax reform programmes to increase voluntary compliance rather than punitively effect an increase.
Outcome Indicator 1.1 | No. of active taxpayers as % of total number in the register | This indicator seeks to identify the proportion of taxpayers that are regularly contributing to tax collections, compared to those who are registered and not doing so. It can be used as a proxy for the engagement and compliance levels within the tax system, although does not take into account taxpayers who are registered but earning below the threshold for the period considered. Information on total number of taxpayers in the register, and those who are active, to be taken from SIGTAS reports on an annual basis. Active is defined as taxpayers who have "paid or filed taxes in the past 3 years". | This assumes 1) TTP being given access to the relevant data from SIGTAS; 2) That the data from SIGTAS is up to date and accurate; 3) MoR are on board with sharing this information. Taxpayers who have not submitted a return or a payment during the last 3 years will be archived. The risk is there is a taxpayer who has not been compliant for the last 3 years+ and are archived, so they will not appear in the calculations under active taxpayers, and therefore results may be skewed because of this.
Outcome Indicator 1.2 | % of tax collected from filings/returns vs debt to total domestic tax revenues | This indicator aims to measure the proportion of tax revenue generated from voluntary filings and returns, against the total tax revenues collected. The idea is that as voluntary compliance increases, so will this proportion, therefore acting as a measure of the effectiveness of voluntary compliance measures. Information on total domestic tax revenues collected, as well as tax collected from filings/returns will be obtained from relevant SIGTAS reports. The % calculation will then be based off these figures. | This assumes 1) TTP being given access to the relevant data from SIGTAS; 2) That the data from SIGTAS is up to date and accurate. This also assumes accurate and timely submissions of tax returns, which is something to be cross-checked against audit results or comparisons against expected revenue collections.
Outcome Indicator 1.3 | % of taxpayers with improved perception of the tax system, indicating equitability and fairness | The purpose of this indicator is to measure the perception of taxpayers of the tax system's overall fairness and equitability - i.e. do they feel they are being unfairly targeted, or overtaxed, compared to the rest of the population. It aims to identify areas of perceived inequity or unfairness that could later be addressed. The data from this indicator will be sourced through a taxpayer perception survey, to be conducted annually. The survey will target at least 5% of registered Large taxpayers, from around the country. Questions measuring the perception of fairness and equitabiltiy include : TBC. Respondents will rate their perceptions for each these metrics on a scale of 1-10, and the indicator figure used in this logframe will be an average of the total responses over the questions asked for equitability and fairness. In addition to these quantitative responses, qualitative responses will also be gathered to assess trends on which areas any perceived inequality/unfairness lies.The data for this indicator will be only be collected for large taxpayers, due to the importance of large taxpayers in terms of total revenue collected, and the high volume of small taxpayer surveys that would need to be conducted to get proportionate representation. | This indicator assumes the logic that improved perceptions of the equitabiltiy and fairness will result in a consequent increase in voluntary compliance in tax payments. It also assumes that the perceptions of individuals have a causal link to behaviour
Outcome Indicator 1.4 | % of tax revenue paid on time (Disaggregated by VAT and CIT) | This indicator measures to what extent tax revenue is generated from voluntary payments that do not require further follow-up from the MoR. The data for this indicator is sourced directly from the SIGTAS system. Note that there is currently poor practice because the tax period and due date are not stated in the process when the payment requirement is opened. This means that when extracting a report on tax paid by due date it captures: i) tax paid by due date; ii) tax paid late; and iii) Other which comprises payments for which no due date is issued. We expect to see a reduction in both late and "Other" payment amounts. Note that it is the % of the taxes paid, rather than the % of taxpayers who paid on time that we will measure. | This assumes that TTP will consistently be provided with the relevant data from SIGTAS, and that it is up to date and accurate. We do note that the due date for Large Taxpayers on CIT is November 10th, and therefore not all payments will be captured by the milestone dates of 31st of May, however it is expected that this is capturing sufficient information.
Outcome 2 | A tax environment that encourages business | This outcome measures indicators designed to improve institutional legal and regulatory conditions under which businesses operate, including changes to government policies, laws, regulatory frameworks and administrative practices by public sector entities.
Outcome indicator 2.1 | % of taxpayers using e-filing for VAT and Corporate Income Tax disaggregated by: Large/Medium/Federal Small Tax Office in Addis Ababa | This indicator tracks the adoption rate of e-filing for VAT and CIT among different categories of taxpayers. The idea is that e-filing will ease the burden of tax administration, and increases the ease of doing business, which will therefore result in more taxpayers filing and paying taxes. This measures the efficiency of the e-filing processes and the effectiveness of the promotion of digital platforms for tax compliance. Data obtained from SIGTAS will be used to report against this indicator, which could also be cross-referenced against responses on the taxpayer perception survey about % of which who file using e-filing. | 1) Accuracy of SIGTAS reports on e-filing; 2) Honest/accurate perceptions of taxpayers on their use of e-filing. Depends on adeqaute taxpayer awareness and capacity to use e-filing systems.
Outcome Indicator 2.2 | The time taxpayers take to file taxes. | This indicator is based off the Tax Administration Diagnostic Assessment Tool (TADAT) Performance methodology, focusing on Performance Outcome Area (POA) 4: "Timely filing of tax declaration". The indicator seeks to measure the average time taken by taxpayers to complete and submit their tax filings, which is a measure of the administrative burden on taxpayers, and measures the improvement in efficiency of the tax filing process - factors which ease the operating environment for businesses within Ethiopia. Methodology to be used for this is the self-reporting of taxpayers, as per their answers in the taxpayer perception survey, under questions such as : "How long on average does it take you to file your taxes?". An average will then be taken of all responses, with appropriate disaggregation made. | This assumes accurate reporting from taxpayers, as well as the survey being conducted on a representative sample of taxpayers (e.g. even spread of small/medium/large taxpayers). | IPE to carry out a contribution analysis?
Outcome Indicator 2.3 | The time taxpayers take to pay taxes | This indicator is based off the Tax Administration Diagnostic Assessment Tool (TADAT) Performance methodology, focusing on Performance Outcome Area (POA) 5: "Timely Payment of Taxes". The indicator seeks to measure the average time taken by taxpayers to complete their payment of taxes after the submission of their tax filings. This is a measure of the administrative burden on taxpayers, and measures the improvement in efficiency of the tax payment process - factors which ease the operating environment for businesses within Ethiopia. Methodology to be used for this is the self-reporting of taxpayers, as per their answers in the taxpayer perception survey, under questions such as : "How long on average does it take you to file your taxes?". An average will then be taken of all responses, with appropriate disaggregation made. Delays are primarily due to system interoperability issues between SIGTAS and commercial banks, inconsistent data reporting from regional offices, and continued reliance on some manual payment processes. These factors slow the consolidation and verification of taxpayer payment time data. | This assumes accurate reporting from taxpayers, as well as the survey being conducted on a representative sample of taxpayers (e.g. even spread of small/medium/large taxpayers).
Output indicators
Output 1 | Improved relationships between customers (taxpayers) and government
Output indicator 1.1 | Number of Business Process Transformation (BPT) Standard Operating Procedures (SOPs) developed, agreed and implemented for enhanced SIGTAS functionalities | This indicator seeks to measure both the development of new SOPs (with TTP support) and the implementation of them, which aim at enhancing SIGTAS reporting and functionalities. This measures the improved system efficiency and logically also the data quality. The focus on the success of this indicator will be heavier weighted to SOPs that have been implemented rather than those simply developed, with IPE to potential provide support in verifying those SOPs which are actually operationalised (see IPE Scope >>>). Methodology to measure SOPs developed and agreed wil include reviewing programme documentation on SOPs developed, and documenting GoE approval of those SOPs. To measure implementation, this will involve looking at any GoE implementation records, as well as conducting interviews with key stakeholders (e.g. MoR management) to check whether procedures are being operationalised and utilised effectively, and whether they are having a positive impact. This can be carried out by independent monitors. | Assumes that improvements to the SOPs leads to increase in quality of the data and usability. Also assume GoE collaboration and agreement on the implementation of SOPs, and that they are effectively implemented and adhered to by all staff. | IPE to verify whether SoPs have been implemented (e.g. through interviewing management)
Output indicator 1.2 | Percentage of SIGTAS blocking and critical issues resolved relative to total number of issues in hand during period | This indicator measures the resolution rate of critical issues within SIGTAS, with the objective of measuring the reductions in downtimes and operational disruptions and measuring any increases in system reliability/improvements in usability. Data for this inidicator will be collected using information from the data centre on issues logged/resolved, as well as possibly gathering feedback from system users on issue resolution (triangulation).
Output indicator 1.3 | Number of improved SIGTAS reports: i) # reports produced and used in practice ii) # reports improved | This indicator measures the production and utilisation of enhanced reports generated by SIGTAS, to measure any increases in the practical use of system-generated reports which provide actionable insights and data for decision making within MoR. Data on the number and type of reports can be generated from SIGTAS, while information around their usage and improvements can be gathered from surveys to management. To be disaggregated by types of report (e.g. Revenue reports) generated. Annual Management Questionnaire to establish usage: - Survey to be sent annually to management to determine how the reports are being used, how often and what for - Questions over perceptions of whether the quality of the reports (and date) have improved in the last period [develop baseline and then do it every year] - Questionnaires to contain a question on role in institution | This assumes that the reports are relevant to the user's needs and that user's are subsequently trained on how to utilise these reports effectively.
Output indicator 1.4 | Improved capacity of Ministry of Revenues IT Officers measured by: i) Number of staff trained (disaggregated by gender); ii) % satisfied with training; iii) Average % improvement in pre-post test | This indicator measures 3 core tenets of our capacity building efforts: 1). The number of staff trained within the IT space of MoR; 2) The proportion of which are satisfied with the training received (relevance, length, quality etc.); 3) The % of improvement noted in the pre-post test scores of participants after receiving training. Overall this measures the enhancement of technical skills and knowledge of IT staff. Data for the number of staff trained will be taken from internal TTP programme documentation (e.g. Training logs, disaggregated by gender, institution etc.). Data for the satisfaction levels will be taken from post-training feedback forms which ask questions around perceptions over the training's quality, applicabiltiy, and logistical elements. Data for the improved knowledge will be calculated by taking the average improvement (post-test score - pre-test score) in the scores of each participant . E.g. if the average score before was 60% and the average score after was 70%, then that is an increase of 10 percentage points. Range for IT officers trained based off estimation of number of staff available, factoring in staff changes in the year and expected availability. | In order to obtain the benefit of enhancing the capacity of MoR staff, this indicator assumes one of two things: 1) Staff turnover remains low and that staff trained remain in the positions for which they are receiving training; 2) Sustainabiltiy is taken into account, and training activities leave a legacy (e.g. in terms of training materials/manuals produced with best practices/Training of Trainer approaches, which could be used in handovers for new staff. It also assumes honest feedback from staff receiving training and relevant pre-post tests in relation to the content of the training received.
Output 2 | An Improved Robust and High-Functioning Tax Administration System
Output indicator 2.1 | Number of LTO audit cases started/completed with audit expert support | This indicator measures the number of audits in which TTP experts have supported the process within the Large Taxpayer Office (LTO). The logic is that the presence of the expert will enhance the quality, and ultimately the efficiency of the audit process, which has an impact on the overall functionality of the tax administration and also the perception of taxpayers who may experience more efficient audit experiences. The indicator is a proxy for audit effectiveness and coverage. Data for this can be obtained through both Project and Audit records from both internal TTP and external MoR documentation, on how many audits have been conducted in the period with the support of the TTP expert. Interviews could also be conducted with management in MoR to establish the effectiveness and utiltiy of the audit expert's support. The indicator has been disaggregated by started/completed to take into account the reality of the time often taken to complete an audit process. | This indicator assumes that the input by the audit expert is relevant and helpful for audit staff, and that their input leads to a more effective and efficient audit process. It also assumes that the support provide remains in the institutional memory through either a Training of the Trainer approach, or and audit guide/manual being left behind in the working documents for staff in future years to follow.
Output indicator 2.2 | Number of tax forms simplified and rationalised | This indicator measures the efforts to simplify and streamline tax forms, which ultimately seeks to measure the improved usability of the forms which should have an impact on compliance rates through reducing the administrative burden for taxpayers. The primary source of data for this indicator is project documentation (i.e. the reports from our Registration Expert which will detail the number of tax forms we have provided support for). The secondary source of data, to verify this, could be corresponding agreement from MoR (Registration Director/Filing Director) to implement these forms and this could also be supported with surveys/interviews with taxpayers to gather further feedback on the usability of forms, and supplemented by the Outcome Indicator on time taken to file taxes. | This assumes that the proposed simplified tax forms are then utilised, and then effectively communicated to taxpayers. It also assumes that this will have a corresponding positive impact on taxpayer experience and therefore compliance. | IPE to verify primary source of data with interviews/surveys done with government staff/taxpayers.
Output indicator 2.3 | Average (VAT) refund decision time for traders and service providers (LTO) | The indicator seeks to track the improvements made to the effiency and timeliness of VAT refunds, which should improve taxpayer satisfaction and cashflow. Decision time defined as time within which the taxpayer is informed about the refund amount or whether the refund request has been declined. The primary source of data, when available, would be the World Bank reports, which report on such information. In the absence of this, or to triangulate findings, secondary sources of data could include information from SIGTAS (VAT refund processing times - once this module has been developed) and responses from taxpayer perception surveys from respondents who have reported receiving VAT refunds. | This assumes the accurate tracking of refund request processing times, and the accurate input of this information into SIGTAS, as well as efficient and transparent refund processing procedures. From the taxpayer side, it also assumes honest and accurate perceptions of the refunds times, hence the desire for triangulation. Baseline information may not be as reliable as the report for the first years comes from a manual system, whereas later quality should be more reliable as the refund processing will be through SIGTAS when enhancement takes hold, beginning Year 2.
Output indicator 2.4 | Improved capacity of Large Taxpayer Office auditors measured by: i) Number of staff trained (disaggregated by gender); ii) % satisfied with training; iii) Average % improvement in pre-post test | This indicator measures 3 core tenets of our capacity building efforts: 1). The number of staff trained within the audit department of MoR; 2) The proportion of which are satisfied with the training received (relevance, length, quality etc.); 3) The % of improvement noted in the pre-post test scores of participants after receiving training. Overall this measures the enhancement of technical skills and knowledge of auditors. Data for the number of staff trained will be taken from internal TTP programme documentation (e.g. Training logs, disaggregated by gender, institution etc.). Data for the satisfaction levels will be taken from post-training feedback forms which ask questions around perceptions over the training's quality, applicabiltiy, and logistical elements. Data for the improved knowledge will be calculated by taking the average improvement (post-test score - pre-test score) in the scores of each participant . E.g. if the average score before was 60% and the average score after was 70%, then that is an increase of 10 percentage points. Range for Large Taxpayer Officer Auditors trained based off estimation of number of staff available, factoring in staff changes in the year and expected availability. | In order to obtain the benefit of enhancing the capacity of MoR staff, this indicator assumes one of two things: 1) Staff turnover remains low and that staff trained remain in the positions for which they are receiving training; 2) Sustainabiltiy is taken into account, and training activities leave a legacy (e.g. in terms of training materials/manuals produced with best practices/Training of Trainer approaches, which could be used in handovers for new staff. It also assumes honest feedback from staff receiving training and relevant pre-post tests in relation to the content of the training received.
OUTPUT 3 | Strengthened Tax Policy Analysis and Legislative Drafting Capacity in the Ministry of Finance |  | It has been learned that the implementation of the new business processes is contingent on legal changes, structural changes, human resource and technological changes. Therefore the acquisition of the new technology is a priority and therefore the new milestone makes more sense.
Output Indicator 3.1 | Number of pieces of tax policy analysis delivered and accepted by counterparts | This indicator measures the production, delivery and acceptance (marked by approval of Ministry) of tax policy analyses and recommendations made by TTP experts. Pieces of tax policy analysis includes TTP's evaluation of previous policies, as well as responses to ad hoc demands from MoF to analyse new/proposed policies. Analysis can include impact calculations, desk reviews, comparisons to other countries etc. The indicator seeks to ensure that TTP is providing robust, and useful tax policy advice to MoF to inform evidence-based decision making. Methodology to collect relevant information for this indicator includes review of TTP programme documentation, including the review of pieces of analysis submitted, and tracking the acceptance of these tax policy analyses. Interviews could also be conducted with key MoF staff to assess whether the analysis provided was useful. | Assumes that the counterparts are willing and able to implement recommendations. Achieving the milestone for this indicator is also somewhat dependent on the number and frequency of requests by MoF for policy advice, as well as the timing of this, assuming TTP has adequate capacity to provide tax policy advisory services at the time of the request (and that such requests are in line with TTP objectives).
Output Indicator 3.2 | Improved capacity of Ministry of Finance tax policy officers measured by: i) Number of staff trained (disaggregated by gender); ii) % satisfied with training; iii) Average % improvement in pre-post test | This indicator measures 3 core tenets of our capacity building efforts: 1). The number of Tax Policy Officers trained in MoF; 2) The proportion of which are satisfied with the training received (relevance, length, quality etc.); 3) The % of improvement noted in the pre-post test scores of participants after receiving training. Overall this measures the enhancement of technical skills and knowledge of the staff. Data for the number of staff trained will be taken from internal TTP programme documentation (e.g. Training logs, disaggregated by gender, institution etc.). Data for the satisfaction levels will be taken from post-training feedback forms which ask questions around perceptions over the training's quality, applicabiltiy, and logistical elements. Data for the improved knowledge will be calculated by taking the average improvement (post-test score - pre-test score) in the scores of each participant . E.g. if the average score before was 60% and the average score after was 70%, then that is an increase of 10 percentage points. | In order to obtain the benefit of enhancing the capacity of MoR staff, this indicator assumes one of two things: 1) Staff turnover remains low and that staff trained remain in the positions for which they are receiving training; 2) Sustainabiltiy is taken into account, and training activities leave a legacy (e.g. in terms of training materials/manuals produced with best practices/Training of Trainer approaches, which could be used in handovers for new staff. It also assumes honest feedback from staff receiving training and relevant pre-post tests in relation to the content of the training received.
Output Indicator 3.3 | Improved capacity of Ministry of Finance legislative drafters measured by: i) Number of staff trained (disaggregated by gender); ii) % satisfied with training; iii) Average % improvement in pre-post test | This indicator measures 3 core tenets of our capacity building efforts: 1). The number of Legislative Drafters trained in MoF; 2) The proportion of which are satisfied with the training received (relevance, length, quality etc.); 3) The % of improvement noted in the pre-post test scores of participants after receiving training. Overall this measures the enhancement of technical skills and knowledge of the staff. Data for the number of staff trained will be taken from internal TTP programme documentation (e.g. Training logs, disaggregated by gender, institution etc.). Data for the satisfaction levels will be taken from post-training feedback forms which ask questions around perceptions over the training's quality, applicabiltiy, and logistical elements. Data for the improved knowledge will be calculated by taking the average improvement (post-test score - pre-test score) in the scores of each participant . E.g. if the average score before was 60% and the average score after was 70%, then that is an increase of 10 percentage points. | In order to obtain the benefit of enhancing the capacity of MoF staff, this indicator assumes one of two things: 1) Staff turnover remains low and that staff trained remain in the positins for which they are receiving training; 2) Sustainabiltiy is taken into account, and training activities leave a legacy (e.g. in terms of training materials/manuals produced with best practices/Training of Trainer approaches, which could be used in handovers for new staff). It also assumes honest feedback from staff receiving training and relevant pre-post tests in relation to the content of the training received.
OUTPUT 4 | Programme is managed effectively and plays a central role in supporting donor coordination on tax
Output Indicator 4.1 | % progress of planned initiatives Green - on track Yellow - delayed Red - Not on track | This indicator monitors the progress of TTP initatives by categorising them as either on track, delayed, or not on track. The programme team, including the Team Leader, Project Director and Project Manager, will discuss the status of each initative on a regular (quarterly) basis, and report this progress to the FCDO who will verify if the status matches the description of the latest activities. The objective of this inidcator is to flag the extent of any issues in implementation, and to keep planned programme activities on track. Methodologies to be used in obtaining information for this indicator include: Project Documents (including quarterly meeting minutes, or progress reports) and conversations with initative leads. | Accurate and timely reporting of program initative statuses. Effective project management practices in place, i.e. quarterly meetings/progress reports being produced and reviewed.
Output Indicator 4.2 | Effective donor coordination, measured by: a) Quarterly sharing of information b) Number of meetings convened | This indicator measures the effectiveness of TTP's donor coordination, through not only the number of meetings convened in the year, but also the quarterly sharing of information. This information could include items like: a) What activities are being planned in the coming months? b) What activities are currently under operation? c) What is the status of these operations? d) Where are there opportunities for overlap? The information sharing should take the form of a prescribed template which is circulated and collated each quarter. Information to be captured and stored on TTP Dashboard. | This indicator assumes active participation and engagement from all donors, as well as effective communication and information-sharing mechanisms being put in place.
Output Indicator 4.3 | Workplan Agreed | This indicator measures whether the TTP workplan has been agreed with counterparts and FCDO. Acceptance of the workplan should be documented and saved for reference. TTP dashboard to be updated upon agreement. | Assumes consensus reached among stakeholders on the workplan (including on activities and timelines) - risk that this could be delayed. Also relies on effective communication and negotiation processes.
Output Indicator 4.4 | Number of minuted SteerCo meetings held annually | This indicator monitors the oversight and governance of the programme, as measured by the number of steering committee meetings held each year. Such meetings should contain accurate minutes recorded and circulated by participants, including discussion points, agreed items, and actionable steps. Such minutes should also contain the details of attendees.TTP dashboard to be updated after SteerCo meetings held. | Assumes the regular scheduling and participation in SteerCo meetings, as well as the effective documentation and follow-up on meeting outcomes.

## Change Frame (OLD)
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
1 | Outcome 2, Indicator 1 | Milestones 3 and 4 amended to "null". Customs workstream was removed because of budget cut. This data is not being calculated and is not available without a customs advisor. It is very unlikely that we will start the customs work again, since we will not get additional budget and only have one year left on the project | TTP | 2022-12-07
2 | Output 1, Indicator 4 | Milestones 3 and 4 amended to "null". Project is no longer working directly towards this indicator (e.g. on taxpayer comms), as we are only working on key technical support within the Ministry itself. This specific dimention is not included in MoR's Taxpayer Satisfaction Survey (TPSS), TTP have asked MoR to incorporate it, however they have not agreed. TPSS is for MoR, so ultimately MoR can't be expected to revise it based on TTP's needs. There is a similar indicator at Outcome Level (2.4), which uses the information which is available under TPSS, and perhaps the outcome level is more appropriate for this sort of indicator. The Outcome indicator 2.4 already uses the TaxPayer satisfaction survey, so a source of similar information is already available within this logframe. Therefore, this indicator is not needed, in addition to being unmeasurable. | TTP | 2022-12-07
3 | Output 1 | Impact weighting amended to 30% | TTP | 2022-12-07
4 | Output 2, Indicator 1 | Milestones 3 and 4 amended to "null" . We are not doing any work in this technical area. Therefore, this indicator is completely out of TTP's control. | TTP | 2022-12-07
5 | Output 2, Indicator 2 | Milestones 3 and 4 amended to "null" . We are no longer working on customs. No longer within our sphere of influence. No expert responsible | TTP | 2022-12-07
6 | Output 2, Indicator 4 | Indicator amended to "average LTO VAT refund time (days)"; Milestone 3 amended to 15; Milestone 4 amended to 12. TTP advisors & coordinator have improved and depoyed new VAT refund model and are now looking to create a data source. However, will only be able to collect data at the LTO level, so we have proposed to focus the indicator on the LTO only. The new model will improve VAT refund time. | TTP | 2022-12-07
7 | Output 2 | Impact weighting amended to 10% | TTP | 2022-12-07
8 | Output 3, Indicator 1 | Milestone 3 amended to "Procurement of ITAS initiatied"; Indicator for Milestone 4 amended to "Procurement of ITAS and e-invoicing completed". A key focus of our BPT work has been harmonizing business process transformation with preparation for the new ITAS. This is a key priority for both MOR as well as BE, recognised by the provision of support via the Procurement Agent (separate to TTP). Therefore we have updated our milestones to reflect how interwoven our BPT work is with ITAS. Our final proposed milestone is ambitious but we hope achievable, representing a key legacy for TTP. | TTP | 2022-12-07
9 | Output 3, Indicator 3 | Milestone 3 amended to 13%. Althought we are no longer supporting directly, we have provide enough support in the past and can still measure this indicator. As such, we have proposed a milestone for March 2023, though this was previously removed in light of the fact that our support here was cut | TTP | 2022-12-07
10 | Output 3 | Impact weighting amended to 30% | TTP | 2022-12-07
11 | Output 4, Indicator 1 | Milestones 3 and 4 amended to "null". Currently, none of our advisors have full-time days available due to successive budget cuts. However, simply to deliver on our core workplan activities, they often need to work days they cannot bill. There is no resourcing available at all for organisational health initiatives measured by this indicator. | TTP | 2022-12-07
12 | Output 4, Indicator 2 | Milestones 3 and 4 amended to "null". MoF can't produce tax expenditure report without the help of TTP's advisor who no longer works for TTP because of budget cut. | TTP | 2022-12-07
13 | Output 4 | Impact weighting amended to 0% | TTP | 2022-12-07
14 | Output 5, Indicator 4 | Milestone 3 amended to 1; milestone 4 amended to 2. The new milestones reflect the high-level buy-in TTP has, with very senior officials making time to attend our SteerCos. Being realistic about their schedules means concentrating on less frequent and more impactful SteerCos - this is the strategy we have taken in practice, and reflecting it in the logframe is appropriate. | TTP | 2022-12-07
15 | Output 5 | Impact weighting amended to 30% | TTP | 2022-12-07