## Annual Review Template
## Tax Transformation Programme
## 2026

Title: Tax Transformation Programme (TTP)
Programme Value £ (full life): £24m		Review date: / April 14, 2026
Programme Code: 300553	AMP start date: 12 April 2018	AMP end date: 30 June 2028

Summary of Programme Performance
Year	2018/19	2019/20	2020/21	2021/22	2022/23	2023/24	2024/25	2025/26
Overall Output Score	A	B	A	A	A	A	A	A
Risk Rating	Major	Major	Major	Major	Major	Major	Major	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/45010791.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/S30055319.xlsx

List of Key Acronyms

AR: Annual Review
BE: British Embassy
BC: Business Case
BPT: Business Process Transformation
CBU: Capacity Building Unit
DPO: Development Policy Operations
ETB: Ethiopian Birr
EY: Ethiopian Calendar Year
EFY: Ethiopian Fiscal Year
EU: European Union
FY: Financial Year
GoE: Government of Ethiopia
GDP: Gross Domestic Product
HMRC: Her Majesty's Revenue and Customs
IMF: International Monetary Fund
ITAS: Integrated Tax Administration System
KPIs: Key Performance Indicators
LTO: Large Taxpayers Office
MTO: Medium Taxpayers Office
MoR: Ministry of Revenues
MoF: Ministry of Finance
MoF TPU: Ministry of Finance Tax Policy Unit
MTRS: Medium Term Revenue Strategy
NRET: National Revenue Enhancement Taskforce
OANDA – Online Automated Network Data Access
ODA – Overseas Development Assistance
PAF: Performance Assessment Framework
SIGTAS: Standard Integrated Government Tax Administration System
SOPs Standard Operating Procedures
STO: Federal Small Taxpayers Office
TTP: Tax Transformation Program me
TSEI: Taxpayer Services and Engagement Improvement
TSTP: Tax Systems Transformation Programme
TTO: Tax Transformation Office
ToC: Theory of Change
TADAT: Tax Administration Diagnostic Assessment
VFM: Value for Money
WB: World Bank

A. SUMMARY AND OVERVIEW
Description of the programme
1) The Tax Transformation Programme (TTP) business case was approved on 6 November 2017 with a total budget of up to £35 million over 5 years, all to be provided in technical assistance. The MoU with Government of Ethiopia was signed on 8 August 2018. The contract was signed with Cowater International, the main supplier, on 13 March 2019, to deliver the programme using the accelerated Delivery Unit (DU) approach. The DU approach is characterised by performance dialogue and decision-making process at the highest levels of government involving the Prime Minister and other key Ministers like the Minister of Finance and the Minister of Revenues.
2) The programme’s overall purpose was to transform Ethiopia's tax system. Specific objectives included increasing domestic revenue mobilisation and improving the investment climate, aiming to play a key role in supporting Ethiopia to self-finance and deliver its ambitious growth plan. However, during 2020-2022, the programme faced a rapidly changing and challenging operating environment. Large shocks, including 2019 droughts, Covid-19, the Tigray war, two rounds of drawdowns of international staff, growing macroeconomic crisis, high inflation, as well as ODA reductions and budget cuts had knock-on effects on the initial pace, scope and impact of the programme’s implementation.
3) These shocks prompted the programme team to make a deliberate shift in TTP's focus from ambitious transformation to stabilisation of core functions during the first round of extension in 2023, namely: i) Standard Integrated Government Tax Administration System (SIGTAS) - Ministry of Revenues Data and IT system, ii) Taxpayer Service and Compliance Improvement, and iii) Tax Policy/Legislation. The 2023 business case addendum and contract agreement extended the programme until end of March 2026. With the introduction of the macroeconomic reform initiative in 2024, and the IMF Externded Credit Facilities and World Bank Development Policy Operations, domestic revenue mobilisation became a fundamental objective of the Government with considerable ambition to increase the tax:GDP ratio by 1% per annum. This opened the window of opportunity for the TTP programme to have a substantial impact, and FCDO received requests from GoE, World Bank and IMF for this programme to support on these ambitious targets.
4) Responding to this opportunity, the programme was extended for a second time in 2025 with an end date of June 2028. The main purpose of this extension is to align with the IMF and World Bank-supported macroeconomic reform programme and respond to the reform demands flexibly. The extensions reduced the programme budget from the original £35 million to £24 million overall because of budget cuts.
5) Tax reform holds a pivotal role in the macroeconomic reform package because the success of the reforms depends on improvement in revenue mobilisation. The IMF requires Ethiopia to increase tax revenue by a minimum of 1% GDP a year. The World Bank also supports domestic revenue mobilization to become more efficient. Therefore, the Government of Ethiopia has committed to a National Medium-Term Revenue Strategy (NMTRS).  The NMTRS covers a range of policy and administrative reforms, aimed at increasing revenues by 4 percentage points of GDP over the 4 years of the macroeconomic reform period.
6) Subsequently, the GoE formed a National Revenue Enhancement Taskforce (NRET), chaired by the Prime Minister’s Office, emphasising their political commitment to revenue collection and reform. Despite this high-level attention, capacity within the MoR and MoF remains limited and TTP advisers are closely involved in a technical level taskforce reporting to the NRET. TTP has maintained excellent relationships with policymakers and officials. Long term embedded advisers, supported by TTP since 2019, are highly trusted by Ministers and senior officials in the Prime Minister’s Office, MoR and MoF, as well as among development partners including the WB and IMF. Consequently, the programme has been well placed to respond quickly and flexibly to increased demands over the last year.
7) Importantly, the tax programme’s advisers provide BE Addis with access and influence to Finance and Revenue Ministries. The programme’s Steering Committee is chaired by the Minister of Finance and attended by the Minister of Revenues, as well as senior officials of these Ministries. FCDO’s Development Director and other key staff of the programme as well as the Cowater International (the main supplier) are members of this Steering Committee. The Steering Committee makes decisions on key policy and implementation issues related to the programme. The programme also provides us with a convening role amongst existing and upcoming development partners in the tax reform space in Ethiopia, enabling the UK to provide leadership across the development community. Keeping the revenue reforms on the road and influencing business friendly taxation can also provide benefits for the wider UK-Ethiopia relationship and associated objectives.
8) This Annual Review has been supported by independent evaluation[1]. The evaluation team assessed progress against the workplan, weaknesses of the Government Tax System and proposed priority intervention areas going forward. The evaluation report confirms strong performance of the programme. The findings and recommendations of the evaluation team focus on the broader tax system. The programme annual review team therefore selectively adapted the recommendations to serve the purpose of this review.
[1] British Embassy Addis Ababa contracted IPE Global who have reviewed the programme and provided their independent views.
9) The programme team is developing a sustainable strategy for responsible exit by the end of the programme in 2028. The programme will move from the business-as-usual support in which the programme experts and advisers fix problems; to a modern development partnership approach where interventions focus on systems strengthening and delivering against Smart TA principles. The exit strategy will set out what the government should be able to do independently by 2028 and how progress of the programme’s intervention will be tracked during the remaining two years. The team will also refresh the Theory of Change and the logframe to reflect this strategic shift and provide a clearer attribution story.
10) Sustainability strategy and responsible exit. With two years remaining, TTP is implementing a deliberate and structured exit strategy shifting focus to enabling the MoR to continue with the reforms beyond TTP in a sustainable manner with responsibility and accountability. The goal is building long‑term institutional capability within the MoR. The programme’s exit approach is centred on ensuring that core tax administration functions can be operated, maintained and improved independently by the MoR by 2028. This includes a progressive reduction in direct delivery by TTP advisers and a corresponding increase in Ministry ownership across IT systems, compliance processes, and operational policy implementation. Success at exit will be measured not only by the completion of activities, but by the Ministry’s ability to operate enhanced systems, apply procedures more consistently, and manage reform without excessive reliance on external technical assistance.
In practice, the exit strategy is implemented by embedded advisers through skills transfer across the programme’s priority areas (tax compliance, data/IT, business process transformation, tax policy and legislation). These include the development of designated super‑users, internal trainers and change managers within the Ministry; systematic mentoring and co‑delivery rather than parallel delivery; and the creation of a central repository of standard operating procedures, manuals and training materials to be retained and used beyond the life of the programme. In the IT domain, sustainability will be evidenced by enhanced SIGTAS functionalities operating as designed, with implementation and maintenance increasingly driven by Ministry staff, and by the gradual assumption of technical responsibility by the Ministry’s IT Centre. A jointly owned sustainability and exit roadmap, with monitorable KPIs, will be finalised and tracked through to programme.
11) Systems strengthening and shift away from service delivery. Across its interventions, TTP is deliberately shifting from doing the work the Government should do such as in the case of DATA/IT, legislative drafting and opinions towards enabling the MoR through system strengthening that builds sustainable institutional capability. While periods of hands‑on support were necessary to prevent system failure and respond to acute capacity constraints, particularly in SIGTAS and compliance functions, the programme is now prioritising reforms that embed skills, processes and systems within the Ministry. This approach aligns with modern development partnership principles and SMART technical assistance, emphasising country leadership, capability transfer, and long‑term functionality.
This shift is evident across multiple workstreams. In IT and data, TTP support has moved from resolving critical issues to developing business‑led system enhancements, standard operating procedures, and internal development capacity within the Ministry’s IT Centre. In compliance and audit, expert support is increasingly focused on hands‑on case mentoring, peer learning, and institutionalisation of practices such as non‑filer management, rather than ongoing external execution.
12) Attribution and additionality - what TTP has achieved this year. While recent improvements in domestic revenue mobilisation reflect a combination of political commitment, macroeconomic reform and government action in tax legislation and administration, TTP has played a clear and additional role in enabling these outcomes by addressing binding technical, institutional and systems constraints within Ethiopia’s tax system. The programme’s contribution is not claimed as sole attribution for revenue increases, but as targeted additionality that enabled reforms to be designed, implemented and operationalised at pace and on scale. TTP focusses on reforms that will have longer-term impact on revenues rather than short-term gains even though it gave a hands-on quick wins to help with immediate revenues.
First, TTP made a material contribution to revenue performance through compliance and administration reforms. The programme designed and supported the implementation of non‑filer identification and follow‑up programmes, including the development of SIGTAS reporting tools, procedures, and training for officers. These initiatives strengthened follow‑up on non‑filers, non‑payers and nil‑filers and are now being institutionalised as standard practice within the Ministry. TTP also supported the enhancement of SIGTAS to operationalise new legislative requirements, including quarterly advance payments and the Minimum Alternative Tax, without which timely implementation would have been significantly delayed. These interventions directly supported the Ministry’s ability to translate policy changes into collectible revenue.
Second, TTP played a central role in tax policy and legislative reform during the year. The programme contributed directly to the drafting of major tax proclamations, regulations and directives approved in 2025, including through analytical inputs, interpretation of provisions, and extensive training of Ministry of Finance and Ministry of Revenues staff on application and implementation. In fact, the policy and legislative adviser contracted by the TTP played a leading role in all these activities from drafting stage. TTP’s earlier income tax policy analysis informed the Income Tax Proclamation Amendment, while ongoing technical support enabled faster and more consistent rollout of legislative changes. This policy‑to‑implementation support represents clear additionality, bridging gaps in analytical and drafting capacity.
Third, TTP’s support to SIGTAS stabilisation and enhancement was critical to maintaining system functionality and enabling delivery reform. The programme addressed blocking and critical system issues, developed new modules and reports, integrated legislative changes, and supported data cleansing strategies and procedures. Without this support, there was a high risk of system stagnation or failure, undermining compliance efforts and revenue collection. Importantly, responsibility for key reporting and system functions has begun to be transferred to the Ministry’s IT Centre, demonstrating both attribution and progress towards sustainability.
Fourth, TTP delivered additional value through development partner coordination and strategic convening. The programme provided a focal point for tax reform partners, reducing duplication, aligning support with government priorities, and enabling coherent sequencing of reforms. This coordination has helped ensure that external assistance complements, rather than overwhelms, limited government capacity and has positioned the UK as a trusted and influential partner in Ethiopia’s revenue reform agenda.
13) The table below summarises performance, attribution of the programme and shift towards systems strengthening in line with Smart TA principles[2]. Specific interventions as parts of shift towards systems strengthening will be further refined during the workplan discussion in April 2026. The third column below highlights TTP’s leading, supporting or problem fixing role. In future, as set out in column 4, the programme will step back from leading or problem fixing role to focus on backstopping and systems strengthening.
[2] Smart TA responds to a shared vision between the supporting and counterpart organisations and can only operate as part of a collaborative partnership. It follows four basic principles: 1) Rooted in Diagnostics; 2) An organisational view; 3) Constructively political; and 4) Success, not failure, is rewarded.
Logframe results area	Performance during the year	The programme’s attribution	Shift towards systems strengthening going forward
1) Tax revenue increment	The tax revenue has sharply increased, exceeding expectations.	Tax revenue increment is a result of cumulative effort including political commitment, tax policy and legislation, and tax administrative process improvements. TTP role is significant in tax legislative amendments, tax process improvement and e-taxation. Quantifying is difficult and any attempt would be disputable.	TTP will focus on reforms that will have longer term impact on revenues rather than short term gains in its intervention of systems strengthening.
2) Voluntary Compliance: simplifying tax payment process and improving monitoring of taxpayers	This result area is about simplifying tax payment process and paying taxes on time – from active filing and debt as well as by tax types (value-added tax, corporate income tax). The performances have met expectations.	- TTP has led direct SITGAS enhancements enabling better monitoring of taxpayers / - TTP has led simplification of procedures and processes to improve voluntary compliance. / - TTP has led Taxpayer Services and Engagement Improvement Strategy based on the perception survey results. / - TTP has supported (not led) MoR’s reporting capacity in data warehouse on taxpayers who have paid on time or not for day-to-day management of filers and payers. / - TTP has supported in rapidly resolving blockages and continuously enhancing user-friendly features	- Supporting this aspect of the system will be transferred to the IT Centre of the MoR in full; only providing advice as needed. / - This will continue to be supported, and reform institutionalised at MoR (through transfer of capacity). / - TTP will support the Ministry with planning and executing measures to improve the areas of weakness the survey has indicated, as captured in the action plan. / - This support will be institutionalised at MoR (through transfer of capacity), the ministry assuming full role. / - This is more MoR led but TTP will further support in embedding capacity and institutionalisation.
3) Processes, procedures and systems reforms	This result area is about tax administration systems (SIGTAS functionality, data management, Standard Operating Procedures, different tax processing forms, registration, tax audit, etc). This result area also performed well meeting expectations overall- although some challenges like weaknesses in tax audit persisted.	- TTP has led streamlining processes to align workflows and create system enhancements / - TTP has trained IT Centre officers in both classroom and practical module development, troubleshooting, and maintenance. / - TTP has led procedural enhancement reforms to improve tax compliance in tax audit case managements.	- TTP will support implementation through user acceptance testing, and training. The training will be done on Training the Trainer to enable internal capacity. / - Going forward, TTP will involve the MoR IT officers in the development of the new functionalities and continue providing targeted intervention of resolving issues. / - The implementation of Audit Case Management System will continue through hands-on case mentoring and peer learning. There will also be creation of a central repository of standard operating procedures, manuals and training materials to be retained and used beyond the life of the programme.
5) Tax policy and legislative changes	This result area is about tax policy and legislative changes and related capacity improvement. Delivery on policy and legislative amendment has been impressive. However, progress on capacity development training has not moved as desired due to delay in recruitment of staff by the MoF. The policy and legal drafting staff in the MoF are very few and often over stretched.	New tax policy was developed in 2023/24 by a joint team of experts contracted by TTP and TaxDev. Based on the Tax Policy, the TTP Tax Policy and Legislative Adviser led the drafting of law amendments and directives. He led explanations to Ministry of Justice, Council of Ministers, Parliament, and interest groups. He also led training to different tax officers to support implementation of the new rules.	Going forward, the TTP adviser will play supportive role instead of leading role. This has already been agreed with the Ministry of Finance Legal Affairs and Policy Directorate. For example, instead of the TTP Adviser drafting law amendments and directives, the MOF staff will draft and seek his comment and advice.

Summary supporting narrative for the overall score in this review
Overall, outputs met expectations which led to the overall score of “A” for this Annual Review.
The independent evaluation team has summarised that,
‘The TTP has continued the path of positive changes initiated following the extension in 2024. The programme’s support focused on strengthening SIGTAS (MoR’s data and IT system), compliance improvement and policy/legislative frameworks. These included SIGTAS stabilization, SIGTAS enhancement, IT governance strategy, tax registration and segmentation, making improvements to filing of different tax types (VAT, CIT, withholding tax) as well as non-filers and loss-filers, tax audit case management, excise reforms, debt management, taxpayer communication and services, change management, and tax policy and legislative frameworks’’.
	Output	Sore	Weighting %
1	SIGTAS system is enhanced, and data quality is strengthened	A	50
2	An improved robust and high-functioning Tax administration system	A	30
3	Strengthened tax policy analysis and legislative drafting capacity in the Ministry of Finance	A	10
4	Programme is managed effectively and plays a central role in supporting donor coordination on tax.	A	10

Key achievements (A summary of activities showing progress during the year is annexed to this Annual Review.)
1) Revenue mobilization
Tax revenue has increased sharply during the last two years of the macroeconomic reform period. Total revenue has increased from 513 billion birr in 2023/24 to 900 billion birr in 2024/25, an increase of 75% in nominal terms. In the first six months of the current Ethiopian fiscal year (2025/26), the MoR reported collection of 709 billion birr, nearly about 80% of the 2024/25 full year collection. Following the high performance of the first six months, the government increased annual revenue target from the initial 1.2 trillion birr to 1.5 trillion birr. Tax revenues have increased in constant prices for the first time in 2024/25, reversing the previous decline over several years. During the Tax Reform Donor Coordination[3] meeting on 5 March 2026, both IMF and World Bank representatives indicated that the tax to GDP ratio has increased to 7.8% in 2024/25 and projected to 9.1% in 2025/26, increasing by about 1.3% annually. Ethiopia’s tax to GDP ratio is one of the lowest even by the Sub-Saharan African standard whose average is estimated at about 15%. Ethiopia’s tax to GDP ratio deteriorated starting from about 12% in 2014/15, reaching a low of about 6.5%, a year before the macroeconomic reform implementation.
[3] Tax Reform Donor Coordination meeting is a forum of donors that takes place twice in a year. The objective of the forum is to coordinate their support and avoid duplication.
Quite a substantial amount of the revenue gains came from changes in legislation in which the TTP’s Tax Policy and Legislative Adviser played a key role through drafting proclamations, regulations and directives supplemented by extensive training to the MoF and MoR officers on the application of the legislative changes. Moreover, TTP has supported enhancing of SIGTAS to build functionalities for the processing of quarterly advance payments and the 2.5% minimum alternative tax (the two major amendments in income tax law). TTP has also contributed by designing and implementing a non-filer identification and follow-up programme, as well as by providing training to tax officers and giving technical support.
2) IT Systems (SIGTAS functionality and enhancement)
Significant progress has been made in stabilising and upgrading SIGTAS including e-taxation. Enhancements focused on improving taxpayer services and internal efficiencies through the rollout of improved case management modules, upgraded dashboards, and new SIGTAS integrations. The technical team deployed new modules to improve taxpayer authentication and focused on adapting SIGTAS to legislative changes, integrating the National ID (Fayda) within the TIN in SIGTAS.
Consequently, e-taxation (e-filing, e-payment, e-registration and e-clearance) has shown impressive progress. For example, the coverage of e-filing has reached 95% on average (100%, 95% and 86% for large taxpayers, medium taxpayers and small taxpayers respectively). These changes represent a substantial improvement in the efficiency and convenience of the tax payment process, significantly contributing to compliance improvement to Federal and Addis Ababa taxpayers. Figure 1 on page 9 shows the progress overtime.
3) Tax policy and legislative amendment
To achieve the revenue targets, different tax proclamations were amended and approved by parliament in July 2025. These included introduction of ‘Minimum Alternative Tax’, advance payment on a quarterly basis, introduction of VAT in financial institutions and utilities, tax expenditure overhaul, and new property tax legislation. In addition to legislative amendments, different directives, operational improvements, and training workshops were supported to help the government move on to the implementation of the changes.
As stated above, TTP played a primary role with drafting the laws, interpreting the key provisions, writing the various directives and providing training to officers.
 4) Data Cleansing, Registration, and Filing
There is renewed political emphasis on data cleansing, taxpayer registration, and filing compliance. Taxpayer registration form rationalisation advanced significantly in preparation for upcoming data cleansing efforts, including the new Economic Classification Standard (ISIC) and missing information in SIGTAS, such as email addresses. Efforts are underway to identify non-filers, zero-filers, and credit-filers, with a data cleansing exercise targeted for completion by July 2026.
TTP developed a comprehensive strategy for data cleansing, developed ToRs for MoR's data cleansing team, provided training and currently supports the cleansing effort. In addition, TTP identified gaps with the MoR's existing practice that led to errors in the registration database and taxpayer accounts database, which is used as a starting point for the data cleansing effort.
 5) Communication and Taxpayer Services
A review of the newly revamped website was conducted, and The Ministry of Revenues’ Taxpayer Services and Engagement Improvement (TSEI) Strategy was finalised. The programme supported review of the newly revamped Ministry website and recommended features for improvement. Tax laws, amendments and directives are now directly uploaded to the website. The absence of an active website had been a serious gap leading to complaints from reviewers and businesses. TTP has also initiated change management focusing on the leadership and communications directorate.
6) Training and Capacity Development
More than 8 training sessions and workshops with over 255 attendees have been delivered, along with training on the new Income Tax law to foster a shared understanding of the updated legislation. Additional training was also provided on Excise Tax and Data Analytics. Training has been conducted with a physical, hands-on approach, including Excise inspections, non-filer inspections, and audit inspection. (The table showing types of training and number of people trained is annexed to this Annual Review with data disaggregated by gender).
8) Development Partner Coordination and External Support
TTP has been playing a convening role intended to ensure coordination, avoid duplication, and foster experience sharing. Internally, the TTO provided direct support to the Director of Strategic Partnerships of the MoR. Externally, TTP facilitated and chaired development partner coordination meetings during the year ensuring timely information exchange and coordination. This is particularly important given the risk that a large number of reform priorities across different partners can overwhelm the Ministry’s absorptive capacity. Moreover, the programme has created an engagement sheet where every tax partner regularly updates covering specific areas of their interventions. This has facilitated not only partner coordination but also reduced transaction costs of communicating with every partner separately.
Lessons
Implications of broader governance challenges. To inform the TTP interventions, a Political Economy Analysis (PEA) was conducted in July 2025. The analysis confirmed that the tax administration cannot be divorced from the broader governance challenges. Reforms must balance technical precision with pragmatic realism, prioritising basics while embedding longer-term cultural shifts, such as fostering a compliance-centric ethos. The political context, staff competence, transparency and accountability, and quality of systems in place will continue to have significant implication on the tax administration.
Sustainability concerns. The sharp recovery in tax revenues in 2024/25 demonstrates that Ethiopia retains significant untapped revenue potential. However, an enforcement-driven approach raises sustainability concerns. Continued reliance on short-term measures and discretionary practices risks undermining voluntary compliance and weakening the investment climate. Without parallel improvements in core tax administration systems, broadening the tax base, audit quality, risk management, and taxpayer services, recent gains may prove fragile and difficult to sustain. Understanding this concern, TTP has helped development of a tax revenue strategy and roadmap and will continue to focus on long-term systems strengthening.
The need for continuous training. The evaluation team has observed that the training across MoR remains largely traditional, classroom-based, and has limited reach and sustainability. There is no systematic use of online or video-based learning platforms, and training is typically accessible to only a small number of staff at any given time. High staff turnover in previous years has further diluted the impact of such training. The TTP team has discussed the gaps in training and proposed online training as one option. The MoR decided to proceed with classroom-based training. The TTP team will continue to offer different skills transfer options including mentoring and peer-learning.
Summary of major recommendations
Shift from service delivery or problem fixing to systems strengthening. This shift is in line with the modern development partnership approach, where in future TTP’s interventions will focus on systems strengthening and delivering against Smart TA principles. This is about enabling the MoF and MoR to continue with the reforms beyond TTP in a sustainable manner with clear responsibility and accountability.
A strategy for sustainable exit. The exit strategy and roadmap will set out what the programme and the GoE institutions should be doing and how progress will be tracked. A jointly owned and monitored set of KPIs will need to be finalised in April 2026.
Materials to be used beyond the life of the programme. TTP will help in creation of a central repository of standard operating procedures, manuals and training materials to be retained and used beyond the life of the programme.
Theory of Change and the logframe refresh. The programme team will update the theory of change and logframe to reflect the strategic shift, and ensure the indicators and milestones are substantive and relevant to the final years of the programme.
Refine the workplan with clearer roles and responsibilities between MoF/MoR and TTP, making the attribution more explicit.
Tax partner coordination - Continue to play a convening role in partner coordination, ensuring alignment with the Medium-Term Tax Revenue Strategy (MTRS). This will help avoid duplication, assist resource optimization and support a sustainable exit/transition.

B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme's theory of change, including any changes to outcome and impact indicators from the original business case.
There were no revisions to the Theory of Change or to the outcome and impact indicators during the reporting year. The programme's emphasis shifted from a broad tax transformation agenda towards a stabilisation-focused approach in 2023, and lately towards alignment with the macroeconomic reform programme responding to demands flexibly since 2025. The outcome indicators have continued to focus on voluntary compliance and taxpayer services improvement while the impact level indicator has continued to prioritise revenue increment.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
The programme is on track to contribute to achieving the impact objective of increased revenue mobilisation. During the year, there has been a marked revenue increase due to the heightened political commitment mainly reinforced by IMF and World Bank reform support. The programme seized on these opportunities and responded proactively both in tax administration and tax policy measures, significantly contributing to both impact and outcome level indicators as discussed in other sections of this annual review.
In the year ahead, the programme will reduce direct hands-on support and prioritise knowledge and skills transfer to MoR and MoF staff to build their technical skills, and confidence to independently manage core tax administration and policy functions respectively. This is in line with the shift to Smart TA principles. The programme will also revise the theory of change and logframe to reflect the changing context.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio.

The TTP has been extended to June 2028 in order to align with the macroeconomic reform programme of the GoE. Its continuation for the coming two years is essential not only to consolidate the gains that have been achieved so far but also to capitalise on real political commitment and support delivery of the targets agreed with IMF and World Bank.

The programme will also continue to play a pivotal role backstopping the tax system reform as the GoE’s commitment increases, more partners show interest to support tax reform and Foreign Direct Investors (FDIs) explore opportunities in Ethiopia in tandem with macroeconomic reform.

Impact: GoE can self-finance its development through increased, sustainable revenue collection
### Indicator 1.1: Tax revenue collected by the Federal Government
Revenue collection has sharply increased over the past two years. As summarised in the preceding section, tax revenues have increased both in constant prices and in tax to GDP ratio. The agreement with IMF under the macroeconomic reform framework is to increase tax revenues by 1% every year during the reform period. The performance so far indicates that the GoE exceeded this figure attaining about 1.3% growth.
### As indicated earlier, the tax revenue collection has increased sharply during the year. To achieve the revenue targets, different tax legislations were amended and approved by the parliament in July 2025. The amendments mainly focus on broadening the tax base instead of increasing tax rates. The amendments also try to close leakages in different types of taxes (income tax, excise tax, VAT, etc). The major changes were 1) introduction of ‘Minimum Alternative Tax’; 2) modest increases in some areas of taxes like payments on dividends, interests, etc.; 3) advance payment requiring taxpayers to pay income taxes every quarter instead of annual payment after end of the year; 4) introduction of VAT in financial institutions and utilities; 5) overhauling of investment incentive/tax expenditure provision; 6) further explaining the federal and regional revenue allocations that encourages regions to mobilise more domestic revenue from sources like agricultural taxes and land use fees.
Outcome 1: Improved Voluntary Compliance
Outcome Indicator 1.1: Number of active taxpayers as % of total number in the register
(The progress with this indicator is not being reported during the year as it stabilised at a high target percentage in the earlier years. Previously, TTP's contribution was on supporting SIGTAS to produce a report on active and inactive taxpayers based on standard rules the Ministry had adopted).
Outcome Indicator 1.2: % of tax collected from filings/returns to total domestic tax revenues
The MoR has reported that this indicator is on track to achieve its milestone of 90% of tax collected from filing/returns and has already exceeded the 10% target from debt. During the first half year performance review that covers July-December 2025, the figures were 88% and 12% respectively. The higher-than-target performance in debt collection indicates improved follow-up and enforcement efforts. As stated earlier, TTP has led preparation of taxpayer engagement strategy and will continue to support its implementation for further compliance improvement from filings.
Outcome Indicator 1.3: % of Taxpayers with improved perception of the tax administration system, indicating neutrality and fairness

Outcome Indicator 1.3: “The percentage of taxpayers with improved perception of the tax system, indicating equitability and fairness.”; Outcome indicator 2.2: “The time taxpayers take to file taxes” and Outcome indicator 2.3: “The time taxpayers take to pay taxes” are all measured through an independent taxpayer perception survey. TTP conducted the first such survey in 2025 (the draft report was submitted to the Ministry in May 2025), representing the first recent independent assessment of taxpayer perceptions of the Ministry of Revenue. The survey was implemented in response to both logframe requirements and recommendations from the 2024 Tax Administration Diagnostic Assessment Tool (TADAT), which emphasised the need for independent perception monitoring. There was also a plan to repeat the survey in February/March 2026, but this did not go ahead for the reasons discussed below.

The 2025 survey identified a number of perception challenges, including that approximately 30% of surveyed large taxpayers reported feeling unfairly targeted by the tax administration. According to the independent review team, there are two contradicting opinions. From a revenue administration perspective, best practice calls for the application of the Pareto Principle which calls for tax systems to focus on 20% of taxpayers which bring in 80% of the revenues. In this sense, the Ministry’s intensive follow up on large taxpayers could be perceived as unfairly targeting them. On the other hand, large taxpayers often mention practical/experienced concerns related to rules and processes causing disincentives to businesses. The Ministry has yet to act in communicating better to alter not only the perception but also the experiences businesses have been reporting. Taking another survey now will not change last year’s results as the Ministry has yet to address the previous findings. TTP will provide technical support in the preparation of action plan and its implementation to respond to the perception findings.

Outcome Indicator 1.4: % of tax revenue paid on time (Disaggregated by VAT and CIT)
Based on SIGTAS sources, it has been reported that against the VAT target of 95% and the CIT target of 75%, MOR has achieved VAT of 94.96% and CIT of 91.8%, with tax revenue paid on time at the end of June 2025 (end of the Ethiopian calendar year). The data for March 2026 is not available.
On the other hand, based on their own calculation, the independent evaluation team reported discrepancy of returns on time, showing persistent challenges in data quality and reliability. The team said that they have identified at least 4 inconsistent revenue datasets. This underscores the critical importance of TTP's data cleansing efforts in SIGTAS to establish it as the single source of truth. Data quality has remained a serious challenge and TTP will continue to work closely with the MoR IT centre and relevant officers.

Outcome 2: A tax environment that encourages business
This year, efforts were made to create a more business-friendly tax environment. Taxpayer-facing systems were enhanced, including improvements to e-filing, e-payment and e-clearance.
Figure 1 Progress in e-taxation (EFY 2017 corresponds to 2024/25: July 2024-June 2025)

Outcome indicator 2.1: % of taxpayers using e-filing for VAT and Corporate Income Tax disaggregated by: Large/Medium/Federal Small Tax Office in Addis Ababa
Baseline	Milestone	Achieved
VAT	VAT	VAT
LTO: 99.6%	LTO: 99.6% (maintained)	LTO: 98.4%
MTO: 99.9%	MTO: 99.9% (maintained)	MTO: 99.57%
STO: 92.8%	STO: 96%	STO: 93.9%
CIT	CIT	CIT
LTO: 96.7%	LTO: 98%	LTO: 95.4% (97)
MTO: 94.3%	MTO: 96%	MTO: 97.6% (99)
STO: 51.5%	STO: 70%	STO: 86.4% (96)

On track. Significant progress was made on e-filing overall in the previous years and sustained during the year in review. The goal of sustaining high e-filing rates continues in LTO and MTO along with a sharp increase in STO which is commendable.
This year, the e-filing and e-payment platforms' functionality was enhanced, along with bolstered security. The e-Tax application servers were optimised to support the rising number of electronic filers. The e-Clearance system was fully deployed across all federal tax centres in Addis Ababa. The e-Payment system was also updated to incorporate the requirements introduced by the new Income Tax Amendment, ensuring the platform remains aligned with recent legislative changes.

Outcome Indicator 2.2: The time taxpayers take to file taxes

As explained under outcome indicator 1.3 above, the independent survey planed for February/March 2026 did not go ahead to inform this milestone. However, the digital filing environment has expanded significantly over the past year. Coverage of electronic filing has increased across taxpayer segments:

- Large taxpayers: approximately 100% filling electronically
- Medium taxpayers: approximately 95% filling electronically, and
- Small taxpayers: approximately 86% filling electronically.

System performance improvements and upgrades to the e-tax platform have also significantly reduced processing times. SIGTAS transaction data shows that:
- The majority of Taxpayers typically require 5–15 minutes to complete and submit an online declaration form.
- Return processing and acceptance within the system typically takes 1–2 minutes.

These improvements are largely attributable to system upgrades that enhanced platform stability and reduced service interruptions. Previously, taxpayers frequently experienced delays caused by system outages or manual processing steps.

The expansion of e-filing coverage and the reduction in transaction processing times represent a significant improvement in filing efficiency and reduce the administrative burden on taxpayers.

Outcome Indicator 2.3: The time taxpayers take to pay taxes

Significant improvements have also been achieved in the tax payment process through further integration of digital payment systems.

Following submission of an electronic declaration, a payment document is automatically generated within the taxpayer portal. Once payment reaches the Government of Ethiopia account at the National Bank of Ethiopia, the Ministry automatically issues an electronic receipt via email and the taxpayer portal.

As a result:
• Tax payment confirmation on the MoR side is effectively instantaneous once funds reach the government account.
• Taxpayers no longer need to visit MoR offices to obtain payment slips or receipts.
• Tax clearance certificates have been fully digitised during the past year.

These changes represent a substantial improvement in the efficiency and convenience of the tax payment process. The removal of in-person administrative steps significantly reduces compliance time and improves overall taxpayer experience.

Lessons
The actual interventions and supports for the attainment of outcomes 1 and 2 look very similar as both talk about e-services improvement. These are likely to be measured under just one outcome.

Recommendation
During the theory of change and logframe refresh, the programme team will need to discuss and revise indicator statements and milestone measurements for clearer planning, intervention, monitoring and reporting of each area of progress. This will also improve clarity of roles (who contributes to what) and better understanding of attribution.

## C. DETAILED OUTPUT SCORING

Output Title	SIGTAS system is enhanced, and data quality is strengthened
Output number:		1	Output Score:	A
Impact weighting (%):		50	Weighting revised since the last AR?	No
Indicator			Milestone	Progress
1.1 Number of BPT SoPs developed, agreed and implemented for enhanced SIGTAS functionalities.			4	4
1.2 Percentage of SIGTAS blocking and critical issues resolved relative to total number of issues in hand during the period.			80%	82.6%
1.3 Number of improved SIGTAS reports: / i) # reports produced and used in practice / ii) reports improved.			i) 60 new types of reports produced and used / ii) 45 reports improved	i) 60 reports produced and used / ii) 54 reports improved
1.4 Improved capacity of Ministry of Revenues IT Officers measured by: / i) Number of staff trained (disaggregated by gender). / ii) % satisfied with training. / iii) Average % improvement in pre-post test			i) 28-33 IT Officers trained / ii) 95% / iii) 15%	i) 30 IT officers (18 male and 12 female), / ii) 100%, / iii) Not measured

Source: SIGTAS data

Briefly describe the output's activities and provide a supporting narrative for the score.

Indicator 1.1 Number of Business Process Transformation (BPT) Standard Operating Procedures (SOPs) developed, agreed and implemented for enhanced SIGTAS functionalities.

This indicator has met expectations. The indicator measures both the development of new SOPs and their implementation, which aim to enhance SIGTAS reporting and functionality. Standard Operating Procedures for four tax administration sub-processes, namely Taxpayer/TIN Deregistration and Tax Type Deregistration, were drafted, discussed and approved. Additionally, the updated registration and cancellation forms for individual and non-individual taxpayers were incorporated. The SOPs are expected to benefit the Ministry in boosting operational efficiency and refine service delivery by streamlining processes and standardising practices across branches.

Indicator 1.2 Percentage of SIGTAS blocking and critical issues resolved relative to total number of issues in hand during the period.

This indicator moderately exceeded expectations. The initiative focuses on stabilising core tax administration systems while introducing targeted enhancements to support greater process automation until system replacement. Key achievements include upgrading SIGTAS and e-Tax to align with the Income Tax Amendment, enabling online Fayda–TIN harmonisation, advancing taxpayer registration and case management modules, and resolving critical IT issues. Together, these improvements have strengthened system stability, compliance, identity verification, and operational efficiency across MoR.

Indicator 1.3 Number of improved SIGTAS reports: This indicator substantially exceeded expectations. The enhanced SIGTAS-generated reports help track and increase their practical use. The reports provide actionable insights and data for MoR’s decision-making. Data on report numbers and types is extracted directly from SIGTAS, while usage and improvement feedback is gathered through surveys. Notably, the IT Centre now directly manages this initiative rather than TTP's IT team, which accounts for the high-performance figures, with TTP taking a supporting role. The SIGTAS reports now replace previously manually generated reports that gathered information from multiple sources (such as emails and telephone calls) and were presented in Excel files.

Indicator 1.4 Improved capacity of the Ministry of Revenue's IT Officers

This indicator has met expectations. The indicator measures 3 core tenets of capacity building efforts: 1). The number of staff trained within the IT space of MoR; 2) The proportion of which are satisfied with the training received (relevance, length, quality etc.); 3) The % of improvement noted in the pre-post test scores of participants after receiving training. Overall, this measures the enhancement of technical skills and knowledge of IT staff.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

MoR's IT Center underwent a structural overhaul during the period, including the creation of a dedicated development team. This was a part of the MoR’s restructuring that created a Digital and Data branch led by a state minister. This has positively enhanced MoR’s capacity to manage IT-related matters and has enabled it to begin assuming responsibilities from TTP, starting with SIGTAS support applications.

As a part of sustainable exit/transition strategy, the output indicators will be tailored towards MoR IT staff development including mentoring and backstopping as they takeover more responsibility for SIGTAS operation.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

Lessons
- Staff are frequently reassigned from training to address operational needs. However, over the past year, the number of resolved tickets has increased significantly, reflecting notable improvement—primarily due to leadership's high priority on SIGTAS and the revamped MoR's IT Centre.
- As observed by the independent evaluation team, although training target has been achieved, and visible progress was made, the knowledge/skills transfer within IT Directorate has not progressed as desired and therefore the MoR remained largely dependent on the TTP consultants/advisers.

Recommendations
- TTP and MoR relevant leads jointly develop a clear sustainability plan and exit strategy to ensure staff are well trained, SIGTAS is a single source of truth, and taxpayers are well informed and comply.
- Revisit the milestones to ensure that they sufficiently represent and reflect the output description and reasonably stretched.

Output Title	An improved, robust, and high-functioning Tax administration system
Output number:		2	Output Score:	A
Impact weighting (%):		30	Weighting revised since the last AR?	No

Indicator	Milestone	Progress
2.1 Number of LTO audit cases started/completed with audit expert support.	2	2
2.2 Number of tax forms simplified and rationalised.	14	14
2.3 Improved capacity of Large Taxpayer Office auditors measured by: / i) Number of staff trained (disaggregated by gender): / ii) % satisfied with training. / iii) Average % improvement in pre-post-test.	i) 20-25 Trained / ii) 95% / iii) 15%	i) 22 (18 Male (82%) & 4 Female (18%) / ii) 83.4% / iii) N/A

Briefly describe the output's activities and provide a supporting narrative for the score.

Indicator 2.1 Number of LTO audit cases started/completed with audit expert support.

This indicator has met expectations. This indicator tracks the number of audits in the Large Taxpayer Office (LTO) supported by TTP experts. During the reporting period, two expert-supported audits were completed—one in the manufacturing sector and one in the manufacturing with excise. In the next period, audits in the construction sector are expected to be supported. Expert engagement is intended to transfer skills and knowledge and to strengthen audit quality, thereby improving overall tax administration performance and taxpayer confidence.

Indicator 2.2 Number of tax forms simplified and rationalised

This indicator has met expectations. Simplified and streamlined tax forms have improved their usability and reduced the administrative burden on taxpayers, thereby supporting compliance. These were mainly done for the registration processes. Progress has been made in enhancing the integrity of the taxpayer registration database. Notable achievements include revisions to both registration and cancellation forms for individual and non-individual taxpayers and the updating of the registration manuals to align with recent amendments to tax proclamations. In addition, development of a comprehensive taxpayer segmentation manual and a taxpayer segmentation directive is in progress, and both drafts are currently under internal review.

Indicator 2.3 Improved capacity of Large Taxpayer Office auditors

This indicator has met expectations. A training programme on federal taxes was conducted for the LTO auditors, 22 in total during the year.

However, despite the sheer number of trained staff meeting expectations, the challenges with the LTO tax auditors remain serious. The field visit evaluation team report indicates that audit capacity is still rudimentary and often do not follow the Standard Operating Procedures and guidelines, or the manual that was developed. Also, staff members are not sufficiently prepared to utilise the knowledge gained, and there is a challenge of high staff turnover. The review team also noted that strong pressure to achieve revenue mobilisation targets distorts audit practices and compromises transparency. Further, the absence of clear guidance or commonly agreed interpretations of tax proclamations has often led to inconsistent and contested audits, increasing disputes and arbitrariness and ultimately undermining audit quality. This is an area frequently receiving complaints from taxpayers.

TTP provided practical hands-on support on a manufacturing and construction audit cases, the expert working directly with large taxpayer audit teams. Based on this actual audit case, training is provided to a larger group of auditors building sector audit capacity. TTP will continue to support during the extension focusing on transferring skills and knowledge to the MoR audit staff.
Describe any changes to this output during the past year, and any planned changes as a result of this review:

Pre-post-test has not been conducted due to trainees' resistance, feeling their skills may be wrongly judged. This was discussed at a high level with the ministerial team. No major decision was made on how to proceed. The 82% satisfaction was based on simple feedback collection.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead]:

Two key recommendations from the previous year on computer-based audit training and the review and use of the audit manual have not yet been implemented. It was understood that there were discussions between GIZ and MoR regarding support for computerised auditing; but these discussions have yet to translate into concrete action.

Lessons

Strong revenue mobilisation pressures require officers to expedite audit work, limiting their ability to apply the newly updated manual in full. Feedback suggests a preference for sector-specific audit manuals rather than a single, general audit guideline.

Recommendations
- In future, TTP will need to discuss with MoR and change this indicator to a more substantive milestone that can measure improvement in tax audit competence and behaviours.
- The approaches to exit have been outlined under different sections including training superusers, trainers, change managers and document repository. This will also apply for the audit capacity development.

Output Title	Strengthened tax policy analysis and legislative drafting capacity in the Ministry of Finance
Output number:		3	Output Score:	A
Impact weighting (%):		10	Weighting revised since the last AR?	No

Indicator	Milestone	Progress
3.1 Number of pieces of tax policy analysis delivered and accepted by counterparts.	2	3
3.2 Improved capacity of Ministry of Finance / Ministry of Revenue operational staff measured by: / i) Number of staff trained (disaggregated by gender). / ii) % satisfied with training. / iii) Average % improvement in pre-post test	i) 55-65 legal and operational staff trained / ii) 95% / iii) 15%	i) 45 operational staff trained / ii) 100% / iii) N/A

Briefly describe the output's activities and provide a supporting narrative for the score.

Indicator 3.1 Number of pieces of tax policy analysis delivered and accepted by counterparts

This output moderately exceeded expectation. As summarised in section A and B, several legislative amendments have been prepared and ratified by the parliament in July 2025. Directives and explanations for amended proclamations have also been developed and briefings provided at different platforms including with business representatives, all led by the Tax Policy and Legislative Adviser of TTP.

Indicator 3.2 Improved capacity of Ministry of Finance / Ministry of Revenue operational staff

This output moderately did not meet expectations. As indicated in the table above, 45 operational staff from the MoR Legal Directorate and branches were familiarised/trained on the newly amended tax laws and their implementation. The purpose of training the operational staff is to support implementation of the amended laws. Originally, the main purpose of this output indicator was to train tax policy and legislative draft staff in the MoF to build their capacity for policy analysis and for drafting tax legislations. However, due to understaffing and inability to release the available staff in the MoF, the training did not go ahead as desired.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This output was revised during the 2025 logframe review in response to recommendations from the previous Annual Review (AR). During 2024/25, the plan was to train 4 policy officers at MoF, but only 2 were available, and their demanding schedules prevented any training from being delivered. Consequently, the indicator was revised to include MoR staff at the Legal Affairs Directorate and other operational staff in MoR HQ and branches.

This output needs to be revised. The TTP team will need to discuss with the relevant Directorates and leads to agree scope and content of the indicators and milestones that can sensibly reflect key priorities as the programme prepares for sustainable exit. If MoF tax policy and legislative units unable to recruit new staff, TTP may decide to focus on working with those available and transfer skills and knowledge through peer-learning, mentoring and backstopping as necessary. Obviously, as observed by the evaluation team, the number of staff in the Tax Policy Directorate and Legal Drafters are too small to the size of Ethiopia’s tax sector.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

Progress against the recommendations has been limited. The recommendations were on recruitment in Tax policy staff, producing guidance and explanatory notes, and ensuring their availability and accessibility on the website and through other channels. There has been limited progress on producing explanatory guidance, practical case studies, and clarifications on the application and interpretation of tax proclamations and regulations. Only legal briefs have been issued on certain provisions of the tax laws at the request of MoR. While the website has been revamped and now includes information on the new Income Tax Proclamation, overall progress in strengthening taxpayer guidance and communication remains modest.

Lessons
The previous annual review lessons and recommendations seem to mix the roles and responsibilities of TTP and GoE institutions. For example, the recommendation to recruit policy and legal drafters is relevant only to MoF, and not TTP. The current annual review recommendations try to limit within the control of TTP.

Recommendation
As indicated in other sections, the TTP’s role will move from leading and hands-on support to enabling and backstopping during the extensions. The Tax Policy and Legislative Adviser of TTP will stop drafting and leading briefing towards intervention in these activities to support the MoF staff.

Revise the output indicators and the milestones focusing on what TTP can deliver and in its control to resolve issues in case delays encounter. Most importantly, these need to be clearly differentiated from what the MoF should be doing in their role.

Output Title	The programme is managed effectively and plays a central role in supporting donor coordination on tax.
Output number:		4	Output Score:	A
Impact weighting (%):		10	Weighting revised since the last AR?	No

Indicator	Milestone	Progress
4.1 % progress of planned initiatives / Green - on track / Yellow - delayed / Red - not on track	Green: 90% / Yellow: 5% / Red: 5%	Green: 95% / Yellow: 5% / Red: 0%
4.2 Effective donor coordination, measured by: / a) Quarterly sharing of information / b) Number of meetings convened.	a) 4 reports shared / b) 2 meetings held in the year	a) 4 reports shared / b) 2 meetings held in the year
4.3 Workplan Agreed	Yes	Yes
4.4 Number of minuted Steering Co meetings held annually	2	1

Briefly describe the output's activities and provide a supporting narrative for the score.
Indicator 4.1 % progress of planned initiatives
This output moderately exceeded expectations. The indicator monitors the progress of the programme initiatives by categorising them as either on track, delayed, or not on track. The objective of this indicator is to flag the extent of any issues in implementation, and to keep planned programme activities on track. The progress or lack of progress with this indicator also informs the Performance Assessment Framework (PAF). FCDO retains 25% of the monthly payment as a part of the performance requirement and effects the payment quarterly following review of a quarter report against the KPIs. Most of the KPIs were achieved in time or were on track with some delay. The quality of reports was much better than the previous years. The programme had also proper workplan with timelines and prioritisation.
Indicator 4.2 Effective partner coordination
This output has met expectations. The indicator measures the effectiveness of partner coordination and information sharing. More coordination meetings and information sharing are considered important particularly during this period when Ethiopia has embarked on major macroeconomic reform. Two partner coordination meetings were held during the year – 9 July 2025 and 5 March 2026. The TTO has emerged as a key point of contact for all partners looking to work on revenue. Proactive partner engagement is an area of weakness for the MOR, primarily owing to serious capacity gaps but also the intense pressure following the commitment to macroeconomic reforms that include stretching targets on revenue collection. Separate from the general tax partner group meeting, FCDO and Cowater TTP team have had several bilateral meetings with the existing and potential tax partners with the objective of espousing coordination and alignment intended to pre-empt potential duplication. The coordination activities have eliminated potential overlap with other partners who are also keen on providing technical assistance on the revenue sector.
The number of reports reflects the wide amount of information shared including MoR’s reform strategy, the partner coordination matrix, IT Reform Strategy, Strategic Partnerships matrix which is used by Partnerships Directorate of MoR and several in-year reports and minutes. TTP has provided both internal and external support. TTO Head is an active member of the Prime Minister Office Tax Revenue Enhancement Taskforce with latest information on strategic direction of the government. He has provided different updates on priorities and approaches of the government to partners interested in supporting the tax system. The feedback obtained from the World Bank and other bilateral partners also commended TTP and its office TTO for playing pivotal role in liaising between MoR and partners and providing all the necessary information on behalf of the Ministry.
Indicator 4.3 Workplan Agreed
This output has met expectations. The indicator measures whether the programme workplan has been prepared with the required quality, discussed and agreed with counterparts and FCDO within the time framework. The 2025/26 draft work plan was submitted by the programme team to the GoE and FCDO. The work plan was also discussed at the Steering Committee meeting held on 26 February 2025. The final workplan with detailed implementation timeline was discussed and approved during the validation workshop held in the first week of April 2025.
 Indicator 4.4 Number of Steering Committee meetings held annually.
This output moderately did not meet expectations. The indicator monitors the oversight and governance of the programme, as measured by the number of steering committee meetings held each year. These Steering Committee meetings were important to discuss and agree the priorities for and scope of the programme support. The SC also makes decisions to resolve any bottlenecks causing delay to the programme implementation. The Steering Committee met only once during the year, on 11 March 2026.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
There was no change to the output during the last year. As recommended by the evaluation team, indicators 4.3 and 4.4 will need to be revised to reflect more substantive and relevant activities. The new indicators and milestones will need to cover progress against consolidation of achievements and sustainable exit/transition.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.
Recommendations
- The indicator and milestone for SC need to change from sheer number of meetings to impact measurement.
- The FCDO team will need to remain engaged with other tax partners bilaterally, in addition to all tax partner coordination meetings. Bilateral engagement would help timely exchange of latest information and provide opportunity to play a more influential role, including supporting FDIs.

## D: VALUE FOR MONEY

We assess the Tax Transformation Programme to represent value for money (VfM).

VfM can be evaluated across several dimensions: economy (e.g., staff recruitment, fee rates, training costs), efficiency (e.g., high-quality, timely delivery), effectiveness (e.g., achieving desired results and customer satisfaction), and equity (e.g., fair impact across social groups, such as gender). TTP has been essential for SIGTAS stabilisation at the Ministry of Revenue (MoR); without it, system collapse would have been likely. GoE officials have repeatedly noted that TTP-contracted staff were critical in preventing core IT system failure and advancing tax policy reforms.

Key costs and cost drivers

The biggest cost has remained the advisory fee, accounting for 70% of the year's costs.

Economy

TTP's fee rates continue to compare favourably with those for similar positions on FCDO programmes delivered by COWATER in other countries (e.g., Somalia and Zimbabwe). While advisers were paid for 17-20 days of work, each worked effectively full-time, often flexibly when needed, including beyond their contract terms to support the ministries. This is mainly due to the trust and relationships the advisers developed with both ministries and Prime Minister’s Office. MoR and MoF officials continued to maintain their high expectations of both the advisers' availability and the programme deliverables throughout the year.

The supplier's profit margins were strongly scrutinised by the FCDO TTP team, together with the commercial team. Travel expenses including flights and hotels are scrutinised through the monthly expenses review before approval.

Efficiency

During the year in review, the programme had planned to deliver 10 key milestone. Out of the total, 9 are either completed or on track while there is a delay with 1. The delay is around audit case management due to delays in data cleansing. These deliverables were produced in a challenging context, when MoR staff were under pressure to meet competing demands for short-term revenue mobilisation, which distracted them from long-term reform activities.

The VfM was strengthened by the agreement and application of performance-based payment with the supplier. That means, 25% of their monthly service fee payment was retained and linked to the supplier's KPI achievements. It is released only if they met the KPIs agreed.

Effectiveness

As discussed under the outcome assessment, the tax revenue has significantly increased during the year. The programme has significantly contributed to the revenue increase in different ways, such as simplifying processes and other taxpayer service improvements, legislative amendment and capacity development training to tax officers. E-taxation not only saved times both for taxpayers and tax officials but also improved accountability and transparency where these are properly implemented. However, it was noted that there are resistances to fully move to e-taxation at regional and municipality levels. We will continue to exert pressure during our discussion with government officials.

Equity

The programme has added a gender mainstreaming lens in tax reform. All training data has been disaggregated by gender as the table annexed to this AR shows.

Several reform initiatives are advancing equity in different ways. i) simplification of presumptive taxation for micro, small and medium enterprises by reducing administrative burdens and promoting compliance - supports smaller businesses in formalising and accessing tax benefits more easily; and ii) adjustments to personal income tax system by proposing changes to raise the tax-free threshold and revise marginal tax rates aiming to create a more progressive system. These adjustments focus on easing the tax burden for lower-income earners, ensuring fairness and aligning with taxpayers' ability to pay. Further, the increasing coverage of e-taxation to small taxpayers would save time and cost of contact for small businesses reducing their overall cost.

Recommendation
The programme team will need to consider how to strengthen the gender equality aspects of the programme in future and identify an indicator(s) to be monitored during the implementation.

E: RISK

Overview of risk management
The programme has been assessed as carrying an overall Moderate risk rating. A total of eleven risks has been identified: six with moderate residual ratings, three classified as major, and two considered minor. Many of the risks that were active at the beginning and mid stage of the programme are now closed. Harnessing inputs from Africa’s risk lead and in consultation with the suppliers, the team exhaustively evaluated the current risks of the programme and agreed that the overall risk rating has to be moderate. The programme maintains both online and offline risk registers, each updated at least once per month. Cowater, the programme’s primary supplier, also maintains its own risk register, which is reviewed and updated on a quarterly basis.
The programme holds quarterly risk review meetings with Cowater, in addition to regular internal risk meetings. These discussions support shared understanding, alignment, and collective decision making, and they inform updates to the programme’s risk register. They also ensure that stakeholders receive relevant and timely information, enabling a common understanding of the risks and their potential effects on delivery.
Each risk discussion assesses both the likelihood of risks materialising and the potential impact on achieving programme objectives. The effectiveness of mitigation measures is also reviewed, including their adequacy, the responsible parties, and timelines for implementation.
Table 1. Distribution of risks in relation to appetite
Risk category	Total risks	Ratings	Programme risk appetite	FCDO Ethiopia risk appetite	Total Risks Outside programme/FCDO risk appetites
Strategy & Context	3	Major	Receptive	Receptive	0
Policy & Programme Delivery	3	Moderate	Receptive	Receptive	0
Financial & Fiduciary	1	Minor	Receptive	Receptive	0
Reputational	1	Moderate	Cautious	Cautious	0
Safeguarding	1	Moderate	Receptive	Receptive	0
People	1	Minor	Cautious	Cautious	0
Public Service Delivery & Operations	1	Moderate	Cautious	Cautious	0
Total	11

From the below main identified risks, the first three are strategic and context, their residual risk rated as ‘Major’. The final three are policy and programme delivery risks, each with a ‘Moderate’ residual rating.
The main identified risks of the programme are:
Conflict induced risks, the ongoing conflicts in Amhara and Oromia Regions and the political instability in Tigray Region not only require significant resources to fund the war but also hinder revenue collection in the regions. The regions in conflict may also be excluded from the tax transformation programme support. This may cause tension between federal and regional governments one blaming another for failure in tax system improvement and DRM. This may hinder the effort to improve the tax system, encourage poor tax collection, poor service delivery and weak state-society relations. The team maintained up to date PEA covering how conflict in the country is affecting the programme and the tax sector at large; keep up to date communications with all stakeholders; engaging with regions in key policy and admin areas; and kept lines of communication open with MOR, MOF, and BE.
Lack of strategic leadership in tax system transformation, political pressure and unpredictability of the country context distracting leadership from long-term, sustainable reform; deploying or pushing to deploy resources to short-term objectives; frequent change in leadership causing delay and affecting continuity of transformational initiatives. This may affect the programme to remain short of supporting long-term transformational tax system with possibility of undermining the value for money (effectiveness). To mitigate this, the programme is utilising different structures such as the Steering Committee to build consensus on / reinforce the transformation agenda; embed flexibility in the programme to facilitate onboarding of new appointees; effective communications both at leadership and technical staff levels with MoR and MoF.
Excessive pressure on short-term DRM, there is a high pressure on government to meet both internal and external revenue requirements. The pressure to increase revenue may cause overstretch to taxpayers, affect businesses, erode voluntary compliance and damage government-taxpayer relationships, potentially causing unrest. This type of drive may involve arbitrary measures and worsen corruption. Due to this, the programme reform intervention may be unable to meet expectations, that is, improvement of the tax system. To mitigate this, the programme is continuously gathering up to date information that shows how the drive to increase revenue is affecting government-taxpayer relationships and provide advice in the MoR/MoF/Customs Technical Committee which feeds into the Macroeconomic Committee. The programme will also advocate for international best practice; encourage development of a formal reform roadmap, and work with likeminded tax donors.
Low absorptive capacity within GoE (MoR, MoF), competing demands on staff time reducing availability for core tax reform. Their capability/capacity remains limited, low motivation and high turnover of key staff members. The reform initiatives introduced/enhanced by the programme may not be fully owned, mainstreamed and sustained. To mitigate this and to ensure that the gains aren’t lost, TTP is preparing sustainable exit strategy. The exit strategy and its phased implementation during the remaining period of the programme is expected to help the ministries to sustain the gains. The exit strategy includes different arrangement like interventions with well-designed classroom-based training, on-the-job training; encouraging more direct contact between Technical Advisors and Initiative Leads; and coordination with other development partners
Duplication of donor support, increasing number of donors is showing interest to support the DRM efforts of the GoE. The limited capacity within the GoE would mean that they may not be able to effectively coordinate and lead the sequencing and coherence of reform. Many donors would prioritise supporting critical areas like IT, technical capability of tax specific technical areas. This would mean crowding in similar priorities. This may undermine the VfM; burden on GoE partners; increased transaction cost. To alleviate this, TTO will continue to be used as a hub for the tax support initiatives of different donors, providing background information and reform progress in different tax reform areas. FCDO, using the TTP management and technical expert inputs, will continue to play a convening role for the tax donors.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Programme management
Summarise the performance of partners and FCDO, notably on commercial and financial issues. [max 1 page]
TTP was originally designed as a five‑year programme, launched in March 2019 with a total budget of up to £35 million. The programme’s business case and contract of the main supplier have since been amended twice. The first amendment, made in February 2024, reduced the programme’s value to £20.3 million and revised the end date to March 2026. A second amendment in November 2025 extended the programme by a further twenty‑seven months until 30 June 2028 to align with the completion of the IMF Extended Credit Facility, the World Bank DPO series, and the National Medium-Term Revenue Strategy. This amendment also increased the programme’s value to £24 million.
To date, the programme has spent £18.7 million. Expenditures across all TTP components for the review year are detailed in the table below.
Component	Description	Budget/ / Forecast 2025/26	Spend to end of March 2026	Budget Utilisation
300553-101	Support to Tax Transformation through Service Provider	£ 2,671,507.78	2,666,668.78	99.81 %
300553-103	Analysis, research, and programme support	£ 75,000.00	£ 54909.51	73.2 %
Total		£ 2,746,507.78	£2,721,578	99.1 %

Component 1: Accelerated Delivery: Technical assistance support to the Ministry of Revenue through the Tax Transformation Office (TTO).

Cowater International is the lead implementing partner for this component and holds a £22,848,653 contract with FCDO. Cowater oversees the Tax Transformation Office (TTO), a delivery unit embedded within the Ministry of Revenue (MoR) that drives practical reforms across the tax system. The organisation provides overall project leadership, with work concentrated in three priority areas: Data and IT (SIGTAS), Tax Compliance Improvement, and Tax Policy and Legislation. As of 31 March 2026, Cowater will have spent £18,039,775.22, with an additional £4.84 million allocated for the extension period covering FY26/27 and FY27/28.
Cowater also deploys long‑term advisors and technical experts covering IT, excise, registration, filing, debt management, and policy and legislation who are embedded within the Ministries of Revenues and Finance. These experts have built strong working relationships with senior officials and ministers.
Component 2: Peer-to-peer support from HMRC.
During the review year, the HMRC team conducted three visits, providing data‑related support aligned with the current programme. However, the Memorandum of Understanding (MoU) between HMRC and the Ministry of Revenue (MoR) expired on 2 July 2025. Although there were frequent discussions about continuing this technical support, it was ultimately decided to close the programme.

Component 3: Strategic Tax Transformation Support Fund.

IPE Global has been primarily responsible for evaluating and analysing the Tax Transformation Programme throughout its implementation period. Budget reductions in recent years required the team to reduce some programme related activities. These changes were reflected in the first contract amendment, which reduced the component’s budget from the original £726,875 to £392,314. Due to these financial constraints, the team decided to conclude this component by 31 March 2026. To date, a total of £309,702.6 has been utilised.

Commercial:
The team decided to extend the contract with the main supplier, Cowater, until March 2028 to deepen the programme’s impact, ensure the long‑term sustainability of revenue improvements, and promote equitable and transparent taxation of international investors. This two‑year extension increased the contract value from £18 million to £22.8 million.
G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

Different arrangements are in place for monitoring, implementation support and evaluation of the programme. These include:
- Six monthly Ministerial and Development Director level Steering Committee meeting (this year it happened once due to change of a minister in charge)
- Monthly technical and programme management review meeting between the supplier/Cowater and the FCDO programme team
- Quarterly technical report and review meeting as well as performance assessment against KPIs
- Monthly financial forecasts and reports
- Weekly SRO, PRO and Programme Officer catch up to health check of the programme
- Annual stock takes and evaluation by an independent firm (IPE Global)
- Annual audit report
- Quarterly risk and delivery plan updates
- Annual asset spot checks
- Ad hoc meeting with the relevant GoE officials (as necessary).

Every month, the team has two sets of meetings with the main supplier to check the progress of key deliverables and to discuss issues of programme management. The status of financial expenditure is also reviewed on a monthly and quarterly basis. The performance of the programme is evaluated during each quarter using weighted indicators that examine progress against the outputs and management performance which evaluates the programme's responsiveness to FCDO and GoE needs. The team also makes sure that the reported spend is within the 5% variance of the forecast. The team has conducted the annual asset spot check in February 2026 and found no gap in the asset management.

During the review period, FCDO has conducted three quarterly KPI assessments against the agreed Performance Assessment Framework (PAF): in the first quarter (April-June 2025), second quarter (July-Sep 2025) and third quarter (Oct-Dec 2025). The implementing partner has met 100% of the key performance indicators in the above mentioned three quarterly assessments.

During December 2025 – February 2026, the independent monitoring and evaluation supplier, the IPE Global team, assessed the progress of the programme while conducting various interviews with Cowater, MoR, MoF, businesses, selected tax donors and other concerned stakeholders of the programme. Findings of these assessments are shared with the TTP team and used as inputs in preparation of this annual review.

The programme was audited during December 2025 – January 2026 and the final audit report submitted during the first week of February 2026. The report found no financial discrepancies.

Evidence

Tax reform support by partners is more effective when political commitment is high. As a part of macroeconomic reform programme, GoE’s commitment for tax reform has increased. The TTP has seized the opportunity to respond to government’s increased commitment by supporting changes of tax laws, enhancement of e-taxation and streamlining of tax procedures. These interventions have significantly contributed to the increment of tax revenues.

Learning

The TTP team engaged in several face-to-face and conference call meetings with suppliers of the programme and tax reform partners in the country. These meetings were helpful not only to draw lessons from the implementation at different phases of the programme but also to understand policy and contextual level challenges.

Despite some improvements during the year, both MoR and MoF have continued to depend on the TTP for SIGTAS functionality and tax related legislations respectively. The porgramme team will work with both ministries to develop monitorable agreed actions for sustainable transition/exit by March 2028.

Another key learning point is the importance of engagement at the top level of government. Engagement with the Prime Minister's Office and Steering Committee have been useful means of understanding the government thinking and the value they attach to UK's partnership, with implication on Ethiopia-UK diplomatic relationships and business deals as well.

Date of last audited TTP annual statement (s)	Jan 2026
Date of last TTP narrative and financial report(s)	Jan 2026

Annex 1

Annex 2