Memorandum of Understanding Amendment Letter

Project Name: Rohingya Response and National Resilience Programme (RRNRP)
Project Number: 300554-111, 300554-115, 300554-118 and 30554-404

I refer to the Memorandum of Understanding between the Government of the United Kingdom of Great Britain and Northern Ireland acting through the Foreign, Commonwealth & Development Office (“FCDO”) and the Office of the United Nations High Commission for Refugees (UNHCR) signed on 12 June 2025.

Following recent “correspondence” (ref to email of 09 Feb’26), FCDO proposes to “increase” the amount made available to UNHCR by £550,000 CDEL – capital expenditure (Five Hundred and Fifty Thousand Pounds Sterling) to be utilised by 31 March 2026. The additional funding is for procurement of shelter materials for prepositioning ahead of the monsoon season and for essential operations and maintenance of prioritised WASH infrastructure.

I propose that the figures and words £5,500,000 (Five million and five hundred thousand pounds sterling) in paragraph three (3) of the original Memorandum of Understanding be deleted and replaced with the figures and words £6,050,000 (Six Million and Fifty Thousand Pounds Sterling).

Following recent “correspondence” (ref to e-mail dated 09 Feb’26), FCDO proposes to change the end date of the Memorandum of Understanding.

I propose that the end date of 31 March 2026 in paragraph two (2) of the original Memorandum of Understanding be deleted and replaced with 31 May 2026. The No Cost Extension is specifically valued at £512,350 CDEL which has been already disbursed for shelter construction activities only.

In addition, FCDO proposes to delete the words ‘’The Partner will provide within three (3) months after the date of completion or termination of this
Memorandum, a final report (for June’25 to March’26) summarising programme or project performance and results as well as provisional financial data’’ in paragraph twenty-six (26) of the original Memorandum of Understanding and replace them with the following words

1. ‘’The Partner will provide within two (2) months an interim final report (for June’25 to March’26) summarising programme or project performance and results in line with the log frame as well as provisional financial report’’, by no later than 31st May 2026.
2. ’The Partner will provide within three (3) months after the date of completion or termination of this Memorandum, a final narrative and financial report (for June’25 to May’26), by no later than 30th September 2026.
3. All other clauses to the original Memorandum of Understanding will remain the same.

This letter of amendment will place on record our common understanding of the above change(s) and will come into operation on the date you sign your confirmation below. This note will be known as Amendment No. 01/2026.

Please sign both copies of this letter; return one to me and retain the other for your own records.

Signed on behalf of FCDO:
Name:
Position:	Acting Deputy High Commissioner and Acting Development Director
Address/Contact Details:	British High Commission Dhaka / UN Road, Baridhara, Dhaka – 1212 / Bangladesh
Date:	25/02/2026

Signed on behalf of the Partner:
Name:
Position:	Head of Donor Relations and Resource Mobilisation Services
Address/Contact Details:	UNHCR / 94, Rue de Montbrillant / 1202 Geneva / Switzerland
Date:	24/02/2026