## Template
Updated LF June 2026
PROJECT TITLE | Rohingya Response and National Resilience Programme (RRNRP)
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 (March 2022) | Milestone 2 (March 2023) | Milestone 3 (March 2024) | Milestone 4 (March 2025) | MIlestone5 (March 2026) | Remarks
Improved safety and wellbeing of the Rohingya and host populations | Under 5 deaths / 1000 /month in camps | Planned | 25 | 25 | 23 | 26 | 24 | 18
|  | Achieved |  | 23 | 26 | 24 | 18 | 18
Source
|  |  | Baseline: Joint Response Plan; Achievement: Data provided by Inter Sectoral Co-ordination Group Health(ISCG) Sector -Co-ordiantor |  |  |  | Health Sector Co-ordinator | Health Sector Co-ordinator
| Impact Indicator 2 |  | Baseline | Milestone 1 (March 2022) | Milestone 2 (March 2023) | Milestone 3 (March 2024) | Milestone 4 (March 2025) | MIlestone5 (March 2026)
| Under 5 malnutrition Global Acute Malnutrition(GAM) and Severe Accute Malnutrition(SAM) | Planned | GAM: 11.4% (2020) SAM: 1.0% (2020) | GAM: 11.4% (2020) SAM: 1.0% (2020) | GAM 13.7% (2021) SAM 1.3% (2021) | GAM 12.3% (2022) SAM 0.7% (2022) | GAM 15.4% (2024) SAM 2.1% (2024) | GAM: 10% SAM: 10% | GAM Over 10% is considered serious emergency and over 15% the emergency is considered critical
|  | Achieved |  | GAM 13.7% (2021) SAM 1.3% (2021) | GAM 12.3% (2022) SAM 0.7% (2022) | GAM 15.4% (2023) SAM 2.1% (2023) | data not available as SENS Survey not published
Source
| Impact Indicator 3 |  | Baseline | Milestone 1 (March 2022) | Milestone 2 (March 2023) | Milestone 3 (March 2024) | Milestone 4 (March 2025) | MIlestone5 (March 2026)
| Percentage of Rohingya refugees feeling safe in their shelter and immediate environment in the camps- disaggregated by sex | Planned | 39% |  |  |  |  | 80%
|  | Achieved | [5 empty] | 85%
Source
Baseline: PCR SHPR 2021; Achievement: no data available as Multi sectoral Needs Assessment (MSNA) not being conducted in 2021-2022 period. MSNA for 2022 will be
| Impact Indicator 4 |  | Baseline | Milestone 1 (March 2022) | Milestone 2 (March 2023) | Milestone 3 (March 2024) | Milestone 4 (March 2025) | MIlestone5 (March 2026)
| Number of annual maternal deaths / 100,000 live births in the camps | Planned | 326 |  | 315 | 321 | 195 | 136 | Global standards is considered to be less than 70 as per SDG (by 2030)
|  | Achieved |  | 315 | 321 | 195 | 136 | 110
Source
|  |  | Baseline: JRP 2022, Achievement: UNFPA report on Maternal and Parinatal Mortality Surveillance and Reponse Report (MPMSR) and data received from WHO health sector co-ordinator, |  |  |  | Health Sector Co-ordinator | Health Sector Co-ordinator
Objective 1 : Maintain humanitarian assistance and improve safety to enhance the well-being of the Rohingya and neighbouring local Bangladeshi communities
OUTCOME 1 | Outcome Indicator 1.1 (Food) |  | Baseline | Milestone 1 (March 2022) | Milestone 2 (March 2023) | Milestone 3 (March 2024) | Milestone 4 (March 2025) | MIlestone5 (March 2026) |  | Assumptions
Maintain humanitarian assistance and improve safety to enhance the well-being of the Rohingya and neighbouring local Bangladeshi communities | Percentage of households with an acceptable Food Consumption Score | Planned | Rohingya: 50% Host: 67% | Rohingya: 50% Host: 67% | Rohingya: 55% Host: 62% | Rohingya 56% (2022) Host: 65% (2022) | Rohingya 30% (2023) Host: 55% (2023) | Rohingya 68% | Global standards is considered to be above 80% | Safe environment and beneficiary participation enables the survey to be conducted.
|  | Achieved |  | Rohingya: 55% Host: 62% | Rohingya 56% (2022) Host: 65% (2022) | Rohingya 30% (2023) Host: 55% (2023) | Rohingya 65% (2024) Host: 75% (2024) | Rohingya 73%
Source
|  |  | Data extracted from Refugee Influx Vulnerability Assessment(REVA) 5; Milestone 2: Refugee Influx Vulnerability Assessment(REVA) 6, IPC 2024. For 2025, partner proposal suggested that realistically 65% as food ration went up. |  |  |  | REVA 8 | REVA 9
| Outcome Indicator 1.2 (WASH) |  | Baseline | Milestone 1 (March 2022) | Milestone 2 (March 2023) | Milestone 3 (March 2024) | Milestone 4 (March 2025) | MIlestone5 (March 2026)
| Number of cases of Acute Watery Diarrhoea. | Planned | 138415 |  | 147,376 (2021) | 152,834 (2022) | 131,084 (2023) | 138830 | Global standards : minimum
|  | Achieved |  | 147376 | 152,834 (2022) | 131,084 (2023) | 138,830(2024) | 116852 | EWARS
Source
|  |  | data received from ISCG Health Sector Co-ordinator's Early Warning, Alert and Response System (EWARS) |  |  |  | Health Sector Co-ordinator | Health Sector Co-ordinator
| Outcome Indicator 1.3 (WASH) |  | Baseline | Milestone 1 (March 2022) | Milestone 2 (March 2023) | Milestone 3 (March 2024) | Milestone 4 (March 2025) | MIlestone5 (March 2026)
| % of households reporting having access to water in line with SPHERE standards | Planned | 88% | 88% | 67% | 85% | 90% | 90% | Sector standards is considered to be above 90%
|  | Achieved |  | 67% | 85% | 86% | 85% | 83%
Source
|  |  | Baseline: MSNA 2020 fact sheet, Achievement WASH Sector Co-ordiantor UNICEF' WASH Monitoring Report, Joint Respone Pla(JRP)n 2022 Indicator, HH survey |  |  |  | WASH Sector Co-ordinator- Monitoring report | WASH Sector Co-ordinator- Monitoring report
| Outcome Indicator 1.4 (WASH) |  | Baseline | Milestone 1 (March 2022) | Milestone 2 (March 2023) | Milestone 3 (March 2024) | Milestone 4 (March 2025) | MIlestone5 (March 2026)
| % of sanitation facilities that are functional and accessible (latrines & bathing spaces) in line with SPHERE standards | Planned | 75% | 80% | 93% | 97% | 96% | 96% | Sector standard is considered to be above 95% | Maintained ability of partners to access camps. PSEA FPs of targeted agencies participate to the meetings of the Network and provide staff to conduct activities with POCs. Agencies participating in the Network fund SEA community volunteers to disseminate SEA messages across all camp.
|  | Achieved |  | 93% | 97% | 96% | 96% | 98%
Source
|  |  | Data received from WASH Sector Co-ordiantor Household survey report and WASH Monitoring Report 2023. |  |  |  | WASH Sector Co-ordinator- Monitoring report | WASH Sector Co-ordinator- Monitoring report
| Outcome Indicator 1.5 (Health) |  | Baseline | Milestone 1 (March 2022) | Milestone 2 (March 2023) | Milestone 3 (March 2024) | Milestone 4 (March 2025) | MIlestone5 (March 2026)
| Percentage of target population reporting satisfaction with Health Assistance/service/SRH received. | Planned | 75% | 80% | 93% | 90% | 90% | 98% | Going forwards this needs to checked with the Health sector
|  | Achieved |  | 93% | 90% | 90% | 97.5% | 91.6%
Source
|  |  | IOM and UNFPA logframe indicator agreed with the FCDO ahead of UK-funding |  |  |  | UNFPA | UNFPA
| Outcome Indicator 1.6 (Health) |  | Baseline | Milestone 1 (March 2022) | Milestone 2 (March 2023) | Milestone 3 (March 2024) | Milestone 4 (March 2025) | MIlestone5 (March 2026)
| Percentage of deliveries which are facility-based | Planned | 68% | 68% | 70% | 83% | 87% | 98%
|  | Achieved |  | 70% | 83% | 87% | 98% | 91%
Source
|  |  | UNHCR (CHW Working Group Database)and data provided by World Health Organization(WHO) sector co-oridnator |  |  |  | Health Sector Co-ordinator | Health Sector Co-ordinator
| Outcome Indicator 1.7 (Shelter) |  | Baseline | Milestone 1 (March 2022) | Milestone 2 (March 2023) | Milestone 3 (March 2024) | Milestone 4 (March 2025) | MIlestone5 (March 2026)
| Percentage of households with unmet shelter needs | Planned | 63% |  |  | 63% | 72% |  | Using the Shelter Standard Assessment by EU.
|  | Achieved |  |  |  | 72% | 60%
Source
|  |  | data not provided as MSNA was not conducted in 2021-2022 |  |  |  | Shelter Performance Standard Assessment (14+46=60)
| Outcome Indicator 1.8 (SMSD and NFI) |  | Baseline | Milestone 1 (March 2022) | Milestone 2 (March 2023) | Milestone 3 (March 2024) | Milestone 4 (March 2025) | MIlestone5 (March 2026)
| Percentage of feedback and complaints received through the Common Feedback Platform that are addressed and resolved in line with AAP standards. | Planned | 25% |  | 66% | 63.4 | 47% | 26%
|  | Achieved |  | 66% | 63.4% | 46.6% | 26% | 52%
Source
|  |  | JRP 2021 indicator, Common Feedback Platform(CFP) Camp Analysis Yearly data |  |  |  | Common Feedback Platform Zite Manager | Common Feedback Platform Zite Manager
| Outcome Indicator 1.9 (Protection) |  | Baseline | Milestone 1 (March 2022) | Milestone 2 (March 2023) | Milestone 3 (March 2024) | Milestone 4 (March 2025) | MIlestone5 (March 2026)
| Percentage of reported sexual violence cases that were referred and received medical care within 10 days | Planned | 38% |  |  | 48 | 90% | 92%
|  | Achieved |  | 48% | 48% | 90.1% | 92% | 93%
Source
|  |  | GBVIMs monthly monitoring report March 2022. https://rohingyaresponse.org/wp-content/uploads/2026/05/GBVIMS-factsheet-Q1-2026-Final.pdf |  |  |  | GBVIMS Report | GBVIMS Report
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
| £27,472,139 FY(21-22); £17,472,335 FY(22-23); £21,347,859 FY(23-24); £17,848,713 FY(24-25) |  |  |  |  | 100%
OUTPUT 1 | Output Indicator 1.1 (Food) |  | Baseline | Milestone 1 (March 2022) | Milestone 2 (March 2023) | Milestone 3 (March 2024) | Milestone 4 (March 2025) | MIlestone5 (March 2026) |  | Assumptions
Maintain humanitarian assistance and improve safety to enhance the well-being of the Rohingya and neighbouring local Bangladeshi communities | Number of refugees receiving food assistance through e-vouchers in Cox’s Bazar and Bhasan Char per month | Planned | 0 | 369701 | 477437 | 546100 | 200281 | 186120
|  | Achieved |  | 368879 | 471500 | 568180 | 203186 | 184607 | WFP claimedthat the variance was due to the foreign exchange loss.
Source
|  | WFP logframe indicator agreed with the FCDO ahead of UK-funding |  |  |  |  | WFP | WFP
| Output Indicator 1.2 (WASH) |  | Baseline | Milestone 1 (March 2022) | Milestone 2 (March 2023) | Milestone 3 (March 2024) | Milestone 4 (March 2025) | Milestone 5 (March 2026)
| Number of people with access to safe drinking water (includes both Rohingya and host communities) per month | Planned | 0 | 412929 | 72043 | 46000 | 274000 | 77395 | Check with partners on the catchment areas and enure no duplication
|  | Achieved |  | 417328 | 75810 | 46000 | 300925 | 79680
Source
|  | UNHCR, IOM, Christian Aid and UNFPA logframe indicator agreed with the FCDO ahead of UK-funding |  |  |  |  | UNICEF | UNICEF, UNHCR
| Output Indicator 1.3 (WASH) |  | Baseline | Milestone 1 (March 2022) | Milestone 2 (March 2023) | Milestone 3 (March 2024) | Milestone 4 (March 2025) | Milestone 5 (March 2026)
| Number of people with access to proper sanitation facilities according to sector standards (includes both Rohingya and host communities) per month | Planned |  | 179750 | 72043 | 68024 | 75000 | 77395 | Check with partners on the catchment areas and enure no duplication | Maintained ability of partners to access camps.
|  | Achieved |  | 196575 | 75810 | 69164 | 97180 | 79680
Source
|  | UNHCR, IOM, Christian Aid and UNFPA logframe indicator agreed with the FCDO ahead of UK-funding. Milestone 2: Logframe indicator agreed with UNICEF |  |  |  |  | UNICEF | UNICEF, UNHCR
| Output Indicator 1.4 (WASH) |  | Baseline | Milestone 1 (March 2022) | Milestone 2 (March 2023) | Milestone 3 (March 2024) | Milestone 4 (March 2025) | Milestone 5 (March 2026)
| Number of women and girls reached with appropriate menstrual hygiene materials to meet their needs in Cox's Bazar and Bhasan Char (includes both Rohingya and host communities) per month | Planned |  | 73825 | 24958 | 15400 | 21450 | 151660 |  | Maintained ability of partners to access camps.
|  | Achieved |  | 85168 | 21306 | 15180 | 46700 | 183559
Source
|  | UNHCR, IOM, Christian Aid and UNFPA logframe indicator agreed with the FCDO ahead of UK-funding |  |  |  |  | UNICEF | UNICEF, IOM, UNFPA
| Output Indicator 1.5 (Health) |  | Baseline | Milestone 1 (March 2022) | Milestone 2 (March 2023) | Milestone 3 (March 2024) | Milestone 4 (March 2025) | Milestone 5 (March 2026)
| Total Number of health consultations provided to refugees and host communities in Cox's Bazar and Bhasan Char (includes both Rohingya and host communities) | Planned | 0 | 466795 | 443580 | 299583 | 517429 | 541203
|  | Achieved |  | 355344 | 538376 | 430505 | 529144 | 550469
Source
|  | UNHCR, IOM and UNFPA logframe indicator agreed with the FCDO ahead of UK-funding |  |  |  |  | IOM, UNFPA and NRC Consortium | IOM, UNFPA, UNICEF and NRC Consortium
| Output Indicator 1.6 (Health) |  | Baseline | Milestone 1 (March 2022) | Milestone 2 (March 2023) | Milestone 3 (March 2024) | Milestone 4 (March 2025) | Milestone 5 (March 2026)
| Total Number of community members reached by Community Health Workers with SRHR. | Planned | 0 | 336758 | 230989 | 217639 | 422459 | 418005
|  | Achieved |  | 396096 | 232987 | 245467 | 567873 | 427943
Source -
|  | UNFPA Logframe indicator agreed with the FCDO ahead of UK-funding |  |  |  |  | IOM, UNFPA and NRC Consortium | IOM, UNFPA, UNICEF and NRC Consortium
| Output Indicator 1.7 (Shelter) |  | Baseline | Milestone 1 (March 2022) | Milestone 2 (March 2023) | Milestone 3 (March 2024) | Milestone 4 (March 2025) | Milestone 5 (March 2026)
| Total Number of households receiving shelter assistance | Planned |  | 8900 | 10131 | 1000 | 24487 | 586 |  | Tensions between refugee and host community do not inhibit operations COVID-19 and political situation in Bangladesh does not deteriorate impacting ability to implement.
|  | Achieved |  | 9211 | 10733 | 1170 | 25087 | 406
Source
|  | IOM logframe indicator agreed with the FCDO ahead of UK-funding |  |  |  |  | IOM and UNHCR | IOM and UNHCR
| Output Indicator 1.8 (SMSD and NFIs) |  | Baseline | Milestone 1 (March 2022) | Milestone 2 (March 2023) | Milestone 3 (March 2024) | Milestone 4 (March 2025) | Milestone 5 (March 2026)
| Total Number of people benefitting from site improvement works. (includes both Rohingya and host communities) | Planned |  | 62383 | 252351 | 418295 | 425529 | 560589
|  | Achieved |  | 57774 | 294546 | 422552 | 560589 | 599989
Source
|  | IOM logframe indicator agreed with the FCDO ahead of UK-funding |  |  |  |  | IOM | IOM
| Output Indicator 1.9 (SMSD and NFIs) |  | Baseline | Milestone 1 (March 2022) | Milestone 2 (March 2023) | Milestone 3 (March 2024) | Milestone 4 (March 2025) | Milestone 5 (March 2026)
| Total Number of square meters of slopes stabilized in the camps to protect the shelters and camp residents from soil erosion and landslide. | Planned |  | 3800 | 4000 | 7000 | 55267 | 40136 |  | Humanitarian actors and beneficiaries receive and understand information on Protection risks and available services. Beneficiaries accept protection services provided by Ir partners. Humanitarians and other key stakeholders apply the "do no harm" approach, are inclusive, and accountable to affected populations. Partners has access to persons in need of protection services, can strengthen referral mechanisms and raise awareness.
|  | Achieved |  | 6397 | 21901 | 7006 | 55384 | 36835
Source
|  | IOM and WFP Logframe indicator agreed with the FCDO ahead of UK-funding |  |  |  |  | IOM | IOM and UNHCR
| Output Indicator 1.10 (Protection) |  | Baseline | Milestone 1 (March 2022) | Milestone 2 (March 2023) | Milestone 3 (March 2024) | Milestone 4 (March 2025) | Milestone 5 (March 2026)
| Number of people who have accessed specialized protection services including GBV, legal support, property dispute, trafficking. (protection sector) per month | Planned | 0 | 89580 |  | 24000 | 38524 | 71839
|  | Achieved |  | 96394 |  | 24574 | 43046 | 85119
Source
|  | IOM and UNFPA logframe indicator agreed with the FCDO ahead of UK-funding |  |  |  |  | IOM, UNFPA and NRC Consortium | IOM, UNFPA and NRC Consortium
IMPACT WEIGHTING (%)
60%
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
| £27,472,139 FY(21-22); £17,472,335 FY(22-23); £21,347,859 FY(23-24); £17,848,713 FY(24-25) |  |  |  |  | 100%
INPUTS (HR): | FCDO (FTEs)
6 Full time FCDO Staffs, 0.25 FCDO Social Development Advisor, 1 Humanitarian Advisor Contractor from Palladium
Objective 2: Create economic opportunities for the Rohingya and Bangladeshis living in Cox’s Bazar to reduce poverty, despondency, criminality and local conflicts; and help refugees prepare for their future return.
OUTCOME 2 | Outcome Indicator 3.1 (Livelihoods) |  | Baseline | Milestone 1 (March 2022) | Milestone 2 (March 2023) | Milestone 3 (March 2024) | Milestone 4 (March 2025) | Milestone 5 (March 2026) |  | Assumptions
Rohingya and Host Communiities have consistent access to livelihoods opportunities. | Number of HHs reporting reduction in negative coping strategies | Planned | [6 empty] | Consider adding separate indicators for Rohingya and Host communities.
Achieved
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
Funding for this output is covered under the Site Management and Site Development services in output 1. There is no seggragated data of funding on livelihoods provided by the partners.
OUTPUT 2 | Output Indicator 2.1 (Livelihoods) |  | Baseline | Milestone 1 (March 2022) | Milestone 2 (March 2023) | Milestone 3 (March 2024) | Milestone 4 (March 2025) | Milestone 5 (March 2026) |  | Assumptions
Rohingya and bangladeshi Host Communities have consistent access to livelihoods opportunities. | Number of Rohingyas and Host Community members engaged in Cash for Work schemes and volunteer stipends per month- disaggregated by sex | Planned | 0 | 17210 | 8211 | 4455 | 41414 | 26133 |  | The Government of Bangladesh maintains access for humanitarian actors
|  | Achieved |  | 20602 | 8211 | 4455 | 41414 | 27772
Source
|  |  | UNHCR, IOM, UNICEF and WFP logframe indicator agreed with the FCDO ahead of UK-funding |  |  |  | UNFPA and IOM | UNFPA and IOM
| Output Indicator 2.2 (Livelihoods) |  | Baseline | Milestone 1 (March 2022) | Milestone 2 (March 2023) | Milestone 3 (March 2024) | Milestone 4 (March 2025) | Milestone 5 (March 2026)
| Number of beneficiaries (R + Host) receiving income generating inputs (training, skills, start up grants etc.) | Planned | [5 empty] | 44540 | 99.98% | The Government of Bangladesh maintains access for humanitarian actors
|  | Achieved | [5 empty] | 44530
IMPACT WEIGHTING (%) |  |  | Source
10% |  |  | UNHCR, IOM, UNICEF and WFP logframe indicator agreed with the FCDO ahead of UK-funding |  |  |  | WFP | WFP
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
Funding for this output is covered under the Site Management and Site Development services in output 1. There is no seggragated data of funding on livelihoods provided by the partners.
INPUTS (HR) INPUTS (HR): | FCDO (FTEs)
6 Full time FCDO Staffs, 0.25 FCDO Social Development Advisor, 1 Humanitarian Advisor Contractor from Palladium
Objective 3: Rehabilitate the environment in Cox’s Bazar to reverse damage caused to forest, land and water resources by the presence of the Rohingya population
OUTCOME 3 | Outcome Indicator 3.1 (Energy and Environment) |  | Baseline | Milestone 1 (March 2022) | Milestone 2 (March 2023) | Milestone 3 (March 2024) | Milestone 4 (March 2025) | Milestone 5 (March 2026) |  | Assumptions
Reducing negative environmental impact of the refugee community | Percentage of households whose cooking energy needs are met through environmentally safe sources that do not degrade the local environment. | Planned | 100% | 100% | 100% | 100% | 100% | 90% |  | The Government of Bangladesh's policies remain unchanged and maintained ability to access camps.
|  | Achieved |  | 100% | 100% | 58% | 90% | 60%
Source
|  |  | IOM, UNHCR and Safeplus logframe indicators agreed with the FCDO ahead of UK-funding |  |  |  | IOM | IOM
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
| £9,166,777 FY(21-22); £2,795,389 FY(22-23); £6,749,106 FY(23-24); £1,871,287 FY(24-25) |  |  |  |  | 100%
OUTPUT 3 | Output Indicator 3.1 (Energy and Environment) |  | Baseline | Milestone 1 (March 2022) | Milestone 2 (March 2023) | Milestone 3 (March 2024) | Milestone 4 (March 2025) | Milestone 5 (March 2026) |  | Assumptions
Rohingya and host communities’ domestic cooking fuel needs are met | Number of Rohingya HHs are receiving refills | Planned |  | 280891 | 82730 | 161414 | 189014 | 226475 |  | The Government of Bangladesh's policies remain unchanged and maintained ability to access camps.
|  | Achieved |  | 280891 | 95246 | 161414 | 201856 | 226475
Source
|  | UNHCR, IOM and Safeplus logframe indicator agreed with the FCDO ahead of UK-funding |  |  |  |  | UNHCR and IOM | UNHCR and IOM
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
| £9,166,777 FY(21-22); £2,795,389 FY(22-23);£6,749,106 FY(23-24); £1,871,287 FY(24-25) |  |  |  |  | 100%
INPUTS (HR) | FCDO (FTEs)
6 Full time FCDO Staffs, 0.25 FCDO Social Development Advisor, 1 Humanitarian Advisor Contractor from Palladium
Objective 4: Strengthen resilience to COVID-19 and disasters nationally and help people affected by current and future crises, including extreme climate events
OUTCOME 4 | Outcome Indicator 4.1 (National Disasters) |  | Baseline | Milestone 1 (March 2022) | Milestone 2 (March 2023) | Milestone 3 (March 2024) | Milestone 4 (March 2025) | Milestone 5 (March 2026) |  | Assumptions
Help people affected by current and future crises, including extreme climate events | Average number of days to reach beneficiaries with response | Planned | 20 | 10 | 7 | 6 | 7 | 6 |  | Mobility of partners remains and not disrupted by COVID 19 containment mesures imposed by the government.
|  | Achieved |  | 7 | 6 | 10 | 6 | 6
| Number of people whose resilience has been improved as a result of project support (ICF KPI 4) |  | Source
| % of beneficiary statisfied with humanitarian assistance |  | SFB and UNRCO Logframe indicator agreed with the FCDO ahead of UK-funding |  |  |  | UNRCO | START Network
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
| £665,000 FY(21-22); £1,979,543 FY(22-23); £568,285 FY(23-24); £1,287,597 FY(24-25) |  |  |  |  | 100%
OUTPUT 4 | Output Indicator 4.1 (Preparedness) |  | Baseline | Milestone 1 (March 2022) | Milestone 2 (March 2023) | Milestone 3 (March 2024) | Milestone 4 (March 2025) | Milestone 5 (March 2026) |  | Assumptions
Improved, coordinated approach to preparedness for emergency response | Total Number of humanitarian personal (including Govt and Non Govt) trained co-ordination and assessment methodoly including gender sesitative tools. | Planned | 100 | 190 | 250 | 40 | 90 | 50 | Reduced target since we stopped funding RCO and this now only delivered through CARE | Mobility of partners is not affected. Community is willing to partcipate and members have commitment of participation. National movement and work restrictions related to disease outbreak, elections, etc. do not disrupt process. NOGAB provides timely approval of FD6 and FD7 to partners which is key requirement for the NGOs to be able to run projects in Bangladesh.
|  | Achieved |  | 190 | 153 | 72 | 117 | 49
Source
Needs Assessment Working Group (NAWG) logframe indicator agreed with the FCDO ahead of UK-funding
| Output Indicator 4.2 (Preparedness) |  | Baseline | Milestone 1 (March 2022) | Milestone 2 (March 2023) | Milestone 3 (March 2024) | Milestone 4 (March 2025) | Milestone 5 (March 2026)
| Improving BHC – Government preparedness planning through signing of MoUs | Planned
Achieved
Source
UNRCO Logframe indicator agreed with the FCDO ahead of UK-funding
| Output Indicator 4.3 (Response) |  | Baseline | Milestone 1 (March 2022) | Milestone 2 (March 2023) | Milestone 3 (March 2024) | Milestone 4 (March 2025) | Milestone 5 (March 2026)
| Number of UK offers activated by the Government for emergency response | Planned
Achieved
Source
START Fund logframe indicaor agreed with the FCDO ahead of UK-funding
| Output Indicator 4.4 (Response) |  | Baseline | Milestone 1 (March 2022) | Milestone 2 (March 2023) | Milestone 3 (March 2024) | Milestone 4 (March 2025) | Milestone 5 (March 2026)
| Percentage of emergency response delivered through local and national organisations. | Planned | [5 empty] | 70%
|  | Achieved | [5 empty] | 83%
Source
START Fund logframe indicaor agreed with the FCDO ahead of UK-funding
IMPACT WEIGHTING (%) | Output Indicator 4.5 (Preparedness and Response) |  | Baseline | Milestone 1 (March 2022) | Milestone 2 (March 2023) | Milestone 3 (March 2024) | Milestone 4 (March 2025) | Milestone 5 (March 2026)
15% | Number of organizations (Government, UN Agencies, I/NNGOs, Civil Society)participating in the collection and anaylsis of data on hazards and vulnerability to inform decision making on preparedness and response prior to disasters. | Planned | 50 | 75 | 80 | 80 | 80
|  | Achieved |  | 70 | 70 | 70 | 100
Source
UNRCO Logframe indicator agreed with the FCDO ahead of UK-funding
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
| £665,000 FY(21-22); £1,979,543 FY(22-23); £568,285 FY(23-24); £1,287,597 FY(24-25) |  |  |  |  | 100%
INPUTS (HR) | FCDO (FTEs)
6 Full time FCDO Staffs, 0.25 FCDO Social Development Advisor, 1 Humanitarian Advisor Contractor from Palladium
Note on I60: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Awaiting UNHCR’s reporting
Note on J60: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Awaiting UNHCR’s reporting
Note on I87: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to check if UNHCR is providing anything.
Note on I92: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is UNFPA providing anything?
Note on J150: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3440 is under RAF Reply: Updated now
Note on J151: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3423 is under RAF Reply: updated
Note on J176: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 19790 per month
Note on J177: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 19790 per month
Note on I179: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: UNHCR to confirm

## Change frame
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
E.g. | Output 1, Indictor 2 | Indicator amended from 'No of children enrolled in primary schools' to 'Number of children enrolled in UNICEF supported primary schools (disagregated by sex) | Joe Bloggs | 2018-01-01
1
2
3
4
5
6
7
8
9
10

## Guidance Notes
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from FCDO and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR). Ongoing monitoring of progress against outcome milestones should still take place as an assessment of whether you expect to achieve the Outcome by the end of the programme will be included in Annual Reviews.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
Progress against Output milestones and results achieved will be assessed and scored during Annual Reviews and the Project Completion Review.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by FCDO and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The FCDO share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined - if relevant include indicators which towards the DRF / OP / ICF KPIs / MDGs.
l | Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your PRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
FCDO’s Approach to Value for Money (PrOF Guide) provides further advice on ensuring VfM.