## Annual Review Template 2025

Title: Rohingya Response and National Resilience Programme (RRNRP)
Programme Value £ (full life): £200m		Review date: 29 July 2025
Programme Code: 300554	AMP start date: 01/04/2021	AMP end date: / 31/03/2028

Summary of Programme Performance
Year	2021/22	2022/23	2023/24	2024/25
Overall Output Score	A	A	A	A+
Risk Rating	Major	Major	Major	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/60403949.odt
DevTracker Link to results framework:	To be uploaded

A. SUMMARY AND OVERVIEW
Description of programme

The Rohingya Response and National Resilience Programme (RRNRP), part of FCDO’s Major Project Portfolio, completed its fourth year of implementation from April 2024 to March 2025. It continued to deliver critical humanitarian support to over 1million Rohingya refugees and host communities, including food, water, sanitation, protection, energy, and livelihood opportunities. The programme has been delivering in line with the UK Government’s approach to International Development by reaching the most vulnerable people in humanitarian crises. Delivery was led by UN agencies—UNHCR, IOM, WFP, UNICEF, UNFPA and UNDP who implement directly and through local NGO partners. The programme continued to support the INGO Consortium featuring Norwegian Refugee Council (NRC), Danish Refugee Council (DRC), International Rescue Committee (IRC) and Humanity & Inclusion (HI). The programme also strengthens Bangladesh’s disaster preparedness and response capacity through collaboration with START Fund Bangladesh (SFB), Care Bangladesh and the UN Resident Coordinators Office (UNRCO), responding to four disaster events across Bangladesh (flood and cyclone) during the reporting period. In addition, the UK supported UNDP Cox's Bazar Analysis & Research Unit (CARU) to produce data-driven reports, analyses, early warnings, and research papers for two months.

In October 2024, an additional £8million from the Resilience and Adaptation Fund (RAF) was channeled through RRNRP. Both the global-level contribution and the specific activity for Bangladesh were approved by Minister Dodds. RAF funding helped to strengthen the resilience of smallholder farmers and improved access to sustainable water, sanitation, and hygiene services in the host community in Cox’s Bazar. It has also enhanced the resilience of the Rohingya community by supporting shelter interventions, particularly through the scale-up of the lime-stabilised soil shelter (LSS) and the provision of Site Management and Site Development (SMSD) services. This additional allocation has been instrumental in fostering social cohesion between the host and Rohingya communities.

The RRNRP disbursed £43.35 million (including RAF and in-year top-ups) during the review period and maintained a strong performance, earning an overall rating of A+.

This annual review covers the activities undertaken during the period from May 2024 to March 2025. This review was conducted by FCDO’s Humanitarian Team, including the newly appointed technical adviser from HSOT, and was quality assured by the Second Secretary Political at the British High Commission in Dhaka. Quantitative data was sourced from implementing partners and qualitative data was collected through consultation during field visits and online information https://rohingyaresponse.org/.

Major lessons and recommendations for the year ahead

Global funding pressures in 2025 have significantly impacted the financing of the Rohingya response; some services have already been suspended (e.g. education in June 2025), and we expect further service reductions this year, including pipeline breaks in food, fuel, soap and a probable reduction in and targeting of food rations. In response, the Inter-Sector Coordination Group (ISCG) launched a rapid and ongoing prioritisation exercise, urging donors to focus their support on essential life-saving activities, and the most vulnerable.

High operational costs on Bhasan Char – for both the government and the humanitarian community – and the growing number of Rohingyas attempting to leave the island have raised concerns regarding the sustainability of Bhasan Char operations. The UN agencies are considering a phased withdrawal from Bhasan Char, though this decision remains contingent on final approval from the Interim Government (IG). Considering these challenges and the need to prioritise funding, the FCDO in Bangladesh will likely cease funding the response on Bhasan Char from FY2026/27 and has informed relevant partners.

Key Recommendations
1. The UK should engage more systematically with coordination leadership, including sector leads, in Dhaka and Cox’s Bazar. FCDO should challenge all partners and response leadership to find increasingly innovative, cost effective and impactful ways to deliver and coordinate assistance. The UK should also monitor the prioritisation exercise and the funding situation, targeting the most urgent priorities, leveraging our flexibility to respond to emerging gaps, and using our advocacy and policy engagement to drive a more sustainable and effective response.
2. The FCDO team will review and revise output indicators of objective 2 by December 2025. The FCDO should acknowledge the contracting funding landscape and focus increasing diplomatic efforts on policy advocacy, resource mobilisation and disrupting the status quo to create an enabling environment for self-reliance.

To enhance the effectiveness of the Rohingya humanitarian response, the UK should advocate for more flexible funding approaches, particularly from UK-funded multilateral funds and development banks. FCDO should also encourage and support partners to shift funding mid-year to fill emerging gaps. This would enable adaptive programming and timely resource allocation based on real-time needs.

Currently, VfM considerations are incorporated through partners’ annual funding proposals and the annual review process. However, the absence of a programme-wide VfM framework limits the ability to consistently track and measure VfM at the Strategic Outcome level. To address this, the FCDO programme team will explore the development of overarching programme-level VfM indicators in consultation with implementing partners.

By institutionalising more formal quarterly meetings in addition to current regular ad-hoc ones, Programme Managers will determine whether Implementing Partners have improved performance and adhere to our request to proactively inform FCDO of any potential risks related to programme delivery, finance, fraud and safeguarding, along with corresponding mitigation plans. FCDO should use quarterly meetings to reiterate our expectation that we are consulted in advance of any proposed changes to the project scope or budget, particularly those involving exchange rate gains or underspends.

The UK should increase its engagement with the multilateral development banks (MDBs) and international financial institutions (IFIs) such as the World Bank and Asian Development Bank and should encourage other donors to do the same. The UK should stay abreast of grants and loans in the pipeline and leverage its diplomatic position and ability to meaningfully influence program policy, design and implementation at earlier stages of development. Comments received from ADB focal points indicated that member states don’t often offer such detailed and helpful guidance, and this will be important for ensuring inclusive, risk-based, decentralised anticipatory action and DRR, and ensuring refugee hosting regions are incorporated into climate and development plans in a meaningful way to prevent regional inclusive economic growth disparities. The UK should also strengthen its oversight of MDB/IFI humanitarian investments in Bangladesh (e.g. through targeted monitoring visits) and should encourage their full participation in coordination structures.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

ToC summary. The programme’s Theory of Change remains valid, positioning UK diplomatic engagement and humanitarian programming as key to enhancing Rohingya self-reliance and protection, supporting their eventual return to Myanmar, and strengthening Bangladesh’s resilience to shocks. Expected outcomes include reduced GBV, increased incomes, more cost-effective responses, and improved disaster preparedness.
[note] RRNRP’s full ToC is set out in its Business Case (2021), p. 28.

Context Shifts: The operating context for RRNRP deteriorated significantly in FY2024/25 and remains volatile. The political shift in Bangladesh and escalating conflict in Myanmar—particularly in Rakhine State—have further reduced prospects for the safe, voluntary, and dignified return of the Rohingya. Over 150,000 new arrivals have already been added to the response in 2025, placing additional strain on overstretched services and requiring an additional $84m of humanitarian assistance. Global ODA cuts in 2025 have led to significant funding pressures. The 2025 JRP was only 22.11% funded ($206.8m) as per OCHA FTS, or 41% ($360.4m) based on tentative in-country estimates—down from 68.5% in 2024. There are reports of increasing calls for recruitment to armed groups and early repatriation. Bangladesh also remains highly vulnerable to natural disasters, exacerbated by the ongoing El Niño pattern. Cox’s Bazar is classified as IPC Phase 3 (Crisis) for food security, indicating serious vulnerability whereas Bhashan char and national averages are in IPC Phase 2 (Stressed). Overall stunting and wasting rates are significantly higher among Rohingya children, especially in Cox’s Bazar in comparison on national averages.
[note] Joint-Protection-Monitoring-Report-Quarter-1_2025-Final.pdf
[note] Bangladesh: Acute Food Insecurity Projection Update October - December 2024 | IPC - Integrated Food Security Phase Classification

Validity of ToC assumptions: While the logic of the RRNRP’s Theory of Change remains valid, some assumptions have not been realised. During the reporting period, the previous government did not permit progress on livelihoods. However, the IG has made some headway by allowing limited self-reliance initiatives, responding to the asks in the UK co-drafted non-paper and high-level advocacy. These include granting access to SIM cards and enabling mobile cash transfers for Rohingyas in the camps. Sectoral technical proposals are currently being developed for government endorsement, and their outcomes will be reflected in the next review.

On the political front, there has been no advancement toward creating conditions for the safe, voluntary, and dignified return of the Rohingya. Instead, escalating conflict between the Arakan Army and the Myanmar military has led to the arrival of an additional 150,000 people in Cox’s Bazar, further complicating prospects for repatriation. This influx, combined with a sharp decline in aid funding, has placed increased pressure on humanitarian operations within the camps.

Diplomatic engagement in Bangladesh. The UK continues to engage with the Government of Bangladesh (GoB) on improving camp conditions, supporting Rohingya self-reliance, and ensuring any returns to Myanmar are safe, voluntary, and dignified. As co-coordinator of the Rohingya Donor Group, the UK has led donor engagement, represented the group in senior forums, and driven collaboration with the humanitarian system. This leadership has continued informally beyond the co-coordination rotation. In FY 2025–26, the UK will maintain advocacy with the UN and GoB to reduce response costs through efficiencies and policy reforms, particularly around self-reliance, where progress has already been made.

Diplomatic engagement and mobilisation internationally. The UK continues to lead diplomatic efforts for a political solution and accountability for Rohingya atrocities, including supporting the Gambia’s ICJ case, and the Myanmar Witness and Independent Investigation Mechanism on Myanmar to collect evidence. As UN Security Council penholder, it drives action on Myanmar. The UK also co-hosted a UN High-Level Meeting in Bangkok and joined the Rohingya Multi-Stakeholder Pledge at the Global Refugee Forum.

Progress Towards Outcomes: The programme continues to progress against its outcome and impact indicators for April 2024–March 2025 with consistent and significant progress made from the previous reporting period in many areas and slight deterioration in others:

Outcomes (improvements): Rohingya Response 2024-25 continued to see significant improvements, particularly in maternal and newborn child healthcare: maternal mortality continued to drop by 30% to 136 deaths per 100,000 births; skilled birth attendance rose to 98%, underpinned by UK-backed community health referral networks; and health-service satisfaction jumped to 98% - all dramatically beating expectations and planned targets. After food ration cuts in 2023 dropped acceptable Food Consumption Scores to 30%, UK-supported ration restoration helped enable recovery to 65% in 2024, meeting the annual target. However, with global ODA reductions, maintaining this progress in 2025 will be challenging, and ration cuts are anticipated, underscoring the urgent need to scale up self-reliance programming for refugees and affected host communities. National Disaster Response: There was progress in the speed of response efforts. The average time for a national response to reach beneficiaries (through NGOs funded by SFB), after an emergency reduced from 10 days to 6 in the last year. This is the result of refining response mechanisms and coordination between SFB members.

Outcomes (stable): Some indicators remained stable. For example, household access to sufficient water held steady at 85%, and the percentage of sanitation facilities in the camps reported to be functional and accessible remained at 96%—testimony, in part, to the UK’s sustained investments in the water, sanitation and hygiene sector during the review period and the consistent coordination leadership, innovation and performance of the Sector. Shelter protection needs were stable, with 72% of households feeling safe from rain and flooding, backed by UK-supported slope stabilisation and fire-break construction.

Outcomes (worsening): Killings and firearm use dropped by 36% in early 2025 due to “Mission Harmony”, but abductions rose by 12%. Organised groups reportedly used public gatherings and coercion to recruit refugees for conflict in Myanmar. This underscores the urgent need to maintain the camps as safe, civilian, and humanitarian spaces. Requests resolved via the Common Feedback Platform plunged from 47% to 26% during the review period, reflecting rising protection concerns. Sexual Exploitation and Abuse (SEA) and Intimate Partner Violence (IPV) risks remain high. Under-reporting persists, and camp insecurity hinders night-time referrals. Membership in the Preventing SEA network fell from 190 agencies to 168, primarily due to funding cuts and closure of operations, underscoring the need to strengthen protection partnerships, which we have done through increased investment in the NRC-led Protection Consortium in 2025-26.
[note] https://rohingyaresponse.org/wp-content/uploads/2025/05/Joint-Protection-Monitoring-Report-Quarter-1_2025-Final.pdf

Impact (mixed): Progress towards the impact indicators has been mixed. Last year, food ration cuts increased malnutrition dramatically, with Global Acute Malnutrition (GAM) rising from 12.3% to 15.4 (emergency level) for the first time since 2017. Severe Acute Malnutrition (SAM) levels tripled from 0.7% to 2.1%. Unfortunately, at the time of publishing we had no access to the latest nutritional status data, and the UK is actively holding partners to account for strengthening data collection and analysis processes. Though full rations have been restored, and food consumption scores recovered fully, the effects of this will take time to reverse, and we expect there to be no immediate reversal of the post-ration-cut spike in malnutrition. On the positive side, the number of under 5 deaths per 1000 births in the camps fell for the second year from 24 to 18, beating expectations and targets.

Increased Justification for the RRNRP to Continue: The RRNRP has shown sustained performance amid funding shocks and rising protection risks, as the Rohingya crisis enters its ninth year. With no viable conditions for return to Myanmar, refugees remain reliant on donor-funded assistance for their safety and wellbeing. The UK’s role has become increasingly pivotal, shifting from main participant to principal stabiliser, especially following broader donor contraction. This has enabled the UK to have an even greater influence over the response, as evidenced in recent breakthroughs with the IG on creating a conducive environment for self-reliance, and mobilising central funding to operationalise them in partnership with peer donors. Emphasis is also growing on expanding the donor base, including non-traditional donors, in anticipation of further funding cuts. Continued UK support is essential to prevent service breakdowns, strengthen disaster response capacity, and maintain diplomatic credibility and influence.

## C. DETAILED OUTPUT SCORING

Output Title	Objective 1: Maintain humanitarian assistance and improve safety to enhance the wellbeing of the Rohingya and neighbouring local Bangladeshi communities.
Output number:		1	Output Score:	A+
Impact weighting (%):		60%	Weighting revised since last AR?	No

Indicators	Milestones for this review	Progress
1.1 Total number of refugees receiving food assistance through e-vouchers in Cox’s Bazar and Bhasan Char (Food Security)	200,281	203,186 (101%) A
1.2 Number of refugees and members of the host community with access to safe drinking water in Cox’s Bazar and Bhasan Char per month (WASH)	274,000	300,925 (110%) A+
1.3 Number of refugees and members of the host community with access to adequate sanitation facilities according to sector standards in Cox’s Bazar and Bhasan Char per month (WASH)	75,000	97,180 (130%) A+
1.4 Number of women and girls (refugees and members of the host community) reached with appropriate menstrual hygiene materials to meet their needs in Cox’s Bazar and Bhasan Char per month (WASH)	21,450	46,700 (218%) A++
1.5 Total number of health consultations provided to refugees and members of the host community in Cox’s Bazar and Bhasan Char (Health)	517,429	529,144 (102%) A
1.6 Total number of refugees and members of the host community reached by Community Health Workers with SRHR and COVID-19 awareness, counselling, and outreach (Health)	422,459	567,873 (134%) A+
1.7 Total number of refugee households receiving shelter assistance (Shelter)	24,487	25,007 (102%) A
1.8 Total number of refugees and members of the host community benefitting from site improvement works (SMSD)	425,529	560,589 (131%) A+
1.9 Total number of square meters of slopes stabilised in the refugee camps (SMSD)	55,267	55,384 (100%) A
1.10 Number of refugees who received community-based protection in Cox’s Bazar and Bhasan Char per month (Protection)	51,821	52,102 (101%) A
[note] All indicators under Outputs 1-3 are for activity in Cox’s Bazar, unless Bhasan Char is referenced in the indicator.
[note] All output indicators in this review are sourced from partners’ end of project reporting to FCDO.

This output scored an A+ for continuing to provide quality humanitarian support to Rohingya refugees and host communities.

Food assistance Food assistance in Cox’s Bazar, delivered through WFP’s e-voucher outlets, was the RRNRP’s largest single contribution, accounting for 17.5% of total programme expenditure. Targeting camps with the highest refugee populations, the programme exceeded its goal by reaching 203,186 refugees per month for three months—3,000 more than planned—thanks to exchange rate savings. Due to funding shortfalls, rations were temporarily reduced to USD 10 per person per month (Aug–Nov 2024), but were restored to USD 12.5 from January 2025, thanks to prioritisation of food aid by the UK and other donors.

Water, Sanitation and Hygiene (WASH) services were delivered by UNICEF and their downstream NGO partners in both Cox’s Bazar and Bhasan Char. These efforts surpassed expectations by reaching a larger number of refugees and host community members with safe drinking water, improved sanitation facilities, and essential hygiene supplies. 51% of the beneficiaries were women, and 1% were persons with disabilities. In response to a severe water shortage in Teknaf (Jan–Mar), UNICEF, supported by a top-up from FCDO, implemented water trucking to ensure at least 10 litres of water per person per day for drinking and cooking, addressing urgent needs among vulnerable Rohingya and host populations.

Health: UK-funded health services in Cox’s Bazar, delivered by IOM through the national NGO Friendship, included five Primary Health Centres (PHCs) and a maternity centre, with additional support from UNFPA and the NRC Consortium in both Cox’s Bazar and Bhasan Char. These interventions slightly exceeded expectations, delivering 529,144 consultations and 13,620 facility-based deliveries by skilled birth attendants. This is attributed to increased patient load in IOM facilities due to closure of other facilities, improved quality of service, expansion of palliative care and Hep C treatment services. While 38 maternal deaths were reported, this marked a 28% reduction from the previous period. Community Health Workers also reached 274,384 individuals with SRHR and COVID-19 awareness, counselling, and outreach.

Shelter: UK-funded shelter support through IOM and UNHCR met targets for households receiving shelter materials and safe shelter solutions. In December 2024, the IG endorsed one new ‘safer shelter’ design, the Lime Stabilised Soil Shelter (LSS), which, despite higher upfront costs, is expected to be cost-effective over five years. FCDO’s Resilience and Adaptation Fund (RAF) played a key role in rolling out these new shelters, enhancing disaster resilience, fire safety, and sustainability. RAF also supported safe housing for 318 Extremely Vulnerable Individuals (EVIs), with IOM assisting in material transport and construction.

SMSD: FCDO’s support through IOM and UNHCR has enhanced the resilience of vulnerable communities to climate shocks through sustainable land management and improved adaptive capacity. The initiative exceeded expectations in stabilising slopes to reduce landslide risks and rehabilitating stairs, pathways, and roads damaged by monsoon rains. Site Development (SD) activities have significantly improved safety, dignity, and accessibility in affected areas, with strong community participation in planning and implementation.

Protection: Implementing partners delivered a comprehensive range of protection services, including general protection support (including GBV services), legal counselling and information sharing, referrals, housing, land and property (HLP) assistance, individual protection assistance (IPA), and support in obtaining civil documentation. With support from FCDO, the construction of a second emergency safe shelter was completed. 43,046 individuals received specialised protection services. The new facility significantly improved access to GBV recovery support, offering a safe, dignified space that promotes psychosocial well-being for survivors and their families.

Education: The UK continued to support education in Cox’s Bazar through its centrally managed contributions to Education Cannot Wait (ECW) and the Global Partnership for Education (GPE)—initiatives outside the RRNRP—demonstrating the complementarity of UK funding channels.

Prevention of Sexual Exploitation, Abuse, and Harassment (PSEAH): Rohingya women and girls remain vulnerable to various forms of SEA, including forced or abusive marriages, commercial sexual exploitation, and domestic violence. FCDO’s continued funding for the PSEA Network Coordinator has been catalytic in mainstreaming PSEA in the JRP, introducing mandatory PSEA activities for JRP partners and developing a Joint Action Plan in collaboration with the National Network. Two Training of Trainers (ToT) sessions on the IASC “Saying No to Sexual Misconduct” learning package were successfully conducted, strengthening the capacity of PSEA Focal Points across the network.

Changes to the output: No significant changes have taken place or are proposed for this output.
Lessons and Recommendations:
L1: Global funding cuts in early 2025 have severely impacted multiple sectors, including essential health services. Eleven primary healthcare centres (PHCs) are now at risk of closure, potentially affecting access for around 300,000 refugees, depending on partners’ ability to reprioritise resources. Nine Health Posts are also at risk of closure and one has been closed. Vulnerable groups are likely to be disproportionately affected, and morbidity and mortality might increase. FCDO was initially able to support some health facilities at risk of closure; we should continue working to fill gaps where possible and encourage flexibility among our partners.
[note] https://rohingyaresponse.org/wp-content/uploads/2025/05/CXB-Health-Sector-Bulletin-Mar-2025.pdf
[note] https://rohingyaresponse.org/wp-content/uploads/2025/07/CXB-Health-Sector-Bulletin-May-2025.pdf

L2: Although safer shelter designs and materials have been approved by the Government of Bangladesh, full upgrades will require years and substantial funding. With limited resources and competing priorities like food, shelter services remain constrained. FCDO supports SCCCM’s initiative to adopt a multi-sectoral approach by establishing a Multi-Sectoral Settlement Planning (MSSP) Task Force to improve access and service delivery across camps.

R1. Prevent Food and Hygiene Pipeline Breaks: Without additional resources mobilised at short notice in March 2024, rations would have dropped by 50% to $6/person per month. At time of writing, WFP funding for General Food Assistance is secured only through December 2025, with soap supplies and LPG expected to run out by August 2025. The UK should urgently monitor funding gaps, advocate with key donors, and support a coordinated response to avoid a pipeline break, including through engagement with non-traditional donors and the multilateral development banks. Timeframe: March 2026

R2. Strengthen Health Referral Systems: FCDO should intensify advocacy to drive inter-agency collaboration and establish a harmonised health referral mechanism, ensuring more efficient and equitable access to services. Timeframe: March 2026

R3. Safeguard Community Accountability: FCDO should leverage its influence with partners and sector leads within the response to promote regular, safe, independent, transparent, and inclusive consultations with refugees and civil society. This can be achieved by streamlining and consolidating feedback and complaints mechanisms, potentially starting with the Protection Consortium. This approach will strengthen accountability to affected populations (AAP) and ensure that community voices are meaningfully integrated into programme design and delivery. Timeframe: March 2026

R4: Nutrition: In 2024, initial results from the annual Standardised Expanded Nutrition Survey (SENS) indicated improvements in Global Acute Malnutrition (GAM) and Severe Acute Malnutrition (SAM) rates, aligning with findings from the Health Sector. However, concerns over data quality meant the Nutrition Sector chose not to publish the SENS results, forcing them to base their activities on alternative data sources. To rebuild confidence, the nutrition sector will need to provide a written account of what happened, explain what data sources they are using instead, and set out how they will avoid similar issues in future SENS surveys. Without these measures, FCDO cannot consider funding nutrition. Timeframe: September 2025

Progress on previous recommendations from the 2024 Annual review:

R1: It remains clear that a more sustainable approach to the Rohingya response would help to mitigate the deteriorating camp environment. Continued engagement with GoB is required to explore opportunities to move this forward, particularly on more durable shelters and greater income generation opportunities. Update: After two years of sustained advocacy, a significant milestone was achieved in December 2024 when Bangladesh’s Ministry of Foreign Affairs (MOFA) approved one new ‘safer shelter’ designs. These are designed to better protect the Rohingya from fires, cyclones and disasters.

R2: The worsening conflict in Myanmar risks affecting the camps in Cox’s Bazar and prompting a further influx of people into Bangladesh. BHC Dhaka and BE Yangon should continue to closely coordinate humanitarian and political activities to address these issues where possible. Update: In the review period there has been close collaboration between BHC Dhaka and BE Yangon. This was demonstrated by a visit of the BE Yangon Charge d’Affaires to the Rohingya refugee camps in February 2025 and his continued engagement with the Government of Bangladesh on cross-border issues.

Output Title	Objective 2: Create economic opportunities for the Rohingya and Bangladeshis living in Cox’s Bazar to reduce poverty, despondency, criminality, and local conflicts; and help refugees prepare for their future return.
Output number:		2	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator	Milestone for this review	Progress
2.1 Number of refugees engaged in Cash for Work schemes and ‘volunteer’ stipends	41,414	41,840 (101%) A
2.2 Number of members from host communities engaged in Cash for Work schemes or other income generation opportunities	8,750	14,206 (162%) A+

This output scored A. Substantive livelihood opportunities remain restricted. However, the UK funded Cash for Work and Volunteer activities through IOM, WFP, UNHCR and UNFPA, providing short-term income opportunities for refugees.

Resilience and Adaptation Fund: Under RAF funding, WFP implemented three core components to strengthen food security and resilience among host communities in Cox’s Bazar. The project upgraded 62 aggregation centres, boosting local food production and supply to Fresh Food Corners in Rohingya camps. Despite a shortened timeline, over 8,800 people participated in climate-resilient infrastructure works, earning short-term income while improving agricultural access. Livelihood support reached 5,384 smallholder farmers—85% women—through training, seed grants, and group initiatives. In total, 14,207 people directly benefited, with over 30,000 households indirectly supported. Digital platforms ensured transparency and strengthened market linkages.

Changes to the output: No significant changes have taken place for this output. The FCDO team will review and revise the indicators by December 2025.

Lessons and recommendations:

L1: Under the RAF programme, WFP constructed climate-resilient infrastructure—such as roads, canals, and irrigation systems—by employing host community members through a Cash-for-Work initiative. Due to delays and a compressed implementation timeline, WFP significantly scaled up efforts mid-project, increasing participants from 3,350 to 8,823. While infrastructure targets were met, the shortened work period (from 5 months to 2.5) limited income opportunities and highlighted the need for stronger contingency planning for time-sensitive activities. Also, the construction of LSS shelters under the RAF posed a significant challenge due to short project timeline (four months). Limited space for prefabrication activities and a lack of skilled personnel, including carpenters and volunteers, further constrained progress, ultimately leading to a No Cost Extension for the activities delivered by IOM. In response, IOM expanded on-the-job training opportunities for interested carpenters and labourers across multiple camps, supporting the site management unit and helping to close the skills gap. In future FCDO should aim, where possible, to allocate more time to resilience projects.

R1: The original four-year Business Case (BC) envisioned that by Year 3 (April 2023), the environment in Cox’s Bazar would become more conducive to supporting livelihoods opportunities, with funding to commence in the final two years of the RRNRP. This aspiration has not been realised, as substantive livelihoods was not permitted by the previous government. The UK should continue to advocate for a more permissive policy environment on self-reliance and should explore opportunities to fund self-reliance activities, balancing this with urgent lifesaving assistance. Timeframe: by March 2026.

Progress on previous recommendations from the 2024 Annual review:
R3: Linked to R2, the UK should continue to advocate for an expansion of income generation and skills training opportunities available to improve self-reliance and reduce the risk of the skills market becoming saturated. This could include revisiting the Skills Development framework to suggest an expansion of the number, level and sustainability of skills that training is permitted for. Update: The UK has been one of the lead donors in advocating to reinforce the Rohingya Refugees’ self-reliance while they remain in Bangladesh. The High Commissioner has met regularly with the IG to raise this issue, alongside other donors, and there are early indications that policy change may be possible.

Output Title	Objective 3: Rehabilitate the environment in Cox’s Bazar to reverse damage caused to forestland and water resources by the presence of the Rohingya population
Output number:		3	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	No

Indicators	Milestones for this review	Progress
3.1 Number of Rohingya households receiving LPG refills	189,014	201,856 (107%) A
3.2 Number of LPG refills provided to households	160,000	192,597 (120%) A+
3.3 Number of pressure cookers distributed to Rohingya refugees	98,811	100,659(102%) A

The output met expectations for LPG distribution. The UK, through IOM and UNHCR, provided LPG cylinders to refugees in Cox’s Bazar, reducing the need for firewood collection and mitigating environmental degradation, health risks, and tensions with the host community.

During the review period, the UK allocated additional funding to IOM to expand LPG refills in the camps. The distribution of 100,659 pressure cookers helped lower LPG consumption, reduce fire hazards, and cut costs. Refugees received training on proper stove placement during LPG and fire safety sessions to ensure adequate ventilation and reduce fire hazards. However, a potential disruption in LPG supply from August 2025 in IOM-managed camps could increase reliance on firewood, posing environmental risks. The UK has actively engaged to broaden the donor base for energy provision through diplomatic engagement with other donors, including the Gulf States, and is discussing possible co-financing of LPG with the Qatar Fund for Development (QFFD).

Changes to the output: No changes in this reporting period

Lessons and recommendations:
L1: Recent studies on the use of pressure cookers have confirmed their potential to significantly extend LPG refill cycles, resulting in measurable cost reductions, as noted in previous Annual Reviews. These findings have informed a more targeted approach, allowing for customized refill schedules based on household size. Implementation is already underway: both IOM and UNHCR have begun distributing pressure cookers and are coordinating efforts to standardize refill cycles across all 33 camps by 2025. This is a positive example of coordination between implementing partners.

L2: The project's overachievement was driven by favourable foreign exchange gains, which led to cost savings. These savings were strategically redirected to provide additional LPG refills, ensuring full utilisation of funds and uninterrupted progress of the LPG pipeline in the camps. FCDO was informed of the decision after the project ended, with an exceptional approval request by one of the partners. Going forward, FCDO will proactively follow up on the exchange gains on a quarterly basis and remind partners of their obligation to consult FCDO before any funds are redirected.

R3: BHC will seek to finalise a co-funding agreement with QFFD and scope out further opportunities to collaborate with Gulf States to unlock resources and build strategic partnerships for sustainable energy. Timeline: November 2025.

Progress on previous recommendations from the 2024 Annual review:
R4: The provision of pressure cookers has led to savings in the cost of LPG. The UK should explore providing funding for pressure cookers to IOM’s camps during the next review period. It should also closely monitor the impact of reducing the cycle length on the refugees’ needs and work with the UN on whether an increase to the cycle length of LPGs is required. Update: The UK continued funding pressure cooker distribution during the review period.

R5: LPG is widely recognised as the safest, cleanest, and most efficient method of cooking currently available. However, the UK should continue to pursue research for cost effective alternatives, such as solar, to reduce costs and emissions, including through UK-funded CMPs. Update: FCDO funded research to test out Rohingya and host community user experience with solar-powered e-Cooking which holds promise as a complementary solution to LPG use in both refugee camps and host communities. (Refer to evidence section)

Output Title	Objective 4: Strengthen resilience to disasters nationally and help people affected by current and future crises, including extreme climate events
Output number:		4	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	No

Indicators	Milestones for this review	Progress
4.1 Preparedness: Total number of humanitarian personnel (including Government and Non-Government) trained on co-ordination and assessment methods, including gender sensitive tools	90	117 (130%) A+
4.2 Preparedness: Total number of strategy and contingency plans developed for national disasters efforts	1	0 (0%) C
4.3 Response: Average number of days taken for support to reach beneficiaries after the onset of a disaster (this figure only accounts for FCDO-funded activities through SFB)	10	6 (100%) A
4.4 Response: Total number of humanitarian coordination meetings organised, including in emergency situations .	14	30 (214%) A++
4.5 Preparedness & Response: Number of organisations (Government, UN, NGOs, Civil Society) participating in the collection and analysis of data on hazards and vulnerability to inform decision making on preparedness and responses prior to disasters	80	100 (125%) A+

This output met expectations, scoring an A+ overall. UK support helped Bangladesh to increase its preparedness systems and response to disasters. The UK supported response and preparedness for 4 disasters, starting from Cyclone Remal in April 2024 to three phases of flooding in the Northeast (Sylhet) and Eastern division in Bangladesh. The support was provided through preparedness, response and recovery efforts through four partners:

  1. START Fund Bangladesh (SFB) is a network of local and international NGOs that provides rapid emergency response for 45 days after the onset of a crisis. SFB activated nine response alerts this reporting year, responding to Cyclone Remal and three phases of flooding in Sylhet, Eastern and Southeastern districts. Delivered through national NGOs, the response reached 79,000 beneficiaries (51% female and 2.9% disabled persons) with cash transfers, WASH, and shelter services. Despite political disruptions, SFB met its six-day response target (making it the fastest responder in Bangladesh) and fully utilised its funds, thanks to strong local presence.

Furthermore, in the reporting period, SFB provided capacity building support to its 35 national member NGOs. This focused on safeguarding and beneficiary feedback mechanisms. SFB is also the co-lead of the Localisation Technical Working Group, working to build more locally driven humanitarian responses across the country.

The UN Resident Coordinator’s Office (UNRCO) co-ordinates humanitarian responses amongst the government, donor and humanitarian agencies during disasters, primarily through platforms such as Humanitarian Co-ordination Task Team (HCTT) and Humanitarian Advisory Group (HAG). UNRCO also engage with GoB on improving preparedness, co-ordination, and resource allocation. Following Cyclone Remal and flooding from April to September 2024, the UNRCO generated a Humanitarian Response Plan (HRP) activating international support through the CERF and DREF totalling £25m (18% of the total funding requested under HRP). The RCO also facilitated decentralised area-based co-ordination efforts with local government, UN, NGOs and CSOs, which helped cover over 1 million climate vulnerable people across Bangladesh with early warnings prior to the disaster occurrence. However, political turmoil hindered progress on key outputs, including an earthquake contingency plan, resulting in 55% of the UNRCO’s allocated budget in the financial year going unspent. These funds were later repurposed for the Rohingya response.

  1. The CARE-led Needs Assessment Working Group (NAWG) conducts comprehensive assessments of humanitarian needs after disasters. Prior to Cyclone Remal and severe flooding that occurred last year, NAWG generated 5 Anticipatory Impact analyses to enable the government and humanitarian agencies to act early before disasters. Additionally, they generated five situation overviews, four joint needs assessments and two damage and loss analyses after the disasters. This helped to enable evidence-based resource allocation by GoB, donors, and humanitarian agencies. Beyond this, CARE helped to build the capacity of 58 staff from local government and national NGOs on damage and loss data collection.

  1. WFP (Eastern Flood Recovery): To support the recovery of flood-affected communities in Noakhali, WFP implemented the Eastern Flood Recovery initiative, benefiting over 32,000 people through conditional assistance. More than 19,000 individuals received support via income-generating activities such as livestock rearing, agriculture, and crafts, with each household receiving a BDT 10,000 cash grant upon completing entrepreneurship and skills training. This was complemented by capacity-building sessions on digital literacy, value chains, business planning, and social behaviour change. Additionally, 12,615 individuals participated in cash-for-work schemes, earning BDT 500 per day over 20 days for rehabilitating critical infrastructure including roads, embankments, and canals. An estimated 200,000 people and 4,000 acres of farmland benefited from improved infrastructure and economic stimulation undertaken through this project.

Changes to the output: No changes in this reporting period

Lessons and recommendations:
L1: SFB used in-kind assistance (cooked food) in place of cash transfers following eastern flooding in Bangladesh when they identified markets not to be functioning. This indicated SFB’s ability to adapt to the changing context, design response modality through community consultation, and strengthen its accountability through practically addressing the needs on the ground. FCDO should continue to support the application of context-specific approaches in disaster response.

L2: The CARE project faced challenges in integrating the NAWG with the Government’s Department of Disaster Management (DDM) due to the political turmoil and shift in the government. This led to CARE being unable to deliver its objective of strengthening government ownership and institutionalizing the NAWG within the government’s disaster management systems. CARE aims to complete this during the next review period.

L3: A key lesson from WFP’s flood recovery project is the importance of integrating with government social protection systems. By aligning WFP’s targeting with national registries and mechanisms, the programme improved coordination, minimized duplication, and effectively reached the most vulnerable households. Beyond the programme, WFP could integrate with the government into future recovery programming to ensure inclusive, scalable, and sustainable outcomes.

R3: We have seen in SFB’s response to Cyclone Remal that providing short term emergency response fails to provide a meaningful impact in reducing the stress of the communities. During our monitoring visit, we found that the cash grants provided by START were primarily used by communities to repay existing debts. As a result, many households remained in a state of extreme poverty and continued to struggle with the aftermath of climate-related disasters. The need for recovery support remains substantial, particularly in constructing durable embankments, rebuilding resilient housing, and promoting climate-adaptive livelihoods to strengthen resilience against future shocks. There is a need to engage with START Fund to rethink its response activities based on the context and needs of communities and whether early recovery would be a more meaningful intervention instead of emergency response. Timeframe: March 2026.

Progress on previous recommendations from the 2024 Annual review:
R4: Linked to L5, BHC Dhaka should emphasise that partners need to notify early if there are any challenges in delivery and revise their budgets and workplans accordingly they anticipate a delayed start or underspend. Update: FCDO arranged quarterly meetings with partners updating on workplan, financial expenditures, and flagging risks in delivery and financial forecasts. In quarter 3 (December 2024), UNRCO and CARE confirmed unspent programme funds, which the FCDO Humanitarian Team swiftly repurposed to UNICEF under the Rohingya response programme to address acute water shortages in Teknaf.
## D: VALUE FOR MONEY

Key cost drivers and performance

The RRNRP continues to deliver Value for Money (VfM) across all five dimensions, despite operating in an unpredictable, deteriorating funding and security environment. While assessing and engaging partners and programs in detailed VfM conversations throughout partnership lifecycle, the programme has additionally, and successfully, adapted to shifting donor dynamics, rising unmet needs, and policy constraints by prioritising resources on lifesaving services, leveraging long-term partnerships, and deploying cost-effective innovations.

Economy: Economy: The programme demonstrated strong financial stewardship and cost-effective delivery. Partners procured bulk items through competitive bidding, achieving up to 17% savings via pooled sourcing of LPG, SRH kits, and pressure cookers. FCDO assessed partners’ commercial processes through Due Diligence and independent audits. Partner continuity and grants to large multilaterals and expert NGO consortia enhanced economies of scale, keeping transaction and overhead costs low. WFP sourced most food locally from Cox’s Bazar host communities. For every dollar spent, 81 cents reached Rohingyas—a 15.7% increase from last year—with the remainder covering operational costs.

Efficiency: WFP’s use of digital platforms like SCOPE and Building Blocks reduced staffing needs and manual errors, enabling real-time, targeted distributions based on the joint GoB-UNHCR refugee dataset. The ISCG-led rationalisation exercise continued to streamline service delivery by reducing partner overlaps in camps. Global ODA reductions have pushed organisations to find efficiencies through restructuring, localisation, partnerships, and in some cases, closures and handovers. Despite these constraints, delivery ratios remained high, with all major output targets met or exceeded—including LPG refills, shelter upgrades, and GBV/SRH services. Cost-effective pilots, such as lime-stabilised shelters and pressure cookers (saving 11% in LPG), improved resilience, reduced costs, and lowered environmental impact. The UK also led efforts to harmonise referral protocols and SEA risk assessments, reducing duplication and improving service integration, though there is scope for further progress on this.

Effectiveness: The programme delivered measurable impact: maternal mortality dropped by 28%, over 529,000 health consultations were conducted, and 37,742 women and girls accessed GBV/SRH services. UK support helped restore food rations and stabilise nutrition pipelines, with WFP’s e-voucher system and 2024 ration restoration improving food choice, dietary diversity, and dignity—reflected in a rise in acceptable Food Consumption Scores from 30% to 65%. IOM introduced more climate- and fire-resistant shelters, sourcing materials locally and creating jobs. The PSEA Network also established a SEAH Investigation Task Team, which contributed to the draft Sexual Harassment Prevention and Protection Act 2024, reinforcing national accountability systems and aligning with donor priorities on gender equality and safeguarding. SFB's post-disaster response has contributed to reducing the response time for natural disasters from ten days to six, enabling quicker assistance to those affected.

Equity: UK-funded services prioritised the most vulnerable—including women, girls, boys, persons with disabilities (PWDs), older people, gender-diverse groups, and host communities. Increased investment in the protection consortium ensured no one was left behind. Geographic targeting remained proportionate, with 99% of funding directed to Cox’s Bazar and 0.95% to Bhasan Char. UNFPA reached 225 PWDs with GBV and PSEA awareness messages, while 1,566 PWDs accessed services such as skills training, MHPSS, and inclusion sessions. The UK also co-led donor coordination on protection and self-reliance and re-engaged the Interim Government of Bangladesh on policy reforms to expand access and inclusion.

Environment: The programme promoted climate-smart delivery through lime-stabilised shelters (reducing fire and landslide risks), slope stabilisation, and a solar-powered surface water treatment plant. Pressure cookers cut LPG use by 11%, while scaled-up fecal sludge management reduced environmental degradation. The RAF project maintained 250 hectares of forest plantations across four upazilas and 53 km of roadside plantations in Teknaf, supporting green belt development, erosion control, and carbon sequestration. WFP also promoted climate-smart agriculture, enabling farmers to adopt organic inputs and water-efficient practices, improving soil health, reducing chemical use, and boosting resilience to climate shocks.

Cost-effectiveness: The programme continues to demonstrate VfM overall, although the latest data shows overall impact indicators are mixed, as set out above. Where the intended impact has not been achieved, it is due to factors outside the UK’s control: for example, rising malnutrition was caused by a lagging spike following ration cuts, which were caused by an overall funding shortfall. The UK should continue to maximise the impact of our funding contributions through high-level advocacy and diplomatic engagement.

E: RISK

Overview of risk management

Risk summary. As in previous years, the overall risk level of the RRNRP remains assessed as ‘Major’. Currently, the RRNRP has 16 active risks: 2 classified as ‘Severe’, 6 as ‘Major’, and 8 as ‘Moderate’ (based on residual risk levels). However, the risk level remains within BHC Dhaka’s defined risk appetite. Significant risks persist due to the inherent complexities of operating in refugee and disaster contexts, as well as the high vulnerabilities of affected populations. BHC Dhaka continues to monitor and document these risks through partner reporting, field observations, and ongoing engagement with donors and the Government of Bangladesh. A summary of key risks by category is provided below.

Strategic and contextual:
Reduced donor funding. Global funding cuts have had a profound and destabilising impact on the Rohingya refugee response. This abrupt reduction in support poses a serious risk of deteriorating conditions for the Rohingya population. With no significant progress in promoting self-reliance and a shrinking pool of humanitarian funding, the wellbeing of refugees is increasingly at risk. FCDO’s funding ensured the continuity of CARU for two months and was used to fill other gaps, such as to support health centres that lost funding.

Bhasan Char. A sustainable UN-led operation on Bhasan Char has yet to materialise due to a range of persistent challenges, including refugees’ reported desire to leave the island, high operational costs, and limited livelihood opportunities. The current IG has not reaffirmed its commitment to the Bhasan Char initiative and hence it is unclear how long the response there will continue. Returns to Cox’s Bazar or onwards migration would have significant implications for food security, protection, and migration dynamics within the broader Rohingya response, as well as on space in Cox’s Bazar (which is already highly constrained). Considering these challenges and the need to prioritise funding, the FCDO in Bangladesh will likely cease funding the response on Bhasan Char from FY2026/27 and has informed relevant partners.

Extreme natural disasters: Bangladesh faces a significant risk of a major natural disaster, such as an earthquake, which could result in substantial loss of life, livelihoods, and property. The UK is mitigating this risk by continuing to support the strengthening of disaster response and preparedness systems, while also advocating for enhanced risk reduction measures by the Government.

Insecurity. The safety and security of Rohingya refugees remain a complex and pressing challenge. In particular, there have been reports of increasing calls for recruitment to armed groups in Rakhine and encouragement of self-repatriation, despite our assessment that the conditions for return do not currently exist. As per the Joint Protection Monitoring report 1,767 serious protection incidents and 344 cases of human trafficking of refugees within Bangladesh were recorded during the review period. The UK provided additional funding for protection services which ensured increased access for GBV survivors. The UK will continue to monitor developments closely and engage with the GoB (RRRC), UN, and other donors to advocate for improvements in the security situation and protection environment, with a particular focus on the most vulnerable populations.
[note] https://rohingyaresponse.org/sectors/coxs-bazar/protection/

Further influx. As of March 2025, a total of 1,009,044 Rohingya refugees were registered and residing in Cox’s Bazar and Bhasan Char. MoFA approved the biometric identification of new arrivals who fled renewed conflict and persecution following the resumption of hostilities in Rakhine State in November 2023. Despite Bangladesh’s ongoing closed-border policy, over 150,000 refugees are now being issued family assistance cards to access life-saving support. While this enables the delivery of essential services, the continued influx of new arrivals and the expansion of assistance mechanisms will have significant implications for the overall humanitarian response, including increased pressure on resources, service delivery, and protection systems.

Safeguarding

PSEAH. Due to their extreme dependence on humanitarian aid, the Rohingya refugees are among the world’s most vulnerable populations to Sexual Exploitation, Abuse, and Harassment (SEAH). Rohingya women and girls reported mistrust and fear when seeking services or reporting GBV cases due to the involvement of community leaders in the case management process that breaches confidentiality. This vulnerability is further compounded by limited reporting from multilateral organisations, raising concerns about the effectiveness and transparency of existing reporting mechanisms. Only two cases were reported, investigated by the partners and closed accordingly. FCDO will collaborate with both PSEA Network (in Dhaka and Cox’s Bazar) and follow up on the development as well as implementation of the Joint Action Plan.

Financial and fiduciary As in other humanitarian settings, there remains a risk of financial loss due to fraud, misuse, or aid diversion. To mitigate this, FCDO continues to engage partners through quarterly meetings, ensuring they adhere to the FCDO Aid Diversion Policy. This includes reinforcing the FCDO’s zero-tolerance stance on fraud and corruption, requiring partners to report incidents promptly and maintain fraud registers. During the reporting period, partners reported four fraud incidents. All were investigated, with three confirmed and resulting in full recovery and reimbursement of the misused funds by the respective agencies.

Programme delivery
Last year’s political unrest disrupted START’s flood response in Sylhet, resulting in delays in project implementation by one month, and prevented CARE and UNRCO from undertaking planned work with the government, resulting in an underspend. The experience showed that political unrest may impact humanitarian operations, especially supply chains, which in turn might threaten the timely distribution of aid to beneficiaries. This could also constrain delivery of services for the Rohingya. To mitigate these risks, the UK will closely monitor the situation and coordinate proactive measures with implementing partners.

Recent global aid cuts have disproportionately impacted the most vulnerable groups—particularly women, children, and the elderly who rely heavily on humanitarian assistance. The overall reduction in services has heightened the risks of malnutrition, preventable diseases, GBV, and human trafficking. Moreover, the funding cuts have jeopardised fragile progress toward durable solutions. Dialogue around voluntary repatriation to Myanmar has stalled, and initiatives aimed at improving livelihoods and access to education have been severely disrupted. FCDO should continue to prioritise funding to ensure that it is achieving the maximum impact, filling gaps in the response where possible, while also advocating for policy change on self-reliance.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Performance of Partners: UN agencies (WFP, UNHCR, IOM, UNICEF, UNFPA, UNRCO) and national NGOs (SFB, CARE Bangladesh) have been long-standing partners in delivering UK-funded activities under the RRNRP. Annual allocations were determined based on humanitarian needs, with proposals, log frames, and budgets reviewed by the programme team and approved by the Development Director. In FY2024/25, FCDO continued its support to the INGO Protection Consortium, (NRC, DRC, IRC, HI), maintaining close collaboration with all partners, escalating issues to senior management when necessary.

Programme Governance: The RRNRP programme is overseen by a Senior Responsible Owner at the British High Commission in Dhaka, by a Programme Responsible Owner, Humanitarian Adviser, and Programme Managers. The team held regular meetings with implementing partners to review progress, address challenges, and coordinate solutions. Regular engagement ensured effective coordination and monitoring of activities. The team conducted 15 field visits in the last reporting year to assess progress, identify risks, and gather feedback from beneficiaries on service delivery. They also actively participated in coordination meetings (Strategic Engagement Group, Donor Council, ISCG, Protection Consortium, HAG) contributing to strategic decisions within the broader humanitarian response and delivering the objectives of RRNRP business case.

While the FCDO maintains an open and transparent relationship with its UN partners, opportunities for proactive engagement on fraud and safeguarding case management remain limited, unless a case is escalated to HQ as per the framework arrangement. BHC Dhaka has raised this risk with the relevant leads in HQ.

Financial Management: Partner performance on programme delivery has been satisfactory as evidenced in their A+ score during this review. As of March 2025, £131,355,450.32 (65.68% of £200 million budget) has been dispersed, including £43.35 million in FY 2024–2025 alone. The expenditure trend is steadily increasing and remains on track within the project timeline and approved budget. The original FY 2024-2025 budget of £21 million was supplemented by an additional £22.35 million – £8 million from RAF, £8.25 million from underspending across the Post, and £6.1 million from HQ underspend – bringing total expenditure to £43.35 million.

Two partners (UNRCO, CARE) under the national disaster component, reported a combined underspend of £228,000 in Q4, which was repurposed into the Rohingya Response programme. The underspend was primarily due to the political turmoil of 2024 which prevented them from implementing some activities jointly with the Government.

Throughout the year, partners consistently provided realistic financial forecasts and timely expenditure reports aligned with the delivery plan. Variances remained within FCDO’s acceptable range (3-5%), thanks to strong financial management by partners and effective FCDO monitoring. The FCDO programme team demonstrated agility in disbursing in-year top-ups at pace, and partners have shown their ability to rapidly deliver services and absorb additional funding where available. This has been critical for enabling the UK to fill urgent gaps in the response when they have arisen, such as the water shortage in Teknaf.

RRNRP successfully delivered planned activities, with partners demonstrating strong programme, commercial, and financial performance. Regular reporting kept the FCDO Humanitarian Team well-informed on programme delivery, expenditure, and any emerging risks. Financial reports and fund requests were scrutinised, enabling timely identification and reprogramming of underspend. Most financial returns were submitted on time and were of good quality.

Due Diligence and Asset Management: FCDO conducted a due diligence assessment (DDA) for all partners at the beginning of the RRNRP programme, confirming that each had robust policies and systems in place to manage and mitigate risks. In the reporting year refresh of the DDAs for UNFPA, Start Fund and UNICEF were initiated.

During the reporting period, NRC and START fund undertook procurements with prior FCDO consultation and approval In April 2025, FCDO conducted a spot check of START fund’s procurement procedures, including a review of randomly selected procurements and asset inventory verification. The review report confirmed that START fund followed rigorous processes, ensuring VfM and compliance with policies. NRC submitted an updated asset resister, which was reviewed by the FCDO Programme Officer, confirming assets were used as intended.

Audits: As per framework arrangements, UN partners are not required to conduct external audits. Instead they provide certified annual financial statements to FCDO. The statements confirm that each partner has systems in place to manage their own and downstream partners’ financial transactions in accordance with FCDO financial rules. UN partners have internal control mechanisms to review downstream partner expenditure. The final audit reports for FY 2024-25 are expected by mid-September 2025 from all partners (including NRC Consortium and Start Fund Network).

G: MONITORING, EVIDENCE AND LEARNING

Monitoring

BHC Dhaka monitors the RRNRP through multiple mechanisms including quarterly narrative reports, consortium briefings, regular field visits, and consultations with partners and beneficiaries. These mechanisms assess performance, manage risks, and address implementation challenges. The newly appointed humanitarian adviser also contributed valuable insights to the review, bringing a fresh perspective to the team’s analysis.

Refugee feedback is routinely collected through focus group discussions and digital platforms, (ie. Zite Manager of IOM) and synthesised by the ISCG’s Communicating with Communities Working Group. FCDO cross-references this feedback through conversations with beneficiaries during regular field visits which have been key in identifying practical challenges on the ground. Implementing partners also have their own monitoring mechanisms. Internal audits of all UN programmes are conducted periodically by the UN Office of Internal Oversight Services and the United Nations Board of Auditors, while some partners also undergo annual audits by commercial auditing firms. The Protection Sector’s Joint Protection Monitoring Framework enables systematic collection and analysis of protection incidents and risks in the camps and protection actors regularly brief donors on these findings. The 2024 Inter-Sector Needs Assessment informed the JRP for 2025-2026, with NAWG contributing data and analysis to the UNRCO-led Humanitarian Response Plan (HRP) and 5W monitoring matrix to prevent duplication and overlap in the response.
[note] https://rohingyaresponse.org/wp-content/uploads/2025/04/BGD_CXB_ISNA-2024_Full_Report_Camps_Feb-2024.pdf

With FCDO support, CARU published seven weekly reports reaching 376 stakeholders, and delivered five targeted briefings to key UN, diplomatic, and humanitarian actors. Additionally, three data-driven presentations were shared at ISCG Border and Security Meetings, and two analytical reports were produced within a short timeframe. These outputs were instrumental in monitoring the evolving situation in the camps and informing UK policy.

Evidence

In the review period, the UK has continued to fund evidence generation, which has shaped both FCDO policy and programming and the wider response:

Gender-based violence and insecurity – research on GBV and insecurity in the camps, supported by central FCDO funding and published in XJan’25 highlighted the urgent need for comprehensive interventions that address the underlying causes of insecurity, including cross-border dynamics. This research was disseminated through a launch event in Dhaka with the Government of Bangladesh.

Inter-Agency Risk Assessment – The first Inter-Agency Risk Assessment on SEA in Bangladesh, funded by the UK under the RRNRP programme, assessed the status of PSEA, contributing factors, and potential solutions. The assessment confirmed high levels of risk and exposure to SEA in both humanitarian and development contexts. In response, the PSEA Network will develop a three-year strategy to address the identified risks and implement recommended mitigation measures. This report is intended to be a living document, which will be updated as new data emerges and as progress is made.

e-Cooking Potential - FCDO funded research under the centrally-managed Modern Energy Cooking Services (MECS) programme (MECS) to assess Rohingya and host community user experience, using standalone solar-powered appliances (i.e. electric pressure cookers, induction and infrared stoves). Preliminary findings indicate that e-Cooking could compliment LPG use in both refugee camps and host communities. However, implementation faces operational and financial barriers, including frequent flooding, fire outbreaks in camps, shading of solar panels, dust related maintenance issues, security concerns, and the high cost of solar e-cooking systems. A pilot is being planned to further test feasibility.
Learning

There is scope for closer collaboration with and oversight of centrally managed FCDO programming and multilaterals, such as Education Cannot Wait and the World Bank. The FCDO programme team will conduct monitoring visits of these funds to ensure that they are delivering on objectives and coordinating effectively with wider response efforts, including the UK’s bilateral funding.

Date of last narrative financial report	Partners submitted financial reports (quarterly and annually) as per the agreed AGs, CAs and MoUs.	Date of last audited annual statement	External Audit Report. IOM and CARE’s report are due by December 2025. / Certified Financial Report from other UN partners are expected by September 2025. Previous years’ financial reports are reviewed before new funding is dispersed. / BHC Dhaka conducted a ‘financial spot check’ of NRC Consortium in September 2024 and took actions according to the findings. The consortium is currently conducting an external audit which is due by September 2025.