Land Facility Annual Review - September 2024
Title: Global Land Governance (GLG) programme
Programme Value £ (full life): £105 million		Review date: September 2025
Programme Code: 300555	AMP start date: / 19 December 2019	AMP end date: / 31 December 2030

Summary of Programme Performance
Year	2020	2021	2022	2023	2024	2025
Overall Output Score	A	A	A	A	A	A+
Risk Rating	Major	Major	Major	Major	Major	Minor

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/58850441.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/58855752.xlsx

A. SUMMARY AND OVERVIEW
Description of programme
Effective land governance systems are key to addressing many development priorities, including food security and resilience, sustainable land-use, inclusive economic growth and responsible investment. Land disputes are a key driver of conflict, and pressure on land will continue to rise due to competing demand from growing populations, urbanisation, and clean energy. Land governance systems in many fragile and conflict affected states (FCAS) and developing countries are weak, with large amounts of unregistered land and disputed ownership rights. Where communities have secure tenure, this contributes to resilience from climate and economic shocks, and supports rural livelihoods and women’s empowerment
Despite the strong case for systematic land reform in many low-middle income countries progress has historically been slow due to weak capacity and political incentives. However, there is significant demand for support from partner countries and UK Posts as weak land governance hampers many development priorities. In response, FCDO’s Global Land Governance Programme (GLGP) works with HMG Posts, partner governments and communities to develop robust land governance systems that provide the foundation for climate resilience, food security, economic growth and stability. To date the programme has included three complementary components (see Figure 1):
Figure 1 - Structure of GLGP projects
[note] Some examples of positive progress include Rwanda’s National Land Tenure Reform Programme and the groundbreaking Customary Land Rights and National Land Commission Acts 2022 in Sierra Leone: Sierra Leone passes globally unprecedented legislation related to climate and environment, Namati, August 2022: https://namati.org/news-stories/sierra-leone-passes-globally-unprecedented-legislation-on-climate-environment/
1. The Land Facility (LF) – driving systemic land and forest governance reforms through partnerships with governments. This will strengthen the recognition, documentation and protection of all legitimate tenure rights through more effective, fair, and transparent land administration systems.
2. Strengthening Community Tenure Rights – advancing tenure security for local communities: channelling direct support for vulnerable communities at the frontline of climate mitigation and adaptation, to protect their land rights, homes and livelihoods.
3. Advancing Land-based Investment Governance (ALIGN) – enabling responsible land-based investment (RBLI): this project works with governments and communities to develop fair and transparent land investment approval processes in core sectors including energy, extractives and agriculture.
Summary supporting narrative for the overall score in this review
This annual review (AR) provides an update on GLGP progress from 1st April 2024 to 31st March 2025 (FY2024/2025). The AR covers the fifth year of the ALIGN project, the second year of implementation of forest tenure projects, and the inception phase and first quarter of implementation of the Land Facility including its Decision Support Unit (DSU) (these contracts started in April 2024). In the context of decision to reduce ODA, this year has also been an important year of transition, wrapping up 3 components and refocusing the Land Facility on delivery of UK nature, resilience/conflict prevention and growth objectives, taking care to ensure a break/end point at end 25/26 if needed following SR decisions.
[note] It is important to note that outcomes and output results for the Tenure Facility represent results across 2024 calendar year rather than the 2024/25 financial year. They also represent Tenure Facility’s results as a whole organisation which FCDO contributes towards. Results for specific FCDO-funded projects are also provided in the narrative.
For the previous AR, GLGP used a revised Logframe which included updated Outcome/Outputs indicators for ALIGN, Outcomes and Outputs for the new forest tenure projects, and updated Output indicators for the Land Facility’s procurement phase. The Programme Logframe has been updated to include revised LF indicators as agreed with the delivery partners as part of the Inception Phase.
The GLGP has scored an A+ for this AR, reflecting strong delivery and achievements across all active projects; A++ for ALIGN and A+ for the two community tenure components (see Focus Box 1 for highlights). Although the Land Facility outputs have a 50% weighting, 3 out of 4 indicators are binary (reflecting how progress was measured in the inception period), which has limited the score to an A, which was achieved. This leads on an overall A+ score for the whole programme.
Focus Box 1: Global Land Governance Programme Highlights over this AR
1. Systemic land governance reform (Land Facility): The Land Facility launched in 2024 with significant interest and demand from HMG Post and governments confirmed during the inception phase. The LF began two instances of technical support (Congo Basin and Zimbabwe), and scoping for four country projects in collaboration with HMG Posts and partner Governments (Brazil, Ethiopia, Indonesia and Zambia). Projects support a wide set of UK development objectives including sustainable green growth, the energy transition and climate resilience, and addressing drivers of natural resource-based conflict and instability.
2. Responsible Land Based Investment (ALIGN): During its fifth year ALIGN made tangible progress in shaping laws, policies and practices which govern land-based investments – from community-level negotiations to national legislative reform. Across its focus countries (Zambia, Sierra Leone and Indonesia) it is supporting green, sustainable and inclusive growth across mining, criterial minerals, carbon and agriculture sectors. ALIGN contributed to the development and reform of carbon strategies, policies and laws, helped strengthen safeguards in carbon and mining projects, and supported lower-carbon investment pathways, such as energy transition minerals. ALIGN has also delivered responsive technical support and knowledge sharing across 23 countries. A notable highlight is ALIGN’s contribution to the intersection of land governance and international climate finance priorities.
3. Community rights (Tenure Facility): The Tenure Facility made rapid progress in its second year of project implementation over 2024. It has supported the formal recognition of indigenous and community land and forest rights across more than 4.6 million hectares – more than double recognised in 2023. This includes the recognition of over 2.5 million hectares which was directly supported by FCDO-funded projects. These projects led to direct benefits for more than 2,100 communities. In addition to many examples of how community-led efforts and trusted partnerships have led to legal recognition of indigenous territories, projects have also led to policy shifts which strengthen environmental governance. For example, building on the momentum of COP16, the Colombian government issue a national decree recognising indigenous authorities as official environmental regulators, enabling them to manage and protect biodiversity based on their knowledge systems.
4. Community rights (Cadasta): In this second full year of the project, Cadasta made significant progress to support the mapping of over 4.5 million hectares of forested land by communities and the demarcation of over 300,000 hectares of community land parcels for formal recognition by authorities. In this period Cadasta have also focused on building technical capacity across partners for data collection and analysis to enable to sustainable land governance.
Major lessons and recommendations for the year ahead:
1. Recommendation: adapt programme scope and focus to reflect new SR priorities and opportunities, ODA funding constraints (with the shift to 0.3 of ODA), and future geographic prioritisation. The new SR period will involve significant shifts in the ODA operating model alongside reduced and more prioritised ODA spending in a prioritised set of countries. The current scope of the programme will need to change to reflect these priorities – not yet confirmed by the point of this review. the programme has so far positioned to hold a narrower focus on strategic interventions that drive system change alongside the ability to respond to demand from posts and partner countries, with a greater focus on conflict prevention and resilience building in FCAS, alongside work to promote sustainable land-use and inclusive growth. Once the SR parameters are clear the programme team will need to work at pace with delivery partners to review and agree how the scope of work will need to be adjusted, what work will need to stop, and work through implications for budgets, results and workplans.
2. Recommendation: Review and update the GLGP Logframe and Theory of Change as Land Facility enters full implementation, other projects approach completion and to reflect SR shifts: The first year of Land Facility was focused on a 9-month inception phase (May 2024 – January 2025), and two months of implementation, with current outcomes and outputs for Land Facility reflecting that. The GLGP Logframe will need to be updated to reflect Land Facility outcomes for the implementation phase as well as the implications of the SR for programme scope and scale.
3. Recommendation: Work with an FCDO economist to review, agree and finalise the VfM indicators that the Land Facility developed in inception phase: As part of the inception phase, the Land Facility submitted VfM indicators to assess progress against. The GLGP programme team should draw on internal support to test that the VfM indicators are able to effectively capture VfM assessment, as the Land Facility enters its first full year of implementation.
Updates on recommendations from 2023 AR:
Recommendation	Update
Maximise opportunities for the GLGP to support wider thematic priorities; including our work in FCAS and contribution to resilience and food security.	During this AR period the team have continued to assess how GLGP engages across a broader range of thematic areas. We worked with Land Facility partners and HMG Posts to identify opportunities in FCAS contexts. Projects were started in Ethiopia, Zimbabwe and the Congo Basin, and outside of this review period we have now started scoping potential projects in Chad and Nigeria. Across projects, GLGP is directly supporting priorities around climate resilience, forests & biodiversity, green growth and investment.
Systemise processes for Land Facility engagement with HMG Posts and Centrally Managed Programmes	During this AR period we have developed clear and accessible information on the Land Facility for outreach with internal and external audiences and conducted outreach to HMG Posts and CMPs, based on initial country prioritisation. To date we have confirmed demand from 17 of the 20 Posts we have engaged with and have established strong relationships with country teams with positive feedback on the Land Facility approach and offer. We also hired a dedicated Land Facility Country Coordinator position who will play a key role in future standardisation and facilitation of engagement with Posts.
Update the GLGP Logframe to reflect new Land Facility outcomes and outputs	We updated the GLGP Logframe to include agreed outcomes and outputs for the active projects during this AR period. Over the 25/26FY we will review the Logframe again to adapt to the Land Facility’s transition into implementation, and changes needed from Spending Review outcomes and closure of projects (depending on timings and as appropriate).
Prioritise GLGP monitoring visits	The GLG PM team have conducted three country visits during the reporting period: Ethiopia (for LF scoping), and Brazil and Indonesia as part of Land Facility scoping visits and project monitoring for Tenure Facility. These allowed for FCDO representation at key introductory meetings with partner governments, alongside Post, establishing strong engagement with the projects and LF delivery partners. The visits to Tenure Facility projects were the first time we were able to see how these were delivered on the ground and gave better understanding of monitoring and safeguarding.

B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
GLGP’s Theory of Change (See Figure 2) identifies a wide range of land governance problems and how these impact on stability, livelihoods and sustainable investment and nature. It then sets out the three interconnected intervention areas of the programme, centred on (a) support for national land system reform, including work on political space, capacity and coordination (‘top-down’); (b) interventions that enable communities to strengthen their tenure rights (‘bottom-up’); and (c) efforts to connect these two to improve the quality of system reforms and the reach of community interventions. These interventions then contribute to the main GLGP outcomes, including a dotted line to how the programme intends to support scale-up through close coordination with the WB IDA portfolio and other financial institutions.
The diagram includes the causal chains that connect the programme outcomes with a wide range of impacts, where GLGP outcomes are necessary but often, alone, not sufficient to deliver the desired long-term impact. Equal recognition and protection of men and women’s land and home ownership rights, as well as of all other legitimate rights holder provides the foundation for a wide range of impact. For example, it secures one of, if not the, main asset the rural and urban poor depend on for their security, shelter, food security and livelihood, as well as the foundation and safety net that enables the poor, and especially women, to diversify into alternative and higher-return economic activities. Secure tenure incentivises long-term investment in higher productivity agricultural practices that also protect nature and increase carbon sequestration. Lastly, clarifying land tenure rights and resolving disputes over land play a vital role in decreasing the triggers for local and wider conflict.
Describe where the programme is on/off track to contribute to the expected outcomes. What action is planned in the year ahead?
Figure 2 - Theory of Change
The late start of the Land Facility component has set back progress against some of the main programme outcomes, but the time extension to 2030 (approved in 2023) provides a realistic timeframe to deliver these by the end of the programme. The active GLGP projects are broadly on track to contribute towards the programme Outcomes. The revised GLGP Logframe now has five outcomes, to better reflect the range of programme delivery areas across the five projects and wider programme ambitions.
The UK will reduce its aid spending to 0.3% of gross national income by 2027/28. As the UK transitions to this, and new programmatic budgets are confirmed during the 2026-2028 Spending Review (SR), we will review and adapt the GLGP in the next year of implementation (FY25/26) onwards.

Figure 3 illustrates the primary strategic entry points of each GLGP project, and how these complement each other to achieve the wider impact of the programme (see Section B Theory of Change). The Land Facility focus is at national level, developing land governance systems and structures which create the framework for sustained progress on community land rights; in parallel, support for these local communities empowers action at grassroots level to feed into these national processes and achieve greater tenure security. Work on Responsible Land Investment works across government, regional and local stakeholders and processes, and also involves private sector actors.

Support for local communities
National policy and administration reform

Figure 3 - GLGP Strategic Entry Points
Community Land Rights
Land Facility
Responsible Land Investment
Support for local communities

GLGP’s three accountable grant agreements (ALIGN, Cadasta, Tenure Facility) will enter their final year of implementation in 25/26, and programme activities will focus on ensuring these projects are ended in a sustainable manner. If protected in the SR, the Land Facility will enter its full first year of implementation, with some initial country support projects expected to be delivered across a range of thematic issues and countries. Note that all these initial CSPs will run up until March 2026 with scope to end or expand into the next SR depending on SR prioritisation.
Outcome 1 (Land Facility): Programme interventions and outputs contribute to systemic and sustainable improvements in central land administration systems and more efficient, inclusive and fair land (rural or urban) tenure governance practices:
Not applicable as Land Facility was in Inception Phase for the majority of this annual review period. However, Inception Phase deliverables have been designed to ensure that projects will contribute to systems-level change.
Outcome 2 (Land Facility): Programme interventions and outputs help establish the building blocks and a clear pathway to sustained land reform implementation;
Not applicable as Land Facility was in Inception Phase for the majority of this annual review period. However, Inception Phase deliverables have been designed to ensure that projects are contributing to systemic and sustained land reform.
Outcome 3 (ALIGN): Improved country-level RLBI governance systems and effective stakeholder RBLI practices: On-track:
    1. Number of improvements to national policies, practices and decision-making processes concerning land investment approval and governance processes: The final project Outcome target seeks to make 35 improvements to national policies, practices and decision-making processes, and ALIGN has achieved 22 instances of (11 new improvements in this AR period).
    2. Number of cases in which land-based investment outcomes are improved for communities: ALIGN has made significant progress under this outcome, with a total of 98 (48 new, against total target of 111) of positive outcomes for communities now achieved, continuing progress in Sierra Leone, Zambia and Indonesia (new for this reporting period).
This reporting year ALIGN has contributed to the development and reform of carbon strategies, policies, and laws; helped strengthen safeguards in carbon and mining projects; and supported lower-carbon investment pathways, such as energy transition minerals. These shifts reflect ALIGN’s growing contribution to the intersection of land governance and international climate finance priorities, shaping laws, policies and practices governing land-based investments, from community-level negotiations to national legislative reform.
For example: in Zambia, ALIGN contributed to several major policy processes, including reviews of the Lands Act, Forest Act, and the Minerals Regulations Commission Bill. ALIGN successfully advocated for a new legal requirement for carbon projects to include community development in the recently adopted Green Economy and Climate Change Act, and for benefit-sharing agreements with affected communities; in Sierra Leone, ALIGN played a central role in national consultations on three draft laws related to land governance and on the National Carbon Strategy. Government officials were supported to ensure successful and sustainable implementation of new laws, demonstrating ALIGN’s approach from development to implementation and delivery of reform processes.
Outcome 4 (Forest Tenure): Strengthened community tenure security, including for women, from increased legal recognition and strengthened government practices: On-track:
1. Number of communities/people (men and women) with increased tenure security through formal recognition by government of tenure rights: In this second year of implementation, overall results for this indicator are lower than expected, with just over 2,665 communities (1,622 new) receiving formal recognition of land rights through support from Tenure Facility (cumulative target was 2,800).
2. Hectares of land area with formal government recognition/protection of community tenure rights: Partners are making strong progress on this target, with over 6.5 million ha of land area with formal government recognition secured these community tenure rights protected, more than double this year’s target of 3.2m ha and already exceeding the overall target of 6.2m ha.
3. Number projects contributing to changes in policies, laws and regulations that advance land rights: Partners have significantly exceeded this target, with 21 (11 new) projects contributing to changes at legal and reform level this reporting period against a target of 7 this reporting period.
Strong progress has been made by partners across this Outcome, with notable increases in legal recognition and protection of community tenure rights across country projects. For example, in Kenya, partners made progress in strengthening rights and governance over 4 million hectares in 2024 —approximately 7% of the national land area— representing a major shift in land recognition for pastoralist, forest-dwelling, and agricultural communities. Notably, an increase was achieved in female representation in local governance structures, with an increase in gender and social inclusion strategies adopted by community organisations. Increasing influence is being demonstrated at systems level on national reforms; for example, in Indonesia, partners developed a formal agreement between key ministries and civil society to accelerate agrarian reform, and local partnerships also advanced land redistribution and new land-use regulations in three provinces.
Outcome 5 (all projects): GLGP activities and outputs support the UK's global policy work on land tenure governance, catalysing action and replication by other stakeholders On-track:
          1. Number of examples of GLGP either supporting UK input into and influence in global policy or of GLGP influencing action and/or replication of activities by third parties related to good land governance. During this AR period, we delivered 2 significant global policy and influencing contributions.
- The UK sponsored the highly successful relaunch of the World Bank Land Conference in May 2024, which had not been held in person since Covid-19. This is an important platform, bringing together key stakeholders in the land sector and beyond: the conference convened one thousand government, civil society, and land stakeholders in person, including 34 Ministers, and brought visibility to the UK’s leadership on the global land rights agenda. The event opened with a message from the Minister of Development, who confirmed UK support for this agenda and announced the launch of GLG’s Land Facility.
  [note] https://www.worldbank.org/en/events/2023/10/05/land-conference-2024
  [note] Announcement of Land Facility by UK Minister of Development: https://www.linkedin.com/posts/international-development-services_landrights-landreform-activity-7196897295097806848-fv1G/G
- At COP29 in November, the UK Foreign Secretary David Lammy hosted an event and gave an opening speech on the role of Indigenous Peoples and local communities in protecting forests, and the importance of tenure security. This brought together tropical forest country (Brazil, Colombia) and funder governments (UK, Norway), philanthropy (Bezos Earth Fund) and Indigenous leadership to emphasise the importance of collaborations and partnerships to advance tenure rights and identified initiatives such as the renewed Land and Forest Tenure Pledge to be launched at COP30.
  [note] Indigenous Peoples and protecting forests: Foreign Secretary's speech at COP29 - GOV.UK
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio:
GLGP is the only HMG central programme dedicated to advancing systemic changes to land governance reform. The unique Land Facility model, which provides in-depth and country-specific technical assistance, based on political economy analysis, was welcomed by HMG Posts. The highly flexible and adaptive nature of the programme was a key draw, responding to a range of thematic opportunities. The co-creation process with both HMG Post and country stakeholders – in particular shaped by government partnership – has been very positively received with high engagement from Posts. More than 20 HMG Posts have demonstrated demand for the LF Offer (see Box 1). The Land Facility offers specific and strategic technical expertise and assistance, and harnesses the UK’s own land expertise, for example through partnerships with HM Land Registry and Ordinance Survey. It prioritises collaboration and partnerships with organisations and governments at the local, national and global level, as well as leveraging investment from other bilateral and multilateral donors for scalable impact. It is demand-led, responding to the needs and priorities of local communities, partner governments and FCDO posts.
The GLG programme has consistently delivered strong programme performance since the start (scores of A and this year A+, with strong progress against targets, despite challenging delivery contexts such as COVID19 and ongoing FCDO budget uncertainties causing delays to delivery.
The strategic case for investment in land tenure security remains vital, with growing pressure on land due to conflict, sustainable economic growth, climate change, and the vital role access to land and secure tenure plays in safeguarding food security and livelihoods. From conversations with multiple HMG Posts, they have repeatedly identified effective land governance and secure land tenure as a critical foundation for UK development priorities, which are central to GLGP programme focus areas including green growth and investment, climate change resilience, and reducing the drivers of conflict.
The UK is in a strong position to deliver wider systemic change in this space, building on the UK’s global leadership on land governance over the last two decades, including flagship reforms supported by the UK in Ethiopia and Rwanda), and its position as a trusted global partner with experience and technical expertise. GLGP’s work is a foundation to other sectors and thematic areas of the UK’s ODA portfolio, including green climate resilient growth and derisking investment.
There is therefore a strong case for key elements of the programme to continue based on its own delivery record and potential, as well as its strategic role in the wider FCDO portfolio, both underpinning delivery on global priorities (including inclusive growth, climate mitigation and nature protection, conflict prevention and resilience) and responding to strong demand from posts and partner countries. This is being fed into SR considerations.
C. DETAILED OUTPUT SCORING
Logframe targets and results reporting is cumulative, bringing together previous and this AR results to show overall progress, with ‘new’ targets and results specific to this AR period in brackets. Tenure Facility results follow calendar year to align with Tenure Facility’s reporting.
[note] For example, a result of ‘50 (10) projects’ indicates a cumulative total of 50 projects achieved over the course of the programme lifetime, with 10 new projects achieved this reporting year.

Outputs 1 & 2 (Land Facility)	Land Facility Procurement and Inception Phase / 1: LF & DSU procurement process completed / 2: Inception Phase implemented according to agreed plans, with all key deliverables completed and demand from posts re-established
Output number:		1-2	Output Score:	A: met expectation
Impact weighting (%):		50	Weighting revised since last AR?	No

Indicators	Milestone(s) for this review	Progress
LF & DSU procurement process completed:		Score A Met expectations
1.1 LF and DSU procurement completed, contracts signed, and inception phase started by early 24/25		Score A – The procurement process was concluded in April 2024 when the contracts were signed for both Land Facility Lead Supplier (Lot 1) and the Decision Support Unit (Lot 2). The inception phase began in May 2025
2. Inception Phase implemented according to agreed plans, with all key deliverables completed and demand from posts re-established		Score A+ Moderately exceeded expectations
2.1 Inception Phase KPIs completed by Lead Supplier and DSU	Q1 and Q2 KPIs/milestones delivered by suppliers	Score A – Successful submission of all inception phase deliverables from both Land Facility Lead Supplier and Decision Support Unit.
2.2 Interest and demand from posts confirmed with emerging pipeline of light and/or deep projects.	Confirmed interest for LF support from 10+ HMG posts	Score A+ – demand from 17 of the 20 Posts engaged, during inception phase, including introductory conversations, expressed interest in support and potential opportunities. 2 projects began implementation, 4 projects began scoping, and a pipeline of potential projects.

Briefly describe the output’s activities and provide supporting narrative for the score.
 The LF tender was launched in July 2023 and was concluded in April 2024 when the contracts were signed. We have therefore still scored Output 1, as the procurement phase did not officially conclude until April 2024. We have also scored Output 2, as the inception phase was conducted and completed during this reporting period. We have scored an A for both the procurement and contracting process, and the inception phase as both were carried forward as smoothly as possible.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
No changes to the output in the past year, as procurement process and inception phase were ongoing throughout the reporting period.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.
The LF Inception Phase required over 30 deliverables from each delivery partner over the course of nine months. The deliverables produced ranged from operational ways of working, technical notes, and two country scoping reports. These were delivered to high standard, and critical for establishing the project foundations, teams, and ways of working. Going forward, the Inception Phase documents will continue to be adapted and refined during implementation.

Focus Box 3: Land Facility Implementation
Following a successful Inception Phase, the Land Facility (LF) started Implementation Phase in February 2025.At the time of writing, LF has received interest from more than 20 HMG Posts across Sub-Saharan Africa, South-East Asia and Latin America as part of the HMG GIG CoE offer, with projects underway or completed (scoping, design or delivery phases) in 8 FCDO priority countries, including FCAS countries (Fragile and Conflict Affected Situations). Brazil, Zambia, Indonesia and Ethiopia have been selected as initial focus regions, working in partnership with governments to further land governance reform as a fundamental foundation of priority development objectives around inclusive green growth, climate resilience, and conflict resolution.
The flexibility and adaptability of the programme design and activities is critical in responding to HMG’s priorities and the evolving contexts of focus countries. It is working closely with HMG Posts to identify strategic projects to address land-related barriers in delivering priorities for Posts and partner governments:
- In Eastern Chad, LF is providing technical support to HMG Post’s delivery partners on land and resource governance issues and options as part of humanitarian assistance, conflict resolution, and increasing resilience with pathways to sustainable livelihoods - particularly where this can exacerbate food insecurity and support restoring ecosystems management;
- In Zambia, the LF will be looking to catalyse multistakeholder partnerships for coordinated action, learning and evidence-based engagement to gain buy-in for national land governance reforms that support inclusive, land-based economic growth;
- In Ethiopia, LF, the government and other stakeholders will collaborate to identify pathways to sustain results from its success with large scale certification of land rights in rural areas, to expand access to related services and to catalyse increased coordination, particularly across rural and urban spaces, linked with inclusive growth and sustainable agriculture.
- In Brazil, LF is engaging partners, including GIZ, the WB, the Amazon Fund among others, in support of the government’s efforts to accelerate progress on critical land administration systems needs that constrain equitable and green growth such as designation of public lands and forests;
- In the Congo Basin Region, LF produced a political economy analysis of land tenure and resource governance to support a new HMG Forest Programme, along with syntheses of best practices community forest management and of innovations in climate finance linked with tenure security;
- In Indonesia, LF aims to support land governance progress linked to food and energy security and social forestry in support of wider government’s growth ambitions and climate commitments whilst protecting community land rights;
The LF also works to identify unique and time-sensitive opportunities to build country and regional-level support for driving the global agenda on accelerating robust land governance systems, and achieving meaningful commitments from governments on this agenda, such as through facilitation of peer-to-peer government workshops at COP30 in November 2025.
With support from the LF Decision Support Unit, the Land Facility will continue to centre political economy analysis at the heart of its work to ensure activities are designed and delivered effectively. This will be complemented by a culture of learning across the team. Technical assistance will be shaped according to the needs of partner governments, and will benefit from the UK’s own land expertise, such as in geospatial mapping with Ordnance Survey.
Output 3 (Responsible Land-Based Investment)	Strengthened demand and implementation capacity to address Responsible Land-Based Investment challenges in government agencies, civil society and wider stakeholders
Output number:		3	Output Score:		A++ Significantly exceeded
Impact weighting (%):		30	Weighting revised since last AR?		Yes
Indicator(s)				Milestone(s) for this review		Progress
3.1 Engagement with governments and civil society to enhance awareness of and support for RLBI, building pressure for reform of policies and practices:						Score A++ Significantly exceeded / Progress against this output has met expectations against the planned results.
3.1.1 Number of deepened or sustained relationships with key national actors for improved RLBI policies and practices				Target: 50 (29 new) / 8: Sierra Leone (2 new) / 17: Zambia (2 new) / 25: Indonesia (25 new		Score A++ / Total 136 (115 new) / 7 - Sierra Leone (1 new) / 43 - Zambia (28 new) / 86 - Indonesia (86 new)
3.1.2 Number of meetings that bring together representatives from government, civil society, affected communities and/or other relevant actors and seek to contribute to improve national RLBI systems and practices				Target: 93 (29 new) / 20 Sierra Leone (2 new) / 46 Zambia (12 new) / 27 Indonesia (15 new)		Score A++ / Total - 184 (120 new) 30 - Sierra Leone (12 new) / 68 - Zambia (34 new) / 86 - Indonesia (74)
3.2 Direct support to communities (%M/F):						Score A++ Significantly exceeded
3.2.1 Number of interventions supporting communities / affected by potential or actual investments in investment hotspots				Target: 59 (10 new) / 36: Sierra Leone (2 new) / 18: Zambia (3 new) / 5: Indonesia (5 new)		Score A++ / Total 184 (135 new) / 39: Sierra Leone (5 new) / 28: Zambia (13 new) / 117 Indonesia (117 new)
3.2.2 Number of affected citizens supported through the project to engage in resolving grievances related to RLBI issues in investment hotspots				Target: 10,360 (870 new) / 10,000: Sierra Leone (657 new) / 340: Zambia (193 new) / 20: Indonesia (20 new)		Score A++ / Total - 20,137 (10,647 new) [45% female; 55% male] / 12,684: Sierra Leone (3,341 new) / [45% female; 55% male] / 689: Zambia (542 new) / [45% female; 55% male] / 6,764: Indonesia (6,764 new)
[note] Disaggregated data by gender was not available for FY 24/25 but will be included in FY 25/26.

Briefly describe the output’s activities and provide supporting narrative for the score.
ALIGN partners aim to strengthen the enabling environment for Responsible Land-Based Investment (RBLI) reform, implemented by a consortium of IIED, Namati and CCSI. This Output was met, and for many indicators significantly exceeded, over this reporting year and has therefore scored an A++. ALIGN has both expanded its core in-depth country project work to 3 countries (Sierra Leone, Zambia and Indonesia), while continuing to strengthen demand and implementation capacity to address land investment challenges across government agencies, civil society and wider stakeholders, and has provided direct support to communities on the ground. Part of the GIG COE Offer, ALIGN has also built on the partnership with HMG Post South Africa last year and this year secured buy-in from HMG Post Indonesia.

3.1 Engagement with governments and civil society to enhance awareness of and support for RLBI, building pressure for reform of policies and practices: ALIGN has continued progress on facilitating cross-stakeholder collaboration and active working partnerships on RBLI, guiding these dialogues to achieve progressive change in how RLBI policies are designed and implemented. Highlights include:
- In Indonesia: work continued on building the advocating power of local groups, with buy-in support from HMG Post Indonesia allowing the workplan and geographical scope to be expanded, bringing new partnerships. In Southeast Sulawesi, partners have led strategic policy interventions to shape the governance of the nickel mining and palm oil industries. In North Konawe, a multi-party form was established to facilitate dialogue between local government actors, village governments, communities, and the private sector and provide a pathway for influencing district level policies on land governance.
- In Zambia: further progress was seen on policy reform, with ALIGN helping to shape the Minerals Regulations Commission (MRC) Bill of 2024, engaging Members of Parliament and the Ministry of Mines on the importance of aligning the Bill with the National Green Growth Strategy and the importance of incorporating community development agreements and benefit-sharing mechanisms. Partners convened collaboration platforms for government, CSOs, and the private sector on RBLI, and have established and ongoing coordination platform.
- In Sierra Leone: in partnership with FCDO’s Invest Salone programme, ALIGN led consultations on the forthcoming National Carbon Strategy, facilitating roundtable discussions across all five regions of the country with representatives from forest-edge and coastal communities, carbon project developers, environmental CSOs, government regulators, and local leaders. This will feed into a National Carbon Strategy being developed by Namati and Invest Salone, in partnership with the Ministry of Environment and Climate Change. Namati organised the first intra-government learning workshop on the Customary Land Rights Act (CLRA) 2022, and led discussions during nation-wide consultations on three new draft laws critical to implementing the National Land Policy.
3.2 Direct support to communities: ALIGN’s support for communities directly affected by land related investments has continued to increase, improving capacity for community level action. Results were higher than anticipated with proactive demand and engagement at the community level. Highlights include:
- In Sierra Leone, ALIGN-supported paralegals took forward four new land negotiation cases including mining project and agribusiness projects. In one case, rent is now being paid for 9,754 hectares of land, and investors are paying US$ 20,000 into the development fund for three communities. Increasing requests are being seen for support on carbon investment projects, and paralegal partners facilitated direct negotiation meetings between community representatives and a blue carbon developer in the south of the country to finalise a revenue sharing agreement. There was a significant increase in number of citizens supported this year, with paralegals working on 15 active cases across 10 projects during the reporting period, positively impacting 10,800 people – 51% of whom are women.
- In Zambia, the combined approach of building strong relationships at community, traditional authority, and local government levels enabled in-country partners to facilitate community-led action and advocacy. This strategic engagement at the grassroots amplified the impact of interventions, leading to tangible policy and practice outcomes at both local and national levels. For example, ALIGN partners conducted meetings with chiefs and council members in Central and Northwestern provinces to discuss community investment guidelines. These are under development and will serve as a minimum standard for RLBI in customary areas.
- In Indonesia, buy-in from HMG Post enabled partners to expand activities and respond rapidly to changing community needs and contexts. ALIGN supported civil society coalitions to establish community-led grievance posts, organising the first province-wide public consultation on the rights of Adat communities, and documenting rights violations across the oil palm, mining, and forestry sectors. Both coalitions are building strategic and financial plans to sustain their work beyond ALIGN. ALIGN supported activities have been supporting 327 heads of families to obtain register and obtain certification for their palm oil cooperatives for the Cultivation Registration Certificate, which is a new legal requirement to access national and international markets. Once they secure their certification, they will also be able to sell their product at a 160% higher price.
Describe any changes to this output during the past year, and any planned changes as a result of this review
No changes during the past year.
Recommendation: Agree targets for the final year of implementation, following the no-cost extension agreed during this annual review period.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.
No specific recommendations from last year. For the next year ahead, which is the final year of implementation, we will work with ALIGN partners to ensure programme close out is carried through efficiently and smoothly as possible and partners supported through this transition period, exploring opportunities to ensure the sustainable impact and legacy of the work established and how this can be taken forward.

Output 4 / Community tenure rights	Increased recognition of land and forest tenure rights for communities, with more inclusive participatory governance reform/land administration processes; and greater capacity of communities to implement solutions and access donor funding, including increased participation of women
Output number:		4	Output Score:		A+
Impact weighting (%):		20	Weighting revised since last AR?		No
Indicator(s)				Milestone(s) for this review		Progress this AR
4.1 More inclusive and participatory land reform processes for communities:						Score A+ Moderately exceeded expectations
4.11 #projects where government or companies have partnered with community-led organisations on issues related to land rights and territorial governance				Target: 12 / (Tenure Facility)		Score A+ / Total: 26 (10 new) / Cumulative total: 28
4.12 #projects that have contributed to consultations with communities and other actions related to Free, Prior and Informed Consent (FPIC)				Target: 10 / (Tenure Facility)		Score A+ / Total: 19 (11 new) / Cumulative total: 22
4.2 Strengthened gender equality in community organisational governance structures and greater participation/inclusion of women						Score A+ Moderately exceeded expectations
4.21 # projects that have strengthened gender equality in communal land and forest rights governance, and/or community orgs				Target: 20 / (Tenure Facility)		Score A+ / Total: 28 (8 new) / Cumulative total: 29
4.22 % of women in target communities included and participating				Target: 90% / (Cadasta)		Score A+ / Total: 100%
4.3 Increased mapping, documentation, and monitoring by communities of their land and resource rights, including by women:						Score A+ Moderately exceeded expectations
4.31 ha of land documented by communities				Target: 3,000,000(2,700,000 new) / (Cadasta)		Score A / Total: 4,418,117.33 hectares (1,927,705.97 new)
4.32 # partners/projects using tech and leveraging data to document and secure rights				Target: 27 / Cadasta 12 (6 new) / Tenure Facility 15		Score A+ / Total: 31 / Cadasta 13 (10 new) / Tenure Facility 18 (6 new); cumulative total 24
[note] Tenure Facility milestones are for this review period only, not cumulative targets
[note] Progress total this AR is the total achievement for this reporting period. Tenure Facility’s cumulative figures represent the total unique projects achieving results across 2023 and 2024. Some projects that reported results in 2023 also achieved results in 2024. These projects are counted only once in the cumulative total to avoid duplication.

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 4 covers projects delivered through two global partners, Tenure Facility and Cadasta, who provide direct support to increase forest protection and land tenure security for forest communities at the frontline of climate mitigation, providing greater protection for livelihoods of vulnerable communities, including women. During this second full year of implementation significant progress was made, with milestones largely exceeded by both partners.
  1. More inclusive and participatory land reform processes for communities
Tenure Facility has continued to strengthen local community rights, including through FPIC processes and building capacity for IP and LC organisations to participate in processes related to land reform. The target for this AR period was 37 (21 new), and partners exceeded this through supporting a total of 47 organisations (28 of which were new):
- In Indonesia, Tenure Facility supported partners working to map 600,000 hectares of Indigenous territories and advance governance processes, with a particular focus on increasing Indigenous women's involvement in decision-making. The project also supports policy advocacy, regional legal reforms, and collaboration with local governments and civil society to achieve legal recognition and better management of Indigenous lands
- In Brazil, Tenure Facility partners played a central role in negotiating a landmark conciliation agreement between Quilombola leaders and the Brazilian Air Force which has resolved a 44-year conflict in Alcântara, Maranhão. The Presidential declaration will allow the expropriation of overlapping private areas and the formal titling of 78,100 hectares. Around 3,350 Quilombola families in more than 152 communities will benefit from the agreement. Alcantara is the municipality with the largest proportion of Quilombolas in Brazil (85%).
  1. Strengthened gender equality in community organisational governance structures and greater participation/inclusion of women
Partners have worked to ensure that gender equality is embedded into project design and activities with community organisations, which is often challenging and a longer-term process of change, in partnership with communities. This year Tenure Facility has made particular advances in increasing women and youth representation in the councils and committees where decisions about forests are made: of the 35 projects in full implementation, 3 (10%) are led by women’s organisations, including both in Brazil and DRC. Many projects fund women’s organisations as local partners. In DRC, 289 women leaders were identified and integrated into Community Forest Concession governing bodies, significantly increasing female representation in local forest governance structures. In Indonesia, partners supported Engendered Participatory Mapping which helped women in five communities take on greater roles in territorial protection and local economies.
Cadasta have made significant improvements in the past year, co-creating gender strategies with each partner within their scope of work that has resulted in extremely high participation of women in activities, Cadasta has developed, including achieving gender balance attendance in trainings, women leading data collection teams in areas, and invitations for participation in focus group discussions.
Partners reported that promoting women's access to secure land requires a long-term perspective. Continuous engagement with local stakeholders and authorities, alongside ongoing advocacy and education, have proven critical in maintaining momentum and ensuring that advancements in women’s land rights were achieved and preserved over time. This includes holding frequent meetings and workshops with municipal authorities to discuss rural women’s land rights issues, ensuring the topic is on these authorities’ decision-making agendas, and creating space for women to participate in their meetings and present their experiences first hand. Additionally, gender-inclusive training, particularly leadership training, has successfully improved the representation and leadership of women in land governance.
  1. Increased mapping, documentation, and monitoring by communities of their land and resource rights
Both delivery organisations have continued to progress and deliver on this target area, on track or exceeding total targets. For example, Tenure Facility reported 18 new projects (against a target of 15) which are strengthening local communities’ skills to map and monitor their land: In Guyana, partners trained 14 local mappers, monitors, and knowledge holders to ensure boundaries were accurately recorded and culturally significant sites—such as sacred creeks, mountains, and hunting grounds—were included. This work is helping protect not just land, but also community heritage and identity; In Indonesia in Papua, partners are supporting 40 Indigenous communities to map 5.8 million hectares and submit these maps for government approval. By strengthening trust and governance, it enhances land security and promotes collaboration between communities and authorities.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
No planned changes to this Output. At a project level, some minor revisions in Cadasta logframe were agreed during the last annual review period, which were implemented for this annual review period. For instance, Cadasta’s Project Logframe FY 24/25 now differentiates between data ‘migrated’ and ‘newly mapped’.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
A key learning for Cadasta this year was on refining the monitoring and reporting process with grantees to identify bottlenecks, delays in data collection and the lack of use of survey forms in the field by some partners. This robust multi-pronged approach at progress monitoring and evaluation helped Cadasta work with partners more effectively. As we transition to the final year of implementation for both Cadasta and Tenure Facility, it will be important to ensure a smooth project close out and ensure that partners are supported as possible through this process, including alternative options for how partners can continue to be supported as TF and Cadasta develop and expand.
D: VALUE FOR MONEY
Key cost drivers and performance
VfM performance compared to the original VfM proposition in the business case
The live GLGP projects (ALIGN, Cadasta, Tenure Facility, Land Facility and Decision Support Unit) all apply and report against the “5 Es” of VfM (Economy, Efficiency, Effectiveness, Equity, Cost-Effectiveness), as set out in the FCDO PrOF rules, in their narrative reports and annual review self-assessment form.
The Programme Team and HFRD Economist reviewed the programme against key VfM metrics and overall found evidence of good VFM practices and cost-effective delivery against programme objectives. Ongoing monitoring and evaluation ensure partners are using resources efficiently while proactively ensuring benefits for a range of identified beneficiaries. Cost effectiveness of the GLGP is demonstrated not only through project delivery, but also through how the programme contributes to wider UK development commitments and policy outcomes, such as ICF targets and the IPLC Forest Tenure Pledge. In this first year where all projects are being implemented, the Programme is delivering strategic interventions through complementary entry points, from national systemic change to supporting local communities, enabling greater collective impact and effectiveness (see Section B Theory of Change).
Examples of successful application of VfM considerations from project partners over the reporting year are summarised below:
- All partners regularly look to combine events and multiple meetings to maximise time and cost efficiency and economy, such as at field visits and conferences (for example, with funders, implementation partners and governments at the World Bank Land Conference). Land Facility has successfully trialled ‘rapid’ reviews and approvals for two projects (Zimbabwe and Congo Basin). Partners have combined multiple country visits into one regional trip in order to reduce flight costs. All partners have assessed the needs and benefits of travelling for in-person meetings, ensuring these will support essential engagement. Otherwise, virtual meetings are used at lower cost.
- Land Facility, Tenure Facility ad ALIGN have mobilised additional resources from HMG Posts (notably Indonesia and Congo Basin) through the GIG COE offer, demonstrating the programme’s ability for efficiency and effectiveness through responding quickly to Post interest and absorbing buy-in from another programme to deliver high quality activities within a short space of time. Resources were managed flexibly in response to an increased workload, through delivery models being able to bring in extended teams and expertise at short notice.
Progress on Equity: is an ongoing consideration for all partners, including for gender and vulnerable and marginalised groups. In 2024, 78% of Tenure Facility grant funding went to projects where the main partners are extremely vulnerable minority Indigenous Peoples, Afro-descendant, or local community groups. Many of these groups experience systemic discrimination and have few opportunities to access finance. Cadasta have adapted their reporting requirements for finance, narrative, and MEL to make reporting more accessible for smaller grassroots organisations. Although primarily in inception phase during this reporting period, Land Facility, have designed a Gender Equality and Social Inclusion strategy, and will ensure effective reporting on GESI. GESI factors are also included in the desk-based diagnostic for each CSP so have been referenced for all four countries under scoping.
Assessment of whether the programme continues to represent value for money
The examples mentioned above reflect the VFM that GLG is delivering. Work on VfM metrics for Land Facility was initiated in the inception phase with some indicators developed, however, now that we are in implementation we will look to revisit these indicators. Recommendation: Work with economist to review, agree and finalise the VfM indicators Land Facility developed in Inception Phase once Implementation Phase is underway.
E: RISK
Overview of risk management
The risk rating for GLGP has been changed from major to minor, reflecting the changing scope of programme activities with some components ending in 25/26 and an updated risk assessment in the context of HFRD’s overall risk appetite and portfolio. The risk appetites are between ‘receptive’ and ‘cautious’, meaning the FCDO are willing to accept a higher degree of risk in the majority of activities to achieve objectives. Currently, GLGP’s risk appetite does not exceed HFRD levels, which do not set a ceiling for each programme or activity. The matrix below provides a visualisation of the residual risk after mitigation across the seven risk categories
Specific Risks During the Review Period
- Strategy & Context: The political economy and complexities of land governance reforms will continue as part of the programme, with this being an ongoing risk that the programme is designed to manage (for example, through ongoing PEA and flexible programme design). During this annual review reporting period, the donor funding landscape shifted with some donors stopping or significantly reducing their ODA. The implications of this are numerous, including affecting the downstream delivery chain, the broader implementation landscape in specific countries, and how the UK works with other partners to influence change. To mitigate this risk, we have regular reviews with all partners, reviewing changes at the global, and also country level to identify how the changing donor landscape may affect implementation, and what measures can be taken to adapt for this changing landscape.
- Policy & Programme Delivery: In this reporting period budget, uncertainty for this and future financial years increased in light of the UK government’s decision to reduce the ODA budget from FY 26/27. This has inevitably affected delivery partners’ ability to plan forward given delays in confirming the 25/26 budget and the uncertainty around future years. The Programme Team worked with partners to help prepare as far as possible for different scenarios, adapt the nature of activities (e.g. focus on policy and influencing, and smaller activities) and also identify other potential funding options (such as buy-in from Posts and CMPs).
- Public Service Delivery & Operations: During this reporting period staff resource needed for the Land Facility increased, in particular for engagement with Posts and wider stakeholders to effectively design and manage projects. Recruitment of a Programme Funded Posts was successfully initiated during this reporting period, which will make a significant positive impact on central team resources and bring the capacity needed to focus on successful delivery of LF activities.
- Safeguarding: During this period two potential safeguarding incidents were identified by delivery partners, which were investigated and resolved, with support from FCDO’s central safeguarding team. From this we revised our approach as a programme team and worked with delivery partners to ensure they understood the process and that this was strengthened. We continue to proactively monitor the potential risk for sexual exploitation, abuse, and harassment (SEAH).
- Financial and Fiduciary: Two delivery partners provide direct grants to community organisations, who often have weaker financial management capacity. This means that there is a risk of funds being misused and misappropriated by downstream partners. We manage this risk through ensuring robust due diligence of suppliers’ financial systems and processes.
- Reputational Risks: There is continued reputational risk associated with uncertainty about budgets or delays to programme delivery – particularly at Post/country level where we have taken care not to raise expectations given the SR process. This is an ongoing particular risk, especially in the context of the changing donor landscape and the change to UK’s development funding levels. This is a particular risk in relation to the UK’s COP26 IPLC Tenure Rights Pledge commitment and ability to demonstrate progress, with the GLG a key contributing programme.
- Delivery chain risk map: All partners update their risk registers frequently and provide this to the FCDO team with each 6-monthly narrative report. The Delivery Chain Risk Map (DCRM) which supports overall risk mitigation is updated six monthly and details downstream delivery to Tier 4 partners. The DCRM details risks at each tier of the delivery chain.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
Summarise the performance of partners and FCDO, notably on commercial and financial issues.
GLGP had 4.25% underspend against its final agreed allocation for 24/25, partly due to delays in procurement of the Land Facility and ongoing internal delays with budget confirmations beyond control of the programme. Cadasta spent 87% of their budget in 24/25, with the underspend attributed to reducing spend to allow for a no-cost time-extension to responsibly close down the project in FY25/26 within the agreed AGA ceiling. This provides Cadasta with more time to achieve their Outcomes, some of which (formal recognition of tenure) required a longer lead in time than anticipated. ALIGN, and Tenure Facility spent their full budget allocation, and both were able to absorb additional budget from South Africa and Indonesia Posts to expand project activities; this mobilised an additional £2,067,662 for FY24/25.
Additional funding both from central and other Post budgets was made available for Land Facility, who were able to absorb this funding to increase the number of countries for initial scoping and conduct a short-term piece of research for HMG Post on their Congo Basin project, which will be utilised by other programmes within FCDO. Additionally, we were able to contribute additional funding to the World Bank Land Conference which facilitated the attendance of IP and LC stakeholders and also funded the Land Data Interactive Map that was developed by the World Bank to highlight the value of land systems for achieving sustainable and inclusive development.
We have worked closely with all partners to ensure that ongoing strong understanding of FCDO processes and policies related to UK development funding. This has been particularly important with discussing the future of the community rights projects. With ongoing uncertainty around UK aid budgets, such as not being able to confirm final project budgets until well into the financial year, we have ensured regular and open communication with all partners to navigate uncertainties. Due to UK budget constraints and uncertainties throughout ALIGN project implementation, delivery was slower in the first half of project implementation phase. A no-cost extension was requested and agreed in FY24/25 to enable completion of outstanding Outputs and Outcomes over FY25/26.
Delivery and Reporting
Partner management and reporting agreements for ALIGN, Cadasta and Tenure Facility are included in Accountable Grant Agreements (AGA), including reporting deadlines, processes for budget adjustments and formal approval points. Partners provided six monthly and annual progress reports covering FY24/25.
The Land Facility Lead Supplier and the Decision Support Unit submitted multiple reports throughout the period. Whilst in Inception Phase reporting was tied to Inception Phase deliverables, both also submitted quarterly reports covering the first two months of implementation, as well as Annual Reports. Going forward, both Land Facility Lead Supplier, and the Decision Support Unit will provide quarterly reports which will allow us to effectively monitor progress and assess performance against agreed key performance indicators.
All the final reports were informative, highlighted progress, key challenges and were of high quality, with questions raised by the GLG Programme team addressed satisfactorily.
The GLG Programme team hold monthly management meetings (MMMs) and programme management specific check-in calls with each partner to receive regular updates on risk, spend and delivery progress. For Land Facility, we hold both monthly operational check-ins with each delivery partner and a joint MMM. These have been particularly helpful during Inception Phase to establish the Programme ways of working, for navigating changes in personnel, challenges with delivery or relationship management, and budget both on delivery partner and FCDO side.
In Q4 FY 24/25, we held hybrid and virtual away days with each partner, which we used as an opportunity to take a step-back from our usual MMM agenda and discuss wider reflections on ways of working, reflections on previous years of implementation and strategically what we would like future delivery to be. This was particularly important in light of the UK ODA reduction announcements which came that quarter, enabling the Programme Team to discuss future plans and clarify questions for long-standing partners. With ALIGN and Cadasta about to enter their last year of operation, after an agreed no-cost time-extension for both projects in FY24/25, we discussed with each partner potential implications, and how they can adapt their delivery for the final year.
Financial Performance
Frequent and positive communication between all GLGP Project teams and GLG Programme team continues to be strengthened to ensure accurate financial planning and reporting. The FCDO Programme team reflected that frequent communication allowed for close management and ensured any financial issues were addressed in a timely manner. This was greatly helped through the establishment of specific project management meetings with each partner, especially for scenario planning throughout the year and during the last quarter as we awaited confirmation on UK ODA allocations to ensure disruption to teams and activities were continuously discussed and kept minimal. Project Management meetings have also allowed for advance communication and coordination on potential additional budget, in particular to manage Post buy-in and monitoring of activities and allowed for the GLG Programme team and wider directorates to take any necessary internal action. For example, these discussions supported the Tenure Facility, Land Facility and ALIGN to forward plan and absorb additional funding from FCDO Posts when this opportunity became available.
G: MONITORING, EVIDENCE AND LEARNING
Monitoring and Evaluation
Throughout the Annual Review period two monitoring visits were conducted by the GLG Programme Team to existing Tenure Facility projects in Indonesia and Brazil. This was particularly important, as Tenure Facility funds activities which are considered ‘high-risk’ by FCDO and follows on from a trip to Tenure Facility HQ during the last Annual Review period. This brought more in-depth understanding of their processes such as due diligence, risk management and auditing, but this also went both ways giving partners time to understand reasoning behind FCDO requests. The Programme Team also accompanied three initial scoping visits with Land Facility partners to Ethiopia, Brazil and Indonesia, which increased understanding of LF design processes and activity entry points, as well as ensuring a strong partnership model with FCDO Post. The HMG and LF Programme Team, joined by HMG Post, met with Government Ministries, CSOs, Academics, and community organisations.
Due to constraints and costs of holding in-person meetings, the GLG Programme team also organised virtual and hybrid half-day strategic sessions with ALIGN, and Cadasta on ways of working between FCDO and partners, delivery challenges, strengthening Post engagement, and linkages between GLGP project partners. These were particularly important as both projects are due to end in the next reporting period and provided a valuable moment to reflect and consider next steps. Alongside Monthly Management Meetings, the programme team held multiple strategic meetings with the Land Facility team throughout the Inception Phase, which have helped ensure the project was aligned with other GLGP projects, and wider FCDO priorities. During inception, the Land Facility have also developed a monitoring, evaluation and learning plan and value for money framework. Activities will include process evaluations of a selection of country support projects.
For this Annual Review, as well as an FCDO economist, the new Land Facility Project Coordinator who has no prior involvement in the GLGP during FY24/25 has provided an independent review; partner’s annual reports, self-assessment forms and/or interviews with partners to inform their inputs. This has been valuable in challenging our assumptions and picking up on details which may otherwise have been overlooked.
Evidence
Political Economy Analysis is a core tool of the Land Facility to design and deliver projects which are constantly monitoring and responding to the needs, challenges and opportunities of each country or regional context. During Inception, the Land Facility developed a Political Economy & Influencing Strategy and launched the Political Economy advisory group. The guidance, tools and lessons-sharing will support the team to address complex land-related political economy challenges and barriers to reform and illustrate how these can be tailored and used in practice, supported by evidence. Additionally, all light and deep country projects are designed following an in-depth scoping phase which includes desk-based research and remote and in-country stakeholder engagement, informed by sector and in-country experts. In this reporting year, desk based and in-country scoping was successfully completed for Ethiopia and underway for Brazil, Zambia and Indonesia. This will be followed by further visits and scoping during the Design Phase. The findings and analysis are instrumental to identifying and informing the project opportunities.
Learning
Over the past year we have employed a number of methods to capture learning for both FCDO and delivery partners during project implementation, including:
- Ensuring Learning is continually captured and reviewed: ALIGN now submit regular project closure reports which capture conclusions from short term pieces of technical assistance work, which has allowed us to capture learning, and also share with Posts which has been useful.
- HMG land governance sharing and learning sessions: As a result of more in-depth discussions with partners during the virtual away days and MMMs, we held two strategic learning and discussion sessions between ALIGN and FCDO/wider HMG staff on: land-based investments and sustainable economic growth; and land rights and food and agriculture security. Both sessions considered recently announced UK ODA reductions and how land governance themes could be integrated across wider HMG programme and policy priority objectives.
- Learning and Adaptation – As part of the Land Facility design, the Decision Support Unit will “support and enhance effective programme learning and programme adaptation in response to that learning”. In the first year the DSU have started to establish the structures to facilitate ongoing learning and adaptation for the Land Facility. During the inception phase DSU led a regular series of internal LF learning sessions, including consultation with LFLS to identify learning objectives and priority topics. The first iteration of the learning and adaptation strategy was shared during this reporting period. During this AR period a “learning and reflection session” was planned, to reflect on lessons learnt from the inception phase, due to delays this was held after this reporting period concluded.
Date of last narrative financial report	ALIGN – 13/08/24 / Tenure Facility – 03/06/24 / Cadasta – 09/08/24 / Land Facility – 15/07/25	Date of last audited annual statement	ALIGN – 23rd December 2024 / Tenure Facility – 26th June, 2025 / Cadasta – March 19th, 2025 / Land Facility Lead Supplier – 23rd September 2025 / Land Facility DSU – 27th August 2025

ANNEX 1
Acronyms
Acronym	Explanation
ALIGN	Advancing Land-based Investment Governance (project within GLG Programme)
AGA	Accountable Grant Agreement
AMAN	Indigenous Peoples Alliance of the Archipelago
AR	Annual Review
CSO	Civil Society Organisation
CFUG	Community Forest User Groups
CMP	Centrally Managed Programme
CoE	Centre of Expertise
CLRA	Customary Land Rights Act
CTR	Community Tenure Rights
CoE	Centre of Expertise
DDA	Due Diligence Assessment
DFID	Department for International Development
DSU	Decision Support Unit project within GLG Programme
DCRM	Delivery Chain Risk Map
FCAS	Fragile and Conflict-Affected Situations
FCDO	Foreign, Commonwealth and Development Office
FPIC	Free, Prior and Informed Consent
GFAL	Global Food Security and Land Department
GIG	Green and Inclusive Growth
GLGP	Global Land Governance Programme
HMG	His Majesty’s Government
HMFD	Humanitarian, Migration and Food Security Directorate
ICF	International Climate Finance
INGO	International Government Organisation
IP and LC	Indigenous Peoples and local communities
LF	Land Facility project within GLG Programme
MEL	Monitoring and Evaluation
NPV	Net Present Value
NLCA	National Lands Commission Act
PCN	The Black Communities’ Process
PFP	Programme Funded Post
RLBI	Responsible Land Based Investment
SR	Spending Review
SRO	Senior Responsible Owner
ToC	Theory of Change
ToRs	Terms of Reference
VfM	Value for Money
MMM	Monthly Management Meeting
SEA	South East Asia region
SEAH	Sexual exploitation, abuse and harassment
SSA	Sub-Saharan Africa region

ANNEX 2
Geographic Coverage
This table outlines the focus countries for programme delivery in FY24/25. As the Land Facility was in Inception Phase the table includes where project scoping was underway.

	ALIGN	Cadasta	Tenure Facility*	Land Facility
Argentina		Yes
Brazil			Yes	Yes
Belize		Yes	Yes
Chad				Yes
Cambodia		Yes
Colombia		Yes	Yes	Yes
DRC		Yes		Yes
Ecuador		Yes
Ethiopia				Yes
Guatemala			Yes
Ghana		Yes
Guyana			Yes
India		Yes
Indonesia	Yes	Yes	Yes	Yes
Kenya			Yes
Myanmar		Yes
Nigeria				Yes
Nepal			Yes
Panama		Yes
Sierra Leone	Yes
South Africa	Yes
Suriname		Yes
Zambia	Yes			Yes
Zimbabwe				Yes

*This includes projects which FCDO is directly supporting. However, FCDO also supports Tenure Facility’s wider activities which includes other geographies.