## Annual Review

Title: Green Cities, Infrastructure and Energy Programme (GCIEP)
Programme Value £ (full life): £53,000,000		Review date: June 2025
Programme Code: 300566	AMP start date: / 13/02/2020	AMP end date: / 31/12/2025

Summary of Programme Performance
Year	2020/21	2021/22	2022/23	2023/24	2024/5
Overall Output Score	A	B	B	A	A+
Risk Rating	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-300566 Documents
DevTracker Link to results framework:	As above

A. SUMMARY AND OVERVIEW
Description of programme
GCIEP is the main delivery mechanism of the new UK Economic Development Centre of Expertise for Green Cities, Infrastructure and Energy (CoE GCIE)[1]. It utilises the UK’s expertise in urban development, infrastructure and energy to address poverty, increase economic growth and enhance climate resilience in low- and middle-income countries. It does this by catalysing investment in sustainable infrastructure and improving municipal finance and public services – creating jobs and improving productivity. GCIEP has two sets of delivery partners: a consortium led by PwC, the ‘Alliance’, that manages the programme, and a group of UK public agencies providing sectoral expertise, described in this report as ‘UK agencies’. They are the British Geological Survey (BGS), British Standards Institution (BSI) Connected Places Catapult (CPC), Crossrail International (CI), Ofgem, Ordnance Survey (OS), the National Infrastructure and Service Transformation Authority (NISTA) and Transport for London (TFL). There is an integrated UK Expertise Offer (UKEO) across the programme, through which world-leading UK capability and methodologies are deployed to meet recipient demand. Projects are delivered in partnership with national governments and cities, with a mix of larger-scale ‘Deep Offer’ (DO) and smaller-scale ‘Targeted Offer’ (TO) projects across Asia-Pacific, Africa, Latin America and the Caribbean.
[1] In recognition of the increasingly important role of energy projects within the CoE, the name was changed during 2025 from GCIEP to GCIEP.
GCIEP also contributes to The Infrastructure Transparency Initiative (CoST), which works with partner countries to implement open data standards to improve transparency and accountability and reduce infrastructure costs. It also supports the Public-Private Infrastructure Advisory Facility (PPIAF), run by the World Bank: the only global facility dedicated to strengthening institutions to realise sustainable infrastructure with private participation and enabling finance for sub-national entities.
This Annual Review (AR) focuses mainly on GCIEP. The initial TO projects with UK agencies began in July 2023. During the reporting period of this AR there was a significant increase in the number of TOs, while implementation began for the six DOs and there was an evolution of the UKEO. In some DO partner countries, there have been significant and rapid changes which have also had implications for programmes. The AR draws on evidence from the Alliance Annual Report and other programme documents and interviews with delivery partner staff, FCDO staff and government stakeholders in the DO countries of Ghana, Indonesia, the Philippines and Zambia, and the TO countries of DRC, Bangladesh, Egypt, India and Indonesia (ASEAN).
The reduction in UK ODA announced in February 2025 and the subsequent process for confirming 25/26 budget allocations has delayed the decision over extension of the Alliance contract, the continuation of DOs, and the mobilisation of new TOs.
About changes to UK ODA
- At this time of profound change, with conflicts overseas undermining security and prosperity, the UK Prime Minister has taken the difficult decision to increase spending on defence to 2.5% of GDP from 2027, funded by reducing the UK’s Official Development Assistance (ODA) and reinvesting it into defence. The ODA budget will be gradually reduced to the equivalent of 0.3% of GNI by 2027, to help smooth the transition.
- The UK remains fully committed to playing a globally significant role in humanitarian aid and development. The transition to spending 0.3% of GNI on ODA will require significant shifts, building on those already underway as the government implements its modernised approach to development, which centres on establishing long-term partnerships based on mutual interests and respect.
- ODA allocations and the impact on programmes are being worked through based on various factors, including impact assessments. We will be taking a rigorous approach to ensure all ODA delivers value for money and maximises the impact of our work to best support the people it benefits, including those in humanitarian crises.
- We remain committed to spending 0.7% of GNI on ODA when the fiscal circumstances allow.

Summary supporting narrative for the overall score in this review
The GCIEP programme is highly relevant to FCDO priorities and well positioned to deliver results. Its impact goal, ‘Increased inclusive and low-carbon economic growth and enhanced climate resilience leading to poverty reduction’, addresses growth, climate and development: three of FCDO’s six priorities. The theory of change remains relevant, with broad overall outcomes at the centre, and more specific outcomes at country level.
After two years, the FCDO and the Alliance have invested well to establish a strong foundation for a long-term programme, with strong management processes, detailed policies and clear guidance for practitioners. Through the UKEO, the expertise, tools and methodologies of expert partners have been incorporated into project designs. As shown in Section B, the programme is delivering an extensive range of projects, with some already completed and showing outcome level results. The programme is well managed, with staff adapting in response to lessons learned, for example by incorporating additional ‘Buy-in’ projects funded by posts. The need to better integrate all the delivery partners into a fully coherent programme is well understood. All this gives us confidence it will deliver value for money (VfM) for the UK and partner countries if it continues over the eight-year timeframe it was designed for. We have assigned an overall score of A+.

Major lessons and recommendations for the year ahead
Recommendations
1. Increase joined-up working between programme partners and coherence in reporting by establishing a governance policy to cover projects co-delivered between the Alliance and the UK agencies and those delivered solely by UK agencies, applying lessons learned. Identify ODA-management capability or resourcing gaps in agency teams and support them as appropriate with training, written guidance and advice, including on Gender Equality, Disability and Social Inclusion (GEDSI) and International Climate Finance (ICF), risk management, VfM and monitoring and reporting. Ensure the full portfolio of UK agency-led projects is represented in the logframe and that UKEO objectives and performance are fully reflected. In reviewing the logframe, consider how to better set targets and expectations for performance.
2. Work with the Alliance to develop an action plan to accelerate finance mobilisation, based on learning and successes to date. Clarify the steps already being taken by the Alliance and consider additional steps to link finance providers, public and private, with existing and planned GCIEP investments.
3. Maintain the current range of thematic issues addressed and remain open to any demands for expansion into new sectors where the UK has a comparative advantage. There are, however, value for money risks from expanding the geographical spread to enter countries where the Alliance is not present. If post also lack capacity in those countries, the resource burden and risk of failure will be higher and should be considered carefully in the appraisal of bids. This will become more important as FCDO adjusts overseas resourcing allocations in response to the reduction in ODA.
4. When appraising bids for new TOs and the potential sustainability of the new intervention, consider the resource available at post and whether existing government-to-government agreements are sufficient to enable the project to achieve it full objectives. There are VFM challenges with maintaining a high number of TOs, with support from posts being essential to engagement with partner governments and municipalities. In Mumbai, for example, GCIEP funded technical experts from Crossrail International to develop the new metro’s Operation and Maintenance (O&M) strategy.
5. Work with the Alliance and UK agencies to establish an evidence-based narrative describing and quantifying the potential short, medium and long-term impacts of GCIEP on partner-country and UK economic growth, and how collaboration with DBT and the use of non-ODA could enhance those effects without compromising the poverty reduction goals of ODA.
6. The programme is overly reliant on partner reporting of results. Triangulate reporting to strengthen the evidence of results, including of the outcomes of TOs, by incentivising and supporting PM staff in-country to visit and observe delivery of projects and to feel empowered to challenge. Provide opportunities for different staff at post to visit projects and meet stakeholders. Select a sample of up to five TOs and DOs for monitoring and partner engagement visits by FCDO’s central GCIEP team and establish a system for recording TO outcomes.
Lessons learned
- Support through GCIEP can lead to longer term sustainability in the form of new business opportunities for GCIEP partners. In India, a project led by CI to improve transport mobility in support of increased employment and investment, led to the direct award of a substantial contract from Mumbai Metro to CI for Phases 2 and 3 of the work.
- From Transport for London’s bus reform work in Dhaka, Bangladesh, it became clear that the recruitment of a local adviser to support the project was a key ingredient to its success.
- Regional training approaches for government officials from many different countries can offer both positive impact and good value for money (VFM) - this is one of the conclusions from the third iteration of the ASEAN Sustainable Leadership in Infrastructure Programme (ASLIP).
- With mitigation measures against risks associated with political upheaval and security issues, GCIEP projects have been successful in countries like DRC, Mozambique, Bangladesh, and Ethiopia.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
GCIEP will contribute to inclusive and low-carbon economic growth and enhanced climate resilience, leading to poverty reduction in FCDO partner countries and cities. Its technical assistance will lead to enhanced capacity and knowledge in supported national and sub-national institutions in partner countries, with the collaboration of the private sector and local communities, resulting in:
- A strong pipeline of prioritised, sequenced and “investible” climate resilient and inclusive infrastructure projects; mobilising sources of finance and funding available in the private sector, UK, and donor agencies, combined with innovative approaches to structuring and financing public projects that ensure their long-term viability; and
- A strengthened enabling environment for the provision of infrastructure and urban services including: i) better urban planning, land use management and climate impact risk management; ii) improvements in infrastructure policy making and regulation and on the overall business environment; iii) enhancements in municipal fiscal and financial management, revenue generation and procurement systems by municipal authorities; and iv) more effective investment-related processes, including project selection and procurement frameworks, to foster a conducive investment climate.
The impact goals are central to ministerial objectives and the theory of change (TOC) assumptions remain relevant and valid. There have been no changes in the global context that affect the TOC to date, although it relies on the assumptions that its budget will be maintained and that public finance through IDBs will continue to be available, both factors that may change in the coming year. The TOC was updated in Nov 2024 to add a section defining transformational change in GCIEP and is clearly set out in a full narrative showing the above pathway, underlying assumptions and strength of evidence.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
Following its first year of mainly scoping and design, the programme substantially scaled up activity in Year Two and all outputs were delivered. It is now delivering deep-offer programmes (DOs) in six countries: Ghana, Indonesia, Mozambique, Philippines, Vietnam and Zambia. TOs have delivered technical assistance in 25 countries: in Year One, 40 TOs were approved and mobilised. In Year Two, 29 new TOs were mobilised and in Year Three a further 29 TOs have been approved and are in the pipeline (TORs being drafted at the time of writing). The majority were delivered and assessed within the same financial year. All but a small number went beyond one financial year due to the particular context. Best practice from UK agencies has been applied across the programme. Over 1,000 people have been trained over this reporting period, with satisfaction rates in the high 90s. All the workplans led by the Alliance have been assessed for their GEDSI ambition, with 63% having been found to meet the criteria for Level 2 (Empowerment) of FCDO’s Checklist for integrating Gender Equality, Disability and Social Inclusion (GEDSI) across Economic development programmes. The percentage of funding that complies with ICF criteria has increased from 30 to 70% (and 80% for the Alliance managed projects), with a 50/50 split between climate mitigation and adaptation. The core Alliance team has demonstrated a mindset of continuous improvement and has an active learning plan in place, capturing lessons and sharing them between staff through various means.
Although most outcomes will take two or more years to happen, some of the TOs have produced early outcomes. These include two cases of finance mobilised under Outcome 1. First, GCIEP played a key role in India, facilitating £800 million through the Credit Enhancement Platform (CEP) of the National Bank for Financing Infrastructure and Development (NaBFID).[2] Second, in Tanzania, GCIEP informed the design of a solid waste management loan totalling $110 million (£82 million) under the Dar Es Salaam Metropolitan Development Project Phase 2 by providing data, analysis and recommendations to reallocate the investment. The Alliance does not claim GCIEP caused these outcomes, but that it contributed to the mobilisation of the finance.
[2] GCIEP Annual Report 2025: "The initiative aims to improve municipalities’ access to financial markets for climate-positive urban infrastructure projects. GCIEP successfully supported NaBFID to refine and operationalise its CEP, while also helping to identify a viable project pipeline focused on waste-to-energy (WtE), wastewater treatment, and waste-to-gas sectors, together valued at £800 million. NaBFID, which currently holds a mandate to support £1.2 billion in infrastructure financing, has committed to financing this pipeline. GCIEP also created a project support facility (PSF) framework that NaBFID will apply to appraise projects for consideration under the credit facility and support each project in working with the NaBFID CEP. The initiative aims to improve municipalities’ access to financial markets for climate-positive urban infrastructure projects.”
Cases of improvements to the enabling environment have also been seen under Outcome 2. In Ukraine, GCIEP strategic support for infrastructure reconstruction and training of 213 government officials on the National Infrastructure and Service Transformation Authority (NISTA) Five Case Model (5CM), contributing to the issuance of a decree in August 2024 by Ukraine’s Prime Minister Cabinet mandating the use of the 5CM format for all infrastructure business cases in the 2025 budget year. In Vietnam, GCIEP was instrumental in shaping the emerging policy on urban rail and Transport Oriented Development (TOD), at both city and national levels. In Indonesia, the national planning agency approved the Project Funding and Financing Options Framework and associated digital tool for infrastructure and mobility projects to support the selection of financing types for shortlisted projects under the 2025–2029 National Medium Term Development Plan, which is in the process of being adopted. Further outcomes are likely in the coming year, including in Vietnam, Mozambique and Zambia.
The reviewers noted that, other than to highlight standout achievements, as above, there is no system in place to follow up, evaluate and record the outcomes of completed TOs after the project has closed.
Central factors in the programme’s success have been the clear theory of change, directing all activity towards either improving the enabling environment or mobilising finance, and the co-design with stakeholders. Through a demand-led process of commissioning, most activity has focused on energy, transport and water. This focus allows the programme to build specialist advisory teams in communities of practice, while maintaining the flexibility to address the full range of requests from partner countries.
Overall, management by the Alliance has been strong, and issues have been addressed when they have arisen. Activities have generally been delivered to a high standard, with the adaptive management approach ensuring outputs are relevant to partner governments’ needs and allowing a degree of flexibility that allows HMG to be opportunistic and agile, for example, by stepping in to fill a gap left by USAID cuts that has allowed progression of the Zambia/Tanzania electricity interconnector.
The UKEO has delivered important outputs through its strategic engagement with the UK agencies to bring their expertise and methodologies into many of the workplans, and through its convening of existing UK methodologies and the development of new tools. These include Reference Class Forecasting (RCF) and the Gender Equality, Diversity and Social Inclusion (GEDSI) Lens Toolkit for Project Developers, both of which have been well received with HMG and external partners. Alongside mainstreaming the GEDSI Lens Toolkit in GCIEP, there is significant interest across wider HMG programmes and externally with a clear opportunity to support its uptake across the global infrastructure ecosystem with BSI showing interest in turning it into a PAS standard. Specific objectives and indicators of success in the logframe would improve accountability of this area of work, ensure its performance is fully reflected in GCIEP’s outcomes and make it easier for reviewers to assess.
CoST continues to demonstrate that it is improving the evidence and accuracy of data on infrastructure by supporting governments to publish data on 10,571 projects worth nearly $6bn in 2024-25. This compares to publishing data on 9,341 infrastructure projects in 2023/24, although it is below the target of 12,000.
PPIAF supported governments in the adoption of 15 new policies and regulations aimed at strengthening the enabling environment for private sector participation in infrastructure investment, while nine economies adopted PPIAF recommendations to meet their climate mitigation and adaptation policy targets.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
The programme should continue. Through substantial early investment, the Alliance has established a strong foundation, as appropriate for a large-scale, eight-year programme. This includes detailed policies, strategies and guidance on programme management, monitoring and reporting, value for money (VFM), adaptive management, learning and communications, gender equality, disability and social inclusion (GEDSI), climate, nature and the environment (CNE), risk, social value, measurement of finance mobilised, ICF reporting. Lessons learned have been systematically documented and should make the design and mobilisation of new projects smoother and quicker. It delivered many outputs and can already demonstrate some examples of outcomes. With the up-front investments made, the programme is well-poised to continue making a major and high-value contribution to UK objectives for the next six years.
Central management by the Alliance has been flexible and able to adapt to new funding streams, for example through incorporating bilateral Buy-in projects, commissioned by posts with commitments from Tanzania (Dar es Salaam Urban Resilience Project (DURP)), the Democratic Republic of the Congo (DRC), Indonesia (Future Cities Infrastructure Programme (FCIP)), Ukraine (5CM) and South Africa. The Alliance has been proactive and forward thinking in seeking to adapt to the changing political landscape, for example by putting forward proposals to increase the contribution of the programme to UK growth goals.
The quality of the technical inputs and deliverables has been high, and the UK agencies add value and uniqueness to the programme. The quality of reporting has been mixed between UK agencies, many of which are not used to the concepts and expectations that come with ODA. There have been some issues with integration between UK agencies and the Alliance, bringing risks to HMG’s reputation with stakeholders. Progress has been made, though more work will be needed by FCDO, the Alliance and the UK agencies, to clarify governance, develop relationships and ensure that reporting to FCDO is sufficiently detailed and relevant. Greater efficiency has been seen where the UK agencies act as a contractors, as in the case of Crossrail International in Vietnam, contributing to an overall intervention and country strategy owned by the Alliance.
The programme has successfully mitigated significant delivery risks in the last year, although there has been an unavoidable effect on VFM in some cases. The uncertainty surrounding further funding of the programme, due to the spending review, affected planning and reduced the time available for delivery of many projects. In most cases, the quality of outputs was protected through flexible and adaptive programming, but it put staff under pressure and affected recruitment, morale and retention. The Alliance overcame challenges to recruitment of in-country experts where its members are not represented and demonstrated its ability to deliver in countries with heightened security risks, such as DRC and Mozambique. Within the FCDO programme team there were several important vacancies carried through most of the year, which affected the team’s capacity to coordinate between delivery partners, monitor outputs and act on lessons learned. Most of the posts have now been filled, which will allow these issues to be fully addressed in the coming year.

## C. DETAILED OUTPUT SCORING
Overall, the programme has performed well. It has a strong focus on quality and met its targets for incorporating UK expertise and best practice into project design and delivery. It has mainstreamed GEDSI across all of its work and has produced a flagship product on GEDSI in infrastructure programming which will become a GEDSI project in the coming year. Over 60% of its projects have been assessed as meeting the FCDO’s GEDSI marker of Level 2 (Empowerment). It has a good story to tell, which it could communicate more strongly. On Climate, it has surpassed its target for 70% of projects to be meet ICF compliance (those led by the Alliance reached 81% ICF compliance) and lessons have been learned on appraisal of project proposals to increase this rate. Support for CoST has met most of its target KPIs, with good reasons where not - some improvements could be made in engagement with FCDO posts. PPIAF supported governments in the adoption of 15 new policies and regulations, while nine economies adopted PPIAF recommendations to meet their climate mitigation and adaptation policy targets.
Detailed overviews of each output follow.

Output Title	High-quality TA deliverables completed by GCIEP for FCDO posts to facilitate economic transformation and inclusive growth (in line with VfM targets)
Output number:		1	Output Score:	A+
Impact weighting (%):		40	Weighting revised since last AR?	Up from 30

Indicator(s)	Milestone(s) for this review	Progress
O 1.1a: DO scoping: Number of TA deliverables to scope proposed GCIEP DO programmes (scoping reports)	Target: N/A	Total: 1 (Ghana urban scoping (Y2Q1))
O1.1b: DO detailed design: Number of active TA deliverables to undertake detailed design of proposed GCIEP DO programmes or Buy-ins (number of DO interventions or Buy-ins)	Target: N/A	Total: 25 (DO: 20, Buy-Ins: 5) / (1–5) Mozambique, (6–9) Ghana, (10) Zambia, (11–13) Philippines, (14–17) Indonesia, (18–20) Vietnam, (21–25) Five Buy-in ToRs: Tanzania, ASEAN, South Africa, DRC; Ukraine.
O1.1c: DO implementation: Number of active GCIEP DO programmes in implementation	Target: N/A	Total: 6 (Ghana, Mozambique, Zambia, Philippines, Indonesia and Vietnam)
O1.2: Average achievement of planned activities	70%	All DOs: 86.4% / Ghana: 90.1% / Mozambique: 79.1% / Zambia: 89.2% / Philippines: 88.7% / Indonesia: 95.8% / Vietnam: 88.6%
O1.3: Number of TO ToRs completed and submitted for approval	Target: N/A	Total: 11 / ODA: 9 / Non-ODA: 1 / Combined: 1

O1.4: Average achievement of planned deliverables across active TO portfolio	Target: 70%	Total: 90.3% / ODA: 89.4% / Non-ODA: 95.8% / Combined: 75.0%

Briefly describe the output’s activities and provide supporting narrative for the score.
All GCIEP’s output level milestones were achieved (with many overachieved) across all the portfolios, signifying maturity and high operational performance. Overall, 87.4% of workplans at the programme level were achieved.
For DO Countries (DOCs), 26 deliverables related to scoping and design were carried out, resulting in six DOCs moving into active implementation. For implementation, GCIEP achieved 86.4% of planned activity, surpassing its target of 70%. The lowest DO was Mozambique, with 79.1%, which in part is due to civil unrest which affected the implementation of certain deliverables.
TO, Investment and Buy-in portfolios delivered technical assistance in Year Two across 22 workplans in over 25 countries. This amounted to 90% of planned deliverables. Of these, five are Buy-ins and seven are Investment WPs. They buy-ins have extended the reach of the GCEIP beyond what was anticipated at the start.
GCIEP also compiled a portfolio of world class UK methodologies ready for global deployment. These include the GEDSI lens toolkit, Reference Class Forecasting (RCF), the International Growth Centre (IGC), Cities Spatial Model (CSM), Whole Systems Approach to Energy (WSA), Five Case Model (5CM) and Building Information Model (BIM), alongside integrating CoST’s suite of transparency tools. Of these, nearly 80% of UKEO investment in methodology appraisal and development went into the GEDSI lens toolkit and applying RCF to Bus Rapid Transit systems, both completed in March 2025. These two tools have high potential for application across GCIEP workstreams and for uptake more broadly by partner governments.
While the deliverables were achieved across the portfolio, the consistency of quality varies, which is discussed in the value for money section.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
There have been changes to the deliverables expected from DO programmes as they moved from design to implementation. To streamline this process, future DO programming will skip scoping and either integrate existing TO workplans into DOs or move to detailed design. As the programme spent the majority of the year mobilising there have been some edits of the logframe to reflect expected outputs throughout the year, but nothing of significance.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
The previous AR flagged the UKEO as an important element of GCIEP delivery, with acknowledgement of the challenge that the UK infrastructure landscape remains complex, and matching UK expertise to global demand even more so. The UKEO has been successfully developed and incorporated into delivery in DOs and TOs and an explanatory handbook developed to increase awareness of its capabilities at post. It has also demonstrated its ability to be a flexible and versatile resource, able to respond to emerging Ministerial priorities, for example by exploring the potential to use non-ODA budgets to generate opportunities for UK companies arising from GCIEP outcomes.
As the programme’s focus in Year One was on scoping and design, there were minimal lessons from implementation to apply in Year Two. The activity in Year Two was affected by the shortened timeframes and budget uncertainty; while outputs were delivered, the quality (discussed in the VfM section) was an issue in some cases. This must be considered in future, particularly in view of the long-term ambition which needs consistency and strategy to fulfil its impacts.
Recommendations for improvement are to continue building on work that has already been implemented, where stakeholder buy-in is already established, and to consider streamlining the quality assurance process.

Output Title	Best practices in place to maximise effectiveness in GCIEP delivery in TO and/or DO countries
Output number:		2	Output Score:	A
Impact weighting (%):		10	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
No. of instances where GCIEP team has worked and/or coordinated* with partners** / A) GCIEP DO interventions / B) GCI CoE delivery partners*** / C) Any other UK expert organisations / D) Development partners (Instances that DO and Buy-ins have collaborated with development partners) / (disag by DO, TO and UKEO)	No target set	a) 4 / b) 17 / c) 23 / d) 37

Briefly describe the output’s activities and provide supporting narrative for the score.
This output records the programmes cross-learning, and collaborating activities (including internally) to deploy best practice to deliver more effectively and increase sustainability. The achieved number of instances recorded suggests high proportion of opportunities were taken. The score A has been assigned on the basis that expectations most likely were met. However, with no baseline or target it is difficult to use this measure as evidence of progress or success.
At the end of Year Two, the GCIEP annual report records four instances of cross-learning between DO programmes, an example being the three Asia DOs (Philippines, Indonesia, Vietnam) holding a joint session on TOD approaches at the design stage. It records 74 instances of external organisations being involved in GCIEP delivery: 18 of UK agencies, 20 of other UK organisations (examples include Arup, British International Investment (BII), Oxford Global Projects, London School of Economics) and 37 of international non-government organisations (such as Asia Development Bank, African Development Bank, GIZ, UN-Habitat). The baseline measure was the end of Year One results, which were three for COE DPs and 0 for other organisations (few projects had started).
The results recorded for Year Two are positive and show that the programme has been successful in its engagement with other organisations. The indicator assumes these partners brought best practice into the programme.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
During the past year the programme has extended the scope of this output’s metrics beyond collaboration with the CoE delivery partners to include A) cross-learning between GCIEP DO interventions, C) collaboration with other UK expert organisations and D) collaboration with international development partners. This change was properly recorded in the ‘Change log’ section of the logframe.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Considerable progress has been made on the lessons and recommendations from last year, particularly in improving the UKEO. These were recorded on a recommendations tracker shared with the review team. For the year ahead, we recommend consideration of how to strengthen the evidence for this output, including to verify and explain the assumption that such collaboration brings best practice into GCIEP. This could include in-person monitoring of cross-DO learning sessions and more case studies on the effectiveness of collaboration with the programme, with input from FCDO infrastructure advisers and the partners concerned.
The Alliance’s original justification for omitting targets was that they cannot be set for a demand-led programme. While it is true that an absolute target might create false incentives, a percentage-based target could mitigate that risk. For example, we would expect all DOs to regularly engage in cross-learning sessions with others; it would therefore be feasible to set a target of 100% of DOs taking part in a minimum threshold of such activities.

Output Title	Enhancing capacity and knowledge to strengthen GCIEP supported institutions and agencies in partner countries
Output number:		3	Output Score:	A
Impact weighting (%):		10	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number (#) of people trained on UK tools and methodologies that successfully passed the training (and % that received the certification – if applicable) (disaggregated by country, gender, PWD (men/women), youth and type of method)	No Target Set	91.5% (205/224) / TO (including investment and Buy-ins) / 84.6% (11 out of 13,10 women) in Egypt / UKEO / 91.9% (194 of 211, 124 women) in Ukraine
Number (#) of people trained via GCIEP supported work packages/interventions (disaggregated by women professionals (W), PWD (men/women), youth (Y), number of professionals from government, private sector, academics, MSMEs)	No Target Set	963 (398W, 63Y, 6PwD) / DO: / 155 delegates (61W, 37Y) in Mozambique / 62 representatives (16W) in Ghana / 272 representatives (95W, 6 PwD) in Indonesia / 20 representatives (13W) in Zambia / TO (including investment and Buy-ins) / 16 delegates (10W) in Egypt / 48 delegates (18W) from ASEAN countries / 57 delegates (15W) in the Philippines / 120 representatives (61W, 26Y) in Tanzania / UKEO / 213 senior officials (109W) in Ukraine
% of participants indicating that the training/capacity building in Output 3.1 or 3.2 was "useful" or "very useful" on a 5-point scale	70%	96.6% (402/416) / DO: / 23 of 23 respondents in Mozambique / 55 of 58 survey respondents in Ghana / 65 of 67 respondents in Indonesia / 1 of 1 respondent in Zambia / TO (including investment and Buy-ins) / 15 of 16 survey respondents in Egypt / 24 of 24 delegates from ASEAN countries / 19 of 23 respondents in Philippines / 38 of 40 survey respondents in Tanzania / UKEO / 162 of 164 respondents in Ukraine

Briefly describe the output’s activities and provide supporting narrative for the score.
Overall, the results for this output are strong. For the first indicator, 128 people were certified in the Five Case Model (5CM) training at foundation level and another 77 people at the practitioner level. About 95% of these participants were from Ukraine where the government, with GCIEP support, has made 5CM mandatory for infrastructure procurement. This represents a substantial increase from the previous year when 52 people, also from Ukraine, were certified. Furthermore, the result demonstrates a positive gender balance where 134, or 60%, of the participants were women. Going forward, this indicator may need to reflect the fact that 5CM has been the only UK methodology in GCIEP offering certification for the past two years.
For the second indicator on training, there were strong results for four DOs especially Indonesia and Mozambique, and a good mix between Africa (373 participants) and Asia (377 participants). Types of training offered covered urban and infrastructure topics such as climate finance, mobility, energy planning, and waste management. Of the total 963 people trained, 41% were women, 6.5% were youth, and less than 1% were people with disabilities. Those planning future GCIEP training events should consider what additional efforts can be made to increase participant diversity especially those living with disabilities. For the final indicator, an impressive 402 people (96.6% of the total) rated their training as “useful” or “very useful”. For the second year running, this result has been well above the 70% minimum. For future years, the minimum may need to be revised upwards.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
In the Alliance’s forthcoming review of the logframe, it should address the predominance of 5CM in indicator 3.1 and raise the target minimum for indicator 3 from 70% to 80% or 90%
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
In the 2024/25 GCIEP AR, Output 3 had the following recommendation: Training needs to be part of a wider, strategic offer to deliver strong value. GCIEP needs to refine how it assesses likely value for money when assessing requests for training. As a result, most TO proposals in bidding window rounds 2 and 3 solely requesting training were rejected. Revised bidding guidance, and the updated Concept Note template, encouraged Posts to link training requests to opportunities for system reform or transformation.

Output Title	GEDSI is mainstreamed across GCIEP DO interventions and Target Offer (TO) work packages (WPs) (disag by DO and TO)
Output number:		4	Output Score:	A+
Impact weighting (%):		15	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1: Percentage of GCIEP-supported DO interventions/TO WPs that have an ambition level 2, empowerment, or higher as per the FCDO GEDSI framework	50%	Achieved 63%[3] / DO: Level of ambition (LoA) assigned to each of the 45 WSs across 6 DO. Of these, 32 WSs have expected ambition level 2 (L2) Empowerment or higher; none have been completed, therefore, actual achievement cannot be assessed and reported / TO (including investment): 11 WPs assigned LoA, of which 4 were assigned L2 and all 4 achieved L2 Empowerment. / Buy-In: 3 WPs assigned LoA, of which 2 were assigned L2 and have achieved L2 Empowerment / UKEO: 6 WPs assigned LoA, of which 3 were assigned L2 Empowerment -2 have achieved L2 and the other is on track to achieve L2
[3] *(32+4+2+3) / (45+11+3+6) = 41/65 = 0.63

Briefly describe the output’s activities and provide supporting narrative for the score.
Mainstreaming is supported by a GEDSI lead who is part of the central Alliance team, and national and sector-specific experts for the six DOs. Alliance programme staff have been trained on GEDSI, as have staff at two DPs, CI and TfL. The 45 DO work packages have been reviewed for GEDSI ambition and assigned a level. Of these, 32 (71%) have an expected level of L2 (Empowerment) or higher (none have been completed). The 11 TO work packages were assigned levels of ambition – strong examples include the Dar es Salaam Urban Resilience Project which was designed after wide consultation with marginalised groups. Four (40%) were assigned and achieved L2. Of the 3 Buy-ins, two were assigned and achieved L2. Of six UKEO work packages, three (50%) were assigned L2 and two had achieved it by year-end. The GEDSI Lens Toolkit for Infrastructure Project Developers was a product of the UKEO and has exceeded expectations in its reception. It will be used by GCIEP projects and has been shared within others in FCDO and GCIEP delivery partners. Peer reviewers included BII, InfraCredit, AfDB, ADB and IFC.
At project level, there has been a strong effort to mainstream GEDSI. This has not been straightforward, and it is early to know how well it will influence final policies and plans. For example, in the Philippines DO, we found a good level of GEDSI ambition embedded in the current versions of the feasibility studies and that UK agencies have made a strong effort to bring the right GEDSI expertise on board. The agreed vision and objectives of the TOD Framework ensure that future projects incorporate goals related to accessibility, equality, and social mobility. GCIEP’s work on the Water Tariff policy is focused on making the draft Water Bill more inclusive. However, it is too early to determine which specific GEDSI requirements will carry through to later project phases, as this will depend on continued advocacy and negotiations with stakeholders. Ongoing engagement will be particularly important for the TOD feasibility study to safeguard a GEDSI-compatible direction for the project. For enabling environment work, GEDSI goals are even further from implementation, but, if successful, the programme could deliver far-reaching impact.
We found evidence of mainstreaming at country level. In Indonesia, the GEDSI mainstreaming was kick-started through a workshop on the GEDSI Lens Toolkit for staff in the Bappenas (GoI) Infrastructure and Financing Directorate. In Zambia, stakeholders, including officials in the Ministry of Energy, described the impact of increased access to electricity for impact on women and girls. We also found a strong awareness of GEDSI in the sample of TOs included in the review. The specific needs of women were incorporated in the design of contracting for transport interventions in India. In Egypt, GEDSI criteria were applied to training participant selection, covering gender, ethnicity and disability. In DRC, GEDSI was incorporated into all aspects of the scoping work and into proposals for project work in three sectors.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
The programme has responded well to the three recommendations of the last AR. The GEDSI Strategy and Action Plan (Feb 2024) addressed the recommendation for impact metrics; it has systematically applied GEDSI assessments of all workstreams; and it has shared the GCIEP GEDSI strategy and approach within FCDO, including through a working group on GEDSI and infrastructure for social development advisers (SDAs). The GEDSI Lens Toolkit was presented to SDAs at their monthly meetings in December 2024 and January 2025. The Alliance held a workshop in February with FCDO infrastructure advisers to integrate GEDSI into the design of the ‘Alliance for Green Infrastructure in Africa’ (AGIA) programme. We recommend: enabling and incentivising the Alliance to achieve greater GEDSI impact through strengthened coordination with other delivery partners and; formalising a strategy to incentivise the Alliance to develop and further promote the GEDSI Lens Toolkit for uptake in the global infrastructure ecosystem.
The Alliance has demonstrated intention and capability to build on this in the year ahead through an internal community of practice and quarterly meetings with FCDO SDAs working on infrastructure and urban development. It has created a standalone GEDSI-focused workplan to ensure that GEDSI is incorporated into all its projects.

Output Title	CN&E is mainstreamed across GCIEP DO interventions and Target Offer (TO) work packages (WPs) (ICF compliance) (disag by DO and TO)
Output number:		5	Output Score:	A
Impact weighting (%):		15	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
5.1 Percentage of GCIEP-supported DO interventions/TO WPs that are mainstreaming CN&E (by DO and TO)	Target: 100%	Total: 100%
5.2 Percentage of total spend that is ICF compliant in relation to the total GBP value of GCIEP programmes – of eligible ODA percentage (by DO and TO)	Target: 80%	Total: 81.3%26 / DO: 87.7% / TO: 87.1% / Core Programme: 65%
5.3 Number of countries supported by ICF TA (ICF TA KPI 1)	Target: N/A	Total: 33 / DO: too early / TO: 33
5.4 Number of individuals supported by ICF TA (ICF TA KPI 2.1)	Target: N/A	Total: 661 / DO: too early / TO: 661
5.5 Number of organisations supported by ICF TA (ICF TA KPI 2.2)	Target: N/A	Total: 118 / DO: too early / TO: 118
5.6 Number of climate policies informed by ICF TA (ICF TA KPI 3)	Target: N/A	Total: 2 / DO: too early / TO: 2

Briefly describe the output’s activities and provide supporting narrative for the score.
The programme aimed to mainstream CN&E across DOs, TOs, and Buy-ins, resulting in 80% ICF compliancy across projects, against a target 80%. The six DO’s were 100% ICF compliant. A clear CN&E strategy, with a central team managing quality assurance across the portfolio to ensure alignment with this strategy, was important in finding and building on potential climate opportunities. There is also a clear mix of climate adaptation and mitigation, with a 50/50 split, and often both integrated in the same project.
A high level of ambition has been embedded with good examples across Deep Offers; in the Philippines the transport and water projects offer a strong focus on adaptation and mitigation. Specific CN&E measures include green building standards, renewable energy integration, and resilience to flooding and heat. In the water sector project, early assessments of environmental conditions and impact played a key role in shaping the intervention and elevating CN&E ambition.
This has also been seen in different contexts: in Ghana, mitigation measures include supporting variable renewable energy for a just and inclusive clean energy transition, while the urban project will improve the readiness of projects to leverage donor funding for climate adaptation investments in water security and green/grey infrastructure for flood resilience. However, Ghana has been less clear on the value of the climate finance measures due to mismatched expectations and a lack of clarity on delivery mechanisms, thus questioning the value of work even if it is labelled as ICF.
Furthermore, there have been certain instances where ICF has been recorded but in practice the level of ambition has not been applied consistently. In Indonesia support was given to Bappenas for priority projects selection. However, CN&E considerations were not properly integrated into the criteria, which resulted in GCIEP initially recommending oil and gas projects. This may be due in part to inconsistency of messaging from the central GCIEP team to local staff in country.
There are several examples of nature-based solutions (NbS) being considered and recommended through the programme. This has been predominantly in the water sector, with elements incorporated in the Philippines, Indonesia, Mozambique and Ghana. Notable exceptions beyond the water sector include Tanzania, where the Dar es Salaam Urban Resilience Project (DURP) which, for example, looks to transform waste into fibres for clothing and textiles.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
The Alliance increased its level of ambition for ICF from 30% to 80%, following a recommendation in the 2024 annual review. This better reflects the scope and objectives of the programme.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Due to recognised appetite from partner countries, the previous AR called for clearer strategic intent on accelerating climate action and higher ICF ambition from the start of design. To achieve this, they needed increased engagement with teams in the field to better support CN&E integration as well as further application of the ICF attribution tool to ensure improved CN&E assessment and integration across all ICF-tagged programmes. The ambition has mostly been met, but the application of the tool and engagement with local teams has led to varying quality of ICF reporting and mainstreaming.
A strength of the programme is the balanced mix of adaptation and mitigation objectives and the complementarity to work already taking place through other programmes, such as Partnering for Accelerated Climate Transitions (UKPACT).
In the next year, we recommend the quality assurance process is used to ensure CN&E work is on track to meet the commitments in ToRs. The programme should seek further opportunities for NbS beyond the water sector and do more to capture and share learning in this area.
Output Title	Learning (evidence) management and action learning mechanisms in place establishing GCIEP as an integrator of UK and international urban/infrastructure expertise in the global ecosystem
Output number:		6	Output Score:	A+
Impact weighting (%):		10	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
No. of GCIEP products (analysis and learning including events) that deliver insights which inform/shape FCDO policies and programmes (#)	No Target Set	53 products: / 5 GCIEP products / 22 DO products / 16 TO products / 10 UKEO products / 40 events / 3 GCIEP events / 20 DO events / 9 TO events / 8 UKEO events

Briefly describe the output’s activities and provide supporting narrative for the score.
Over the past year, GCIEP exceeded expectations on this learning Output. In total, 53 high-quality learning products including reports, studies, training packs, approach papers, and toolkits were prepared and disseminated in Africa, Asia, Europe, and virtually. Similarly, GCIEP led, facilitated or attended 40 different learning events including launches, webinars, workshops, and steering committee meetings across Africa, Asia, the Caribbean, and Europe. This included showcasing its work at the World Urban Forum (WUF) in Cario in November 2024. These activities represent a large jump over the previous year and helped raise the profile of the Programme and the UK with a wide variety of external stakeholders including national, regional and local governments, the private sector, academia, and multilateral and bilateral agencies. It also provided learning sessions for FCDO staff. This Output demonstrates GCIEP’s proactive approach to systematic learning and to sharing and deepening knowledge on important urban and infrastructure themes like climate resilience, sustainability, social impact, access to finance, and innovative tools and models. The only area this Output does not measure is the impact of these learning products and events. In future, some sampling of participants’ views would help gauge the quality and likely application of GCIEP learning activities.
In addition to the products and events listed above, GCIEP has developed an extensive learning framework over the past year. The new learning processes are designed to capture and disseminate evidence that improves project management and delivery for internal and external audiences. The list of processes includes i) quarterly learning cycles for each DO; ii) project completion learning sessions for TOs; iii) a thematic learning framework; iv) a learning library with hundreds of entries; v) a DO community of practice (CoP) with plans for a GEDSI one too; vi) knowledge sharing and learning sessions; vii) a GCIEP Knowledge Hub; viii) a compendium of deliverables with over 120 documents; and ix) GCIEP guidance notes for cross-learning. Not all learning processes have worked perfectly. The PwC Alliance Learning and Communications Team continues to address challenges as they arise.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
No changes were made.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
In the 2024/25 GCIEP AR, Output 6 had the following recommendation: For future TO bidding windows, more support will be needed to coach teams on what a learning product looks like, as well as when and how to create one. Regarding the CoE GCI, learning here holds potential. Communities of practice are planned, and other modes are likely to emerge as familiarity with delivery partner approaches to learning grows. In response, the Alliance developed a new GCIEP Learning Strategy and greatly amplified the number and quality of GCIEP learning products and events.
In the forthcoming Alliance review of the logframe, a new recommendation should be considered, to capture the effects of learning activities, e.g. by conducting sample surveys with product recipients and event participants to gauge the quality and likely application of new knowledge and learning acquired through GCIEP.

Output Title	CoST – The Infrastructure Transparency Initiative
Output number:		7	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 (a) Number of national or sub-national Infrastructure Transparency Index’s published	4	2 – ITI’s published in Uganda and El Salvador. / ITI’s for Malawi, Costa Rica, Ghana and Guatemala are expected to be published in the upcoming quarter.
3.1 (b) Number of updated and new technical guidance notes and manuals published	1	6
3.2 (a) Total number of stakeholders from (i) government, (ii) civil society (iii) private sector who are trained to disclose, validate and use infrastructure data	Total trained 1800 / (i) 1,200 / (ii) 500 / (iii) 100	Total trained 957 / (i) 439 / (ii) 428 / (iii) 90
3.2 (b) % of women from i) government, ii) civil society and media and iii) private sector trained to disclose, validate and use infrastructure data.	(i) 40% / (ii) 40% / (iii) 25%	(i) 40% / (ii) 39% / (iii) 47%
3.3 (a) Number of international and regional organisations endorse CoST and or incorporates CoST tools and standards into their frameworks	2	3
3.3 (b) Number and description of Invitations to participate at international and regional events to promote CoST tools and standards	20	16
3.4 (a) Percentage of technical visits, learning workshops and webinars carried out by the CoST IS that score good or very good in the feedback survey.	Average 90%	Average 98%
3.4 (b) Number of knowledge products (KP) that capture activities/results/lessons from implementing CoST that are disseminated.	4	2
3.5 Number of new sources of funding to support CoST IS activities.	1	2 / Inter-American Development Bank (extension) / US Department of State (extension)

Briefly describe the output’s activities and provide supporting narrative for the score.
CoST continues to demonstrate that it is improving the evidence and accuracy of data on infrastructure by supporting governments to publish data on 10,571 projects worth nearly $6bn in 2024-25. This compares to publishing data on 9,341 infrastructure projects in 2023/24, although it is below the target of 12,000.
Four out of nine targets were not achieved. First, the number of people trained by CoST members has been unusually low due to limited financial independence of members amid a challenging international fundraising environment. Second, only two Infrastructure Transparency Indexes were published, although it is noted that four more are in the pipeline for publishing in the next 2-3 months. Third, CoST was invited to participate in 16 international and regional events – more than the 15 attended in 2023/24 – but below the target of 20. Fourth, CoST published only two impact stories over the last twelve months. Despite these shortfalls, CoST continues to receive excellent feedback from beneficiaries. It also significantly exceeded its target for publishing new technical resources in collaboration with key international partners, reflecting a growing emphasis on knowledge products.
Notable achievements include:
- The President of Guatemala endorsed the establishment of a National Infrastructure Commission based on evidence presented in nine CoST Guatemala Assurance reports that highlighted delays, cost increases and procurement and contracting irregularities.
- The Thai Ministry of Finance reported budget savings of US$73 million in 2024 on the 2,591 infrastructure investments published using CoST data standards.
- CoST authored a World Bank study that has recently been published by International Finance Corporation on Promoting Transparency in Sustainable Infrastructure Procurement. Cost also contributed towards the publication of OECD’s Infrastructure Anti-Corruption Toolbox handbook funded by the US Department of State which supports the implementation of the anti-corruption criteria within the Blue Dot Network certification of quality infrastructure investments.
- The CoST Members Managers Workshop and CoST Awards demonstrate that CoST has established a global community of practitioners who are committed to improving infrastructure transparency.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
There were no changes to this output during the past year. This review proposes revising the 3.1(b) target upwards and 3.2(a) target downwards. This reflects the increasing focus of CoST on developing knowledge products and thought leadership.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Progress on previous recommendations
No stable FCDO funding has been identified for CoST, as it was contingent on Spending Review decisions that remain under consideration. To address this, the CoST plans to develop a comprehensive fundraising strategy as part of its new strategic plan. This strategy will focus on diversifying funding sources to reduce reliance on delayed donor disbursements and to ensure financial sustainability, programme continuity, and growth.
Lessons Learned
- Open Government Partnership regional meetings have proven valuable in engaging governments and civil society and in promoting consistent messaging on transparency and integrity in climate finance.
- Engagement with FCDO posts has been uneven – stronger in Latin America than in Africa. Support from posts is often critical during early-stage scoping and relationship-building.
- Most members no longer rely solely on CoST for funding. Many partners provide co-financing or in-kind contributions, such as staff time for data analysis and platform development. These contributions are often undervalued, and CoST aims to better capture them in future evaluations.
- While project-level support remains essential, there is a growing shift towards knowledge generation and thought leadership. CoST has expanded its portfolio of knowledge products, often in partnership with other organisations – a trend reflected in its upcoming strategic plan.
Recommendations:
- Identifying the added value of CoST tools and standards in the implementation of the GCIEP DO portfolio remains a challenge. FCDO and the Alliance should enhance CoST’s integration into GCIEP and strengthen engagement with FCDO posts.
- There is scope for CoST to strengthen its communications with non-technical audiences. Identifying and publishing clear, evidence-based impact stories would help improve public understanding of CoST’s role and value.
- FCDO intends to commission an external review of CoST. The findings will provide important insights and considerations for both FCDO and CoST as the programme evolves.

Output Title	The Public-Private Infrastructure Advisory Facility (PPIAF) demonstrates a contribution towards strengthening the enabling environment for private sector participation in infrastructure investment (which contributes to the GCIEP outcome of ‘Finance and investment is leveraged for sustainable and inclusive infrastructure and the built environment’).
Output number:		8	Output Score:	A
Impact weighting (%):		5	Weighting revised since last AR?	No

This output was established in the second GCIEP business case amendment. It is delivered as a separate, complementary component to the GCIEP Programme contract by the GCI Policy Team. There are no quantitative indicators.
Briefly describe the output’s activities and provide supporting narrative for the score.
The 2024/25 financial year was the first in which GCEIP provided funding, of US$2 million, as part of a trust fund.
PPIAF has a portfolio of US$14million and is funded and governed by a council of ODA donors/investors including the UK, Australia, Germany, Sweden, Netherlands, Singapore and Switzerland. The USA withdrew funding in February 2025. The UK uses its seat on the council to inform the workplan of technical assistance and to ensure it serves UK equities on climate and social inclusion, and to coordinate with GCIEP.
An independent evaluation in 2025 reported that PPIAF’s operational portfolio met all its policy targets. It had assisted 25 institutions and trained 635 government officials in project preparation. It contributed to the adoption of 15 new policies and regulations. Nine economies adopted PPIAF recommendations to meet their climate mitigation and adaptation policy targets. Examples include Pakistan, where it assisted to mobilise private capital through the amendment of the Public-Private Partnership Authority (PPP) Authority Act 2014 to enable enforcement of Fiscal Commitments and Contingent Liabilities guidelines; Cameroon, where the Government adopted Law No. 2023/008 to establish a regime for PPP contracts. The law integrated PPIAF’s recommendations to enhance legal harmonization, institutional oversight, project evaluation, risk allocation, and budgetary control.
All PPIAF activities have integrated climate equities. They have complemented UK bilateral assistance. For example, the GCIEP TO ‘Caribbean resilient infrastructure platform’ (UK ODA £216K), was coordinated with the PPIAF ‘Scaling up Renewable Energy Procurement in Eastern Caribbean’ project. It strengthens the legal and regulatory frameworks in Saint Lucia and Saint Vincent and the Grenadines. It has led to an update of the Electricity Supply Acts to enable competitive, transparent procurement.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

In September 2024 PPIAF merged with the World Bank’s ‘Global Infrastructure Hub’ that is the World Bank’s library for statistics and research on infrastructure. The merger has given PPIAF an important role within the multilateral system to provide independent evidence to inform G7 and G20 fora. For example, PPIAF developed a ‘Market Date Note’ for the G20 Infrastructure Working Group to inform discussion on a common definitional framework for infrastructure.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
PPIAF was not funded in 2023/2024.
Pending forthcoming FCDO funding decisions, we recommend the UK uses its seat to encourage PPIAF to increase collaboration with other project preparation facilities, such as the African Development Bank’s New Partnership for African Development (NEPAD) Infrastructure Project Preparation Facility.
## VALUE FOR MONEY

Key cost drivers and performance
The two key drivers for GCIEP are the daily rates (fees) of specialists and number of paid days. Fees accounted for 93% of total programme spend in Year 2, with the remainder allocated to travel and expenses, which remain a relatively minimal proportion and are carefully managed in line with the GCIEP expenses policy. The average daily rate paid by the Alliance was successfully kept down through adherence to the contracted rate card and by increasing the proportion of specialists recruited in-country and paid at national market rates. Agency rates fall outside the contract with the Alliance and are set within

VfM performance compared to the original VfM proposition in the business case
Overall, the cost-effectiveness of the programme is good, with the expected outcomes representing good value in relation to the total investment. As described above, the first full year of delivery demonstrated the programme’s ability to mobilise finance and bring about sustainable change within the enabling environment for green infrastructure development with embedded GEDSI principles.
Given the long-term nature of the programme, resource has been focused on creating and adapting the correct structures for management and quality assurance of the programme. The value for money can only be properly evaluated in the long term, but there is potential for significant gains; for example UKEO is delivering strong VfM by strategically investing in tools and delivery partnerships that generate transformative returns. By developing and promoting UK methodologies and mainstreaming CoE DPs across GCIEP, UKEO is beginning to demonstrate exceptional leverage and impact. The application of a GEDSI lens and the use of RCF tools, mentioned above, show high potential to improve project design and appraisal – enabling stronger development outcomes and making projects more attractive to finance. One notable advancement is the Whole Systems Approach to Energy update, which now provides step-by-step guidance for non-experts to apply systems thinking to energy projects.
Economy: The programme has demonstrated good economy, with systems for contracting staff and procuring services based on sound VFM principles. Cost savings have been found in-country through the use of Alliance member offices in Ghana, Vietnam and Indonesia, and through negotiating office-sharing agreements with local partners in Tanzania. Further savings were found in Mozambique, Philippines and Ghana by embedding advisers into government institution workspaces, which also resulted in more effective collaboration. Synergies have been found with previous FCDO programmes; in Zambia GCIEP builds on the Cities and Infrastructure for Growth (CIG) programme (a centrally managed programme that ran between 2018 and 2023, and was continued by the British High Commission in Lusaka), with the same staff used which builds relationships and trust as well as the sharing of resources. These cost-cutting efforts have been less apparent in the case of the UK Agencies. There is potential for reducing costs to FCDO by leveraging greater contributions from partner governments, particularly in Asia. The level of the contributions gained to date is not clear and should be more systematically monitored and recorded.
Close collaboration with Post also led to reduced venue-related expenses – for example, two UKCRIP-focused sessions were delivered during FCDO led Climate Finance Unit (CFU) in Jamaica, avoiding the venue and logistics costs associated with securing separate venues. Similarly, the Resilient Infrastructure Roundtable was hosted at the British High Commission in Barbados, allowing GCIEP to fully avoid venue hire costs while maintaining visibility and engagement with key stakeholders. However, the complexity of the programme, time constraints, and budget uncertainty has led to cases of increased management costs because of larger than expected teams, high staff turnover and recruitment challenges. VFM principles are well integrated in the UKEO procurement approach. Incorporation or design of new tools is dependent on evidence of demand and meeting set criteria for their likely level of transformational effect.
Efficiency: Completion of planned activity, supported by the adaptive management approach was good, with 89.6% of planned deliverables completed, against a milestone target of 70%. The feedback across DOs and TOs on the level of technical knowledge provided has been good. For example, the work in Ghana under the energy and urban pillars was recognised by stakeholders as having been effective and valuable, and they have requested continued collaboration. Efficiency has been affected by the hiring issues and in some cases, the spread of countries covered by the TOs, particularly in those with limited resource available at Post to manage and monitor the work.
While bringing in the UKEO further increases programme management and complexity, it was felt that this provides vital expertise, is well regarded by stakeholders, and provides an offer which sets us apart from other donors. To be fully effective it requires ongoing investment in relationship management and governance clarity, with more effective co-delivery models.
Coordination with PPIAF project proposals has increased the impact of GCIEP. The GCIEP Caribbean Resilient Infrastructure Platform was coordinated with the PPIAF Scaling up Renewable Energy Procurement in Eastern Caribbean project, leading to an update of the Electricity Supply Acts to enable competitive, transparent procurement. Sustainability is a core objective of PPIAF, making it a complementary partner for GCIEP to increase its reach.
Effectiveness: As well as the outcomes reported in Section A, seven of the Alliance-led workplans from Year Two have led to follow-up TOs, demonstrating the continued momentum towards further outcomes. Additionally, the India Mumbai intervention from CI with MMRDA was well received and is likely to deliver significant impact, on-going partnership and opportunities for UK infrastructure companies, meaning it is likely to have been highly cost-effective. There have been cases where effectiveness was below expectations due to the efficiency issues described above. The Five Case Model project in Egypt, for example, appears to have been too short and too limited to achieve uptake of outputs. The programme should do more to track the follow-on actions of completed TOs to ensure all GCIEP’s outcomes are properly recorded and reported.
The adaptive nature of the programme has allowed teams to pivot when work is ineffective or the context changes. Due to its adaptive approach, GCIEP was able to rapidly step in to support a US$292 million World Bank-supported Zambia–Tanzania electricity interconnector programme, following a last-minute withdrawal of small but critical US funding. GCIEP fast-tracked the approval of a vital biodiversity study with only weeks remaining before the wet season ended. However, in other instances there have been questions raised about the timeliness of such decisions, as with the OIKN intervention in Indonesia. It was also felt that this had been used to cover a lack of progress, as with the Climate Finance work in Ghana.
Equity: The programme has a systematic approach to mainstreaming GEDSI and has documented how each workstream is integrating GEDSI principles (see Output 4). UK agencies have also demonstrated a commitment to incorporating GEDSI, for example, TfL has a workstream in its Dhaka project to address the experience of women in the planned bus reforms. Social inclusion is a core objective of PPIAF, with inclusivity integrated throughout all its workstreams.
Assessment of whether the programme continues to represent value for money
The adaptive programming model is well-suited to the complex, multi-country nature of GCIEP. However, the need for better documentation and clearer governance structures was acknowledged, particularly in early phases and with other delivery partners. It is also important to consider if the checks and balances are proportionate; it was felt that the levels of quality assurance are sometimes too thorough, and delay progress. However, this needs to be managed with recommendations elsewhere in the report which indicate a lack of consistency in the quality of outputs.
The TOs should be kept under review given the complexity in delivery across different geographies, the impact on resource where Posts do not have the personnel or expertise, and the inability to properly measure the long-term impact of the intervention. The programme needs time to implement its expertise offer and the strategies that have been developed over the past year. There is also a need to mobilise quicker when starting interventions to ensure delivery is not rushed and quality is assured. But overall it represents value for money, with impacts often seen in the longer term with infrastructure programmes.
E: RISK
Overview of risk management
Risk is systematically and effectively managed at the centre by the Alliance through a refined and comprehensive risk management strategy. The strategy ensures that risk management is consistently integrated and evidenced into the culture of GCIEP. The strategy consists of several parts. The first is a live central programme risk register enhanced by separate risk registers for each DO, TO and UKEO project. The second is a monthly, formal risk management meeting between FCDO and the Alliance to evaluate programme risks as well as contractual risks around potential conflicts of interest, safeguarding, whistleblowing, duty of care and travel risks are also covered. The final part of the strategy is the GCIEP risk matrix which the Alliance updates regularly to ensure continued alignment with the risk management strategy. Over the past year, the strategy identified 48 new or emerging risks and removed 27 former ones. As part of the annual risk strategy refresh, several core risk related policies on safeguarding, anti-bribery and fraud, conflict of interest, and artificial intelligence were added or updated. Corresponding training sessions are being rolled out across the programme to keep staff fully informed of the new policies and guidance.
In practice, when programme risks appear, they are escalated and dealt with rapidly by the central Alliance team. Risk management in-country can be more varied. For example, in Ghana and Vietnam specific workstreams experienced unreported challenges which then affected VfM. This could have been mitigated through triangulation with government stakeholders. Going forward, a new arrangement is recommended whereby both Alliance managers and FCDO staff working in DOs contribute to quarterly progress monitoring with key government representatives.
In addition to the GCIEP risk management strategy, the FCDO team also keeps an internal risk register. Based on the original GCIEP business case, this register covers risks such as contract management, budget and political considerations. From the FCDO’s perspective, there has been a significant risk related to programme underspend. This stems partly from over-optimism on the timelines required for DO and TO project development and implementation. Since September 2024, the Alliance has mitigated this risk by providing Probability Adjusted Budgets and Forecasts, which are now used as the default standard. This has resulted in more accurate financial forecasts.
CoST risk management is considered through FCDO GCIEP programme management structures. CoST also discusses and updates its risk register and appropriate mitigations at each of its Board meetings.
The risk management strategy for PPIAF is aligned with FCDO principles and aims to reduce the key risk of duplication with GCIEP targeted offers. PPIAF shares its project proposals with FCDO to consult on a project’s merits and to object to a proposal, if the proposal is not aligned with FCDO priorities on climate change and social inclusion. PPIAF maintains a risk register at the project level, and consults FCDO at the quarterly partnership council meetings on the achievement against milestones and the threats and mitigating actions.
Some other examples of risks and mitigation measures, that GCIEP addressed over the past year include:
1. Heightened security risks in GCIEP partner countries including Mozambique, DRC, Bangladesh, and Ethiopia impacting on project activities. To mitigate this, the Alliance recruited an experienced Risk Specialist to strengthen programme-wide risk processes and to provide tailored support to project delivery teams operating in high-risk environments.
2. Programme delivery risk stemming from ODA budget reductions impacting the planning and delivery processes of GCIEP and CoST. For GCIEP, the main mitigation is flexible and adaptive programming which permits implementing teams to respond to evolving circumstances with agility. CoST is aiming to diversify funding sources and has successfully secured a 12-month grant agreement with US State Department.
3. Working in countries where Alliance members are not represented raises challenges in recruiting in-country expertise, particularly in countries where there are fewer people with the relevant expertise. This was addressed by partnering with local SMEs.
4. For CoST, high level government support in member or affiliate programmes is essential. A new membership policy has been agreed and will be further developed and monitored to target efforts to strengthen national uptake.
5. Within the FCDO programme team there were several important vacancies carried through most of the year, which affected the team’s capacity to coordinate between delivery partners, monitor outputs and act on lessons learned. Most of the posts have now been filled, which will allow these issues to be fully addressed in the coming year.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.
Programme management by the Alliance has been strong. In its second year, GCIEP consolidated its programme maturity, with a focus on strengthening, routinising and further establishing systems and processes to meet the increasing demands, pace of delivery and multi-sectoral delivery model.
The programme scaled up delivery where it had established itself in Year One and expanded at pace into new in countries and cities. The Alliance onboarded 546 specialists during Year Two. Mobilisation and localisation have been more effective where the Alliance has strong in-country presence. New portfolios were established, including UKEO, investment and Buy-ins. The design phase of the DO portfolio was a significant investment. Setting out clear theories of change and co-designing projects with FCDO were factors that ensured effective management of the process.
To enable GCIEP’s demand-driven approach, the programme retained a flexible central operating model, adapting throughout Year Two to meet evolving priorities and ensuring that lessons translate into real-time course corrections. The adaptive programming model remains a core strength but comes with a more complex programme management system. To address this, the Alliance improved its change control matrix, enabling faster decision making.
As the programme matured, GCIEP’s decision-making centre of gravity shifted to country level. This transition was further supported by improvements in financial management systems, which enabled country teams to make informed decisions about budget and resource allocation. Several core processes were further embedded to ensure consistency across delivery. These included the rollout of the GCIEP programme manual, the development of the GCIEP results monitoring handbook and the adoption of a unified ToR template across portfolios. These resources have contributed to a more coherent, consistent and routinised operating model as GCIEP has grown in complexity and scale.
Strong progress has been made in integrating UK agencies under a more unified GCIEP framework, but challenges were faced. The different types of expertise and ways of working of UK agencies took longer to integrate than the design period. An adequate level of integration was achieved during implementation. Continued improvement in delivery partner engagement, especially around roles and responsibilities, reporting and learning is needed.
Rigorous financial management has been a key priority during Year Two A monthly rolling forecast approach was successfully embedded across the programme, improving flexibility, supporting real-time decision-making, and enabling earlier identification of potential budget variances. As a result, forecasting accuracy improved significantly, with all relevant KPIs being met in the last quarter.
The process for managing changes using the change control matrix has not been followed in all cases by the Alliance. They have acknowledged this, and we would expect them to improve in the year ahead. The UK Agencies lead projects have also not always actioned agreed project change audit requirements. FCDO should carefully monitor compliance with the change controls and improve project change audit records.
FCDO received quarterly progress and finance reporting from CoST for FY24-25 and held auarterly meetings to discuss progress, delivery and risks. CoST also produced an annual report for FCDO that covered key results, lessons learned and reporting against the programme’s impact and outcome indicators.
The commercial relationship with PPIAF is managed through a World Bank Trust Fund. The risk of ‘payment ahead of need’ was reduced by UK funds being matched with specific PPIAF projects to be delivered within the financial year.
Looking ahead, long-term clarity on budget and strategic direction will be essential to sustaining and improving programme management performance.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation: The Alliance has put a robust monitoring and reporting system in place that is well integrated with the programme’s adaptive management approach. A logframe review for year 3 is planned and should consider adding percentage targets where possible, increasing the measurement of UKEO outputs, monitor the contributions made by partner governments, whether in-kind or financial and adjust the measurement of output 2 to better reflect UKEO and monitor the extent to which best practice is integrated into GCIEP outputs. UK agencies also use the programme indicators relevant to their work, although more consistency in this is required along with better integration into the overall Alliance logframe. Monitoring by FCDO is variable between countries, depending on capacity, although in general there is insufficient in-person monitoring. In some TO countries it was particularly weak (Egypt), while others are relatively well resourced (DRC). Asian DOCs have programme staff at Post (Indonesia, Vietnam, Philippines), while there are vacancies in Ethiopia (technical adviser) and Zambia (programme manager). Indonesia and Philippines have GCIEP technical advisers in place.
The contract and budget do not make provisions for an impact evaluation. While the impact of this programme will be in the long-term, the evidence base could be strengthened through an impact evaluation of legacy DFID infrastructure programmes. The FCDO MREL adviser has an objective to review the existing evidence of long-term impact and explore the potential of commissioning an impact evaluation of UK infrastructure spend over the past two decades.
The FCDO is procuring an independent evaluation of CoST that will consider the value of historical UK funding to date, its alignment with current FCDO priorities; and considerations for its future operating model in the context of reduced development funding. An independent evaluation of PPIAF of its 2025 portfolio reported positively on results and set out lessons learned across institutional and political factors, project design and implementation.
Evidence: The contribution of sustainable infrastructure and city development to economic growth and the barriers impeding it are well-evidenced in the original business case and are unlikely to have changed. The Alliance showed initiative in strengthening the evidence base by commissioning a rapid evidence review (January 2025). Country staff were generally able to refer to technical evidence that informed design, including local stakeholder knowledge (Philippines) and predecessor projects (Zambia). Agencies referred to evidence from recent experience of similar interventions elsewhere (Crossrail International in Mumbai). Knowledge of the operating context in DRC outside of Kinshasa informed a decision to focus only on the capital.
The programme builds on a legacy of UK ODA technical assistance to improve the enabling environment for infrastructure service delivery and urban development, exploiting a UK comparative advantage in this area, including a willingness for flexible and rapid funding. Despite this experience going back over 20 years, evaluative evidence of the long-term impact of UK spending in this area appears to be lacking.
Learning: Output 6, on learning, has a dedicated indicator showing a strong focus on learning by the central Alliance team. Learning sessions have also been organised between country teams and have included UK agency delivery partners. As the programme matures, there will be more to share and more to gain from doing so. Posts called for a more structured approach to this, while acknowledging the value of the informal learning that takes place (usually out of sight) between programme teams. Across FCDO, lessons have been shared, for example on the GEDSI toolkit, and voucher scheme model which was tested in the first round to TOs and discontinued thereafter.

Date of last narrative financial report	Alliance: 23 May 2025 / CoST: 14 June 2024	Date of last audited annual statement	Alliance: Expected by end July 2025 / CoST: 14 June 2024