## Definitions
Concept | Definition
Buy-in | Portfolio of work packages funded through bilateral country budgets that wish to opt into the GCIEP iniative, managed by the relevant Post. ​These WPs can be up to £1 million in budget
Targeted Offer (TO) | Portfolio composed of short-term work packages that address specific or immediate TA upstream (generally) demand, requested via Posts. This accounts for 25 per cent of the overall GCIEP programme budget.​
Deep Offer (DO) | Portfolio composed of longer-term, systemic interventions in selected GCIEP priority countries. This is the largest component, with approximately 75 per cent of the overall GCIEP programme budget allocated to it.​
Intervention (related to DO portfolio) | An intervention is a structured package of activities delivered under the DO portfolio in a given DOC country, designed to provide longer-term, systemic technical assistance in priority countries.
Work package (WP) (related to TO & Buy-in portfolio) | A work package is a structured set of short- to medium-term technical assistance activities, delivered under the Targeted Offer (TO) or Buy-in portfolios, to respond to specific or immediate demand. * A TO WP is centrally funded, demand-driven, short-term support (≈25% of budget). * A Buy-in WP is country-funded activities managed directly by Posts.
Centre of Expertise (CoE) delivery partner (DP) | The GCIEP Centre of Expertise deploys the UK’s expertise in infrastructure planning and inclusive urban development across a range of countries; the CoE’s eight delivery partners include: British Geological Survey (BGS), British Standards Institution (BSI), Connected Places Catapult (CPC), Crossrail International (CI), Ofgem, Ordnance Survey (OS), National Infrastructure and Service Transformation Authority (NISTA), and Transport for London (TfL).
Development partners | Non UK based multilateral or bilateral development agencies​
Gender, Equality, Disability & Social Inclusion (GEDSI) | GEDSI is fully mainstreamed across all GCIEP DOC interventions, TOs, and Buy-in work packages. GCIEP applies the Moser Framework (developed by Caroline Moser and the FCDO-supported ICED programme), which provides a structured and practical approach to translating FCDO’s GEDSI policies into programming. The framework helps assess how interventions and work packages can maximise benefits for disadvantaged and vulnerable groups, moving from minimum compliance to more ambitious and transformative approaches that build assets, capabilities, and opportunities for marginalised groups. At programme level, GCIEP’s target is for 50% of its work to align with Level 2 – Empowerment, going beyond basic compliance (Level 1) to actively build assets, skills, and employment opportunities, in line with FCDO’s GEDSI – Moser Framework. The Moser Framework Levels are: Level 1 – Minimum Compliance: addressing basic needs and vulnerabilities of women and marginalised groups. Level 2 – Empowerment: building assets, capabilities, and opportunities for women and marginalised groups. Level 3 – Transformation: addressing unequal power relations and seeking institutional and societal change.
ICF compliance target | GCIEP aims for 80% of the programme’s ODA budget to be compliant with International Climate Finance (ICF) requirements.​
Bankable project | A project that has been developed to a stage where it is considered financially viable and ready to seek investment or financing from banks, development institutions, or private investors. A project is deemed bankable when it has: * A clearly defined business case, including expected revenues and costs; * Demonstrated technical, financial, environmental, and social feasibility; * Appropriate risk assessment and mitigation measures in place; * Preliminary approvals or permits secured (where applicable); * Documentation of key project components (e.g. feasibility studies, financial models, term sheets, or investment memoranda).
Clean Energy (as per ICF KPI 2.1 Methodology Note on Number of people and social institutions with improved access to clean energy as a result of ICF) | Clean energy access refers to: • New household connections to off-grid renewable energy sources such as micro or mini-grids, or solar home systems • Households that use more efficient cookstoves that materially improve energy efficiency of essential services daily (e.g. air quality, reduced fuel consumption, fuel savings or improved family income) • Solar lamps and/or solar lanterns with or without chargers Note that on-grid access is not included in these figures because once energy access is on-grid, it is often difficult to determine the energy source. However, where the on grid energy source is known to be clean, we can report on clean energy access based on the on-grid renewable energy sources. Clean energy is generated from both combustible and non-combustible renewables. Non-combustible renewables include geothermal, solar, wind, hydro, tide, and wave energy. Combustible renewables include biofuels (biogas, bioethanol, biodiesel); biomass products (fuelwood, vegetal waste, pulp and paper waste, animal waste, bagasse); municipal waste (waste produced by the residential, commercial and public service sectors that is collected by local authorities for disposal); and industrial waste. It is generally not possible to disaggregate grid electricity by source (clean vs. fossil).
Direct Job | Full time or part time employment generated during the construction and operations and mantainance of an infrastructure asset, that is attributable to activities/projects supported by GCIP supported interventions.
Transformational change (as per ICF KPI 15 Methodology Note on Extent to which ICF intervention is likely to lead to Transformational Change) | Transformational Change is ‘change that catalyses further changes’, enabling either a shift from one state to another (e.g., from conventional to lower carbon or more climate-resilient patterns of development), or faster change (e.g., speeding up progress on cutting the rate of deforestation). However, it can entail a range of simultaneous transformations to political power, social relations, decision-making processes, equitable markets and technology. (extracted from ICF KPI 15 Methodlogy Note). GCIEP is designed to deliver a set of interlocking & reinforcing interventions which work together as a coherent Deep Offer Country (DOC) package to support transformational change. Transformation implies a ‘new state’, which for GCIEP interventions in DOC means that a country / city is characterised by one or all of the following transitions: * Sistemic change in the institutional, policy, and/or governance landscape that embed climate-smart behaviours with GEDSI focus in infrastructure and urban investments * Structural economic changes in processes, operations and financing mechanisms towards a low-carbon economy and green growth * A shift to a resilient infrastructure and urban environment that is able to withstand the adverse impacts of climate change
Mobilising finance (related to Outcome 1) | Non-GCIEP financing resources (in the form of debt, equity, grant or guarantees) mobilised/committed, forecast (quantified) or targeted by third parties (public or private sector) to projects, products, funds, financial instruments or initiatives where GCIEP has provided high quality, relevant and critical support in the form of technical assistance. GCIEP cannot claim 100% attribution for financing mobilized, but GCIEP is expected to contribute to mobilizing finance through 4 distinct pathways.
4 types of mobilising finance (related to Outcome 1): * Catalysed * Re-allocated * Unlocked * Facilitated | The GCIEP 4 pathways to mobilising finance are: CATALYSED: Catalyse investment because of directly leading on the incubation, design and/or implementation of financing products, funds, platforms or other financial mechanisms FACILITATED: Facilitate investment as a result of supporting the incubation, design and/or implementation of financing products, funds, platforms or other financial mechanisms led by other parties. UNLOCKED: Unlock investment into infrastructure projects as a result of providing critical support along the project development cycle. REALLOCATED: Provide support to reallocate investment from traditional grey infrastructure to incorporate green elements.
Enabling environment indicators * Informed​-related to Int. Outcome 3.1 * Approved-related to Outcome 2.1 * Adopted-related to Int. Outcome 3.1 | Influencing and collaboration is monitored via the uptake of relevant knowledge and evidence generated by GCIEP and/or its delivery partners, by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services. Indicators include: Outcome 2.1. APPROVAL: Formal endorsement of GCIEP supported policy/regulations/strategies/roadmaps/frameworks/institutional structures at FCDO partner countries by the beneficiary stakeholder (or the appropriate designated authority) Outcome 2.3. ADOPTION: The formal embedding and / or implementation of a GCIEP-supported structure, process, methodology or practices by FCDO partner countries, maintaining the core design and function of the original model, through minor contextual adjustments may be made. Linked to sustainability. Outcome 2: A deliverable is counted either as APPROVED or ADOPTED but not both, except in the case where GCIEP provides continious to support over time resulting in an evolution from APPROVAL to ADOPTION. In such execptional cases policy / regulations / strategies / roadmaps / frameworks / institutional structures may be reported at both level, usually for different years. Additionally, Int.Outcome 3.1 REVIEWED / ACCEPTED: Targets and results include deliverables that are REVIEWED/ ACCEPTED by the beneficiary stakeholder that are used as as source of evidence, insights, or recommendations to inform policies, strategies, or actions in FCDO partner countries. A deliverable is counted as reviewed/accepted when the client issues a letter/email stating that they have reviewed and are satisfied with the deliverable or there are meeting minutes recording that the deliverable has been shared with the client and they have no further comments. We make an assumption that stakeholders have commissioned GCIEP outputs to inform specific policies, strategies or actions, and that when they accept the output, the stakeholder will use it to inform that policy, strategy, or action. It is rarely possible (with the monitoring resources available) to know the actual degree of influence the output achieved.
Enabling environment indicators categories * Strategy & Planning * Legal & Regulatory Framework * Financial Mechanisms * Institutitional capacity & Governance * Networks & Partnerships | Across all the above indicators, GCIEP uses a five categories framework to classify different contributions to enabling environment improvements: Strategy & Planning (including decision making tools): Covers the approval of strategies, action plans, roadmaps, or analytical/decision-making tools that guide national or sectoral transitions; set priorities, define clear targets, and guide decision-making for sustainable and inclusive growth. Legal & Regulatory Framework: Refers to laws, regulations and standards formally approved to enable and enforce policy implementation across GCIEP TA supported sectors, providing certainty, and ensure compliance for implementing low-carbon and climate-resilient policies. Financial Mechanisms: Establishment of financial instruments and facilities that mobilize investment, reduce risks, and unlock public and private capital for climate and energy transitions. Institutional capacity & governance: Covers the creation of new organizations or entities and the strengthening of existing institutions to advance programs and initiatives. This also includes building their capacity and establishing or reforming governance structures and coordination mechanisms (e.g., dedicated agencies, inter-ministerial committees, regulatory bodies) to enhance transparency, accountability, cross-sectoral coordination, and effective policy delivery. Networks & Partnerships: Builds collaboration and coordinated action among key stakeholders—such as governments, international organizations, civil society, the private sector, and academia—to advance renewable energy, non-fossil fuel livelihoods, and energy access.
Learning or evidence produced by GCIEP: * Products * Events | PRODUCT: any knowledge, learning, or analytical written output produced or comissioned by GCIEP for the purpose of informing or influencing policies, programmes or practice. Includes: (i) Policy briefs, research reports, case studies, or technical notes; (ii) toolkits, guidance notes, frameworks or methodologies; (iii) published articles or blogs EVENT: any structured GCIEP supported convening aimed at sharing, generating or disseminating learning and evidence with stakeholders including FCDO, stakeholders in FCDO partner countries, development partners or wider ecosystem. Includes: (i) workshops, roundtables, or policy dialogues; (ii) regional meetings or thematic sessions; (iii) conferences or side-events where GCIEP presents or leads learning sessions; (iv) online / virtual learning events including webinars and panel discussions
Note on C17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Check definitions are against the right terms. Reallocated and facilitated are the wrong way round. Reply: Amended
Note on C18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Do we need a definition of reviewed/accepted? We are not counting the deliverables that have been accepted. Please remove this definition, and instead give a point of clarification, such as: “Approval of a deliverable is a step beyond its acceptance by a partner government point of contact. A deliverable can be accepted and can inform policy without being formally approved by a minister or committee. We do not record the number of ‘accepted’ deliverables. Instead, we record the number of polices, etc, that have been informed by deliverables (see intermediate outcome indicator 3.1). Reply: Now not relevant as we have agreed to change the relevant indicator wording in the LF. Instead we have included the evidence required to tag a deliverable as reviewed/accepted.

## GCIEP Y3 LF
PROGRAMME NAME: | Green Cities and Infrastructure a nd Energy Programme (GCIEP) Y3 Logframe (22 January 2026) - FOR APPROVAL
IMPACT 1 | Impact Indicator 1.1 |  | Baseline (2022) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Increased inclusive and low-carbon economic growth and enhanced climate resilience leading to poverty reduction (REPORTED ANNUALLY) | UNCTAD's Productive Capacities Index (PCI) (proxy for economic growth) | Planned - annual | Ghana (37.8) Philippines (43.8) Mozambique (29.5) Zambia (32.2) Indonesia (46.7) Vietnam (46.6) | N/A - programme kicked off no long term effects as of yet | Data for 2023 expected to be reported d by UNCTAD in September 2025 | N/A | * Political stability and no major deterioration in the investment climate in Deep Offer Countries (DOCs) *The international political economy is supportive of and receptive to infrastructure and urban development work
|  | Achieved - annual |  | Too early
Source
PCI: measures the economy from an input perspective across eight core components of productive capacities, capturing economic potential and highlights key areas for development policy focus. These are natural capital, human capital, energy (electricity), ICTs, structural change, transport, private sector and institutions, which are mapped using 42 indicators. https://unctad.org/news/unctad-launches-new-index-countries-better-measure-economic-potential https://unctadstat.unctad.org/datacentre/dataviewer/US.PCI
INTERMEDIATE IMPACT 1 | INT Impact Indicator 1.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Improved access to responsible, inclusive, low-carbon and climate resilient infrastructure services and urban services (DOC only and TO - if reported by Post) (REPORTED ANNUALLY) | Number of people with improved access to infrastructure services Disaggregation by gender and PWD (men/women) and youth (>25), infrastructure service (energy, transport, water, waste and sanitation, smart cities/digital) | Planned -annual | n/a | Too early | Too early | Too early | *Partner government continued support for: i) pro-poor, inclusive, low carbon and resilient objectives and targeted approaches; and ii) channel private and public investment into urban development and economic infrastructure *Improved urban services, amenities and public infrastructure stimulates national and regional integration, creates employment opportunities, and leads to economic growth *Results will be based only on DOC interventions; but GCIP will also report on results from TO work packages, in case there is GCIP contribution and results have been tracked either by GCIP or FCDO Post (post completion monitoring) *Targets will be set once the GBP million-value investment for specific projects and initiatives is forecasted. The associated methodologies will be determined on a case-by-case basis, likely relying on proxy multipliers and/or information from project development documents. Data sources related to access and jobs will be extracted from detailed designed/full feasibility studies from GCIEP supported projects. In these documents project developers/sponsors provide with expected improved/new access and jobs they expect to generate during the construction. Then once the infrastructure asset is built, we can update the data with REAL data, also provided by the project developer/sponsor.
|  | Achieved - annual |  | Too early | Too early
|  | Achieved - cumulative |  | Too early | Too early
Source
GCIP results monitoring (RM) and operational databases Note: Improved includes: new or improved access
| INT Impact Indicator 1.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of people and social institutions with improved access to clean energy as a result of international climate finance Disaggregation by disaggregated by gender and PWD (men/women) and youth (ICF KPI 2.1) | Planned -annual | n/a | Too early | Too early | Too early
|  | Achieved - annual |  | Too early | Too early
|  | Achieved - cumulative |  | Too early | Too early
Source
GCIP results monitoring (RM) and operational databases Note: Clean energy improved access refers to: i) New household connections to off-grid renewable energy sources (micro or mini-grids, or solar home systems); ii) Households that use more efficient cookstoves; iii) Solar lamps and/or solar lanterns with or without chargers https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/1139427/international-climate-finance-KPI_2_Methodology_Note_People_and_social_institutions_with_improved_access_to_clean_energy.pdf
| INT Impact Indicator 1.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Total megawatts (MW) of solar / wind / hydro / renewable energy generation capacity installed as a result of GCIEP TA Disaggregation by technology type (solar, wind, hydro), by location (country), by on-grid / off-grid | Planned -annual | n/a | Too early | Too early | Too early
|  | Achieved - annual |  | Too early | Too early
|  | Achieved - cumulative |  | Too early | Too early
Source
GCIP results monitoring (RM) and operational databases
INTERMEDIATE IMPACT 2 | INT Impact Indicator 2.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26)
Employment and livelihoods generated through enhanced economic opportunities (DOC only and TO - if reported by Post) (REPORTED ANNUALLY) | Number of direct (during construction and O&M) jobs created attributable to activities/projects supported by GCIP supported interventions (FTE) EXPECTED /REAL Disaggregation by gender and PWD (men/women) and youth (>25) | Planned -annual | n/a | Too early | Too early | Too early
|  | Achieved - annual |  | Too early | Too early
|  | Achieved - cumulative |  | Too early | Too early
|  | Source |  |  |  |  | RISK RATING
|  | GCIP monitoring and operational databases Note: Counts the people ‘directly’ employed (both on a temporary and permanent basis) in the construction, installation, operations, and maintenance of infrastructure services |  |  |  |  | MODERATE
INTERMEDIATE IMPACT 3 | INT Impact Indicator 3.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Progress towards climate-neutral, inclusive, resilient, and sustainable development pathways is accelerated via transformational change (DOC only) (REPORTED ANNUALLY) | Extent to which GCIEP programming is likely to lead to Transformational Change through the integration of climate-resilient design, low-carbon strategies, and environmental resilience best practices (ICF KPI 15) | Planned -annual | n/a | n/a (DOCs not operational) | 3 (baseline) | 4 | *GCIP defines, measures and assesses its contribution to transformational change whereas DOCs transition to a low Green House Gas (GHG) emissions economy with climate resilient and low carbon national infrastructure and an urban environment *Targets and results focus only on DOC interventions ICF KPI 15 Scoring criteria 1. Substantial evidence that suggests transformational change is unlikely or will not occur 2.Partial evidence that suggests transformational change is unlikely 3.Not enough evidence yet to assess, or the balance of evidence is inconclusive 4. Partial evidence that suggests transformational change is likely 5. Substantial evidence that suggests transformational change is likely or already occurring
|  | Achieved - annual |  | n/a (DOCs not operational) | 3
|  | Source |  |  |  |  | RISK RATING
|  | Annual assessment document prepared by an independent CN&E expert. It is a bottom up exercise taking DOC programmes ICF KPI 15 assessments. ICF KPI Methodology: https://assets.publishing.service.gov.uk/media/63fe28fb8fa8f527fb67caf8/international-climate-finance_KPI_15_Methodology_Note_Extent_to_which_ICF_intervention_is_likely_to_lead_to_transformational_change.pdf |  |  |  |  | MODERATE
OUTCOME 1 | Outcome Indicator 1.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Finance and Investment is leveraged for sustainable and inclusive infrastructure and the built environment (DOC only and TO - if reported by Post) (REPORTED ANNUALLY) | Total volume of non-GCIP financing mobilised as a result of GCIP interventions (£ ) Disaggregation by: type of funding organisation (Private/Donor/Public -National/Municipal), financing categories (catalysed, facilitated, unlocked, and reallocated) To track off logframe, GCIP country programmes where non-FCDO funds have been leveraged downstream | Planned -annual | n/a | Too early | Too early | If the following three projects reach financial close, the total would be £282M. DOC Ghana: ££132M £120M Sekondi-Takoradi Metropolitan Area (STMA) project & £12M Wa Water project (Phase 2) TO: £150 million (GetFiT- legal support for the financing of 120 MW for 6 solar projects in Zambia) | *GCIP TA makes a contribution towards facilitating investment into urban economic infrastructure projects and overcoming obstacles to project delivery *Partner government continued support for: i) pro-poor, inclusive, low carbon and resilient objectives and targeted approaches; and ii) channel private and public investment into urban development and economic infrastructure *Target and Results will be based only on DOC interventions; but GCIP will also report on results from TO work packages, in case there is GCIP contribution and results have been tracked either by GCIP or FCDO Post (post completion monitoring) * COMMITTED refers to: The financing quantified has already been committed/mobilised by other investors, where GCIP TA is being used to make the investment “bigger, better or faster."
|  | Achieved - annual |  | Too early | £885 million (£800 million - CEP of NaBFID in India and $110 million (£85 million) from DURP In Tanzania) | £12M grant from DANIDA as a result of the Wa water project feasibility study completed by GCIEP (DKK100M) - November 2025
|  | Achieved - cumulative |  | Too early | £885 million
Source
GCIP DOC and TO RM databases Note: £1bn committed is expected to come from: TO Zambia (Get FIT): £150m; and TO Tanzania buy-in (SWM): $110m); Ghana Water and Transport (EU): EUR 100-130 m; CEP (India) £800m
| Outcome Indicator 1.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Volume of public finance mobilised for climate change purposes (£) (as a result of GCIP interventions ) (disag by new financing vs reallocated financing) (ICF KPI 11) | Planned -annual | n/a | n/a | n/a | n/a: ICF KPI methodology only allows actuals to be reported
| ICF KPI 12 Volume of private finance mobilised for climate change purposes | Achieved - annual |  | n/a | £885 million (£800 million - CEP of NaBFID in India and $110 million (£85 million) from DURP In Tanzania) | £12M grant from DANIDA as a result of the Wa water project feasibility study completed by GCIEP (DKK100M) - November 2025
|  | Achieved - cumulative |  | n/a | £885 million
Source
GCIP RM databases and ICF monitoring ICF KPI Methodology: https://assets.publishing.service.gov.uk/media/5b17935be5274a190c1b6f8c/KPI11-Public-finance-Updated-methodology.pdf
| Outcome Indicator 1.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Volume of private finance mobilised for climate change purposes (£) (as a result of GCIP interventions) (ICF KPI 12) | Planned -annual | n/a | Too early | n/a | n/a: ICF KPI methodology only allows actuals to be reported
| ICF KPI 12 Volume of private finance mobilised for climate change purposes | Achieved - annual |  | Too early | 0
|  | Achieved - cumulative |  | Too early | 0
|  | Source |  |  |  |  | RISK RATING
|  | GCIP RM databases and ICF monitoring ICF KPI Methodology: https://assets.publishing.service.gov.uk/media/65e0b9913f6945001d036030/KPI-12-volume-private-finace-mobilised.pdf |  |  |  |  | MODERATE
OUTCOME 2 | Outcome 2.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
GCIEP TA contributed to a stronger enabling environment in FCDO partner countries for the provision of climate resilient&inclusive infrastructure services (REPORTED ANNUALLY) | APPROVAL: Number of approved policies/regulations/strategies/roadmaps/frameworks/institutional structures at FCDO partner countries supported by GCIEP TA (disag by DOC and TO including Buy-in) (disag by Strategy & Planning, Legal & Regulatory Framework, Financing Mechanisms, Institutional capacity & governance, Networks & Partnerships) | Planned -annual | n/a | n/a | 1 TO Ukraine: Cabinet decree passed mandating the use of the 5CM for all infrastructure business cases in the 2025 budget year. | If all the intended EE changes progress, then there would be 5 cases of strengthened enabling environment across 4 countries. DOC Ghana: 1 (Phase 1) DOC Mozambique: 1 (Phase 1) & 2 (Phase 2) DOC Zambia: 1 (Phase 1) TO&Buy-In: 1 (GetFit Zambia) | *Central FCDO and country offices are open to learning from and being influenced by GCIP generated knowledge - when relevant * Collaboration with CoE DPs collaboration increase urban and infrastructure effectiveness leading to local adoption and replication * No material change in government priorities with any political changes in countries that undergo national elections * Deliverables can include policies, regulations, roadmaps, strategies, frameworks, institutional structure / governance report, etc. that have been submitted/reviewed/accepted/approved by the beneficiary stakeholder/s (depending on country context) * APPROVAL: Formal endorsement of GCIEP supported policy/regulations/strategies/roadmaps/frameworks/institutional structures at FCDO partner countries by the beneficiary stakeholder (or the appropriate designated authority) * ADOPTION: The formal embedding and / or implementation of a GCIEP-supported structure, process, methodology or practices by FCDO partner countries, maintaining the core design and function of the original model, through minor contextual adjustments may be made. A deliverable is counted either as APPROVED or ADOPTED but not both, except in the case where GCIEP provides continuous to support over time resulting in an evolution from APPROVAL to ADOPTION. In such exceptional cases policy/regulations/strategies/roadmaps/frameworks/institutional structures may be reported at both level, usually for different years.
|  | Achieved - annual |  | 2 TO Egypt EERA- improved wheeling regulations TO Pemba MoZ - Urban Structured Plan approved | 3 DOC Vietnam: National Assembly Resolution 188 on urban rail and TOD passed in February 2025 DOC Zambia: Fast track procurement process approved by the Steering Committee, including Ministry of Energy and other stakeholders TO Ukraine: Cabinet decree passed mandating the use of the 5CM for all infrastructure business cases in the 2025 budget year | DOC Ghana 1.M&E Plan to monitor implementation of the national urban policy approved (Phase 1) DOC Mozambique 2. National Climate Finance Strategy and Roadmap approved by Council of Ministers (Phase 1) - achieved earlier than expected, moved from IO 3.1 3. Urban Municipal Observatory in Pemba launched and operational (Phase 1) 4. Urban detail plan to inform urban planning in the Mucurungo Miquejo area approved by the Municipal Assembly (Phase 1) - moved from IO 3.1 5. Detailed design plans for the 2 pilot areas approved by the Municipal Assembly in Pemba - moved from IO 3.1 6. Nacala Urban Structured Plan informing urban planning approved by the Municipal Assembly (Phase 1) - moved from IO 3.1 DOC Zambia 7. A one-stop service for energy sector to streamline multiple approval energy-related processes into a single, integrated workflow is further-improved (Phase 1) 8. Analysis to Power Sector Incentives informing a new tax incentive regime for independent power producers approved by the Office for Promoting Private Power Investment (Phase 1) - achieved earlier than expected, moved from IO 3.1 DOC Indonesia 9-10. Flood management practices: Two flood Risk Assessments reports for Surabaya and Denpasar approved by respective city governments (Phase 1) - approvedd earlier than expected, moved from IO 3.1
|  | Achieved - cumulative |  | 2 | 5
Source
GCIP L&C tracking tool, GCIP K&L documentation
| Outcome 2.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| ADOPTION: Number of GCIEP supported policies/regulations/strategies/roadmaps/frameworks/institutional structures adopted as evidence of GCIEP legacy / sustainability in GCIP supported entities (sustainability) (disag by DOC and TO including Buy-in) (disag by Strategy & Planning, Legal & Regulatory Framework, Financing Mechanisms, Institutional capacity & governance, Networks & Partnerships) | Planned -annual | n/a | Too early | Too early | If all the intended EE changes progress, then there would be 3 cases of strengthened enabling environment across 3 countries. DOC Mozambique: 1 (Phase 2) DOC Indonesia: 1 (Phase 2) DOC Vietnam: 1 (Phase 2)
|  | Achieved - annual |  | Too early | 0 | DOC Ghana 1. Energy planning: DIgSILENT Power Factory software adopted by GRIDCo following the 10-day training provided by GCIEP (GRIDCo spent ~£250K to acquire the software) (Phase 1) 2. EU-funded Ghana Urban Observatory: Risk and hazard screening report and risk maps for each of the 9 cities designed and operationalised - (Phase 1) - achieved earlier than expected, moved from IO 3.1 DOC Indonesia 3. Project Funding and Financing Options Framework version 1 adopted by Bappenas (Phase 1) - achieved earlier than expected, moved from IO 3.1 DOC Vietnam GCIEP inputs adopted by the regulators to approve: 4. HCMC Transport Oriented Development (TOD) Resolution nº 38 guiding implementation of Article 6 of National Assembly's Resolution 188 related to TOD development was passed by the HCMC People's Council (August 2025) - Moved from Int. Outcome 3.1 as per achieved earlier than expected. 5. Hanoi TOD Resolution 15 was passed by the Hanoi City People's Council (November 2025) (including also GCIEP inputs to former Resolution 16 which has now been integrated under Resolution 15) - Moved from Int. Outcome 3.1 as per achieved earlier than expected
|  | Achieved - cumulative |  | Too early | 0
|  | Source |  |  |  |  | RISK RATING
|  | GCIP RM databases and Intervention Pathways Packages at the intervention level |  |  |  |  | MODERATE
Y3 Interim PLF (August 2025) the following indicators were considered obsolete in agreement with FCDO: * Outcome 2.2 Replication: Number of GCIEP supported structures, processes, and / or methodologies replicated (and adapted) by country government ministries
INTERMEDIATE OUTCOME 1 | INT Outcome Indicator 1.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
GCIEP DOC programmes are effectively delivered using a demand-drive adaptive approach, based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development. (REPORTED ANNUALLY) | A) Increase in scope: Percentage of DOC interventions that have increase their scope since the start of the programme - CUMULATIVE (total number of DOC interventions scaled up / total number of DOC interventions) B) Closed / curtailed: Percentage of DOC interventions closed and / or curtailed since the start of the programme - CUMULATIVE (total number of DOC interventions closed or curtailed / total number of DOC interventions) C) New DOC interventions: Total number of DOC interventions introduced based on learning during GCIEP implementation phase Disaggregation by DOC | Planned -annual | n/a | Too early | n/a | n/a | *GCIP can effectively target its assistance, to choose the right agencies/municipalities and/or institutions with which to partner and select and test the adequate interventions * GCIP has in place the Impact Pathway packages to monitor DOC interventions applying adaptive programming principles *No material change in government priorities with any political changes in countries that undergo national elections * Well prepared projects (including feasibility studies) supported by GCIP will attract the necessary downstream financing. *Int. Outcome 1.1: Targets (n/a):Targets are not applicable, as we are a demand driven programme working under adaptive programming principles
|  | Achieved - annual |  | Too early | a) 2 DOC Ghana GH01 Climate Finance & DOC Vietnam VN02 TOD b) 2 DOC Indonesia ID03 OIKN & VN01 Green Cities c) 1 DOC Mozambique MZ04 Nacala | c) Ethiopia (3), Ghana (3), Mozambique (3), Zambia (2), Indonesia (3), Philippines (2), Vietnam (1)
|  | Achieved - cumulative |  | Too early | a) 2 b) 2 c) 1
Source
GCIP RM databases and Intervention Pathways Packages at the intervention level Phase 1 interventions treated as scaled up for Phase 2
| INT Outcome Indicator 1.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) Disaggregation by DOC Disaggregated by stage of the infrastructure development cycle: (I) Project pipeline and (II) Project specific support including (a) Planning & preparation (concept note, business cases, (pre) feasibility studies); (b) Financing structuring (project development agreement, investment round tables etc); (c) Commercial and financial close; (d) Procurement; and (e) Implementation | Planned -annual | n/a | Too early | Too early | Target:80% DOC Ethiopia: 2 (Phase 2) DOC Ghana:11 (6 Phase 1 & 5 Phase 2) DOC Mozambique: 9 (7 Phase 1 & 2 Phase 2) DOC Zambia: 2 (1 Phase 1 & 1 Phase 2) DOC Indonesia: 1 (Phase 2) DOC Philippines: 2 (1 Phase 1 & 1 Phase 2) PH02 TOD WS2 (CI led) i) Feasibility Study (FS) - a viable/deliverable scheme developed to balance key stakeholder requirements and comply with NEDA Board ICC Guidelines ii) Approval of the FS scheme by landowner Department of Education (DepEd) and key stakeholder Department of Transportation (DOTr)
|  | Achieved - annual |  | Too early | I. Project Pipeline: 2 DOC Zambia: ZM01 Prioritised renewable energy pipeline of 40 solar projects based on GCIEP analysis reviewed by Office for Promoting Private Power Investment DOC Indonesia: IN02 WS1a (Support to Surabaya on Visioning and Project Prioritisation): Pipeline of prioritised urban mobility projects arising from the SUMP based on joint analysis with stakeholders through capacity building workshops | I. Project Pipeline: 4 DOC Ghana 1. VRE Project pipeline developed (Phase 1) DOC Mozambique 3. GCF country programme report for MoZ reviewed/accepted by the CFU (Phase 1) 4. GCF multi-year readiness proposal reviewed/accepted by the CFU (Phase 1) 5. Portfolio of investments reviewed/accepted by the Pemba Muncipality II. Project specific support: 9 DOC Ghana 1. Project Preparation Facility feasibility study accepted (Phase 1) 2. 12,500m2 biogas plant (DasBiogas and Accra Metropolitan Assembly); 75 MW wind power in Keta Municipality (VRA Ghana); 5,000 capacity student complex at Kwame Nkrumah Univ. of Science and Technology in Kumasi (Nilex): Three scoping Briefing notes for project preparation to feed into the PPF accepted by FCDO (Phase 1) 3. Akuse Floating PV Plant: Pre-Feasibility study accepted by GRIDCo (Phase 1) 4. Sawla PV Plant: Pre-Feasibility study accepted by GRIDCo (Phase 1) 5. Wa Water: Feasibility study accepted by DANIDA and Gvt of Ghana (Phase 1) DOZ Mozambique 6. Green Energy project : Strategic Outline business case (SOBC) reviewed/accepted by the Municipality 7. Green Urban Park project: SOBC reviewed/accepted by the Municipality 8. Bypass Green Road project: Concept Note reviewed/accepted by the Muncipality 9. Miramar park project: Business Case reviewed/accepted by the Muncipality
|  | Achieved - cumulative |  | Too early | 2
Source
GCIP RM databases and Intervention Pathways Packages at the DOC intervention level Note: High quality equals to projects that have mainstreamed GEDSI and CN&E GCIEP DO C supported projects/initiatives along the infrastructure development cycle: (a) Planning & preparation (project pipelines, concept note, business cases, (pre) feasibility studies); (b) Financing structuring (project development agreement, investment round tables etc); (c) Commercial and financial close; (d) Procurement; and (e) Implementation
INTERMEDIATE OUTCOME 2 | INT Outcome Indicator 2.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26)
High quality TO and buy-ins support is successfully contributing to improving the enabling environment and project pipeline for infrastructure investment and economic development (REPORTED ANNUALLY) | Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritized, sequenced or developed (includes signposting stage of the infrastructure development cycle) Disaggregated by stage of the infrastructure development cycle: (I) Project pipeline and (II) Project specific support including (a) Planning & preparation (concept note, business cases, (pre) feasibility studies); (b) Financing structuring (project development agreement, investment round tables etc); (c) Commercial and financial close; (d) Procurement; and (e) Implementation | Planned -annual | n/a | n/a | 0 | Target: 80% I. Project Pipeline: 3 TO: 2 Buy-in:1 I. Project specific support: 6 TO: 2 Buy-In: 4
|  | Achieved - annual |  | 0 | 0 | 1. Surabaya urban mass transit feasibility study reviewed/accepted by Post /client (TO Indonesia)
|  | Achieved - cumulative |  | 0 | 0
Source
GCIP monitoring and operational databases
| INT Outcome Indicator 2.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Percentage (and number into brackets) of follow on TO and Buy-ins WPs (repeat business as a result of stakeholder satisfaction or and FCDO strategic interest) Disaggregation by: Portfolio (TO and Buy-in), delivery partner (Alliance and CoE DP) | Planned -annual | n/a | n/a | n/a | n/a
|  | Achieved - annual |  | 13 (9 completed WPs integrated into DOCs; 4 WPs with follow on WPs) | 7 | 13 buy-ins across 9 unique countries = 5 repeted buy-in (2xSA, 1xUkraine, 1xDRC, 1xJordan)
|  | Achieved - cumulative |  | 13 (9 completed WPs integrated into DOCs; 4 WPs with follow on WPs) | 20
|  | Source |  |  |  |  | RISK RATING
|  | GCIP monitoring and operational databases Note: Follow on TO WPs can also be under DOC Programme |  |  |  |  | MODERATE
INTERMEDIATE OUTCOME 3 | INT Outcome Indicator 3.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Influencing and collaboration Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services (REPORTED ANNUALLY) | INFORMING DECISION MAKING: Number of potential policies/regulations/strategies/roadmaps/frameworks/institutional structures at FCDO partner countries that have been informed with GCIEP TA. (disag by DOC and TO including Buy-in) (disag by Strategy & Planning, Legal & Regulatory Framework, Financing Mechanisms, Institutional capacity & governance, Networks & Partnerships) | Planned -annual |  |  | n/a | Target: 80% DOC Ethiopia: 2 (Phase 2) DOC Ghana: 2 (Phase 1) DOC Mozambique: 13 (7 Phase 1 & 6 Phase 2) DOC Zambia: 11 (5 Phase 1 & 6 Phase 2) DOC Indonesia: 13 (8 Phase 1 & 5 Phase 2) DOC Philippines: 3 (1 Phase 1 & 2 Phase 2) DOC Vietnam: 10 (7 Phase 1 & 3 Phase 2) DOC Philippines: PH02 TOD﻿ WS1: Proof of Concept TOD Implementation framework accepted by Philippines DOTr PH02 TOD WS2: Senate DepEd site pilot study - TOD masterplan accepted by Philippines DOTr and DepEd TO: 13 Buy-In: 8 | * Central FCDO and country offices are open to learning from and being influenced by GCIEP generated knowledge - when relevant . * Deliverables can include policies, regulations, roadmaps, strategies, frameworks, institutional structure / governance report, etc. that have been submitted/reviewed/accepted/approved by the beneficiary stakeholder/s (depending on country context). *Targets and results include deliverables that are REVIEWED/ ACCEPTED by the beneficiary stakeholder that are used as source of evidence, insights, or recommendations to inform policies, strategies, or actions in FCDO partner countries.
|  | Achieved - annual |  |  | DOC Zambia Recommended fast track procurement approach accepted/reviewed by MoE DOC Indonesia PSN Criteria and dashboard for determining National Strategic Projects (PSNs) accepted | DOC Ghana 1. Decision-making framework for identifying areas of the grid suitable for VRE interconnection accepted by GRIDCo (based on GRIDCo pipeline) (Phase 1) 2. Procurement framework for grid-connected VRES in Ghana accepted by GRIDCo(Phase 1) DOC Mozambique 3. Financial and Investment Public Assessment (PEFA & PIMA) concluded to inform municipal financial and investment decision-making (Phase 1) 4. Detailed design plans to inform urban planning in Metula and Maringhana areas in Pemba reviewed/accepted by the Muncipality (Phase 1) 5.Strategic approach on O&M for Coastal Protection to suppport communities improve coastral protecion infrastructure reviewed/accepted by the Municipality 6. Manual for Community Evacuation Planning in Case of Cyclones and Floods for Beira Municipality eviewed/accepted by the Municipality DOC Zambia 7. 100 MW suite of solar projects: Recommended Legal Risk Allocation Structure for solar power accepted/reviewed by the Office for Promoting Private Power Investment (Phase 1) 8. 100 MW suite of solar projects: Fast track procurement approach recommendations for solar projects (including detail on RfP structure, content, adjudication process, and credit support structure) reviewed/accepted by the MoE 9.Recommended Policy, Legal, and Institutional framework for energy procurement to inform public procurement reviewed/accepted by FCDO Zambia and submitted to the Ministry of Energy (Phase 1) 10. Final recommendation of procurement process reviewed/accepted by Permanent Secretary at the Ministry of EnergyWS5 Energy Sector Financial Sustainability (Phase 1) DOC Indonesia 11. PSN Criteria and dashboard for determining National Strategic Projects (PSNs) accepted (Phase 1) 12. Standarised SUMP appraisal framework with accompanying Governance and Operations Manual accepted by Bappenas following pilot application with Surabaya provincial level governement & relevant capacity building (Phase 1) 13. Selected transit line in Gerbangkartosusilo (GKS+): High -level TOD Roadmap reviewed/accepted by Bappeda East Java Province (Phase 1) 14. National Level Legislative Recommendations Report accepted by East Java Economic Bureau (Phase 1) 15. Integrated transport authority in GKS+: Institutional Roadmap accepted accepted by East Java Economic Bureau(Phase 1) DOC Philippines 16. Viability assessment emerging from piloting Regulatory Asset Based (RAB) water tariffs and lifeline pricing in three selected water districts is accepted by relevant Local water districts, LWUA, and Department of Environment and Natural Resources (DENR) (Phase 1) DOC Vietnam 17. Hanoi:Strategic framework for structuring TOD projects reviewed/accepted by MRB (Phase 1) 18. HCMC: trategic framework for structuring TOD projects in HCMC reviewed/accepted by HCMC authorities (adapted from Hanoi following extensive stakeholder consultation to contextualise it to HCMC) 19. Hanoi: TOD financing mechanisms and recommendations (to inform final inputs on resolution 17) reviewed/accepted by MRB (Phase 1) 20. HCMC:TOD financing mechanisms and recommendations reviewed/accepted by HCMC Department of Construction (Phase 1) 21. HCMC:TOD Resolution guiding Article 9 of National Assembly's Resolution 188 related to TOD development as a result of GCIEP support is reviewed/accepted by Department of Construction / Department of Planning and Architecture and taking for consultation with HCMC People's Council (Phase 1)
Achieved - cumulative
|  | Source |  |  |  |  | RISK RATING
|  | GCIEP monitoring and operational databases |  |  |  |  | MODERATE
INTERMEDIATE OUTCOME 4 - NEW | INT Outcome Indicator 4.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
DOC interventions/ TO work packages (WPs) have successfully integrated GEDSI risks and opportunities resulting in Empowerment (REPORTED ANNUALLY) | % of DOC interventions/ TO work packages (WPs) that include GEDSI considerations in accordance with Level 2 - Empowerment - as per the FCDO GEDSI framework (realised target ambition) - Linked to Output 4 | Planned -annual |  |  | 50% | 50% | *Resources at DOC and TO level are deployed to ensure that GEDSI is effectively mainstreamed during implementation, regularly identifying and assessing GEDSI risks and opportunities
|  | Achieved - annual |  |  | 88.8% (from completed TO WPs)
|  | Source |  |  |  |  | RISK RATING
|  | GCIP GEDSI monitoring; GCIP deliverables TOR and GCIP work package progress reports Note: it only applies to interventions that have GEDSI potential |  |  |  |  | MODERATE
OUTPUT 1 | Output Indicator 1.1 (c) |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26)
High-quality TA deliverables completed by GCIP for FCDO posts to facilitate economic transformation and inclusive growth (in line with VfM targets) (REPORTED QUARTERLY) | DOC Implementation: Number of active GCIP DOC programmes in implementation (# of countries that started mobilisation) Y3 disaggregation: by country and intervention | Planned -annual | n/a | n/a | 6 | 7
|  | Achieved - annual |  | Too early | 6
|  | Achieved - cumulative |  | Too early | 6
Source
GCIP monitoring and operational databases
| Output Indicator 1.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| DOC Percentage of the activities planned at the start of each quarter that are completed. Disaggregation by DOC | Planned -annual | Planned activities to be completed as per workplan submitted to FCDO at the start of the quarter | n/a | 70% | 70%
|  | Achieved - annual |  | n/a | DOC Ghana: 90.1% DOC Mozambique: 79.1% DOC Zambia: 89.2% DOC Philippines: 88.7% DOC Indonesia: 95.8% DOC Vietnam: 88.6%
Source
GCIP DOC intervention workplans Note: Total number of activities completed during the quarter / total number of activities planned to be completed as per workplan submitted to FCDO at the start of the quarter. It is expected that the activities detailed (and related deliverables) in the intervention workplan will be updated on a quarterly basis in line with adaptive management best practice.
| Output Indicator 1.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Targeted-offer & Buy-ins Number of TO and buy-in work packages completed and submitted for approval (#) Disaggregation by: portfolio (TO and Buy-ins), budget type (ODA, non-ODA, combined) | Planned -annual | n/a | n/a | n/a | n/a
|  | Achieved - annual |  | 18 (14: ODA; 4-non ODA) | 11 (9 ODA, 1 non ODA, 1 combined)
|  | Achieved - cumulative |  | 18 (14: ODA; 4-non ODA) | 29 (23 ODA, 5 non ODA, 1 combined)
Source
GCIP monitoring and operational databases
| Output Indicator 1.4 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Targeted-offer & Buy-ins Percentage of the deliverables planned at the start of each quarter that are completed. Disaggregation by: portfolio (TO and Buy-ins), budget type (ODA, non-ODA, combined) | Planned -annual | n/a | n/a | 70% | 70%
|  | Achieved - annual |  | n/a | 90.3% (89.4% ODA, 95.8% non ODA, 75% Combined)
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
40% |  | GCIP monitoring and operational databases Note: Total number of deliverables completed during the quarter / total number of deliverables planned to be completed as per workplan submitted to FCDO at the start of the quarter. It is expected that the deliverables detailed in the TO& Buy-in workplan will be updated on a quarterly basis in line with adaptive management best practice. |  |  |  |  | MINOR
Y3 Interim PLF (August 2025) the following indicators were considered obsolete in agreement with FCDO: * Output Indicator 1.1 (a) DOC Scoping: Number of active TA deliverables to scope proposed GCIP DOC programmes (# scoping reports) * Output Indicator 1.1 (b) "DOC Detailed Design: Number of active TA deliverables to undertake detailed design of proposed GCIP DOC programmes (# of DOC interventions)
OUTPUT 2 | Output Indicator 2.1 | GCIP monitoring and operational databases Note: Total number of deliverables completed during the quarter / total number of deliverables planned to be completed as per workplan submitted to FCDO at the start of the quarter. It is expected that the deliverables detailed in the TO& Buy-in workplan will be updated on a quarterly basis in line with adaptive management best practice. | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Proactive strategic collaboration to maximise effectiveness in GCIEP delivery in TO and/or DOC countries (REPORTED QUARTERLY) | No. of instances where GCIP team has worked and/or coordinated* with partners** A) GCIP DOC interventions B) GCI CoE delivery partners C) Any other UK expert organisations D) Development partners (instances that DOC and Buy-ins have collaborated with development partners) Disaggregation by: portfolio (DOC, TO and Buy-in) | Planned -annual | n/a | n/a | n/a | A) 3 operational DOC Communities of Practice (Energy, Climate Finance, DOC delivery) B) 15 C) 15 D) 30 | *GCIP can effectively target its assistance, to choose the right agencies/municipalities and/or institutions with which to partner and select the right interventions * Targets (n/a): Targets are not applicable, as we are a demand driven programme working under adaptive programming principles
|  | Achieved - annual |  | 3 through UKEO (ODA) | a) 4 b) 17 c) 20 d) 37
|  | Achieved - cumulative |  | 3 through UKEO (ODA) | a) 4 b) 17 c) 23 d) 37
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
10% |  | GCIP monitoring and operational databases Notes: *Co-ordination defined as having an active Community of Practice/signed MoU/other formal engagement process in place) ** Partners defined as any in-country international development agency or donor based in a DOC country ***GCIP CoE delivery partners: Cross Rail Intl, Ofgem, Infrastructure and Projects Authority, Transport for London, BSI; CATAPULT, Ordinance Survey and British Geological Survey |  |  |  |  | MINOR
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Enhancing capacity and knowledge to strengthen GCIP supported institutions and agencies in partner countries (disag by DOC and TO) (REPORTED QUARTERLY) | Percentage and number of people certified in UK tools and methodologies (Only applicable if there is formal UK certification offer. UK tools and methodologies with certification exam include, for example, 5CM) | Planned -annual | n/a | n/a | n/a | 360 | * GCIEP has the capacity to deliver targeted and high quality trainings, adapted to the needs to targeted stakeholders *GCIEP can leverage on UK expertise to successfully deliver TA *Setting a target for this indicator was deemed not applicable (in agreement with FCDO) during GCIEP’s first full year of delivery in Year 2 , due to the demand-driven nature of the programme. Instead, it was agreed we would report Actuals in the Y2 log frame. However, where there are continuing interventions in Y3 (second full year of GCIEP delivery) with many of the same stakeholders and sectors, we have included targets in the Year 3 log frame for this indicator.
|  | Achieved - annual |  | 93% (52/56) | 91.5% (205/224)
|  | Achieved - cumulative |  | 93% (52/56) | 91.8% (257/280)
Source
GCIP RM and operational databases Note: Number of people certified / total number of people trained in UK tools and methodologies taking the exam.
| Output Indicator 3.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number (#) of people trained via GCIEP supported work packages/interventions Disaggregation: portfolio (DOC, TO, Buy-in), women professionals, people with disabilities, and youth, indicate if UK methodology. | Planned -annual | n/a | n/a | n/a | 1,960 DOC Ethiopia: 0 DOC Ghana: 115 DOC Mozambique: 815 DOC Zambia: 25 DOC Indonesia: 80 DOC Philippines: 70 DOC Vietnam: 15 TO&BUY-IN: 840
|  | Achieved - annual |  | 223 (122 (M); 100 (W); 1 (Prefer no to say); 0 (PwD); 17 (Youth)) | 963 (398W, 63Youth, 6PwD)
|  | Achieved - cumulative |  | 223 (122 (M); 100 (W); 1 (Prefer no to say); 0 (PwD); 17 (Youth)) | 1186 (498W, 80Youth, 6PwD)
Source
GCIP RM and operational databases
| Output Indicator 3.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| % of participants indicating that the training/capacity building in Output 3.1 or 3.2 was "useful" or "very useful" on a 5 point scale | Planned -annual | n/a | n/a | 70% | 85%
|  | Achieved - annual |  | 99% (110/111) | 96.6% (402/416)
|  | Achieved - cumulative |  | 99% (110/111) | 97.2% (512/527)
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
10% |  | GCIP RM and operational databases |  |  |  |  | MINOR
OUTPUT 4 | Output Indicator 4.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
GEDSI is mainstreamed across GCIP DOC interventions and Target Offer (TO) work packages (WPs) (disag by DOC and TO) (REPORTED ANNUALLY) | % of GCIP supported DOC interventions/TO WPs that have an ambition of level 2 - Empowerment as per the FCDO GEDSI framework Disaggregated by FCDO GEDSI framework levels 1-3 | Planned -annual | n/a | n/a | 50% | 50% | *The FCDO GEDSI Framework is effective into translating FCDO’s GEDSI policies into programming; enabling GCIP to take a structured and practical approach to exploring how GCIP interventions can maximise benefits to disadvantaged and vulnerable groups
|  | Achieved - annual |  | 41% | GCIP: 64% CoE DPs PH02 TOD: (WS1: 100%, WS2: 100%)
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
15% |  | GCIP GEDSI monitoring; GCIP deliverables TOR and GCIP work package progress reports Note: it only applies to interventions that have GEDSI potential |  |  |  |  | MINOR
OUTPUT 5 | Output Indicator 5.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
CN&E is mainstreamed across GCIP DOC interventions and Target Offer (TO) work packages (WPs) (ICF compliance) (disag by DOC and TO) (REPORTED ANNUALLY) | % of GCIP supported DOC interventions/TO work packages that are mainstreaming CN&E | Planned - annual |  | 100% | 100% | 100% | *ICF compliant: An interventions that contributes to at least 1 ICF KPI indicator *ICF KPI TA methodology only allows actuals to be reported
|  | Achieved - annual |  | 100% | 100%
Source
GCIEP ICF monitoring; DOC intervention ToRs and TO Work Package ToRs; GCIEP progress reports
| Output Indicator 5.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| % of total spend that is ICF compliant in relation to the total £ value of GCIP programmes - of eligible ODA | Planned - annual | n/a | 30% | 80% | 80%
|  | Achieved - annual |  | 87% | 81.3%
Source
GCIEP ICF monitoring; DOC intervention ToRs and TO Work Package ToRs; GCIEP progress reports
| Output Indicator 5.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of countries supported by ICF technical assistance ICF TA KPI 1 (reported only on completed DOC interventions/TO WPs) | Planned - annual | n/a | n/a | n/a | n/a
|  | Achieved - annual |  | 18 (Tanzania, Nepal, Bangladesh, Rwanda, Egypt, Ghana, Mozambique, India, Indonesia (direct TO) + through direct and targeted (multi-country ASLIP training) Cambodia, Laos, Philippines, Singapore, Timor Leste, Thailand, Malaysia, Vietnam and Brunei) | 22 New countries (11): (DRC, Kyrgyzstan, South Africa, Zambia, Myanmar (part of ASLIP), CRIP - Saint Lucia, Grenada, Dominica, Saint Vincent and the Grenadines, Belize, Jamaica) Same countries supported as in Year 1 (11): Tanzania, Egypt, India, Indonesia, (multi-country ASLIP training) Cambodia, Laos, Philippines, Timor Leste, Thailand, Malaysia and Vietnam)
|  | Achieved - cumulative |  | 18 | 29 (unique counting of countries) Bangladesh, Belize, Brunei, Cambodia, Dominica, DRC, Egypt, Ghana, Grenada, India, Indonesia, Jamaica, Kyrgyzstan, Laos, Malaysia, Mozambique, Myanmar, Nepal, Philippines, Rwanda, Saint Lucia, Saint Vincent and the Grenadines, Singapore, South Africa, Tanzania, Thailand, Timor Leste, Vietnam and Zambia.
Source
GCIEP CN&E monitoring; DOC intervention ToRs and TO work package ToRs; GCIEP progress reports
| Output Indicator 5.4 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of individuals supported by ICF technical assistance ICF TA KPI 2.1 (reported only on completed DOC interventions/TO WPs) | Planned - annual | n/a | n/a | n/a | n/a
|  | Achieved - annual |  | 288 | 246
|  | Achieved - cumulative |  | 288 | 534 (cumulative)
Source
GCIEP CN&E monitoring; DOC intervention ToRs and TO work package ToRs; GCIEP progress reports
| Output Indicator 5.5 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of organisations supported by ICF technical assistance ICF TA KPI 2.2 (reported only on completed DOC interventions/TO WPs) | Planned - annual | n/a | n/a | n/a | n/a
|  | Achieved - annual |  | 57 | 76
|  | Achieved - cumulative |  | 57 | 117 (cumulative) 16 organisations consulted on multiple interventions (NITI Aayog (Indonesia), Ministry of Transport, (Indonesia) MoF - PIAD and NRECCU - Natural Resource, Environmental and Climate Change Unit (Ghana), Public Investment Units (Ghana), Ghana Infrastructure Investment Fund (GIIF), MESTI (Ghana), Environmental Protection Authority (Ghana), Ministry of Transport (Ghana), Public Procurement Authority (Ghana), National Development Planning Commission (Ghana), NaBFID (National Bank for Financing Infrastructure Development), EgyptERA, Dar es Salaam City Council (DCC), Central Public Health and Environmental Engineering Organisation (CPHEEO) (Indonesia), MoHUA (Ministry of Housing and Urban Affairs) (Indonesia) and National Institute of Urban Affairs (NIUA) (Indonesia).
Source
GCIEP CN&E monitoring; DOC intervention ToRs and TO work package ToRs; GCIEP progress reports
| Output Indicator 5.6 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of climate policies informed by ICF technical assistance ICF TA KPI 3 (reported only on completed DOC interventions/TO WPs) | Planned - annual | n/a | n/a | n/a | n/a
|  | Achieved - annual |  | 0 | 2
|  | Achieved - cumulative |  | 0 | 2
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
15% |  | GCIEP CN&E monitoring; DOC intervention ToRs and TO work package ToRs; GCIEP progress reports |  |  |  |  | MINOR
OUTPUT 6 | Output Indicator 6.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Learning (evidence) produced and in place for GCIEP to collate and disseminate UK and international urban / infrastructure expertise within GCIEP, FCDO, and to the wider ecosystem (REPORTED QUARTERLY) | No. of GCIEP products (analysis and learning including events) that deliver insights which inform/shape FCDO/wider development partner policies and programmes Disaggregation by events and products | Planned - annual | n/a | n/a | n/a | 121 DOC Ethiopia: 5 DOC Ghana: 17 DOC Mozambique: 20 DOC Zambia: 12 DOC Indonesia: 20 DOC Philippines: 9 DOC Vietnam: 8 TO&BUY-IN: 30 | *Sufficient GCIP budget is allocated to undertake planned L&C activities approved in the ToR L&C * Targets (n/a): Targets are not applicable, as we are a demand driven programme working under adaptive programming principles
|  | Achieved - annual |  | 4 products | 40 events 53 products
|  | Achieved - cumulative |  | 4 products | 40 events 53 products
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
10% |  | GCIP RM and L&C monitoring, GCIP K&L documentation (including links to public KPs and materials published) Note: a. A GCIP Product is any written material produced by GCIP and/or its delivery partners, through its DOC interventions/ TO work packages, that has been repackaged according to targeted audience/s and dissemination channel/s including learning events, that seek to contribute to the body of infra delivery and urban development knowledge towards improving FCDO and GCIP delivery partners programming . This GCIP product is out of the budget of the TO WP. |  |  |  |  | MINOR
º
Note on A7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: How can we start to draw in the forecasts for these indicators from the projections work done by Smita and Mat? These could be reported in a section in the QR/AR? Or a separate projected benefits grid could be created to accompany the projections paper. For those which have progressed to finance mobilised and for those still in the pipeline. Reply: We can only insert expected number at project level once a project reaches financial close. Currently too early for all projects being supported by GCIEP. In the case of ICF KPI we can only insert actual numbers when a project is fully built and operational as per ICF methodology. However, Mat’s paper does include project level projections for those under development and we will reproduce the relevant data in the Y3 Annual Report
Note on G32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What does a 4 imply? That one or more of the six DOCs hits 4, or that all of them do? Reply: Portfolio level assessment; Expect that all 6 DOCs will hit 4
Note on B37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Delete second ‘total’. Should the indicator refer to ‘committed’ funds if different to 1.2 and 1.3? Reply: Second cumulative is Achieved vs First total which is Planned/target Reply: Done
Note on G37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Why 70%? And why 302million? Can we just say the figure we aim to reach? There is no payment milestone contingent on meeting the target. Or say: If pipeline projects reach financial close (?), the amount will be £302m. Reply: Include narrative with caveats - potential we can reach, no target Reply: Done
Note on G43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Why can’t we have a target for actuals then? If this is different standard to the first indicator, where does it say that? Reply: ICF methodology only reports Actuals
Note on G49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: As above Reply: ICF methodology only reports Actuals
Note on F55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Can we say a) what is the policy and b) what is the deliverable that informed or supported it? Reply: For actuals, we have included the Enabling Environment change along with GCIEP inputs / deliverables that informed or supported it. - TO DO For Targets, please see “Targets list” tab for details of the deliverables linked to the Enabling Environment targeted change
Note on G55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Delete the 70% target and put the total number from the list below. It doesn’t matter if you fail - you just have to explain why, and that becomes a lesson learned. Write out the country in every case to be clear and consistent. Reply: Or if prefered, explain: if all pipeline projects progress, the total will be X Reply: Inserted explanation and country name as suggested above
Note on G61: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Delete the 70% Reply: Inserted explanation and country name as suggested above
Note on G62: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Remove ‘overachievement’ and find another way to flag additional, unplanned outcomes. In what sense is it an overachievement? The language is too promotional and emotive for a logframe. It should be neutral and descriptive. Reply: Achieved earlier than expected Reply: Done
Note on A68: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Note for future consideration - the indicator 1.1. is not really telling us about the quality of the interventions. What is the definition of ‘scaled up’? Reply: Changed wording
Note on G68: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Why can’t we add a target here? We already have some results from last year, so at minimum, they can be in the cumulative target. It should be an indicative number to tell us what we can expect. If there is no target, how can we assess the results? What does good look like? Reply: Demand - driven Reply: As per your last email, we agreed not to insert targets, instead we have inserted actuals.
Note on G74: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Remove 80%. Just put the total number. Reply: Restated as 80% equivalent in numbers Reply: Once the logframe is approved we will convert all % targets to number equivalent-
Note on F75: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If these are project pipeline, they should name the actual infrastructure projects. Reply: Separate pipeline support vs project support; where project - clearly identify the project name Reply: Make distinction between pipeline and project clearer; include pipeline in dashboard - stage by itself Reply: Done indicating Project Pipeline vs Project specific support for actuals including project names when relevant. We will also signpost the type and stage of support in the dashboard for Y3Q3
Note on G75: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: HI Nick and Olanda, Can we state the following as ACHIEVED? As I am not sure that we have any evidence of acceptance, as letter, emails etc? Thanks Alexia DOC Mozambique 3. Strategic Outline business case (SOBC) for Green Energy reviewed/accepted by the Municipality (Phase 1) 4. SOBC for Urban Green Park reviewed/accepted by the Municipality (Phase 1) 5. Concept Note for Bypass Green Road reviewed/accepted by the Municipality (Phase 1) 6. Portfolio of investments reviewed/accepted by the Municipality (Phase 1) Reply: Is a project preparation facility not EE, rather than PP? The others also seem to be more EE. Perhaps name the projects, rather than the intervention delivered? Reply: Yes, a Project Preparation Facility (PPF) is closely linked to the enabling environment, often supporting its development, but they are distinct concepts: the enabling environment (policies, laws, institutions) creates the conditions for projects, while the PPF provides specific support (funding, technical help) to develop projects to a bankable stage within that environment. A good PPF builds or strengthens the enabling environment by creating better project documentation and structures, while also tackling project-specific hurdles. Here's the relationship explained: Enabling Environment: Refers to the overarching framework—the laws, regulations, institutional capacity, and political will that make infrastructure development possible and attractive. Project Preparation Facility (PPF): A mechanism (like those from the GCF or GIF) that offers targeted support (e.g., feasibility studies, financial structuring, risk mitigation) to turn project ideas into investment-ready proposals. Reply: Add some description of potential project names/description to each target
Note on B92: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is a point that will run through other reports as well - but it should be ‘Financing mechanisms’ rather than ‘Financial’. Reply: Agreed - will change
Note on G93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Results should only be included if there is an actual decision that has been taken by the partner. Accepting the dellvierable is not enough. Reply: Changed wording to add in Potential
Note on G98: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If you reached 88% last year, why such a low target for this year? Reply: The 88% is only related to completed TOs from Phase 1, we expect the average across portfolios (DOC, TO, BUY-IN) to be lower and more in line with the target set in the GEDSI strategy of 50% Level 2 Empowerment. This is an ambitious target for an infrastructure programme and the strategy will need to be revisited if it is to be increased.
Note on G114: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What does good look like? Reply: Same logic as for Intermediate Outcome 1.1 applies.
Note on G126: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Why nothing for A? Reply: Insert A target and actuals Reply: Done
Note on A155: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What is the definition of ‘mainstreaming’? Reply: Please refer to GEDSI and CN&E strategies for mainstreaming definition and process implemented by GCIEP

## GCIEP Y3 LF - Targets & Status
Green Cities and Infrastructure and Energy Programme (GCIEP) Y3 Logframe (22 January 2026) - FOR APPROVAL
Full list of Outcome 2.1, 2.3, and Intermediate Outcomes 1.2, 2.1, and 3.1 Targets (including achievement status)
YEAR | STATEMENT | INDICATOR NAME | INDICATOR CATEGORY | PORTFOLIO | Country | PROJECT | NAME | STATUS | DATE OF ACHIEVEMENT | NOTE
3 | OUTCOME 1: Finance and Investment is leveraged for sustainable and inclusive infrastructure and the built environment | OUTCOME INDICATOR 1.1: Total volume of total non-GCIP financing mobilised as a result of GCIP interventions (£) | Public finance | DOC Ghana | Ghana | DOC GH.P1.03 Urban | £12M grant from DANIDA as a result of the Wa water project feasibility study completed by GCIEP (DKK100M) | Achieved | 2025-11-01
3 | OUTCOME 1: Finance and Investment is leveraged for sustainable and inclusive infrastructure and the built environment | OUTCOME INDICATOR 1.1: Total volume of total non-GCIP financing mobilised as a result of GCIP interventions (£) | Public finance | DOC Ghana | Ghana | DOC GH.P2.01 Urban development project preparation support | £120M Sekondi-Takoradi Metropolitan Area (STMA) project | Target
3 | OUTCOME 1: Finance and Investment is leveraged for sustainable and inclusive infrastructure and the built environment | OUTCOME INDICATOR 1.1: Total volume of total non-GCIP financing mobilised as a result of GCIP interventions (£) | Public finance | TO | Zambia | TO Zambia Legal Get FiT | £150 million (GetFiT- legal support for the financing of 120 MW for 6 solar projects in Zambia) | Target
3 | OUTCOME 2: GCIEP TA contributed to a stronger enabling environment in FCDO partner countries for the provision of climate resilient&inclusive infrastructure services | OUTCOME INDICATOR 2.1 APPROVAL: No. of approved policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries supported by GCIEP TA | A. Strategy & Planning | DOC Ghana | Ghana | DOC GH.P1.03 Urban | M&E Plan to monitor implementation of the national urban policy approved (Phase 1) | Achieved | 2025-09-30 | Related to WS3a Urban baseline and M&E framework for new urban policy
3 | OUTCOME 2: GCIEP TA contributed to a stronger enabling environment in FCDO partner countries for the provision of climate resilient&inclusive infrastructure services | OUTCOME INDICATOR 2.1 APPROVAL: No. of approved policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries supported by GCIEP TA | B. Legal & Regulatory Framework | DOC Mozambique | Mozambique | DOC MZ.P1.01 Sustainable finance | National Climate Finance Strategy and Roadmap approved by Council of Ministers (Phase 1) | Achieved (moved from IO 3.1) | 2025-09-30
3 | OUTCOME 2: GCIEP TA contributed to a stronger enabling environment in FCDO partner countries for the provision of climate resilient&inclusive infrastructure services | OUTCOME INDICATOR 2.1 APPROVAL: No. of approved policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries supported by GCIEP TA | D. Institutional capacity & governance | DOC Mozambique | Mozambique | DOC MZ.P1.02 Pemba urban development | Urban Municipal Observatory in Pemba launched and operational (Phase 1) | Achieved | 2025-09-30
3 | OUTCOME 2: GCIEP TA contributed to a stronger enabling environment in FCDO partner countries for the provision of climate resilient&inclusive infrastructure services | OUTCOME INDICATOR 2.1 APPROVAL: No. of approved policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries supported by GCIEP TA | D. Institutional capacity & governance | DOC Mozambique | Mozambique | DOC MZ.P1.03 Beira urban development | Urban detail plan to inform urban planning in the Mucurungo Miquejo area approved by the Municipal Assembly (Phase 1) | Achieved (moved from IO 3.1) | 2025-12-18
3 | OUTCOME 2: GCIEP TA contributed to a stronger enabling environment in FCDO partner countries for the provision of climate resilient&inclusive infrastructure services | OUTCOME INDICATOR 2.1 APPROVAL: No. of approved policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries supported by GCIEP TA | D. Institutional capacity & governance | DOC Mozambique | Mozambique | DOC MZ.P1.04 Nacala urban development | Nacala Urban Structured Plan informing urban planning approved by the Municipal Assembly (Phase 1) | Achieved (moved from IO 3.1) | 2025-12-18
3 | OUTCOME 2: GCIEP TA contributed to a stronger enabling environment in FCDO partner countries for the provision of climate resilient&inclusive infrastructure services | OUTCOME INDICATOR 2.1 APPROVAL: No. of approved policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries supported by GCIEP TA | D. Institutional capacity & governance | DOC Zambia | Zambia | DOC ZM.P1.01 Energy | A one-stop service for energy sector to streamline multiple approval energy-related processes into a single, integrated workflow is further-improved (Phase 1) | Achieved | 2025-08-31
3 | OUTCOME 2: GCIEP TA contributed to a stronger enabling environment in FCDO partner countries for the provision of climate resilient&inclusive infrastructure services | OUTCOME INDICATOR 2.1 APPROVAL: No. of approved policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries supported by GCIEP TA | A. Strategy & Planning | DOC Zambia | Zambia | DOC ZM.P1.01 Energy | Analysis to Power Sector Incentives informing a new tax incentive regime for independent power producers approved by the Office for Promoting Private Power Investment (Phase 1) | Achieved (moved from IO 3.1) | 2025-07-30 | Related to WS5 Energy Sector Financial Sustainability
3 | OUTCOME 2: GCIEP TA contributed to a stronger enabling environment in FCDO partner countries for the provision of climate resilient&inclusive infrastructure services | OUTCOME INDICATOR 2.1 APPROVAL: No. of approved policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries supported by GCIEP TA | A. Strategy & Planning | DOC Indonesia | Indonesia | DOC ID.P1.02 Surabaya | Flood management practices: Flood Risk Assessments report for Surabaya approved by city government (Phase 1) | Achieved (moved from IO 3.1) | 2025-04-30 | Related to WS4 Support to Surabaya on Flood Risk Assessments
3 | OUTCOME 2: GCIEP TA contributed to a stronger enabling environment in FCDO partner countries for the provision of climate resilient&inclusive infrastructure services | OUTCOME INDICATOR 2.1 APPROVAL: No. of approved policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries supported by GCIEP TA | A. Strategy & Planning | DOC Indonesia | Indonesia | DOC ID.P1.02 Surabaya | Flood management practices: Flood Risk Assessments report for Denpasar approved by city government (Phase 1) | Achieved (moved from IO 3.1) | 2025-04-30 | Related to WS4 Support to Surabaya on Flood Risk Assessments
3 | OUTCOME 2: GCIEP TA contributed to a stronger enabling environment in FCDO partner countries for the provision of climate resilient&inclusive infrastructure services | OUTCOME INDICATOR 2.1 APPROVAL: No. of approved policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries supported by GCIEP TA | D. Institutional capacity & governance | DOC Mozambique | Mozambique | DOC MZ.P2.04 Climate Finance | Participatory Group and Technical Council group established and operational to support the Implementation of the National Sustainable FInance strategy in Mozambique | Target
3 | OUTCOME 2: GCIEP TA contributed to a stronger enabling environment in FCDO partner countries for the provision of climate resilient&inclusive infrastructure services | OUTCOME INDICATOR 2.1 APPROVAL: No. of approved policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries supported by GCIEP TA | C. Financing Mechanisms | DOC Mozambique | Mozambique | DOC MZ.P2.03 Cities & investment | Medium-term Debt Management Strategy to improve the Municipality's financial health endorsed by the Pemba Municipal Assembly | Target
3 | OUTCOME 2: GCIEP TA contributed to a stronger enabling environment in FCDO partner countries for the provision of climate resilient&inclusive infrastructure services | OUTCOME INDICATOR 2.1 APPROVAL: No. of approved policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries supported by GCIEP TA | C. Financing Mechanisms | TO | Zambia | TO Zambia Legal Get FiT | 120 MW for 6 solar projects: Implementation Agreements and Long-term liquidity mechanism approved by lenders and the government of Zambia(Get Fit Zambia) | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | A. Strategy & Planning | DOC Philippines | Philippines | DOC PH.P1.02 TOD | PH02 TOD﻿ WS1: Proof of Concept TOD Implementation framework accepted by Philippines DOTr | Target | TBC | CI led -Phase 1
3 | OUTCOME 2: GCIEP TA contributed to a stronger enabling environment in FCDO partner countries for the provision of climate resilient&inclusive infrastructure services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | A. Strategy & Planning | DOC Philippines | Philippines | DOC PH.P1.02 TOD | PH02 TOD WS2: Senate DepEd site pilot study - TOD masterplan accepted by Philippines DOTr and DepEd | Target | TBC | TfL led Phase 1
3 | OUTCOME 2: GCIEP TA contributed to a stronger enabling environment in FCDO partner countries for the provision of climate resilient&inclusive infrastructure services | OUTCOME INDICATOR 2.3 ADOPTION: Number of GCIEP supported policies / regulations / strategies / roadmaps / frameworks / institutional structures adopted as evidence of GCIEP legacy / sustainability in GCIP supported entities (sustainability) | A. Strategy & Planning | DOC Ghana | Ghana | DOC GH.P1.02 Energy | Energy planning: DIgSILENT Power Factory software adopted by GRIDCo following the 10-day training provided by GCIEP (GRIDCo spent ~£250K to acquire the software) (Phase 1) | Achieved | 2025-05-30 | Not anticipated as potential target
3 | OUTCOME 2: GCIEP TA contributed to a stronger enabling environment in FCDO partner countries for the provision of climate resilient&inclusive infrastructure services | OUTCOME INDICATOR 2.3 ADOPTION: Number of GCIEP supported policies / regulations / strategies / roadmaps / frameworks / institutional structures adopted as evidence of GCIEP legacy / sustainability in GCIP supported entities (sustainability) | A. Strategy & Planning | DOC Ghana | Ghana | DOC GH.P1.03 Urban | EU-funded Ghana Urban Observatory: Risk and hazard screening report and risk maps for each of the 9 cities designed and operationalised | Achieved (moved from IO 3.1) | 2025-08-31
3 | OUTCOME 2: GCIEP TA contributed to a stronger enabling environment in FCDO partner countries for the provision of climate resilient&inclusive infrastructure services | OUTCOME INDICATOR 2.3 ADOPTION: Number of GCIEP supported policies / regulations / strategies / roadmaps / frameworks / institutional structures adopted as evidence of GCIEP legacy / sustainability in GCIP supported entities (sustainability) | A. Strategy & Planning | DOC Indonesia | Indonesia | DOC ID.P1.01 Bappenas project planning | Project Funding and Financing Options Framework version 1 adopted by Bappenas (Phase 1) | Achieved (moved from IO 3.1) | 2025-09-30
3 | OUTCOME 2: GCIEP TA contributed to a stronger enabling environment in FCDO partner countries for the provision of climate resilient&inclusive infrastructure services | OUTCOME INDICATOR 2.3 ADOPTION: Number of GCIEP supported policies / regulations / strategies / roadmaps / frameworks / institutional structures adopted as evidence of GCIEP legacy / sustainability in GCIP supported entities (sustainability) | B. Legal & Regulatory Framework | DOC Vietnam | Vietnam | DOC VN.P1.02 TOD | HCMC Transport Oriented Development (TOD) Resolution nº 38 guiding implementation of Article 6 of National Assembly's Resolution 188 related to TOD development was passed by the HCMC People's Council (August 2025) | Achieved (moved from IO 3.1) | 2025-08-31 | Achieved earlier than expected. Moved from Intermediate Outcome 3.1 as per GCIEP inputs adopted by the regulators to approve resolutions
3 | OUTCOME 2: GCIEP TA contributed to a stronger enabling environment in FCDO partner countries for the provision of climate resilient&inclusive infrastructure services | OUTCOME INDICATOR 2.3 ADOPTION: Number of GCIEP supported policies / regulations / strategies / roadmaps / frameworks / institutional structures adopted as evidence of GCIEP legacy / sustainability in GCIP supported entities (sustainability) | B. Legal & Regulatory Framework | DOC Vietnam | Vietnam | DOC VN.P1.02 TOD | Hanoi TOD Resolution 15 was passed by the Hanoi City People's Council (November 2025) (including also GCIEP inputs to former Resolution 16 which has now been integrated under Resolution 15) | Achieved (moved from IO 3.1) | 2025-11-27 | Achieved earlier than expected. Moved from Intermediate Outcome 3.1 as per GCIEP inputs adopted by the regulators to approve resolutions
3 | OUTCOME 2: GCIEP TA contributed to a stronger enabling environment in FCDO partner countries for the provision of climate resilient&inclusive infrastructure services | OUTCOME INDICATOR 2.3 ADOPTION: Number of GCIEP supported policies / regulations / strategies / roadmaps / frameworks / institutional structures adopted as evidence of GCIEP legacy / sustainability in GCIP supported entities (sustainability) | D. Institutional capacity & governance | DOC Mozambique | Mozambique | DOC MZ.P2.04 Climate Finance | Operational Web-based Climate Finance Dashboard with integrated information | Target
3 | OUTCOME 2: GCIEP TA contributed to a stronger enabling environment in FCDO partner countries for the provision of climate resilient&inclusive infrastructure services | OUTCOME INDICATOR 2.3 ADOPTION: Number of GCIEP supported policies / regulations / strategies / roadmaps / frameworks / institutional structures adopted as evidence of GCIEP legacy / sustainability in GCIP supported entities (sustainability) | A. Strategy & Planning | DOC Indonesia | Indonesia | DOC ID.P2.01 Bappenas | Project Funding and Financing Options Framework version 2 adopted by Bappenas deputy of Development financing and investment | Target
3 | OUTCOME 2: GCIEP TA contributed to a stronger enabling environment in FCDO partner countries for the provision of climate resilient&inclusive infrastructure services | OUTCOME INDICATOR 2.3 ADOPTION: Number of GCIEP supported policies / regulations / strategies / roadmaps / frameworks / institutional structures adopted as evidence of GCIEP legacy / sustainability in GCIP supported entities (sustainability) | B. Legal & Regulatory Framework | DOC Vietnam | Vietnam | DOC VN.P2.01 TOD&BIM | Resolution on Land Value Capture (LVC) financing mechanisms for HCMC passed by the HCMC People's Council | Target
3 | INTERMEDIATE OUTCOME 1: GCIEP DOC programmes are effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 1.2: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) | II. Project Specific support | DOC Ethiopia | Ethiopia | DOC ET.P2.02 Energy | Use case for an identified intervention for Smart Grid Optimisation (SGO) reviewed/accepted by Ethiopian Electric Utility (EEU) / Ethiopian Electric Power (EEP) | Target
3 | INTERMEDIATE OUTCOME 1: GCIEP DOC programmes are effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 1.2: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) | II. Project Specific support | DOC Ethiopia | Ethiopia | DOC ET.P2.02 Energy | Use case for an identified Distributed Renewable Energy (DRE) focused initiative including viability of accessing carbon market revenues reviewed/accepted by Ministry of Water and Energy (MoWE) | Target
3 | INTERMEDIATE OUTCOME 1: GCIEP DOC programmes are effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 1.2: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) | I. Project pipeline | DOC Ghana | Ghana | DOC GH.P1.02 Energy | Pipeline of 100 VRE projects developed from GridCo and the Energy Commission list of projects | Achieved | 2025-09-30
3 | INTERMEDIATE OUTCOME 1: GCIEP DOC programmes are effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 1.2: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) | II. Project Specific support | DOC Ghana | Ghana | DOC GH.P1.01 Climate finance | Project Preparation Facility (PPF): feasibility study accepted by FCDO | Achieved | 2025-06-30
3 | INTERMEDIATE OUTCOME 1: GCIEP DOC programmes are effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 1.2: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) | II. Project Specific support | DOC Ghana | Ghana | DOC GH.P1.01 Climate finance | 12,500m2 biogas plant (DasBiogas and Accra Metropolitan Assembly); 75 MW wind power in Keta Municipality (VRA Ghana); 5,000 capacity student complex at Kwame Nkrumah Univ. of Science and Technology in Kumasi (Nilex): Three scoping Briefing notes for project preparation to feed into the PPF accepted by FCDO | Achieved | 2025-09-30
3 | INTERMEDIATE OUTCOME 1: GCIEP DOC programmes are effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 1.2: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) | II. Project Specific support | DOC Ghana | Ghana | DOC GH.P1.02 Energy | Akuse Floating PV Plant: Pre-Feasibility study accepted by GRIDCo | Achieved | 2025-09-30
3 | INTERMEDIATE OUTCOME 1: GCIEP DOC programmes are effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 1.2: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) | II. Project Specific support | DOC Ghana | Ghana | DOC GH.P1.02 Energy | Sawla PV Plant: Pre-Feasibility study accepted by GRIDCo | Achieved | 2025-09-30
3 | INTERMEDIATE OUTCOME 1: GCIEP DOC programmes are effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 1.2: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) | II. Project Specific support | DOC Ghana | Ghana | DOC GH.P1.03 Urban | Wa Water: Feasibility study accepted by DANIDA and Gvt of Ghana | Achieved | 2025-11-30 | Related to WS1: Water security and access to water services for vulnerable urban communities in Wa
3 | INTERMEDIATE OUTCOME 1: GCIEP DOC programmes are effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 1.2: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) | II. Project Specific support | DOC Ghana | Ghana | DOC GH.P2.03 Climate Finance | DBG Climate Finance Faciliy: Action plan on how to operationalise the facility reviewed/accepted by DBG | Target
3 | INTERMEDIATE OUTCOME 1: GCIEP DOC programmes are effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 1.2: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) | II. Project Specific support | DOC Ghana | Ghana | DOC GH.P2.03 Climate Finance | FSD-Africa PPF: Summary report on future financial sustainability for the PPF and pipeline development reviewed/accepted by FSD Africa | Target
3 | INTERMEDIATE OUTCOME 1: GCIEP DOC programmes are effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 1.2: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) | II. Project Specific support | DOC Ghana | Ghana | DOC GH.P2.01 Urban development project preparation support | Sekondi-Takoradi Metropolitan Area (STMA) project: detailed Feasibility report accepted by Department of Urban Roads/Ministry of Roads and Highways and the Ghana Hydrological Authority/Ministry of Works, Housing, and Water Resources | Target |  | As per additional request from donors at the end of Phase 1, the original target has been moved and linked to Phase 2
3 | INTERMEDIATE OUTCOME 1: GCIEP DOC programmes are effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 1.2: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) | II. Project Specific support | DOC Ghana | Ghana | DOC GH.P2.01 Urban development project preparation support | Climate smart fecal sludge treatment plant (FSTP) project in 5 cities: revised Feasibility report accepted by Ministry of Local Government, Chieftaincy and Religious Affairs | Target
3 | INTERMEDIATE OUTCOME 1: GCIEP DOC programmes are effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 1.2: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) | II. Project Specific support | DOC Ghana | Ghana | DOC GH.P2.02 Energy | Akuse Floating PV Plant: Pre-Feasibility study report completed and accepted by Volta River Authority (VRA) | Target
3 | INTERMEDIATE OUTCOME 1: GCIEP DOC programmes are effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 1.2: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) | I. Project pipeline | DOC Mozambique | Mozambique | DOC MZ.P1.01 Sustainable finance | GCF country programme report for MoZ, an GCF requirement to be able to access TA funds and put forward project proposals reviewed/acccepted by the CFU | Achieved | 2025-09-30
3 | INTERMEDIATE OUTCOME 1: GCIEP DOC programmes are effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 1.2: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) | I. Project pipeline | DOC Mozambique | Mozambique | DOC MZ.P1.01 Sustainable finance | GCF multi-year readiness proposal to allow CFU access TA funding for project development reviewed/accepted by the CFU | Achieved | 2025-09-30
3 | INTERMEDIATE OUTCOME 1: GCIEP DOC programmes are effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 1.2: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) | I. Project pipeline | DOC Mozambique | Mozambique | DOC MZ.P1.02 Pemba urban development | Portfolio of investments reviewed/accepted by the Pemba Muncipality | Achieved | 2025-12-30
3 | INTERMEDIATE OUTCOME 1: GCIEP DOC programmes are effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 1.2: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) | II. Project Specific support | DOC Mozambique | Mozambique | DOC MZ.P1.02 Pemba urban development | Green Energy project : Strategic Outline business case (SOBC) reviewed/accepted by the Municipality | Achieved | 2025-12-30
3 | INTERMEDIATE OUTCOME 1: GCIEP DOC programmes are effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 1.2: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) | II. Project Specific support | DOC Mozambique | Mozambique | DOC MZ.P1.02 Pemba urban development | Green Urban Park project: SOBC reviewed/accepted by the Municipality | Achieved | 2025-12-30
3 | INTERMEDIATE OUTCOME 1: GCIEP DOC programmes are effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 1.2: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) | II. Project Specific support | DOC Mozambique | Mozambique | DOC MZ.P1.02 Pemba urban development | Bypass Green Road project: Concept Note reviewed/accepted by the Muncipality | Achieved | 2025-12-30
3 | INTERMEDIATE OUTCOME 1: GCIEP DOC programmes are effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 1.2: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) | II. Project Specific support | DOC Mozambique | Mozambique | DOC MZ.P1.03 Beira urban development | Miramar park project: Business Case reviewed/accepted by the Muncipality | Achieved | 2026-01-21
3 | INTERMEDIATE OUTCOME 1: GCIEP DOC programmes are effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 1.2: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) | II. Project Specific support | DOC Mozambique | Mozambique | DOC MZ.P2.03 Cities & investment | Triangulo Basin project in Nacala: Prefeasibility report reviewed/accepted by the Muncipality | Target
3 | INTERMEDIATE OUTCOME 1: GCIEP DOC programmes are effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 1.2: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) | II. Project Specific support | DOC Mozambique | Mozambique | DOC MZ.P2.03 Cities & investment | Nacala public space: Strategic Outline Business Case reviewed/accepted by the Muncipality | Target
3 | INTERMEDIATE OUTCOME 1: GCIEP DOC programmes are effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 1.2: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) | I. Project pipeline | DOC Zambia | Zambia | DOC ZM.P1.01 Energy | Prioritised renewable energy pipeline of 40 solar projects based on GCIEP analysis reviewed/acccepted by Office for Promoting Private Power Investment | Achieved | 2025-03-30 | Related to WS1 Fast Track Procurement. Anticipated as target for Y3 but achieved during Y2 therefore the target section of this indicator under Y3 shows this as target but the achievement is under Y2.
3 | INTERMEDIATE OUTCOME 1: GCIEP DOC programmes are effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 1.2: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) | II. Project Specific support | DOC Zambia | Zambia | DOC ZM.P2.01 Procurement & Open Access | 100 MW suite of solar projects: Tender Documentation (RfP) aligned with RELM reviewed/acccepted by the Gvt of Zambia | Target
3 | INTERMEDIATE OUTCOME 1: GCIEP DOC programmes are effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 1.2: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) | II. Project Specific support | DOC Indonesia | Indonesia | DOC ID.P2.02 East Java Transport | Advancing Urban Rail Transport System (URTS): Project Development Plan completed and accepted by East Java Provincial Governement | Target |  | Related to WS1
3 | INTERMEDIATE OUTCOME 1: GCIEP DOC programmes are effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 1.2: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) | II. Project Specific support | DOC Philippines | Philippines | DOC PH.P1.01 Water | Baguio Water Bulk supply Project: Feasibility Study accepted (as per MoU, accepted = written approval from the Baguio City Council as well as approval from the Water board of directors) | Target
3 | INTERMEDIATE OUTCOME 1: GCIEP DOC programmes are effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 1.2: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) | II. Project Specific support | DOC Philippines | Philippines | DOC PH.P2.01 Water | Baguio Water Bulk supply PPP support: Options for Project Structuring and Financial Models accepted by Baguio City | Target
3 | INTERMEDIATE OUTCOME 1: GCIEP DOC programmes are effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 1.2: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) | II. Project Specific support | DOC Philippines | Philippines | DOC PH.P1.02 TOD | Feasibility Study (FS) - a viable/deliverable scheme developed to balance key stakeholder requirements and comply with NEDA Board ICC Guidelines | Target
3 | INTERMEDIATE OUTCOME 1: GCIEP DOC programmes are effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 1.2: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) | II. Project Specific support | DOC Philippines | Philippines | DOC PH.P1.02 TOD | Approval of the FS scheme by landowner Department of Education (DepEd) and key stakeholder Department of Transportation (DOTr) | Target
3 | INTERMEDIATE OUTCOME 2: GCIEP TO and buy-ins support is successfully contributing to improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 2.1: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritized, sequenced or developed (includes signposting stage of the infrastructure development cycle) | I. Project pipeline | TO | India | TO India Credit Enhancement Platform for climate positive urban infrastructure projects Phase 3 | NaBFID-aligned project pipeline for waste to energy and waste water sector projects for urban local bodies in Indian cities reviewed/accepted by Post | Target
3 | INTERMEDIATE OUTCOME 2: GCIEP TO and buy-ins support is successfully contributing to improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 2.1: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritized, sequenced or developed (includes signposting stage of the infrastructure development cycle) | I. Project pipeline | TO | Nepal | TO Nepal Lumbini Capital City Master Plan | Project prioritisation report capturing the long-list and shortlisted urban development projects for Lumbini province (with 5 brief concept notes) reviewed/accepted by Post (Nepal) | Target
3 | INTERMEDIATE OUTCOME 2: GCIEP TO and buy-ins support is successfully contributing to improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 2.1: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritized, sequenced or developed (includes signposting stage of the infrastructure development cycle) | I. Project pipeline | Buy-in | South Africa | BUY-IN SOUTH AFRICA: Strategic & Special Delivery Unit (SSDU) Initiation Phase: The Department of Public Works and Infrastructure (DPWI) of Government of South Africa ​ | Prioritised project pipeline to revitalise national unused and obsolete public building insfraestructure reviewed/accepted by Post/DPWI | Target
3 | INTERMEDIATE OUTCOME 2: GCIEP TO and buy-ins support is successfully contributing to improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 2.1: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritized, sequenced or developed (includes signposting stage of the infrastructure development cycle) | II. Project Specific support | TO | Mauritius | TO Mauritius Developing TOR for FS for 100MW Offshore Wind | Offshore wind project: ToR for feasibility study reviewed/accepted by Post / GoM | Target
3 | INTERMEDIATE OUTCOME 2: GCIEP TO and buy-ins support is successfully contributing to improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 2.1: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritized, sequenced or developed (includes signposting stage of the infrastructure development cycle) | II. Project Specific support | TO | Indonesia | TO Indonesia Feasibility Study Surabaya Mass Urban transit infrastructure | Surabaya urban mass transit feasibility study reviewed/accepted by Post /client | Achieved | 2025-09-26
3 | INTERMEDIATE OUTCOME 2: GCIEP TO and buy-ins support is successfully contributing to improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 2.1: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritized, sequenced or developed (includes signposting stage of the infrastructure development cycle) | II. Project Specific support | Buy-in | Cambodia | BUY-IN Cambodia Feasibility Study for a Green Special Economic Zone in Cambodia | Green Special Economic Zone Concept master plan for ~174hectare project site reviewed/accepted by Post | Target
3 | INTERMEDIATE OUTCOME 2: GCIEP TO and buy-ins support is successfully contributing to improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 2.1: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritized, sequenced or developed (includes signposting stage of the infrastructure development cycle) | II. Project Specific support | Buy-in | DRC | BUY-IN DRC UK support to high-impact infrastructure and urban projects in DRC | Solid Waste Management: Technical design for future pre-collection platform, payment systems and sorting centre in Kinshasa reviewed/accepted b Post, ANAT & CDUK | Target
3 | INTERMEDIATE OUTCOME 2: GCIEP TO and buy-ins support is successfully contributing to improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 2.1: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritized, sequenced or developed (includes signposting stage of the infrastructure development cycle) | II. Project Specific support | Buy-in | DRC | BUY-IN DRC UK support to high-impact infrastructure and urban projects in DRC | Urban Resilience and Drainage: Technical design for THIMO-based desilting operations in Kinshasa reviewed/accepted by Post / ANAT & CDUK | Target
3 | INTERMEDIATE OUTCOME 2: GCIEP TO and buy-ins support is successfully contributing to improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 2.1: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritized, sequenced or developed (includes signposting stage of the infrastructure development cycle) | II. Project Specific support | Buy-in | DRC | BUY-IN DRC UK support to high-impact infrastructure and urban projects in DRC | Transport and Mobility: Technical design for a transport project in Kinshasa reviewed/accepted by Post / ANAT & CDUK | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | A. Strategy & Planning | DOC Ethiopia | Ethiopia | DOC ET.P2.01 Secondary Cities | Prioritised Investment Program report reviewed/accepted by counterpart | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | A. Strategy & Planning | DOC Ethiopia | Ethiopia | DOC ET.P2.04 Electrifying Transport | Feasible financial product for minibus owners/drivers seeking finance to transition to electric vehicles reviewed/accepted by relevant financial institutions | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | A. Strategy & Planning | DOC Ghana | Ghana | DOC GH.P1.02 Energy | Decision-making framework for identifying areas of the grid suitable for VRE interconnection reviewed/accepted by GriDCO (based on GRIDCo pipeline) | Achieved | 2025-08-31
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | B. Legal & Regulatory Framework | DOC Ghana | Ghana | DOC GH.P1.02 Energy | Procurement framework for grid-connected VRES in Ghana reviewed/accepted by GriDCO | Achieved | 2025-09-30
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | A. Strategy & Planning | DOC Mozambique | Mozambique | DOC MZ.P1.02 Pemba urban development | Financial and Investment Public Assessment (PEFA & PIMA) concluded to inform municipal financial and investment decision-making | Achieved | 2025-09-30
3 | INTERMEDIATE OUTCOME 2: GCIEP TO and buy-ins support is successfully contributing to improving the enabling environment and project pipeline for infrastructure investment and economic development | OUTCOME INDICATOR 2.1 APPROVAL: No. of approved policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries supported by GCIEP TA | A. Strategy & Planning | DOC Mozambique | Mozambique | DOC MZ.P1.02 Pemba urban development | Detailed design plans to inform urban planning in Metula and Maringhana areas in Pemba reviewed/accepted by the Muncipality | Achieved | 2026-02-05
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | A. Strategy & Planning | DOC Mozambique | Mozambique | DOC MZ.P1.03 Beira urban development | Strategic approach on O&M for Coastal Protection to suppport communities improve coastral protecion infrastructure reviewed/accepted by the Municipality | Achieved | 2026-01-21
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | A. Strategy & Planning | DOC Mozambique | Mozambique | DOC MZ.P1.03 Beira urban development | Manual for Community Evacuation Planning in Case of Cyclones and Floods for Beira Municipality eviewed/accepted by the Municipality | Achieved | 2025-12-09
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | A. Strategy & Planning | DOC Mozambique | Mozambique | DOC MZ.P2.01 Land management | Municipal cadastre scaling strategy to enhance Nacala land management is reviewed/accepted by the Municipality | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | A. Strategy & Planning | DOC Mozambique | Mozambique | DOC MZ.P2.01 Land management | Municipal cadastre scaling strategy to enhance Pemba land management is reviewed/accepted by the Municipality | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | A. Strategy & Planning | DOC Mozambique | Mozambique | DOC MZ.P2.01 Land management | Digital cadastre piloted in Nacala selected areas | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | A. Strategy & Planning | DOC Mozambique | Mozambique | DOC MZ.P2.01 Land management | Digital cadastre piloted in Pemba selected areas | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | A. Strategy & Planning | DOC Mozambique | Mozambique | DOC MZ.P2.02 Climate Resilience (Beira) | Note on how training could be replicated in other disaster-prone coastal cities in Mozambique accepted/reviewed by CMB
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | A. Strategy & Planning | DOC Mozambique | Mozambique | DOC MZ.P2.03 Cities & investment | Municipal physical asset register piloted in selected areas (Pemba) | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | B. Legal & Regulatory Framework | DOC Zambia | Zambia | DOC ZM.P1.01 Energy | 100 MW suite of solar projects: Recommended Legal Risk Allocation Structure for solar power accepted/reviewed by the Office for Promoting Private Power Investment | Achieved | 2025-03-30 | Related to WS1 Fast Track Procurement
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | A. Strategy & Planning | DOC Zambia | Zambia | DOC ZM.P1.01 Energy | 100 MW suite of solar projects: Fast track procurement approach recommendations for solar projects (including detail on RfP structure, content, adjudication process, and credit support structure) reviewed/accepted by the MoE | Achieved | 2025-08-31 | Related to WS1 Fast Track Procurement
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | A. Strategy & Planning | DOC Zambia | Zambia | DOC ZM.P1.01 Energy | Recommended Policy, Legal, and Institutional framework for energy procurement to inform public procurement reviewed/accepted by FCDO Zambia and submitted to the Ministry of Energy | Achieved | 2025-09-30 | Related to WS3 Policy, Institutional and Legal Environment
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | A. Strategy & Planning | DOC Zambia | Zambia | DOC ZM.P1.01 Energy | Final recommendation of procurement process reviewed/accepted by Permanent Secretary at the Ministry of Energy | Achieved | 2025-09-30 | Related to WS4 Functional Procurement Process
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | D. Institutional capacity & governance | DOC Zambia | Zambia | DOC ZM.P2.01 Procurement & Open Access | Report on governance structure, seed funding, and key roles for the establishment of new procurement office reviewed/accepted by MoE | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | B. Legal & Regulatory Framework | DOC Zambia | Zambia | DOC ZM.P2.01 Procurement & Open Access | Electricity bill: Inputs in the bill in relation to the public service trader reviewed/accepted by MoE | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | A. Strategy & Planning | DOC Zambia | Zambia | DOC ZM.P2.01 Procurement & Open Access | Report on model that unbundles ZESCOs costs to inform open access reviewed/accepted by ZESCO | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | C. Financing Mechanisms | DOC Zambia | Zambia | DOC ZM.P2.02 Financing, Transmission & Sector | Pitch Decks to inform South African banks and other capital providers interested in Zambia’s power sector reviewed/accepted by ZESCO | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | A. Strategy & Planning | DOC Zambia | Zambia | DOC ZM.P2.02 Financing, Transmission & Sector | Priority Transmission Development Report to 2035 reviewed/accepted by ZESCO | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | A. Strategy & Planning | DOC Zambia | Zambia | DOC ZM.P2.02 Financing, Transmission & Sector | Transmission Financing Report and Recommendations reviewed/accepted by ZESCO | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | A. Strategy & Planning | DOC Indonesia | Indonesia | DOC ID.P1.01 Bappenas project planning | PSN Criteria and dashboard for determining National Strategic Projects (PSNs) reviewed/accepted | Achieved | 2025-03-31 | Related to WS1 Support to Bappenas on Prioritisation and Financing of Projects
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | A. Strategy & Planning | DOC Indonesia | Indonesia | DOC ID.P1.01 Bappenas project planning | Standarised SUMP appraisal framework with accompanying Governance and Operations Manual accepted by Bappenas following pilot application with Surabaya provincial level governement & relevant capacity building (Phase 1) | Achieved | 2025-08-31 | Related to WS2 Support to Bappenas on Appraising Projects arising from SUMPs
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | A. Strategy & Planning | DOC Indonesia | Indonesia | DOC ID.P1.02 Surabaya | Selected transit line in Gerbangkartosusilo (GKS+): High -level TOD Roadmap reviewed/accepted by Bappeda East Java Province | Achieved | 2025-09-30 | Related to WS1a Support to Surabaya on TOD Roadmap
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | B. Legal & Regulatory Framework | DOC Indonesia | Indonesia | DOC ID.P1.02 Surabaya | National Level Legislative Recommendations Report reviewed/accepted by Bappeda East Java Province | Achieved | 2025-09-30 | Related to WS3 Support to Surabaya on Integration Transport Authority
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | D. Institutional capacity & governance | DOC Indonesia | Indonesia | DOC ID.P1.02 Surabaya | Integrated transport authority (ITA) in Gerbangkartasusilo (GKS+): Institutional Roadmap reviewed/accepted by East Java Economic Bureau | Achieved | 2025-09-30 | Related to WS3 Support to Surabaya on Integration Transport Authority
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | C. Financing Mechanisms | DOC Indonesia | Indonesia | DOC ID.P2.01 Bappenas | Bappenas financing practices: Innovative Financing Study reviewed/accepted by Bappenas | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | D. Institutional capacity & governance | DOC Indonesia | Indonesia | DOC ID.P2.02 East Java Transport | Integrated transport authority (ITA) in GKS+: Input to ITA Business Model Feasibility Study reviewed/accepted by East Java Provincial Government | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | D. Institutional capacity & governance | DOC Indonesia | Indonesia | DOC ID.P2.02 East Java Transport | Integrated transport authority (ITA) in GKS+: Draft inventory of issues reviewed/accepted by East Java Provincial Governement | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | D. Institutional capacity & governance | DOC Indonesia | Indonesia | DOC ID.P2.02 East Java Transport | Integrated transport authority (ITA) in GKS+: Legal Academic Script reviewed/accepted by East Java Provincial Governement | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | A. Strategy & Planning | DOC Indonesia | Indonesia | DOC ID.P2.03 Surabaya Drainage | Surabaya Sustainable Drainage Master Plan updates for Benowo and Wiyung reviewed/accepted by city government | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | B. Legal & Regulatory Framework | DOC Philippines | Philippines | DOC PH.P1.01 Water | Viability assessment emerging from piloting Regulatory Asset Based (RAB) water tariffs and lifeline pricing in three selected water districts is reviewed/accepted by relevant Local water districts, LWUA, and Department of Environment and Natural Resources (DENR) | Achieved | 2025-09-17
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | B. Legal & Regulatory Framework | DOC Philippines | Philippines | DOC PH.P2.01 Water | Four Water Districts with the RAB and Missionary Water Tariff (MWT) frameworks successfully piloted. | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | B. Legal & Regulatory Framework | DOC Philippines | Philippines | DOC PH.P2.01 Water | RAB and MWT water tariffs: Roadmap (policy note with overview of high potential national adoption roadmap) reviewed/accepted by DENR | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | A. Strategy & Planning | DOC Philippines | Philippines | DOC PH.P1.02 TOD | Proof of Concept TOD Implementation framework accepted by Philippines DOTr | Target |  | TfL led
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | A. Strategy & Planning | DOC Philippines | Philippines | DOC PH.P1.02 TOD | Senate DepEd site pilot study - TOD masterplan accepted by Philippines DOTr and DepEd | Target |  | CI led
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | B. Legal & Regulatory Framework | DOC Vietnam | Vietnam | DOC VN.P2.01 TOD&BIM | Hanoi: TOD Resolution 16 on urban railways is informed by GCIEP technical expertise - reviewed / accepted by Metro Railway Management Board (MRB) and for submission to Hanoi People's Council for its approval | Target obsolete |  | No longer applicable, GCIEP inputs to this were captured under resolution 15
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | B. Legal & Regulatory Framework | DOC Vietnam | Vietnam | DOC VN.P2.01 TOD&BIM | Hanoi: TOD Resolution 17 on financing mechanisms is informed by GCIEP technical expertise - reviewed / accepted by Metro Railway Management Board (MRB) and for submissio nto Hanoi People's Council for its approval | Target |  | Target relevant to Phase 1 & 2
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | B. Legal & Regulatory Framework | DOC Vietnam | Vietnam | DOC VN.P2.01 TOD&BIM | HCMC: TOD Resolution guiding the implementation of Article 9 of National Assembly's Resolution 188 related to TOD development as a result of GCIEP support is reviewed/accepted by Department of Construction / Department of Planning and Architecture and submitted to HCMC People's Council for its approval | Target |  | Target relevant to Phase 1 & 2
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | B. Legal & Regulatory Framework | DOC Vietnam | Vietnam | DOC VN.P2.01 TOD&BIM | Hanoi:Strategic framework for structuring TOD projects reviewed/accepted by MRB | Achieved | 2025-10-30
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | C. Financing Mechanisms | DOC Vietnam | Vietnam | DOC VN.P2.01 TOD&BIM | Hanoi: TOD financing mechanisms and recommendations (to inform final inputs on resolution 17) reviewed/accepted by MRB | Achieved | 2025-09-30
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | B. Legal & Regulatory Framework | DOC Vietnam | Vietnam | DOC VN.P2.01 TOD&BIM | HCMC: Strategic framework for structuring TOD projects reviewed/accepted by Department of Construction / Department of Planning and Architecture (DPA) | Achieved | 2025-10-30
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | C. Financing Mechanisms | DOC Vietnam | Vietnam | DOC VN.P2.01 TOD&BIM | HCMC: TOD financing mechanisms and recommendations (to inform final inputs on TOD financing resolution) reviewed/accepted by DPA | Achieved | 2025-09-30
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | B. Legal & Regulatory Framework | DOC Vietnam | Vietnam | DOC VN.P2.01 TOD&BIM | HCMC: TOD Technical Guidelines to support in the implementation reviewed/accepted by HCMC Department of Constructuion / Department of Planning and Architecture | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | A. Strategy & Planning | TO | India | TO India Credit Enhancement Platform for climate positive urban infrastructure projects Phase 3 | 1. Detailed handbook with concept note template to operationalise the Project Support Facility reviewed/accepted by Post (CEP, India) | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | A. Strategy & Planning | TO | Tanzania | TO Tanzania Greening and enhancing accessibility of Tanzania’s public bus systems | 2. Options Analysis to inform the development of the National E-mobility Strategy reviewed/accepted by Post / Ministry of Transport (Public bus, Tanzania) | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | A. Strategy & Planning | TO | Tanzania | TO Tanzania Climate Resilience of the Port of Dar es Salaam Phase 2 | 3. Climate Adaptation Strategy and Roadmap for Dar es Salaam Port reviewed/accepted by Post / Tanzania Port Authority (Dar es Salaam Port, Tanzania) | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | A. Strategy & Planning | TO | Sierra Leone | TO Sierra Leone Strengthening the commercial framework for grid-scale power procurement | 10. Standard PPA template (solar and BESS) accepted by Electricity Generation and Transmission Compan (Commercial framework for grid-scale power procurement, Sierra Leone) | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | A. Strategy & Planning | TO | Nepal | TO Nepal Lumbini Capital City Master Plan | 4. Lumbini City Master plan reviewed/accepted by Post (Lumbini, Nepal) | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | A. Strategy & Planning | TO | Sri Lanka | TO Sri Lanka Creating the enabling environment for sustainable public transport in Colombo | 6. Briefing Note to inform Electric Bus Infrastructure and Operations for Public Transport in Colombo reviewed/accepted by Post / UNDP (Sri Lanka) | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | D. Institutional capacity & governance | TO | Sri Lanka | TO Sri Lanka Creating the enabling environment for sustainable public transport in Colombo | 7. Action Plan to operationalise the World Bank 5-phase roadmap in Colombo reviewed/accepted by Post / Ministry of Transport (Sri Lanka) | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | B. Legal & Regulatory Framework | TO | Zimbabwe | TO Zimbabwe Developing a Model Mini-Grid Policy Framework | 8. Model policy framework for solar mini-grid development in Zimbabwe reviewed/accepted by Post / government (Zimbabwe) | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | B. Legal & Regulatory Framework | TO | Solomon Islands | TO Solomon Island - Support to the Establishment of an Independent Electricity Regulator (IER) | 5. Proposed amendments to the Electricity Act, and proposals for primary legislation to establish regulator reviewed/accepted in Solomon Islands by Post / Ministry of Mines, Energy and Rural Electrification (MMERE) (Solomon Islands) | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | D. Institutional capacity & governance | TO | Sierra Leone | TO Sierra Leone Extending EDSA Revenue Protection Pilot | 9. Final Technical Report to inform a revenue protection pilot to reduce energy distribution loses in Districts 79 and 81 of Southern Province, Sierra Leone reviewed/accepted by Post / Electricity Distribution and Supply Authority (Revenue protection pilot, Sierra Leone) | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | D. Institutional capacity & governance | TO | Senegal | TO Senegal UK Support to Senegal's JETP | 11. M&E system for the Just Energy Transition Partnership (JET-P) of Senegal reviewed/accepted by JET-P Unit (Senegal) | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | C. Financing Mechanisms | TO | Kyrgyzstan | TO Kyrgyzstan Review of legal framework | 12.Financial model reviewed/accepted by Post (Kyrgyzstan) | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | B. Legal & Regulatory Framework | TO | Mexico | TO Mexico: Supporting the Development of Mexico’s Regulatory and Policy Agenda on Renewable Hydrogen | 13. Renewable Hydrogen Analytical Options Pack reviewed/accepted by Post / SENER for consideration and refinement (Mexico) | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | A. Strategy & Planning | Buy-in | South Africa | BUY-IN SOUTH AFRICA: Strategic & Special Delivery Unit (SSDU) Initiation Phase: The Department of Public Works and Infrastructure (DPWI) of Government of South Africa ​ | 14.Strategic plan with three-year overview and first-year business plan to operationalise the Strategic and Special Delivery Unit (SSDU) from the Department of Public Works and Infrastructure of the Gvt of South Africa reviewed/accepted to the DBT/ FCDO and DPWI (South Africa) | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | A. Strategy & Planning | Buy-in | South Africa | BUY-IN SOUTH AFRICA: Strategic & Special Delivery Unit (SSDU) Initiation Phase: The Department of Public Works and Infrastructure (DPWI) of Government of South Africa ​ | 15. Prioritisation framework for project inclusion to be used by the SSDU from the Department of Public Works and Infrastructure of the Gvt of South Africa reviewed/accepted by Post / DPWI (SSDU, South Africa) | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | C. Financing Mechanisms | Buy-in | Zambia | BUY-IN ZAMBIA Assssment of the Power Sector infrastructure requirements to enable demand growth in critical minerals | 16.Comparative analysis of commercial models to help transmission projects realise demand growth in critical minerals reviewed/accepted by Post (Zambia) | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | A. Strategy & Planning | Buy-in | DRC | BUY-IN DRC UK support to high-impact infrastructure and urban projects in DRC | 17.Solid Waste Management: Governance Framework for municipal waste pre-collection in Kinshasa accepted/reviewed by Post / National Agency for Territorial Development (ANAT), Urban Development Unit of Kinshasa (CDUK) (DRC) | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | D. Institutional capacity & governance | Buy-in | DRC | BUY-IN DRC UK support to high-impact infrastructure and urban projects in DRC | 18. Urban Resilience and Drainage: GIS Coordination Framework in Kinshasa accepted/reviewed by Post / ANAT & CDUK (DRC) | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | D. Institutional capacity & governance | Buy-in | DRC | BUY-IN DRC UK support to high-impact infrastructure and urban projects in DRC | 19.Transport and Mobility: Traffic management Analysis in Kinshasa reviewed/accepted by Post / ANAT & CDUK (DRC) | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | D. Institutional capacity & governance | Buy-in | South Africa | BUY-IN South Africa Development of PgMO for the office of Premier – GPG Phase 2 | 20. Outputs to operationalise the Programme Management Office (PgMO) office under the Gauteng Provincial Government (GPG) are reviewed/accepted by Post / GPG (PgMO, South Africa) | Target
3 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | C. Financing Mechanisms | Buy-in | Jordan | BUY-IN JORDAN | 21.Risk Management Facility design to support the Jordan’s National Conveyor Project during its construction and operational phase is reviewed/accepted Post (Jordan) | Target
1 | OUTCOME 2: GCIEP TA contributed to a stronger enabling environment in FCDO partner countries for the provision of climate resilient&inclusive infrastructure services | OUTCOME INDICATOR 2.1 APPROVAL: No. of approved policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries supported by GCIEP TA | B. Legal & Regulatory Framework | TO | Egypt | TO Egypt Deepening energy and infrastructure partnerships | Wheeling regulations and Renewable Guarantees of Origin approved by Egypt Energy Regulatory Authority | Achieved | Y1Q3
1 | OUTCOME 2: GCIEP TA contributed to a stronger enabling environment in FCDO partner countries for the provision of climate resilient&inclusive infrastructure services | OUTCOME INDICATOR 2.1 APPROVAL: No. of approved policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries supported by GCIEP TA | D. Institutional capacity & governance | TO | Mozambique | TO Mozambique Investment Plan / Strategy for Pemba City | Pemba Urban Structured Plan approved | Achieved | Y1Q4
2 | OUTCOME 2: GCIEP TA contributed to a stronger enabling environment in FCDO partner countries for the provision of climate resilient&inclusive infrastructure services | OUTCOME INDICATOR 2.1 APPROVAL: No. of approved policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries supported by GCIEP TA | B. Legal & Regulatory Framework | DOC Vietnam | Vietnam | DOC VN.P1.02 TOD | National Assembly Resolution 188 on urban rail and TOD passed in February 2025 | Achieved | 2025-02-01
1 | OUTCOME 2: GCIEP TA contributed to a stronger enabling environment in FCDO partner countries for the provision of climate resilient&inclusive infrastructure services | OUTCOME INDICATOR 2.1 APPROVAL: No. of approved policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries supported by GCIEP TA | A. Strategy & Planning | DOC Zambia | Zambia | DOC ZM.P1.01 Energy | Fast track procurement process approved by the Steering Committee, including Ministry of Energy and other stakeholders | Achieved | Y2Q4
1 | OUTCOME 2: GCIEP TA contributed to a stronger enabling environment in FCDO partner countries for the provision of climate resilient&inclusive infrastructure services | OUTCOME INDICATOR 2.1 APPROVAL: No. of approved policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries supported by GCIEP TA | B. Legal & Regulatory Framework | Buy-in | Ukraine | BUY-IN UKEO Ukraine 5CM | Cabinet decree passed mandating the use of the 5CM for all infrastructure business cases in the 2025 budget year | Achieved | Y2Q4
2 | INTERMEDIATE OUTCOME 1: GCIEP DOC programmes are effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 1.2: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) | I. Project pipeline | DOC Zambia | Zambia | DOC ZM.P1.01 Energy | Prioritised renewable energy pipeline of 40 solar projects based on GCIEP analysis reviewed by Office for Promoting Private Power Investment | Achieved | Y2Q4
2 | INTERMEDIATE OUTCOME 1: GCIEP DOC programmes are effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 1.2: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) | I. Project pipeline | DOC Indonesia | Indonesia | DOC ID.P1.02 Surabaya | Pipeline of prioritised urban mobility projects arising from the SUMP based on joint analysis with stakeholders through capacity building workshops | Achieved | Y2Q4 | Related to WS1a Support to Surabaya on Visioning and Project Prioritisation
2 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | A. Strategy & Planning | DOC Zambia | Zambia | DOC ZM.P1.01 Energy | Recommended fast track procurement approach accepted/reviewed by MoE | Achieved | Y2Q4
2 | INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | D. Institutional capacity & governance | DOC Indonesia | Indonesia | DOC ID.P1.01 Bappenas project planning | PSN Criteria and dashboard for determining National Strategic Projects (PSNs) accepted | Achieved | Y2Q4

## List (hidden)
STATEMENT | INDICATOR NAME | INDICATOR CATEGORY | PORTFOLIO | COUNTRY | PROJECT | NAME | STATUS
OUTCOME 1: Finance and Investment is leveraged for sustainable and inclusive infrastructure and the built environment | OUTCOME INDICATOR 1.1: Total volume of total non-GCIP financing mobilised as a result of GCIP interventions (£) | Public finance | DOC |  | BUY-IN DRC UK support to high-impact infrastructure and urban projects in DRC |  | Achieved
OUTCOME 2: GCIEP TA contributed to a stronger enabling environment in FCDO partner countries for the provision of climate resilient&inclusive infrastructure services | OUTCOME INDICATOR 2.1 APPROVAL: No. of approved policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries supported by GCIEP TA | Private finance | TO |  | BUY-IN Indonesia FCIP |  | Achieved (moved from IO 3.1)
INTERMEDIATE OUTCOME 1: GCIEP DOC programmes are effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development | OUTCOME INDICATOR 2.3 ADOPTION: Number of GCIEP supported policies / regulations / strategies / roadmaps / frameworks / institutional structures adopted as evidence of GCIEP legacy / sustainability in GCIP supported entities (sustainability) | I. Project pipeline | BUY-IN |  | BUY-IN SOUTH AFRICA: Strategic & Special Delivery Unit (SSDU) Initiation Phase: The Department of Public Works and Infrastructure (DPWI) of Government of South Africa ​ |  | Target
INTERMEDIATE OUTCOME 2: GCIEP TO and buy-ins support is successfully contributing to improving the enabling environment and project pipeline for infrastructure investment and economic development | INTERMEDIATE OUTCOME INDICATOR 1.2: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) | II. Project Specific support |  |  | BUY-IN Tanzania DURP |  | Target obsolete
INTERMEDIATE OUTCOME 3: Influencing and collaboration. Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services | INTERMEDIATE OUTCOME INDICATOR 2.1: Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritized, sequenced or developed (includes signposting stage of the infrastructure development cycle) | A. Strategy & Planning |  |  | BUY-IN UKEO Ukraine 5CM
| INTERMEDIATE OUTCOME INDICATOR 3.1 INFORMING DECISION MAKING: Number of potential policies / regulations / strategies / roadmaps / frameworks / institutional structures at FCDO partner countries that have been informed with GCIEP TA. | B. Legal & Regulatory Framework |  |  | BUY-IN ZAMBIA Assssment of the Power Sector infrastructure requirements to enable demand growth in critical minerals
|  | C. Financing Mechanisms |  |  | BUY-IN JORDAN
|  | D. Institutional capacity & governance |  |  | DOC GH.P1.01 Climate finance
|  | E. Networks & Partnerships |  |  | DOC GH.P1.02 Energy
DOC GH.P1.03 Urban
DOC GH.P2.01 Urban development project preparation support
DOC GH.P2.02 Energy
DOC GH.P2.03 Climate Finance
DOC ID.P1.01 Bappenas project planning
DOC ID.P1.02 Surabaya
DOC ID.P1.03 OIKN
DOC ID.P2.01 Bappenas
DOC ID.P2.02 East Java Transport
DOC ID.P2.03 Surabaya Drainage
DOC MZ.P1.01 Sustainable finance
DOC MZ.P1.02 Pemba urban development
DOC MZ.P1.03 Beira urban development
DOC MZ.P1.04 Nacala urban development
DOC MZ.P2.01 Land management
DOC MZ.P2.02 Urban Drainage (Beira)
DOC MZ.P2.03 Cities & investment
DOC MZ.P2.04 Climate Finance
DOC PH.P1.01 Water
DOC PH.P1.02 TOD
DOC PH.P2.01 Water
DOC PH.P2.02 TOD
DOC VN.P1.01 Green Cities
DOC VN.P1.02 TOD
DOC VN.P2.01 TOD&BIM
DOC ZM.P1.01 Energy
DOC ZM.P2.01 Procurement & Open Access
DOC ZM.P2.02 Financing, Transmission & Sector
DOC ET.P2.01 Secondary Cities
DOC ET.P2.02 Energy
DOC ET.P2.03 Digital
DOC ET.P2.04 Electrifying Transport
TO UK-Malaysia Green Transport Dialogue and Project Scoping
TO Bangladesh: Improve the management of cities
TO Egypt Deepening energy and infrastructure partnerships
TO Ghana Climate finance infrastructure plan
TO Ghana Public infrastructure investment and PPP delivery
TO Green Pipeline Scoping Study (Renewable Energy)
TO India CEP
TO India Develop Green, Resilient and Inclusive Infrastructure Standards for Cities and demonstrate access to climate finance in two pilot cities
TO Indonesia Flood Risk Assessment
TO Indonesia Joglosemar Mobility Corridor Assessment
TO Indonesia Nusantara Outline Business Case Review
TO Kenya Waste to Energy
TO Mozambique Investment Plan / Strategy for Pemba City
TO Nepal Urban feasibility Study
TO Philippines investment roundtable
TO Rwanda Spatial economic planning and effective monitoring of Land Use Master Plans implementation
TO Tanzania Enhancing price tariffs for sustainable energy
TO Tanzania Improved Waste Management for strengthening Dar es Salaam Resilience and Adaptive Capacity to Climate Shocks
TO Sri Lanka Creating the enabling environment for sustainable public transport in Colombo
TO Caribbean Resilient Infrastructure Platform (CRIP) Support
TO Egypt 5CM
TO Egypt Energy Partnerships (phase 2)
TO Ethiopia EV
TO India CEP (phase 2)
TO India Green Guidelines (phase 2)
TO Indonesia Bali Transport Study
TO Kyrgyzstan Review of legal framework
TO GCPA
TO Indonesia Feasibility Study Surabaya Mass Urban transit infrastructure
TO Indonesia Kota (phase 2)
TO Laos Urban Transport
TO Senegal UK Support to Senegal's JETP
TO Solomon Island - Support to the Establishment of an Independent Electricity Regulator (IER)
TO Ukraine PEA
TO Zambia Legal Get FiT
TO Zambia Net Metering
BUY-IN Cambodia Feasibility Study for a Green Special Economic Zone in Cambodia
TO India Credit Enhancement Platform for climate positive urban infrastructure projects Phase 3
TO Kyrgyzstan Financial modelling to inform decision-making on sovereign guarantees for renewable energy PPAs
TO Sierra Leone Strengthening the commercial framework for grid-scale power procurement
TO Sierra Leone Support to Guma Valley Water Company: Mountain Communities Bulk Water Supply
TO Sierra Leone Extending EDSA Revenue Protection Pilot
BUY-IN South Africa Development of PgMO for the office of Premier – GPG Phase 2
TO Tanzania Climate Resilience of the Port of Dar es Salaam Phase 2
TO Tanzania Greening and enhancing accessibility of Tanzania’s public bus systems
TO Zimbabwe Developing a Model Mini-Grid Policy Framework
TO Laos Enhancing Urban Transport Management
TO Sierra Leone Strengthening the commercial framework for grid-scale power procurement
TO Nigeria Unlocking waste to value opportunities for UK and international expertise in Lagos
TO Mauritius Developing TOR for FS for 100MW Offshore Wind
TO Nepal Lumbini Capital City Master Plan
TO Mexico: Supporting the Development of Mexico’s Regulatory and Policy Agenda on Renewable Hydrogen

## TO& Buy-in nested LF
PROGRAMME NAME: | Green Cities and Infrastructure Programme (GCIEP) Y3 Logframe - TO and Buy-In Portfolio (22 January 2026)
OUTCOME 1 | Outcome Indicator 1.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Finance and Investment is leveraged for sustainable and inclusive infrastructure and the built environment (DOC only and TO - if reported by Post) (REPORTED ANNUALLY) | Total volume of total non-GCIEP financing mobilised as a result of GCIEP interventions (£ ) Disaggregation by: type of funding organisation (Private/Donor/Public -National/Municipal), financing categories (catalysed, facilitated, unlocked, and reallocated) To track off logframe, GCIEP country programmes where non-FCDO funds have been leveraged downstream | Planned -annual | n/a | Too early | Too early | £150 million (GetFiT- legal support for the financing of 120 MW for 6 solar projects in Zambia) | *GCIEP TA makes a contribution towards facilitating investment into urban economic infrastructure projects and overcoming obstacles to project delivery *Partner government continued support for: i) pro-poor, inclusive, low carbon and resilient objectives and targeted approaches; and ii) channel private and public investment into urban development and economic infrastructure * COMMITTED refers to: The financing quantified has already been committed/mobilised by other investors, where GCIEP TA is being used to make the investment “bigger, better or faster."
|  | Achieved - annual |  | Too early | £885 million ( £800 million -CEP of NaBFID in India and $110 million (£85 million) from DURP In Tanzania)
|  | Achieved - cumulative |  | Too early | £885 million
Source
GCIEP DOC and TO RM databases Note: £1bn committed is expected to come from: TO Zambia (Get FIT): £150m; and TO Tanzania buy-in (SWM): $110m); Ghana Water and Transport (EU): EUR 100-130 m; CEP (India) £800m
| Outcome Indicator 1.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Volume of public finance mobilised for climate change purposes (£) (as a result of GCIEP interventions ) (disag by new financing vs reallocated financing) (ICF KPI 11) | Planned -annual | n/a | n/a | n/a | n/a: ICF KPI methodology only allows actuals to be reported
|  | Achieved - annual |  | n/a | £885 million ( £800 million -CEP of NaBFID in India and $110 million (£85 million) from DURP In Tanzania)
|  | Achieved - cumulative |  | n/a | £885 million
Source
GCIEP RM databases and ICF monitoring ICF KPI Methodology: https://assets.publishing.service.gov.uk/media/5b17935be5274a190c1b6f8c/KPI11-Public-finance-Updated-methodology.pdf
| Outcome Indicator 1.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Volume of private finance mobilised for climate change purposes (£) (as a result of GCIEP interventions) (ICF KPI 12) | Planned -annual | n/a | Too early | n/a | n/a: ICF KPI methodology only allows actuals to be reported
|  | Achieved - annual |  | Too early | 0
|  | Achieved - cumulative |  | Too early | 0
|  | Source |  |  |  |  | RISK RATING
|  | GCIEP RM databases and ICF monitoring ICF KPI Methodology: https://assets.publishing.service.gov.uk/media/65e0b9913f6945001d036030/KPI-12-volume-private-finace-mobilised.pdf |  |  |  |  | MODERATE
OUTCOME 2 | Outcome 2.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
GCIEP TA contributed to a stronger enabling environment in FCDO partner countries for the provision of climate resilient&inclusive infrastructure services (REPORTED ANNUALLY) | APPROVAL: Number of approved policies/regulations/strategies/roadmaps/frameworks/institutional structures at FCDO partner countries supported by GCIEP TA (disag by Strategy & Planning, Legal & Regulatory Framework, Financing Mechanisms, Institutional capacity & governance, Networks & Partnerships) | Planned -annual | n/a | n/a | 1. Cabinet decree passed mandating the use of the 5CM for all infrastructure business cases in the 2025 budget year (Buy-in Ukraine) | 1. 120 MW for 6 solar projects: Implementation Agreements and Long-term liquidity mechanism approved by lenders and the government of Zambia(Get Fit Zambia) | * Collaboration with CoE DPs collaboration increase urban and infrastructure effectiveness leading to local adoption and replication * No material change in government priorities with any political changes in countries that undergo national elections * APPROVAL: Formal endorsement of GCIEP supported policy/regulations/strategies/roadmaps/frameworks/institutional structures at FCDO partner countries by the beneficiary stakeholder (or the appropriate designated authority) *ADOPTION: The formal embedding and / or implementation of a GCIEP-supported structure, process, methodology or practices by FCDO partner countries, maintaining the core design and function of the original model, through minor contextual adjustments may be made. A deliverable is counted either as APPROVED or ADOPTED but not both, except in the case where GCIEP provides continuous to support over time resulting in an evolution from APPROVAL to ADOPTION. In such exceptional cases policy/regulations/strategies/roadmaps/frameworks/institutional structures may be reported at both level, usually for different years.
|  | Achieved - annual |  | 2 1.Egypt EERA- improved wheeling regulations (TO Egypt EERA) 2. Pemba MoZ - Urban Structured Plan approved (TO Pemba) | 1. Cabinet decree passed mandating the use of the 5CM for all infrastructure business cases in the 2025 budget year ( Buy-in Ukraine)
|  | Achieved - cumulative |  | 2 | 3
Source
GCIEP L&C tracking tool, GCIEP K&L documentation
| Outcome 2.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| ADOPTION: Number of GCIEP supported policies/regulations/strategies/roadmaps/frameworks/institutional structures adopted as evidence of GCIEP legacy / sustainability in GCIEP supported entities (sustainability) (disag by Strategy & Planning, Legal & Regulatory Framework, Financing Mechanisms, Institutional capacity & governance, Networks & Partnerships) | Planned -annual | n/a | Too early | Too early | 0
|  | Achieved - annual |  | Too early | 0
|  | Achieved - cumulative |  | Too early | 0
|  | Source |  |  |  |  | RISK RATING
|  | GCIEP RM databases and Intervention Pathways Packages at the intervention level |  |  |  |  | MODERATE
Y3 Interim PLF (August 2025) the following indicators were considered obsolete in agreement with FCDO: * Outcome 2.2 Replication: Number of GCIEP supported structures, processes, and / or methodologies replicated (and adapted) by country government ministries
INTERMEDIATE OUTCOME 2 | INT Outcome Indicator 2.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
High quality TO and buy-ins support is successfully contributing to improving the enabling environment and project pipeline for infrastructure investment and economic development (REPORTED ANNUALLY) | Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritized, sequenced or developed (includes signposting stage of the infrastructure development cycle) DDisaggregated by stage of the infrastructure development cycle: (I) Project pipeline and (II) Project specific support including (a) Planning & preparation (concept note, business cases, (pre) feasibility studies); (b) Financing structuring (project development agreement, investment round tables etc); (c) Commercial and financial close; (d) Procurement; and (e) Implementation | Planned -annual | n/a | n/a | 0 | (I) Project pipeline:3 TO 1.NaBFID-aligned project pipeline for waste to energy and waste water sector projects for urban local bodies in Indian cities reviewed/accepted by Post (India) 2. Project prioritisation report capturing the long-list and shortlisted urban development projects for Lumbini province (with 5 brief concept notes) reviewed/accepted by Post (Nepal) Buy-In 3.Prioritised project pipeline to revitalise national unused and obsolete public building insfraestructure reviewed/accepted by Post/DPWI (SSDU South Africa) (II) Project specific support: 6 TO 1. Offshore wind project: ToR for feasibility study reviewed/accepted by Post / GoM (Mauritius) 2. Surabaya urban mass transit feasibility study reviewed/accepted by Post /client (Indonesia) Buy-In 3. Green Special Economic Zone Concept master plan for ~174hectare project site reviewed/accepted by Post (GEZ Cambodia) 4.Solid Waste Management: Technical design for future pre-collection platform, payment systems and sorting centre in Kinshasa reviewed/accepted b Post, ANAT & CDUK (DRC) 5.Urban Resilience and Drainage: Technical design for THIMO-based desilting operations in Kinshasa reviewed/accepted by Post / ANAT & CDUK (DRC) 6.Transport and Mobility: Technical design for a transport project in Kinshasa reviewed/accepted by Post / ANAT & CDUK (DRC) | *GCIEP can effectively target its assistance, to choose the right agencies/municipalities and/or institutions with which to partner and select and test the adequate interventions *No material change in government priorities with any political changes in countries that undergo national elections * Well prepared projects (including feasibility studies) supported by GCIP will attract the necessary downstream financing
|  | Achieved - annual |  | 0 | 0 | 1. Surabaya urban mass transit feasibility study reviewed/accepted by Post /client (Indonesia)
|  | Achieved - cumulative |  | 0 | 0
Source
GCIEP monitoring and operational databases
| INT Outcome Indicator 2.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Percentage (and number into brackets) of follow on TO and Buy-ins WPs (repeat business as a result of stakeholder satisfaction or and FCDO strategic interest) | Planned -annual | n/a | n/a (demand driven) | n/a (demand driven) | n/a (demand driven)
|  | Achieved - annual |  | 13 (9 completed WPs integrated into DOCs; 4 WPs with follow on WPs) | 7
|  | Achieved - cumulative |  | 13 (9 completed WPs integrated into DOCs; 4 WPs with follow on WPs) | 20
|  | Source |  |  |  |  | RISK RATING
|  | GCIEP monitoring and operational databases Note: Follow on TO WPs can also be under DOC Programme |  |  |  |  | MODERATE
INTERMEDIATE OUTCOME 3 | INT Outcome Indicator 3.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Influencing and collaboration Uptake of relevant knowledge and evidence generated by GCIEP and/or its delivery partners by FCDO partner governments as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services (REPORTED ANNUALLY) | INFORMING DECISION MAKING: Number of policies/regulations/strategies/roadmaps/frameworks/institutional structures at FCDO partner countries that have been informed with contributions from GCIEP TA. (disag by Strategy & Planning, Legal & Regulatory Framework, Financing Mechanisms, Institutional capacity & governance, Networks & Partnerships) | Planned -annual |  | n/a | n/a | TO 1. Detailed handbook with concept note template to operationalise the Project Support Facility reviewed/accepted by Post (CEP, India) 2. Options Analysis to inform the development of the National E-mobility Strategy reviewed/accepted by Post / Ministry of Transport (Public bus, Tanzania) 3. Climate Adaptation Strategy and Roadmap for Dar es Salaam Port reviewed/accepted by Post / Tanzania Port Authority (Dar es Salaam Port, Tanzania) 4. Lumbini City Master plan reviewed/accepted by Post (Lumbini, Nepal) 5. Proposed amendments to the Electricity Act, and proposals for primary legislation to establish regulator reviewed/accepted in Solomon Islands by Post / Ministry of Mines, Energy and Rural Electrification (MMERE) (Solomon Islands) 6. Briefing Note to inform Electric Bus Infrastructure and Operations for Public Transport in Colombo reviewed/accepted by Post / UNDP (Sri Lanka) 7. Action Plan to operationalise the World Bank 5-phase roadmap in Colombo reviewed/accepted by Post / Ministry of Transport (Sri Lanka) 8. Model policy framework for solar mini-grid development in Zimbabwe reviewed/accepted by Post / government (Zimbabwe) 9. Final Technical Report to inform a revenue protection pilot to reduce energy distribution loses in Districts 79 and 81 of Southern Province, Sierra Leone reviewed/accepted by Post / Electricity Distribution and Supply Authority (Revenue protection pilot, Sierra Leone) 10. Standard PPA template (solar and BESS) accepted by Electricity Generation and Transmission Compan (Commercial framework for grid-scale power procurement, Sierra Leone) 11. M&E system for the Just Energy Transition Partnership (JET-P) of Senegal reviewed/accepted by JET-P Unit (Senegal) 12.Financial model reviewed/accepted by Post (Kyrgyzstan) 13. Renewable Hydrogen Analytical Options Pack reviewed/accepted by Post / SENER for consideration and refinement (Mexico) Buy-In 14.Strategic plan with three-year overview and first-year business plan to operationalise the Strategic and Special Delivery Unit (SSDU) from the Department of Public Works and Infrastructure of the Gvt of South Africa reviewed/accepted to the DBT/ FCDO and DPWI (South Africa) 15. Prioritisation framework for project inclusion to be used by the SSDU from the Department of Public Works and Infrastructure of the Gvt of South Africa reviewed/accepted by Post / DPWI (SSDU, South Africa) 16.Comparative analysis of commercial models to help transmission projects realise demand growth in critical minerals reviewed/accepted by Post (Zambia) 17.Solid Waste Management: Governance Framework for municipal waste pre-collection in Kinshasa accepted/reviewed by Post / National Agency for Territorial Development (ANAT), Urban Development Unit of Kinshasa (CDUK) (DRC) 18. Urban Resilience and Drainage: GIS Coordination Framework in Kinshasa accepted/reviewed by Post / ANAT & CDUK (DRC) 19.Transport and Mobility: Traffic management Analysis in Kinshasa reviewed/accepted by Post / ANAT & CDUK (DRC) 20. Outputs to operationalise the Programme Management Office (PgMO) office under the Gauteng Provincial Government (GPG) are reviewed/accepted by Post / GPG (PgMO, South Africa) 21.Risk Management Facility design to support the Jordan’s National Conveyor Project during its construction and operational phase is reviewed/accepted Post (Jordan) | * Central FCDO and country offices are open to learning from and being influenced by GCIEP generated knowledge - when relevant . * Deliverables can include policies, regulations, roadmaps, strategies, frameworks, institutional structure / governance report, etc. that have been submitted/reviewed/accepted/approved by the beneficiary stakeholder/s (depending on country context). *Targets and results include deliverables that are REVIEWED/ ACCEPTED by the beneficiary stakeholder that are used as source of evidence, insights, or recommendations to inform policies, strategies, or actions in FCDO partner countries.
Achieved - annual
|  | Source |  |  |  |  | RISK RATING
|  | GCIEP monitoring and operational databases |  |  |  |  | MODERATE
INTERMEDIATE OUTCOME 4 | INT Outcome Indicator 4.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
DOC interventions/ TO work packages (WPs) have successfully integrated GEDSI risks and opportunities resulting in Empowerment (REPORTED ANNUALLY) | % of DOC interventions/ TO work packages (WPs) that include GEDSI considerations in accordance with Level 2 - Empowerment - as per the FCDO GEDSI framework (realised target ambition) - Linked to Output 4 | Planned -annual |  |  | 50% | 50% | *Resources at DOC and TO level are deployed to ensure that GEDSI is effectively mainstreamed during implementation, regularly identifying and assessing GEDSI risks and opportunities
|  | Achieved - annual |  |  | 100%
|  | Source |  |  |  |  | RISK RATING
|  | GCIEP GEDSI monitoring; GCIEP deliverables TOR and GCIEP work package progress reports Note: it only applies to interventions that have GEDSI potential |  |  |  |  | MODERATE
OUTPUT 1 | Output Indicator 1.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
High-quality TA deliverables completed by GCIEP for FCDO posts to facilitate economic transformation and inclusive growth (in line with VfM targets) (REPORTED QUARTERLY) | Targeted-offer & Buy-ins Number of TO and buy-in work packages completed and submitted for approval (#) Disaggregation by: portfolio (TO and Buy-ins), budget type (ODA, non-ODA, combined) | Planned -annual | n/a | n/a | n/a | n/a
|  | Achieved - annual |  | 18 (14: ODA; 4-non ODA) | 11 (9 ODA, 1 non ODA, 1 combined)
|  | Achieved - cumulative |  | 18 (14: ODA; 4-non ODA) | 29 (23 ODA, 5 non ODA, 1 combined)
Source
GCIEP monitoring and operational databases
| Output Indicator 1.4 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Targeted-offer & Buy-ins Percentage of the deliverables planned at the start of each quarter that are completed. Disaggregation by: portfolio (TO and Buy-ins), budget type (ODA, non-ODA, combined) | Planned -annual | n/a | n/a | 70% | 70%
|  | Achieved - annual |  | n/a | 90.3% (89.4% ODA, 95.8% non ODA, 75% Combined)
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
40% |  | GCIEP monitoring and operational databases Note: Total number of deliverables completed during the quarter / total number of deliverables planned to be completed as per workplan submitted to FCDO at the start of the quarter. It is expected that the deliverables detailed in the TO& Buy-in workplan will be updated on a quarterly basis in line with adaptive management best practice. |  |  |  |  | MINOR
Y3 Interim PLF (August 2025) the following indicators were considered obsolete in agreement with FCDO: * Output Indicator 1.1 (a) DOC Scoping: Number of active TA deliverables to scope proposed GCIEP DOC programmes (# scoping reports) * Output Indicator 1.1 (b) "DOC Detailed Design: Number of active TA deliverables to undertake detailed design of proposed GCIEP DOC programmes (# of DOC interventions)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Proactive strategic collaboration to maximise effectiveness in GCIEP delivery in TO and/or DOC countries (REPORTED QUARTERLY) | No. of instances where GCIEP team has worked and/or coordinated* with partners** A) GCIEP DOC interventions B) GCI CoE delivery partners C) Any other UK expert organisations D) Development partners (instances that DOC and Buy-ins have collaborated with development partners) Disaggregation by: portfolio (DOC, TO and Buy-in) | Planned -annual | n/a | n/a | n/a | B) 5 -TfL, NISTA,Ofgem, Ornance Survey (OS), British Geological Survey (BGS) C) 7 -London School of Economics, NEC4, PLP Architecture, Royal Institution Chartered Surveyors, Unlocking Expert Credit Financing, WRAP NGO, FSD Africa (Nigeria) (Mauritius) D) 4- United Nations Environment Programme, Kfw, World Bank, JICA Phase 1: B) 6 (4 TO: TfLx2, NISTAx1, Ofgemx1 ¦ 2 BUY-IN: BGSx1, OSx1) C) 7 (6 TO: Arup, LSE, NEC4, PLP Architecture, Royal Institution Chartered Surveyors, Unlocking Expert Credit Financing ¦ 1 BUY-IN: WRAP NGO) D) 6 (5 TO: United Nations Environment Programme, World Bankx2, ADB, JICA ¦ 1 BUY-IN: World Bank) Phase 2: B) 1 (NISTA) C) 2 FSD Africa (Nigeria), D) 1 KfW (Zambia) UNEP (Mauritius) | *GCIEP can effectively target its assistance, to choose the right agencies/municipalities and/or institutions with which to partner and select the right interventions *Targets were not applicable until the end of Year 2 , as per agreement with FCDO given that we are a demand driven programme working under adaptive programming principles. However, since September 2025 (starting of Phase 2 that finishes in March 2026) it was decided to insert targets when possible, that have been extracted from the approved TORs.
|  | Achieved - annual |  | 0 | b) 6 (4 TO: TfLx2, NISTAx1, Ofgemx1 ¦ 2 BUY-IN: BGSx1, OSx1) c) 7 (6 TO: Arup, LSE, NEC4, PLP Architecture, Royal Institution Chartered Surveyors, Unlocking Expert Credit Financing ¦ 1 BUY-IN: WRAP NGO) c) 6 (5 TO: United Nations Environment Programme, World Bankx2, ADB, JICA ¦ 1 BUY-IN: World Bank)
|  | Achieved - cumulative |  | 0 | b) 6 c) 7 d) 6
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
10% |  | GCIEP monitoring and operational databases Notes: *Co-ordination defined as having an active Community of Practice/signed MoU/other formal engagement process in place) ** Partners defined as any in-country international development agency or donor based in a DOC country ***GCIEP CoE delivery partners: Cross Rail Intl, Ofgem, Infrastructure and Projects Authority, Transport for London, BSI; CATAPULT, Ordinance Survey and British Geological Survey |  |  |  |  | MINOR
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Enhancing capacity and knowledge to strengthen GCIEP supported institutions and agencies in partner countries (disag by DOC and TO) (REPORTED QUARTERLY) | Percentage and number of people certified in UK tools and methodologies (Only applicable if there is formal UK certification offer. UK tools and methodologies with certification exam include, for example, 5CM) | Planned -annual | n/a | n/a | n/a | 360 | * GCIEP has the capacity to deliver targeted and high quality trainings, adapted to the needs to targeted stakeholders *GCIEP can leverage on UK expertise to successfully deliver TA *Targets were not applicable until the end of Year 2 , as per agreement with FCDO given that we are a demand driven programme working under adaptive programming principles. However, since September 2025 (starting of Phase 2 that finishes in March 2026) it was decided to insert targets when possible, that have been extracted from the approved TORs.
|  | Achieved - annual |  | 93% (52/56) | 91.5% (205/224)
|  | Achieved - cumulative |  | 93% (52/56) | 91.8% (257/280)
Source
GCIEP RM and operational databases Note: Number of people certified / total number of people trained in UK tools and methodologies taking the exam.
| Output Indicator 3.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number (#) of people trained via GCIEP supported work packages/interventions Disaggregation: portfolio (DOC, TO, Buy-in), women professionals, people with disabilities, and youth, indicate if UK methodology. | Planned -annual | n/a | n/a | n/a | 840
|  | Achieved - annual |  | TO: 223 total (100 women & 1 prefer not to say, 17 Youth) | TO: 121 total (43 women) BUY-IN: 120 total (61 women, 26 Youth) UKEO Ukraine: 213 total (109 women)
|  | Achieved - cumulative |  | 223 total (100 women & 1 prefer not to say, 17 Youth) | 667 Total (313 women & 1 prefer not to say, 43 Youth)
Source
GCIEP RM and operational databases
| Output Indicator 3.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| % of participants indicating that the training/capacity building in Output 3.1 or 3.2 was "useful" or "very useful" on a 5 point scale | Planned -annual | n/a | n/a | 70% | 85%
|  | Achieved - annual | 97.35% | 99% (110/111) | 96.6% (258/267)
|  | Achieved - cumulative |  | 99% (110/111) | 97.35% (368/378)
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
10% |  | GCIEP RM and operational databases |  |  |  |  | MINOR
OUTPUT 4 | Output Indicator 4.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
GEDSI is mainstreamed across GCIEP DOC interventions and Target Offer (TO) work packages (WPs) (disag by DOC and TO) (REPORTED ANNUALLY) | % of GCIEP supported DOC interventions/TO WPs that have an ambition of level 2 - Empowerment as per the FCDO GEDSI framework Disaggregated by FCDO GEDSI framework levels 1-3 | Planned - annual | n/a | n/a | 50% | 50% | *The FCDO GEDSI Framework is effective into translating FCDO’s GEDSI policies into programming; enabling GCIEP to take a structured and practical approach to exploring how GCIEP work packages can maximise benefits to disadvantaged and vulnerable groups
|  | Achieved - annual |  | 41% | 40%
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
15% |  | GCIEP GEDSI monitoring; GCIEP deliverables TOR and GCIEP work package progress reports Note: it only applies to interventions that have GEDSI potential |  |  |  |  | MINOR
OUTPUT 5 | Output Indicator 5.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
CN&E is mainstreamed across GCIEP DOC interventions and Target Offer (TO) work packages (WPs) (ICF compliance) (disag by DOC and TO) (REPORTED ANNUALLY) | % of GCIEP supported DOC interventions/TO work packages that are mainstreaming CN&E | Planned - annual |  | 100% | 100% | 100% | *ICF compliant: An interventions that contributes to at least 1 ICF KPI indicator *ICF KPI TA methodology only allows actuals to be reported
|  | Achieved - annual |  | 100% | 100%
Source
GCIEP ICF monitoring; DOC intervention ToRs and TO Work Package ToRs; GCIEP progress reports
| Output Indicator 5.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| % of total spend that is ICF compliant in relation to the total £ value of GCIEP programmes - of eligible ODA | Planned - annual | n/a | 30% | 80% | 80%
|  | Achieved - annual |  | 87% | 87%
Source
GCIEP ICF monitoring; DOC intervention ToRs and TO Work Package ToRs; GCIEP progress reports
| Output Indicator 5.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of countries supported by ICF technical assistance ICF TA KPI 1 (reported only on completed DOC interventions/TO WPs) | Planned - annual | n/a | n/a | n/a | n/a
|  | Achieved - annual |  | 18 (Tanzania, Nepal, Bangladesh, Rwanda, Egypt, Ghana, Mozambique, India, Indonesia (direct TO) + through direct and targeted (multi-country ASLIP training) Cambodia, Laos, Philippines, Singapore, Timor Leste, Thailand, Malaysia, Vietnam and Brunei) | 22 New countries (11): (DRC, Kyrgyzstan, South Africa, Zambia, Myanmar (part of ASLIP), CRIP - Saint Lucia, Grenada, Dominica, Saint Vincent and the Grenadines, Belize, Jamaica) Same countries supported as in Year 1 (11): Tanzania, Egypt, India, Indonesia, (multi-country ASLIP training) Cambodia, Laos, Philippines, Timor Leste, Thailand, Malaysia and Vietnam)
|  | Achieved - cumulative |  | 18 | 29 (unique counting of countries) Bangladesh, Belize, Brunei, Cambodia, Dominica, DRC, Egypt, Ghana, Grenada, India, Indonesia, Jamaica, Kyrgyzstan, Laos, Malaysia, Mozambique, Myanmar, Nepal, Philippines, Rwanda, Saint Lucia, Saint Vincent and the Grenadines, Singapore, South Africa, Tanzania, Thailand, Timor Leste, Vietnam and Zambia.
Source
GCIEP CN&E monitoring; DOC intervention ToRs and TO work package ToRs; GCIEP progress reports
| Output Indicator 5.4 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of individuals supported by ICF technical assistance ICF TA KPI 2.1 (reported only on completed DOC interventions/TO work packages) | Planned - annual | n/a | n/a | n/a | n/a
|  | Achieved - annual |  | 288 | 246
|  | Achieved - cumulative |  | 288 | 534 (cumulative)
Source
GCIEP CN&E monitoring; DOC intervention ToRs and TO work package ToRs; GCIEP progress reports
| Output Indicator 5.5 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of organisations supported by ICF technical assistance ICF TA KPI 2.2 (reported only on completed DOC interventions/TO WPs) | Planned - annual | n/a | n/a | n/a | n/a
|  | Achieved - annual |  | 57 | 76
|  | Achieved - cumulative |  | 57 | 117 (cumulative) 16 organisations consulted on multiple interventions (NITI Aayog (Indonesia), Ministry of Transport, (Indonesia) MoF - PIAD and NRECCU - Natural Resource, Environmental and Climate Change Unit (Ghana), Public Investment Units (Ghana), Ghana Infrastructure Investment Fund (GIIF), MESTI (Ghana), Environmental Protection Authority (Ghana), Ministry of Transport (Ghana), Public Procurement Authority (Ghana), National Development Planning Commission (Ghana), NaBFID (National Bank for Financing Infrastructure Development), EgyptERA, Dar es Salaam City Council (DCC), Central Public Health and Environmental Engineering Organisation (CPHEEO) (Indonesia), MoHUA (Ministry of Housing and Urban Affairs) (Indonesia) and National Institute of Urban Affairs (NIUA) (Indonesia).
Source
GCIEP CN&E monitoring; DOC intervention ToRs and TO work package ToRs; GCIEP progress reports
| Output Indicator 5.6 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of climate policies informed by ICF technical assistance ICF TA KPI 3 (reported only on completed DOC interventions/TO WPs) | Planned - annual | n/a | n/a | n/a | n/a
|  | Achieved - annual |  | 0 | 2
|  | Achieved - cumulative |  | 0 | 2
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
15% |  | GCIEP CN&E monitoring; DOC intervention ToRs and TO work package ToRs; GCIEP progress reports |  |  |  |  | MINOR
OUTPUT 6 | Output Indicator 6.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Learning (evidence) produced and in place for GCIEP to collate and disseminate UK and international urban / infrastructure expertise within GCIEP, FCDO, and to the wider ecosystem (REPORTED QUARTERLY) | No. of GCIEP products (analysis and learning including events) that deliver insights which inform/shape FCDO/wider development partner policies and programmes Disaggregation by events and products | Planned - annual | n/a | n/a | n/a | 30 | *Sufficient GCIEP budget is allocated to undertake planned L&C activities. *Targets were not applicable until the end of Year 2 , as per agreement with FCDO given that we are a demand driven programme working under adaptive programming principles. However, since September 2025 (starting of Phase 2 that finishes in March 2026) it was decided to insert targets when possible, that have been extracted from the approved TORs.
|  | Achieved - annual |  | 1 product (TO) | 9 events (5 TO & 4 BUY-IN) 16 products (15 TO & 1 BUY-IN)
|  | Achieved - cumulative |  | 1 product | 9 events 17 products
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
10% |  | GCIEP RM and L&C monitoring, GCIEP K&L documentation (including links to public KPs and materials published) Note: a. A GCIEP Product is any written material produced by GCIEP and/or its delivery partners, through its DOC interventions/ TO work packages, that has been repackaged according to targeted audience/s and dissemination channel/s including learning events, that seek to contribute to the body of infra delivery and urban development knowledge towards improving FCDO and GCIEP delivery partners programming . This GCIEP product is out of the budget of the TO WP. |  |  |  |  | MINOR+CA1:H135
Note on G34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Make the project or group of projects the subject. 1. What kind of projects are they and where? 2. the wind farm is the subject - the feasibilty study will be the GCIEP conttribution 3. what kind of projects? 4. Good 5. Switch the order so that the project is first and the contribution second. 6. what kind of projects? 7. what’s the project? Expand acronyms. 8. expand acronyms and make it more clear what the project is. 9. where is this project? 10. be a more specific about what the project is. Reply: Done as requested above. Target 5 has been deleted in line with recently approved change log for this ToR making the target redundant. Reply: Your suggestion and proposed amended have been taken forward.
Note on G46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: As above, there needs to be enough detail here on each item for an external reviewer to understand what the policy etc is and what GCIEP has done to inform it. Expand acronyms. Reply: Put in name of intervention and what the deliverable contributed towards Reply: Targets amends to they detail what the deliverable is informing.

## ETHIOPIA nested LF
PROGRAMME NAME: | Green Cities, Infrastructure and Energy Programme (GCIEP) Y3 Logframe - DOC ETHIOPIA (22 January 2026)
OUTCOME 1 | Outcome Indicator 1.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Finance and Investment is leveraged for sustainable and inclusive infrastructure and the built environment in Vietnam (DOC only and TO - if reported by Post) (REPORTED ANNUALLY) | Total volume of total non-GCIEP financing mobilised as a result of GCIEP interventions in Vietnam (£ ) Disaggregation by: type of funding organisation (Private/Donor/Public -National/Municipal), financing categories (catalysed, facilitated, unlocked, and reallocated) To track off logframe, GCIEP country programmes where non-FCDO funds have been leveraged downstream | Planned -annual | n/a | n/a | n/a | 0 | *GCIEP TA makes a contribution towards facilitating investment into urban economic infrastructure projects and overcoming obstacles to project delivery *Partner government continued support for: i) pro-poor, inclusive, low carbon and resilient objectives and targeted approaches; and ii) channel private and public investment into urban development and economic infrastructure *Target and Results will be based only on DOC interventions; but GCIEP will also report on results from TO work packages, in case there is GCIEP contribution and results have been tracked either by GCIEP or FCDO Post (post completion monitoring) * COMMITTED refers to: The financing quantified has already been committed/mobilised by other investors, where GCIEP TA is being used to make the investment “bigger, better or faster."
|  | Achieved - annual | n/a | n/a | n/a
|  | Achieved - cumulative | n/a | n/a | n/a
Source
GCIEP DOC and TO RM databases
| Outcome Indicator 1.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Volume of public finance mobilised for climate change purposes in Vietnam (£) (as a result of GCIEP interventions ) (disag by new financing vs reallocated financing) (ICF KPI 11) | Planned -annual | n/a | n/a | n/a | n/a: ICF KPI methodology only allows actuals to be reported
| ICF KPI 12 Volume of private finance mobilised for climate change purposes | Achieved - annual | n/a | n/a | n/a
|  | Achieved - cumulative | n/a | n/a | n/a
Source
GCIEP RM databases and ICF monitoring ICF KPI Methodology: https://assets.publishing.service.gov.uk/media/5b17935be5274a190c1b6f8c/KPI11-Public-finance-Updated-methodology.pdf
| Outcome Indicator 1.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Volume of private finance mobilised for climate change purposes in Vietnam (£) (as a result of GCIEP interventions) (ICF KPI 12) | Planned -annual | n/a | n/a | n/a | n/a: ICF KPI methodology only allows actuals to be reported
| ICF KPI 12 Volume of private finance mobilised for climate change purposes | Achieved - annual | n/a | n/a | n/a
|  | Achieved - cumulative | n/a | n/a | n/a
|  | Source |  |  |  |  | RISK RATING
|  | GCIEP RM databases and ICF monitoring ICF KPI Methodology: https://assets.publishing.service.gov.uk/media/65e0b9913f6945001d036030/KPI-12-volume-private-finace-mobilised.pdf |  |  |  |  | MODERATE
OUTCOME 2 | Outcome 2.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
GCIEP TA contributed to a stronger enabling environment for the provision of climate resilient&inclusive infrastructure services (REPORTED ANNUALLY) | APPROVAL: Number of approved policies/regulations/strategies/roadmaps/frameworks/institutional structures in Ethiopia supported by GCIEP TA (disag by Strategy & Planning, Legal & Regulatory Framework, Financing Mechanisms, Institutional capacity & governance, Networks & Partnerships) | Planned -annual | n/a | n/a | n/a | 0 | *Central FCDO and country offices are open to learning from and being influenced by GCIEP generated knowledge - when relevant * Collaboration with CoE DPs collaboration increase urban and infrastructure effectiveness leading to local adoption and replication * No material change in government priorities with any political changes in countries that undergo national elections * Deliverables can include policies, regulations, roadmaps, strategies, frameworks, institutional structure / governance report, etc. that have been submitted/reviewed/accepted/approved by the beneficiary stakeholder/s (depending on country context) * APPROVAL: Formal endorsement of GCIEP supported policy/regulations/strategies/roadmaps/frameworks/institutional structures at FCDO partner countries by the beneficiary stakeholder (or the appropriate designated authority) *ADOPTION: The formal embedding and / or implementation of a GCIEP-supported structure, process, methodology or practices by FCDO partner countries, maintaining the core design and function of the original model, through minor contextual adjustments may be made. A deliverable is counted either as APPROVED or ADOPTED but not both, except in the case where GCIEP provides continuous to support over time resulting in an evolution from APPROVAL to ADOPTION. In such exceptional cases policy/regulations/strategies/roadmaps/frameworks/institutional structures may be reported at both level, usually for different years.
|  | Achieved - annual | n/a | n/a | n/a
|  | Achieved - cumulative | n/a | n/a | n/a
Source
GCIEP L&C tracking tool, GCIEP K&L documentation Note: Deliverables must be approved by the beneficiary entity
| Outcome 2.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| ADOPTION: Number of GCIEP supported policies/regulations/strategies/roadmaps/frameworks/institutional structures adopted as evidence of GCIEP legacy / sustainability in GCIEP supported entities in Vietnam (sustainability) (disag by Strategy & Planning, Legal & Regulatory Framework, Financing Mechanisms, Institutional capacity & governance, Networks & Partnerships) | Planned -annual | n/a | n/a | n/a | 0
|  | Achieved - annual | n/a | n/a | n/a
|  | Achieved - cumulative | n/a | n/a | n/a
|  | Source |  |  |  |  | RISK RATING
|  | GCIEP RM databases and Intervention Pathways Packages at the intervention level |  |  |  |  | MODERATE
Y3 Interim PLF (August 2025) the following indicators were considered obsolete in agreement with FCDO: * Outcome 2.2 Replication: Number of GCIEP supported structures, processes, and / or methodologies replicated (and adapted) by country government ministries
INTERMEDIATE OUTCOME 1 | INT Outcome Indicator 1.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
GCIEP DOC Ethiopia is effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development (REPORTED ANNUALLY) | A) Increase in scope: Percentage of DOC interventions that have increase their scope since the start of the programme - CUMULATIVE (total number of DOC interventions scaled up / total number of DOC interventions) B) Closed / curtailed: Percentage of DOC interventions closed and / or curtailed since the start of the programme - CUMULATIVE (total number of DOC interventions closed or curtailed / total number of DOC interventions) C) New DOC interventions: Total number of DOC interventions introduced based on learning during GCIEP implementation phase | Planned -annual | n/a | n/a | n/a | n/a | *GCIEP can effectively target its assistance, to choose the right agencies/municipalities and/or institutions with which to partner and select and test the adequate interventions * GCIEP has in place the Impact Pathway packages to monitor DOC interventions applying adaptive programming principles *No material change in government priorities with any political changes in countries that undergo national elections * Well prepared projects (including feasibility studies) supported by GCIEP will attract the necessary downstream financing * In some cases, targets are not applicable, as we are a demand driven programme working under adaptive programming principles
|  | Achieved - annual | n/a | n/a | n/a | C) 3 ET.P2.01 Secondary Cities ET.P2.02 Energy ET.P2.03 EV
|  | Achieved - cumulative | n/a | n/a | n/a
Source
GCIEP RM databases and Intervention Pathways Packages at the intervention level Phase 1 interventions treated as scaled up for Phase 2
| INT Outcome Indicator 1.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) Disaggregated by stage of the infrastructure development cycle: (I) Project pipeline and (II) Project specific support including (a) Planning & preparation (concept note, business cases, (pre) feasibility studies); (b) Financing structuring (project development agreement, investment round tables etc); (c) Commercial and financial close; (d) Procurement; and (e) Implementation | Planned -annual | n/a | n/a | n/a | (II) Project specific support:2 ET.P2.02 Energy Access 1. Use case for an identified intervention for Smart Grid Optimisation (SGO) reviewed/accepted by Ethiopian Electric Utility (EEU) / Ethiopian Electric Power (EEP) 2. Use case for an identified Distributed Renewable Energy (DRE) focused initiative including viability of accessing carbon market revenues reviewed/accepted by Ministry of Water and Energy (MoWE)
|  | Achieved - annual | n/a | n/a | n/a
|  | Achieved - cumulative | n/a | n/a | n/a
Source
GCIEP RM databases and Intervention Pathways Packages at the DOC intervention level Note: High quality equals to projects that have mainstreamed GEDSI and CN&E
INTERMEDIATE OUTCOME 3 | INT Outcome Indicator 3.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Influencing and collaboration Uptake of relevant knowledge and evidence generated by GCIEP and/or its delivery partners by the GoV as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services (REPORTED ANNUALLY) | INFORMING DECISION MAKING: Number of policies/regulations/strategies/roadmaps/frameworks/institutional structures in Vietnam that have been informed with contributions from GCIEP TA. (disag by Strategy & Planning, Legal & Regulatory Framework, Financing Mechanisms, Institutional capacity & governance, Networks & Partnerships) | Planned -annual | n/a | n/a | n/a | ET.P2.01 Secondary Cities 1. Prioritised Investment Program report reviewed/accepted by counterpart ET.P2.03 Electrifying Transport 2. Feasible financial product for minibus owners/drivers seeking finance to transition to electric vehicles reviewed/accepted by relevant financial institutions | * Central FCDO and country offices are open to learning from and being influenced by GCIEP generated knowledge - when relevant . * Deliverables can include policies, regulations, roadmaps, strategies, frameworks, institutional structure / governance report, etc. that have been submitted/reviewed/accepted/approved by the beneficiary stakeholder/s (depending on country context). *Targets and results include deliverables that are REVIEWED/ ACCEPTED by the beneficiary stakeholder that are used as source of evidence, insights, or recommendations to inform policies, strategies, or actions in FCDO partner countries.
|  | Achieved - annual | n/a | n/a | n/a
|  | Achieved - cumulative | n/a | n/a | n/a
|  | Source |  |  |  |  | RISK RATING
|  | GCIEP monitoring and operational databases |  |  |  |  | MODERATE
INTERMEDIATE OUTCOME 4 | INT Outcome Indicator 4.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
DOC interventions have successfully integrated GEDSI risks and opportunities resulting in Empowerment (REPORTED ANNUALLY) | % of DOC intervention that include GEDSI considerations in accordance with Level 2 - Empowerment - as per the FCDO GEDSI framework (realised target ambition) - Linked to Output 4 | Planned -annual | n/a | n/a | n/a | 50% | *Resources at DOC and TO level are deployed to ensure that GEDSI is effectively mainstreamed during implementation, regularly identifying and assessing GEDSI risks and opportunities
|  | Achieved - annual | n/a | n/a | n/a
|  | Source |  |  |  |  | RISK RATING
|  | GCIEP GEDSI monitoring; GCIEP deliverables TOR and GCIEP work package progress reports Note: it only applies to interventions that have GEDSI potential |  |  |  |  | MODERATE
OUTPUT 1 | Output Indicator 1.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
High-quality TA deliverables completed by GCIEP for FCDO posts to facilitate economic transformation and inclusive growth (in line with VfM targets) (REPORTED QUARTERLY) | DOC Percentage of the activities planned at the start of each quarter that are completed. | Planned -annual | n/a | n/a | n/a | 70%
|  | Achieved - annual | n/a | n/a | n/a
|  | Source |  |  |  |  | RISK RATING
|  | GCIEP DOC intervention workplans Note: Total number of activities completed during the quarter / total number of activities planned to be completed as per workplan submitted to FCDO at the start of the quarter. It is expected that the activities detailed (and related deliverables) in the intervention workplan will be updated on a quarterly basis in line with adaptive management best practice. |  |  |  |  | MINOR
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Proactive strategic collaboration to maximise effectiveness in GCIEP delivery in TO and/or DOC countries (REPORTED QUARTERLY) | No. of instances where GCIEP team has worked and/or coordinated* with partners** A) GCIEP DOC interventions B) GCI CoE delivery partners C) Any other UK expert organisations D) Development partners (instances that DOC and Buy-ins have collaborated with development partners) | Planned -annual | n/a | n/a | n/a | B) 1 (TfL) D) 9 (World Bank, Agence Française de Développement (AFD, International Finance Corporation (IFC), EU, Trade and Development Bank, World Resources Institute, Global Green Growth Institute, Cities Alliance, SouthSouthNorth) | *GCIEP can effectively target its assistance, to choose the right agencies/municipalities and/or institutions with which to partner and select the right interventions Setting a target for this indicator was deemed not applicable (in agreement with FCDO) during GCIEP’s first full year of delivery in Year 2 , due to the demand-driven nature of the programme. Instead, it was agreed we would report Actuals in the Y2 log frame. However, where there are continuing work packages in Y3 (second full year of GCIEP delivery) with many of the same stakeholders and sectors, we have included targets in the Year 3 log frame for this indicator.
|  | Achieved - annual | n/a | n/a | n/a
|  | Achieved - cumulative | n/a | n/a | n/a
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
10% |  | GCIEP monitoring and operational databases Notes: *Co-ordination defined as having an active Community of Practice/signed MoU/other formal engagement process in place) ** Partners defined as any in-country international development agency or donor based in a DOC country ***GCIEP CoE delivery partners: Cross Rail Intl, Ofgem, Infrastructure and Projects Authority, Transport for London, BSI; CATAPULT, Ordinance Survey and British Geological Survey |  |  |  |  | MINOR
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Enhancing capacity and knowledge to strengthen GCIEP supported institutions and agencies in partner countries (disag by DOC and TO) (REPORTED QUARTERLY) | Percentage and number of people certified in UK tools and methodologies (Only applicable if there is formal UK certification offer. UK tools and methodologies with certification exam include, for example, 5CM) | Planned -annual | n/a | n/a | n/a | 0 | * GCIEP has the capacity to deliver targeted and high quality trainings, adapted to the needs to targeted stakeholders *GCIEP can leverage on UK expertise to successfully deliver TA *Setting a target for this indicator was deemed not applicable (in agreement with FCDO) during GCIEP’s first full year of delivery in Year 2 , due to the demand-driven nature of the programme. Instead, it was agreed we would report Actuals in the Y2 log frame. However, where there are continuing interventions in Y3 (second full year of GCIEP delivery) with many of the same stakeholders and sectors, we have included targets in the Year 3 log frame for this indicator.
|  | Achieved - annual | n/a | n/a | n/a
|  | Achieved - cumulative | n/a | n/a | n/a
Source
GCIEP RM and operational databases Note: Number of people certified / total number of people trained in UK tools and methodologies taking the exam.
| Output Indicator 3.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number (#) of people trained via GCIEP supported work packages/interventions Disaggregation: portfolio (DOC, TO, Buy-in), women professionals, people with disabilities, and youth, indicate if UK methodology. | Planned -annual | n/a | n/a | n/a | 0
|  | Achieved - annual | n/a | n/a | n/a
|  | Achieved - cumulative | n/a | n/a | n/a
Source
GCIEP RM and operational databases
| Output Indicator 3.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| % of participants indicating that the training/capacity building in Output 3.1 or 3.2 was "useful" or "very useful" on a 5 point scale | Planned -annual | n/a | n/a | n/a | n/a
|  | Achieved - annual | n/a | n/a | n/a
|  | Achieved - cumulative | n/a | n/a | n/a
WEIGHTING: |  | Source
10% |  | GCIEP RM and operational databases |  |  |  |  | MNOR
OUTPUT 4 | Output Indicator 4.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
GEDSI is mainstreamed across GCIEP DOC interventions and Target Offer (TO) work packages (WPs) (disag by DOC and TO) (REPORTED ANNUALLY) | % of GCIEP supported DOC interventions/TO WPs that have an ambition of level 2 - Empowerment as per the FCDO GEDSI framework Disaggregated by FCDO GEDSI framework levels 1-3 | Planned - annual | n/a | n/a | n/a | 50% | *The FCDO GEDSI Framework is effective into translating FCDO’s GEDSI policies into programming; enabling GCIEP to take a structured and practical approach to exploring how GCIEP interventions can maximise benefits to disadvantaged and vulnerable groups
|  | Achieved - annual | n/a | n/a | n/a
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
15% |  | GCIEP GEDSI monitoring; GCIEP deliverables TOR and GCIEP work package progress reports Note: it only applies to interventions that have GEDSI potential |  |  |  |  | MINOR
OUTPUT 5 | Output Indicator 5.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
CN&E is mainstreamed across GCIEP DOC interventions and Target Offer (TO) work packages (WPs) (ICF compliance) (disag by DOC and TO) (REPORTED ANNUALLY) | % of GCIEP supported DOC interventions/TO work packages that are mainstreaming CN&E | Planned - annual | n/a | n/a | n/a | 100% | *ICF compliant: An interventions that contributes to at least 1 ICF KPI indicator *ICF KPI TA methodology only allows actuals to be reported
|  | Achieved - annual | n/a | n/a | n/a
Source
GCIEP ICF monitoring; DOC intervention ToRs and TO Work Package ToRs; GCIEP progress reports
| Output Indicator 5.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| % of total spend that is ICF compliant in relation to the total £ value of GCIEP programmes - of eligible ODA | Planned - annual | n/a | n/a | n/a | 80%
|  | Achieved - annual | n/a | n/a | n/a
Source
GCIEP ICF monitoring; DOC intervention ToRs and TO Work Package ToRs; GCIEP progress reports
| Output Indicator 5.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of countries supported by ICF technical assistance ICF TA KPI 1 (reported only on completed DOC interventions/TO WPs) | Planned - annual | n/a | n/a | n/a | n/a
|  | Achieved - annual | n/a | n/a | n/a
|  | Achieved - cumulative | n/a | n/a | n/a
Source
GCIEP CN&E monitoring; DOC intervention ToRs and TO work package ToRs; GCIEP progress reports
| Output Indicator 5.4 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of individuals supported by ICF technical assistance ICF TA KPI 2.1 (reported only on completed DOC interventions/TO WPs) | Planned - annual | n/a | n/a | n/a | n/a
|  | Achieved - annual | n/a | n/a | n/a
|  | Achieved - cumulative | n/a | n/a | n/a
Source
GCIEP CN&E monitoring; DOC intervention ToRs and TO work package ToRs; GCIEP progress reports
| Output Indicator 5.5 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of organisations supported by ICF technical assistance ICF TA KPI 2.2 (reported only on completed DOC interventions/TO WPs) | Planned - annual | n/a | n/a | n/a | n/a
|  | Achieved - annual | n/a | n/a | n/a
|  | Achieved - cumulative | n/a | n/a | n/a
Source
GCIEP CN&E monitoring; DOC intervention ToRs and TO work package ToRs; GCIEP progress reports
| Output Indicator 5.6 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of climate policies informed by ICF technical assistance ICF TA KPI 3 (reported only on completed DOC interventions/TO WPs) | Planned - annual | n/a | n/a | n/a | n/a
|  | Achieved - annual | n/a | n/a | n/a
|  | Achieved - cumulative | n/a | n/a | n/a
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
15% |  | GCIEP CN&E monitoring; DOC intervention ToRs and TO work package ToRs; GCIEP progress reports |  |  |  |  | MINOR
OUTPUT 6 | Output Indicator 6.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Learning (evidence) produced and in place for GCIEP to collate and disseminate UK and international urban / infrastructure expertise within GCIEP, FCDO, and to the wider ecosystem (REPORTED QUARTERLY) | No. of GCIEP products (analysis and learning including events) that deliver insights which inform/shape FCDO/wider development partner policies and programmes Disaggregation by events and products | Planned - annual | n/a | n/a | n/a | 5 | *Sufficient GCIEP budget is allocated to undertake planned L&C activities approved in the ToR L&C
|  | Achieved - annual | n/a | n/a | n/a
|  | Achieved - cumulative | n/a | n/a | n/a
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
10% |  | GCIEP RM and L&C monitoring, GCIEP K&L documentation (including links to public KPs and materials published) Note: a. A GCIEP Product is any written material produced by GCIEP and/or its delivery partners, through its DOC interventions/ TO work packages, that has been repackaged according to targeted audience/s and dissemination channel/s including learning events, that seek to contribute to the body of infra delivery and urban development knowledge towards improving FCDO and GCIEP delivery partners programming . This GCIEP product is out of the budget of the TO WP. |  |  |  |  | MINOR
º
Note on A21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Refers to Vietnam - also in the indicators Reply: We have made the indicator more generic so that it does not need to be changed for every nested logframe Reply: Updated outcome 2.1 to include Ethiopia.
Note on G40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Expand acronyms SGO and DRE Reply: The subject should be the identified intervention - the use case is the deliverable Reply: Done spell out. Details on Use Case to be added when reporting actuals
Note on G46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1. is the deliverable - what is the policy we expect it to inform? 2. the policy/product, ‘a feasible financial product’ should be the subject of the sentence. The TA is the deliverable. Reply: 1. there is no specific policy linked to this deliverable, we are developing a pipeline of potential investment opportunities across Berbera corridor 2. This toolkit is comprised of a set of options to fit into the development of feasible financial product in due course. Hence, the toolkit is the deliverable as a result of our TA

## GHANA nested LF
PROGRAMME NAME: | Green Cities, Infrastructure and Energy Programme (GCIEP) Y3 Logframe - DOC GHANA (22 January 2026)
OUTCOME 1 | Outcome Indicator 1.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Finance and Investment is leveraged for sustainable and inclusive infrastructure and the built environment in Ghana (DOC only and TO - if reported by Post) (REPORTED ANNUALLY) | Total volume of total non-GCIEP financing mobilised as a result of GCIEP interventions in Ghana (£ ) Disaggregation by: type of funding organisation (Private/Donor/Public -National/Municipal), financing categories (catalysed, facilitated, unlocked, and reallocated) To track off logframe, GCIEP country programmes where non-FCDO funds have been leveraged downstream | Planned -annual | n/a | Too early | Too early | £132M (£120M Sekondi-Takoradi Metropolitan Area (STMA) project & £12M Wa Water project) | *GCIP TA makes a contribution towards facilitating investment into urban economic infrastructure projects and overcoming obstacles to project delivery *Partner government continued support for: i) pro-poor, inclusive, low carbon and resilient objectives and targeted approaches; and ii) channel private and public investment into urban development and economic infrastructure *Target and Results will be based only on DOC interventions; but GCIP will also report on results from TO work packages, in case there is GCIEP contribution and results have been tracked either by GCIP or FCDO Post (post completion monitoring) * COMMITTED refers to: The financing quantified has already been committed/mobilised by other investors, where GCIP TA is being used to make the investment “bigger, better or faster."
|  | Achieved - annual | n/a | Too early | 0 | £12M grant from DANIDA as a result of the Wa water project feasibility study completed by GCIEP (DKK100M) - November 2025
|  | Achieved - cumulative | n/a | Too early | 0
Source
GCIP DOC and TO RM databases
| Outcome Indicator 1.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Volume of public finance mobilised for climate change purposes in Ghana (£) (as a result of GCIP interventions ) (disag by new financing vs reallocated financing) (ICF KPI 11) | Planned -annual | n/a | Too early | n/a | n/a: ICF KPI methodology only allows actuals to be reported
| ICF KPI 12 Volume of private finance mobilised for climate change purposes | Achieved - annual | n/a | Too early | 0 | £12M grant from DANIDA as a result of the Wa feasibility study completed by GCIEP (KRO 100M)
|  | Achieved - cumulative | n/a | Too early | 0
Source
Year 3 Target (1st Apr 25 - 31 Mar 26)
| Outcome Indicator 1.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Volume of private finance mobilised for climate change purposes in Ghana (£) (as a result of GCIP interventions) (ICF KPI 12) | Planned -annual | n/a | Too early | n/a | n/a: ICF KPI methodology only allows actuals to be reported
| ICF KPI 12 Volume of private finance mobilised for climate change purposes | Achieved - annual | n/a | Too early | 0
|  | Achieved - cumulative | n/a | Too early | 0
|  | Source |  |  |  |  | RISK RATING
|  | GCIP RM databases and ICF monitoring ICF KPI Methodology: https://assets.publishing.service.gov.uk/media/65e0b9913f6945001d036030/KPI-12-volume-private-finace-mobilised.pdf |  |  |  |  | MODERATE
OUTCOME 2 | Outcome 2.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
GCIEP TA contributed to a stronger enabling environment in Ghana for the provision of climate resilient&inclusive infrastructure services (REPORTED ANNUALLY) | APPROVAL: Number of approved policies/regulations/strategies/roadmaps/frameworks/institutional structures in Ghana supported by GCIEP TA (disag by Strategy & Planning, Legal & Regulatory Framework, Financing Mechanisms, Institutional capacity & governance, Networks & Partnerships) | Planned -annual | n/a | Too early | Too early | GH.P1.03 WS3a Urban baseline and M&E framework for new urban policy 1. M&E Plan to monitor implementaiton of the national urban policy approved | *Central FCDO and country offices are open to learning from and being influenced by GCIP generated knowledge - when relevant * Collaboration with CoE DPs collaboration increase urban and infrastructure effectiveness leading to local adoption and replication * No material change in government priorities with any political changes in countries that undergo national elections * Deliverables can include policies, regulations, roadmaps, strategies, frameworks, institutional structure / governance report, etc. that have been submitted/reviewed/accepted/approved by the beneficiary stakeholder/s (depending on country context) * APPROVAL: Formal endorsement of GCIEP supported policy/regulations/strategies/roadmaps/frameworks/institutional structures at FCDO partner countries by the beneficiary stakeholder (or the appropriate designated authority) * ADOPTION: The formal embedding and / or implementation of a GCIEP-supported structure, process, methodology or practices by FCDO partner countries, maintaining the core design and function of the original model, through minor contextual adjustments may be made. A deliverable is counted either as APPROVED or ADOPTED but not both, except in the case where GCIEP provides continuous to support over time resulting in an evolution from APPROVAL to ADOPTION. In such exceptional cases policy/regulations/strategies/roadmaps/frameworks/institutional structures may be reported at both level, usually for different years.
|  | Achieved - annual |  | Too early | 0 | GH.P1.03 WS3a Urban baseline and M&E framework for new urban policy 1. M&E Plan to monitor implementaiton of the national urban policy approved
|  | Achieved - cumulative |  | Too early | 0
Source
GCIP L&C tracking tool, GCIP K&L documentation Note: Deliverables must be approved by the beneficiary entity
| Outcome 2.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| ADOPTION: Number of GCIEP supported policies/regulations/strategies/roadmaps/frameworks/institutional structures adopted as evidence of GCIEP legacy / sustainability in GCIP supported entities in Ghana (sustainability) (disag by Strategy & Planning, Legal & Regulatory Framework, Financing Mechanisms, Institutional capacity & governance, Networks & Partnerships) | Planned -annual | n/a | Too early | Too early | 0
|  | Achieved - annual |  | Too early | 0 | GH.P1.02 Scaled Renewable Energy for GRIDCo 1.Energy planning: DIgSILENT Power Factory software adopted by GRIDCo following the 10-day training provided by GCIEP (GRIDCo spent ~£250K to acquire the software) GH.P1.03 Urban - WS3b Multi hazard risk mapping 2.EU-funded Ghana Urban Observatory: Risk and hazard screening report and risk maps for each of the 9 cities designed and operationalised - operationalised and moved from Intermediate Outcome 3.1 (to avoid double counting)
|  | Achieved - cumulative |  | Too early | 0
|  | Source |  |  |  |  | RISK RATING
|  | GCIP RM databases and Intervention Pathways Packages at the intervention level |  |  |  |  | MODERATE
Year 3 Target (1st Apr 25 - 31 Mar 26)
INTERMEDIATE OUTCOME 1 | INT Outcome Indicator 1.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
GCIEP DOC is effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development (REPORTED ANNUALLY) | A) Increase in scope: Percentage of DOC interventions that have increase their scope since the start of the programme - CUMULATIVE (total number of DOC interventions scaled up / total number of DOC interventions) B) Closed / curtailed: Percentage of DOC interventions closed and / or curtailed since the start of the programme - CUMULATIVE (total number of DOC interventions closed or curtailed / total number of DOC interventions) C) New DOC interventions: Total number of DOC interventions introduced based on learning during GCIEP implementation phase | Planned -annual | n/a | n/a | n/a | n/a | *GCIP can effectively target its assistance, to choose the right agencies/municipalities and/or institutions with which to partner and select and test the adequate interventions * GCIP has in place the Impact Pathway packages to monitor DOC interventions applying adaptive programming principles *No material change in government priorities with any political changes in countries that undergo national elections * Well prepared projects (including feasibility studies) supported by GCIP will attract the necessary downstream financing * In some cases, targets are not applicable, as we are a demand driven programme working under adaptive programming principles
|  | Achieved - annual | n/a | n/a | A) DOC Ghana GH01 Climate finance | C) 3 GH.P2.01 Urban development project preparation support GH.P2.02 Climate Finance GH.P2.03 Energy
|  | Achieved - cumulative | n/a | n/a | A) DOC Ghana GH01 Climate finance
Source
GCIP RM databases and Intervention Pathways Packages at the intervention level Phase 1 interventions treated as scaled up for Phase 2
| INT Outcome Indicator 1.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) Disaggregated by stage of the infrastructure development cycle: (I) Project pipeline and (II) Project specific support including (a) Planning & preparation (concept note, business cases, (pre) feasibility studies); (b) Financing structuring (project development agreement, investment round tables etc); (c) Commercial and financial close; (d) Procurement; and (e) Implementation | Planned -annual | n/a | Too early | Too early | I. Project pipeline: 1 GH.P1.02 (Scaled Renewable Energy for GridCo) 1. Pipeline of 100 VRE projects developed from GridCo and the Energy Commission list of projects II. Project Specific support: 10 GH.P1.01 (Scaling climate finance flows in Ghana) 1. Project Preparation Facility (PPF): feasibility study accepted by FCDO 2. 12,500m2 biogas plant (DasBiogas and Accra Metropolitan Assembly); 75 MW wind power in Keta Municipality (VRA Ghana); 5,000 capacity student complex at Kwame Nkrumah Univ. of Science and Technology in Kumasi (Nilex): Three scoping Briefing notes for project preparation to feed into the PPF accepted by FCDO GH.P1.02 (Scaled Renewable Energy for GridCo) 3. Akuse Floating PV Plant: Pre-Feasibility study accepted by GRIDCo 4. Sawla PV Plant: Pre-Feasibility study accepted by GRIDCo GH.P1.03 WS 1 (Water security and access to water services for vulnerable urban communities in Wa) 5. Wa Water: Feasibility study accepted by DANIDA and Gvt of Ghana GH.P2.03 Climate Finance 6. DBG Climate Finance Faciliy: Action plan on how to operationalise the facility reviewed/accepted by DBG 7. FSD-Africa PPF: Summary report on future financial sustainability for the PPF and pipeline development reviewed/accepted by FSD Africa GH.P2.01 Urban development project preparation support 8. Sekondi-Takoradi Metropolitan Area (STMA) project: detailed Feasibility report accepted by Department of Urban Roads/Ministry of Roads and Highways and the Ghana Hydrological Authority/Ministry of Works, Housing, and Water Resources 9. Climate smart fecal sludge treatment plant (FSTP) project in 5 cities: revised Feasibility report accepted by Ministry of Local Government, Chieftaincy and Religious Affairs GH.P2.02 Energy 10. Akuse Floating PV Plant: Pre-Feasibility study report completed and accepted by Volta River Authority (VRA)
|  | Achieved - annual |  | Too early | 0 | I. Project pipeline: 1 GH.P1.02 (Scaled Renewable Energy for GridCo) 1. Pipeline of 100 VRE projects developed from GridCo and the Energy Commission list of projects II. Project Specific support: 5 GH.P1.01 (Scaling climate finance flows in Ghana) 1. Project Preparation Facility (PPF): feasibility study accepted by FCDO 2. 12,500m2 biogas plant (DasBiogas and Accra Metropolitan Assembly); 75 MW wind power in Keta Municipality (VRA Ghana); 5,000 capacity student complex at Kwame Nkrumah Univ. of Science and Technology in Kumasi (Nilex): Three scoping Briefing notes for project preparation to feed into the PPF accepted by FCDO GH.P1.02 (Scaled Renewable Energy for GridCo) 3. Akuse Floating PV Plant: Pre-Feasibility study accepted by GRIDCo 4. Sawla PV Plant: Pre-Feasibility study accepted by GRIDCo GH.P1.03 WS 1 (Water security and access to water services for vulnerable urban communities in Wa) 5. Wa Water: Feasibility study accepted by DANIDA and Gvt of Ghana
|  | Achieved - cumulative |  | Too early | 0
Source
GCIP RM databases and Intervention Pathways Packages at the DOC intervention level Note: High quality equals to projects that have mainstreamed GEDSI and CN&E GCIEP DO C supported projects/initiatives along the infrastructure development cycle: (a) Planning & preparation (project pipelines, concept note, business cases, (pre) feasibility studies); (b) Financing structuring (project development agreement, investment round tables etc); (c) Commercial and financial close; (d) Procurement; and (e) Implementation
INTERMEDIATE OUTCOME 3 | INT Outcome Indicator 3.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
Influencing and collaboration Uptake of relevant knowledge and evidence generated by GCIP and/or its delivery partners by the GoV as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services (REPORTED ANNUALLY) | INFORMING DECISION MAKING: Number of policies/regulations/strategies/roadmaps/frameworks/institutional structures in Ghana that have been informed with contributions from GCIEP TA. (disag by Strategy & Planning, Legal & Regulatory Framework, Financing Mechanisms, Institutional capacity & governance, Networks & Partnerships) | Planned -annual |  |  |  | GH.P1.02 Scaled Renewable Energy for GRIDCo 1. Decision-making framework for identifying areas of the grid suitable for VRE interconnection reviewed/accepted by GriDCO (based on GRIDCo pipeline) 2. Procurement framework for grid-connected VRES in Ghana reviewed/accepted by GriDCO GH.P1.03 WS3b (Multi hazard risk mapping) 3. EU-funded Ghana Urban Observatory: Risk and hazard screening report and risk maps for each of the 9 cities reviewed/accepted by the Gvt of Ghana
|  | Achieved - annual |  |  |  | GH.P1.02 Scaled Renewable Energy for GRIDCo 1. Decision-making framework for identifying areas of the grid suitable for VRE interconnection accepted (based on GRIDCo pipeline) 2. Procurement framework for grid-connected VRES in Ghana accepted GH.P1.03 Urban - WS3b Multi hazard risk mapping *EU-funded Ghana Urban Observatory: Risk and hazard screening report and risk maps for each of the 9 cities reviewed/accepted by the Gvt of Ghana- Counted against Outcome 2.3 as it has been adopted
Achieved - cumulative
|  | Source |  |  |  |  | RISK RATING
|  | GCIEP monitoring and operational databases |  |  |  |  | MODERATE
INTERMEDIATE OUTCOME 4 | INT Outcome Indicator 4.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
DOC interventions have successfully integrated GEDSI risks and opportunities resulting in Empowerment (REPORTED ANNUALLY) | % of DOC intervention that include GEDSI considerations in accordance with Level 2 - Empowerment - as per the FCDO GEDSI framework (realised target ambition) - Linked to Output 4 | Planned -annual | n/a | Too early | 50% | 50% | *Resources at DOC and TO level are deployed to ensure that GEDSI is effectively mainstreamed during implementation, regularly identifying and assessing GEDSI risks and opportunities
Achieved - annual
|  | Source |  |  |  |  | RISK RATING
|  | GCIEP GEDSI monitoring; GCIP deliverables TOR and GCIP work package progress reports Note: it only applies to interventions that have GEDSI potential |  |  |  |  | MODERATE
OUTPUT 1 | Output Indicator 1.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
High-quality TA deliverables completed by GCIP for FCDO posts to facilitate economic transformation and inclusive growth (in line with VfM targets) (REPORTED QUARTERLY) | DOC Percentage of the activities planned at the start of each quarter that are completed. | Planned -annual | n/a | n/a | 70% | 70%
|  | Achieved - annual | n/a | n/a | 90.1%
Source
GCIP DOC intervention workplans Note: Total number of activities completed during the quarter / total number of activities planned to be completed as per workplan submitted to FCDO at the start of the quarter. It is expected that the activities detailed (and related deliverables) in the intervention workplan will be updated on a quarterly basis in line with adaptive management best practice.
WEIGHTING: | [6 empty] | RISK RATING
MINOR
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Proactive strategic collaboration to maximise effectiveness in GCIEP delivery in TO and/or DOC countries (REPORTED QUARTERLY) | No. of instances where GCIP team has worked and/or coordinated* with partners** A) GCIP DOC interventions B) GCI CoE delivery partners C) Any other UK expert organisations D) Development partners (instances that DOC and Buy-ins have collaborated with development partners) | Planned -annual | n/a | n/a | n/a | B) 2 British Geological Survey (BGS), Ordnance Survey D) 4 (Invest International, European Investment Bank, EU, World Bank) , | *GCIP can effectively target its assistance, to choose the right agencies/municipalities and/or institutions with which to partner and select the right interventions * Targets (n/a): Targets are not applicable, as we are a demand driven programme working under adaptive programming principles
|  | Achieved - annual | n/a | n/a | B) 1 (Ofgem) C) 5 (Climate Compatible Growth, Green Grids Initiative, National Energy System Operator, National Grid, Transport Research Lab) D) 6 (DANIDA, EIB, EU, KfW, United Nationals Children's Fund, World Bank)
|  | Achieved - cumulative | n/a | n/a | B) 1 C) 5 D) 6
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
10% |  | GCIP monitoring and operational databases Notes: *Co-ordination defined as having an active Community of Practice/signed MoU/other formal engagement process in place) ** Partners defined as any in-country international development agency or donor based in a DOC country ***GCIP CoE delivery partners: Cross Rail Intl, Ofgem, Infrastructure and Projects Authority, Transport for London, BSI; CATAPULT, Ordinance Survey and British Geological Survey |  |  |  |  | MINOR
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Enhancing capacity and knowledge to strengthen GCIP supported institutions and agencies in partner countries (disag by DOC and TO) (REPORTED QUARTERLY) | Percentage and number of people certified in UK tools and methodologies (Only applicable if there is formal UK certification offer. UK tools and methodologies with certification exam include, for example, 5CM) | Planned -annual | n/a | Too early | n/a | 0 | * GCIP has the capacity to deliver targeted and high quality trainings, adapted to the needs to targeted stakeholders *GCIP can leverage on UK expertise to successfully deliver TA *Setting a target for this indicator was deemed not applicable (in agreement with FCDO) during GCIEP’s first full year of delivery in Year 2 , due to the demand-driven nature of the programme. Instead, it was agreed we would report Actuals in the Y2 log frame. However, where there are continuing interventions in Y3 (second full year of GCIEP delivery) with many of the same stakeholders and sectors, we have included targets in the Year 3 log frame for this indicator.
|  | Achieved - annual | n/a | Too early | 0
|  | Achieved - cumulative | n/a | Too early | 0
Source
GCIP RM and operational databases Note: Number of people certified / total number of people trained in UK tools and methodologies taking the exam.
| Output Indicator 3.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number (#) of people trained via GCIEP supported work packages/interventions Disaggregation: portfolio (DOC, TO, Buy-in), women professionals, people with disabilities, and youth, indicate if UK methodology. | Planned -annual | n/a | n/a | n/a | 115
|  | Achieved - annual | n/a | n/a | 62 Total (16 women)
|  | Achieved - cumulative | n/a | n/a | 62 Total (16 women)
Source
GCIP RM and operational databases
| Output Indicator 3.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| % of participants indicating that the training/capacity building in Output 3.1 or 3.2 was "useful" or "very useful" on a 5 point scale | Planned -annual | n/a | n/a | 70% | 85%
|  | Achieved - annual | n/a | n/a | 94.8% (55 of 58)
|  | Achieved - cumulative | n/a | n/a | 94.8% (55 of 58)
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
10% |  | GCIP RM and operational databases |  |  |  |  | MNOR
OUTPUT 4 | Output Indicator 4.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
GEDSI is mainstreamed across GCIP DOC interventions and Target Offer (TO) work packages (WPs) (disag by DOC and TO) (REPORTED ANNUALLY) | % of GCIP supported DOC interventions/TO WPs that have an ambition of level 2 - Empowerment as per the FCDO GEDSI framework Disaggregated by FCDO GEDSI framework levels 1-3 | Planned - annual | n/a | n/a | L2: 50% | L2: 50% | *The FCDO GEDSI Framework is effective into translating FCDO’s GEDSI policies into programming; enabling GCIP to take a structured and practical approach to exploring how GCIP interventions can maximise benefits to disadvantaged and vulnerable groups
|  | Achieved - annual | n/a | n/a | 64%
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
15% |  | GCIP GEDSI monitoring; GCIP deliverables TOR and GCIP work package progress reports Note: it only applies to interventions that have GEDSI potential |  |  |  |  | MINOR
OUTPUT 5 | Output Indicator 5.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
CN&E is mainstreamed across GCIP DOC interventions and Target Offer (TO) work packages (WPs) (ICF compliance) (disag by DOC and TO) (REPORTED ANNUALLY) | % of GCIP supported DOC interventions/TO work packages that are mainstreaming CN&E | Planned - annual | n/a | n/a | 100% | 100% | *ICF compliant: An interventions that contributes to at least 1 ICF KPI indicator *ICF KPI TA methodology only allows actuals to be reported
|  | Achieved - annual | n/a | n/a | 100%
Source
GCIEP ICF monitoring; DOC intervention ToRs and TO Work Package ToRs; GCIEP progress reports
| Output Indicator 5.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| % of total spend that is ICF compliant in relation to the total £ value of GCIP programmes - of eligible ODA | Planned - annual | n/a | n/a | 80% | 80%
|  | Achieved - annual | n/a | n/a | 92%
Source
Year 3 Target (1st Apr 25 - 31 Mar 26)
| Output Indicator 5.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of countries supported by ICF technical assistance ICF TA KPI 1 (reported only on completed DOC interventions/TO WPs) | Planned - annual | n/a | n/a | n/a | n/a
|  | Achieved - annual | n/a | n/a | TBC by Dec25
|  | Achieved - cumulative | n/a | n/a | TBC by Dec25
Source
GCIEP CN&E monitoring; DOC intervention ToRs and TO work package ToRs; GCIEP progress reports
| Output Indicator 5.4 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of individuals supported by ICF technical assistance ICF TA KPI 2.1 (reported only on completed DOC interventions/TO WPs) | Planned - annual | n/a | n/a | n/a | n/a
|  | Achieved - annual | n/a | n/a | TBC by Dec25
|  | Achieved - cumulative | n/a | n/a | TBC by Dec25
Source
GCIEP CN&E monitoring; DOC intervention ToRs and TO work package ToRs; GCIEP progress reports
| Output Indicator 5.5 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of organisations supported by ICF technical assistance ICF TA KPI 2.2 (reported only on completed DOC interventions/TO WPs) | Planned - annual | n/a | n/a | n/a | n/a
|  | Achieved - annual | n/a | n/a | TBC by Dec25
|  | Achieved - cumulative | n/a | n/a | TBC by Dec25
Source
GCIP ICF monitoring; DOC ToR and TO WPs ToR; GCIP progress reports
| Output Indicator 5.6 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of climate policies informed by ICF technical assistance ICF TA KPI 3 (reported only on completed DOC interventions/TO WPs) | Planned - annual | n/a | n/a | n/a | n/a
|  | Achieved - annual | n/a | n/a | TBC by Dec25
|  | Achieved - cumulative | n/a | n/a | TBC by Dec25
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
15% |  | GCIEP CN&E monitoring; DOC intervention ToRs and TO work package ToRs; GCIEP progress reports |  |  |  |  | MINOR
OUTPUT 6 | Output Indicator 6.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Learning (evidence) produced and in place for GCIEP to collate and disseminate UK and international urban / infrastructure expertise within GCIEP, FCDO, and to the wider ecosystem (REPORTED QUARTERLY) | No. of GCIEP products (analysis and learning including events) that deliver insights which inform/shape FCDO/wider development partner policies and programmes Disaggregation by events and products | Planned - annual | n/a | Too early | n/a | 17 | *Sufficient GCIP budget is allocated to undertake planned L&C activities approved in the ToR L&C *Setting a target for this indicator was deemed not applicable (in agreement with FCDO) during GCIEP’s first full year of delivery in Year 2 , due to the demand-driven nature of the programme. Instead, it was agreed we would report Actuals in the Y2 log frame. However, where there are continuing interventions in Y3 (second full year of GCIEP delivery) with many of the same stakeholders and sectors, we have included targets in the Year 3 log frame for this indicator.
|  | Achieved - annual | n/a | Too early | 6 (4 products & 2 events)
|  | Achieved - cumulative | n/a | Too early | 6 (4 products & 2 events)
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
10% |  | GCIP RM and L&C monitoring, GCIP K&L documentation (including links to public KPs and materials published) Note: a. A GCIP Product is any written material produced by GCIP and/or its delivery partners, through its DOC interventions/ TO work packages, that has been repackaged according to targeted audience/s and dissemination channel/s including learning events, that seek to contribute to the body of infra delivery and urban development knowledge towards improving FCDO and GCIP delivery partners programming . This GCIP product is out of the budget of the TO WP. |  |  |  |  | MINOR
º
Note on G40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This should be a list of infrastructure development projects, not of completed deliverables. In line with what the indicator describes. Reply: Text added to relate the deliverable to a specific project
Note on G46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This should be describing the Ghanain policies etc that have been informed. The results listed here are deliverables. Reply: Targets amended to reflect your request

## MOZAMBIQUE nested LF
PROGRAMME NAME: | Green Cities, Infrastructure and Energy Programme (GCIEP) Y3 Logframe - DOC MOZAMBIQUE (22 January 2026)
OUTCOME 1 | Outcome Indicator 1.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Finance and Investment is leveraged for sustainable and inclusive infrastructure and the built environment in Mozambique (DOC only and TO - if reported by Post) (REPORTED ANNUALLY) | Total volume of total non-GCIEP financing mobilised as a result of GCIEP interventions in Mozambique (£ ) Disaggregation by: type of funding organisation (Private/Donor/Public -National/Municipal), financing categories (catalysed, facilitated, unlocked, and reallocated) To track off logframe, GCIEP country programmes where non-FCDO funds have been leveraged downstream | Planned -annual | n/a | Too early | Too early | 0 | *GCIEP TA makes a contribution towards facilitating investment into urban economic infrastructure projects and overcoming obstacles to project delivery *Partner government continued support for: i) pro-poor, inclusive, low carbon and resilient objectives and targeted approaches; and ii) channel private and public investment into urban development and economic infrastructure *Target and Results will be based only on DOC interventions; but GCIEP will also report on results from TO work packages, in case there is GCIEP contribution and results have been tracked either by GCIEP or FCDO Post (post completion monitoring) * COMMITTED refers to: The financing quantified has already been committed/mobilised by other investors, where GCIEP TA is being used to make the investment “bigger, better or faster."
|  | Achieved - annual | n/a | Too early | 0
|  | Achieved - cumulative | n/a | Too early | 0
Source
GCIEP DOC and TO RM databases
| Outcome Indicator 1.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Volume of public finance mobilised for climate change purposes in Mozambique (£) (as a result of GCIEP interventions ) (disag by new financing vs reallocated financing) (ICF KPI 11) | Planned -annual | n/a | Too early | n/a | n/a: ICF KPI methodology only allows actuals to be reported
| ICF KPI 12 Volume of private finance mobilised for climate change purposes | Achieved - annual | n/a | Too early | 0
|  | Achieved - cumulative | n/a | Too early | 0
Source
GCIEP RM databases and ICF monitoring ICF KPI Methodology: https://assets.publishing.service.gov.uk/media/5b17935be5274a190c1b6f8c/KPI11-Public-finance-Updated-methodology.pdf
| Outcome Indicator 1.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Volume of private finance mobilised for climate change purposes in Mozambique (£) (as a result of GCIEP interventions) (ICF KPI 12) | Planned -annual | n/a | Too early | n/a | n/a: ICF KPI methodology only allows actuals to be reported
| ICF KPI 12 Volume of private finance mobilised for climate change purposes | Achieved - annual | n/a | Too early | 0
|  | Achieved - cumulative | n/a | Too early | 0
|  | Source |  |  |  |  | RISK RATING
|  | Year 3 Target (1st Apr 25 - 31 Mar 26) |  |  |  |  | MODERATE
OUTCOME 2 | Outcome 2.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
GCIEP TA contributed to a stronger enabling environment in Mozambique for the provision of climate resilient&inclusive infrastructure services (REPORTED ANNUALLY) | APPROVAL: Number of approved policies/regulations/strategies/roadmaps/frameworks/institutional structures in Mozambique supported by GCIEP TA (disag by Strategy & Planning, Legal & Regulatory Framework, Financing Mechanisms, Institutional capacity & governance, Networks & Partnerships) | Planned -annual | n/a | Too early | Too early | MZ.P1.02 Pemba: 2. Urban Municipal Observatory in Pemba launched and operational MZ.P2.04 Climate Finance: 1. Participatory Group and Technical Council group established and operational to support the Implementation of the National Sustainable FInance strategy in Mozambique MZ.P2.03 Cities: 2. Medium-term Debt Management Strategy to improve the Municipality's financial health endorsed by the Pemba Municipal Assembly | *Central FCDO and country offices are open to learning from and being influenced by GCIEP generated knowledge - when relevant * Collaboration with CoE DPs collaboration increase urban and infrastructure effectiveness leading to local adoption and replication * No material change in government priorities with any political changes in countries that undergo national elections (MoZ, Ghana and Indonesia) * Deliverables can include policies, regulations, roadmaps, strategies, frameworks, institutional structure / governance report, etc. that have been submitted/reviewed/accepted/approved by the beneficiary stakeholder/s (depending on country context) * APPROVAL: Formal endorsement of GCIEP supported policy/regulations/strategies/roadmaps/frameworks/institutional structures at FCDO partner countries by the beneficiary stakeholder (or the appropriate designated authority) * ADOPTION: The formal embedding and / or implementation of a GCIEP-supported structure, process, methodology or practices by FCDO partner countries, maintaining the core design and function of the original model, through minor contextual adjustments may be made. A deliverable is counted either as APPROVED or ADOPTED but not both, except in the case where GCIEP provides continious to support over time resulting in an evolution from APPROVAL to ADOPTION. In such execptional cases policy/regulations/strategies/roadmaps/frameworks/institutional structures may be reported at both level, usually for different years.
|  | Achieved - annual |  | Too early | 0 | MZ.P1.02 Pemba: 1. Urban Municipal Observatory in Pemba launched and operational Achieved earlier than expected - moved from Int. Outcome 3.1 MZ.P1.01 Sustainable Finance: 2. National Climate Finance Strategy and Roadmap approved by Council of Ministers MZ.P1.02 Pemba 3. Detailed design plans for the 2 pilot areas approved by the Municipal Assembly in Pemba MZ.P1.03 Beira 4. Urban detail plan to inform urban planning in the Mucurungo Miquejo area approved by the Municipal Assembly MZ.P1.04 Nacala: 5. Nacala Urban Structured Plan to inform urban planning approved by the Municipal Assembly
|  | Achieved - cumulative |  | Too early | 0
Source
GCIEP L&C tracking tool, GCIEP K&L documentation Note: Deliverables must be approved by the beneficiary entity
| Outcome 2.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| ADOPTION: Number of GCIEP supported policies/regulations/strategies/roadmaps/frameworks/institutional structures adopted as evidence of GCIEP legacy / sustainability in GCIEP supported entities in Mozambique (sustainability) (disag by Strategy & Planning, Legal & Regulatory Framework, Financing Mechanisms, Institutional capacity & governance, Networks & Partnerships) | Planned -annual | n/a | Too early | Too early | DOC MZ.P2.04 Climate Finance: 1. Operational Web-based Climate Finance Dashboard with integrated information
|  | Achieved - annual |  | Too early | 0
|  | Achieved - cumulative |  | Too early | 0
|  | Source |  |  |  |  | RISK RATING
|  | GCIEP RM databases and Intervention Pathways Packages at the intervention level |  |  |  |  | MODERATE
Y3 Interim PLF (August 2025) the following indicators were considered obsolete in agreement with FCDO: * Outcome 2.2 Replication: Number of GCIEP supported structures, processes, and / or methodologies replicated (and adapted) by country governement ministries
INTERMEDIATE OUTCOME 1 | INT Outcome Indicator 1.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
GCIEP DOC is effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development (REPORTED ANNUALLY) | A) Increase in scope: Percentage of DOC interventions that have increase their scope since the start of the programme - CUMULATIVE (total number of DOC interventions scaled up / total number of DOC interventions) B) Closed / curtailed: Percentage of DOC interventions closed and / or curtailed since the start of the programme - CUMULATIVE (total number of DOC interventions closed or curtailed / total number of DOC interventions) C) New DOC interventions: Total number of DOC interventions introduced based on learning during GCIEP implementation phase | Planned -annual | n/a | n/a | n/a | n/a | *GCIEP can effectively target its assistance, to choose the right agencies/municipalities and/or institutions with which to partner and select and test the adequate interventions * GCIEP has in place the Impact Pathway packages to monitor DOC interventions applying adaptive programming principles *No material change in government priorities with any political changes in countries that undergo national elections (MoZ, Ghana and Indonesia) * Well prepared projects (including feasibility studies) supported by GCIEP will attract the necessary downstream financing * In some cases, targets are not applicable, as we are a demand driven programme working under adaptive programming principles
|  | Achieved - annual | n/a | n/a | C) 1 (Nacala intervention) | C) 3 MZ.P2.01 Strengthen urban resilient planning, improve land management and governance; MZ.P2.03 Strengthening cities to attract investment; Enable Access to Climate Funding at National Level; MZ.P2.04 Enable Access to Climate Funding at National Level
|  | Achieved - cumulative | n/a | n/a | C) 1 (Nacala intervention)
Source
GCIEP RM databases and Intervention Pathways Packages at the intervention level Phase 1 interventions treated as scaled up for Phase 2
| INT Outcome Indicator 1.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) Disaggregated by stage of the infrastructure development cycle: (I) Project pipeline and (II) Project specific support including (a) Planning & preparation (concept note, business cases, (pre) feasibility studies); (b) Financing structuring (project development agreement, investment round tables etc); (c) Commercial and financial close; (d) Procurement; and (e) Implementation | Planned -annual | n/a | Too early | Too early | I. Project pipeline: 3 MZ.P1.01 Sustainable Finance: 1.GCF country programme report for MoZ, an GCF requirement to be able to access TA funds and put forward project proposals reviewed/acccepted by the CFU 2. GCF multi-year readiness proposal to allow CFU access TA funding for project development reviewed/accepted by the CFU MZ.P1.02 Pemba: 3. Portfolio of investments reviewed/accepted by the Pemba Muncipality II. Project Specific support: 6 MZ.P1.02 Pemba: 1. Green Energy project : Strategic Outline business case (SOBC) reviewed/accepted by the Municipality 2. Green Urban Park project: SOBC reviewed/accepted by the Municipality 3. Bypass Green Road project: Concept Note reviewed/accepted by the Muncipality MZ.P1.03 Beira: 4. Miramar park project: Business Case reviewed/accepted by the Muncipality MZ.P2.03 Cities: 5. Triangulo Basin project in Nacala: Prefeasibility report reviewed/accepted by the Muncipality 6. Nacala public space: Strategic Outline Business Case reviewed/accepted by the Muncipality
|  | Achieved - annual |  | Too early | 0 | I.Project pipeline: 3 MZ.P1.01 Sustainable Finance: 1.GCF country programme report for MoZ, an GCF requirement to be able to access TA funds and put forward project proposals reviewed/acccepted by the CFU 2. GCF multi-year readiness proposal to allow CFU access TA funding for project development reviewed/accepted by the CFU MZ.P1.02 Pemba: 3. Portfolio of investments reviewed/accepted by the Pemba Muncipality II. Project Specific support: 4 MZ.P1.02 Pemba: 1. Green Energy project : Strategic Outline business case (SOBC) reviewed/accepted by the Municipality 2. Green Urban Park project: SOBC reviewed/accepted by the Municipality 3. Bypass Green Road project: Concept Note reviewed/accepted by the Muncipality MZ.P1.03 Beira: 4. Miramar park project: Business Case reviewed/accepted by the Muncipality
|  | Achieved - cumulative |  | Too early | 0
Source
GCIEP RM databases and Intervention Pathways Packages at the DOC intervention level Note: High quality equals to projects that have mainstreamed GEDSI and CN&E GCIEP DO C supported projects/initiatives along the infrastructure development cycle: (a) Planning & preparation (project pipelines, concept note, business cases, (pre) feasibility studies); (b) Financing structuring (project development agreement, investment round tables etc); (c) Commercial and financial close; (d) Procurement; and (e) Implementation
INTERMEDIATE OUTCOME 3 | INT Outcome Indicator 3.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Influencing and collaboration Uptake of relevant knowledge and evidence generated by GCIEP and/or its delivery partners by the GoV as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services (REPORTED ANNUALLY) | INFORMING DECISION MAKING: Number of policies/regulations/strategies/roadmaps/frameworks/institutional structures in Mozambique that have been informed with contributions from GCIEP TA. (disag by Strategy & Planning, Legal & Regulatory Framework, Financing Mechanisms, Institutional capacity & governance, Networks & Partnerships) | Planned -annual |  |  | n/a | MZ.P1.01 Climate Finance 1. National Climate Finance Strategy and Roadmap accepted by CFU MZ.P1.02 Pemba 2. Financial and Investment Public Assessment (PEFA & PIMA) concluded to inform municipal financial and investment decision-making 3. Detailed design plans to inform urban planning in Metula and Maringhana areas in Pemba reviewed/accepted by the Muncipality MZ.P1.03 Beira 4. Strategic approach on O&M for Coastal Protection to suppport communities improve coastral protecion infrastructure reviewed/accepted by the Municipality 5. Urban detail plan to inform urban planning in the Mucurungo Miquejo area reviewed/accepted by the Municipality 6. Manual for Community Evacuation Planning in Case of Cyclones and Floods for Beira Municipality eviewed/accepted by the Municipality MZ.P1.04 Nacala: 7. Urban Structured Plan to inform Nacala urban planning reviewed /accepted by the Directorate of Land and Territorial Development at the Municipality MZ.P2.01 Land mgt 8. Municipal cadastre scaling strategy to enhance Nacala land management is reviewed/accepted by the Municipality 9. Municipal cadastre scaling strategy to enhance Pemba land management is reviewed/accepted by the Municipality 10. Digital cadastre piloted in Nacala selected areas 11. Digital cadastre piloted in Pemba selected areas MZ.P2.01 Beira 12. Note on how training could be replicated in other disaster-prone coastal cities in Mozambique accepted/reviewed by CMB MZ.P2.03 Cities 13. Municipal physical asset register piloted in selected areas (Pemba) | * Central FCDO and country offices are open to learning from and being influenced by GCIEP generated knowledge - when relevant . * Deliverables can include policies, regulations, roadmaps, strategies, frameworks, institutional structure / governance report, etc. that have been submitted/reviewed/accepted/approved by the beneficiary stakeholder/s (depending on country context). *Targets and results include deliverables that are REVIEWED/ ACCEPTED by the beneficiary stakeholder that are used as as source of evidence, insights, or recommendations to inform policies, strategies, or actions in FCDO partner countries.
|  | Achieved - annual |  |  |  | MZ.P1.02 Pemba: 1. Financial and Investment Public Assessment (PEFA & PIMA) concluded to inform municipal financial and investment decision-making 2. Detailed design plans for the 2 pilot areas reviewed/accepted by the CMP MZ.P1.03 Beira 3.Strategic approach on O&M for Coastal Protection to suppport communities improve coastral protecion infrastructure reviewed/accepted by the Municipality 4. Manual for Community Evacuation Planning in Case of Cyclones and Floods for Beira Municipality eviewed/accepted by the Municipality Counted against Outcome 2.1 as per it was formally approved, achieved earlier than expected: MZ.P1.01 Climate Sustainble: National Climate Finance Strategy and Roadmap accepted by the CFU MZ.P1.02 Pemba: Detailed design plans for the 2 pilot areas accepted b by the Municipal Assembly in Pemba MZ.P1.03 Beira: Urban detail plan to inform urban planning in the Mucurungo Miquejo area reviewed/accepted by the Municipality MZ.P1.04 Nacala: Nacala Urban Structured Plan to inform urban planning reviewed /accepted by the Directorate of Land and Territorial Development at the Municipality
Achieved - cumulative
|  | Source |  |  |  |  | RISK RATING
|  | GCIEP monitoring and operational databases |  |  |  |  | MODERATE
INTERMEDIATE OUTCOME 4 | INT Outcome Indicator 4.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
DOC interventions have successfully integrated GEDSI risks and opportunties resulting in Empowerment (REPORTED ANNUALLY) | % of DOC intervention that include GEDSI considerations in accordance with Level 2 - Empowerment - as per the FCDO GEDSI framework (realised target ambition) - Linked to Output 4 | Planned -annual |  |  |  | 50% | *Resources at DOC and TO level are deployed to ensure that GEDSI is effectively mainstreamed during implementation, regularly identifying and assessing GEDSI risks and opportunities
Achieved - annual
|  | Source |  |  |  |  | RISK RATING
|  | GCIEP GEDSI monitoring; GCIEP deliverables TOR and GCIEP work package progress reports Note: it only applies to interventions that have GEDSI potential |  |  |  |  | MODERATE
OUTPUT 1 | Output Indicator 1.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
High-quality TA deliverables completed by GCIEP for FCDO posts to facilitate economic transformation and inclusive growth (in line with VfM targets) (REPORTED QUARTERLY) | DOC Percentage of the activities planned at the start of each quarter that are completed. | Planned -annual | n/a | n/a | 70% | 70%
|  | Achieved - annual | n/a | n/a | 79.1%
Source
GCIEP DOC intervention workplans Note: Total number of activities completed during the quarter / total number of activities planned to be completed as per workplan submitted to FCDO at the start of the quarter. It is expected that the activities detailed (and related deliverables) in the intervention workplan will be updated on a quarterly basis in line with adaptive management best practice.
WEIGHTING: | [6 empty] | RISK RATING
MINOR
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Proactive strategic collaboration to maximise effectiveness in GCIEP delivery in TO and/or DOC countries (REPORTED QUARTERLY) | No. of instances where GCIEP team has worked and/or coordinated* with partners** A) GCIEP DOC interventions B) GCI CoE delivery partners C) Any other UK expert organisations D) Development partners (instances that DOC and Buy-ins have collaborated with development partners) | Planned -annual | n/a | n/a | n/a | B) 2 (British Geological Survey (BGS), Ordnance Survey) D) 4 (AfDB, Green Climate Fund, World Bank, JICA) | *GCIEP can effectively target its assistance, to choose the right agencies/municipalities and/or institutions with which to partner and select the right interventions * Targets (n/a): Targets are not applicable, as we are a demand driven programme working under adaptive programming principles
|  | Achieved - annual | n/a | n/a | C) 1 (Oxford Survey) D) 9 (AfDB, Belgian Development Agency, Deutsche Gesellschaft fur Interantinoale Zusammenarbeit, Dutch Government, E35, Green Climate Fund, KfW, Netherlands Enterprise Agency, United Nationals Human Settlements Programme, World Bank)
|  | Achieved - cumulative | n/a | n/a | C) 1 D) 9
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
10% |  | GCIEP monitoring and operational databases Notes: *Co-ordination defined as having an active Community of Practice/signed MoU/other formal engagement process in place) ** Partners defined as any in-country international development agency or donor based in a DOC country ***GCIEP CoE delivery partners: Cross Rail Intl, Ofgem, Infrastructure and Projects Authority, Transport for London, BSI; CATAPULT, Ordinance Survey and British Geological Survey |  |  |  |  | MINOR
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Enhancing capacity and knowledge to strengthen GCIEP supported institutions and agencies in partner countries (disag by DOC and TO) (REPORTED QUARTERLY) | Percentage and number of people certified in UK tools and methodologies (Only applicable if there is formal UK certification offer. UK tools and methodologies with certification exam include, for example, 5CM) | Planned -annual | n/a | Too early | 0 | 0 | * GCIEP has the capacity to deliver targeted and high quality trainings, adapted to the needs to targeted stakeholders *GCIEP can leverage on UK expertise to successfully deliver TA *GCIEP will report on ACTUALS across all indicators, on a quarterly basis (wherever relevant) * Targets (n/a): Targets are not applicable, as we are a demand driven programme working under adaptive programming principles
|  | Achieved - annual | n/a | Too early | 0
|  | Achieved - cumulative | n/a | Too early | 0
|  | Source |  |  |  |  | RISK RATING
|  | GCIEP RM and operational databases Note: Number of people certified / total number of people trained in UK tools and methodologies taking the exam. |  |  |  |  | MINOR
| Output Indicator 3.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
| Number (#) of people trained via GCIEP supported work packages/interventions Disaggregation: portfolio (DOC, TO, Buy-in), women professionals, people with disabilities, and youth, indicate if UK methodology. | Planned -annual | n/a | n/a | n/a | 815 | *GCIEP has the capacity to deliver targeted and high quality trainings, adapted to the needs to targeted stakeholders *GCIEP can leverage on UK expertise to successfully deliver TA *Setting a target for this indicator was deemed not applicable (in agreement with FCDO) during GCIEP’s first full year of delivery in Year 2 , due to the demand-driven nature of the programme. Instead, it was agreed we would report Actuals in the Y2 log frame. However, where there are continuing interventions in Y3 (second full year of GCIEP delivery) with many of the same stakeholders and sectors, we have included targets in the Year 3 log frame for this indicator.
|  | Achieved - annual | n/a | n/a | 155 total (61 women, 37 youth)
|  | Achieved - cumulative | n/a | n/a | 155 total (61 women, 37 youth)
Source
GCIEP RM and operational databases
| Output Indicator 3.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| % of participants indicating that the training/capacity building in Output 3.1 or 3.2 was "useful" or "very useful" on a 5 point scale | Planned -annual | n/a | n/a | 70% | 85%
|  | Achieved - annual | n/a | n/a | 100% (23 of 23)
|  | Achieved - cumulative | n/a | n/a | 100% (23 of 23)
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
10% |  | GCIEP RM and operational databases |  |  |  |  | MINOR
OUTPUT 4 | Output Indicator 4.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
GEDSI is mainstreamed across GCIEP DOC interventions and Target Offer (TO) work packages (WPs) (disag by DOC and TO) (REPORTED ANNUALLY) | % of GCIEP supported DOC interventions/TO WPs that have an ambition of level 2 - Empowerment as per the FCDO GEDSI framework Disaggregated by FCDO GEDSI framework levels 1-3 | Planned - annual | n/a | n/a | L2: 50% | 50% | *The FCDO GEDSI Framework is effective into translating FCDO’s GEDSI policies into programming; enabling GCIEP to take a structured and practical approach to exploring how GCIEP interventions can maximise benefits to disadvantaged and vulnerable groups
|  | Achieved - annual | n/a | n/a | 75%
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
15% |  | GCIEP GEDSI monitoring; GCIEP deliverables TOR and GCIEP work package progress reports Note: it only applies to interventions that have GEDSI potential |  |  |  |  | MINOR
OUTPUT 5 | Output Indicator 5.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
CN&E is mainstreamed across GCIEP DOC interventions and Target Offer (TO) work packages (WPs) (ICF compliance) (disag by DOC and TO) (REPORTED ANNUALLY) | % of GCIEP supported DOC interventions/TO work packages that are mainstreaming CN&E | Planned - annual | n/a | n/a | 100% | 100% | *ICF compliant: An interventions that contributes to at least 1 ICF KPI indicator *ICF KPI TA methodology only allows actuals to be reported
|  | Achieved - annual | n/a | n/a | 100%
Source
GCIEP ICF monitoring; DOC intervention ToRs and TO Work Package ToRs; GCIEP progress reports
| Output Indicator 5.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| % of total spend that is ICF compliant in relation to the total £ value of GCIEP programmes - of eligible ODA | Planned - annual | n/a | n/a | 80% | 80%
|  | Achieved - annual | n/a | n/a | 87%
Source
GCIEP ICF monitoring; DOC intervention ToRs and TO Work Package ToRs; GCIEP progress reports
| Output Indicator 5.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of countries supported by ICF technical assistance ICF TA KPI 1 (reported only on completed DOC interventions/TO WPs) | Planned - annual | n/a | n/a | n/a: ICF KPI methodology only allows actuals to be reported | n/a
|  | Achieved - annual | n/a | n/a | TBC by Dec25
|  | Achieved - cumulative | n/a | n/a | TBC by Dec25
Source
GCIEP CN&E monitoring; DOC intervention ToRs and TO work package ToRs; GCIEP progress reports
| Output Indicator 5.4 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of individuals supported by ICF technical assistance ICF TA KPI 2.1 (reported only on completed DOC interventions/TO WPs) | Planned - annual | n/a | n/a | n/a: ICF KPI methodology only allows actuals to be reported | n/a
|  | Achieved - annual | n/a | n/a | TBC by Dec25
|  | Achieved - cumulative | n/a | n/a | TBC by Dec25
Source
GCIEP CN&E monitoring; DOC intervention ToRs and TO work package ToRs; GCIEP progress reports
| Output Indicator 5.5 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of organisations supported by ICF technical assistance ICF TA KPI 2.2 (reported only on completed DOC interventions/TO WPs) | Planned - annual | n/a | n/a | n/a: ICF KPI methodology only allows actuals to be reported | n/a
|  | Achieved - annual | n/a | n/a | TBC by Dec25
|  | Achieved - cumulative | n/a | n/a | TBC by Dec25
Source
GCIEP CN&E monitoring; DOC intervention ToRs and TO work package ToRs; GCIEP progress reports
| Output Indicator 5.6 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of climate policies informed by ICF technical assistance ICF TA KPI 3 (reported only on completed DOC interventions/TO WPs) | Planned - annual | n/a | n/a | n/a: ICF KPI methodology only allows actuals to be reported | n/a
|  | Achieved - annual | n/a | n/a | TBC by Dec25
|  | Achieved - cumulative | n/a | n/a | TBC by Dec25
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
15% |  | GCIEP CN&E monitoring; DOC intervention ToRs and TO work package ToRs; GCIEP progress reports |  |  |  |  | MINOR
OUTPUT 6 | Output Indicator 6.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Learning (evidence) produced and in place for GCIEP to collate and disseminate UK and international urban / infrastructure expertise within GCIEP, FCDO, and to the wider ecosystem (REPORTED QUARTERLY) | No. of GCIEP products (analysis and learning including events) that deliver insights which inform/shape FCDO/wider development partner policies and programmes Dissaggregation by events and products | Planned - annual | n/a | Too early | n/a | 20 | *Sufficient GCIEP budget is allocated to undertake planned L&C activities approved in the ToR L&C *Setting a target for this indicator was deemed not applicable (in agreement with FCDO) during GCIEP’s first full year of delivery in Year 2 , due to the demand-driven nature of the programme. Instead, it was agreed we would report Actuals in the Y2 log frame. However, where there are continuing interventions in Y3 (second full year of GCIEP delivery) with many of the same stakeholders and sectors, we have included targets in the Year 3 log frame for this indicator.
|  | Achieved - annual | n/a | Too early | 8 (5 products & 3 events)
|  | Achieved - cumulative | n/a | Too early | 8 (5 products & 3 events)
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
10% |  | GCIEP RM and L&C monitoring, GCIEP K&L documentation (including links to public KPs and materials published) Note: a. A GCIEP Product is any written material produced by GCIEP and/or its delivery partners, through its DOC interventions/ TO work packages, that has been repackaged according to targeted audience/s and dissemination channel/s including learning events, that seek to contribute to the body of infra delivery and urban development knowledge towards improving FCDO and GCIEP delivery partners programming . This GCIEP product is out of the budget of the TO WP. |  |  |  |  | MINOR
º
Note on G40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These are not infrastructure projects Reply: Agreed, some of them are not but they are contributing to develop a set of projects in future.
Note on G46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1. If no decision making has happened, this doesn’t qualify 2. what’s the decision that is being considered or has been made? 3. Is there a municipality strategy planned that this will inform? (continuing, all these should state the policy etc that the deliverables are expected to inform.)

## ZAMBIA nested LF
PROGRAMME NAME: | Green Cities, Infrastructure and Energy Programme (GCIEP) Y3 Logframe - DOC ZAMBIA (22 January 2026)
OUTCOME 1 | Outcome Indicator 1.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Finance and Investment is leveraged for sustainable and inclusive infrastructure and the built environment in Zambia (DOC only and TO - if reported by Post) (REPORTED ANNUALLY) | Total volume of total non-GCIEP financing mobilised as a result of GCIEP interventions in < (£ ) Disaggregation by: type of funding organisation (Private/Donor/Public -National/Municipal), financing categories (catalysed, facilitated, unlocked, and reallocated) To track off logframe, GCIEP country programmes where non-FCDO funds have been leveraged downstream | Planned -annual | n/a | Too early | Too early | 0 | *GCIEP TA makes a contribution towards facilitating investment into urban economic infrastructure projects and overcoming obstacles to project delivery *Partner government continued support for: i) pro-poor, inclusive, low carbon and resilient objectives and targeted approaches; and ii) channel private and public investment into urban development and economic infrastructure *Target and Results will be based only on DOC interventions; but GCIEP will also report on results from TO work packages, in case there is GCIEP contribution and results have been tracked either by GCIEP or FCDO Post (post completion monitoring) * COMMITTED refers to: The financing quantified has already been committed/mobilised by other investors, where GCIEP TA is being used to make the investment “bigger, better or faster."
|  | Achieved - annual | n/a | Too early | 0
|  | Achieved - cumulative | n/a | Too early | 0
Source
GCIEP DOC and TO RM databases
| Outcome Indicator 1.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Volume of public finance mobilised for climate change purposes in Zambia (£) (as a result of GCIEP interventions ) (disag by new financing vs reallocated financing) (ICF KPI 11) | Planned -annual | n/a | Too early | n/a | n/a: ICF KPI methodology only allows actuals to be reported
| ICF KPI 12 Volume of private finance mobilised for climate change purposes | Achieved - annual | n/a | Too early | 0
|  | Achieved - cumulative | n/a | Too early | 0
Source
GCIEP RM databases and ICF monitoring ICF KPI Methodology: https://assets.publishing.service.gov.uk/media/5b17935be5274a190c1b6f8c/KPI11-Public-finance-Updated-methodology.pdf
| Outcome Indicator 1.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Volume of private finance mobilised for climate change purposes in Zambia (£) (as a result of GCIEP interventions) (ICF KPI 12) | Planned -annual | n/a | Too early | n/a | n/a: ICF KPI methodology only allows actuals to be reported
| ICF KPI 12 Volume of private finance mobilised for climate change purposes | Achieved - annual | n/a | Too early | 0
|  | Achieved - cumulative | n/a | Too early | 0
|  | Source |  |  |  |  | RISK RATING
|  | GCIEP RM databases and ICF monitoring ICF KPI Methodology: https://assets.publishing.service.gov.uk/media/65e0b9913f6945001d036030/KPI-12-volume-private-finace-mobilised.pdf |  |  |  |  | MODERATE
OUTCOME 2 | Outcome 2.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
GCIEP TA contributed to a stronger enabling environment in Zambia for the provision of climate resilient&inclusive infrastructure services (REPORTED ANNUALLY) | APPROVAL: Number of approved policies/regulations/strategies/roadmaps/frameworks/institutional structures in Zambia supported by GCIEP TA. (disag by Strategy & Planning, Legal & Regulatory Framework, Financing Mechanisms, Institutional capacity & governance, Networks & Partnerships) | Planned -annual | n/a | Too early | Too early | ZM.P1.01 Energy 1. A one-stop service for energy sector to streamline multiple approval energy-related processes into a single, integrated workflow is further-improved | *Central FCDO and country offices are open to learning from and being influenced by GCIEP generated knowledge - when relevant * Collaboration with CoE DPs collaboration increase urban and infrastructure effectiveness leading to local adoption and replication * No material change in government priorities with any political changes in countries that undergo national elections * Deliverables can include policies, regulations, roadmaps, strategies, frameworks, institutional structure / governance report, etc. that have been submitted/reviewed/accepted/approved by the beneficiary stakeholder/s (depending on country context) * APPROVAL: Formal endorsement of GCIEP supported policy/regulations/strategies/roadmaps/frameworks/institutional structures at FCDO partner countries by the beneficiary stakeholder (or the appropriate designated authority) * ADOPTION: The formal embedding and / or implementation of a GCIEP-supported structure, process, methodology or practices by FCDO partner countries, maintaining the core design and function of the original model, through minor contextual adjustments may be made. A deliverable is counted either as APPROVED or ADOPTED but not both, except in the case where GCIEP provides continious to support over time resulting in an evolution from APPROVAL to ADOPTION. In such execptional cases policy/regulations/strategies/roadmaps/frameworks/institutional structures may be reported at both level, usually for different years.
|  | Achieved - annual |  | Too early | 0 | ZM.P1.01 Energy 1. A one-stop service for energy sector to streamline multiple approval energy-related processes into a single, integrated workflow is further-improved 2. Analysis to Power Sector Incentives informing a new tax incentive regime for independent power producers approved by the Office for Promoting Private Power Investment
|  | Achieved - cumulative |  | Too early | 0
Source
GCIEP L&C tracking tool, GCIEP K&L documentation Note: deliverables must be approved by the beneficiary entity
| Outcome 2.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| ADOPTION: Number of GCIEP supported policies/regulations/strategies/roadmaps/frameworks/institutional structures adopted as evidence of GCIEP legacy / sustainability in GCIEP supported entities in Zambia (sustainability) (disag by Strategy & Planning, Legal & Regulatory Framework, Financing Mechanisms, Institutional capacity & governance, Networks & Partnerships) | Planned -annual | n/a | Too early | Too early | 0
|  | Achieved - annual |  | Too early | 0
|  | Achieved - cumulative |  | Too early | 0
|  | Source |  |  |  |  | RISK RATING
|  | GCIEP RM databases and Intervention Pathways Packages at the intervention level |  |  |  |  | MODERATE
Y3 Interim PLF (August 2025) the following indicators were considered obsolete in agreement with FCDO: * Outcome 2.2 Replication: Number of GCIEP supported structures, processes, and / or methodologies replicated (and adapted) by country governement ministries
INTERMEDIATE OUTCOME 1 | INT Outcome Indicator 1.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
GCIEP DOC is effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development (REPORTED ANNUALLY) | A) Increase in scope: Percentage of DOC interventions that have increase their scope since the start of the programme - CUMULATIVE (total number of DOC interventions scaled up / total number of DOC interventions) B) Closed / curtailed: Percentage of DOC interventions closed and / or curtailed since the start of the programme - CUMULATIVE (total number of DOC interventions closed or curtailed / total number of DOC interventions) C) New DOC interventions: Total number of DOC interventions introduced based on learning during GCIEP implementation phase | Planned -annual | n/a | n/a | n/a | n/a | *GCIEP can effectively target its assistance, to choose the right agencies/municipalities and/or institutions with which to partner and select and test the adequate interventions * GCIEP has in place the Impact Pathway packages to monitor DOC interventions applying adaptive programming principles *No material change in government priorities with any political changes in countries that undergo national elections * Well prepared projects (including feasibility studies) supported by GCIEP will attract the necessary downstream financing * In some cases, targets are not applicable, as we are a demand driven programme working under adaptive programming principles
|  | Achieved - annual | n/a | n/a | 0 | 2 C) ZM.P2.01 Procurement and Open Access; ZM.P2.02 Financing, transmission and sector coordination
|  | Achieved - cumulative | n/a | n/a | 0
Source
GCIEP RM databases and Intervention Pathways Packages at the intervention level Phase 1 interventions treated as scaled up for Phase 2
| INT Outcome Indicator 1.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) Disaggregated by stage of the infrastructure development cycle: (I) Project pipeline and (II) Project specific support including (a) Planning & preparation (concept note, business cases, (pre) feasibility studies); (b) Financing structuring (project development agreement, investment round tables etc); (c) Commercial and financial close; (d) Procurement; and (e) Implementation | Planned -annual | n/a | Too early | Too early | I. Project pipeline: 1 ZM.P1.01: (WS1) Fast Track Procurement 1.Prioritised renewable energy pipeline of 40 solar projects based on GCIEP analysis reviewed/acccepted by Office for Promoting Private Power Investment II. Project Specific support: 1 ZM.P2.01: Procurement & Open Access 1.100 MW suite of solar projects: Tender Documentation (RfP) reviewed/acccepted by the Gvt of Zambia
|  | Achieved - annual |  | Too early | I. Project pipeline: 1 ZM.P1.01: (WS1) Fast Track Procurement 1.Prioritised renewable energy pipeline of 40 solar projects based on GCIEP analysis reviewed by Office for Promoting Private Power Investment
|  | Achieved - cumulative |  | Too early | 1
Source
GCIEP RM databases and Intervention Pathways Packages at the DOC intervention level Note: High quality equals to projects that have mainstreamed GEDSI and CN&E GCIEP DO C supported projects/initiatives along the infrastructure development cycle: (a) Planning & preparation (project pipelines, concept note, business cases, (pre) feasibility studies); (b) Financing structuring (project development agreement, investment round tables etc); (c) Commercial and financial close; (d) Procurement; and (e) Implementation
INTERMEDIATE OUTCOME 3 | INT Outcome Indicator 3.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Influencing and collaboration Uptake of relevant knowledge and evidence generated by GCIEP and/or its delivery partners by the GoV as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services (REPORTED ANNUALLY) | INFORMING DECISION MAKING: Number of policies/regulations/strategies/roadmaps/frameworks/institutional structures in Zambia that have been informed with contributions from GCIEP TA. (disag by Strategy & Planning, Legal & Regulatory Framework, Financing Mechanisms, Institutional capacity & governance, Networks & Partnerships) | Planned -annual |  |  | Too early | ZM.P1.01 WS1 Fast Track Procurement 1. 100 MW suite of solar projects: Recommended Legal Risk Allocation Structure for solar power accepted/reviewed by the Office for Promoting Private Power Investment 2. 100 MW suite of solar projects: Fast track procurement approach recommendations for solar projects (including detail on RfP structure, content, adjudication process, and credit support structure) reviewed/accepted by the MoE WS3 Policy, Institutional, and Legal Environment 3. Recommended Policy, Legal, and Institutional framework for energy procurement to inform public procurement reviewed/accepted by FCDO Zambia and submitted to the Ministry of Energy WS4 Functional Procurement Process 4. Final recommendation of procurement process reviewed/accepted by Permanent Secretary at the Ministry of EnergyWS5 Energy Sector Financial Sustainability 5. Analysis to Power Sector Incentives informing a new tax incentive regime for independent power producers reviewed/accepted by the Office for Promoting Private Power Investment ZM.P2.01 Procurement &Open Access 6.Report on governance structure, seed funding, and key roles for the establishment of new procurement office reviewed/accepted by MoE 7.Electricity bill: Inputs in the bill in relation to the public service trader reviewed/accepted by MoE 8.Report on model that unbundles ZESCOs costs to inform open access reviewed/accepted by ZESCO ZM.P2.02 Transmission 9. Pitch Decks to inform South African banks and other capital providers interested in Zambia’s power sector reviewed/accepted by ZESCO 10. Priority Transmission Development Report to 2035 reviewed/accepted by ZESCO 11.Transmission Financing Report and Recommendations reviewed/accepted by ZESCO | * Central FCDO and country offices are open to learning from and being influenced by GCIEP generated knowledge - when relevant . * Deliverables can include policies, regulations, roadmaps, strategies, frameworks, institutional structure / governance report, etc. that have been submitted/reviewed/accepted/approved by the beneficiary stakeholder/s (depending on country context). *Targets and results include deliverables that are REVIEWED/ ACCEPTED by the beneficiary stakeholder that are used as as source of evidence, insights, or recommendations to inform policies, strategies, or actions in FCDO partner countries.
|  | Achieved - annual |  |  | ZM.P1.01 (WS1) Fast Track Procurement Recommended fast track procurement approach accepted/reviewed by MoE | ZM.P1.01 Energy WS1 Fast Track Procurement 1. 100 MW suite of solar projects: Recommended Legal Risk Allocation Structure for solar power accepted/reviewed by the Office for Promoting Private Power Investment 2. 100 MW suite of solar projects: Fast track procurement approach recommendations for PV solar projects (including detail on RfP structure, content, adjudication process, and credit support structure) accepted by the MoE WS3 Policy, Institutional, and Legal Environment 3. Recommended Policy, Legal, and Institutional framework for energy procurementaccepted/reviewed by Post and submitted to the MoE WS4 Functional Procurement Process 4. Final recommendation of procurement process shared with Permanent Secretary at the Ministry of Energy WS5 Energy Sector Financial Sustainability * Analisis to Power Sector Incentives approved by the Office for Promoting Private Power Investment - Moved to Outcome 2.1 as it has been formally approved, achieved earlier than expected
|  | Achieved - cumulative |  |  | 1
|  | Source |  |  |  |  | RISK RATING
|  | GCIEP monitoring and operational databases |  |  |  |  | MODERATE
INTERMEDIATE OUTCOME 4 | INT Outcome Indicator 4.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
DOC interventions have successfully integrated GEDSI risks and opportunties resulting in Empowerment (REPORTED ANNUALLY) | % of DOC intervention that include GEDSI considerations in accordance with Level 2 - Empowerment - as per the FCDO GEDSI framework (realised target ambition) - Linked to Output 4 | Planned -annual |  |  |  | 50% | *Resources at DOC and TO level are deployed to ensure that GEDSI is effectively mainstreamed during implementation, regularly identifying and assessing GEDSI risks and opportunities
Achieved - annual
|  | Source |  |  |  |  | RISK RATING
|  | GCIEP GEDSI monitoring; GCIEP deliverables TOR and GCIEP work package progress reports Note: it only applies to interventions that have GEDSI potential |  |  |  |  | MODERATE
OUTPUT 1 | Output Indicator 1.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
High-quality TA deliverables completed by GCIEP for FCDO posts to facilitate economic transformation and inclusive growth (in line with VfM targets) (REPORTED QUARTERLY) | DOC Percentage of the activities planned at the start of each quarter that are completed. | Planned - cumulative | n/a | n/a | 70% | 70%
|  | Achieved - annual | n/a | n/a | 89.2%
Source
GCIEP DOC intervention workplans Note: Total number of activities completed during the quarter / total number of activities planned to be completed as per workplan submitted to FCDO at the start of the quarter. It is expected that the activities detailed (and related deliverables) in the intervention workplan will be updated on a quarterly basis in line with adaptive management best practice.
WEIGHTING: | [6 empty] | RISK RATING
MINOR
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Proactive strategic collaboration to maximise effectiveness in GCIEP delivery in TO and/or DOC countries (REPORTED QUARTERLY) | No. of instances where GCIEP team has worked and/or coordinated* with partners** A) GCIEP DOC interventions B) GCI CoE delivery partners C) Any other UK expert organisations D) Development partners (instances that DOC and Buy-ins have collaborated with development partners) | Planned -annual | n/a | n/a | n/a | C) 2 (CIG Zambia, Climate Compatible Growth) D) 7 (African Development Bank (AfDB), EU, KfW (German), USAID,Multilateral International Guarantee Agency (MIGA), World Bank and International Finance Corporation (IFC) (both part of the WB Group)) | *GCIEP can effectively target its assistance, to choose the right agencies/municipalities and/or institutions with which to partner and select the right interventions
|  | Achieved - annual | n/a | n/a | C) 3 (BII&Globaleq, CIG Zambia, Climate Compatible Growth) D) 6 (AfDB, EU, KfW, MIGA, USAID, WB)
|  | Achieved - cumulative | n/a | n/a | C) 3 D) 6
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
10% |  | GCIEP monitoring and operational databases Notes: *Co-ordination defined as having an active Community of Practice/signed MoU/other formal engagement process in place) ** Partners defined as any in-country international development agency or donor based in a DOC country ***GCIEP CoE delivery partners: Cross Rail Intl, Ofgem, Infrastructure and Projects Authority, Transport for London, BSI; CATAPULT, Ordinance Survey and British Geological Survey |  |  |  |  | MINOR
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Enhancing capacity and knowledge to strengthen GCIEP supported institutions and agencies in partner countries (disag by DOC and TO) (REPORTED QUARTERLY) | Percentage and number of people certified in UK tools and methodologies (Only applicable if there is formal UK certification offer. UK tools and methodologies with certification exam include, for example, 5CM) | Planned -annual | n/a | Too early | n/a | 0 | * GCIEP has the capacity to deliver targeted and high quality trainings, adapted to the needs to targeted stakeholders *GCIEP can leverage on UK expertise to successfully deliver TA *Setting a target for this indicator was deemed not applicable (in agreement with FCDO) during GCIEP’s first full year of delivery in Year 2 , due to the demand-driven nature of the programme. Instead, it was agreed we would report Actuals in the Y2 log frame. However, where there are continuing interventions in Y3 (second full year of GCIEP delivery) with many of the same stakeholders and sectors, we have included targets in the Year 3 log frame for this indicator.
|  | Achieved - annual | n/a | Too early | 0
|  | Achieved - cumulative | n/a | Too early | 0
Source
GCIEP RM and operational databases Note: Number of people certified / total number of people trained in UK tools and methodologies taking the exam.
| Output Indicator 3.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number (#) of people trained via GCIEP supported work packages/interventions Disaggregation: portfolio (DOC, TO, Buy-in), women professionals, people with disabilities, and youth, indicate if UK methodology. | Planned -annual | n/a | n/a | n/a | 25
|  | Achieved - annual | n/a | n/a | 20 Total (13 women)
|  | Achieved - cumulative | n/a | n/a | 20 Total (13 women)
Source
GCIEP RM and operational databases
| Output Indicator 3.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| % of participants indicating that the training/capacity building in Output 3.1 or 3.2 was "useful" or "very useful" on a 5 point scale | Planned -annual | n/a | n/a | 70% | 85%
|  | Achieved - annual | n/a | n/a | 100% (1 of 1)
|  | Achieved - cumulative | n/a | n/a | 100% (1 of 1)
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
10% |  | GCIEP RM and operational databases |  |  |  |  | MINOR
OUTPUT 4 | Output Indicator 4.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
GEDSI is mainstreamed across GCIEP DOC interventions and Target Offer (TO) work packages (WPs) (disag by DOC and TO) (REPORTED ANNUALLY) | % of GCIEP supported DOC interventions/TO WPs that have an ambition of level 2 - Empowerment as per the FCDO GEDSI framework Disaggregated by FCDO GEDSI framework levels 1-3 | Planned - annual | n/a | n/a | L2: 50% | 50% | *The FCDO GEDSI Framework is effective into translating FCDO’s GEDSI policies into programming; enabling GCIEP to take a structured and practical approach to exploring how GCIEP interventions can maximise benefits to disadvantaged and vulnerable groups
|  | Achieved - annual | n/a | n/a | 66%
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
15% |  | GCIEP GEDSI monitoring; GCIEP deliverables TOR and GCIEP work package progress reports Note: it only applies to interventions that have GEDSI potential |  |  |  |  | MINOR
OUTPUT 5 | Output Indicator 5.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
CN&E is mainstreamed across GCIEP DOC interventions and Target Offer (TO) work packages (WPs) (ICF compliance) (disag by DOC and TO) (REPORTED ANNUALLY) | % of GCIEP supported DOC interventions/TO work packages that are mainstreaming CN&E | Planned - annual | n/a | Too early | 100% | 100% | *ICF compliant: An interventions that contributes to at least 1 ICF KPI indicator *ICF KPI TA methodology only allows actuals to be reported
|  | Achieved - annual | n/a | Too early | 100%
Source
GCIEP ICF monitoring; DOC intervention ToRs and TO Work Package ToRs; GCIEP progress reports
| Output Indicator 5.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| % of total spend that is ICF compliant in relation to the total £ value of GCIEP programmes - of eligible ODA | Planned - annual | n/a | Too early | 80% | 80%
|  | Achieved - annual | n/a | Too early | 89%
Source
GCIEP ICF monitoring; DOC intervention ToRs and TO Work Package ToRs; GCIEP progress reports
| Output Indicator 5.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of countries supported by ICF technical assistance ICF TA KPI 1 (reported only on completed DOC interventions/TO WPs) | Planned - annual | n/a | Too early | n/a | n/a
|  | Achieved - annual | n/a | Too early | TBC by Dec25
|  | Achieved - cumulative | n/a | Too early | TBC by Dec25
Source
GCIEP CN&E monitoring; DOC intervention ToRs and TO work package ToRs; GCIEP progress reports
| Output Indicator 5.4 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of individuals supported by ICF technical assistance ICF TA KPI 2.1 (reported only on completed DOC interventions/TO WPs) | Planned - annual | n/a | Too early | n/a | n/a
|  | Achieved - annual | n/a | Too early | TBC by Dec25
|  | Achieved - cumulative | n/a | Too early | TBC by Dec25
Source
GCIEP CN&E monitoring; DOC intervention ToRs and TO work package ToRs; GCIEP progress reports
| Output Indicator 5.5 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of organisations supported by ICF technical assistance ICF TA KPI 2.2 (reported only on completed DOC interventions/TO WPs) | Planned - annual | n/a | Too early | n/a | n/a
|  | Achieved - annual | n/a | Too early | TBC by Dec25
|  | Achieved - cumulative | n/a | Too early | TBC by Dec25
Source
GCIEP CN&E monitoring; DOC intervention ToRs and TO work package ToRs; GCIEP progress reports
| Output Indicator 5.6 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of climate policies informed by ICF technical assistance ICF TA KPI 3 (reported only on completed DOC interventions/TO WPs) | Planned - annual | n/a | Too early | n/a | n/a
|  | Achieved - annual | n/a | Too early | TBC by Dec25
|  | Achieved - cumulative | n/a | Too early | TBC by Dec25
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
15% |  | GCIEP CN&E monitoring; DOC intervention ToRs and TO work package ToRs; GCIEP progress reports |  |  |  |  | MINOR
OUTPUT 6 | Output Indicator 6.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Learning (evidence) produced and in place for GCIEP to collate and disseminate UK and international urban / infrastructure expertise within GCIEP, FCDO, and to the wider ecosystem (REPORTED QUARTERLY) | No. of GCIEP products (analysis and learning including events) that deliver insights which inform/shape FCDO/wider development partner policies and programmes Dissaggregation by events and products | Planned - annual | n/a | Too early | n/a | 12 | *Sufficient GCIEP budget is allocated to undertake planned L&C activities approved in the ToR L&C *Setting a target for this indicator was deemed not applicable (in agreement with FCDO) during GCIEP’s first full year of delivery in Year 2 , due to the demand-driven nature of the programme. Instead, it was agreed we would report Actuals in the Y2 log frame. However, where there are continuing interventions in Y3 (second full year of GCIEP delivery) with many of the same stakeholders and sectors, we have included targets in the Year 3 log frame for this indicator.
|  | Achieved - annual | n/a | Too early | 7 (1 products & 6 events)
|  | Achieved - cumulative | n/a | Too early | 7 (1 products & 6 events)
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
10% |  | GCIEP RM and L&C monitoring, GCIEP K&L documentation (including links to public KPs and materials published) Note: a. A GCIEP Product is any written material produced by GCIEP and/or its delivery partners, through its DOC interventions/ TO work packages, that has been repackaged according to targeted audience/s and dissemination channel/s including learning events, that seek to contribute to the body of infra delivery and urban development knowledge towards improving FCDO and GCIEP delivery partners programming . This GCIEP product is out of the budget of the TO WP. |  |  |  |  | MINOR
º
Note on G22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Can we say a) what is the policy and b) what is the deliverable that informed or supported it?
Note on G40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Name the projects or the package of projects. Reply: Done

## INDONESIA nested LF
PROGRAMME NAME: | Green Cities, Infrastructure and Energy Programme (GCIEP) Y3 Logframe - DOC INDONESIA (22 January 2026)
OUTCOME 1 | Outcome Indicator 1.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Finance and Investment is leveraged for sustainable and inclusive infrastructure and the built environment in Indonesia. (DOC only and TO - if reported by Post) (REPORTED ANNUALLY) | Total volume of total non-GCIEP financing mobilised as a result of GCIEP interventions in Indonesia (£ ) Disaggregation by: type of funding organisation (Private/Donor/Public -National/Municipal), financing categories (catalysed, facilitated, unlocked, and reallocated) To track off logframe, GCIEP country programmes where non-FCDO funds have been leveraged downstream | Planned -annual | n/a | Too early | Too early | 0 | *GCIEP TA makes a contribution towards facilitating investment into urban economic infrastructure projects and overcoming obstacles to project delivery *Partner government continued support for: i) pro-poor, inclusive, low carbon and resilient objectives and targeted approaches; and ii) channel private and public investment into urban development and economic infrastructure *Target and Results will be based only on DOC interventions; but GCIEP will also report on results from TO work packages, in case there is GCIEP contribution and results have been tracked either by GCIEP or FCDO Post (post completion monitoring) * COMMITTED refers to: The financing quantified has already been committed/mobilised by other investors, where GCIEP TA is being used to make the investment “bigger, better or faster."
|  | Achieved - annual | n/a | Too early | 0
|  | Achieved - cumulative | n/a | Too early | 0
Source
GCIEP DOC and TO RM databases
| Outcome Indicator 1.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Volume of public finance mobilised for climate change purposes in Indonesia (£) (as a result of GCIEP interventions ) (disag by new financing vs reallocated financing) (ICF KPI 11) | Planned -annual | n/a | Too early | n/a | n/a: ICF KPI methodology only allows actuals to be reported
| ICF KPI 12 Volume of private finance mobilised for climate change purposes | Achieved - annual | n/a | Too early | 0
|  | Achieved - cumulative | n/a | Too early | 0
Source
GCIEP RM databases and ICF monitoring ICF KPI Methodology: https://assets.publishing.service.gov.uk/media/5b17935be5274a190c1b6f8c/KPI11-Public-finance-Updated-methodology.pdf
| Outcome Indicator 1.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Volume of private finance mobilised for climate change purposes in Indonesia (£) (as a result of GCIEP interventions) (ICF KPI 12) | Planned -annual | n/a | Too early | n/a | n/a: ICF KPI methodology only allows actuals to be reported
| ICF KPI 12 Volume of private finance mobilised for climate change purposes | Achieved - annual | n/a | Too early | 0
|  | Achieved - cumulative | n/a | Too early | 0
|  | Source |  |  |  |  | RISK RATING
|  | GCIEP RM databases and ICF monitoring ICF KPI Methodology: https://assets.publishing.service.gov.uk/media/65e0b9913f6945001d036030/KPI-12-volume-private-finace-mobilised.pdf |  |  |  |  | MODERATE
OUTCOME 2 | Outcome 2.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
GCIEP TA contributed to a stronger enabling environment in Indonesia for the provision of climate resilient&inclusive infrastructure services (REPORTED ANNUALLY) | APPROVAL: Number of approved policies/regulations/strategies/roadmaps/frameworks/institutional structures in Indonesia supported by GCIEP TA. (disag by Strategy & Planning, Legal & Regulatory Framework, Financing Mechanisms, Institutional capacity & governance, Networks & Partnerships) | Planned -annual | n/a | Too early | Too early | n/a | *Central FCDO and country offices are open to learning from and being influenced by GCIEP generated knowledge - when relevant * Collaboration with CoE DPs collaboration increase urban and infrastructure effectiveness leading to local adoption and replication * No material change in government priorities with any political changes in countries that undergo national elections * Deliverables can include policies, regulations, roadmaps, strategies, frameworks, institutional structure / governance report, etc. that have been submitted/reviewed/accepted/approved by the beneficiary stakeholder/s (depending on country context) * APPROVAL: Formal endorsement of GCIEP supported policy/regulations/strategies/roadmaps/frameworks/institutional structures at FCDO partner countries by the beneficiary stakeholder (or the appropriate designated authority) * ADOPTION: The formal embedding and / or implementation of a GCIEP-supported structure, process, methodology or practices by FCDO partner countries, maintaining the core design and function of the original model, through minor contextual adjustments may be made. A deliverable is counted either as APPROVED or ADOPTED but not both, except in the case where GCIEP provides continious to support over time resulting in an evolution from APPROVAL to ADOPTION. In such execptional cases policy/regulations/strategies/roadmaps/frameworks/institutional structures may be reported at both level, usually for different years.
|  | Achieved - annual |  | Too early | 0 | ID02 Surabaya - WS4 Support to Surabaya on Flood Risk Assessments 1-2. Flood management practices: Two flood Risk Assessments reports for Surabaya and Denpasar approved by Surabaya City Government (Bappedalitbong) and Denpasar City Government
|  | Achieved - cumulative |  | Too early | 0
Source
GCIEP L&C tracking tool, GCIEP K&L documentation Note: Deliverables must be approved by the beneficiary entity
| Outcome 2.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| ADOPTION: Number of GCIEP supported policies/regulations/strategies/roadmaps/frameworks/institutional structures adopted as evidence of GCIEP legacy / sustainability in GCIEP supported entities in Indonesia (sustainability) (disag by Strategy & Planning, Legal & Regulatory Framework, Financing Mechanisms, Institutional capacity & governance, Networks & Partnerships) | Planned -annual | n/a | Too early | Too early | ID.P2.01 Bappenas 1.Project Funding and Financing Options Framework version 2 adopted by Bappenas deputy of Development financing and investment
|  | Achieved - annual |  | Too early | 0 | ID01 Bappenas - WS1 Support to Bappenas on Prioritisation and Financing of Projects 1. Project Funding and Financing Options Framework version 1 adopted by Bappenas (Phase 2 intervention foundation) - achieved earlier than expected, moved from IO 3.1
|  | Achieved - cumulative |  | Too early | 0
|  | Source |  |  |  |  | RISK RATING
|  | GCIEP RM databases and Intervention Pathways Packages at the intervention level |  |  |  |  | MODERATE
Y3 Interim PLF (August 2025) the following indicators were considered obsolete in agreement with FCDO: * Outcome 2.2 Replication: Number of GCIEP supported structures, processes, and / or methodologies replicated (and adapted) by country governement ministries
INTERMEDIATE OUTCOME 1 | INT Outcome Indicator 1.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
GCIEP DOC is effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development (REPORTED ANNUALLY) | A) Increase in scope: Percentage of DOC interventions that have increase their scope since the start of the programme - CUMULATIVE (total number of DOC interventions scaled up / total number of DOC interventions) B) Closed / curtailed: Percentage of DOC interventions closed and / or curtailed since the start of the programme - CUMULATIVE (total number of DOC interventions closed or curtailed / total number of DOC interventions) C) New DOC interventions: Total number of DOC interventions introduced based on learning during GCIEP implementation phase | Planned -annual | n/a | n/a | n/a | n/a | *GCIEP can effectively target its assistance, to choose the right agencies/municipalities and/or institutions with which to partner and select and test the adequate interventions * GCIEP has in place the Impact Pathway packages to monitor DOC interventions applying adaptive programming principles *No material change in government priorities with any political changes in countries that undergo national elections * Well prepared projects (including feasibility studies) supported by GCIEP will attract the necessary downstream financing * In some cases, targets are not applicable, as we are a demand driven programme working under adaptive programming principles
|  | Achieved - annual | n/a | n/a | B) 1 OIKN | C) 3 ID.P2.01 Bappenas project planning ID.P2.02 East Java Transport ID.P2.03 Surabaya Drainage
|  | Achieved - cumulative | n/a | n/a | B) 1
Source
GCIEP RM databases and Intervention Pathways Packages at the intervention level Phase 1 interventions treated as scaled up for Phase 2
| INT Outcome Indicator 1.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) Disaggregated by stage of the infrastructure development cycle: (I) Project pipeline and (II) Project specific support including (a) Planning & preparation (concept note, business cases, (pre) feasibility studies); (b) Financing structuring (project development agreement, investment round tables etc); (c) Commercial and financial close; (d) Procurement; and (e) Implementation | Planned -annual | n/a | Too early | ID02 WS1a (Support to Surabaya on Visioning and Project Prioritisation) Prioritised pipeline of projects arising from the SUMP based joint analysis with stakeholders through capacity building workshops | I Project Specific Support: 1 ID.P2.02 East Java Transport (WS1) 1. Advancing Urban Rail Transport System (URTS): Project Development Plan completed and accepted by East Java Provincial Governement
|  | Achieved - annual |  | Too early | 1 ID02 WS1a (Support to Surabaya on Visioning and Project Prioritisation) Prioritised pipeline of projects arising from the SUMP based joint analysis with stakeholders through capacity building workshops
|  | Achieved - cumulative |  | Too early | 1
Source
GCIEP RM databases and Intervention Pathways Packages at the DOC intervention level Note: High quality equals to projects that have mainstreamed GEDSI and CN&E GCIEP DO C supported projects/initiatives along the infrastructure development cycle: (a) Planning & preparation (project pipelines, concept note, business cases, (pre) feasibility studies); (b) Financing structuring (project development agreement, investment round tables etc); (c) Commercial and financial close; (d) Procurement; and (e) Implementation
INTERMEDIATE OUTCOME 3 | INT Outcome Indicator 3.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Influencing and collaboration Uptake of relevant knowledge and evidence generated by GCIEP and/or its delivery partners by the GoV as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services (REPORTED ANNUALLY) | INFORMING DECISION MAKING: Number of policies/regulations/strategies/roadmaps/frameworks/institutional structures in Indonesia that have been informed with contributions from GCIEP TA. (disag by Strategy & Planning, Legal & Regulatory Framework, Financing Mechanisms, Institutional capacity & governance, Networks & Partnerships) | Planned -annual |  |  |  | ID.P1.01 Bappenas - WS1 Support to Bappenas on Prioritisation and Financing of Projects 1. PSN Criteria and dashboard for determining National Strategic Projects (PSNs) reviewed/accepted 2. Project Funding and Financing Options Framework version 1 reviewed/accepted ID.P1.01 Bappenas - WS2 Support to Bappenas on Appraising Projects arising from SUMPs 3. Standarised SUMP appraisal framework with accompanying Governance and Operations Manual accepted by Bappenas following pilot application with Surabaya provincial level governement & relevant capacity building (Phase 1) ID.P1.02 Surabaya - WS1a Support to Surabaya on TOD Roadmap 4. Selected transit line in Gerbangkartosusilo (GKS+): High -level TOD Roadmap reviewed/accepted by Bappeda East Java Province IN02 Surabaya - WS3 Support to Surabaya on Integration Transport Authority 5. National Level Legislative Recommendations Report reviewed/accepted by East Java Economic Bureau 6. Integrated transport authority (ITA) in Gerbangkartasusilo (GKS+): Institutional Roadmap reviewed/accepted by East Java Economic Bureau ID.P1.02 Surabaya - WS4 Support to Surabaya on Flood Risk Assessments 7-8. Flood management practices: Two Flood Risk Assessment report for Surabaya and Denpasar reviewed/accepted by Surabaya City Government (Bappedalitbong) and Denpasar City Government ID.P2. 01 Bappenas 9. Bappenas financing practices: Innovative Financing Study reviewed/accepted by Bappenas ID.P2.02 East Java Transport 10. Integrated transport authority (ITA) in GKS+: Input to ITA Business Model Feasibility Study reviewed/accepted by East Java Provincial Government 11. Integrated transport authority (ITA) in GKS+: Draft inventory of issues reviewed/accepted by East Java Provincial Governement 12. Integrated transport authority (ITA) in GKS+: Legal Academic Script reviewed/accepted by East Java Provincial Governement ID.P2.03 Surabaya Drainage 13. Surabaya Sustainable Drainage Master Plan updates for Benowo and Wiyung reviewed/accepted by city government | * Central FCDO and country offices are open to learning from and being influenced by GCIEP generated knowledge - when relevant . * Deliverables can include policies, regulations, roadmaps, strategies, frameworks, institutional structure / governance report, etc. that have been submitted/reviewed/accepted/approved by the beneficiary stakeholder/s (depending on country context). *Targets and results include deliverables that are REVIEWED/ ACCEPTED by the beneficiary stakeholder that are used as as source of evidence, insights, or recommendations to inform policies, strategies, or actions in FCDO partner countries.
|  | Achieved - annual |  |  |  | ID.P1.01 (Support to Bappenas on Prioritisation and Financing of Projects) 1. PSN Criteria and dashboard for determining National Strategic Projects (PSNs) accepted ID.P1.01 (Support to Bappenas on Appraising Projects arising from SUMPs) 2. Standarised SUMP appraisal framework with accompanying Governance and Operations Manual accepted by Bappenas following pilot application with Surabaya provincial level governement & relevant capacity building IN.01.02 (Support to Surabaya on TOD Roadmap) 3. Selected transit line in Gerbangkartosusilo (GKS+): High -level TOD Roadmap reviewed/accepted by Bappeda East Java Province IN.P1.02 (Support to Surabaya on Integration Transport Authority) 4. National Level Legislative Recommendations Report accepted by East Java Economic Bureau 5. Integrated transport authority in GKS+: Institutional Roadmap accepted by East Java Economic Bureau See below targets reported at Outcome 2 level as they have receive formal approval- earlier than expected: ID.P1.01 Bappenas - WS1 Support to Bappenas on Prioritisation and Financing of Projects: Project Funding and Financing Options Framework version 1 reviewed/accepted ID.P1.01 (Support to Bappenas on Prioritisation and Financing of Projects): Project Funding and Financing Options Framework version 1 adopted by Bappenas (Phase 2 intervention foundation) ID.P1.02 (Support to Surabaya on Flood Risk Assessments): Two flood Risk Assessment report for Surabaya and Denpasar approved by respective city governements
Achieved - cumulative
|  | Source |  |  |  |  | RISK RATING
|  | GCIEP monitoring and operational databases |  |  |  |  | MODERATE
INTERMEDIATE OUTCOME 4 | INT Outcome Indicator 4.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
DOC interventions have successfully integrated GEDSI risks and opportunties resulting in Empowerment (REPORTED ANNUALLY) | % of DOC intervention that include GEDSI considerations in accordance with Level 2 - Empowerment - as per the FCDO GEDSI framework (realised target ambition) - Linked to Output 4 | Planned -annual |  |  |  | 50% | *Resources at DOC and TO level are deployed to ensure that GEDSI is effectively mainstreamed during implementation, regularly identifying and assessing GEDSI risks and opportunities
Achieved - annual
|  | Source |  |  |  |  | RISK RATING
|  | GCIEP GEDSI monitoring; GCIEP deliverables TOR and GCIEP work package progress reports Note: it only applies to interventions that have GEDSI potential |  |  |  |  | MODERATE
OUTPUT 1 | Output Indicator 1.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
High-quality TA deliverables completed by GCIEP for FCDO posts to facilitate economic transformation and inclusive growth (in line with VfM targets) (REPORTED QUARTERLY) | DOC Percentage of the activities planned at the start of each quarter that are completed. | Planned -annual | n/a | n/a | 70% | 70%
|  | Achieved - annual | n/a | n/a | 95.8%
Source
GCIEP DOC intervention workplans Note: Total number of activities completed during the quarter / total number of activities planned to be completed as per workplan submitted to FCDO at the start of the quarter. It is expected that the activities detailed (and related deliverables) in the intervention workplan will be updated on a quarterly basis in line with adaptive management best practice.
WEIGHTING: | [6 empty] | RISK RATING
MINOR
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Proactive strategic collaboration to maximise effectiveness in GCIEP delivery in TO and/or DOC countries (REPORTED QUARTERLY) | No. of instances where GCIEP team has worked and/or coordinated* with partners** A) GCIEP DOC interventions B) GCI CoE delivery partners C) Any other UK expert organisations D) Development partners (instances that DOC and Buy-ins have collaborated with development partners) | Planned -annual | n/a | n/a | n/a | B) 4 (TfL, CI, BGS, BSI) C) 4 (FCIP - ID.P2.01 Innovative Finance, ID.P2.03 Surabaya Drainage); (BII - ID.P2.01 Innovative Finance); (UKEF - ID.P2.01 Innovative Finance, ID.P2.02.WS1 Urban Rail Transport System). D) 1 (KfW - ID.P2.02.WS1 Urban Rail Transport System) | *GCIEP can effectively target its assistance, to choose the right agencies/municipalities and/or institutions with which to partner and select the right interventions * Targets (n/a): Targets are not applicable, as we are a demand driven programme working under adaptive programming principles
|  | Achieved - annual | n/a | n/a | B) 4 (TfLx3 and CI) C) 2 (ICE/EBI, Oxford Global Projects) D) 5 (ADB, JICA, KfW, Milenium Challenge Account Indonesia, World Bank)
|  | Achieved - cumulative | n/a | n/a | B) 4 C) 2 D) 5
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
10% |  | GCIEP monitoring and operational databases Notes: *Co-ordination defined as having an active Community of Practice/signed MoU/other formal engagement process in place) ** Partners defined as any in-country international development agency or donor based in a DOC country ***GCIEP CoE delivery partners: Cross Rail Intl, Ofgem, Infrastructure and Projects Authority, Transport for London, BSI; CATAPULT, Ordinance Survey and British Geological Survey |  |  |  |  | MINOR
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Enhancing capacity and knowledge to strengthen GCIEP supported institutions and agencies in partner countries (disag by DOC and TO) (REPORTED QUARTERLY) | Percentage and number of people certified in UK tools and methodologies (Only applicable if there is formal UK certification offer. UK tools and methodologies with certification exam include, for example, 5CM) | Planned -annual | n/a | Too early | n/a | 0 | * GCIEP has the capacity to deliver targeted and high quality trainings, adapted to the needs to targeted stakeholders *GCIEP can leverage on UK expertise to successfully deliver TA *Setting a target for this indicator was deemed not applicable (in agreement with FCDO) during GCIEP’s first full year of delivery in Year 2 , due to the demand-driven nature of the programme. Instead, it was agreed we would report Actuals in the Y2 log frame. However, where there are continuing interventions in Y3 (second full year of GCIEP delivery) with many of the same stakeholders and sectors, we have included targets in the Year 3 log frame for this indicator.
|  | Achieved - annual | n/a | Too early | 0
|  | Achieved - cumulative | n/a | Too early | 0
Source
GCIEP RM and operational databases Note: Number of people certified / total number of people trained in UK tools and methodologies taking the exam.
| Output Indicator 3.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number (#) of people trained via GCIEP supported work packages/interventions Disaggregation: portfolio (DOC, TO, Buy-in), women professionals, people with disabilities, and youth, indicate if UK methodology. | Planned -annual | n/a | n/a | n/a | 80
|  | Achieved - annual | n/a | n/a | 272 Total (95 women. 6 PwD)
|  | Achieved - cumulative | n/a | n/a | 272 Total (95 women. 6 PwD)
Source
GCIEP RM and operational databases
| Output Indicator 3.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| % of participants indicating that the training/capacity building in Output 3.1 or 3.2 was "useful" or "very useful" on a 5 point scale | Planned -annual | n/a | n/a | 70% | 85%
|  | Achieved - annual | n/a | n/a | 98.6% (137 of 139)
|  | Achieved - cumulative | n/a | n/a | 98.6% (137 of 139)
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
10% |  | GCIEP RM and operational databases |  |  |  |  | MINOR
OUTPUT 4 | Output Indicator 4.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
GEDSI is mainstreamed across GCIEP DOC interventions and Target Offer (TO) work packages (WPs) (disag by DOC and TO) (REPORTED ANNUALLY) | % of GCIEP supported DOC interventions/TO WPs that have an ambition of level 2 - Empowerment as per the FCDO GEDSI framework Disaggregated by FCDO GEDSI framework levels 1-3 | Planned - annual | n/a | n/a | L2: 50% | 50% | *The FCDO GEDSI Framework is effective into translating FCDO’s GEDSI policies into programming; enabling GCIEP to take a structured and practical approach to exploring how GCIEP interventions can maximise benefits to disadvantaged and vulnerable groups
|  | Achieved - annual | n/a | n/a | 66%
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
15% |  | GCIEP GEDSI monitoring; GCIEP deliverables TOR and GCIEP work package progress reports Note: it only applies to interventions that have GEDSI potential |  |  |  |  | MINOR
OUTPUT 5 | Output Indicator 5.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
CN&E is mainstreamed across GCIEP DOC interventions and Target Offer (TO) work packages (WPs) (ICF compliance) (disag by DOC and TO) (REPORTED ANNUALLY) | % of GCIEP supported DOC interventions/TO work packages that are mainstreaming CN&E | Planned - annual | n/a | n/a | 100% | 100% | *ICF compliant: An interventions that contributes to at least 1 ICF KPI indicator *ICF KPI TA methodology only allows actuals to be reported
|  | Achieved - annual | n/a | n/a | 100%
Source
GCIEP ICF monitoring; DOC intervention ToRs and TO Work Package ToRs; GCIEP progress reports
| Output Indicator 5.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| % of total spend that is ICF compliant in relation to the total £ value of GCIEP programmes - of eligible ODA | Planned - annual | n/a | n/a | 100% | 100%
|  | Achieved - annual | n/a | n/a | 100%
Source
GCIEP ICF monitoring; DOC intervention ToRs and TO Work Package ToRs; GCIEP progress reports
| Output Indicator 5.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of countries supported by ICF technical assistance ICF TA KPI 1 (reported only on completed DOC interventions/TO WPs) | Planned - annual | n/a | n/a | n/a | n/a
|  | Achieved - annual | n/a | n/a | TBC by Dec25
|  | Achieved - cumulative | n/a | n/a | TBC by Dec25
Source
GCIEP CN&E monitoring; DOC intervention ToRs and TO work package ToRs; GCIEP progress reports
| Output Indicator 5.4 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of individuals supported by ICF technical assistance ICF TA KPI 2.1 (reported only on completed DOC interventions/TO WPs) | Planned - annual | n/a | n/a | n/a | n/a
|  | Achieved - annual | n/a | n/a | TBC by Dec25
|  | Achieved - cumulative | n/a | n/a | TBC by Dec25
Source
GCIEP CN&E monitoring; DOC intervention ToRs and TO work package ToRs; GCIEP progress reports
| Output Indicator 5.5 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of organisations supported by ICF technical assistance ICF TA KPI 2.2 (reported only on completed DOC interventions/TO WPs) | Planned - annual | n/a | n/a | n/a | n/a
|  | Achieved - annual | n/a | n/a | TBC by Dec25
|  | Achieved - cumulative | n/a | n/a | TBC by Dec25
Source
GCIEP CN&E monitoring; DOC intervention ToRs and TO work package ToRs; GCIEP progress reports
| Output Indicator 5.6 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of climate policies informed by ICF technical assistance ICF TA KPI 3 (reported only on completed DOC interventions/TO WPs) | Planned - annual | n/a | n/a | n/a | n/a
|  | Achieved - annual | n/a | n/a | TBC by Dec25
|  | Achieved - cumulative | n/a | n/a | TBC by Dec25
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
15% |  | GCIEP CN&E monitoring; DOC intervention ToRs and TO work package ToRs; GCIEP progress reports |  |  |  |  | MINOR
OUTPUT 6 | Output Indicator 6.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Learning (evidence) produced and in place for GCIEP to collate and disseminate UK and international urban / infrastructure expertise within GCIEP, FCDO, and to the wider ecosystem (REPORTED QUARTERLY) | No. of GCIEP products (analysis and learning including events) that deliver insights which inform/shape FCDO/wider development partner policies and programmes Dissaggregation by events and products | Planned - annual | n/a | Too early | n/a | 20 | *Sufficient GCIEP budget is allocated to undertake planned L&C activities approved in the ToR L&C *Setting a target for this indicator was deemed not applicable (in agreement with FCDO) during GCIEP’s first full year of delivery in Year 2 , due to the demand-driven nature of the programme. Instead, it was agreed we would report Actuals in the Y2 log frame. However, where there are continuing interventions in Y3 (second full year of GCIEP delivery) with many of the same stakeholders and sectors, we have included targets in the Year 3 log frame for this indicator.
|  | Achieved - annual | n/a | Too early | 11 (6 products & 5 events) | 17 (13 products & 4 events)
|  | Achieved - cumulative | n/a | Too early | 11 (6 products & 5 events)
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
10% |  | GCIEP RM and L&C monitoring, GCIEP K&L documentation (including links to public KPs and materials published) Note: a. A GCIEP Product is any written material produced by GCIEP and/or its delivery partners, through its DOC interventions/ TO work packages, that has been repackaged according to targeted audience/s and dissemination channel/s including learning events, that seek to contribute to the body of infra delivery and urban development knowledge towards improving FCDO and GCIEP delivery partners programming . This GCIEP product is out of the budget of the TO WP. |  |  |  |  | MINOR
º
Note on G22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Does this fit the indicator? A flood risk assessment is not a policy, strategy, etc.
Note on G27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The disagregation is missing. Is this Financial mechanisms? Reply: This will be included in the overall GCIEP Y3 LF and it will detailed in the target list

## PHILIPPINES nested LF
PROGRAMME NAME: | Green Cities, Infrastructure and Energy Programme (GCIEP)Y3 Logframe - DOC PHILIPPINES (pending TOD intervention results delivered by WS1 and WS2_to be received by FCDO at the end of Year 3)
OUTCOME 1 | Outcome Indicator 1.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Finance and Investment is leveraged for sustainable and inclusive infrastructure and the built environment in Philippines (DOC only and TO - if reported by Post) (REPORTED ANNUALLY) | Total volume of total non-GCIEP financing mobilised as a result of GCIEP interventions in Philippines (£ ) Disaggregation by: type of funding organisation (Private/Donor/Public -National/Municipal), financing categories (catalysed, facilitated, unlocked, and reallocated) To track off logframe, GCIEP country programmes where non-FCDO funds have been leveraged downstream | Planned -annual | n/a | Too early | Too early | 0 | *GCIEP TA makes a contribution towards facilitating investment into urban economic infrastructure projects and overcoming obstacles to project delivery *Partner government continued support for: i) pro-poor, inclusive, low carbon and resilient objectives and targeted approaches; and ii) channel private and public investment into urban development and economic infrastructure *Target and Results will be based only on DOC interventions; but GCIEP will also report on results from TO work packages, in case there is GCIEP contribution and results have been tracked either by GCIEP or FCDO Post (post completion monitoring) * COMMITTED refers to: The financing quantified has already been committed/mobilised by other investors, where GCIEP TA is being used to make the investment “bigger, better or faster.
|  | Achieved - annual | n/a | Too early | 0
|  | Achieved - cumulative | n/a | Too early | 0
Source
GCIEP DOC and TO RM databases
| Outcome Indicator 1.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Volume of public finance mobilised for climate change purposes in Philippines (£) (as a result of GCIEP interventions ) (disag by new financing vs reallocated financing) (ICF KPI 11) | Planned -annual | n/a | Too early | n/a | n/a: ICF KPI methodology only allows actuals to be reported
| ICF KPI 12 Volume of private finance mobilised for climate change purposes | Achieved - annual | n/a | Too early | 0
|  | Achieved - cumulative | n/a | Too early | 0
Source
GCIEP RM databases and ICF monitoring ICF KPI Methodology: https://assets.publishing.service.gov.uk/media/5b17935be5274a190c1b6f8c/KPI11-Public-finance-Updated-methodology.pdf
| Outcome Indicator 1.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Volume of private finance mobilised for climate change purposes in Philippines (£) (as a result of GCIEP interventions) (ICF KPI 12) | Planned -annual | n/a | Too early | n/a | n/a: ICF KPI methodology only allows actuals to be reported
| ICF KPI 12 Volume of private finance mobilised for climate change purposes | Achieved - annual | n/a | Too early | 0
|  | Achieved - cumulative | n/a | Too early | 0
|  | Source |  |  |  |  | RISK RATING
|  | GCIEP RM databases and ICF monitoring ICF KPI Methodology: https://assets.publishing.service.gov.uk/media/65e0b9913f6945001d036030/KPI-12-volume-private-finace-mobilised.pdf |  |  |  |  | MODERATE
OUTCOME 2 | Outcome 2.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
GCIEP TA contributed to a stronger enabling environment in Philippines for the provision of climate resilient&inclusive infrastructure services (REPORTED ANNUALLY) | APPROVAL: Number of approved policies/regulations/strategies/roadmaps/frameworks/institutional structures in Philippines supported by GCIEP TA. (disag by Strategy & Planning, Legal & Regulatory Framework, Financing Mechanisms, Institutional capacity & governance, Networks & Partnerships) | Planned -annual | n/a | Too early | Too early | 0 | *Central FCDO and country offices are open to learning from and being influenced by GCIEP generated knowledge - when relevant * Collaboration with CoE DPs collaboration increase urban and infrastructure effectiveness leading to local adoption and replication * No material change in government priorities with any political changes in countries that undergo national elections * Deliverables can include policies, regulations, roadmaps, strategies, frameworks, institutional structure / governance report, etc. that have been submitted/reviewed/accepted/approved by the beneficiary stakeholder/s (depending on country context) * APPROVAL: Formal endorsement of GCIEP supported policy/regulations/strategies/roadmaps/frameworks/institutional structures at FCDO partner countries by the beneficiary stakeholder (or the appropriate designated authority) * ADOPTION: The formal embedding and / or implementation of a GCIEP-supported structure, process, methodology or practices by FCDO partner countries, maintaining the core design and function of the original model, through minor contextual adjustments may be made. A deliverable is counted either as APPROVED or ADOPTED but not both, except in the case where GCIEP provides continious to support over time resulting in an evolution from APPROVAL to ADOPTION. In such execptional cases policy/regulations/strategies/roadmaps/frameworks/institutional structures may be reported at both level, usually for different years.
|  | Achieved - annual |  | Too early | 0
|  | Achieved - cumulative |  | Too early | 0
Source
GCIEP L&C tracking tool, GCIEP K&L documentation Note: Deliverables must be approved by the beneficiary entity
| Outcome 2.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| ADOPTION: Number of GCIEP supported policies/regulations/strategies/roadmaps/frameworks/institutional structures adopted as evidence of GCIEP legacy / sustainability in GCIEP supported entities in Philippines (sustainability) (disag by Strategy & Planning, Legal & Regulatory Framework, Financing Mechanisms, Institutional capacity & governance, Networks & Partnerships) | Planned -annual | n/a | Too early | Too early | 0
|  | Achieved - annual |  | Too early | 0
|  | Achieved - cumulative |  | Too early | 0
|  | Source |  |  |  |  | RISK RATING
|  | GCIEP RM databases and Intervention Pathways Packages at the intervention level |  |  |  |  | MODERATE
Y3 Interim PLF (August 2025) the following indicators were considered obsolete in agreement with FCDO: * Outcome 2.2 Replication: Number of GCIEP supported structures, processes, and / or methodologies replicated (and adapted) by country governement ministries
INTERMEDIATE OUTCOME 1 | INT Outcome Indicator 1.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
GCIEP DOC is effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development (REPORTED ANNUALLY) | A) Increase in scope: Percentage of DOC interventions that have increase their scope since the start of the programme - CUMULATIVE (total number of DOC interventions scaled up / total number of DOC interventions) B) Closed / curtailed: Percentage of DOC interventions closed and / or curtailed since the start of the programme - CUMULATIVE (total number of DOC interventions closed or curtailed / total number of DOC interventions) C) New DOC interventions: Total number of DOC interventions introduced based on learning during GCIEP implementation phase | Planned -annual | n/a | n/a | n/a | n/a | *GCIEP can effectively target its assistance, to choose the right agencies/municipalities and/or institutions with which to partner and select and test the adequate interventions * GCIEP has in place the Impact Pathway packages to monitor DOC interventions applying adaptive programming principles *No material change in government priorities with any political changes in countries that undergo national elections * Well prepared projects (including feasibility studies) supported by GCIEP will attract the necessary downstream financing * In some cases, targets are not applicable, as we are a demand driven programme working under adaptive programming principles
|  | Achieved - annual | n/a | n/a | 0 | C) 2 PH.P2.01 Water PH.P2.02 TOD
|  | Achieved - cumulative | n/a | n/a | 0
Source
GCIEP RM databases and Intervention Pathways Packages at the intervention level Phase 1 interventions treated as scaled up for Phase 2
| INT Outcome Indicator 1.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) Disaggregated by stage of the infrastructure development cycle: (I) Project pipeline and (II) Project specific support including (a) Planning & preparation (concept note, business cases, (pre) feasibility studies); (b) Financing structuring (project development agreement, investment round tables etc); (c) Commercial and financial close; (d) Procurement; and (e) Implementation | Planned -annual | n/a | Too early | Too early | II. Project Specific support: 2 PH.P1.01 - Water 1. Baguio Water Bulk supply Project: Feasibility Study accepted (as per MoU, accepted = written approval from the Baguio City Council as well as approval from the Water board of directors) PH.P2.01 - Water 2. Baguio Water Bulk supply PPP support: Options for Project Structuring and Financial Models accepted by Baguio City PH02 TOD WS2 (CI led) i) Feasibility Study (FS) - a viable/deliverable scheme developed to balance key stakeholder requirements and comply with NEDA Board ICC Guidelines ii) Approval of the FS scheme by landowner Department of Education (DepEd) and key stakeholder Department of Transportation (DOTr)
|  | Achieved - annual |  | Too early | 0
|  | Achieved - cumulative |  | Too early | 0
Source
GCIEP RM databases and Intervention Pathways Packages at the DOC intervention level Note: High quality equals to projects that have mainstreamed GEDSI and CN&E GCIEP DO C supported projects/initiatives along the infrastructure development cycle: (a) Planning & preparation (project pipelines, concept note, business cases, (pre) feasibility studies); (b) Financing structuring (project development agreement, investment round tables etc); (c) Commercial and financial close; (d) Procurement; and (e) Implementation
INTERMEDIATE OUTCOME 3 | INT Outcome Indicator 3.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
º | INFORMING DECISION MAKING: Number of policies/regulations/strategies/roadmaps/frameworks/institutional structures in Philippines that have been informed with contributions from GCIEP TA. (disag by Strategy & Planning, Legal & Regulatory Framework, Financing Mechanisms, Institutional capacity & governance, Networks & Partnerships) | Planned -annual |  |  |  | PH.P1.01 Water 1. Viability assessment emerging from piloting Regulatory Asset Based (RAB) water tariffs and lifeline pricing in three selected water districts is reviewed/accepted by relevant Local water districts, LWUA, and Department of Environment and Natural Resources (DENR) PH.P2.01 Water 2. Four Water Districts with the RAB and Missionary Water Tariff (MWT) frameworks successfully piloted. 3. RAB and MWT water tariffs: Roadmap (policy note with overview of high potential national adoption roadmap) reviewed/accepted by DENR PH02 TOD﻿ WS1 3. Proof of Concept TOD Implementation framework accepted by Philippines DOTr PH02 TOD WS2 4. Senate DepEd site pilot study - TOD masterplan accepted by Philippines DOTr and DepEd | * Central FCDO and country offices are open to learning from and being influenced by GCIEP generated knowledge - when relevant . * Deliverables can include policies, regulations, roadmaps, strategies, frameworks, institutional structure / governance report, etc. that have been submitted/reviewed/accepted/approved by the beneficiary stakeholder/s (depending on country context). *Targets and results include deliverables that are REVIEWED/ ACCEPTED by the beneficiary stakeholder that are used as as source of evidence, insights, or recommendations to inform policies, strategies, or actions in FCDO partner countries.
|  | Achieved - annual |  |  |  | PH01 Water 1. Viability assessment emerging from piloting Regulatory Asset Based (RAB) water tariffs and lifeline pricing in three selected water districts is accepted by relevant Local water districts, LWUA, and Department of Environment and Natural Resources (DENR)
Achieved - cumulative
|  | Source |  |  |  |  | RISK RATING
|  | GCIEP monitoring and operational databases |  |  |  |  | MODERATE
INTERMEDIATE OUTCOME 4 | INT Outcome Indicator 4.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
DOC interventions have successfully integrated GEDSI risks and opportunties resulting in Empowerment (REPORTED ANNUALLY) | % of DOC intervention that include GEDSI considerations in accordance with Level 2 - Empowerment - as per the FCDO GEDSI framework (realised target ambition) - Linked to Output 4 | Planned -annual |  |  |  | 50% | *Resources at DOC and TO level are deployed to ensure that GEDSI is effectively mainstreamed during implementation, regularly identifying and assessing GEDSI risks and opportunities
Achieved - annual
|  | Source |  |  |  |  | RISK RATING
|  | GCIEP GEDSI monitoring; GCIEP deliverables TOR and GCIEP work package progress reports Note: it only applies to interventions that have GEDSI potential |  |  |  |  | MODERATE
OUTPUT 1 | Output Indicator 1.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
High-quality TA deliverables completed by GCIEP for FCDO posts to facilitate economic transformation and inclusive growth (in line with VfM targets) (REPORTED QUARTERLY) | DOC Percentage of the activities planned at the start of each quarter that are completed. | Planned -annual | n/a | n/a | PH01 Water: 70% PH02 TOD WS1: 70% PH02 TOD WS2: 70% | 70%
|  | Achieved - annual | n/a | n/a | PH01 Water: 88.7% PH02 TOD WS1: 100% PH02 TOD WS2: 70%
Source
GCIEP DOC intervention workplans Note: Total number of activities completed during the quarter / total number of activities planned to be completed as per workplan submitted to FCDO at the start of the quarter. It is expected that the activities detailed (and related deliverables) in the intervention workplan will be updated on a quarterly basis in line with adaptive management best practice.
WEIGHTING: | [6 empty] | RISK RATING
MINOR
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Proactive strategic collaboration to maximise effectiveness in GCIEP delivery in TO and/or DOC countries (REPORTED QUARTERLY) | No. of instances where GCIEP team has worked and/or coordinated* with partners** A) GCIEP DOC interventions B) GCI CoE delivery partners C) Any other UK expert organisations D) Development partners (instances that DOC and Buy-ins have collaborated with development partners) | Planned -annual | n/a | n/a | n/a | B) 3 (BGS (underground water study); CI & TfL Phase 2 ToD intervention) C) 1 (CoST) | *GCIEP can effectively target its assistance, to choose the right agencies/municipalities and/or institutions with which to partner and select the right interventions
|  | Achieved - annual | n/a | n/a | B) 2 (TfL and CI) D) 1 (ADB)
|  | Achieved - cumulative | n/a | n/a | B) 2 D) 1
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
10% |  | GCIEP monitoring and operational databases Notes: *Co-ordination defined as having an active Community of Practice/signed MoU/other formal engagement process in place) ** Partners defined as any in-country international development agency or donor based in a DOC country ***GCIEP CoE delivery partners: Cross Rail Intl, Ofgem, Infrastructure and Projects Authority, Transport for London, BSI; CATAPULT, Ordinance Survey and British Geological Survey |  |  |  |  | MINOR
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Enhancing capacity and knowledge to strengthen GCIEP supported institutions and agencies in partner countries (disag by DOC and TO) (REPORTED QUARTERLY) | Percentage and number of people certified in UK tools and methodologies (Only applicable if there is formal UK certification offer. UK tools and methodologies with certification exam include, for example, 5CM) | Planned -annual | n/a | Too early | n/a | 0 | * GCIEP has the capacity to deliver targeted and high quality trainings, adapted to the needs to targeted stakeholders *GCIEP can leverage on UK expertise to successfully deliver TA *Setting a target for this indicator was deemed not applicable (in agreement with FCDO) during GCIEP’s first full year of delivery in Year 2 , due to the demand-driven nature of the programme. Instead, it was agreed we would report Actuals in the Y2 log frame. However, where there are continuing interventions in Y3 (second full year of GCIEP delivery) with many of the same stakeholders and sectors, we have included targets in the Year 3 log frame for this indicator.
|  | Achieved - annual | n/a | Too early | 0
|  | Achieved - cumulative | n/a | Too early | 0
Source
GCIEP RM and operational databases Note: Number of people certified / total number of people trained in UK tools and methodologies taking the exam.
| Output Indicator 3.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number (#) of people trained via GCIEP supported work packages/interventions Disaggregation: portfolio (DOC, TO, Buy-in), women professionals, people with disabilities, and youth, indicate if UK methodology. | Planned -annual | n/a | n/a | n/a | 70
|  | Achieved - annual | n/a | n/a | 0
|  | Achieved - cumulative | n/a | n/a | 0
Source
GCIEP RM and operational databases
| Output Indicator 3.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| % of participants indicating that the training/capacity building in Output 3.1 or 3.2 was "useful" or "very useful" on a 5 point scale | Planned -annual | n/a | n/a | 70% | 85%
|  | Achieved - annual | n/a | n/a | 0
|  | Achieved - cumulative | n/a | n/a | 0
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
10% |  | GCIEP RM and operational databases |  |  |  |  | MINOR
OUTPUT 4 | Output Indicator 4.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
GEDSI is mainstreamed across GCIEP DOC interventions and Target Offer (TO) work packages (WPs) (disag by DOC and TO) (REPORTED ANNUALLY) | % of GCIEP supported DOC interventions/TO WPs that have an ambition of level 2 - Empowerment as per the FCDO GEDSI framework Disaggregated by FCDO GEDSI framework levels 1-3 | Planned - annual | n/a | n/a | PH01 Water: L2 - 50% PH02 TOD WS1: 100% PH02 TOD WS2: 100% | PH01 Water: L2 - 50% PH02 TOD WS1: 100% PH02 TOD WS2: 100% | *The FCDO GEDSI Framework is effective into translating FCDO’s GEDSI policies into programming; enabling GCIEP to take a structured and practical approach to exploring how GCIEP interventions can maximise benefits to disadvantaged and vulnerable groups
|  | Achieved - annual | n/a | n/a | PH01 Water: L2 - 75% PH02 TOD WS1: 100% PH02 TOD WS2: 100%
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
15% |  | GCIEP GEDSI monitoring; GCIEP deliverables TOR and GCIEP work package progress reports Note: it only applies to interventions that have GEDSI potential |  |  |  |  | MINOR
OUTPUT 5 | Output Indicator 5.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
CN&E is mainstreamed across GCIEP DOC interventions and Target Offer (TO) work packages (WPs) (ICF compliance) (disag by DOC and TO) (REPORTED ANNUALLY) | % of GCIEP supported DOC interventions/TO work packages that are mainstreaming CN&E | Planned - annual | n/a | n/a | PH01 Water: 100% PH02 TOD WS1: 100% PH02 TOD WS2: 100% | PH01 Water: 100% PH02 TOD WS1: 100% PH02 TOD WS2: 100% | *ICF compliant: An interventions that contributes to at least 1 ICF KPI indicator *ICF KPI TA methodology only allows actuals to be reported
|  | Achieved - annual | n/a | n/a | PH01 Water: 100% PH02 TOD WS1: 100% PH02 TOD WS2: 100%
Source
GCIEP ICF monitoring; DOC intervention ToRs and TO Work Package ToRs; GCIEP progress reports
| Output Indicator 5.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| % of total spend that is ICF compliant in relation to the total £ value of GCIEP programmes - of eligible ODA | Planned - annual | n/a | n/a | PH01 Water: 100% PH02 TOD WS1: 80% PH02 TOD WS2: 80% | PH01 Water: 100% PH02 TOD WS1: 80% PH02 TOD WS2: 80%
|  | Achieved - annual | n/a | n/a | PH01 Water: 100% PH02 TOD WS1: 100% PH02 TOD WS2: 80%
Source
GCIEP ICF monitoring; DOC intervention ToRs and TO Work Package ToRs; GCIEP progress reports
| Output Indicator 5.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of countries supported by ICF technical assistance ICF TA KPI 1 (reported only on completed DOC interventions/TO WPs) | Planned - annual | n/a | n/a | n/a | n/a
|  | Achieved - annual | n/a | n/a | TBC by Dec25
|  | Achieved - cumulative | n/a | n/a | TBC by Dec25
Source
GCIEP CN&E monitoring; DOC intervention ToRs and TO work package ToRs; GCIEP progress reports
| Output Indicator 5.4 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of individuals supported by ICF technical assistance ICF TA KPI 2.1 (reported only on completed DOC interventions/TO WPs) | Planned - annual | n/a | n/a | n/a | n/a
|  | Achieved - annual | n/a | n/a | TBC by Dec25
|  | Achieved - cumulative | n/a | n/a | TBC by Dec25
Source
GCIEP CN&E monitoring; DOC intervention ToRs and TO work package ToRs; GCIEP progress reports
| Output Indicator 5.5 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of organisations supported by ICF technical assistance ICF TA KPI 2.2 (reported only on completed DOC interventions/TO WPs) | Planned - annual | n/a | n/a | n/a | n/a
|  | Achieved - annual | n/a | n/a | TBC by Dec25
|  | Achieved - cumulative | n/a | n/a | TBC by Dec25
Source
GCIEP CN&E monitoring; DOC intervention ToRs and TO work package ToRs; GCIEP progress reports
| Output Indicator 5.6 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of climate policies informed by ICF technical assistance ICF TA KPI 3 (reported only on completed DOC interventions/TO WPs) | Planned - annual | n/a | n/a | n/a | n/a
|  | Achieved - annual | n/a | n/a | n/a
|  | Achieved - cumulative | n/a | n/a | n/a
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
15% |  | GCIEP CN&E monitoring; DOC intervention ToRs and TO work package ToRs; GCIEP progress reports |  |  |  |  | MINOR
OUTPUT 6 | Output Indicator 6.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Learning (evidence) produced and in place for GCIEP to collate and disseminate UK and international urban / infrastructure expertise within GCIEP, FCDO, and to the wider ecosystem (REPORTED QUARTERLY) | No. of GCIEP products (analysis and learning including events) that deliver insights which inform/shape FCDO/wider development partner policies and programmes Disaggregation by events and products | Planned - annual | n/a | Too early | n/a | 9 | *Sufficient GCIEP budget is allocated to undertake planned L&C activities approved in the ToR L&C *Setting a target for this indicator was deemed not applicable (in agreement with FCDO) during GCIEP’s first full year of delivery in Year 2 , due to the demand-driven nature of the programme. Instead, it was agreed we would report Actuals in the Y2 log frame. However, where there are continuing interventions in Y3 (second full year of GCIEP delivery) with many of the same stakeholders and sectors, we have included targets in the Year 3 log frame for this indicator.
|  | Achieved - annual | n/a | Too early | 1 (1 products)
|  | Achieved - cumulative | n/a | Too early | 1 (1 products)
WEIGHTING: |  | Source |  |  |  |  | RISK RATING
10% |  | GCIEP RM and L&C monitoring, GCIEP K&L documentation (including links to public KPs and materials published) Note: a. A GCIEP Product is any written material produced by GCIEP and/or its delivery partners, through its DOC interventions/ TO work packages, that has been repackaged according to targeted audience/s and dissemination channel/s including learning events, that seek to contribute to the body of infra delivery and urban development knowledge towards improving FCDO and GCIEP delivery partners programming . This GCIEP product is out of the budget of the TO WP. |  |  |  |  | MINOR
º
Note on G46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1. The subject should be the eventual pricing policy, to be informed by the viability assessment. 2. expand acronym MWT. What’s the policy etc? 3. Roadmap seems to be the intermediate outcome for 2, rather than a separate item.

## VIETNAM_ nested LF
PROGRAMME NAME: | Green Cities, Infrastructure and Energy Programme (GCIEP) Y3 Logframe - DOC VIETNAM (22 January 2026)
OUTCOME 1 | Outcome Indicator 1.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 (6m - Phase 1 achieved) (1 Apr 25 - 30 Sep 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Finance and Investment is leveraged for sustainable and inclusive infrastructure and the built environment in Vietnam (DOC only and TO - if reported by Post) (REPORTED ANNUALLY) | Total volume of total non-GCIEP financing mobilised as a result of GCIEP interventions in Vietnam (£ ) Disaggregation by: type of funding organisation (Private/Donor/Public -National/Municipal), financing categories (catalysed, facilitated, unlocked, and reallocated) To track off logframe, GCIEP country programmes where non-FCDO funds have been leveraged downstream | Planned -annual | n/a | Too early | Too early | 0 | 0 | *GCIEP TA makes a contribution towards facilitating investment into urban economic infrastructure projects and overcoming obstacles to project delivery *Partner government continued support for: i) pro-poor, inclusive, low carbon and resilient objectives and targeted approaches; and ii) channel private and public investment into urban development and economic infrastructure *Target and Results will be based only on DOC interventions; but GCIEP will also report on results from TO work packages, in case there is GCIEP contribution and results have been tracked either by GCIEP or FCDO Post (post completion monitoring) * COMMITTED refers to: The financing quantified has already been committed/mobilised by other investors, where GCIEP TA is being used to make the investment “bigger, better or faster.
|  | Achieved - annual | n/a | Too early | 0 | 0
|  | Achieved - cumulative | n/a | Too early | 0 | 0
Source
GCIEP DOC and TO RM databases
| Outcome Indicator 1.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 (6m - Phase 1 achieved) (1 Apr 25 - 30 Sep 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Volume of public finance mobilised for climate change purposes in Vietnam (£) (as a result of GCIEP interventions ) (disag by new financing vs reallocated financing) (ICF KPI 11) | Planned -annual | n/a | Too early | n/a | n/a | n/a: ICF KPI methodology only allows actuals to be reported
| ICF KPI 12 Volume of private finance mobilised for climate change purposes | Achieved - annual | n/a | Too early | 0 | 0
|  | Achieved - cumulative | n/a | Too early | 0 | 0
Source
GCIEP RM databases and ICF monitoring ICF KPI Methodology: https://assets.publishing.service.gov.uk/media/5b17935be5274a190c1b6f8c/KPI11-Public-finance-Updated-methodology.pdf
| Outcome Indicator 1.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 (6m - Phase 1 achieved) (1 Apr 25 - 30 Sep 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Volume of private finance mobilised for climate change purposes in Vietnam (£) (as a result of GCIEP interventions) (ICF KPI 12) | Planned -annual | n/a | Too early | n/a | n/a | n/a: ICF KPI methodology only allows actuals to be reported
| ICF KPI 12 Volume of private finance mobilised for climate change purposes | Achieved - annual | n/a | Too early | 0 | 0
|  | Achieved - cumulative | n/a | Too early | 0 | 0
|  | Source | [5 empty] | RISK RATING
|  | GCIEP RM databases and ICF monitoring ICF KPI Methodology: https://assets.publishing.service.gov.uk/media/65e0b9913f6945001d036030/KPI-12-volume-private-finace-mobilised.pdf | [5 empty] | MODERATE
OUTCOME 2 | Outcome 2.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 (6m - Phase 1 achieved) (1 Apr 25 - 30 Sep 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
GCIEP TA contributed to a stronger enabling environment in Vietnam for the provision of climate resilient&inclusive infrastructure services (REPORTED ANNUALLY) | APPROVAL: Number of approved policies/regulations/strategies/roadmaps/frameworks/institutional structures in Vietnam supported by GCIEP TA (disag by Strategy & Planning, Legal & Regulatory Framework, Financing Mechanisms, Institutional capacity & governance, Networks & Partnerships) | Planned -annual | n/a | Too early | Too early | VN02 TOD&BIM 1-3. Three TOD Resolutions (numbers 15, 16, 17) accepted by MRB - MOVED TO INTERMEDIATE OUTCOME 3.1 4. Strategic framework for structuring TOD projects in Hanoi accepted by MRB - MOVED TO INTERMEDIATE OUTCOME 3.1 5. TOD financing mechanisms and recommendations for Hanoi accepted by MRB - MOVED TO INTERMEDIATE OUTCOME 3.1 VN01 Green Cities 6. Minimum of three Background Papers accepted by UDA - OBSOLETE 7. Minimum six concise Briefing Notes and three Comprehensive Briefing Papers that include best practice and recommendations accepted by UDA - OBSOLETE | 0 | *Central FCDO and country offices are open to learning from and being influenced by GCIEP generated knowledge - when relevant * Collaboration with CoE DPs collaboration increase urban and infrastructure effectiveness leading to local adoption and replication * No material change in government priorities with any political changes in countries that undergo national elections * Deliverables can include policies, regulations, roadmaps, strategies, frameworks, institutional structure / governance report, etc. that have been submitted/reviewed/accepted/approved by the beneficiary stakeholder/s (depending on country context) * APPROVAL: Formal endorsement of GCIEP supported policy/regulations/strategies/roadmaps/frameworks/institutional structures at FCDO partner countries by the beneficiary stakeholder (or the appropriate designated authority) * ADOPTION: The formal embedding and / or implementation of a GCIEP-supported structure, process, methodology or practices by FCDO partner countries, maintaining the core design and function of the original model, through minor contextual adjustments may be made. A deliverable is counted either as APPROVED or ADOPTED but not both, except in the case where GCIEP provides continious to support over time resulting in an evolution from APPROVAL to ADOPTION. In such execptional cases policy/regulations/strategies/roadmaps/frameworks/institutional structures may be reported at both level, usually for different years.
|  | Achieved - annual |  | Too early | 1 National Assembly Resolution 188 on urban rail and TOD passed in February 2025 | 0
|  | Achieved - cumulative |  | Too early | 1 | 1
Source
GCIEP L&C tracking tool, GCIEP K&L documentation Note: Deliverables must be approved by the beneficiary entity
| Outcome 2.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 (6m - Phase 1 achieved) (1 Apr 25 - 30 Sep 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| ADOPTION: Number of GCIEP supported policies/regulations/strategies/roadmaps/frameworks/institutional structures adopted as evidence of GCIEP legacy / sustainability in GCIEP supported entities in Vietnam (sustainability) (disag by Strategy & Planning, Legal & Regulatory Framework, Financing Mechanisms, Institutional capacity & governance, Networks & Partnerships) | Planned -annual | n/a | Too early | Too early | 0 | VN.P2.01 TOD 1.Resolution on Land Value Capture (LVC) financing mechanisms for HCMC passed by the HCMC People's Council
|  | Achieved - annual |  | Too early | 0 | 1 GCIEP inputs adopted by the regulators to approve: 1. HCMC TOD Resolution nº 38 guiding implementation of Article 6 of National Assembly's Resolution 188 related to TOD development was passed by the HCMC People's Council (August 2025) - Moved from Intermediate Outcome 3.1 as per overarchievement due to GCIEP inputs being adopted by the regulator to pass Resolutions(to avoid double counting) | GCIEP inputs adopted by the regulators to approve: 1. HCMC Transport Oriented Development (TOD) Resolution nº 38 guiding implementation of Article 6 of National Assembly's Resolution 188 related to TOD development was passed by the HCMC People's Council (August 2025) - Moved from Int. Outcome 3.1 as per achieved earlier than expected. 2. Hanoi TOD Resolution 15 was passed by the Hanoi City People's Council (November 2025) (including also GCIEP inputs to former Resolution 16 which has now been integrated under Resolution 15) - Moved from Int. Outcome 3.1 as per achieved earlier than expected
|  | Achieved - cumulative |  | Too early | 0 | 1
|  | Source | [5 empty] | RISK RATING
|  | GCIEP RM databases and Intervention Pathways Packages at the intervention level | [5 empty] | MODERATE
Y3 Interim PLF (August 2025) the following indicators were considered obsolete in agreement with FCDO: * Outcome 2.2 Replication: Number of GCIEP supported structures, processes, and / or methodologies replicated (and adapted) by country governement ministries
INTERMEDIATE OUTCOME 1 | INT Outcome Indicator 1.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 (6m - Phase 1 achieved) (1 Apr 25 - 30 Sep 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
GCIEP DOC is effectively delivered to be of a high-quality based on learning contributing towards improving the enabling environment and project pipeline for infrastructure investment and economic development (REPORTED ANNUALLY) | A) Increase in scope: Percentage of DOC interventions that have increase their scope since the start of the programme - CUMULATIVE (total number of DOC interventions scaled up / total number of DOC interventions) B) Closed / curtailed: Percentage of DOC interventions closed and / or curtailed since the start of the programme - CUMULATIVE (total number of DOC interventions closed or curtailed / total number of DOC interventions) C) New DOC interventions: Total number of DOC interventions introduced based on learning during GCIEP implementation phase | Planned -annual | n/a | n/a | n/a | n/a | n/a | *GCIEP can effectively target its assistance, to choose the right agencies/municipalities and/or institutions with which to partner and select and test the adequate interventions * GCIEP has in place the Impact Pathway packages to monitor DOC interventions applying adaptive programming principles *No material change in government priorities with any political changes in countries that undergo national elections * Well prepared projects (including feasibility studies) supported by GCIEP will attract the necessary downstream financing * In some cases, targets are not applicable, as we are a demand driven programme working under adaptive programming principles
|  | Achieved - annual | n/a | n/a | A) 1 VN02 TOD intervention B) 1 VN01 Green Cities | B) 1 VN01 Green Cities | C) 1 VN.P2.01 Institutional support for TODs
|  | Achieved - cumulative | n/a | n/a | A) 1 | A) 1 B) 1
Source
GCIEP RM databases and Intervention Pathways Packages at the intervention level Phase 1 interventions treated as scaled up for Phase 2
| INT Outcome Indicator 1.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 (6m - Phase 1 achieved) (1 Apr 25 - 30 Sep 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of GCIEP supported high quality, potentially bankable urban and/or infrastructure projects are identified, prioritised, sequenced or developed (includes signposting stage of the infrastructure development cycle) Disaggregated by stage of the infrastructure development cycle: (I) Project pipeline and (II) Project specific support including (a) Planning & preparation (concept note, business cases, (pre) feasibility studies); (b) Financing structuring (project development agreement, investment round tables etc); (c) Commercial and financial close; (d) Procurement; and (e) Implementation | Planned -annual | n/a | Too early | Too early | 0 | 0
|  | Achieved - annual |  | Too early | 0 | 0
|  | Achieved - cumulative |  | Too early | 0 | 0
Source
GCIEP RM databases and Intervention Pathways Packages at the DOC intervention level Note: High quality equals to projects that have mainstreamed GEDSI and CN&E GCIEP DO C supported projects/initiatives along the infrastructure development cycle: (a) Planning & preparation (project pipelines, concept note, business cases, (pre) feasibility studies); (b) Financing structuring (project development agreement, investment round tables etc); (c) Commercial and financial close; (d) Procurement; and (e) Implementation
INTERMEDIATE OUTCOME 3 | INT Outcome Indicator 3.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 (6m - Phase 1 achieved) (1 Apr 25 - 30 Sep 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Influencing and collaboration Uptake of relevant knowledge and evidence generated by GCIEP and/or its delivery partners by the GoV as well as ecosystem players leading to behavioural changes and changes in practices leading to improved provision and management of infrastructure and urban services (REPORTED ANNUALLY) | INFORMING DECISION MAKING: Number of policies/regulations/strategies/roadmaps/frameworks/institutional structures in Vietnam that have been informed with contributions from GCIEP TA. (disag by Strategy & Planning, Legal & Regulatory Framework, Financing Mechanisms, Institutional capacity & governance, Networks & Partnerships) | Planned -annual |  |  |  | VN.P1.02 TOD+BIM 1-3 Three TOD Resolutions (numbers 15, 16 17) reviewed/accepted by MRB - MOVED FROM Y2 LF OUTCOME 2.1 4. HCMC TOD Resolution no. 38 guiding the implementation of Article 6 of National Assembly's Resolution 188 related to TOD development as a result of GCIEP support is reviewed/accepted by Department of Construction / Department of Planning and Architecture and taking for consultation with HCMC People's Council - MOVED FROM Y2 LF OUTCOME 2.2 5. TOD Resolution guiding Article 9 of National Assembly's Resolution 188 related to TOD development as a result of GCIEP support is reviewed/accepted by Department of Construction / Department of Planning and Architecture and taking for consultation with HCMC People's Council - MOVED FROM Y2 LF OUTCOME 2.2 VN.P1.02 TOD&BIM 6. Strategic framework for structuring TOD projects in Hanoi reviewed/accepted by MRB - MOVED FROM Y2 LF OUTCOME 2.1 7. TOD financing mechanisms and recommendations for Hanoi reviewed/accepted by MRB - MOVED FROM Y2 LF OUTCOME 2.1 8. Strategic framework for structuring TOD projects in HCMC reviewed/accepted by Department of Construction / Department of Planning and Architecture - MOVED FROM Y2 LF OUTCOME 2.2 9. TOD financing mechanisms and recommendations for HCMC reviewed/accepted by Department of Construction / Department of Planning and Architecture - MOVED FROM Y2 LF OUTCOME 2.2 | VN.P1.02 TOD+BIM & VN.P2.01 Institutional support for TODs 1-3 Hanoi: Three TOD Resolutions (numbers 15 (TOD Planning and mgt), 16 (urban railways), 17 (Financing mechanisms)) informed by GCIEP technical expertise reviewed/accepted by Metro Railway Mgt Board (MRB) for submission to Hanoi People’s Council for its approval 4. HCMC: TOD Resolution no. 38 guiding the implementation of Article 6 of National Assembly's Resolution 188 related to TOD development as a result of GCIEP support is reviewed/accepted by Department of Construction / Department of Planning and Architecture and submitted to HCMC People's Council for its approval 5. HCMC: TOD Resolution guiding the implementation of Article 9 of National Assembly's Resolution 188 related to TOD development as a result of GCIEP support is reviewed/accepted by Department of Construction / Department of Planning and Architecture and submitted to HCMC People's Council for its approval VN.P2.02 TOD&BIM 6. Hanoi:Strategic framework for structuring TOD projects reviewed/accepted by MRB 7. Hanoi: TOD financing mechanisms and recommendations (to inform final inputs on resolution 17) reviewed/accepted by MRB 8. HCMC: Strategic framework for structuring TOD projects reviewed/accepted by Department of Construction / Department of Planning and Architecture (DPA) 9. HCMC: TOD financing mechanisms and recommendations (to inform final inputs on TOD financing resolution) reviewed/accepted by DPA VN.P2.01 Institutional support for TODs 10. HCMC: TOD Technical Guidelines to support in the implementation reviewed/accepted by HCMC Department of Constructuion / Department of Planning and Architecture | * Central FCDO and country offices are open to learning from and being influenced by GCIEP generated knowledge - when relevant . * Deliverables can include policies, regulations, roadmaps, strategies, frameworks, institutional structure / governance report, etc. that have been submitted/reviewed/accepted/approved by the beneficiary stakeholder/s (depending on country context). *Targets and results include deliverables that are REVIEWED/ ACCEPTED by the beneficiary stakeholder that are used as as source of evidence, insights, or recommendations to inform policies, strategies, or actions in FCDO partner countries.
|  | Achieved - annual |  |  |  | 4 VN02 TOD&BIM 1. Strategic framework for structuring TOD projects in Hanoi accepted by MRB 2. Strategic framework for structuring TOD projects in HCMC reviewed/accepted by HCMC authorities (adapted from Hanoi following extensive stakeholder consultation to contextualise it to HCMC) 3. TOD financing mechanisms and recommendations for Hanoi accepted by MRB 4. TOD financing mechanisms and recommendations for HCMC reviewed/accepted by HCMC Department of Construction *GCIEP inputs to Hanoi TOD Resolution 15 adopted by the Hanoi City People's Council who approved the Resolution (November 2025) - Moved OC2.3 as per overachievement to avoid double counting *GCIEP inputs to HCMC TOD Resolution no. 38 guiding implementation of Article 6 of the National Assembly's Resolution 188 related to TOD development is adopted by the regulator to pass HCMC Resolution no. 38 - Moved OC2.3 as per overachievement to avoid double counting | VN.P1.02 TOD&BIM 1. Hanoi: Strategic framework for structuring TOD projects in Hanoi accepted by MRB 2. HCMC: Strategic framework for structuring TOD projects in HCMC reviewed/accepted by HCMC authorities (adapted from Hanoi following extensive stakeholder consultation to contextualise it to HCMC) 3. Hanoi: TOD financing mechanisms and recommendations (to inform final inputs on resolution 17) reviewed/accepted by MRB 4. HCMC: TOD financing mechanisms and recommendations reviewed/accepted by HCMC Department of Construction - to be deleted if the LVC resolution is passed by March 2026 5. HCMC: TOD Resolution guiding Article 9 of National Assembly's Resolution 188 related to TOD development as a result of GCIEP support is reviewed/accepted by Department of Construction / Department of Planning and Architecture and taking for consultation with HCMC People's Council - to be deleted if the resolution is passed by March 2026 Moved to Outcome 2.3 as per received formal approval,earlier than expected, to avoid double counting: *GCIEP inputs to Hanoi TOD Resolution 15 adopted by the Hanoi City People's Council who approved the Resolution (November 2025) (renamed Resolution 71) *GCIEP inputs to HCMC TOD Resolution no. 38 guiding implementation of Article 6 of the National Assembly's Resolution 188 related to TOD development is adopted by the regulator to pass HCMC Resolution no. 38
|  | Achieved - cumulative |  | Too early | 0 | 6
|  | Source | [5 empty] | RISK RATING
|  | GCIEP monitoring and operational databases | [5 empty] | MODERATE
INTERMEDIATE OUTCOME 4 | INT Outcome Indicator 4.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 (6m - Phase 1 achieved) (1 Apr 25 - 30 Sep 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
DOC interventions have successfully integrated GEDSI risks and opportunties resulting in Empowerment (REPORTED ANNUALLY) | % of DOC intervention that include GEDSI considerations in accordance with Level 2 - Empowerment - as per the FCDO GEDSI framework (realised target ambition) - Linked to Output 4 | Planned -annual |  |  |  |  | 50% | *Resources at DOC and TO level are deployed to ensure that GEDSI is effectively mainstreamed during implementation, regularly identifying and assessing GEDSI risks and opportunities
Achieved - annual
|  | Source | [5 empty] | RISK RATING
|  | GCIEP GEDSI monitoring; GCIEP deliverables TOR and GCIEP work package progress reports Note: it only applies to interventions that have GEDSI potential | [5 empty] | MODERATE
OUTPUT 1 | Output Indicator 1.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 (6m - Phase 1 achieved) (1 Apr 25 - 30 Sep 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26)
High-quality TA deliverables completed by GCIEP for FCDO posts to facilitate economic transformation and inclusive growth (in line with VfM targets) (REPORTED QUARTERLY) | DOC Percentage of the activities planned at the start of each quarter that are completed. | Planned -annual | n/a | n/a | 70% | 70% | 70%
|  | Achieved - annual | n/a | n/a | 88.6% | n/a
Source
GCIEP DOC intervention workplans Note: Total number of activities completed during the quarter / total number of activities planned to be completed as per workplan submitted to FCDO at the start of the quarter. It is expected that the activities detailed (and related deliverables) in the intervention workplan will be updated on a quarterly basis in line with adaptive management best practice.
WEIGHTING: | [7 empty] | RISK RATING
MINOR
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 (6m - Phase 1 achieved) (1 Apr 25 - 30 Sep 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Proactive strategic collaboration to maximise effectiveness in GCIEP delivery in TO and/or DOC countries (REPORTED QUARTERLY) | No. of instances where GCIEP team has worked and/or coordinated* with partners** A) GCIEP DOC interventions B) GCI CoE delivery partners C) Any other UK expert organisations D) Development partners (instances that DOC and Buy-ins have collaborated with development partners) | Planned -annual | n/a | n/a | n/a | n/a | B) 3 (TfL, CI, CPC) C) 1 (CoST) D) 5 (ADB, JICA, Swiss State Secretariat for Economic Affairs, United Nationals Human Settlements Programme, World Bank) | *GCIEP can effectively target its assistance, to choose the right agencies/municipalities and/or institutions with which to partner and select the right interventions * Targets (n/a): Targets are not applicable, as we are a demand driven programme working under adaptive programming principles
|  | Achieved - annual | n/a | n/a | B) 3 (TfL, CI, CPC) D) 5 (ADB, JICA, Swiss State Secretariat for Economic Affairs, United Nationals Human Settlements Programme, World Bank) | C) 1 (CoST)
|  | Achieved - cumulative | n/a | n/a | B) 3 D) 5 | B) 3 C) 1 D) 5
WEIGHTING: |  | Source | [5 empty] | RISK RATING
10% |  | GCIEP monitoring and operational databases Notes: *Co-ordination defined as having an active Community of Practice/signed MoU/other formal engagement process in place) ** Partners defined as any in-country international development agency or donor based in a DOC country ***GCIEP CoE delivery partners: Cross Rail Intl, Ofgem, Infrastructure and Projects Authority, Transport for London, BSI; CATAPULT, Ordinance Survey and British Geological Survey | [5 empty] | MINOR
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 (6m - Phase 1 achieved) (1 Apr 25 - 30 Sep 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Enhancing capacity and knowledge to strengthen GCIEP supported institutions and agencies in partner countries (disag by DOC and TO) (REPORTED QUARTERLY) | Percentage and number of people certified in UK tools and methodologies (Only applicable if there is formal UK certification offer. UK tools and methodologies with certification exam include, for example, 5CM) | Planned -annual | n/a | Too early | n/a | n/a | 0 | * GCIEP has the capacity to deliver targeted and high quality trainings, adapted to the needs to targeted stakeholders *GCIEP can leverage on UK expertise to successfully deliver TA *Setting a target for this indicator was deemed not applicable (in agreement with FCDO) during GCIEP’s first full year of delivery in Year 2 , due to the demand-driven nature of the programme. Instead, it was agreed we would report Actuals in the Y2 log frame. However, where there are continuing interventions in Y3 (second full year of GCIEP delivery) with many of the same stakeholders and sectors, we have included targets in the Year 3 log frame for this indicator.
|  | Achieved - annual | n/a | Too early | 0 | 0
|  | Achieved - cumulative | n/a | Too early | 0 | 0
Source
GCIEP RM and operational databases Note: Number of people certified / total number of people trained in UK tools and methodologies taking the exam.
| Output Indicator 3.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 (6m - Phase 1 achieved) (1 Apr 25 - 30 Sep 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number (#) of people trained via GCIEP supported work packages/interventions Disaggregation: portfolio (DOC, TO, Buy-in), women professionals, people with disabilities, and youth, indicate if UK methodology. | Planned -annual | n/a | n/a | n/a | n/a | 15
|  | Achieved - annual | n/a | n/a | 0 | 0
|  | Achieved - cumulative | n/a | n/a | 0 | 0
|  | Source | [5 empty] | RISK RATING
|  | GCIEP RM and operational databases | [5 empty] | MINOR
| Output Indicator 3.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 (6m - Phase 1 achieved) (1 Apr 25 - 30 Sep 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
| % of participants indicating that the training/capacity building in Output 3.1 or 3.2 was "useful" or "very useful" on a 5 point scale | Planned -annual | n/a | n/a | 70% | 70% TOD & BIM Capacity development meetings/workshops for decision-makers and technical staff on the recommended TOD approach and sequence of implementation steps Green Cities Three consultations on GCIEP outputs in support of the UDM Law, and three workshops on Comprehensive Briefing Papers for knowledge sharing and capacity building of MOC, UDA, and other public sector practitioners | 85% | * GCIEP has the capacity to deliver targeted and high quality trainings, adapted to the needs to targeted stakeholders *GCIEP can leverage on UK expertise to successfully deliver TA
|  | Achieved - annual | n/a | n/a | 0 | 0
|  | Achieved - cumulative | n/a | n/a | 0 | 0
WEIGHTING: |  | Source | [5 empty] | RISK RATING
10% |  | GCIEP RM and operational databases | [5 empty] | MINOR
OUTPUT 4 | Output Indicator 4.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 (6m - Phase 1 achieved) (1 Apr 25 - 30 Sep 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
GEDSI is mainstreamed across GCIEP DOC interventions and Target Offer (TO) work packages (WPs) (disag by DOC and TO) (REPORTED ANNUALLY) | % of GCIEP supported DOC interventions/TO WPs that have an ambition of level 2 - Empowerment as per the FCDO GEDSI framework Disaggregated by FCDO GEDSI framework levels 1-3 | Planned - annual | n/a | n/a | L2: 50% | L2: 50% | L2: 50% | *The FCDO GEDSI Framework is effective into translating FCDO’s GEDSI policies into programming; enabling GCIEP to take a structured and practical approach to exploring how GCIEP interventions can maximise benefits to disadvantaged and vulnerable groups
|  | Achieved - annual | n/a | n/a | 100% | n/a
WEIGHTING: |  | Source | [5 empty] | RISK RATING
15% |  | GCIEP GEDSI monitoring; GCIEP deliverables TOR and GCIEP work package progress reports Note: it only applies to interventions that have GEDSI potential | [5 empty] | MINOR
OUTPUT 5 | Output Indicator 5.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 (6m - Phase 1 achieved) (1 Apr 25 - 30 Sep 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
CN&E is mainstreamed across GCIEP DOC interventions and Target Offer (TO) work packages (WPs) (ICF compliance) (disag by DOC and TO) (REPORTED ANNUALLY) | % of GCIEP supported DOC interventions/TO work packages that are mainstreaming CN&E | Planned - annual | n/a | n/a | 100% | 100% | 100% | *ICF compliant: An interventions that contributes to at least 1 ICF KPI indicator *ICF KPI TA methodology only allows actuals to be reported
|  | Achieved - annual | n/a | n/a | 100%
Source
GCIEP ICF monitoring; DOC intervention ToRs and TO Work Package ToRs; GCIEP progress reports
| Output Indicator 5.2 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 (6m - Phase 1 achieved) (1 Apr 25 - 30 Sep 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| % of total spend that is ICF compliant in relation to the total £ value of GCIEP programmes - of eligible ODA | Planned - annual | n/a | n/a | 80% | 80% | 80%
|  | Achieved - annual | n/a | n/a | 100%
Source
GCIEP ICF monitoring; DOC intervention ToRs and TO Work Package ToRs; GCIEP progress reports
| Output Indicator 5.3 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 (6m - Phase 1 achieved) (1 Apr 25 - 30 Sep 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of countries supported by ICF technical assistance ICF TA KPI 1 (reported only on completed DOC interventions/TO WPs) | Planned - annual | n/a | n/a | n/a | n/a: ICF KPI methodology only allows actuals to be reported | n/a
|  | Achieved - annual | n/a | n/a | TBC by Dec25
|  | Achieved - cumulative | n/a | n/a | TBC by Dec25
Source
GCIEP CN&E monitoring; DOC intervention ToRs and TO work package ToRs; GCIEP progress reports
| Output Indicator 5.4 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 (6m - Phase 1 achieved) (1 Apr 25 - 30 Sep 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of individuals supported by ICF technical assistance ICF TA KPI 2.1 (reported only on completed DOC interventions/TO WPs) | Planned - annual | n/a | n/a | n/a: ICF KPI methodology only allows actuals to be reported | n/a: ICF KPI methodology only allows actuals to be reported | n/a
|  | Achieved - annual | n/a | n/a | TBC by Dec25
|  | Achieved - cumulative | n/a | n/a | TBC by Dec25
Source
GCIEP CN&E monitoring; DOC intervention ToRs and TO work package ToRs; GCIEP progress reports
| Output Indicator 5.5 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 (6m - Phase 1 achieved) (1 Apr 25 - 30 Sep 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of organisations supported by ICF technical assistance ICF TA KPI 2.2 (reported only on completed DOC interventions/TO WPs) | Planned - annual | n/a | n/a | n/a: ICF KPI methodology only allows actuals to be reported | n/a: ICF KPI methodology only allows actuals to be reported | n/a
|  | Achieved - annual | n/a | n/a | TBC by Dec25
|  | Achieved - cumulative | n/a | n/a | TBC by Dec25
Source
GCIEP CN&E monitoring; DOC intervention ToRs and TO work package ToRs; GCIEP progress reports
| Output Indicator 5.6 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 (6m - Phase 1 achieved) (1 Apr 25 - 30 Sep 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26)
| Number of climate policies informed by ICF technical assistance ICF TA KPI 3 (reported only on completed DOC interventions/TO WPs) | Planned - annual | n/a | n/a | n/a: ICF KPI methodology only allows actuals to be reported | n/a: ICF KPI methodology only allows actuals to be reported | n/a
|  | Achieved - annual | n/a | n/a | n/a
|  | Achieved - cumulative | n/a | n/a | n/a
WEIGHTING: |  | Source | [5 empty] | RISK RATING
15% |  | GCIEP CN&E monitoring; DOC intervention ToRs and TO work package ToRs; GCIEP progress reports | [5 empty] | MINOR
OUTPUT 6 | Output Indicator 6.1 |  | Baseline (2023) | Year 1 (7m) (7 Sep 23 - 31 March 24) | Year 2 (12m) (1 April 24 - 31 March 25 ) | Year 3 (6m - Phase 1 achieved) (1 Apr 25 - 30 Sep 25 ) | Year 3 Target (1st Apr 25 - 31 Mar 26) | Assumptions
Learning (evidence) produced and in place for GCIEP to collate and disseminate UK and international urban / infrastructure expertise within GCIEP, FCDO, and to the wider ecosystem (REPORTED QUARTERLY) | No. of GCIEP products (analysis and learning including events) that deliver insights which inform/shape FCDO/wider development partner policies and programmes Dissaggregation by events and products | Planned - annual | n/a | Too early | n/a | n/a | 8 | *Sufficient GCIEP budget is allocated to undertake planned L&C activities approved in the ToR L&C *Setting a target for this indicator was deemed not applicable (in agreement with FCDO) during GCIEP’s first full year of delivery in Year 2 , due to the demand-driven nature of the programme. Instead, it was agreed we would report Actuals in the Y2 log frame. However, where there are continuing interventions in Y3 (second full year of GCIEP delivery) with many of the same stakeholders and sectors, we have included targets in the Year 3 log frame for this indicator.
|  | Achieved - annual | n/a | Too early | 3 products 2 events | 5 products 1 event
|  | Achieved - cumulative | n/a | Too early | 3 products 2 events | 8 products 3 events
WEIGHTING: |  | Source | [5 empty] | RISK RATING
10% |  | GCIEP RM and L&C monitoring, GCIEP K&L documentation (including links to public KPs and materials published) Note: a. A GCIEP Product is any written material produced by GCIEP and/or its delivery partners, through its DOC interventions/ TO work packages, that has been repackaged according to targeted audience/s and dissemination channel/s including learning events, that seek to contribute to the body of infra delivery and urban development knowledge towards improving FCDO and GCIEP delivery partners programming . This GCIEP product is out of the budget of the TO WP. | [5 empty] | MINOR
º
Note on F22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mention the deliverable that informed /supported this Reply: This is a series of TA in the form of technical papers etc, provided to Hanoi and HMC to support on their city level TOD resolutions, that was taken up by policymakers to inform a national level resolution Reply: Since September 2024, GCIEP Vietnam has supported Hanoi city through MRB and HCMC through Department of Construction and Department of Architecture and Planning to enhance the TOD-enabling environment in Hanoi. Assistance was given for developing Resolution 188/2025/QH15 dated 19 February 2025 and the ongoing City-level TOD resolutions informed by UK expertise and best practices, producing targeted diagnostic review report, technical studies to guide TOD project design and implementation, and translating enabling policy to practical capacity building and private investment mobilisation.
Note on H27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: As above
Note on H28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: In what sense is it an ‘overachievement’? Explain. Reply: Also, as above, mention the deliverable - how is the outcome connected to the intervention? Reply: As above. Reply: Since September 2024, GCIEP Vietnam has supported Hanoi city through MRB and HCMC through Department of Construction and Department of Architecture and Planning to enhance the TOD-enabling environment in Hanoi. Assistance was given for developing Resolution 188/2025/QH15 dated 19 February 2025 and the ongoing City-level TOD resolutions informed by UK expertise and best practices, producing targeted diagnostic review report, technical studies to guide TOD project design and implementation, and translating enabling policy to practical capacity building and private investment mobilisation.
Note on H40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is there a specific TOD we can point to? Or is our work too general/high level? Reply: It is too early. Hanoi and HCMC have some targets to how they want to invest on TOD financing once the resolutions are passed and TOD development starts. That was report Y2 Annual Report.
Note on H46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not all of these are naming policies etc. Some, e.g. 6 and 7 are deliverables. Reply: Text updated