Data and Research in Education (DARE) Annual Review

Title: Data and Research in Education (DARE)
Programme Value £ (full life): £23 million		Review date: 31 Dec 2025
Programme Code: 300575	AMP start date: 25 Sept 2020	AMP end date: 31 Dec 2026

Summary of Programme Performance
Year	2021	2022	2023	2024	2025	2026
Overall Output Score	B	B	A	B	A
Overall programme risk rating	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0003715.odt
DevTracker Link to results framework:	D0006614

Acronyms:
AGA	Accountable Grant Arrangement	MoFEPT	Ministry of Federal Education & Professional Training
ASC	Annual School Census	NAW	National Assessment Wing
ASER	Annual Status of Education Report	NAT	National Achievement Test
BHC	British High Commission	NIM	National Institute of Management
BTAG	Bridging Technical Assistance	NODP	National Open Data Portal
CIES	Comparative & International Education Society	NSPP	National School of Public Policy
CMPs	Centrally Managed Programmes	OOSC	Out‑of‑School Children
CPF	World Bank Country Partnership Framework	OOSC‑CF	Out‑of‑School Children Challenge Fund
DARE	Data and Research in Education Programme	OPM	Oxford Policy Management
DARE‑RC	DARE Research Consortium	PC‑1	Planning Commission Form‑1 (GoP development planning document)
DARE‑TF	DARE Trust Fund (World Bank)	PES	Pakistan Education Statistics
D4FL	Data for Foundational Learning	PFLH	Pakistan Foundational Learning Hub
DSF	Data Standardisation Framework	PIE	Pakistan Institute of Education
ECP	Election Commission of Pakistan	PRO	Programme Responsible Owner
ECW	Education Cannot Wait	PSRP	Public Schools Reorganisation Programme (Punjab outsourcing reform)
EMIS	Education Management Information System	PSS	Private School Survey
FCDO	Foreign, Commonwealth & Development Office	RAG	Research Advisory Group
FDE	Federal Directorate of Education	SDG4	Sustainable Development Goal 4
FLN	Foundational Literacy and Numeracy	SELD	Sindh Education and Literacy Department
GEPD	Global Education Policy Dashboard (WB)	SMC / MCMC	Senior / Mid‑Career Management Course (NSPP/NIM training)
GPE	Global Partnership for Education	STTA	Short‑Term Technical Assistance
GOAL	Girls and Out‑of‑School Children: Access and Learning programme	TA	Technical Assistance
HQ	Headquarters (FCDO)	TFP	Teach For Pakistan
ITA	Idara‑e‑Taleem‑o‑Aagahi	UIS	UNESCO Institute for Statistics
KP	Khyber Pakhtunkhwa	WB	World Bank
LSA	Large‑Scale Assessment	WWHGE	What Works Hub for Global Education
LAYS / micro‑LAYS	Learning‑Adjusted Years of Schooling / programme‑level LAYS	WG‑SS	Washington Group Short Set (disability data instrument)
MIW	Management Information Wing (PIE)

A. SUMMARY AND OVERVIEW
1. The Data and Research in Education (DARE) programme aims to strengthen national education data and policy in Pakistan. This goal will be achieved through an increase in the availability of high-quality learning and administrative data, research and evidence to guide education policy, teaching and learning, and system reforms.
2. DARE’s interventions are vital because Pakistan needs robust data, evidence-based policies and solutions to tackle the learning crisis, and to reduce the staggering number of out-of-school children (OOSC), which ranges between 22.8m to over 26m, with somewhere between 30% to 40% of primary-aged children not in school[1]. Learning poverty[2] has reached an alarming rate of 77%[3], compared to an average of 58% in South Asia. Of the 54.2 million children who are currently enrolled in grades K-12, the average child attends school for 9.4 years but achieves only 5.1 years of learning.[4] Marginalised groups such as girls and children with disabilities and those from religious minorities face even greater challenges in enrolling and accessing a quality education.
  [1] Pakistan Education Statistics 2023-2024, Pakistan Institute of Education (PIE).
  [2] This means that 3 in 4 children cannot read and understand a simple story by age 10.
  [3] Ibid
  [4] Based on the Human Capital Index, World Bank, cited in https://pmc.ncbi.nlm.nih.gov/articles/PMC8554110/
3. DARE contributes to tackling these challenges through four outputs:
- Output 1: Technical assistance (TA) to strengthen provincial and federal education data systems, delivered through the World Bank Pakistan@100 Trust Fund. This includes support to Pakistan Institute of Education (PIE), Pakistan Foundational Learning Hub (PFLH), the Global Education Policy Dashboard[5], and a set of research studies (e.g., a national survey of private schools). (£8 million)
  [5] The Dashboard measures the drivers of learning outcomes in basic education around the world – it currently has data on 39 indicators for 14 countries, including Pakistan.
- Output 2: A citizen-led learning survey and advocacy, delivered through an Accountable Grant Arrangement (AGA) with a national non-governmental organisation, Idara-e-Taleem-o-Aagahi (ITA). ITA delivers the Annual Status of Education Report (ASER); this dataset is important because it provides a citizen-led learning assessment that generates important debate about the state of education and learning in Pakistan. (£2.6 million[6])
  [6] This includes ASER and support to flood emergency from October 2022- September 2023.
- Output 3: Research on what works to improve access and learning outcomes for the most marginalised children, delivered through a Research Consortium under a commercial contract with the Oxford Policy Management (OPM). (£9.3 million)
- Output 4: A teacher training model, delivered through an Accountable Grant Arrangement (AGA) with Teach for Pakistan (TFP). (£2.5 m)
1. All components have strong national outreach and collaboration. The TA we provide through the World Bank has had sustained engagement with all the provinces and federal authorities, including the Planning Commission. The TA further strengthened Pakistan Institute of Education’s (PIE) provincial relationships, positioning the organisation as a national custodian of learning and education administrative data. Similarly, the Pakistan Foundational Learning Hub (PFLH), concluded in September 2025, established regular engagements with all the provinces raising awareness and building momentum around the urgency of foundational learning. The Research Consortium also has an active portfolio of studies in all the provinces.
2. As noted in last year’s annual review (AR), there is a good fit between the programme’s priorities, and the evolving direction of UK’s education offer in Pakistan. The programme will fill vital gaps in evidence in Pakistan and globally. Research produced under DARE will directly guide TA strategy and interventions, and we start to see early signs of uptake by the provincial governments.
3. This is the last AR as the programme concludes in December 2026. Our AGA with ITA (output 2) will conclude on the 1st of April 2026, and with TFP (output 4) on the 30th of June 2026. The commercial contract with OPM (output 3) will conclude on the 30th of December 2026. All activities within the Trust Fund with the World Bank (output 1) will conclude within the grant closing date May 2027.

MAJOR ACHIEVEMENTS:

THE RESEARCH CONSORTIUM:
1. Delivery of a diverse research portfolio: In 2025, the Research Consortium achieved significant momentum across its 34-study portfolio, with four studies completed and the remainder progressing through midterm or final stages. These studies address some of Pakistan’s most persistent education challenges (e.g., learning loss, equity for marginalised groups, foundational learning, and teacher effectiveness) providing a pipeline of evidence for our future TA, governments and development partners.
2. Selection of Special Issue in International Journal: A major milestone this year was the approval of a dedicated Special Issue by an international peer reviewed journal, which will feature 10–12 DARE RC studies. Securing a Special Issue focused entirely on Pakistan - typically reserved for multicountry contributions - is rare and reflects the exceptional quality and relevance of the programme’s research. This achievement also aligns closely with the spirit of DARE: elevating Pakistani academic voices in global education debates.
3. Hosted the First DARE International Education Summit and launched the Deans’ Forum: The Summit convened prominent and emerging voices in education across Pakistan, with strong participation from FCDO’s centrally managed global research programmes. This high‑visibility event elevated DARE‑RC’s credibility and positioned its research at the centre of national reform discussions. It strengthened the connection between local evidence and global policy conversations, significantly enhancing the programme’s potential for research uptake. The Summit also marked the launch of the Deans’ Forum, a convening of Heads of Department from leading Pakistani universities - including Aga Khan University in Karachi, LUMS in Lahore, and the University of the Punjab - designed to strengthen a national education research community and create a structured platform for sustained collaboration with policymakers.
4. Research Uptake for Students Learning Outcomes (SLO) Reforms in Khyber Pakhtunkhwa: DARE supported research led by the University of Oxford and the Institute of Education Peshawar informed the Secretary of Education’s decision to develop SLO aligned teaching and assessment resources for Grades 9–10 across eight subjects. These materials are now being converted into offline video lessons for provincewide teacher access, demonstrating early system level uptake of research with clear potential for scaleup through the Directorate of Professional Development to benefit students across the province.
WORLD BANK:
1. Our partnership with the WB continued to leverage the Bank’s Actions to Strengthen Performance for Inclusive and Responsive Education Program (ASPIRE) multiplying the impact of our investment. (ASPIRE is US$200 million, part of larger pre-CPF $800 Million WB education portfolio in Pakistan). This programme-for-results includes a set of Disbursement Linked Indicators (DLIs) to incentivise the federal and provincial governments to collaborate with DARE on, among other things, data standardisation (paragraph 43), design of a performance-based transfer grant (paragraph 60), implementation of foundational learning policies in the provinces, (paragraph 54).
2. Significant progress was made on the Data Standardisation Framework (DSF), a cornerstone reform for building a coherent national education data system. DSF 2.0 was finalised with full provincial consensus, and and key national datasets[7] (including the Annual School Census) continued to align with the updated standards. These steps matter because they move Pakistan towards a harmonised, comparable and internationally aligned education data system, reducing fragmentation, improving data quality, and providing enabling conditions for the governments to make evidence‑based decisions on planning and budgeting.
  [7] the National Annual School Census (ASC) guidance was aligned with DSF for the third consecutive year, and the Pakistan Education Statistics 2023–24 report was published using DSF for the first time
3. Private Schools Survey: Strong progress was made in designing and preparing the first comprehensive Private Schools Survey, including instrument development, sampling, and coordination with provincial governments. This survey will generate the first reliable, system‑wide data on a sector that educates over one‑third of Pakistan’s children (circa 19.5 millions[8]), filling a longstanding evidence gap. The resulting dataset will enable governments to better understand school characteristics, quality, fees, and geographic distribution—providing the foundation for more informed policy, regulation, and planning.
  [8] This number is based on the calculations in the Pakistan Education Statistics 2023-2024 report. We computed the sum from the private‑sector enrolment counts by level (Pre‑Primary → Higher Secondary) shown in the report’s Annexures tables.
4. Support to the Out‑of‑School Children (OOSC) Challenge Fund (Design Stage): Through the TF, FCDO provided critical early‑stage technical assistance to the design of the PKR 75 billion (approximately £196.7 million) Out‑of‑School Children Challenge Fund, helping shape its strategic architecture, verification systems, and performance‑based financing approach. This early design support lays the foundation for a results‑based financing mechanism that can channel resources to lagging districts and strengthen accountability for enrolment and learning outcomes.
5. National Achievement Test 2026: Following the 2025 delay, the programme reset NAT on a predictable track by completing all preparations and a national pilot for NAT 2026, adding two strategic upgrades—private‑school inclusion and a foundational‑learning module aligned with UIS technical standards for SDG 4[9] reporting—with pilot evidence refining the design to 120 schools per province (60 public/60 private); together with NAT 2023 informing federal guidance, this positions Pakistan to run a standards‑based national Large-Scale Assessment that can track learning poverty from 2026.
  [9] The foundational learning component in NAT will focus on SDG 4.1.1 reporting which measures the the proficiency of children and young people in reading and mathematics at various educational levels.
6. Provincial Foundational Learning Delivery Plans Finalised and Ready for Implementation: All provinces have finalised foundational learning delivery plans through consultative processes; DARE’s support in mapping teaching and learning materials and recommending FLN improvements leaves them implementation‑ready.
TFP and ITA:
1. Teach For Pakistan (TFP) model reached 12,500 students in 2025 across 97 public schools, (22% with disabilities). Learning outcomes exceeded expectations. An independent RAND evaluation reported 6–10 months of additional learning in Maths and around 6 months in English for TFP‑taught students compared with peers in government classrooms.
2. Citizen‑Led Assessment (ASER) – A Decade of UK Partnership: 2025 marks the completion of over 12 years of UK partnership with ITA to deliver ASER, Pakistan’s flagship citizen‑led assessment. Over this period, ASER has become a trusted national public good, generating independent, district‑representative data on enrolment and foundational learning, and providing a low‑cost, community‑driven mechanism that strengthens transparency and accountability across the education system.

KEY CHALLENGES:

1. Continued retreat of federal commitment, threatening the sustainability of key reforms: The most significant threat to sustainability relates to the withdrawal of federal financing for the Foundational Learning Hub (FLH). While education is devolved, federal commitment remains essential for maintaining national coordination functions and sustaining foundational learning reforms. The absence of federal budget allocation jeopardises continuity of FLH’s mandate, undermining the long‑term coherence and institutionalisation of FLN reforms. Similarly, the cessation of financing for the Teach for Pakistan Programme (TFP) might lead to loss of learning from a model that could offer the Federal government a promising intervention for teacher professional development.
2. Significant risk that publication outputs will not materialise within the programme’s lifetime: There is an increasing likelihood that key research publications - including the Special Issue and several DARE‑supported studies - will not be completed or published before programme closure. This is because delays at the start of the programme, complex research commissioning processes in a thin market (see previous AR), and the time-lag between research completion and international publication have all compounded. This delay has implications for Open Access commitments and limits the visibility and influence of the programme’s evidence base. Although alternative publication pathways exist (e.g., an edited volume or dispersed journal submissions), each requires additional time and coordination that may extend beyond the programme period.
3. Sustainability and staffing capacity issues at PIE: The organogram remains only partially approved, leaving critical posts unfilled. With DARE TF technical assistance ending in September 2026, there is a risk that PIE will be unable to sustain key functions[10].
  [10] An ongoing endline capacity assessment will be concluded in June allowing FCDO and World Bank to plan accordingly.
4. Delays and partial progress in provincial data integration and key research studies: Horizontal integration of provincial data systems and data access protocols remain only partially met, slowing progress toward full interoperability. Key research studies, including the major devolution/18th Amendment study, have faced multi‑year delays and remain incomplete, resulting in unmet targets for two consecutive years.
5. There is no evidence that TFP teaching model has influenced the Federal government approach to teacher professional development: While the TFP model has demonstrated its ability to deliver significant improvements in learning for children in under‑resourced schools, its potential for scale and government adoption is not yet assured. Realising this potential will require demonstrable improvements in cost efficiency to make the model affordable and feasible within government systems.

Summary supporting narrative for the overall score in this review:
The programme has scored an A in this annual review (AR). All four outputs scored an A. Output 1 (the World Bank Trust Fund) and output 3 (the Research Consortium) have overcome to an extent the delays of the last review period and are delivering most of the expected results in the last year of the programme. However, some activities (the Private School Survey) under the WB Trust Fund (output 1), and the publications of the research consortium (output 3) will not be completed by the end of the programme (more under the risk section).
Major recommendations for the year ahead:
THE RESEARCH CONSORTIUM:
Sustaining research communities via WWHGE-DARE RC partnership: The RC has energised research networks across Pakistan through Communities of Practice and policy dialogues. Their sustainability requires a dedicated, long‑term convenor. The What Works Hub for Global Education (WWHGE)[11] - the sister programme to DARE‑RC—should co‑convene and resource the Deans’ Forum as a standing platform for Heads of Department from leading universities, aligning WWHGE’s global evidence brokering with DARE‑RC’s Pakistan research pipeline.
[11] Home - What Works Hub for Global Education
(DARE and WWHGE SROs, by June 2026)
1. Ensuring completion of research publications: A focused plan is needed to ensure key research publications - likely to fall beyond programme closure - are completed and disseminated. This should include securing alternative publication routes and building a provision into any future FCDO technical assistance to carry forward outstanding publication and synthesis work, safeguarding the programme’s long‑term impact and visibility. (DARE and GOAL SROs, by June 2026)
2. Make research policy‑relevant through a joint evidence‑to‑action workflow: DARE will convert completed studies into concise policy briefs and thematic recommendation packs with one‑page action pathways (owners, steps, costs, quick wins) aligned to provincial decision windows; where relevant, future TA work will translate these into standardised TA offers. (DARE and GOAL SROs, by March 2026)
THE WORLD BANK:
1. Importance of the World Bank partnership: Education data system reforms yield high long‑term returns but require sustained investment. Collaboration with the World Bank has been key to maintaining momentum and aligning incentives. This partnership should be deepened as part of our broader TA portfolio in order to continue system‑strengthening. (DARE SRO and GOAL PRO, by May 2026)
2. PIE Future & Sustainability: FCDO, the World Bank, and MoFEPT should jointly agree and deliver a “PIE Autonomy Package” consisting of a fully approved organogram, resourcing plan, and a three‑year budget line, alongside a clear governance and data‑access framework to ensure PIE remains operational and effective after DARE support ends, and that critical deliverables remain on track (e.g., the National Achievement Test, National Open Data Portal, continued implementation Data Standardisation) (DARE SRO; by June 2026)
TFP & ITA:
1. TFP, comparability & VfM analytics TFP should produce a full LAYS/micro‑LAYS conversion and a cost‑effectiveness analysis that excludes costs that would not fall on government at scale, resulting in transparent, comparable metrics that respond directly to FCDO’s recommendations. (TFP with DARE‑RC/WWHGE, by June 2026)
2. TFP closure, TFP should complete all close‑out requirements - asset disposition, SEAH attestations, data archiving, and a lessons paper on options for a lower‑cost TFP‑lite model - to protect value for money and ensure knowledge transfer beyond the AGA period. (FCDO PRO, by June 2026)
3. ITA, Positioning ASER within the system, FCDO should broker a Letter of Cooperation between PIE, PBS and ITA clarifying complementarities between ASER and government assessments, agreeing shared metadata and disaggregation standards, and specifying terms for open‑data handover to NODP to strengthen ASER’s legitimacy and system alignment. (FCDO PRO; by June 2026)
4. ITA closure: ITA should finalise all pending deliverables, complete asset verification and disposition, provide SEAH compliance attestations, and close the financial and audit trail in alignment with FCDO due diligence and programme closure requirements. (FCDO PRO, by March 2026)
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
1. During the previous AR period, the ToC was reviewed and is summarised in Annex 2.
2. For this reporting period, the programme is partially on track against the Impact Indicator – DARE is achieving impact at the eco-system level (supporting increased alignment between elements, e.g., assessments and data), but uptake and use of evidence is a longer-term objectives that should be part of the wider objective of future FCDO education portfolio as we transition to bigger focus on politically informed TA with a focus on evidence.
  IMPACT: an education system more aligned towards and cohesive around the objective of improved student learning outcomes; and which is informed by better quality data and driven by quality research evidence. System coherence for learning involves alignment of the relationships (accountability between different actors: teachers, parents, politicians) and elements (curriculum, assessment, and pedagogy) around learning objectives in order to achieve learning.
3. Outcome 1 - Off-Track. We measure this outcome through the regularity and timeliness of data, availability of raw/open access data, and the operational functionality of the Pakistan Institute for Education (PIE) as the national-level custodian of education data. Overall, significant delays and staffing issues are impeding the achievement of the 2025 milestones for outcome 1. Most notably, PIE is not fully operational, with only partial approval of its organogram by the Finance Division. Key technical and administrative positions remain unfilled, hindering effective operations.
  Outcome 1: (a) Pakistan has a strengthened national education data system, in which quality data is produced by government, made publicly available and (b) is used by government at provincial and federal levels and by non-government stakeholders to improve education provision and resource targeting, and to drive continuous improvement.
4. Outcome 2 - On-Track: This outcome focuses on increasing the demand for, access to, and understanding of education evidence by policymakers. Overall, the DARE programme is making good progress in enhancing the use of education evidence to inform policy and practice in Pakistan. DARE‑RC is on track to deliver meaningful impact, with most studies expected to achieve conceptual influence through systematic sharing of findings with government, development partners, academia, and civil society. Instrumental impact - direct effects on policy or programme decisions - is likely to remain limited within the programme timeframe (15–20% of studies) given the short implementation window and the mismatch between research and policy cycles.
  Outcome 2: More rigorous and publicly available research into which innovations work to accelerate learning in– and out of schools (esp girls & marginalised) generated through a strengthened Pakistani education research community and put into the hands of policy makers.
5. Outcome 3 [closed]. This outcome was tracked by looking at whether Education Management Information System (EMIS) data are routinely presented to and used by Education in Emergencies Cluster group to respond to crises. This outcome was tracking our flood response and is no longer active.
  Outcome 3: Pakistan's education system's ability to respond to the coronavirus pandemic and other crises is strengthened.
6. The Theory of Change holds. DARE’s focus on systems strengthening continues to align with the Country Business Plan.
  Figure 1 the Wheel of Impact from The Impact Initiative for International Development Research
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
1. This is DARE’s last implementation year. The programme should continue and it is on track to deliver all its outputs by the end date. The programme has made significant progress in strengthening the education data system, and our decade-long research[12] shows that such work is critical for driving systems coherence, improving learning and building accountable social service delivery funded by government’s own resources. In spite of the market challenges, the programme has also built a diverse research portfolio that will have a profound impact on reform efforts with the right uptake. At portfolio-level, DARE’s research is responsive to government’s expectations and FCDO’s evolving education strategy, thus providing us with flexible TA.
  [12] Focus to Flourish: A Messaging Campaign on Five Actions to Accelerate Progress in Learning | RISE Programme
2. DARE delivers strong value for money by producing high‑quality public goods - standardised data, robust research, and strengthened institutional capability leading to improved planning and contribute to better learning outcomes. The programme has demonstrated clear effectiveness through DSF 2.0 adoption, a substantial research pipeline, and proven learning gains of 6–10 months from TFP. Efficiency and economy were enhanced through methodological standardisation, avoidance of duplication with major partners, and significant cost savings in research procurement and delivery. Equity remains central, with all studies disaggregating data for marginalised groups and prioritising inclusion, supported by strong female participation across research and data collection.
## C. DETAILED OUTPUT SCORING
Output Title	National education data systems are strengthened through improved data management processes and enhanced coordination. The regular and robust monitoring and evaluation of increased administrative and learning data informs decision making.
Output number:		1	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1. Provincial-Federal Data Management processes are strengthened	4 targets including: / Align Annual School Census 2025 (ASC) tools with the updated DSF by November 2025 for nationwide implementation across all provinces. / Update 5 detailed provincial Plans of Action for horizontal (national/provincial) DSF integration, including clear timelines for integrating existing digital data across departments. / Review and update 5 data access protocols (federal and provincial) with inputs from provincial departments to enable efficient data exchange at all levels / Conduct 2 EMIS Technical Working Group (TWG) sessions as a platform for inter-provincial learning, expanding scope to engage Development Partners for improved coordination.	Met - DSF was revised and updated to DSF 2.0, and the ASC tools have been aligned with DSF 2.0. / Partially met – Updates completed in Sindh, KP and Punjab. No work undertaken in Balochistan as their legacy system is being replaced. / Partially met – Updates completed in Sindh, KP and Punjab. No work undertaken in Balochistan as their legacy system is being replaced. / Met – Sessions held on 11-12 August led by GoP
1.2. Education sector level coordination and cooperation is enhanced across Pakistan.	7 targets including: / Complete baseline capacity assessment of PIE’s National Assessment Wing (NAW) / Complete the pilot for the National Achievement Test (NAT) 2026 / Develop National foundational learning Benchmarks for Grade 3 and complete the pilot of the Foundational Learning Assessment. / Support the development of Foundational Learning policy delivery plans, a structured pedagogy package, and the Foundational Learning Assessment Framework. / Initiate provincial engagement on aligning Large-Scale Assessments (LSA) with NAT / Conclude 2-years support to FLN Hub and handover the Hub to the Federal Government as per the agreement between BHC and the Federal Government. / Complete and publish 2 policy-relevant studies. (Devolution and Learning Losses)	Met – The capacity assessment completed. / Met – All preparations completed. The pilot took place in May 2025. / Met – The National Benchmarks were completed and piloted in November 2025. / Met – Delivery plans were developed for each of the provincially notified Foundational Learning Policies. / Met – Provincial engagement has been initiated. / Partially met – Support to the Hub concluded in Sep 2025 but no government funding was committed. / Unmet – The two studies have not been finalised
1.3. Education sector level Monitoring, Evaluation, and Decision Making improves leading to increased use of data for equitable resource distribution	3 targets including: / Private School Survey - Finalise sample calculation, obtain clearance for survey. Complete Phase 1 & start Phase 2. / eLearning Modules developed to enhance PIE's capacity / Support the design of the Out of School Children Challenge Fund	Partially met – Sample calculation is completed, but deployment (phase 1 and 2) is delayed. / Met – Two new courses developed. / Met - This Fund will lay the foundation for transfer-based grants to the most lagging districts.

Briefly describe the output’s activities and provide supporting narrative for the score.

The output received an overall score of A, with performance assessed against 14 milestones: 9 were fully met, 4 were partially met, and 1 was not met. In spite of unmet targets, we judge the progress to be satisfactory and expect all activities to be met during this coming reporting period. The output is delivered through the DARE Trust Fund (TF) with the World Bank. The TF provides technical assistance to strengthen the education data ecosystem (e.g., to track numbers of out of school children, and levels of learning) and promote federal-provincial coordination on policy and implementation. The TF works in tandem with the World Bank’s Actions to Strengthen Performance for Inclusive and Responsive Education Program (ASPIRE) (US$200 million, part of larger pre-CPF $1.2 Billion WB education portfolio in Pakistan).

  1. Provincial-Federal Data Management processes are strengthened (4 targets):

1. The objective of this indicator is to ensure the implementation of a consolidated national education data regime at federal and provincial levels (as agreed in the Data Standardisation Framework, DSF – which was approved at the Inter-Provincial Education Ministerial Conference in 2023). Out of 4 targets, 2 were met, 2 were partially met.
2. Since its inception, DARE TF has been supporting the harmonisation of education data systems in Pakistan through a complex web of activities at provincial and national level involving a myriad of actors in the provinces, especially the education management information system (EMIS) teams.
3. Central to this effort is the Data Standardisation Framework (DSF). During this reporting period, the TA supported the revision of the DSF to version 2.0 with provincial consensus resolving, during a 2-day technical reviews session, many ambiguities identified in the original DSF[13].The TA also supported PIE for the third year to develop the national Annual School Census (ASC) guidance document aligned with DSF 2.0. As noted last year, this progress helps move Pakistan closer towards generating more robust and comparable education sector data through a third round of the ASC. Using DSF for the first time, the most recent Pakistan Education Statistics report (2023-2024), which was unmet target during last year AR, was published by PIE in April 2025, featuring improved data visualization and guided by the DSF for the first time.
  [13] This included the definitions of indicators and terms that required provincial-level interpretation to ensure consistency in national reporting.
4. In the long journey towards harmonisation of the education data in Pakistan, the provinces will need to achieve horizontal integration of data systems between their myriad departments. They will also need to have data access protocols that would allow of interoperability of data within and across the provinces and the federal government. Work on both fronts have been going on for many years supported by DARE TF, and the culmination of this work will be the creation of a National Open Data Portal (NODP).
5. NODP will provide transparent provincial and national education data. Last AR covered the technical updates including the procurement process for the NODP. During this reporting period, further TA was provided to PIE for its completion of the first phase of the NODP — in collaboration with the provinces — following the vertical integration of provincial educational databases with the national system.

1.2. Education sector coordination and cooperation is enhanced across Pakistan (7 targets)
1. This output responds to the weak sector coordination mechanisms between the provinces and the federal government, addressed through four areas of work[14]: getting PIE operational, producing a national assessment framework, assisting Pakistan to participate in international assessment, and producing federal coordination guidelines on national education policy issues. Out of 7 targets, 5 were met, 1 not met, and 1 partially met.
  [14] As per the Theory of Change of the World Bank Trust Fund for DARE.
2. Getting PIE operational helps ensure the availability, quality and comparability of national and provincial learning data. As the DARE TF TA support wraps up in 2026, an endline capacity assessment of PIE’s National Assessment Wing (NAW) and to a lesser extent Management Information Wing (MIW) took place. The assessment is ongoing focused on 12 domains (e.g., DSF, open access, data governance & transparency, etc), 64 capability functions (e.g. data analysis). Initial results (pending verification via interviews) showed that out of the 64, PIE staff showed high capability in 10, moderate 15 and low in 39 functions. While remedial trainings were put in place, complementing training provided in previous years, this shows that PIE will continue to struggle unless it attracts and keeps the right skillset.
3. One example of PIE’s centrality in the data ecosystem in Pakistan is the National Achievement Test (NAT)[15]. As a large-scale assessment[16], NAT helps the government assess proficiency levels and generate nationally comparable data. DARE has so far supported three cycles of NAT: 1) a quality review of NAT 2019; 2) capacity building for government implementation of NAT 2023 (both covered in previous ARs), and in alignment and dialogue with UNESCO Institute of Statistics (UIS), DARE has been providing ongoing support for NAT 2026.
  [15] The National Achievement Test (NAT) is government organised, sampled-based assessment that tests grade 4 and grade 8 students in English, Urdu, Sindhi, Maths, and Science.
  [16] Large-scale assessments are system-level assessments that provide a snapshot of learning achievement for a given group of learners in a given year and in a limited number of domains.
4. NAT should run every two years. After a delay in 2025 (as reported in last AR), all preparations for NAT 2026 and its pilot have been completed. NAT 2026 will include two innovations 1) the inclusion of private schools, 2) a focus on foundational learning. The determination of the NAT large-scale sample size assigned 120 schools for each province, divided equally between 60 public and 60 private institutions. Analysis of the data from the pilot also informed a revision of the sample size calculations for the large-scale NAT.
5. NAT 2026, for the first time, will include a National Foundational Learning Benchmarks. This will serve as the blueprint for foundational learning to be fully part of the NAT in future years allowing Pakistan to move towards reporting against SDG 4.1.1.a[17] in line with UNESCO Institute of Statistics (UIS)[18] requirements and for Pakistan to meet UIS technical criteria for international reporting against SDG 4.1.1.b[19] and understand progress towards SGD4 by 2030. In November, a total of 360 Test Administrators conducted the pilot National Foundational Learning Study (NFLS) data collection across 90 schools representing English, Urdu, and Sindhi mediums of instruction (30 schools each).
  [17] SDG 4.1.1.a is the global indicator referring to the proportion of children and young people in Grade 2 or 3 achieving at least a minimum proficiency level in (i) reading and (ii) mathematics, by sex.
  [18] UNESCO Institute for Statistics (UIS) is the statistical office of UNESCO and is the UN depository for cross-nationally comparable statistics on education, science and technology, culture, and communication.
  [19] Global indicator 4.1.1b refers to the “proportion of children and young people at the end of primary education achieving at least a minimum proficiency level in (i) reading and (ii) mathematics, by sex”
6. Furthermore, during this AR period, as part of NAT 2026 preparations, discussions with the provinces have been initiated to start the process of aligning their assessments with NAT 2026 as this NAT is planned to be a large-scale assessment (LSA) that will allow Pakistan to systematically measure learning poverty rates and report them against SDG 4.1.1 b and c[20]
  [20] SDG 4.1.1.b and c are the global indicators referring to the proportion of children and young people at the end of primary (b); and at the end of lower secondary (c), achieving at least a minimum proficiency level in (i) reading and (ii) mathematics, by sex.
7. In addition to harmonising assessments, the provinces should continue to drive the implementation of the Foundational Learning Policies they had notified. Delivery plans were developed for each of the provincially notified Foundational Learning Policies through a province-specific consultative process. The plans outline the specific actions, resources, and timelines needed to implement a policy and achieve its intended outcomes. Technical support was provided for the identification and mapping of teaching and learning materials, alongside recommendations for resources to improve FL in Pakistan.
8. Foundational Learning Policies would not have been possible without the Pakistan Foundational Learning Hub (PFLH), which was established in September 2024 through an agreement between the British High Commission in Pakistan and the Federal Ministry of Education. The Hub was an outcome of the Pakistan Learning Conference 2023 in which the Government of Pakistan reaffirmed its commitment to bold action on foundational learning. Our objective was for the Hub to transition into a dedicated, government-funded unit, providing a mechanism through which federal and provincial ministries can drive measurable improvements in foundational literacy and numeracy (FLN) as a national priority. The most notable achievement of the Hub is supporting all of the provinces to develop foundational learning policies which have been approved and notified in all provinces. However, the focus must shift to effective implementation, continuous tracking, and timely course correction.
9. Under this output, the TF commissioned two research studies that address issue related to the focus of this output including understanding the impact of the 18th Amendment — devolution — and how it has influenced service delivery, accountability, and equity in education. As noted in last year AR, this study has evolved and is now much more comprehensive with additional financing from the WB. It was not completed by May 2025 as originally envisaged (by Tabadlab) – completion date May 2026. The second study analyses the COVID-19 pandemic’s effects on learning outcomes in rural Punjab, highlighting income shocks as a significant factor in widening educational inequalities (by Panoma College) – completion date TBC.
1.3. Education sector level Monitoring, Evaluation, and Decision Making improves leading to increased use of data for equitable resource distribution (3 targets).
1. This output indicator aims to improve decision-making by using evidence and data produced under the previous two indicators as well as generating responsive evidence. Out of 3 targets, 1 partially met and 2 met.
2. The Private School Survey (PSS): Although approximately 40% of children in Pakistan (around 19.5 million[21]) attend some form of private school, there is limited reliable information on their learning levels and school environments. PPS is a sample-based exercise designed to generate essential data on the characteristics of Pakistan’s private education sector and identify‑ opportunities to better leverage it. During this AR period, the data collection‑ firm was onboarded and developed a robust national sampling frame, and the final sample size has now been agreed[22]. The lack of updated and complete national or provincial registry of private schools slowed down progress. As a result, the survey timeline slipped by four months. Full deployment is now planned for January 2026.
  [21] Ibid 7.
  [22] The sampling process presented all sorts of complications. Following a pilot field check to compare school locations scraped from the web with their actual physical locations revealed major discrepancies and showed that online data alone is insufficient and unreliable. The field check also highlighted the diversity of private schools across different settlement types, reinforcing the need for a more accurate and nuanced sampling strategy.
3. Capacity Building for PIE: Online Courses and Knowledge Retention: More broadly, to ensure sustainability of our TA to PIE, two courses were developed during this AR period to strengthen the skills of the staff of PIE and provincial education departments, and to support knowledge retention following the completion of our TA – started in 2020. They provide accessible and flexible learning opportunities. The courses, available on PIE website, will help staff produce two key publications (Pakistan Education Statistics, Public Financing in Education Report). These courses are available online on PIE portal.
4. Out of School Children Challenge Fund (OOSCCF): Design of a Results Based Financing Mechanism: A contribution from DARE TF has supported the design of the Out of School Children Challenge Fund (OOSC-CF) which will be a federal-to-provincial results-based financing mechanism that channels performance-linked resources toward verified education outcomes. It will aim to reward progress in access, equity, and quality, ensuring that efforts to reach OOSC children translate into measurable improvements in learning and sustained education outcomes. An expert firm was hired in November 2025 and will provide TA to support the design of the OOSC CF's strategic architecture, incentive and verification framework, governance, and capacity-building arrangements. Total value of the fund will be PKR 25 billion (approximately £65.6 million). BHC is a member of the technical working group.
Significant challenges, issues or underperformance:
The future and sustainability of PIE remain an issue. As noted in the last AR, the proposed organogram was only partially approved by the Finance Division and did not, in the first place, respond to existing and anticipated needs of the newly established institution. Key positions[23] are yet to be filled for effective operationalisation of PIE. With the conclusion of our TA by September 2026, there’s a risk that key areas of work might either stop or be understaffed.
[23] These include but are not limited to technical experts to manage standardised data across provinces and the NODP, psychometricians and strategic leads for the National Assessment Wing, deputy to the DG PIE, and positions within the Research Wing

Describe any changes to this output during the past year, and any planned changes as a result of this review.
No future changes to the output as this is the last year of the agreement.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress: Progress on recommendations can be found in Annex A.
Recommendations:
1. Sustainability and institutionalisation of the TA provided to PIE since 2020 is dependent on good documentation of all TA activities: While the online courses (paragraph 59) provide some documentation, a Manual for Replication with clear costing might be necessary. This Manual should include roles and responsibilities, costing of activities, and timelines with clear tasking. (FCDO SRO and World Bank, by June 2026)
2. Private School Survey – accelerate and launch without further delay: The Private School Survey remains four months behind schedule, with Phase 1 and 2 still not deployed despite a completed sampling frame. The World Bank should finalise remaining operational steps and initiate fieldwork immediately to avoid further slippage.
   (World Bank & FCDO PRO – by May 2026)
3. Finalise and release pending research (Devolution & COVID19 studies): The Devolution/18th Amendment study and the COVID19 learning loss study remain overdue for the second consecutive year and must be completed, shared and published as soon as possible to meet output requirements and inform policy dialogue.
   (World Bank & FCDO SRO – by June 2026)
Output Title	Comparable, independent, representative and reliable education data is produced by civil society.
Output number:		2	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2. Improved access to and availability of disaggregated data on marginalised children's access to school and learning outcomes, including: / (i) children living in informal urban settlements and / (ii) children with disabilities	ASER methodology approved and endorsed by key stakeholders (PIE, Pakistan Bureau of Statistics and FCDO) incorporating third party/external recommendations. / ASER 2025-26 survey draft report completed in all districts/primary sampling[24] units including using digital tools with GPS tracking. / Baseline political constituency report finalised, (a). with 8 report cards developed and disseminated to stakeholders in consultation with Election Commission of Pakistan (ECP) and parliamentarians through at least (b) 8 constituency-level dialogues to promote accountability and action on foundational learning. / ASER data and thematic briefs cited in (a). 3 national or provincial education policy documents, sector plans, or official statements, (b). and used to inform planning or advocacy by at least 5 government or civil society stakeholders.	2.1. Met -The ASER 2025 methodology was jointly reviewed and finalised with the Pakistan Institute of Education (PIE) and Pakistan Bureau of Statistics (PBS). / 2.2. Met - Data collection was completed across all 158 districts and 6,681 sampling blocks. / 2.3. Met - The Baseline Political Constituency Report covering 8 constituencies is completed with constituency specific report cards produced and disseminated. 8 dialogues were held with elected parliamentarians, district actors and ECP focal persons. / Partially met - ASER data was widely used and cited, but documentation is insufficient to confirm use by five or more distinct actors, so the full milestone cannot be verified.
[24] Disaggregated data collected for gender, disability, and informal urban/rural settlements and integrate WHO/UNICEF.

Briefly describe the output’s activities and provide supporting narrative for the score.
1. This output tracks the delivery of high quality, independent and representative education data produced by civil society to complement government data systems and strengthen accountability. During this review period, ASER/ITA made substantial progress against three of its four annual milestones, with strong achievements in methodology endorsement, national data collection, digital transformation, and political economy engagement. Overall performance demonstrated improved credibility, technical quality and policy relevance of ASER, warranting an overall score of A.
2. Output 2.1: ASER successfully implemented a strengthened and jointly endorsed 2025-26 methodology, developed through technical engagement with the Pakistan Institute of Education (PIE), Pakistan Bureau of Statistics (PBS) and FCDO. The revised methodology incorporates external recommendations, expands sampling rigour to produce a unified rural–urban national sample for the first time, and enhances comparability through the adoption of aligned global frameworks. The formal endorsement, especially by PBS and PIE, marks a significant step in institutional legitimacy and helps embed ASER more firmly in Pakistan’s wider assessment ecosystem.
3. Output 2.2: ASER completed data collection across all sampled districts and primary sampling units using a fully upgraded digital data collection platform with GPS tracking. This cycle introduced improved digital tools, refined assessment instruments, upgraded household/school questionnaires and enhanced oversight mechanisms. The draft report consolidates fully disaggregated data on gender, disability (using WHO/UNICEF aligned tools), and informal urban settlements—including katchi abadis (e.g. slums, informal settlements) —thereby offering a more granular picture of foundational learning inequities across Pakistan.
4. Output 2.3: the Baseline Political Constituency Report was finalised, and eight detailed constituency report cards were produced and disseminated. ITA convened eight constituency level dialogues with parliamentarians, district officials and the Election Commission of Pakistan (ECP) to promote political accountability for foundational learning. These engagements generated explicit commitments on teacher deployment, girls’ enrolment, school infrastructure and constituency level education planning. This political economy approach strengthens ASER’s influence and improves the enabling environment for evidence informed policymaking. Our funding has only covered the baseline. The plan is to track commitment through a mid and endline.
5. Output 2.4: While ASER’s data and thematic briefs were referenced in several public forums and integrated into multiple national and provincial discussions, documented evidence of use by five or more stakeholders fell slightly short of expectation. The programme met the requirement for at least three policy citations but was not fully able to demonstrate verified uptake by the minimum number of government or civil society actors. This highlights the need for improved tracking and intentional engagement strategies.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

No future changes to the output as this is the last year of the agreement.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress:
Good progress was made across most recommendations from the previous Annual Review. Details in Annex A.
Recommendations:
1. ITA closure: as the ITA grant ends in March 2026, ITA should complete all remaining close‑out requirements, including asset verification, SEAH attestations, data archiving, and full financial and audit closure. This ensures compliance with FCDO due‑diligence and smooth programme closure. (FCDO PRO, March 2026)
2. ASER Sustainability & Funding Diversification: ITA should continue to strengthen ASER’s sustainability by advancing its fundraising strategy and pursuing diversified financing sources. With long‑standing UK support ending and ASER’s national role expanding, ITA must secure multi‑partner funding to maintain the survey’s independence and technical quality. (FCDO PRO, March 2026)
Lessons learnt:
Institutional endorsement strengthens credibility and uptake
Co‑ownership of methodology with PIE and PBS substantially improved government recognition of ASER as a credible data source, demonstrating the value of multi‑stakeholder alignment.
Output Title	Evidence on what works to improve education service delivery in Pakistan produced and synthesised
Output number:		3	Output Score:	A
Impact weighting (%):		50%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1. Number of consortium-led (CL) and grant-funded research studies initiated and completed in line with the research agenda[25]	Consortium-led (CL): All inception reports of 12 CL studies completed and approved; 8 CL studies mid-term review reports completed and approved; 2 consortium-led research studies completed. / Grants: 10 research studies commissioned through grant fund; 13 grant inception reports completed and approved; 2 grant mid-term reports completed and approved.	Exceeded – All CL studies 12 have completed their inception reports, 8 completed the midterm report, 4 studies have been finalised. / Met – 10 commissioned (Cycle 2). 13 inception reports completed and approved. Midterm 2 completed and approved (Cycle 1). Call 2 received 191 studies and 10 were commissioned. This brings the total of active studies to 30.
3.2. Number of implementation pilot to scale initiatives on teaching and learning supported and researched or number of scalability research studies	Progress report for 1 implementation pilot-to-scale initiative (on Student Cohort 1) completed. / 4 research studies on scalability finalised and approved. 4 inception reports completed and approved.	Met – 1 Pilot was initiated and is in implementation. Progress report for cohort 1 has been received and approved. 4 research studies finalised, approved, and contracted. Inception reports for all studies
3.3. Number of synthesis products/working papers produced, address critical evidence gaps & aligned with government priorities.	5 scoping papers commissioned and completed	Met – All 5 papers, which were commissioned last year, have been completed and presented to FCDO
3.4. Number of DARE-RC studies submitted to international conferences, accepted and presented	5 proposals submitted for conferences taking place in 2025, at least 50% accepted, and presented.	Exceeded – 5 proposals were submitted, and 3 (60%) were accepted and presented in the UK, Botswana and the US
3.5. Research Interest Groups established and convened quarterly meetings around DARE-RC themes	4 research interest groups established. 2 meetings per group held (total 8 meetings)	Met – 4 research interest groups established, and 8 total meetings held.
3.6. Number of education research users (federal and provincial governments) participating in capacity strengthening activities and reporting satisfaction with the activities[26]	On average, at least 15 research users reporting 85% satisfaction with capacity strengthening activities and benefitting from 16 workshop hours	Met – Cumulative Satisfaction Rate: 86%.
3.7. Number of DARE-RC engagement events held disaggregated by type of event	A total of 13 events, including 8 policy engagement[27] events, 1 research symposium, 4 webinars	Exceeded – a total of 20 events were organised.
3.8. 1 annual conference held to discuss/disseminate DARE-RC research	1 annual conference held	Met – the Summit was held in early December 2025.
3.9. Evidence of collaboration on research and evidence uptake with other FCDO supported programmes (GOAL, B-TAG, WWHGE) and other development partners	At least 2 collaborations identified through consultative meetings with FCDO supported programmes and development partners	Met – engaging with both bilateral, CMPs and other multilaterals took place leading to effective exchanges.
[25] Disaggregated by i) gender (proportion of women as Principal Investigator) ii) location of the study (province), iii) studies using disaggregated data by gender, disability, or other marginalisation indicator.
[26] Disaggregated by type of capacity strengthening activity, type of participant and gender) Satisfaction to be captured on a 1-5 scale
[27] Including (Provincial roundtable/Policy Exchanges, Thematic discussion/dialogue, bilateral consultation and briefings, Study specific events and engagement, policy dialogues)

Briefly describe the output’s activities and provide supporting narrative for the score.
1. This output covers the commercial contract we have with OPM. The output has scored an A. Out of 9 milestones, 3 exceeded and 6 met expectations.
2. Indicator 3.1 covers the entire portfolio of research commissioned throughout the lifetime of the programme (total of 30 studies, in addition to 4 Pilot to Scale Studies covered in output 3.2). By December 2025, the DARERC portfolio comprised 30 active studies across consortium‑ led research and grant‑ funded‑ cycles 1–3. OPM reporting provided strong assurance on quality and alignment with our expectations. 100% of studies use disaggregated data (gender, disability, or other marginalisation). 65% of studies led by women Principal Investigators (PIs) (19 of 30 studies). All completed studies met quality thresholds for publication, with a Special Issue accepted by an international education journal, and 13 studies accepted to CIES[28] 2026 Conference in March.
  [28] The Comparative and International Education Society is the largest and oldest of 47 comparative and international education societies around the world
3. Indicator 3.2 aims to identify and research promising interventions. It will constitute 40% of the total of RC budget (roughly £3.6m million). As noted in the previous AR, following the onboarding of the new Research Director, FCDO and OPM agreed that we will achieve more impact by focusing on what has already gone to scale instead of funding new pilots. We have therefore focused our resources on research and for scaling of the ongoing pilots. Cycle 3 invited research proposals looking at what works in scaling effective education reform interventions (including the 3 identified by DARE-RC). In addition to one pilot where we are funding both implementation and research, we have identified four scalability studies.
4. Indicator 3.3, like 3.1, aims to build a rigorous body of evidence but primarily focuses on being responsive and demand driven. DARE-RC identifies policy-relevant synthesis products and working papers that address critical evidence gaps in education and can be produced rapidly to seize ‘widows of opportunity’ or capitalise on the interest and attention of policymakers. For example, the RC completed a Scoping Paper on the Government of Punjab’s Policy of Outsourcing Public-Sector Schools under the Public Schools Reorganisation Programme (PSRP), which aims to outsource 13,000 out of 49,000 public schools to private operators to address issues like low enrolment, poor quality, and inefficient management.
5. Output 3.4, DARE-RC researchers presented and participated in major international education conferences in 2025, including CIES in the U.S (March), UKFIET in the UK and the Eleventh Pan-Commonwealth Forum on Open Learning (PCF11) in Botswana (both in September).
6. Output 3.5 aims to build a community of practice to discuss and document emerging findings in the thematic areas of the Research Consortium.
7. Output 3.6 aims to build the capacity of users and producers of research with the assumption that both supply and demand are important for evidence uptake. While good progress took place in previous years, evidence showed lack of uptake and impact at scale. During this AR period, the final set of workshops were delivered targeting 13 officials from PIE and 29 Senior Civil Servants from the National Institute of Management.
8. Output 3.7: During 2025, the programme delivered 20 engagement events to support research uptake across federal and provincial systems. These included 13 policy engagement events, notably eight policy roundtables held with PIE, Durbeen, Lahore University of Management Sciences (LUMS), and provincial governments in Khyber Pakhtunkhwa, Sindh, and Balochistan. Engagement was reinforced through bilateral consultations with provincial and federal governments, alongside study specific consultations led by the University of Oxford and individual research teams. Knowledge exchange was further supported through a national research symposium and four webinars, strengthening sustained dialogue between researchers, policymakers, and practitioners.
9. Output 3.8 focuses on strengthening coherence across FCDO education programmes by improving coordination and shared learning. In 2025, DARE RC deepened collaboration with WWHGE, PIE and projects such as ILMpact, GOAL and BTAG, resulting in targeted alignment efforts and joint knowledge sharing, including WWHGE and EdTech Hub contributions at the DARE RC Annual Summit. Engagement with the World Bank also helped avoid duplicative research in Balochistan, where a $100m WB investment already covers research needs.
Impact story: Government Uptake of Research to Improve SLO Implementation in KP / Research led by Dr Aliya Khalid (University of Oxford, Department of Education), in partnership with Institute of Education in Peshawar, directly informed government action in KP. At the request of the Secretary Elementary and Secondary Education Department (ESED), the study led to the development of Student Learning Outcomes (SLO) based teaching and assessment resources for Grades 9 and 10 across eight subjects, now being converted into offline video lessons for province-wide teacher access. This pilot demonstrates early system uptake of research, with potential for scale-up through the Directorate of Professional Development to benefit 767,249[29] students students in Grades 9 and 10.
[29] This figure might change depending on whether the intervention is scaled up to both public and private schools.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
As reported in last year AR, we continued with two changes to the activities of the programme:

1. Change of approach to output 3.2 (Pilot to Scale): Except for one pilot (Teaching at the Right Level), we chose not to fund implementation of the pilots and instead focused the resources on research on and for scaling by inviting the research and practice community in Pakistan to propose studies on successful interventions that have gone to scale within the government systems.
2. Discontinued activities (output 3.6): The capacity building component was discontinued after implementation challenges, including lower than expected participant capacity, inconsistent attendance, and difficulties in measuring outcomes. Despite proposing stronger measurement tools, the need to focus on the delayed work of the research component and limited feasibility led FCDO and OPM to jointly conclude the component after completing activities with PIE, with no further rollout to universities. Indicator 3.6 reflects the closure of these activities.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress: Details in Annex A.
Recommendations:
Prioritise timely completion and publication of all research products in 2026. Given publication risks highlighted this year — including the likelihood that the Special Issue and multiple studies may not be completed within the programme period — OPM should front‑load review, editing and submission processes and activate alternative publication routes where journal timelines are too slow. Timely publication is essential to protect policy impact and ensure a complete evidence package before programme closure (FCDO SRO, June 2026)
Lessons learnt:
OPM has considered the need to assess PIE’s absorption capacity, and as noted in paragraph 64, the activity was discontinued following completion of the initial plan, thereby avoiding duplication with the Trust Fund.

Output Title	Improved learning outcomes through innovative education practices (TFP)
Output number:		4	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1. Number of total teachers/fellows trained to be placed in public schools (disaggregated by gender) (cumulative)	150 teachers/fellows / 60% female fellows / 40% male fellows / 70% Islamabad and 30% Karachi.	Exceeded – 175[30] in October - 70% in Islamabad & 30% in Karachi. 67% females, 33% males
4.2. Number of students reached[31] with improved teaching methods	Total:10,000 / Girls: 60% / Children with disabilities: 6% using Washington Group questions.	Exceeded – Total: 12,500 (61% girls, and 22% children with disabilities[32])
4.3. Student learning outcomes improved in: / (i) Maths (%) / (ii) English (%)[33]	i) Average mastery of TFP students in English- 30% / (ii) Average mastery of TFP students in Math - 30% / (iii) Students taught by TFP make 5 months of greater learning gains in one academic cycle than their peers taught by government teachers	Exceeded – (i) Average mastery of TFP students in English - 42%[34] (ii) Average mastery of TFP students in Math - 38%[35] (iii) RAND independent evaluation showed that TFP taught students achieved between 6-10 months of additional learning in Math and English.
4.4. Evidence of Teach for Pakistan's approach to teacher recruitment and development being adopted by governments (federal or provincial)	At least two policy changes or programmes influenced by TFP approach	Partially met – limited evidence that TFP model is being adopted at scale by the government. Some evidence of ongoing partnership discussions with government, and that TFP’s fellows are sought after by organisations working on Teacher Professional Development.
[30] Islamabad (2024: 57 & 2025: 68), Karachi (2024: 22 & 2025: 31) – 3 fellows (out 178) dropped off by December 2025.
[31] Disaggregated by gender and disability status, using the Washington Group set of question
[32] Teach For Pakistan disability survey 2024-25 using the Washington Group Short Set on Functioning (WG-SS). A person is considered to be ‘with disability’ if they have A LOT OF DIFFICULTY or CANNOT DO AT ALL in any one domain (Vision, Hearing, Mobility, Cognition, Selfcare, and Communication).
[33] The figures in the milestone column refer to average grade level mastery percentages attained in Summative assessments). Improvement in student academic achievement is greater in TFP classrooms than in non-TFP classrooms, based on months of additional learning
[34] 2024 Cohort Year 1 for both Math and English
[35] 2024 Cohort Year 1 for both Math and English

Briefly describe the output’s activities and provide supporting narrative for the score
1. The purpose of this agreement is to help TFP recruit, train and support a total of 416 Teaching Fellows to effectively teach 21,000+ students in Islamabad and Karachi. This has been co-financed with the Federal Directorate for Education (FDE) up until June 2025. FDE did not renew its funding. But TFP was able to continue its operations in 2025.
2. Indicator 4.1: During this reporting period, TFP completed the recruitment for the 2026 cohort, with 5,873 completed applications received in two recruitment cycles, 1,822 were shortlisted, 584 attended interviews, 153 offers were made and 126 accepted. The overall selection rate was approximately 2.6%. This reflects the competitive and rigorous selection process TFP follows. In terms of previous cohorts, 50 Fellows from 2023 Cohort graduated during this reporting period (out of 68 selected), and from 2024, 81 Fellows moved into Year 2 of the Fellowship (out of 97 Selected). The total number of Fellows placed throughout the agreement is 474 (since 2021 including 2020 second year Fellows), and 206 have completed the programme (excluding currently teaching 2024 and 2025 Cohort's Fellows). Therefore, the completion rate is 75% excluding currently teaching 199 Fellows from 2024 and 2025 Cohorts.
3. Indicator 4.2: During 2025, Fellows taught 31,000 students (including 12,500 reached this year) across 97 schools with 22%of students having disabilities.
4. Indicator 4.3: TFP successfully exceeded its learning targets for the year[36]. The average mastery of TFP students in English and Math improved significantly. These results demonstrate TFP's effective implementation of improved teaching methods and the positive impact of their Fellows on student learning outcomes. These results are consistent with the findings of the independent RAND evaluation, which found that compared to students taught by non‑TFP (government) teachers, students in TFP achieved 0.26 Standard Deviation[37] (SD) ≈ 8–10 months additional learning in Math, and 0.15 SD ≈ 6 months additional learning in English.
  [36] For year-on-year improvements, please see annex A.
  [37] Standard Deviation in statistics is a measure of the variability (dispersion or spread) of any set of numerical values about their arithmetic mean.
5. Indicator 4.4 captures how TFP’s teacher recruitment, development, and management model has influenced education reform, in line with the spirit of the original AGA. In Sindh, after a BDHC‑supported event, TFP submitted a Grant‑in‑Aid proposal to the Sindh Education and Literacy Department (SELD) to advocate for public investment in leadership development through the Fellowship. At the federal level, FDE has not committed further funding, though other teacher development organisations reportedly prefer hiring TFP Fellows. TFP is also diversifying funding through grants, corporate social responsibility (CSR) partnerships, and seed funding; the sustainability and system‑level integration of this model will be assessed in the Project Completion Report in March 2027.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
One output indicator (4.4) was included to capture broader impact of TFP’s model as originally envisaged in the original Accountable Grant. No future changes to the output as this is the last year of the agreement.
Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead.

Progress: Annex 1 providing detailed tracking.
Recommendations:
1. Demonstrate full V4M through clear cost per child analysis: TFP must now clearly demonstrate its V4M offer despite evidence of strong learning impact. While RAND findings showed impressive learning gains, TFP has yet to show a clear calculation for and quantified reduction in cost per child, though ongoing analysis suggests a lower true cost. (FCDO PRO, June 2026)
2. Develop robust measurement & low cost‑ delivery models for future scalability: Progress on measurement comparability improved but key outputs such as micro‑LAYS[38] and full costeffectiveness‑ metrics are still outstanding. To attract future investments, TFP needs to ensure structured testing of scalable, lowercost‑ approaches. This wont be possible in the lifetime of this agreement with FCDO – recommend tracking progress as part of the Programme Competition Report (FCDO PRO, March 2027)
  [38] LAYS, ‘Learning Adjusted Year of Schooling’ (LAYS), was introduced by the World Bank to combine access and learning outcomes into a single measure, allowing funders to compare directly across different kinds of interventions. While LAYS is a macro-measure (e.g. for cross-country comparison), a micro-LAYS is a measure for evaluation of a programme.

VALUE FOR MONEY (V4M):
1. As per the DARE Business Case, VFM is assessed using the 4Es framework, with separate indicators for data‑system strengthening and research. Effectiveness is measured through government budget allocation to data collection and analysis and improved learning outcomes attributable to evidence‑based interventions. Economy focuses on cost per student assessed or reached, and the cost of improved learning outcomes. Efficiency on progress against logframe outputs relative to budget use, and Equity on the extent to which data and research address girls and marginalised groups.
2. Spending profile: In the AR period, the total spending amounted to £4.49m: research through OPM (~65%), World Bank TA on DSF and institutional capacity (~16%), TFP (~13%), and ITA (~6%).
3. Effectiveness: DARE’s core contribution is the creation of public goods - comparable data, credible research, and institutional capability - that support better planning and learning outcomes. DSF 2.0 was completed with provincial consensus, and the Research Consortium advanced a strong pipeline of 30 active studies. The independent evaluation of TFP confirmed 6–10 months of additional learning in Maths and English, providing a strong evidence base for potential integration into public systems while ASER survey (ITA) continued to inform national indices and policy dialogue.
4. Efficiency gains were achieved by standardising definitions and methods (DSF/ASC) and reallocating a percentrage of the Grant Fund of RC budget from funding new pilots to researching what has been scaled within existing reforms. Coordination with the World Bank (and their planned $100m investment via ASPIRE[39]) avoided duplicative research in Balochistan and freed resources for targeted engagements. Under DARE‑RC, strong negotiation achieved an average saving of £60 per consultant per day and £19,308 through competitive procurement.
  [39] ASPIRE includes US$200 million, part of larger pre-CPF $1.2 Billion WB education portfolio in Pakistan
5. Economy was realised through high‑quality inputs and strong quality assurance. DSF and ASC guidance reduce future system costs, while rigorous negotiation with research grantees reduced budgets by £111,130 across Cycle 1 and £595,764 across Cycle 2. Research Consortium management costs were £75,992 (2.6% of annual expenditure). ITA’s volunteer model keeps marginal data‑collection costs low (approx. £7 per volunteer).
6. Equity is embedded across the portfolio: all DARE-RC studies use disaggregated data on gender, disability and marginalisation; most grants are led by women; and study themes prioritise inclusion (e.g., girls’ enrolment, disability, inclusive data systems, minority children’s experiences). ASER strengthens the equity lens further through disaggregated household and school data and strong participation of women volunteers (40% of volunteers are women).
Assessment of whether the programme continues to represent value for money
DARE continues to represent strong value for money, particularly over a longer time horizon. The programme has generated data, institutional capability and research that will continue to influence planning and resource allocation beyond closure, with clear signs of growing uptake at federal and provincial levels.

Recommendations:
The DARE team should maintain a streamlined VfM dashboard to track adoption and use of DSF/ASC, evidence uptake into policy actions, cost per decision‑relevant output, and improvements in equity targeting. This will allow FCDO to monitor long‑term returns, demonstrate the programme’s legacy, and guide prioritisation during the final year. (DARE SRO, Sept 2026 as part of the PCR preparations)
E: RISK
1. The programme maintained a MODERATE overall risk rating, with nine active risks managed through regular monthly and quarterly reviews in line with FCDO’s risk framework. Mitigations and escalation protocols remained effective at both FCDO and partners level, and no risks exceeded agreed appetite.
2. As the programme enters its final year, a key risk is that there is insufficient time to complete and publish the full set of DARE‑supported research outputs, including several studies and the Special Issue. Delays in publication would limit visibility, reduce potential policy influence, and weaken long‑term returns on FCDO’s investment. The team will work to mitigate this risk by prioritising essential publications and exploring mechanisms to continue dissemination support beyond programme closure.

An overview of the risks and mitigation during the review period is outlined below:
1. Strategy and Context: The Pakistan Network and DARE Risk Appetite is RECEPTIVE; Risk Rating is MAJOR. During this AR period, the federal government’s rightsizing plans posed a risk to the autonomy and sustainability of the Pakistan Institute for Education (PIE), and Foundation Learning Hub (FLH). This risk was mitigated through sustained senior‑level engagement with government counterparts. At provincial level, political sensitivities and limited appetite for research on ongoing education reform presented risks to delivery pace and research uptake. The team mitigated this by engaging with senior stakeholders, reinforcing the non‑partisan and academic positioning of the programme, and pausing certain activities until government consent was secured.
2. Public Service Delivery and Operations: The Pakistan Network and DARE Risk Appetite is RECEPTIVE and Risk Rating is MAJOR. Protracted process and delays involved in approval of two contract amendments for DARE-RC component, led to potential underspend and delivery delay. Mitigation included our team closely engaging with OPM and the FCDO commercial team to get HMT approval leading to DARE extension till December 2026 which provided relief from the looming risk. While delivery was disrupted, controls remained effective and risks stayed within appetite.
3. Policy and Programme Delivery: The Pakistan Network Risk Appetite: EAGER - DARE Risk Appetite: RECEPTIVE - Risk Rating is MAJOR. With programme ending in December 2026, there are risks around sustainable exit, including publication of research conducted under the Research Consortium, and complete implementation of the Data Standardisation Framework to embed it within the federal and provincial systems. There is also a risk that, and TFP model would fail to scale up through government systems, and a failure of ITA to attract future funding in unfavorable global ODA environment. Potential opportunities within the education portfolio Technical Assistance component are being discussed to anchor Data Standardisation Framework and publication of research. ITA and TFP are engaging with public and private sector partners to secure funding.
4. Safeguarding: Pakistan Network and DARE Risk Appetite is CAUTIOUS and Risk Rating is MODERATE. Risks linked to inadequate safeguarding systems and capabilities among partners leading to safeguarding incidents remained moderate as the programme team ensured that all partner staff took mandatory Sexual Exploitation Abuse and Harassment (SEAH) training prior to field engagement and conducted routine compliance checks including monitoring of safeguarding registers, and clear reporting and escalation pathways.
5. Financial and Fiduciary: Pakistan Network and DARE Risk Appetite is RECEPTIVE and Risk Rating is MODERATE. The potential risk of weak fiduciary controls and compliance to procurement/financial policies at partners leading to fraud/corruption or fund misappropriation remained low due to active mitigation measures such as mandatory pre-award due diligence assessments (DDAs) and time-bound actions to fill identified gaps. There was regular training on relevant policies, financial reporting and spot checks, and periodic audits of all partners. There is also a delivery chain mapping aligned with FCDO requirements with established confidential fraud and whistleblowing mechanisms.
6. Despite a challenging operating environment, including political uncertainty, commercial delays, and climate‑related disruptions, risks were identified early, actively managed, and remained within agreed appetite. The programme demonstrates appropriate risk management and assurance for a MODERATE risk portfolio in its penultimate year.
7. Update on Partnership Principles: Our overall assessment is that the Federal Government of Pakistan demonstrates credible commitment in selected areas of the Partnership Principles, particularly in public financial management and SDG reporting, where continued collaboration on DSF and national learning indicators reflects steady progress. However, commitment is mixed in relation to sustaining key national education institutions such as the Pakistan Institute of Education (PIE) and the Foundational Learning Hub (FLH). While both institutions play a central role in national data and learning reforms, federal financing and long‑term ownership remain uncertain. Progress across other principles continues to vary. Human rights remain an area of concern with signs of a negative trajectory. Efforts towards achieving the SDGs and reducing poverty continue, though the pace is slow and constrained by population growth. On financial management and anti‑corruption, overall direction is broadly unchanged, with some incremental improvements. Domestic accountability shows mixed results.
F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE:
Financial Performance:
1. The programme has spent £17.12 million since inception in 2020 until 31 Dec 2025, representing a 75% expenditure against an approved lifetime budget of £23 million. During this AR period, spending amounted to £4,498,293. Overall, across ITA, TFP and OPM, annual forecast versus actual expenditure variances remained within FCDO’s approved threshold of 5%, providing assurance on the robustness of partner’s financial forecasting. However, a material variance was observed under the OPM contract in Quarter 2, where an overspend of 27% was recorded. This was primarily owing to early completion of a few activities which were planned for the subsequent quarter.
2. In line with grant agreement requirements, both ITA and TFP conducted internal audits and shared reports of FCDO audited funds for the period 1 July 2024 to 30 June 2025. For OPM, an external audit, covering the financial year ending 31 March 2025 was completed, providing an unqualified audit opinion and satisfactory assurance of compliance with FCDO procurement, financial management and reporting requirements.
3. Overall, financial management and control arrangements have been assessed as fair. The programme team conducted quarterly financial spot checks on a carefully selected sample of expenditure, providing additional assurance regarding value for money, accuracy of reporting, and compliance with contractual requirements. Payments were processed in a timely manner, and clear audit trail was maintained, with documented approvals in place.

Performance of Commercial Partner:
1. The DARE programme entered its fifth year of implementation during this AR period. Delivery performance of the commercial partner OPM improved as the bottlenecks linked to capacity limitations, delivery timelines and financial management were systematically addressed. A critical gap in the intellectual leadership within the DARE‑RC was identified early in the year. This was effectively mitigated through the recruitment of a suitably qualified Research Director and the strengthening of key technical capacities. As a result, the programme has demonstrated notable improvements in both the quality assurance of research outputs and the design and procurement of successive research cycles.
2. OPM met all contractual KPIs and deliverables in line with agreed quality standards and timelines, apart from two KPIs that were delayed during the January–March 2025. In accordance with contract provisions, associated payments were retained and subsequently released following successful completion of the delayed KPIs, demonstrating effective application of performance management and payment by results.
3. During the year, three Contract Amendments (CAs) were approved resolving potential contractual and delivery risks. Although prolonged approval process of the first two amendments led to significant delays in commissioning of research, they improved supplier performance, enhanced value for money, and strengthened the commercial relationship. The programme team worked closely with FCDO’s commercial team over a sustained period to ensure full commercial compliance.
G: MONITORING, EVIDENCE AND LEARNING
1. DARE programme has a functional internal MEL system including a strong Theory of Change, a robust Results Framework and ongoing monitoring reporting, and lesson learning is supporting adaptive management and evidence‑based decision‑making. MEL systems of implementing partners are assessed to be compliant and responsive to FCDO’s reporting needs. FCDO DARE team also conducted regular progress and financial reviews, field visits, and stakeholder engagement at provincial and district levels.
2. Teach for Pakistan - Independent RAND Evaluation: An independent mixed‑methods evaluation by the RAND Corporation (2023–24) found that TFP’s Fellowship model delivers substantial learning gains in public schools. Across 80 schools in Islamabad, students taught by TFP Fellows significantly outperformed their peers, achieving 8–10 months of additional learning in mathematics, around 6 months in English, and up to 16 months in science. These gains were consistent for both girls and boys. Qualitative evidence from principals, teachers, and parents reinforced these findings, highlighting TFP Fellows’ positive contributions to classroom management, parental engagement, and reductions in corporal punishment. Overall, the evaluation provides strong, independent confirmation of the model’s effectiveness in improving learning outcomes in under‑resourced schools.
3. The Research Consortium developed a structured approach to track policy engagement, including a standardised interaction‑log template now pilot‑tested by three grantees. These logs capture who engages with research, how often, and which studies are gaining traction, with insights synthesised into infographics to guide more targeted engagement. In parallel, the RC launched an Impact Stories and Case Studies log to document emerging examples of influence, strengthening institutional learning and contributing to a growing Community of Practice.
4. Evaluation plans: due to reduction in ODA, no evaluation will be commissioned. The FCDO team is considering other options in recognition of lessons learnt as part of the Independent Commission for Aid Impact’s (ICAI) recent synthesis[40] report, and the importance of lessons learning, and in line with FCDO evaluation strategy 2025[41] and its clear focus on strengthening the quality and use of evaluations to ensure continuous learning.
  [40] UK aid under pressure: a synthesis of ICAI findings from 2019 to 2023 - Independent Commission for Aid Impact
  [41] FCDO evaluation strategy 2025 - GOV.UK
Date of last narrative financial report	ITA – Oct – Dec 2025 / TFP– Jan 2206 / WB – Feb 2026 / OPM – Oct – Dec 2205	Date of last audited annual statement	ITA – FY 2024 – 2025 Received / TFP – FY 2024 – 2025 Received / WB – TBC / OPM – FY 2024-26 Received

Annex A: Progress against last AR’s recommendations:
MAJOR RECOMMENDATIONS:
Recommendation	Progress
FCDO Future Portfolio and Design through Learning & Synthesis: As the UK slims down its portfolio and refines its human capital objectives in 2025/26, DARE research should inform the likely new focus of BHC’s education strategy on getting more girls to achieve secondary education. DARE’s research should inform our investments and shape our influencing work, including through synthesising learning from over two decades of UK’s investments in data and evidence generation in Pakistan.	In progress – DARE research will form part of the UK’s future technical assistance offer, and the team is assessing the most suitable modality to ensure this evidence base is fully integrated into future TA functions. As part of the DARE research portfolio, the team is also exploring the best approach to synthesising learning from more than two decades of UK investment in data and evidence generation in Pakistan, so that this synthesis can directly inform the new education strategy and future programming decisions.
Portfolio integration and joint work with CMPs: The BHC education team should start the process of cohering and honing its portfolio outcomes to rationalise our offer to the Government of Pakistan based on the UK’s comparative advantage. We will map which areas the UK can collaborate with key partners (e.g. the World Bank) and where the UK should step back. The BHC team should also explore how to cohere and integrate GOAL and DARE as 25/26 resourcing is set.	In progress – During 2025, the BHC education team began aligning DARE and the wider portfolio with the ongoing review of the UK’s education strategy in Pakistan, which is expected to bring major shifts in priorities and resourcing for 2025/26 and beyond. As part of this process, the team has started work to clarify how programmes will cohere under a more streamlined UK offer, including identifying where UK support should be consolidated, refocused, or stepped back. This integration agenda will continue into the coming year, with the team committed to refining the alignment between GOAL, DARE and emerging TA priorities as the new UK strategy is finalised and implemented.
Portfolio integration and joint work with CMPs: The education team should align better with the central policy teams and centrally managed programmes (CMPs) to provide a coherent FCDO offer and avoid duplication. Building stronger connections with CMPs (WWHGE, SCALE, D4FL), the education policy team, and the Global Funds (ECW and GPE) should be prioritised. For instance, working with WWHGE in its second phase of support to a national coalition on foundational learning. Such a collaboration would complement our offer to the Government of Pakistan, especially as BHC’s focus likely shifts to girls’ secondary education.	In progress – Good progress was made this year in strengthening alignment with centrally managed programmes (CMPs), with DARE‑RC deepening collaboration with WWHGE, EdTech Hub and other CMPs through joint knowledge‑sharing at the DARE International Education Summit and coordinated engagement on thematic priorities. The programme also improved coherence with the World Bank’s broader education portfolio, avoiding duplicative research—for example, adjusting DARE‑RC work in Balochistan in light of the Bank’s $100m investment—and contributing early design support to the Out‑of‑School Children Challenge Fund. While collaboration with CMPs has clearly strengthened, further integration with central policy teams and future WWHGE activities (particularly on foundational learning coalitions) will be important as the education portfolio shifts towards technical assistance.
Engagement and Uptake: The programme should enhance engagement at provincial rather than federal levels to accelerate reforms within the education sector regarding data systems. The Data Standardisation Framework (paragraph 35) has created a minimally acceptable level of coherence and expectations, thus achieving its ‘technical’ objective. However, cross-departmental implementation at provincial levels remains a challenge, undermining the broader objective of the exercise. FCDO, World Bank and PIE should jointly agree a set of success criteria on policy and coordination (e.g., to facilitate communication, address bottlenecks and manage interactions between different stakeholders or departments).	In progress – The programme made meaningful progress this year in strengthening provincial‑level engagement, with all provinces completing Foundational Learning Policy delivery plans and initiating alignment of their assessments with NAT 2026, alongside updated DSF integration plans in Punjab, Sindh and KP (with Balochistan pending system replacement). However, cross‑departmental coordination challenges persist, particularly around horizontal data integration and finalising data‑access protocols, meaning the underlying issue identified in last year’s recommendation remains only partially addressed. FCDO, the World Bank and PIE have increased joint planning—especially through NODP development and the ongoing endline assessment of PIE’s assessment functions—which will inform clearer success criteria for provincial policy coordination in the final year of the programme.
TA and Organisational Sustainability: DARE support to the Pakistan Foundational Learning Hub and to PIE will come to an end in September 2025 and in early 2026 respectively. Financial support of the Government of Pakistan is critical for the sustainability of both institutions. The World Bank PFLH and FCDO should collaborate to draft and submit a PC-1 to ensure the sustainability of the Hub, whilst avoiding substituting Government capacity.	Partially completed – DARE support to the Foundational Learning Hub ended in Sept 2025, but no government financing has yet been committed to sustain the Hub’s functions, underscoring the continued relevance of this recommendation. FCDO and the World Bank have maintained engagement with MoFEPT on potential sustainability options, including the feasibility of a government‑owned PC‑1. For PIE, an endline capacity assessment underway will inform required sustainability actions as DARE TA concludes in 2026.
DARE-RESEARCH CONSORTIUM
OPM should continue to assess the absorption capacity of PIE to avoid duplication of effort with the Trust Fund	Completed - DARE‑RC reviewed the capacity‑strengthening activities delivered to PIE during 2025 and concluded that continuing the previous model would not represent good value for money, given PIE’s limited institutional and human‑resource capacity. The ongoing endline assessment of PIE’s National Assessment Wing (WBTF) shows significant capability gaps across key functions, reinforcing the need to avoid duplicating efforts already supported through the World Bank Trust Fund. In light of this, the consortium has concluded the standalone capacity‑building component.
Considering the delays at the start of inception phase, OPM has recognised the need to extend the contract, and FCDO and OPM are in the process of negotiating a No-Cost Extension (changing the end date from January to December 2026) to ensure both the successful completion and uptake of the research. This no-cost extension will allow the programme team to pivot the programme and align it with the new Co-operation Strategy.	Completed - No cost extension has been finalised in a contract amendment.
Given the overwhelming market response to Call 1 and 2, and the complexity of the research, FCDO should explore the best route to ensure the publication of the research in top global journals as well as its uptake in the biggest possible decision-making circles. This should include considerations for OPM’s confirmation that all studies in the research portfolio are worthy of publication in international journals, have clear links with government reform, and any additional costs can be funded within the reduced ODA environment.	In progress - Publication of the research will continue to pose a challenge and this recommendation is still relevant and will be tracked throughout the last year of the contract
As the focus of the research activities become clearer, OPM should develop uptake plans looking at the whole of the portfolio to identify the RC’s unique contribution and how it responds to government reform priorities, where uptake is likely to be possible (e.g., Punjab outsourcing of schools). This plan should include identifying evidence champions within government who might require bespoke support to use research to drive reform.	In progress - uptake plans have been developed, and the vision of DARE was socalised in Pakistan and internationally (Wilton Park, Cambridge University). However, uptake activities are likely to be scaled down given the reduction in ODA.
WORLD BANK
PIE autonomy: Following the completion of this year’s TA to PIE, BHC’ support will conclude. World Bank, FCDO and PIE should work together to agree a plan of specific actions towards PIE’s autonomy, making clear recommendations to the Government of Pakistan in order to ensure the continuity of PIE and address challenges such as staffing gaps, capability, TA exit and sustainability plan. A clear exit plan and sustainable support from the Government of Pakistan is critical for strengthening PIE’s profile as a data and knowledge brokering partner at the federal level.	Partially completed – PIE autonomy remains a priority, but the institution continues to face major sustainability constraints, including an organogram that is still only partially approved and significant staffing and capability gaps identified in the 2025 endline assessment of PIE’s National Assessment Wing (high capability in only 10 of 64 functions). FCDO and the World Bank have intensified joint planning on PIE’s future, including coordination on data governance and assessment functions, but a full autonomy plan—covering staffing, capability, governance, and TA exit—has not yet been agreed with MoFEPT. Work will continue as DARE support to PIE concludes in 2026.
Joint policy outcomes: World Bank, FCDO and PIE should identify opportunities for influencing policies at provincial levels including but not limited to resource allocation based on insights from PES and learning levels from NAT.	Partially completed – Collaboration between FCDO, the World Bank and PIE strengthened during 2025, particularly through work on NAT 2026 preparations, provincial engagement on aligning provincial assessments with NAT, and the publication of the Pakistan Education Statistics 2023–24 using DSF standards. These steps create entry points for joint policy influence at provincial level. However, opportunities to use PES insights or NAT learning levels directly to inform provincial resource allocation have not yet been fully realised, and a structured set of joint policy outcomes with clear responsibilities across FCDO, WB and PIE has not been formalised. Further progress is expected as the programme moves into its final year.
Out of School Children Challenge Fund: Upon request from the World Bank Country Director, FCDO and World Bank team should work closely on the design of the OOSC Fund and should seek technical input from FCDO International Finance Directorate at HQ.	Completed – FCDO and the World Bank worked closely throughout 2025 on the early design of the Out of School Children Challenge Fund, as requested by the World Bank Country Director. DARE TF contributed technical input on the Fund’s strategic architecture, incentive and verification framework, and governance arrangements, and an expert firm was hired in November 2025 to support the detailed design work, including financial modelling and capacity‑building components for provincial rollout. FCDO also engaged internally with relevant teams, including finance specialists, to ensure alignment with UK systems on results‑based financing. This recommendation is therefore considered completed.
Sustainability and institutionalisation of the TA provided to PIE since 2020 is dependent on good documentation of all TA activities: While the online courses (paragraph 45) provide some documentation, Manual for Replication with clear costing might be necessary. This Manual should include roles and responsibilities, costing of activities, and timelines with clear tasking.	Partially completed – While two online courses were developed this year to help retain institutional knowledge within PIE following the end of DARE TA, a full Manual for Replication—including roles, responsibilities, costing, and timelines—has not yet been produced. Given ongoing staffing and capability gaps at PIE, and the conclusion of TA in 2026, comprehensive documentation remains essential for sustainability. FCDO and the World Bank will continue work on this during the programme’s final year.
ITA
Uptake lessons report: “To strengthen the case for financial sustainability, ITA should consider a high‑level assessment of its efforts to date in policy engagement on the findings of the ASER, analysing who, where, when and why ASER has influenced and/or achieved real uptake – i.e. discernible change in government decision making around policy, plans, resource allocation, etc. a learning focussed report to guide future strategy.	Met - ITA made initial progress toward a high‑level assessment of ASER’s policy uptake by consolidating internal documentation and analysing key engagement pathways. It also outlined the scope for a learning‑focused uptake assessment, identifying where ASER data has informed policy discourse and planning at national and provincial levels. While financial constraints limit the commissioning of external support, ITA is prioritising an internal high‑level review to guide future policy engagement and strengthen the case for financial sustainability.
ASER’s role in the maturing assessment landscape of Pakistan: The assessments landscape is Pakistan has matured over the last few years, and ITA’s engagement with PIE is essential to understand what additionality and complementarity ASER is creating. FCDO, PIE, ITA and World Bank should collaborate to agree an approach to supporting assessments and agree how different assessments complement each other.	Met - ITA has signed a Letter of Understanding with PIE to establish a coordinated approach to strengthening Pakistan’s assessment landscape, ensuring clarity on how different assessments - including ASER - complement one another. ITA also continued close coordination with PIE and PBS to enhance complementarities across systems. As a direct result of this engagement, the ASER 2025 survey sample was successfully finalised and received from PBS.
Financial diversification and sustainability: BHC Islamabad has been supporting ASER since 2012 – our current agreement with ITA will expire in March 2026, and ITA should seek alternative funding sources – through an independent assessment of the survey we have identified areas of work that could further strengthen its reliability and attract alternative donor. ITA should use the assessment to strengthen the survey and approach prospective funders.	Met - ITA developed a five‑year fundraising strategy, secured additional funding from UNICEF and VSO, and continued proactive engagement with development partners, making progress toward the diversification targets.
TFP
Reduce cost per child: Reduce cost-per-child: The cost per child is relatively high (£57 per year). TFP should identify ways to reduce the cost (cost-per-teacher, cost-per-child) and thereby increase the cost-effectiveness (e.g. learning outcome improvements per $) of the model. However, the outcome of an external evaluation, due in March 2025, by RAND Cooperation will allow TFP and FCDO to put the cost per child in context of learning improvement.	Partially met - TFP credibly used the RAND evaluation to justify cost‑effectiveness in learning terms but did not demonstrate a clear reduction in cost‑per‑child nor quantify improvements in cost‑effectiveness. The response remains narrative‑led rather than analytical. TFP is currently conducting a cost‑effectiveness analysis focused solely on Fellow recruitment and development costs, excluding other costs. Based on these isolated costs, the Cost per Child is expected to be significantly lower than previously reported (£57 per child)
Comparability of results: Comparability of results. TFP should engage with research and measurement experts, to identify ways to maximise rigour and comparability of impact and cost-effectiveness data, including reporting of learning impact in micro-LAYS . This should be the basis of ongoing engagement with federal and provincial governments.	Partially met - TFP substantially improved rigor and consistency of learning measurement and used evidence strategically with government but did not deliver on micro‑LAYS or fully comparable cost‑effectiveness metrics, limiting cross‑programme comparability. TPF committed to completing this recommendation by the end of the agreement.
Synergy with other specialist TPF organisations: the TFP model is only likely to make up a small part of provincial strategies to improve teacher competencies and practices. TFP should therefore consider partnerships that could complement its model, and provide provinces with a more holistic, evidence-backed set of models.	Not met - TFP did not substantively address this recommendation. While policy dialogue increased, there is no evidence of operational partnerships or experimentation with lower‑cost delivery models, representing a missed opportunity to respond to affordability and scalability concerns.
Explore twin track: TFP should explore a twin track for the next cohort/intake, with one track receiving the full TFP package of support and the second receiving a lower cost package.	Not met - TFP did not explore or pilot a twin‑track Fellowship model due to the financial burden this would have placed on the organisation against the backdrop of shrinking funding pool. All 2025 cohorts continued to receive the full Fellowship package. While incremental efficiency measures were introduced, the programme did not test structural options to reduce unit costs or increase scalability. Given the programme’s strong learning outcomes, future engagement should prioritise structured experimentation with lower‑cost delivery models, potentially in partnership with government teacher training institutions.
Recommendation	Progress
FCDO Future Portfolio and Design through Learning & Synthesis: As the UK slims down its portfolio and refines its human capital objectives in 2025/26, DARE research should inform the likely new focus of BHC’s education strategy on getting more girls to achieve secondary education. DARE’s research should inform our investments and shape our influencing work, including through synthesising learning from over two decades of UK’s investments in data and evidence generation in Pakistan.	In progress – DARE research will form part of the UK’s future technical assistance offer, and the team is assessing the most suitable modality to ensure this evidence base is fully integrated into future TA functions. As part of the DARE research portfolio, the team is also exploring the best approach to synthesising learning from more than two decades of UK investment in data and evidence generation in Pakistan, so that this synthesis can directly inform the new education strategy and future programming decisions.
Portfolio integration and joint work with CMPs: The BHC education team should start the process of cohering and honing its portfolio outcomes to rationalise our offer to the Government of Pakistan based on the UK’s comparative advantage. We will map which areas the UK can collaborate with key partners (e.g. the World Bank) and where the UK should step back. The BHC team should also explore how to cohere and integrate GOAL and DARE as 25/26 resourcing is set.	In progress – During 2025, the BHC education team began aligning DARE and the wider portfolio with the ongoing review of the UK’s education strategy in Pakistan, which is expected to bring major shifts in priorities and resourcing for 2025/26 and beyond. As part of this process, the team has started work to clarify how programmes will cohere under a more streamlined UK offer, including identifying where UK support should be consolidated, refocused, or stepped back. This integration agenda will continue into the coming year, with the team committed to refining the alignment between GOAL, DARE and emerging TA priorities as the new UK strategy is finalised and implemented.
Portfolio integration and joint work with CMPs: The education team should align better with the central policy teams and centrally managed programmes (CMPs) to provide a coherent FCDO offer and avoid duplication. Building stronger connections with CMPs (WWHGE, SCALE, D4FL), the education policy team, and the Global Funds (ECW and GPE) should be prioritised. For instance, working with WWHGE in its second phase of support to a national coalition on foundational learning. Such a collaboration would complement our offer to the Government of Pakistan, especially as BHC’s focus likely shifts to girls’ secondary education.	In progress – Good progress was made this year in strengthening alignment with centrally managed programmes (CMPs), with DARE‑RC deepening collaboration with WWHGE, EdTech Hub and other CMPs through joint knowledge‑sharing at the DARE International Education Summit and coordinated engagement on thematic priorities. The programme also improved coherence with the World Bank’s broader education portfolio, avoiding duplicative research—for example, adjusting DARE‑RC work in Balochistan in light of the Bank’s $100m investment—and contributing early design support to the Out‑of‑School Children Challenge Fund. While collaboration with CMPs has clearly strengthened, further integration with central policy teams and future WWHGE activities (particularly on foundational learning coalitions) will be important as the education portfolio shifts towards technical assistance.
Engagement and Uptake: The programme should enhance engagement at provincial rather than federal levels to accelerate reforms within the education sector regarding data systems. The Data Standardisation Framework (paragraph 35) has created a minimally acceptable level of coherence and expectations, thus achieving its ‘technical’ objective. However, cross-departmental implementation at provincial levels remains a challenge, undermining the broader objective of the exercise. FCDO, World Bank and PIE should jointly agree a set of success criteria on policy and coordination (e.g., to facilitate communication, address bottlenecks and manage interactions between different stakeholders or departments).	In progress – The programme made meaningful progress this year in strengthening provincial‑level engagement, with all provinces completing Foundational Learning Policy delivery plans and initiating alignment of their assessments with NAT 2026, alongside updated DSF integration plans in Punjab, Sindh and KP (with Balochistan pending system replacement). However, cross‑departmental coordination challenges persist, particularly around horizontal data integration and finalising data‑access protocols, meaning the underlying issue identified in last year’s recommendation remains only partially addressed. FCDO, the World Bank and PIE have increased joint planning—especially through NODP development and the ongoing endline assessment of PIE’s assessment functions—which will inform clearer success criteria for provincial policy coordination in the final year of the programme.
TA and Organisational Sustainability: DARE support to the Pakistan Foundational Learning Hub and to PIE will come to an end in September 2025 and in early 2026 respectively. Financial support of the Government of Pakistan is critical for the sustainability of both institutions. The World Bank PFLH and FCDO should collaborate to draft and submit a PC-1 to ensure the sustainability of the Hub, whilst avoiding substituting Government capacity.	Partially completed – DARE support to the Foundational Learning Hub ended in Sept 2025, but no government financing has yet been committed to sustain the Hub’s functions, underscoring the continued relevance of this recommendation. FCDO and the World Bank have maintained engagement with MoFEPT on potential sustainability options, including the feasibility of a governmentowned PC1. For PIE, an endline capacity assessment underway will inform required sustainability actions as DARE TA concludes in 2026.