## DARE logframe 2025-26
| ORGANISATION NAME | FCDO
| PROJECT NAME | Data and Research in Education (DARE)
| IMPACT | Impact Indicator 1 |  | Baseline (2020) | Milestone 1 (Sep 2021) | Milestone 2 (Sep 2022) | Milestone 3 (June 2023) | Milestone 4 (Dec 2024) | Milestone 5 (Dec 2025) | Target (Dec 2026)
| An education system which is more aligned towards and cohesive around the objective of improved student learning outcomes; and which is informed by better quality data and driven by quality research evidence. | Improved learning outcomes at scale for the most marginalised children: Number of children reading with comprehension by age 10, disaggregated by gender, disability and location | Planned | No federal database on learning outcomes. Punjab: KP: Sindh: 32.8% (2016) Balochistan: Unavailable; ASER 2019 survey finds that percentage of children who can read a short story in Urdu/Sundhi/Pashto in Grade 5 (equivalent to age 10) is: National: 59% (Girls: 38%; Boys: 46%) Punjab: 75% KP: 55% Sindh: 44% Balochistan: 48% |  | Initial central database on learning outcomes. Girls: Boys: Children with disabilities: Punjab: KP: Sindh: Balochistan: | Complete central database on learning outcomes. Girls: Boys: Children with disabilities: Punjab: KP: Sindh: Balochistan: | Complete and functioning central database on learning outcomes. Girls: Boys: Children with disabilities: Punjab: KP: Sindh: Balochistan: | Complete and functioning central database on learning outcomes. Girls: Boys: Children with disabilities: Punjab: KP: Sindh: Balochistan: | Complete and functioning central database on learning outcomes. Girls: Boys: Children with disabilities: Punjab: KP: Sindh: Balochistan:
|  |  | Achieved |  |  | Not initiated | Not initiated | National Open Data Portal (NODP) for education data in Pakistan is under design | National Open Data Portal (NODP) for education data in Pakistan is under design
Source
National PIE data / Pakistan Education Statistics report using National Assessment Test (NAT) data. Alternative data sources in lieu of this: World Bank learning poverty reports, ASER http://aserpakistan.org/document/report_cards/2019/summary_report_cards/National_2019.pdf and Measured GEPD Data (as baseline)
|  | Impact Indicator 2 |  | Baseline (2020) | Milestone 1 (Sep 2021) | Milestone 2 (Sep 2022) | Milestone 3 (June 2023) | Milestone 4 (Dec 2024) | Milestone (Dec 2025) | Target (Dec 2026)
|  | Research, evidence and data inform policies and budget making: (i) Budget allocations to learning assessments as measured by PIE (ii) Federal level financial resources are allocated according to equity criteria identified through government owned data (iii) Increased willingness and capacity of decision makers to use research for education policy making | Planned | (i) Federal: Irregular allocation (no fixed budget line) Punjab: KP: Sindh: Balochistan: (ii) None. |  | (i) Fixed budget line for PIE established. | (i) Increase by 3%; (ii) Equity index critera identified and discussions between Ministry of Education and Ministry of Finance underway. | (i) Increase by 5%; (ii) District Ranking Index launched and discussions started with the Ministry of Finance and Ministry of Planning to use the Index for allocation decisions to lagging districts (iii) 4 agreements reached between DARE RC and research users (decision makers) to use research in policy making AND 3 provincial bodies engaged by DARE RC leading to their effective use of research and policy making | (i) Increase by 10%; (ii) District Ranking Index is used by the Federal Government for allocation decisions to lagging districts (iii) 3 provincial bodies engaged by DARE RC leading to their effective use of research and policy making | (i) PIE is fully operational (ii) District Ranking Index is used by the Federal Government for allocation decisions to lagging districts (iii) 3 provincial bodies engaged by DARE RC leading to their effective use of research and policy making
|  |  | Achieved |  | Separate budget lines for AEPAM and NEAS | Met - 141 million PKR allocated |  |  | (i) Despite PIE’s central role in national data and policy functions, there is no evidence of sustained domestic financing: government commitment remains unclear and recent rightsizing proposals highlight significant fiscal risk. (ii) A results-based OOSC Challenge Fund rewards provinces/districts for improving enrolment and learning, using a DEPIx-based ranking to prioritise districts (70% deprivation via DEPIx, 30% OOSC scale). (iii) Evidence of policy uptake across at least three provincial education bodies, demonstrated through integration of DARE-RC research into government systems (KP), policy development processes (Sindh), and senior-level planning and reform decisions (Punjab).
Source
FCDO analysis/ WB analysis; Federal and provincial budgets; minutes of meetings, Letters of Understanding (LoUs), mutually agreed plans, govt notifications (or any other relevant methods)
| OUTCOME | Outcome Indicator 1 |  | Baseline (2020) | Milestone 1 (Sep 2021) | Milestone 2 (Sep 2022) | Milestone 3 (June 2023) | Milestone 4 (Dec 2024) | Target (Dec 2025) | Target (Dec 2026) | Assumptions
| 1. (a) Pakistan has a strengthened national education data system, in which quality data is produced by government, made publicly available and (b) is used by government at provincial and federal levels and by non-government stakeholders to improve education provision and resource targeting, and to drive continuous improvement. | (i) Regularity and timeliness of data, statistical reports and learning assessments published. (ii) Availability of raw/open access data to the public, academics and other policy makers. (iii) Pakistan Institute for Education (PIE) generates data and studies which are used by provincial governments | Planned | (i) Last federal level report published in 2021, for 2017/18; 2016/17 statistics released in late 2018. (ii) Unknown; (iii) PIE not established. AEPAM and NEAS understaffed and lacks legal mandate for the data it is intended to produce. | PIE director appointed and structure identified. | (i) Annual statistical report and learning assessment (NAT) is published; (ii) Policy of data protection, transparency and access protocols passed; (iii) PIE is established, 80% of vacanices are filled and legal mandate is clear. | (i) Annual statistical report and learning assessment (NAT) is published; (ii) Data is made open access, in accordance with data protection procedures. 100 downloads; (iii) PIE is functioning, 100% of vacancies are filled and has conducted at least two deep-dive analysis/studies for provincial governments. | (i) Annual statistical report (PES) 2023-24 which is DSF compliant is published AND NAT scope and tools are finalised for NAT 2025 allowing PIE to report internationally against SDG4 (ii) Draft Plan of Actions on Data integration are approved at the provincial and federal level. AND 2nd iteration of DSF support initiated informed by review of 1st iteration support. AND Data sharing at all levels based on agreed upon access protocols (iii) PIE is functioning, 90% of vacancies are filled and has conducted at least two deep-dive analysis/studies relevant for provincial governments | (i) Annual statistical report (PES) 2023-24 which is DSF compliant is published AND NAT scope and tools are finalised for NAT 2025 allowing PIE to report internationally against SDG4 (ii) Draft Plan of Actions on Data integration are approved at the provincial and federal level. AND 2nd iteration of DSF support initiated informed by review of 1st iteration support. AND Data sharing at all levels based on agreed upon access protocols (iii) PIE is functioning, 90% of vacancies are filled and has conducted at least two deep-dive analysis/studies relevant for provincial governments. | To be revised - PIE is autonmous, all vacancies are filled through the open market, and is playing a central role in the education data ecosystem in Pakistan including through sroutine assessment and ongoing implemenation of data standarisation. | Federal govt and provincial govts will have buy in for this data to form policies and will be aligned. The data will be publicly available to be used and would be credible. WB TA will be a successful model to provide TA to govt esp in establishment and successful running of PIE
|  |  | Achieved |  | PIE established. Interim PIE director appointed and structure identified. |  |  | (i) PES & NAT: DSF-compliant data and preparatory work are in place, but delays in PES publication and incomplete NAT readiness mean the target is not met. (ii) Data integration: Plans of Action and DSF iteration are completed, but full data sharing and system integration are not yet operational, so the target is only partially met. (iii) PIE functionality: PIE remains only partially operational, with significant staffing gaps and delayed analytical outputs, meaning the target is not met. | (i) Annual Pakistan Education Statistics (PES) report is published using the Data Standardisation Framework (DSF), and a standards‑based National Achievement Test (NAT) is operationally ready to enable international reporting against SDG 4.1.1. (ii) Revised Data Standardisation Framework (DSF 2.0) is adopted, and provincial–federal Plans of Action for data integration are developed and under implementation, with progress towards operational data sharing through agreed access protocols. (iii) PIE’s operationalisation remains incomplete: while core data functions are being delivered (PES, DSF, NAT), significant gaps persist in staffing, institutional capacity, and delivery of analytical outputs.
Source
Government of Pakistan websites, including MoFEPT and provincial education websites
| 2. More rigorous and publicly available research into what innovations work to accelerate learning in – and out of - Pakistan’s schools, particularly for girls and marginalised groups, generated through a strengthened Pakistani education research community (which continues to do this sustainably after the programme’s closure) and put into the hands of key policy makers. | Outcome Indicator 2 |  | Baseline (2020) | Milestone 1 (Sep 2021) | Milestone 2 (Sep 2022) | Milestone 3 (June 2023) | Milestone 4 (Dec 2024) | Target (Dec 2025) | Target (Dec 2026)
|  | (i) Increased demand for, improved access to and better understanding of education evidence by policy makers (ii) Number of citations of learning assessment results in public government documents and the media (iii) Number of researchers from Pakistani education research community reporting benefits of capacity building activities | Planned | (i) Baseline to be established by December 2021. OPM analysis in 2019 suggested overall distrust of the official data by policy makers and lack of use. (ii) None, ASER data primarily used; (iii) No research consortium established. | (i) Baseline survey with government officials designed; (ii) 0; (iii) 0 | (i) Measured only at baseline and endline; (ii) 2 | (i) Measured only at baseline and endline; (ii) 4; (iii) 80% of researchers /participants rated trainings as 'good' or 'excellent' and stated they had 'learned a new skill' | (i) Timely, efficient, and complete databases is available to decision-makers, including PES, and preparations are underway for NODP AND Composite Index informed District Education Rankings developed. AND 1 Impact story (contribution narrative) showing that large-scale reform efforts are influenced by DARE RC research and key decision makers are influenced to change policy and practice accordingly (ii) 8 citation of learning assessments results (ITA, PIE and WB) AND Two impact stories about how ASER Nationwide National Assessment for SDG 4.1.1 a and SDG 4.1 and Right to Education has been informing accountability and actions for Foundational Learning (iii) % increase in the knowledge of Research users participating in capacity strengthening activities | (i) Timely, efficient, and complete databases is available to decision-makers, through the National Open Data Portal (NODP) (ii) 8 citation of learning assessments results (ITA, PIE and WB) (iii) % increase in the knowledge of Research users participating in capacity strengthening activities | 1 impact story delivered Topic to be mutually agreed with FCDO Proposed Topic: Building Momentum for Evidence-Based Policy Development through Inputs on National Education Policy Development Framework1) Full Programme target Sept 2026 cumulative for the programme lifecucle 5 Impact stories (contribution narrative) showing that large-scale reform efforts are influenced by DARE RC research and key decision makers are influenced to change policy and practice accordingly
|  |  | Achieved |  | Baseline survey found: • Departmental data is difficult to access: There aren’t clear access protocols and delays in requesting information in writing can mean data is underutilised for decision-making. Though 68% of education officials have access to compiled data, only 37% have access to raw data for additional, independent analysis. • Quality of education data is perceived to be low: Officials bemoaned the reliability and depth of data as major issues, with more than 73% encountering instances where the data they required was missing. • Research is difficult to understand: More than 70% of officials find the research reports they encounter too technical, and too long. Qualitative research is relatively easier for officials to understand (75%) compared to quantitative research (65%). • There is a reasonable level of motivation and demand for data and research: Officials believe that there is appetite in their departments to link policies and programmes with research and say they sometimes demand data for decision making. • Capacity is low: Officials self-evaluated that they have the ability to analyse data but strongly doubted the capacity of others in their department. • There is a culture of delegation: Despite this low confidence in others’ ability to analyse data, 87% of officials assign analysis of data to someone else. • Sources of data and evidence which are used are narrow: Officials most commonly use their prior experience to inform their decisions, but if they do seek out evidence, they predominantly turn towards departmental sources of data. Information shared on social media was ranked as equally as influential as research undertaken by local researchers/organisations. Women and those with higher education were more likely to seek out alternate sources of research. |  |  | (i) Data systems, DEPIx, and NODP preparation have progressed, but delays in PES publication and limited evidence of policy influence mean the target is only partially met. (ii) Learning assessments (ASER, NAT, WB outputs) are being used and cited, but there is insufficient evidence to confirm the target number of citations and fully developed impact stories, so this is partially met. (iii) Capacity strengthening has led to measurable increases in research user knowledge, indicating the target is met, though based on limited sample sizes. | (i) Progress has been made on DSF implementation and NODP development (with procurement completed and rollout underway), but databases are not yet fully operational or delivering timely, complete access to decision‑makers, so the target remains partially met. (ii) Learning assessment outputs (ASER, NAT, DEPIx, PES) are being produced and used in policy processes and discussions, but available evidence does not confirm achievement of the full citation target, so progress is partial. (iii) Capacity strengthening activities have led to measurable increases in knowledge among participating research users, with evidence of improvement in test scores and high satisfaction, indicating the target is met.
Source
Survey of government officials and report analysis; FCDO analysis of documents, and QPRs, evidence of impact stories submitted by partners
| 3. Pakistan's education system's ability to respond to the coronavirus pandemic and other crises is strengthened | Outcome Indicator 3 |  | Baseline (2020) | Milestone 1 (Sep 2021) | Milestone 2 (Sep 2022) | Milestone 3 (June 2023) | Milestone 4 (Dec 2024) | Milestone (Dec 2025) | Target (Dec 2026)
|  | Education data is presented at and used to inform discussions by Education in Emergencies Cluster group to respond to crises and mitigate learning loss | Planned | Education in Emergencies Cluster meeting minutes do not refer to EMIS data or other government led data on education | Analysing EMIS data is identified as a key activity to undertake in Education in Emergencies Cluster meetings. | Analysing EMIS data is identified as a key activity to undertake in Education in Emergencies Cluster meetings. | EMIS data is routinely presented and used to inform response to crises. | EMIS data is routinely presented and used to inform response to crises. | Completed and CLOSED | Completed and CLOSED
Achieved
Source
Education in Emergencies Cluster group meeting minutes (UNICEF) and World Bank reporting
| INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  |  | FCDO SHARE (%)
| INPUTS (HR) | FCDO (FTEs)
| OUTPUT 1 | Output Indicator 1.1 |  | Baseline (2020) | Milestone 1 (Sep 2021) | Milestone 2 (Sep 2022) | Milestone 3 (Sep 2023) | Milestone 4 (Dec 2024) | Milestone 5 (Dec 2025) | Target (Dec 2026) | Assumption
| National education data systems are strengthened through improved data management processes and enhanced coordination. The regular and robust monitoring and evaluation of increased administrative and learning data informs decision making. (WB) | Provincial-Federal Data Management processes are strengthened. | Planned | No national strategy for data or guidance for data. Provincial data is not routinely shared or accessible. Federal-provincial coordination on education is weak following 18th Amendment. | Kick-off meetings with MoFEPT and Provincial governments held | (i) Study of federal and provincial data landscape, management and reporting practices completed; (ii) At least two provincial consultations held towards developing draft Standardisation Framework; (ii) Pakistan Institute for Education capacity built, enabling them to publish Education Statistics within 4 months of data collection. | (i) National Data Standardisation Framework (DSF) is developed and approved by MoFEPT and Provinces; (ii)Pilot of National Data Regime initiated, covering DSF guidance and implementation of guidance on key issues including Data Protection and Data Access Protocols. (iii) Plan for National level real-time Open Data Portal developed and approved by MoFEPT; | i) Updates to the National Data Standardisation Framework (DSF) done in consultation with EMIS TWG, approved by MoFEPT and Provinces; ii) National Data Regime continues its second round of implementation (ASC conducted in light of updated DSF); iii) PIE plan to operate and manage the NODP is approved by MoFEPT (iv) 1 Pakistan Education Statistics 2023-2024 published by December 2024 (within 4 months of data collection) aligned with DSF (v) Development of 5 detailed provincial Plans of Actions for horizontal (national/provincial) and vertical integration (national) for DSF implementation with clear timelines for completing the integration of existing digital data across departments and inter-departments (vi) 5 Access protocols at federal and provincial levels are agreed and approved setting the standards efficient exchange of data at all provincial and federal levels. | 1. Align Annual School Census 2025 (ASC) tools with the updated DSF by November 2025 for nationwide implementation across all provinces. 2. Update 5 detailed provincial Plans of Action for horizontal (national/provincial) DSF integration, including clear timelines for integrating existing digital data across departments. 3. Review and update 5 data access protocols (federal and provincial) with inputs from provincial departments to enable efficient data exchange at all levels 4. Conduct 2 EMIS Technical Working Group (TWG) sessions as a platform for inter-provincial learning, expanding scope to engage Development Partners for improved coordination |  | i. Federal-Provincial government dynamics will not pose insurmountable challenges to the delivery of technical assistance for data system strengthening. ii. There will be strong government buy-in and support of the data TA supplier’s work and proposed reforms for the data system, factoring in the political economy and governance dynamics between the provincial and federal governments. This includes Provinces agreeing to participate in reform activities, for example development of performance standards and administering assessments and data collection. iii. Government commits to resourcing (funding & staffing) the Pakistan Institute of Education sufficiently and in time. iv. Other development partner activities are aligned to and made coherent with DARE’s activities, to ensure gains are capitalised upon and spread across the country, including into provinces where FCDO has less of a footprint but where other donors are more active (e.g. in Balochistan). i. Data TA supplier’s actions and recommendations will be effective in strengthening the data system. Government capacity will be developed over the course of the programme to both generate improved system data and, more importantly, to use this data to inform policy and decision making. Improved evidenced-based policy making will also be informed by a growing, better quality and more accessible research base which is promoted by civil society and picked up by government to inform education strategy and action. ii. Government is open to being transparent with data publication, including sharing raw data e.g. for use by researchers and civil society, for further analysis possibly leading to criticism. In turn, researchers and civil society will actively pick-up government data and use it to inform policy-relevant research which has as an objective the strengthening of the system.
|  |  | Achieved |  | Kick-off meeting with MoFEPT held. Virtual meetings with Provinces planned. | i. Desk review of federal and provincial data landscape, management and reporting practices completed. ii. Three consultations completed, with the federal government and the provincial governments of Punjab and KP; iii. Capacity needs assessments of NEMIS wing and National Assessment Wing of PIE completed; PES 2018/19 report published and data entry for 2020/2021 report ongoing. | (i) The DSF was endorsed in May 2023, at the highest ministerial level at the Inter-Provincial Education Ministers Conference (ii) DAI have completed timely and effective capacity building workshops in all provinces and federal level to enable implementation of DSF. (iii) The plan for the National level real-time Open Data Portal has been developed and submitted for approval by PIE and MoFEPT. This approval has been granted, exceeding expectations. | Provincial–federal data management processes were strengthened through the implementation of the Data Standardisation Framework and completion of the second Annual School Census using harmonised standards, improving national data comparability and coordination under the Pakistan Institute of Education. | 1. Met - DSF was revised and updated to DSF 2.0, and the ASC tools have been aligned with DSF 2.0. 2. Partially met – Updates completed in Sindh, KP and Punjab. No work undertaken in Balochistan as their legacy system is being replaced. 3. Partially met – Updates completed in Sindh, KP and Punjab. No work undertaken in Balochistan as their legacy system is being replaced. 4. Met – Sessions held on 11-12 August led by GoP
Source
World Bank reporting; interviews with government stakeholders
|  | Output Indicator 1.2 |  | Baseline (2020) | Milestone 1 (Sep 2021) | Milestone 2 (Sep 2022) | Milestone 3 (Sep 2023) | Milestone 4 (Dec 2024) | Milestone 5 (Dec 2025) | Target (Dec 2026)
|  | Education sector level coordination and cooperation is enhanced across Pakistan. | Planned | Irregular national sample assessment of learning. Individual provinces conduct different learning assessments but these are not consistent or frequent and lags between data collection and report publication are common. Federal coordination guidelines on key national education policy issues are lacking. | TORs developed | (i) Annual implementation of National Assessment Test (NAT) conducted and published with results disaggregated by gender, location, in-school/out-of-school, grade and age; (ii) 2 policy-focused research briefs developed and disseminated with PIE. | (i) NAT Assessment Framework developed and results provincially and internationally comparable using Global Proficiency Framework; (ii) Annual implementation of NAT conducted final reports drafted with results disaggregated by gender, location, in-school/out-of-school, grade and age; (iii) At least 2 policy-focused research briefs developed and disseminated by PIE. | (i) NAT 2023 results inform series of MOFEPT/PIE guidelines on national education policy priority issues including 1) teacher training and professional development 2) curriculum and c) assessment for learning. (ii) NAT 2025: Tools and test items for NAT 2025 with expanded scope are developed by December 2024 and piloted in 4 provinces and ICT by February 2025. (iii) Development of 1 National Assessment Framework to Standardize Assessments for grants grades 2/3 (by Foundational Learning Hub), 5 and 8 by PIE (iv) EMIS Data TWG (2 sessions) continues to be a platform for inter-provincial learning and exchange, and its scope is expanded to include and engage other Development Partners (including UNICEF and UNESCO) for improved coordination and alignment driven by PIE. (v) Completion of two policy relevant studies on 1 Devolution study (one study) published and 1 District Rankings (one study) Published (vi) The Foundational Learning Hub supports the implementation the national foundational learning policy including through the development of teacher learning and training materials | 1. Complete baseline capacity assessment of PIE’s National Assessment Wing (NAW) 2. Complete the pilot for the National Achievement Test (NAT) 2026 3. Develop National foundational learning Benchmarks for Grade 3 and complete the pilot of the Foundational Learning Assessment. 4. Support the development of Foundational Learning policy delivery plans, a structured pedagogy package, and the Foundational Learning Assessment Framework. 5. Initiate provincial engagement on aligning Large-Scale Assessments (LSA) with NAT 6. Conclude 2-years support to FLN Hub and handover the Hub to the Federal Government as per the agreement between BHC and the Federal Government. 7. Complete and publish 2 policy-relevant studies. (Devolution and Learning Losses)
|  |  | Achieved |  | WB have shared draft TORs | (i) NAT for 2019/2021 draft report delayed; tools for NAT 2022 developed but not yet piloted; (ii) 2 policy-focused research briefs on TPD and distance learning developed by WB TA and disseminated in partnership with PIE. | (i) The NAT assessment framework has been aligned with the Pakistan National Curriculum's student learning outcomes. CPE plan to conduct refresher trainings on policy linking methodology in Dec 2023 to support the policy linking exercise in NAT 2023. (ii) The NAT data has been collected and analysed and a final draft report with disaggregated data has been shared with PIE and BHC Islamabad. (iii) The Institute of Social and Political Sciences (ISAPs) were engaged by the WB to support institutional capacity building of PIE. | Education sector coordination was strengthened through the use of National Achievement Test (NAT) 2023 results to inform federal policy guidance, regular EMIS Technical Working Group engagement, and the launch of the District Ranking Index, supporting shared understanding of education performance across provinces. | 1. Met – The capacity assessment completed. 2. Met – All preparations completed. The pilot took place in May 2025. 3. Met – The National Benchmarks were completed and piloted in November 2025. 4. Met – Delivery plans were developed for each of the provincially notified Foundational Learning Policies. 5. Met – Provincial engagement has been initiated. 6. Partially met – Support to the Hub concluded in Sep 2025 but no government funding was committed. 7. Unmet – The two studies have not been finalised
Source
World Bank reporting; interviews with government stakeholders
| IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline (2020) | Milestone 1 (Sep 2021) | Milestone 2 (Sep 2022) | Milestone 3 (Sep 2023) | Milestone 4 (Dec 2024) | Milestone 5 (Dec 2025) | Target (Dec 2026)
| 30% | Education sector level Monitoring, Evaluation, and Decision Making improves leading to increased use of data for equitable resource distribution | Planned |  | TORs developed | Development and roll out of Public Expenditure Review (PER) | (i) A minimum of 3 Public Expenditure Review dissemination events held. (ii) Literature review report of composite indexes that use government data for financial allocations | (i) Pilot Private School Survey launched and tested. (1 Pilot) (ii) Dissemination activities: Organize roundtables to launch the Global Education Policy Dashboard (GEPD) targeting stakeholders in the Government, Development Partners and Civil Society organizations (6 round tables). Publish and launch Composite Index Informed District Education Rankings published and disseminated (1 event). Launch of NAT 2023 (1 national event, and 4 provincial) (total: 12 events) (iii) To ensure wide and sustainable dissemination of DARE research, agree the Terms of Reference for 1 online training course (to be completed following the end of the current TA support in June 2025) hosted on PIE website using case studies from TEACH/COACH and GEPD work, as well as the policy linking training and others delivered throughout the course of the programme. (1 course) | 1. Private School Survey - Finalise sample calculation, obtain clearance for survey. Complete Phase 1 & start Phase 2. 2. eLearning Modules developed to enhance PIE's capacity 3. Support the design of the Out of School Children Challenge Fund
|  |  | Achieved |  | WB have shared draft TORs | Desk review and data collection ongoing, draft report due to be submitted by 30 September | (i) The final draft from the review was completed in April 2023 and set for national and provincial dissemination in May 2023 but the events were cancelled due to significant political disruptions on 9th May and has been delayed until the new cabinet is sworn in following the elections, after 8th Feb 2024. (ii) Tabadlab was onboarded by the WB to develop a composite index using the DSF indicators. An inception report has been submitted. | Education sector monitoring and decision‑making were strengthened through 12 national and provincial dissemination events that promoted the use of the National Achievement Test 2023, District Ranking Index, and Global Education Policy Dashboard to inform evidence‑based planning and resource allocation, though some planned data initiatives remain pending. | 1. Partially met – Sample calculation is completed, but deployment (phase 1 and 2) is delayed. 2. Met – Two new courses developed. 3. Met - This Fund will lay the foundation for transfer-based grants to the most lagging districts.
|  |  | Source | [7 empty] | RISK RATING
|  |  | World Bank reporting; interviews with government stakeholders | [7 empty] | Moderate
| INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  |  | FCDO SHARE (%)
8000000 World Bank
| INPUTS (HR) | FCDO (FTEs)
FR 0.4 FTE, RA 0.3 FTE, TA 0.1 FTE
| OUTPUT 2 | Output Indicator 2.1 |  | Baseline (2020) | Milestone 1 (Sep 2021) | Milestone 2 (Sep 2022) | Milestone 3 (Sep 2023) | Milestone 4 (Dec 2024) | Target (Dec 2025) | Target (Dec 2026)-by March 2026 as the project concludes | Assumption
| Comparable, independent, representative and reliable education data is produced by civil society. (ITA) | Improved access to and availablity of disaggregated data on marginalised children's access to school and learning outcomes, including: (i) children living in informal urban settlements and (ii) children with disabilities | Planned |  | 26062024 | (i) Full survey in urban settlements completed; (ii) Annual ASER survey reports disaggregated data for girls and children with disabilities; (iii) ASER runs national campaigns using citizen led data to highlight the learning crisis and limited access to school among marginalised children in order to influence voters and political parties in the election. | i) Quality in the Katchi Abadis Katchi Abadis Pilot: Learning of Pakistan survey in urban settlement is completed (this includes data collection, report analysed and completed and disseminated to key stakeholders at national and sub national levels). ii) 2 launches to be held by February 2023 on Katchi Abadis based on the findings of the survey and actions / recommendations and actions leads are identified. iii) Annual ASER survey report with disaggregated data for gender and disabilities completed (this includes data collected, analysed, report completed and disseminated to key stakeholders at national and sub national levels). iv) 55 spot checks (at least 10 per province) are conducted by data verification through digitalization of the ASER Survey 2023. ASER 2023 will also be conducted in 55-60 districts on a custom made application that will allow GPS Tracking of the household leading to real time data collection. | (i) Development of six thematic report cards on data collected during ASER 2023 (Gender, Foundational Learning, Climate Change, Facilities with SMC’s, Equity & Disability, Technology) – Target: 6 (ii) Number of dissemination events of ASER 2023 findings across Pakistan with all relevant stakeholders (communities, district authorities, teachers’ association, youth organisation and media outlets) – Target: 45 meetings (iii) Selection of and completion of baseline data collection in 8 political constituencies. Target: 8 (iv) Complete an independent review of the ASER survey with key stakeholders to increase robustness of the sampling methodology reflecting best practices in sample weighting, ensure Urban and Rural designs are well integrated to produce national level estimates | 2.1 ASER Methodology approved and endorsed by key stakeholders (PIE, PBS and FCDO) incorporating third party/external recommendations. 2.2. ASER 2025-26 survey draft report completed in all districts/Primary sampling units including using digital tools with GPS tracking. 2.3. Baseline Political constituency report finalised, (a). with 8 report cards developed and disseminated to stakeholders in consultation with Election Commission of Pakistan (ECP) and parliamentarians through at least (b) 8 constituency-level dialogues to promote accountability and action on foundational learning. 2.4. ASER data and thematic briefs cited in (a). 3 national or provincial education policy documents, sector plans, or official statements, (b). and used to inform planning or advocacy by at least 5 government or civil society stakeholders. | (i). ASER 2025-26 national report finalized and launched; disaggregated data sets made publicly accessible. (ii). Findings presented in at least 1 national and 6 provincial policy forums. (iii). Six report cards developed (iii). Sustainability roadmap developed for continued civil society-led data generation beyond the project period. | ASER is widely recognised in the education sector, there is assumption that ASER data will inform more policy making on education with PIE, MOFPT and Provincial govts.
59:108J12660:10559:14159:11559:11459:11359:11259:11059:10859:11059:11259:11359:11459:11559:114 | IMPACT WEIGHTING (%) |  | Achieved |  | (i) Pilot survey in urban settlements completed; (ii) Survey tools are reviewed for suitability for assessing learning levels of children with hearing impairments | i) Survey tools developed and approved by BHC, training of enumerators completed, data collection completed and draft report submitted; ii) Disaggregated data for girls and children with disabilities along with gender wise comparison of learning published in the Annual ASER report; iii) Concept note and survey tools finalised for selected political constituencies, training of enumerators completed, data collection completed and draft report submitted. | i) Quality in the Katchi Abadis Katchi Abadis Pilot: Learning of Pakistan survey in urban settlement is completed (this includes data collection, report analysed and completed and disseminated to key stakeholders at national and sub national levels). ii) ITA conducted education surveys in four constituencies in Punjab, KP, and Sindh, covering strongholds of all major political parties. The project included a review of education commitments in political party manifestos and report cards for each constituency were produced conveying the findings from the school administrative and learning assessment data collected iii) ASER 2023 underwent a significant digital transformation in the review period. ITA hired a third party who developed an interactive, user friendly mobile phone app for the ASER. The app is being piloted in around 50% of districts. Pilot districts were selected based on the digital readiness of downstream partners and are being remotely monitored to ensure reliability and troubleshoot teething issues. The ASER app has enabled real time reporting. A new ability to conduct spot-checks using the GPS feature, if activated, could allow for authentication and increased confidence in data reporting. iv)ITA were slow to initiate spot checks until the ASER data collection was well underway and so, at the time of writing, 36 spot checks have been made, with only Punjab and Sindh meeting the log frame target of a minimum of ten spot checks per province. The milestone has been missed by 30% | Achieved | 2.1. Met -The ASER 2025 methodology was jointly reviewed and finalised with the Pakistan Institute of Education (PIE) and Pakistan Bureau of Statistics (PBS). 2.2. Met - Data collection was completed across all 158 districts and 6,681 sampling blocks. 2.3. Met - The Baseline Political Constituency Report covering 8 constituencies is completed with constituency specific report cards produced and disseminated. 8 dialogues were held with elected parliamentarians, district actors and ECP focal persons. 2.4. Partially met - ASER data was widely used and cited, but documentation is insufficient to confirm use by five or more distinct actors, so the full milestone cannot be verified.
| 10% |  | Source | [7 empty] | RISK RATING
|  |  | ITA-ASER quarterly reports | [7 empty] | Moderate
| INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  |  | FCDO SHARE (%)
£1,404,687 ITA
| INPUTS (HR) | FCDO (FTEs)
FR 0.1 FTE, RA 0.1 FTE, TR 0.3 FTE
| OUTPUT 3 | Output Indicator 3.1 |  | Baseline (2020) | Milestone 1 (Sep 2021) | Milestone 2 (Sep 2022) | Milestone 3 (Sep 2023) | Milestone 4 (Dec 2024) | Target (Dec 2025) | Target (Dec 2026) | Assumptions
| Evidence on what works to improve education service delivery in Pakistan produced and synthesised (OPM) | Number of consortium-led and grant-funded research studies initiated and completed in alignment with project's finalised research agenda, disaggregated by i) gender (proportion of women as Principal Investigator) ii) location of the study (province), iii) studies using disaggregated data by gender, disability, or other marginalisation indicator. | Planned | No research consoritum exists in Pakistan | Research Consortium procurement completed | Research Consoritum procurement completed. | RC procurement is completed with key team members on boarded and selected firm finalises ways of working document. | (i) 15 consortium-led research studies initiated + 1 research agenda published | 1. Consortium-led (CL): All inception reports of 12 CL studies completed and approved; 8 CL studies mid-term review reports completed and approved; 2 consortium-led research studies completed. 2. Grants: 10 research studies commissioned through grant fund; 13 grant inception reports completed and approved; 2 grant mid-term reports completed and approved. | 10 CL studies completed No. research studies commissioned through grant fund (depends on NCE and FCDO) 8 grant studies completed 6 remaining grant studies completed by Dec 26 | There is sufficient supply in the Pakistani education research sector to service the needs of DARE’s research objectives; and there are enough tangible research projects (policies, innovations in practice etc.) to provide the opportunities for research. Innovations are tested through rigorous research methods, based on trusting, challenging and productive partnerships between implementers and researchers. Successful partnerships will be important to the success of this output because implementers need to feel they can open their innovations up to research and perceive the benefits of this, while researchers will need to develop a deep understanding of the context and design of innovations. This is a key interdependency.
|  |  | Achieved |  | Research Consortium procurement is ongoing due to be completed at the end of November 2021 | Contract Award letters have been sent but the procurement is on pause. | Supplier onboarded and contract signed with OPM on 17 July 2023. Within the first two months, OPM successfully filled 80% positions. And within the first month, OPM brought all partners together to establish a strong understanding of the programmes objectives and shared a ways of working document with FCDO which has been finalised and endorsed by FCDO. | Achieved | Exceeded – All CL studies 12 have completed their inception reports, 8 completed the midterm report, 4 studies have been finalised. Met – 10 commissioned (Cycle 2). 13 inception reports completed and approved. Midterm 2 completed and approved (Cycle 1). Call 2 received 191 studies and 10 were commissioned. This brings the total of active studies to 30.
Source
Research consortium quarterly progress reports; external evaluation of programme for endline
|  | Output Indicator 3.2 |  | Baseline (2020) | Milestone 1 (Sep 2021) | Milestone 2 (Sep 2022) | Milestone 3 (June 2023) | Milestone 4 (Dec 2024) | Target (Dec 2025) | Target (Dec 2025)
|  | Number of implementation pilot to scale initiatives on teaching and learning supported and researched or number of scalability research studies | Planned | (i) 0; (ii) 0; (iii) 0. | 0 | 12 | N/A | 4 implementation pilot to scale-up initiatives finalised and mobilised | 1. Progress report for 1 implementation pilot-to-scale initiative (on Student Cohort 1) completed. 2. 4 research studies on scalability finalised and approved. 4 inception reports completed and approved.. | Final completion report for 1 implementation pilot-to-scale initiative. 4 research studies on scalability finalised and approved.
|  |  | Achieved |  |  |  |  | Partially met – 3 Pilot to Scale identified but only 1 Pilot supported due to a mutually agreed change of approach | Met – 1 Pilot was initiated and is in implementation. Progress report for cohort 1 has been received and approved. 4 research studies finalised, approved, and contracted. Inception reports for all studies
Source
Research consortium quarterly progress reports
|  | Output Indicator 3.3 |  | Baseline (2020) | Milestone 1 (Sep 2021) | Milestone 2 (Sep 2022) | Milestone 3 (Sep 2023) | Milestone 4 (Dec 2024) | Target (Dec 2025) | Target (Dec 2026)
|  | Number of synthesis products/working papers, addressing critical evidence gaps in education and aligned with government priorities | Planned | 0 | 0 | 0 | Consultations on capacity building needs identification held with relevant stakeholders | 4 synthesis products/working papers produced | 5 scoping papers commissioned and completed | 15 new scoping papers are commissioned and completed.
|  |  | Achieved |  | 0 | N/A | A preliminary capacity building plan and approach was shared with FCDO and a capacity strengthening plan is on track to be submitted during the inception period. | Partially met – 5 papers were commissioned, but none were finalised. | Met – All 5 papers, which were commissioned last year, have been completed and presented to FCDO
Source
Research consortium quarterly progress reports
|  | Output Indicator 3.4 |  | Baseline (2020)E84:K84 | Milestone 1 (Sep 2021) | Milestone 2 (Sep 2022) | Milestone 3 (Sep 2023) | Milestone 4 (Dec 2024) | Target (Dec 2025) | Target (Dec 2026)
|  | Number of DARE-RC studies submitted to international conferences, accepted and presented | Planned | 0 | No milestones for this year | No milestones for this year | No milestones for this year | No milestones for this year | 5 proposals submitted for conferences taking place in 2025, at least 50% accepted, and presented. | 13 proposals submitted for conferences taking place in 2026, at least 50% accepted, and presented.
|  |  | Achieved | [5 empty] | Exceeded – 5 proposals were submitted, and 3 (60%) were accepted and presented in the UK, Botswana and the US
Source
Research consortium quarterly progress reports
|  | Output Indicator 3.5 |  | Baseline (2020)E84:K84 | Milestone 1 (Sep 2021) | Milestone 2 (Sep 2022) | Milestone 3 (Sep 2023) | Milestone 4 (Dec 2024) | Target (Dec 2025) | Target (Dec 2026)
|  | Research Interest Groups established and convene quarterly meetings around DARE-RC themes | Planned |  | No milestones for this year | No milestones for this year | No milestones for this year | No milestones for this year | 4 research interest groups established. 2 meetings per group held (total 8 meetings) | 3 meetings per group held (12 meetings) to discuss and document emerging findings in the respective thematic areas
|  |  | Achieved | [5 empty] | Met – 4 research interest groups established, and 8 total meetings held
Source
Research consortium quarterly progress reports
|  | Output Indicator 3.6 |  | Baseline (2020)E84:K84 | Milestone 1 (Sep 2021) | Milestone 2 (Sep 2022) | Milestone 3 (Sep 2023) | Milestone 4 (Dec 2024) | Target (Dec 2025) | Target (Dec 2026)
| Strengthened domestic education research capacity | Number of education research users (federal and provincial governments) participating in capacity strengthening activities and reporting satisfaction with the activities | Planned |  | No milestones for this year | No milestones for this year | None Consultations on capacity building needs identification held with relevant stakeholders | On average, at least 30 research users reporting 85% satisfaction with capacity strengthening activities and benefitting from 72 workshop hours and 76 mentoring/backstopping hours. | On average, at least 15 research users reporting 85% satisfaction with capacity strengthening activities and benefitting from 16 workshop hours | N/A
|  |  | Achieved |  |  |  | Achieved | Exceeded – On average 37 research users attended 4 workshops and reported 92% satisfaction rate, including 56 hours of workshops and 76 hours of mentoring and backstopping. | Met – Cumulative Satisfaction Rate: 86%.
Source
Research consortium quarterly progress reports
|  | Output Indicator 3.7 |  | Baseline (2020)E84:K84 | Milestone 1 (Sep 2021) | Milestone 2 (Sep 2022) | Milestone 3 (Sep 2023) | Milestone 4 (Dec 2024) | Target (Dec 2025) | Target (Dec 2026)
| Sustained engagement with Federal and Provincial government representatives researchers, practitioners and development partners for bridging the gap between research and policy | Number of DARE-RC engagement events held disaggregated by type of event | Planned |  | No milestones for this year | No milestones for this year | No milestones for this year | No milestones for this year | A total of 13 events, including 8 policy engagement events 1 Research symposium, 4 webinars | 17 total 12 policy engagement events (Provincial roundtable/Policy Exchanges, Thematic discussion/dialogue, bilateral consultation and briefings Study specific events and engagement , policy dialogues ) 1 Research symposium 4 webinars
|  |  | Achieved | [5 empty] | Exceeded – a total of 20 events were organised.
Source
Letter of understanding/Mutually-agreed plan with NIM for capacity strengthening of civil servants, Workshop Report
|  | Output Indicator 3.8 |  |  | Milestone 1 (Sep 2021) | Milestone 2 (Sep 2022) | Milestone 3 (Sep 2023) | Milestone 4 (Dec 2024) | Target (Dec 2025) | Target (Dec 2026)
|  | 1 annual conferences held to discuss/disseminate DARE-RC research | Planned | [5 empty] | 1 annual conference held | 2nd annual conference held
|  |  | Achieved | [5 empty] | Met – the Summit was held in early December 2025. | N/A
|  | No. of open access digital platforms (For example DARE-RC website, R4D website MOST imp for international reach, AKU-IED website, PIE etc.) where DARE-RC's research outputs/products is made available. |  |  | Achieved |  |  | Partially met – DARE-RC and World Bank are working closely to support data governance at PIE. | 1 | 3
| IMPACT WEIGHTING (%) | Output Indictor 3.9 |  | Baseline (2020)E84:K84 | Milestone 1 (Sep 2021) | Milestone 2 (Sep 2022) | Milestone 3 (Sep 2023) | Milestone 4 (Dec 2024) | Target (Dec 2025) | Target (Dec 2026)
| 50% | Evidence of collaboration on research and evidence uptake with other FCDO supported programmes (GOAL, BTAG, WWHGE) and other development partners | Planned |  |  |  |  | At least 2 collaborations identified with the World Bank to support research users | At least 2 collaborations identified through consultative meetings with FCDO supported programmes and development partners
|  |  | Achieved |  |  |  |  | Achieved | Met – engaging with both bilateral, CMPs and other multilaterals took place leading to effective exchanges.
|  |  | Source | [7 empty] | RISK RATING
|  |  | Research consortium quarterly progress reports | [7 empty] | Moderate
£7,747,140 OPM
FCDO (FTEs)
FP 0.2 FTE; RA 0.2 and TR 0.6 FTE, SA 0.05 FTE
| OUTPUT 4 | Output Indicator 4.1 |  | Baseline (2020) | Milestone 1 (Sep 2021) | Milestone 2 (Sep 2022) | Milestone 3 (Sep 2023) | Milestone 4 (Dec 2024) | Target (Dec 2025) | Target (Dec 2026)
| Improved learning outcomes through innovative education practices (TFP) | Number of total teachers/fellows trained to be placed in public schools (disaggregated by gender) (cumulative) | Planned | 37 teachers/fellows 17 male 20 Female | 77 teachers/fellows | 151 teachers/fellows 68 male 83 female | 155 teachers/fellows 68 male 87 female | 150 teachers/fellows 60% female fellows 40% male fellows 80% in Islamabad and 20% in Karachi | 150 teachers/fellows 60% female fellows 40% male fellows 70% Islamabad and 30% Karachi.
|  |  | Achieved |  | 85 28 male 57 female | 155 teachers/fellows 41 male 114 female | 158 teachers/fellows 111 female 47 male | Achieved | Exceeded – 175 in October - 70% in Islamabad & 30% in Karachi. 67% females, 33% males
Source
TFP quarterly progress reports
|  | Output Indicator 4.2 |  | Baseline (2020) | Milestone 1 (Sep 2021) | Milestone 2 (Sep 2022) | Milestone 3 (Sep 2023) | Milestone 4 (Dec 2024) | Target (Dec 2025) | Target (Dec 2026)
|  | Number of students reached with improved teaching methods | Planned | 1166; Girls: Disability: Unknown | Total: 3850 Girls: 50% Children with disabilities: 10% | Total: 7550 Girls: 65% Children with disabilities: 6% | Total: 9450 Girls: 65% Children with disabilities: 6% | Total: 10,000 Girls: 60% Children with disabilities: 6% | Total:10,000 Girls: 60% Children with disabilities: 6% using Washington Group questions. | TBC
|  |  | Achieved |  | Total: 5341 Girls: 3610 Children with disabilities: data not collected | Total: 10,167 Girls: 74% Children with disabilities: Tools translated and piloted. Data collection planned for October 2022. | Total 10,203 students across 61 schools benefiting from TFP fellows’ teaching since August 2023. Of these, 65% are girls. | Achieved | Exceeded – Total: 12,500 (61% girls, and 22% children with disabilities )
Source
TFP quarterly progress reports
|  | Output Indicator 4.3 |  | Baseline (2020) | Milestone 1 (Sep 2021) | Milestone 2 (Sep 2022) | Milestone 3 (Sep 2023) | Milestone 4 (Dec 2024) | Target (Dec 2025) | Target (Dec 2026)
|  | Student learning outcomes improved in: (i) Maths (%) (ii) English (%) | Planned | (i) English (14% meeting Grade level competency) (ii) Maths (12% meeting Grade level competency) | Summative assessment at end of academic year so not measured in Year 1. | (i) English - 40% meeting grade level competency (ii) Maths - 35% meeting grade level competency | (i) English - 40% meeting grade level competency (ii) Maths - 35% meeting grade level competency | (i) Average mastery of TFP students in English - 30% (ii) Average mastery of TFP students in Math - 30% | i) Average mastery of TFP students in English- 30% (ii) Average mastery of TFP students in Math - 30% (iii) Students taught by TFP make 5 months of greater learning gains in one academic cycle than their peers taught by government teachers | TBC
|  |  | Achieved | Note: Context of pandemic and school closures reflecting low improvement levels |  | (i) English - 33% meeting grade level competency (ii) Maths - 30% meeting grade level competency | In English, students taught by Fellows for two academic years scored an average of 44% on assessments while students taught by Fellows for one academic year scored 40%, from a baseline of 18%. Gains in Maths were even stronger. The average mastery of grade level concepts for students taught by Fellows for two years was 48%, and for students taught by Fellows for one year, it was 42%, from a baseline of just 8%. Overall, in two years with a Teach for Pakistan Fellow, students make, on average, 4.4 years of academic growth. | Exceeded - average mastery of TFP students: English 47%, Math: 37% | Exceeded – (i) Average mastery of TFP students in English - 42% (ii) Average mastery of TFP students in Math - 38% (iii) RAND independent evaluation showed that TFP taught students achieved between 6-10 months of additional learning in Math and English.
Source
|  | Output Indicator 4.4 | [6 empty] | Target (Dec 2025)
|  | Evidence of Teach For Pakistan's approach to teacher recruitment and development being adopted by regional governments (federal or provincial) | Planned |  | No milestones for this year | No milestones for this year | No milestones for this year | No milestones for this year | At least two policy changes or programmes influenced by TFP approach
|  |  | Achieved | [5 empty] | Partially met – limited evidence that TFP model is being adopted at scale by the government. Some evidence of ongoing partnership discussions with government, and that TFP’s fellows are sought after by organisations working on Teacher Professional Development.
IMPACT WEIGHTING (%)
10%
£2,442,606 TFP
|  | FCDO (FTEs) | [8 empty] | RISK RATING
|  | FP 0.2 FTE; RA 0.2 and TR 0.6 FTE, SA 0.05 FTE | [8 empty] | Moderate
Note on C133: new text in red, based on RAND study reporting methods as interpreted using PISA and Hanushek, E. A., Woessmann, L., & Peterson, P . E. (2012) as benchmarks -Khadija S Bakhtiar

## Change Frame
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE - December 2024 | AUTHOR | DETAILS OF CHANGE September 2025 | Author
1 | Impact Indicator 1 | Milestone added for December 2024: 'Complete and functioning central database on learning outcomes. Girls: Boys: Children with disabilities: Punjab: KP: Sindh: Balochistan: | Salim Salamah | None Note: DARE Business Case was extended from June 2025 till December 2026. All targets for June 2025 have been moved to December 2026. | Tahira (on behalf of Salim)
2 | Impact Indicator 2 | Indicator updated: '(i) Budget allocations to learning assessments as measured by PIE annual budgets' Indicator added: '(iii) Increased willingness and capacity of decision makers to use research for education policy making' | Ivanna Smith | None | Tahira (on behalf of Salim)
|  | Milestones added for December 2024: '(i) Increase by 5%; (ii) District Ranking Index launched and discussions started wih the Minstry of Finance and Ministry of Planning to use the Index for allocation decisions to lagging districts (iii) 4 agreements reached between DARE RC and research users (decision makers) to use research in policy making AND 3 provincial bodies engaged by DARE RC leading to their effective use of research and policy making' | Salim Salamah |  | Tahira (on behalf of Salim)
3 | Outcome 1, Indicator 1 | Milestones added for December 2024: (i) Annual statistical report (PES) 2023-24 which is DSF compliant is published AND NAT scope and tools are finalised for NAT 2025 allowing PIE to report internationally against SDG4 (ii) Draft Plan of Actions on Data integration are approved at the provincial and federal level. AND 2nd iteration of DSF support initiated informed by review of 1st iteration support. AND Data sharing at all levels based on agreed upon access protocols (iii) PIE is functioning, 90% of vacancies are filled and has conducted at least two deep-dive analysis/studies relevant for provincial governments | Salim Salamah | Target 2026/27 added -whcih is the same as milestone for 26/27 "(i) Annual statistical report (PES) 2023-24 which is DSF compliant is published AND NAT scope and tools are finalised for NAT 2025 allowing PIE to report internationally against SDG4 (ii) Draft Plan of Actions on Data integration are approved at the provincial and federal level. AND 2nd iteration of DSF support initiated informed by review of 1st iteration support. AND Data sharing at all levels based on agreed upon access protocols (iii) PIE is functioning, 90% of vacancies are filled and has conducted at least two deep-dive analysis/studies relevant for provincial governments". | Tahira (on behalf of Salim)
4 | Outcome 1, Indicator 2 | Indicator updated: '(iii) Number of researchers from Pakistani education research community reporting benefits of capacity building activities' |  | None | Tahira (on behalf of Salim)
|  | Milestones added for December 2024: (i) Timely, efficient, and complete databases is available to decision-makers, including PES, and preparations are underway for NODP AND Composite Index informed District Education Rankings developed. AND 1 Impact story (contribution narrative) showing that large-scale reform efforts are influenced by DARE RC research and key decision makers are influenced to change policy and practice accordingly (ii) 8 citation of learning assessments results (ITA, PIE and WB) AND Two impact stories about how ASER Nationwide National Assessment for SDG 4.1.1 a and SDG 4.1 and Right to Education has been informing accountability and actions for Foundational Learning (iii) % increase in the knowledge of Research users participating in capacity strengthening activities |  | Milestone added: "(i) Analysis of survey results shows policy makers have an increased demands for, improved access to and better understanding of education evidence; (ii) 80% of researchers /participants rated trainings as 'good' or 'excellent' and stated they had 'learned a new skill' (iii) 1 impact story showing that large-scale reform efforts are influenced by DARE-RC research and key decision makers are influenced to change policy and practice accordingly AND Number of agreements reached between research users and DARE-RC on policy and research (4 agreements) | Tahira (on behalf of Salim)
5 | Outcome 1, Indicator 3 | Milestone added for December 2024: 'EMIS data is routinely presented and used to inform response to crises.' |  | None | Tahira (on behalf of Salim)
6 | Output 1, Indicator 1.1 | Milestone added for December 2024: i) Updates to the National Data Standardisation Framework (DSF) done in consultation with EMIS TWG, approved by MoFEPT and Provinces; ii) National Data Regime continues its second round of implementation (ASC conducted in light of updated DSF); iii) PIE plan to operate and manage the NODP is approved by MoFEPT (iv) 1 Pakistan Education Statistics 2023-2024 published by December 2024 (within 4 months of data collection) aligned with DSF (v) Development of 5 detailed provincial Plans of Actions for horizontal (national/provincial) and vertical integration (national) for DSF implementation with clear timelines for completing the integration of existing digital data across departments and inter-departments (vi) 5 Access protocols at federal and provincial levels are agreed and approved setting the standards efficient exchange of data at all provincial and federal levels. | Ivanna Smith | Milestone added for December 2025 a) Align ASC 2025 tools with the updated DSF by November 2025 for nationwide implementation across all provinces. b) Update 5 detailed provincial Plans of Action for horizontal (national/provincial) DSF integration, including clear timelines for integrating existing digital data across departments. c) Review and update 5 federal and provincial data access protocols with inputs from provincial departments to enable efficient data exchange at all levels d) Conduct 2 EMIS TWG sessions as a platform for inter-provincial learning, expanding scope to engage Development Partners (including UNICEF and UNESCO) for improved coordination and PIE-driven alignment. | Tahira (on behalf of Salim)
7 | Output 1, Indicator 1.2 | Indicator updated to: 'Education sector level coordination and cooperation is enhanced across Pakistan.' | Ivanna Smith | Milestones added for December 2025: a) Complete the pilot for NAT 2026 and finalize sample calculation for large-scale implementation, along with development of test items. b) Develop National foundational learning Benchmarks for Grade 3 and complete the pilot of the Foundational Learning Assessment. c) Support the development of Foundational Learning policy delivery plans, a structured pedagogy package, and the Foundational Learning Assessment Framework. d) Complete and publish 2 policy-relevant studies. (Devolution and Learning Losses) e) Initiate provincial engagement on aligning LSAs with NAT | Tahira (on behalf of Salim)
|  | Milestones added for December 2024: (i) NAT 2023 results inform series of MOFEPT/PIE guidelines on national education policy priority issues including 1) teacher training and professional development 2) curriculum and c) assessment for learning. (ii) NAT 2025: Tools and test items for NAT 2025 with expanded scope are developed by December 2024 and piloted in 4 provinces and ICT by February 2025. (iii) Development of 1 National Assessment Framework to Standardize Assessments for grants grades 2/3 (by Foundational Learning Hub), 5 and 8 by PIE (iv) EMIS Data TWG (2 sessions) continues to be a platform for inter-provincial learning and exchange, and its scope is expanded to include and engage other Development Partners (including UNICEF and UNESCO) for improved coordination and alignment driven by PIE. (v) Completion of two policy relevant studies on 1 Devolution study (one study) published and 1 District Rankings (one study) Published (vi) The Foundational Learning Hub supports the implementation the national foundational learning policy including through the development of teacher learning and training materials |  |  | Tahira (on behalf of Salim)
8 | Output 1, Indicator 1.3 | Milestones added for December 2024: (i) Pilot Private School Survey launched and tested. (1 Pilot) (ii) Dissemination activities: Organize roundtables to launch the Global Education Policy Dashboard (GEPD) targeting stakeholders in the Government, Development Partners and Civil Society organizations (6 round tables). Publish and launch Composite Index Informed District Education Rankings published and disseminated (1 event). Launch of NAT 2023 (1 national event, and 4 provincial) (total: 12 events) (iii) To ensure wide and sustainable dissemination of DARE research, agree the Terms of Reference for 1 online training course (to be completed following the end of the current TA support in June 2025) hosted on PIE website using case studies from TEACH/COACH and GEPD work, as well as the policy linking training and others delivered throughout the course of the programme. (1 course) | Ivanna Smith | Milestones added for December 2025 (i). ASER Methodology approved and endorsed by key stakeholders (PIE,PBS and FCDO) incorporating third party/external recommendations. (ii)ASER 2025-26 survey draft report completed in all districts/Primary sampling units including using digital tools with GPS tracking (Disaggregated data collected for gender, disability, and informal urban/rural settlements and integrate WHO/UNICEF) (iii) Baseline Political constituency report finalised, (a). with 8 report cards developed and disseminated to stakeholders in consultation with ECP and parliamentarians through at least (b) 8 constituency-level dialogues to promote accountability and action on foundational learning [committed deep dive data..] (iv). ASER data and thematic briefs cited in (a). 3 national or provincial education policy documents, sector plans, or official statements, (b). and used to inform planning or advocacy by at least 5 government or civil society stakeholders. | Tahira (on behalf of Salim)
9 | Output 2, Indicator 2.1 | Milestones added for December 2024: (i) Development of six thematic report cards on data collected during ASER 2023 (Gender, Foundational Learning, Climate Change, Facilities with SMC’s, Equity & Disability, Technology) – Target: 6 (ii) Number of dissemination events of ASER 2023 findings across Pakistan with all relevant stakeholders (communities, district authorities, teachers’ association, youth organisation and media outlets) – Target: 45 meetings (iii) Selection of and completion of baseline data collection in 8 political constituencies. Target: 8 (iv) Complete an independent review of the ASER survey with key stakeholders to increase robustness of the sampling methodology reflecting best practices in sample weighting, ensure Urban and Rural designs are well integrated to produce national level estimates | Ivanna Smith | Milestones added for December 2025 Total: 10 studies commissioned, 25 inception reports completed, 10 midterm reports completed, 2 studies completed. CL: All inception reports of 12 CL studies completed and approved; 8 CL studies mid-term review reports completed and approved; 2 consortium-led research studies completed. Grants: 10 research studies commissioned through grant fund; 13 grant inception reports completed and approved; 2 grant mid-term reports completed and approved. | Tahira (on behalf of Salim)
10 | Output 3 | Output language updated to include 'The consortium builds the capacity of key research producers and users and ensure research uptake through sustained engagement with key decision makers' | Salim Salamah | None | Tahira (on behalf of Salim)
11 | Output 3, Indicator 3.1 | Indicator updated from 'Research consortium established and runs efficiently, bringing all consortium members to meet agreed performance milestones' to 'High quality research outputs provide new evidence on country level education systems and education reforms (i) Number of consortium-led research studies initiated and completed, disaggregated by i) gender (proportion of women as Principal Investigator) ii) location of the study (province), iv) studies using disaggregated data by gender, disability, or other marginalisation indicator. (ii) Number of research studies submitted to peer reviewed academic journals; (iii) Number of research studies accepted for publication in peer reviewed academic journals | Salim Salamah | Indicator changed from " 'High quality research outputs provide new evidence on country level education systems and education reforms (i) Number of consortium-led research studies initiated and completed, disaggregated by i) gender (proportion of women as Principal Investigator) ii) location of the study (province), iv) studies using disaggregated data by gender, disability, or other marginalisation indicator. (ii) Number of research studies submitted to peer reviewed academic journals; (iii) Number of research studies accepted for publication in peer reviewed academic journals" To "Number of consortium-led and grant-funded research studies initiated and completed in alignment with project's finalised research agenda, disaggregated by i) gender (proportion of women as Principal Investigator) ii) location of the study (province), iii) studies using disaggregated data by gender, disability, or other marginalisation indicator". Milestones added for December 2025 (i) 15 consortium-led research studies initiated + 1 research agenda published | Tahira (on behalf of Salim)
|  | Milestone added for December 2024 '15 consortium led studies + 1 research agenda' |  |  | Tahira (on behalf of Salim)
12 | Output 3, Indicator 3.2 | Indicator changed from 'High quality research outputs provide new evidence on country level education systems and education reforms (i) Number of research studies commissioned; (ii) Number of research studies submitted to peer reviewed academic journals; (iii) Number of research studies accepted for publication in peer reviewed academic journals' to 'Number of research studies commissioned through competitive grants process, disaggregated by i) gender (proportion of women as Principal Investigator) ii) location of the study (province), iv) using disaggregated data by gender, disability, or other marginalisation indicator.' | Salim Salamah | Output indicator From Number of research studies commissioned through competitive grants process, disaggregated by i) gender (proportion of women as Principal Investigator) ii) location of the study (province), iv) using disaggregated data by gender, disability, or other marginalisation indicator. To Number of implementation pilot to scale initiatives on teaching and learning supported and researched or number of scalability research studies Milestone added for Deember 2025 1. Progress report for 1 implementation pilot-to-scale initiative (on Student Cohort 1) completed. 2. 4 research studies on scalability finalised and approved. 4 inception reports completed and approved.. | Tahira (on behalf of Salim)
|  | Milestone added for December 2024 ' Call 1 and Call 2 for proposals launched, with 15 research studies commissioned from Call 1' |  |  | Tahira (on behalf of Salim)
13 | Output 3, Indicator 3.3 | Indicator changed from 'Policy makers and key stakeholders are engaged in research cycle: Number of engagements between consortium individuals/members and national/international stakeholders to discuss evidence or analysis (including research question co-creation workshops and evidence dissemination events)' to 'Number of implementation pilot to scale initiatives supported to take their innovative approached to teaching and learning to scale and are thh focus of research' | Salim Salamah | Indicator changed from 'Number of implementation pilot to scale initiatives supported to take their innovative approached to teaching and learning to scale and are thh focus of research' to 'To Number of synthesis products/working papers, addressing critical evidence gaps in education and aligned with government priority areas, produced. Mile stone added for December 2025 5 scoping papers commissioned and completed | Tahira (on behalf of Salim)
|  | Milestone added for December 2024 '4 implementation pilot to scale-up initiatives finalised and mobilised' |  |  | Tahira (on behalf of Salim)
14 | Output 3, Indicator 3.4 | Indicator changed from 'Number of tranings in which academics at Pakistani education research institutes, universities and think tanks, are strengthened in their capability and expertise to conduct high quality research' to 'Number of rigorous, robust and policy-relevant synthesis products/working papers completed, addressing criticial evidence gaps in education and disaggregated by the proportion using data disaggregated by gender, disability and/or other markers of marginalisation.' | Salim Salamah | Indicator changed from 'Number of tranings in which academics at Pakistani education research institutes, universities and think tanks, are strengthened in their capability and expertise to conduct high quality research' to 'Number of rigorous, robust and policy-relevant synthesis products/working papers completed, addressing criticial evidence gaps in education and disaggregated by the proportion using data disaggregated by gender, disability and/or other markers of marginalisation.' To Number of DARE-RC studies submitted to international conferences, accepted and presente Milestones added for December 2025 5 proposals submitted for conferences taking place in 2025, at least 50% accepted, and presented. | Tahira (on behalf of Salim)
|  | Milestone added for December 2024: '4 synthesis products/working papers produced' |  | Milestone added for December 2024: '30 research users reporting 85% satisfaction with capacity strengthening activities and benefitting from 72 workshop hours and 76 mentoring/backstopping hours.' | Tahira (on behalf of Salim)
15 | Output 3, Indicator 3.5 | Indicator added this year: Number of education research users (federal and provincial governments) participating in capacity strengthening activities and reporting satisfaction with the activities (disaggregated by type of capacity strengthening activity, type of participant and gender) Satisfaction to be captured on a 1-5 scale | Ivanna Smith | Indicator added From Number of education research users (federal and provincial governments) participating in capacity strengthening activities and reporting satisfaction with the activities To Research Interest Groups established and convene quarterly meetings around DARE-RC themes Milestones added for December 2025 4 research interest groups established. 2 meetings per group held (total 8 meetings) | Tahira (on behalf of Salim)
|  | Milestone added for December 2024: '30 research users reporting 85% satisfaction with capacity strengthening activities and benefitting from 72 workshop hours and 76 mentoring/backstopping hours.' |  |  | Tahira (on behalf of Salim)
16 | Output 3, Indicator 3.6 | Indicator added this year: '%age increase in the knowledge of research users participating in capacity strengthening activities' | Salim Salamah | Indiator added from Number of education research users (federal and provincial governments) participating in capacity strengthening activities and reporting satisfaction with the activities (disaggregated by type of capacity strengthening activity, type of participant and gender) To Number of education research users (federal and provincial governments) participating in capacity strengthening activities and reporting satisfaction with the activities (disaggregated by type of capacity strengthening activity, type of participant and gender) Milestone added for December 2025: On average, at least 15 research users reporting 85% satisfaction with capacity strengthening activities and benefitting from 16 workshop hours | Tahira (on behalf of Salim)
|  | Milestone added for December 2024: 'At least 20% average increase from pre-test scores' |  |  | Tahira (on behalf of Salim)
17 | Output 3, Indicator 3.7 | Indicator added for this year: 'Partnerships established with NIM/NSPP and trainings organised with senior civil servants as consumers of research to increase their capacity on use of evidence in policy making' | Salim Salamah | Indicator added from 'Partnerships established with NIM/NSPP and trainings organised with senior civil servants as consumers of research to increase their capacity on use of evidence in policy making' To Number of DARE-RC engagement events held disaggregated by type of event Milestone added for December 2025: A total of 13 events, including 8 policy engagement events 1 Research symposium, 4 webinars | Tahira (on behalf of Salim)
|  | Milestone added for December 2024: 'Partnerships with NIM/NSPP established and 2 trainings delivered to senior civil servants.' |  | Milestone added for December 2025:At least 2 collaborations identified through consultative meetings with FCDO supported programmes and development partners | Tahira (on behalf of Salim)
18 | Output 3, Indicator 3.8 | Indicator added for this year: 'DARE RC and development partners, including World Bank, identify synergies and areas of collaboration around capacity building and policy influencing' | Salim Salamah | Indicator added from 'DARE RC and development partners, including World Bank, identify synergies and areas of collaboration around capacity building and policy influencing' To 1 annual conferences held to discuss/disseminate DARE-RC research Milestone added for December 2025: 1 annual conference held | Tahira (on behalf of Salim)
|  | Milestone added for December 2024: At least 2 collaborations identified with the World Bank to support research users |  |  | Tahira (on behalf of Salim)
| Output 3, Indicator 3.9 |  |  | New output indicator added: Evidence of collaboration on research and evidence uptake with other FCDO supported programmes (GOAL, BTAG, WWHGE) and other development partners
19 | Output 4, Indicator 4.1 | Milestone added for December 2024: '150 teachers/fellows 60% Female Fellows 40% Male Fellows 80% in Islamabad and 20% in Karachi' | Ivanna Smith | Indicator added Number of total teachers/fellows trained to be placed in public schools (disaggregated by gender) (cumulative) Milestones added for December 2025 150 teachers/fellows 60% female fellows 40% male fellows 70% Islamabad and 30% Karachi. | Tahira (on behalf of Salim)
20 | Output 4, Indicator 4.2 | Milestone added for December 2024: 'Total: 10,000 Girls: 60% Children with disabilities: 6%' | Ivanna Smith | Indictor added Number of students reached with improved teaching methods Milestone added for December 2025: Total:10,000 Girls: 60% Children with disabilities: 6% using Washington Group questions. | Tahira (on behalf of Salim)
21 | Output 4, Indicator 4.3 | Indicator updated from 'Percentage of students meeting learning outcomes for their grade level and percentage improvement from beginning of the year: (i) English (%) (ii) Maths (%)' to 'Student learning outcomes improved in: (i) Maths (%) (ii) English (%) (The figures in the milestone column refer to average grade level mastery percentages attained in Summative assessments)' | Ivanna Smith | Indictor from 'Student learning outcomes improved in: (i) Maths (%) (ii) English (%) (The figures in the milestone column refer to average grade level mastery percentages attained in Summative assessments)' To Student learning outcomes improved in: (i) Maths (%) (ii) English (%) Milestone added for December 2025: i) Average mastery of TFP students in English- 30% (ii) Average mastery of TFP students in Math - 30% (iii) Students taught by TFP make 5 months of greater learning gains in one academic cycle than their peers taught by government teachers | Tahira (on behalf of Salim)
|  | Milestone added for December 2024: '(i) Average mastery of TFP students in English - 30% (ii) Average mastery of TFP students in Math - 30%' | Ivanna Smith |  | Tahira (on behalf of Salim)
22 | Output 4, Indicator 4.4 |  | Salim Salamah | New output indicator added: Evidence of Teach For Pakistan's approach to teacher recruitment and development being adopted by regional governments (federal or provincial) | Tahira (on behalf of Salim)

## Guidance Notes
Logframe Template Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
The name of the programme to which this logframe applies, from the business case
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from FCDO and partners to achieve the impact, ie is your project nested within a broader undertaking? This will often be the Impact indicator from the Theory of Change in the Business Case.
OUTCOME
The outcome should link through to the outcome level in the programme Theory of Change as stated in the Business Case. The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Sustainable Development Goals (SDGs) or Climate Change.
Ongoing monitoring of progress against outcome milestones takes place as an assessment of whether you expect to achieve the Outcome by the end of the programme in the programme Annual Reviews. An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR) based on the target milestone for the programme completion.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear. Outputs should reflect the Theory of Change as set out in the Business Case for the programme.
Progress towards the outputs will be assessed and scored at the Annual Review, using output indicators and milestones. Achievement of the outputs will be assessed at project completion, using output indicators and targets.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
1. Promote a more considered approach to the choice of Outputs at project design stage; and
2. Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by FCDO and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The FCDO share at Outcome Level is a simple, pro rata calculation of FCDO’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual FCDO Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
Specific – what will be measured? And how?
Measurable - data can be collected
Relevant - to the results chain
Useful – for management decision making
Does not include any element of the target
Can be disaggregated if relevant (especially when the indicator relates to number of beneficiaries reached with an intervention)
A mix of qualitative and quantitative
Already defined - if relevant include indicators which towards the FCDO Outcome Delivery Plan / ICF KPIs / SDGs.
Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Theory of Change and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your PRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / Management Information Systems.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually and you should record the expected frequency of data availability.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability. Use the Data Quality Prof Guide to help you consider the quality of your data.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same. If you are carrying out any evidence gathering to check your assumptions then make reference to this as part of this section.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
Equity - Is the intervention meeting the needs of all beneficiaries?
FCDO’s Approach to Value for Money (PrOF Guide) provides further advice on ensuring VfM.