## Annual Review Template

Title: Regional and International Tax Initiatives (RITI)
Programme Value £ (full life): £35m		Review date: June 2025
Programme Code: [AMP ID#] 300578	AMP start date: / Oct 2018	AMP end date: / 30 November 2025

Summary of Programme Performance
Year	2020	2021	2022	2023	2024	2025
Overall Output Score	A	A+	A+	A	A	A
Risk Rating	Moderate	Moderate	Moderate	Moderate	Minor	Minor

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-GOV-1-300578/documents
DevTracker Link to results framework:

A. SUMMARY AND OVERVIEW

Description of programme
The Regional and International Tax Initiatives (RITI) programme is a multi-faceted, multi-partner programme focused on helping developing countries improve their revenue base. It helps countries benefit from global best practice on revenue mobilisation and engage with and benefit from international tax standards.

RITI supports several international organisations - the Organisation for Economic Cooperation and Development (OECD), the World Bank (through the Global Tax Programme (GTP)), the African Tax Administration Forum (ATAF) and the International Institute for Sustainable Development (IISD). The programme also funds the Platform for Collaboration on Tax (PCT) which promotes and facilitates better coordination between the World Bank, the International Monetary Fund, the OECD and the United Nations.

RITI began in 2018 and is due to end on 30 November 2025.

Summary supporting narrative for the overall score in this review
This annual review reflects key achievements, lessons learned, and challenges faced in advancing international and domestic tax reform efforts over the 12 months to March 2025. Of the twenty-one output indicators for the period under review, seventeen were met or exceeded and four were not met.

Partners continued to demonstrate progress in delivering technical assistance, driving policy reforms, and shaping international discussions/debates through creating and deepening evidence and knowledge. Partners also prioritised efficiency in their operations, with significant efforts to reduce costs, enhance the use of digital platforms, and improve internal coordination across teams and organisations.
In line with these achievements, the programme's overall performance is rated as 'A,' reflecting the ongoing positive impact being achieved.
Major delivery shifts over the reporting period
PCT: A major achievement was the revision of the Tax Incentives Toolkit, supported by stakeholder engagement and a technical seminar in March that shaped its alignment with emerging global tax developments such as the Global Minimum Tax and climate-related policies. The toolkit provides a concise set of high-level principles designed to help decision makers navigate the policy, legislative and administrative issues related to tax incentives. Engaging a broader range of stakeholders, including Ministries of Finance, regional tax organisations and FCDO partners (ie International Institute for Sustainable Development, International Centre for Tax and Development, ODI), has been crucial for the PCT to ensure its work is relevant and actionable. Improved dissemination has helped maximise the reach of the work and will ultimately benefit those who follow the work of the PCT (be they revenue authorities, ministries of finance and other supporting organisations/ think tanks) and will benefit from their products and thought leadership.
IISD: Building on its strong track record in mining and international tax, in 2024 IISD expanded its program into several new areas including tax incentives, environmental tax, and sovereign debt. The new scope offers countries more comprehensive, systematic support to align tax policy with development, climate, and nature goals.
ATAF: In response to growing demand for technical assistance, ATAF expanded its pool of experts and scaled up peer-to-peer exchanges. It has also made progress in diversifying funding sources and increasing member contributions, enabling it to meet the higher demand.
GTP: The GTPs strategic alignment with the World Bank’s Country Partnership Frameworks (CPFs) and Public Finance Reviews (PFRs) has significantly amplified the impact of its activities. The integration of DRM insights into these frameworks has facilitated policy-based lending and strengthened reform efforts. The GTP built partnerships with over 50 organisations, which helped enhance the impact of its work and foster synergies in providing DRM support, especially in international taxation and tax diagnostics.
OECD: The OECD’s independent evaluation in 2024 highlighted the relevance, coherence, and impact of its tax and development activities. The evaluation noted that over 75% of recipients found the OECD's capacity-building work beneficial for improving their skills and strengthening their administrations. Recommendations included strengthening internal coordination, improving engagement with partner organisations aims to refine its approach to international tax issues, particularly in the areas of BEPS/Transfer Pricing.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The theory of change has not changed over this reporting period and remains as set out in the Business Case:

At Impact level, the programme aims to enable developing countries to increase domestic revenues and strengthen fiscal positions in order to finance pro-poor public services.

To achieve impact, developing countries need to strengthen their capacity to increase domestic revenues (Outcome). Outcomes indicators remain unchanged.

At Output level, RITI is designed to deliver progress in four areas: coordination; international standards (design and implementation); capacity-building through support in improving tax policy development and legislative reform; and global public goods through creation and dissemination of knowledge that underpins existing and future capacity building initiatives.

Over the course of 2024, RITI partners continued to address the call to be more inclusive in their approach, advice and implementation. Some of these measures will be addressed later in this annual review.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

This programme is scheduled to come to an end on 30 November 2025. For this new financial year, the focus will be on delivering against existing initiatives and systematically winding up this programme to ensure minimal impact on on-going initiatives that are funded through joint donor contributions.

An interim assessment of impact determined that RITI has been successful to date in delivering against its original outputs and contributing to the overall outcome of the programme. The Programme Completion Report will review this in greater detail and draw lessons for future programming.

## C. DETAILED OUTPUT SCORING

Output Title	[COORDINATION] Improved coordination among international organisations in their support of improved DRM by developing countries
Output number:		1	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of working level meetings attended by all four PCT partners during reporting period	22	Exceeded: 25 (including regular PCT Technical Working Group meetings, PCT Retreat, PCT Tax Incentives Technical Seminar)
1.2 Number of Principals' meetings attended by all four PCT partners	1	Met: 1 (September 2024)
1.3 Standalone PCT website developed, launched and kept up to date, so that international organisations have easily accessible and updated information on PCT partners' activities	>58,000 unique users	Assumed met: Formal data unavailable this year because of a corporate-level IT glitch beyond PCT control. But it is estimated that the site had much higher website visits this year due to the tax incentives public consultation material.

Briefly describe the output’s activities and provide supporting narrative for the score.

Over the past year, the Platform for Collaboration on Tax (PCT) partners[1] made significant progress through collaborative efforts across several key areas. A major achievement was the revision of the Tax Incentives Toolkit, supported by stakeholder engagement and a technical seminar in March that shaped its alignment with emerging global tax developments such as the Global Minimum Tax and climate-related policies. To advance this work, a dedicated tax incentives subgroup was formed and released a joint paper on principles guiding tax incentives. The Tax Incentives Principles document that has been published is important as it adds to considerable momentum on efforts to improve the transparency and effectiveness of tax expenditures in partner countries. It does this by providing a joined-up view from four institutions on an important issue and will form the basis for further work on the topic in the year ahead.
[1] PCT partners are the International Monetary Fund (IMF), the Organisation for Economic Co-operation and Development (OECD), the United Nations (UN) and the World Bank Group (WBG)

Two additional subgroups were also established — on environmental tax and on results and monitoring. In support of climate-related fiscal dialogue, the Tax and Environment Subgroup guided the organisation of a well-attended “ask-an-expert” webinar in November 2024 on Border Carbon Adjustments, with a spotlight on the EU’s CBAM and its implications for developing economies. To address feedback on outreach, the PCT is exploring options such as a high-level conference to boost visibility and engagement with key stakeholders. Additionally, the newly established Results and Monitoring Subgroup will lead efforts to develop standardized indicators for measuring the effectiveness and impact of tax policy reforms.

Governance and coordination remained strong, with the Technical Working Group meeting biweekly and convening key in-person events including a donor-focused PCT Day in June and a strategic retreat in November. The PCT Principals also met to steer programme direction and contributed to global dialogue through a co-authored blog on taxation and the Sustainable Development Goals.

An ‘A’ score reflects the progress made by the PCT to meet its targets and the inclusive process it has adopted in engaging wider stakeholders.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

2024-25 Recommendations	Progress
The PCT is now at the stage where it can go further on in country coordination. It should do this urgently and comprehensively to meet its original mandate and deliver on this important objective. Ideas are listed above, in particular on more case studies of good practice, sessions to understand what coordination has worked less well, and more systematic thinking and working to be coordinated on the upcoming capacity building challenges i.e. around the global minimum tax and tax incentives.	The PCT noted progress as follows: (i) the ongoing Medium Term Revenue Strategy (MTRS) engagement; (ii) the Tax Incentives Subgroup actively engaged with country teams and stakeholders to refine the Tax Incentives Toolkit, incorporating lessons from practical implementation; and (iii) the establishment of the Results and Monitoring Subgroup which will improve systematic tracking of tax reform outcomes, addressing a key challenge in country-level coordination. / In the remainder of this programme, we will encourage the PCT to focus on: measurements and evaluation (and what can make a substantial difference in country in terms of what works to increase tax take; how the impact of coordinated action is measured); and the G20 capacity building report, which can provide examples of best practice on coordinated capacity building work.
The PCT should ensure its consultation process, in particular on the tax incentives toolkit revision, is inclusive. The PCT should capture lessons/experience of stakeholders beyond the experts of the four partner organisations. The toolkit should then be socialised with partner countries to make it as impactful and useful as possible.	Over the past year, the PCT broadened its consultation process to ensure that the revision of the Tax Incentives Toolkit reflects a diverse range of perspectives beyond the four partner organisations. A key step was the Tax Incentives Technical Seminar held in March 2024, which brought together stakeholders from Ministries of Finance, regional tax organisations, academia, private sector representatives, think tanks and development partners. This engagement provided valuable insights into the practical challenges of designing and implementing tax incentives, helping shape the direction of the toolkit revision. / Additionally, the PCT Tax Incentives Principles Paper was developed as a first step in the toolkit revision and was consulted on in December 2024. This allowed for direct input from partner countries and broader stakeholders; and was another step in the route to try and ensure that the final toolkit is both practical and widely applicable.

Output Title	[INTERNATIONAL STANDARDS] Effective design and implementation of international tax standards
Output number:		2	Output Score:	A+
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Share of developing country participation in key events/consultations/working parties	30%	Met: 30% in Inclusive Framework / 36% of subsidiary bodies in the Global Forum
2.2 Number of developing countries drafting new legislation/other reforms in line with BEPS standards / (over the reporting period)	3	Exceeded: 22 (over reporting period)
2.3 Number of developing countries committed to implement the CRS (cumulative)	24	Exceeded: 27 (cumulative)

Briefly describe the output’s activities and provide supporting narrative for the score.

Developing countries remained active and engaged participants in the OECD’s tax transparency and reform initiatives throughout 2024. Nearly half of the participants at the Inclusive Framework (IF) Plenary were from developing countries. Developing country participants also made up 30–40% of the representation in key BEPS-related working parties. Their engagement was substantive, with 13 countries making interventions during plenaries and 12 submitting written feedback.

Similarly, developing countries played a meaningful role in the Global Forum’s subsidiary bodies, contributing 35% of peer inputs and assessments. A strong focus was placed on improving the IF’s inclusivity and effectiveness, with breakout discussions at the May 2024 plenary generating practical proposals to enhance collaboration. Proposals included a regular schedule of meetings, documents to be shared in advance with sufficient notice, greater regional engagement and a more transparent agenda-setting process. Many of these proposals have now been adopted following the agreement of the Inclusive Framework at its plenary meeting in April 2025.

Implementation efforts also gained momentum, with 22 developing countries drafting or enacting legislation aligned with BEPS standards, including steps toward implementing the global minimum tax and enhancing transfer pricing rules.[2]
[2] 16 enacted legislation in 2024 (the other six developed draft legislation that is likely to be enacted in 2025)

In the area of tax transparency, the Global Forum’s capacity-building programme has enabled the implementation of the Common Reporting Standard (CRS). Since 2017, CRS efforts have helped developing countries identify EUR 36.3 billion in additional revenue, and in 2024, several developing countries committed to future CRS exchanges. Technical support efforts expanded significantly, with 40 countries (e.g. Botswana, Cameroon, Eswatini, Lesotho, Liberia, Namibia, Zambia, Zimbabwe) receiving assistance on data safeguards and confidentiality, particularly through a new initiative assessing readiness for Automatic Exchange of Information (AEOI). These countries participated in a gap analysis exercise covering all aspects of information security management and were provided with a technical assistance report showing strengths and areas of improvement, along with a realistic action plan to address the recommendations made and be ready for AEOI exchanges. Most of these countries agreed to continue the technical assistance programme in 2025 through a detailed maturity assessment to refine the assessment and implement correctives measures. Most participants are on track to begin CRS exchanges within three years.

Following the support provided, Armenia, Georgia, Kenya, Moldova, Uganda and Ukraine, successfully passed their confidentiality review for reciprocal exchanges in 2024 having implemented relevant policies and controls to attain a satisfactory level of maturity in information security management as part of the AEOI process. The focus on Country-by-Country Reporting (CbCR) has intensified and enabled an additional nine countries to meet all the requirements to receive CbC reports by September 2024. These were Albania, Azerbaijan, Costa Rica, Georgia, Kazakhstan, Kenya, Maldives, Thailand, and Ukraine. Two further countries (Armenia and Belize) met the standard by the end of 2024, and work is ongoing with a further 22 jurisdictions to meet the standard in the coming years.

Progress also continued in tackling illicit financial flows, as the OECD’s Task Force on Tax Crime welcomed five new developing jurisdictions and supported 17 in aligning with global standards to combat tax crime.

This output is scored A+ based on the progress detailed above.

A priority for the remainder of the programme will be continued progress in taking forward recommendations to become a more inclusive organisation.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

2024-25 Recommendations	Progress
The OECD should ensure its plans to increase the number of developing countries who can access CBCr is realistic and inclusive. / The OECD should ensure that its plan to support the implementation of the two-pillar solution is inclusive of, and coordinated with, international and regional development partners.	The efforts to increase access to CBCr delivered results with nine additional countries gaining access in the last year. Valuable lessons have been learned in how to get countries over the line, and these will be applied in the future. / Maintaining this rate of progress will be challenging, not least as it requires countries to prioritise and implement legislative changes which may cause delays. However, work is ongoing with a further 22 developing countries that have the potential to gain access in the coming years. / At the IF Plenary in April 2025, two programmes were discussed to support developing countries in gaining access to CbC reports in accordance with their own preferred timescale: / Developing country IF members will be invited to indicate whether they wish to obtain access to CbC reports (a) within two years (or less) (Group 1), (b) within three to four years (Group 2) or if they do not wish to join one of these groups at this time. The OECD will prioritise its support to maximise the likelihood of countries accessing CbC reports in the timescale they themselves specify. / The OECD has identified that the cost of IT tools to access CbC reports is an important barrier to access and can act as a deterrent to countries making progress in implementing the minimum standard. The OECD will explore ways for simple tools to be developed centrally which could be made available to developing countries at zero cost, removing this barrier.
The OECD should consult on fundamental changes in the Inclusive Framework to address continuing concerns raised by developing countries around inclusivity and relevance.	The IF plenary meeting in May 2024 had an extended discussion on reform of the IF, including issues around inclusivity and relevance, including a regular schedule of meetings, documents to be shared in advance with sufficient notice, greater regional engagement and a more transparent agenda-setting process. / The outcomes from these discussions formed the basis of proposals for IF reform that were discussed and agreed in April 2025.

Output Title	CAPACITY BUILDING: Improved capacity of developing countries to design tax policy and collect revenues
Output number:		3	Output Score:	A
Impact weighting (%):		50%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of Tax Inspectors Without Borders programmes running	50 including 25 new programmes	Exceeded: 66 including 25 new programmes
3.2 Number of tax administration officials trained	7,000	Exceeded: 33,412 (including 11,530 by the Global Forum and 505 through the Academy on Tax Crime Investigation)
3.3 Number of Tax Inspectors Without Borders Pilots in new areas running (Criminal investigations, AEOI, Digitalisation of Tax Administrations, CbCR and VAT)	8	Met: 6 new tax and crime programmes, two new digitalisation of tax administration programmes
3.4 Number of training programmes conducted annually by ATAF	30	Not met:17
3.5 Number of participants from ATAF member countries to have attended ATAF training programmes annually	3,000	Not met: 2,261
3.6 Number of ATAF members participating in-country programmes delivered through peer-to-peer support, ATAF internal and external consultants	35	Exceeded: 39
3.7 Number of developing countries that have received tax technical assistance from the GTP	6	Not met: 5
3.8 Number of developing country tax officials trained to strengthen tax policy and administration capacities through the GTP	750	Exceeded: 820
3.9 Number of countries receiving advisory services and training on mining taxation, tax incentives reform, and international tax by IISD	60	Exceeded: 94 / 8 countries receiving deep-dive programmes / 14 countries receiving advisory services / 92 countries receiving regional trainings

Briefly describe the output’s activities and provide supporting narrative for the score.

Capacity building is one of the key outputs of the RITI programme. The quality and reach of RITI partners capacity building offer is critical to ensuring developing countries have the knowledge and tools to implement sound DRM policies and processes. Most delivery partners met or exceeded their targets for this reporting period. Where this was not the case, measures were taken to address the shortfall. Below is a summary of some of the activities each partner achieved in 2024.

OECD: In 2024, the Tax Inspectors Without Borders (TIWB) initiative marked a record year with 25 new programmes launched—16 in Africa—and 19 concluded, including six focused on tax crime investigation and two on tax administration digitalisation. The OECD International Academy for Tax and Financial Crime Investigation trained over 500 officials globally and introduced its first onsite pilot for Francophone countries in Togo. The Centre for Tax Policy and Administration’s (CTPA) training offerings continued to evolve, introducing a blended learning model for extractive sector taxation that combined pre-recorded technical modules with interactive case-based discussions—an approach that received 98% satisfaction and strong feedback for enhancing capacity. Meanwhile, the Global Forum’s Train the Trainer programme continued to build sustainable expertise, having developed a network of 200 certified trainers across 67 jurisdictions who collectively trained over 9,000 officials in information exchange, solidifying its role as a cornerstone of long-term capacity-building.

ATAF: During the period under review, ATAF estimates that its technical assistance enhanced domestic resource mobilisation and tax governance across Africa, helping countries generate US$163.53 million in additional tax revenue. This included: US$47.1 million from transfer pricing audits, which involved collaboration with the OECD and IGF; US$3.57 million from digital service taxes; and US$112.86 million from cross-border VAT compliance efforts as ATAF sole interventions.

ATAF implemented legislative and administrative reforms in countries including Zambia, Tanzania, and Nigeria. They conducted 120 technical assistance missions, supporting 39 member countries with key tax policy reforms, audits, and revenue mobilisation strategies. Logistical constraints and travel restrictions meant that ATAF only completed 17 out of its 30 planned training programmes and did not meet its target of planned participants attending training. It is however set to relaunch its upgraded eLearning platform in 2025 which will broaden access to its virtual training offer. The positive feedback from participants, including senior officials – which include Commissioners, Assistant Commissioners, Directorate Cadre and Managers - highlights the value of ATAF's tailored support. Furthermore, ATAF continued to prioritise developing African tax expertise, with a substantial portion of trainers and experts drawn from local revenue authorities and internal experts drawn from the following countries – Uganda, Kenya, Zimbabwe, Cameroon, DRC, Nigeria, Morocco, Tanzania, Rwanda, Burkina Faso, Madagascar, Mauritius, Eswatini, Malawi and Zambia.

GTP: In 2024, the GTP provided TA to 70 countries, with an emphasis on African nations. Ninety percent of the GTP’s financial resources were dedicated to strengthening tax administrations at the country level. The GTP World Bank project team conducted over 20 workshops, training 820 tax officials, with a strong presence in the African region. Seven workshops concentrated on international tax issues, particularly transfer pricing, held in countries like Eswatini, Rwanda, Nigeria, and Lesotho. Additionally, six training sessions on tax incentives were conducted in African nations such as Ghana and Malawi, covering topics like cost-benefit analysis and tax expenditure reporting.
IISD: In 2024, IISD provided TA to 94 countries, conducted 26 capacity building workshops, and trained 1,303 government officials. IISD’s support led to several significant policy developments in Africa and Asia:
- In Senegal, a ministerial decree was signed establishing a benchmark reference price for phosphate exports, which will streamline the annual royalty audit process by providing a clear floor for phosphate prices, thereby reducing disputes with companies. This policy step is expected to bring financial benefits to Senegal.
- In Mongolia, the tax authority concluded a long running coal pricing audit that IISD and the OECD have been supporting for the last few years. The taxpayer has accepted the tax authority’s assessment and will pay USD 27 million in taxes to the government. This demonstrates the long-term impacts IISD’s interventions may have.
- In Lao PDR, following IISD’s advice, the government reformed the tax incentive regime in the Investment Promotion law. The changes will mean narrower, more focussed eligibility criteria for incentives, defined time periods, strengthened investor screening processes, and increased monitoring and accountability. This is significant considering Lao’s tax-to-GDP ratio is 13% - one of the lowest in the region.
- IISD also launched a new mining tax deep-dive programme in collaboration with the African Tax Administration Forum (ATAF) in Zimbabwe. Plans to launch an additional deep-dive in Tanzania were aborted due the difficulty in making strong contacts with the government. However, IISD remains committed in supporting the Tanzanian’s Mining Commission’s priority areas.
Good progress has been made in providing capacity building. Where targets were not met, steps have been taken to address some of the challenges that caused this shortfall. We have scored this output with an A to reflect the achievements and positive measures being taken.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

2024-25 Recommendations	Progress
The OECD should outline its 5-year plan with UNDP for TIWBs expansion; and report back on how India and other South-South cooperation initiatives can be utilised to address the capacity building challenges in Pillar 2.	The OECD and UNDP continued to develop a revised programme plan, as well as agreeing a new MoU between the institutions. Changes in the funding environment will require a revision of the programme before the plan is published. / TIWB continued to expand its South-South cooperation programmes with 9 new South-South programmes launched in 2024 including the launch of criminal investigation programmes in El Salvador, Liberia and Nigeria. / Since 2018, India has supported eight TIWB programmes, including five international audit programmes, one AEOI programme and two criminal tax investigation programmes. / There have been 36 TIWB South-South programmes, supporting 26 jurisdictions by key countries including Brazil, India, Kenya, Mexico, Morocco, Nigeria, and South Africa. TIWB’s strategic partnership with ATAF has also enhanced South-South co-operation. In addition to partnering with the initiative on all TIWB programmes on the African continent, ATAF has also deployed experts in five South-South TIWB programmes. / Argentina, Türkiye and Egypt have expressed interest in becoming partner administrations as soon as appropriate assistance requests are received from host administrations.

Output Title	GLOBAL PUBLIC GOODS: Increased number of high-quality toolkits, policy papers and research papers available to support policymaking and implementation by developing countries
Output number:		4	Output Score:	A+
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 Number of toolkits, policy papers and research papers published by ATAF to support policy-making and implementation in its member states	20	Exceeded: 21
4.2 Number of global public goods produced by GTP (TPAF/Diamond Modules and documents/toolkits/notes)	19	Exceeded: 27
4.3 Increased number of developing countries in OECD's revenue statistics database	2	Exceeded: 7
4.4 Number of practice notes, published associated materials, training programmes and databases produced by IISD	12	Exceeded: 14: / 4 publications / 8 articles/blogs / 2 contributions/peer-reviews
4.5 Number of knowledge management documents prepared by GTP	12	Exceeded: 16
4.6 Number of PCT toolkits released for public consultation per year	1	Exceeded: 3

Briefly describe the output’s activities and provide supporting narrative for the score.

This output is critical to building awareness and knowledge of specific, as well as cross cutting themes. Each of the RITI partners was active in compiling data, lessons learned, case studies and “how to” notes. They were active in utilising this information and engaging in global and regional forums to raise awareness and promote best practice. Some also engaged to influence discussions and negotiations. Below are partner specific activities.

ATAF: During the period under review ATAF produced a comprehensive catalogue of research papers, toolkits, technical notes and guidelines. These included the 2023 African Tax Outlook - launched in July 2024 – covering tax administrative and customs data from 2010 to 2022. Country specific reports for Zimbabwe, Tanzania, Eswatini and Kenya were produced focusing on the taxation of high-net-worth individuals.

GTP: The GTP produced 43 public goods, including toolkits, databases, microsimulation models, and knowledge management documents. Notable outputs included a Tax Expenditures Manual, which enhances global knowledge on tax expenditures by providing comprehensive guidance on their identification, measurement, and evaluation. The BOOST Revenue project team developed 16 revenue platforms across various countries. These datasets helped improved data availability for tax potential analysis in countries with traditionally limited data.

OECD: Seven additional developing countries joined the Global Revenue Statistics Database, bringing the total number of participating economies to 135. The Global Revenue Statistics initiative provides detailed revenue data for monitoring progress in DRM, with comprehensiveness, accuracy and comparability cross-checked by extensive interactions with participating countries during the annual data collection and by a unique centralised data harmonisation process. The OECD also noted that countries are increasingly leveraging their participation in Global Revenue Statistics to enhance their revenue classification and improve the comprehensiveness of their revenue data, which in turn allows for enhancements in policymaking. This includes more detailed tax revenue data in countries such as Bangladesh, Ghana, and Nigeria. Additionally, several countries, including the Republic of the Congo and Senegal, improved the tracking of extractive industry revenues, further strengthening their fiscal transparency and governance. Recent Global Revenue Statistics data shows that tax-to-GDP ratios increased in 70% of the participating economies from 2010 to 2022. Twelve economies saw tax-to-GDP ratios rise by six percentage points or more.

IISD: In 2024, IISD published guidance for governments on Evolving Standards on Stabilisation”. Stabilisation clauses are common in investor-state contracts, including in the mining sector. However, international norms are shifting—moving away from automatic inclusion toward a narrower, more targeted use. They also published a paper on "Metals Streaming and Royalty Financing", exploring the government revenue implications arising from new mine financing arrangements.

This output scored an ‘A+’ recognising that all targets have been exceeded; the increased partnerships that these organisations have utilised; and the influence these products are having in informing developing countries’ decision-making processes and building awareness of pragmatic solutions to common challenges.
## D: VALUE FOR MONEY

VfM performance compared to the original VfM proposition in the business case

The original business case recognised that efficiency and effectiveness levels would be difficult to measure quantitively because: (1) the exact activities to be undertaken would not be fixed at the outset because partners were expected to respond to requests from supported countries ; (2) the majority of activities would be available to a wide range of countries or globally and therefore it would not be specified in advance which countries would benefit; and (3) economic growth is due to multiple interacting factors and it is therefore difficult to attribute the impact of individual policy advice or capacity development activities on GDP growth.
Over the life of the programme we ensured our partners continuously consider value for money in their operating and programming decisions. Below are examples of how VfM has been achieved in the review period.

ATAF actively identifies key cost drivers that impact its operational and financial efficiency, focusing on travel and related expenses for in-person training, technical assistance, and event participation; translation and interpretation costs to ensure its work is accessible in three languages; and staffing, with an emphasis on leveraging in-house experts from member revenue authorities to build a multilingual delivery team.

IISD ensures value for money by having its project management team oversee and approve all expenses to guarantee efficiency, compliance, and focus on project activities. Contractors are engaged only when specific technical expertise is required. Strong partnerships with organisations like OECD, ATAF, and CIAT help maximise efficiency by bringing diverse expertise at no additional cost. IISD has also increased virtual delivery of content and technical assistance while maintaining important in-person relationships, ensuring regional outreach and fair distribution of impacts. IISD provides translations and interpretation whenever possible and relevant to ensure and recruits experts based on language skills to limit additional costs and improve interpersonal relations with beneficiaries.

The GTP enhanced its efforts to link activities to World Bank lending operations and core diagnostics. As a result, GTP-supported analytics and policy recommendations have influenced the design and implementation of 27 DRM-related lending operations, totalling over $7.67 billion, with $2.2 billion allocated specifically for DRM interventions. For instance, the GTP project team in Nigeria played a pivotal role in the design and preparation of two significant lending operations: the Accelerating Resources Mobilization Reforms (ARMOR) Program-for-Results (PforR) and the revenue mobilisation component of the Reforms for Economic Stabilization to Enable Transformation (RESET) Development Policy Financing (DPF). Following the approval of these operations in June 2024, the project team has been actively supporting DRM reforms – providing analysis, advice and capacity building - under both programs, which the government has committed to implementing over the next four years.

The PCT demonstrated value for money by leveraging the combined expertise and resources of its four partner organisations to produce impactful technical outputs with minimal additional costs. The establishment of specialised subgroups on tax incentives, results measurement, and environmental taxation has improved efficiency by streamlining workstreams and enabling targeted collaboration. By utilising existing regional and international platforms, such as the Tax Incentives Seminar and webinars, the PCT has ensured broader stakeholder engagement without incurring significant additional costs.

The OECD continued to refine its use of virtual, hybrid, and blended approaches to capacity building, maximising the value of in-person activities. The growing use of the "train the trainer" approach has significantly increased the efficiency of training provision. Drawing from lessons learned in the Pilot Programme on the Global Minimum Tax (GMT) and Tax Incentives, which involved nine developing countries between 2022 and 2024, the OECD launched a new series of interactive virtual workshops on GMT and economic impact assessment in September 2024. The series will be replicated in 2025, including workshops for francophone African countries, demonstrating ongoing refinement in cost-effective capacity building and broadening its impact.

E: RISK

Overview of risk management

The overall programme risk is minor and all risks fall within the FCDO Risk Appetite Statement. RITI is going through its final no cost extension and has continued to achieve its core objectives.

At partner level, partner risks are reviewed jointly with the FCDO team on a quarterly basis. The two main risks faced by our partners were financial and operational.
Financial risk
All partners are facing medium term funding risks in the contexts of a changing ODA environment. Whilst the implications of reduced ODA are different for each organisation, all are considering appropriate mitigating actions. Funding concerns are not expected to impact on RITI outputs and outcomes.

Operational risk

Political commitment is a critical success factor for effective tax reforms, and tax reforms tend to underperform without strong political support. To mitigate this risk, partners are working to maintain strong engagement with governments and demonstrate the value of reform. At the same time, they face other challenges, such as limited technical capacity and operating in fragile or unstable environments. In response, they are expanding their networks of experts, strengthening partnerships, and designing flexible programs that can adapt to changing situations. These steps help them continue delivering support and making progress, even in difficult conditions.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The total RITI programme budget on the Business Case is £35,000,000, and as of 31 March 2025 the total spend was £25,940,491. The spend for FY 2024-25 was £2,455,000.

The programme has had several No Cost Extensions approved from the original end date of 31 March 2023 to the current end date of 30 November 2025.

Component	Total Spend as / of 31 March 2025	Spend / FY 2024-25
Platform for Collaboration on Tax Secretariat (PCT)	1,253,000	100,000
Support for the World Bank’s Global Tax Programme (GTP)	4,325,000	450,000
Support to OECD for Centre for Tax Policy and Administration	12,596,850	1,105,000
Support to African Tax Administration Forum (ATAF)	2,284,305	300,000
Secondees to ATAF	232,492	N/A
Support to Intergovernmental Forum for Mining, Minerals, Metal and Sustainable Development (IISD)	3,037,966	500,000
RITI Monitoring and Learning	106,116	N/A
RITI Flexi Fund	2,104,762	N/A
Total	25,940,491	2,455,000

At the end of 2024-25, all budgets, forecasts and spend were on target. The programme team held regular proactive conversations with all partners throughout the reporting year in order to achieve accurate forecasting. There are no concerns about the financial performance of the programme nor the performance of the partners. All Annual Audited Statements are up to date.
PFTD has maintained well-established, effective, good working relationships with RITI partners. Quarterly programme meetings are held with each partner to get an update on progress, and also to discuss budgets, finance, risk, counter-aid diversion and safeguarding (which are all regular items on the agenda). There have been no reports of concern.

G: MONITORING, EVIDENCE AND LEARNING

For this Annual Review, a light touch approach was taken and only sought to collect evidence and feedback from our delivery partners. This approach was chosen because the programme will end on 30 November 2025 followed by a comprehensive project completion review which will include reviewing objectives, outputs and impacts.

Date of last narrative financial report	WB PCT / Sept 2024	Date of last audited annual statement	WB - received / Period ending 30/06/2024 / (next due Sept 2025)
Date of last narrative financial report	WB GTP / Sept 2024	Date of last audited annual statement	WB / Period ending 30/06/2024 / (next due Sept 2025)
Date of last narrative financial report	OECD / Mar 2025	Date of last audited annual statement	OECD - received / Period ending 30/12/2023 / (The 2024 report will be issued at the end of 2025)
Date of last narrative financial report	ATAF / Oct 2024	Date of last audited annual statement	ATAF – due May / Period ending 31/12/2023
Date of last narrative financial report	IISD / March 2025	Date of last audited annual statement	IISD received / Period ending 31/03/2024 / (FY 24-25 due mid-June 2025)