Programme Completion Review

Title: Regional and International Tax Initiatives (RITI)
Final Programme Spend £ (full life): £ £28,530,745.37	Review Date:	February 2026
Programme Code: [AMP ID#] 300578	Start Date: / October 2018	End Date: / 30 November 2025

Summary of Programme Performance

Year	2020	2021	2022	2023	2024	2025	PCR
Programme Score	A	A+	A+	A	A	A	A
Residual Risk Exposure Rating	Moderate	Moderate	Moderate	Moderate	Minor	Minor	Minor

DevTracker Link to Business Case (and any addendum):	https://devtracker.dfid.gov.uk/projects/GB-GOV-1-300578/documents
DevTracker Links to all logframes used during programme lifetime:

A. Summary and Overview

Description of the programme and what it has achieved

The Regional and International Tax Initiatives (RITI) programme (2018–2025) supported developing countries to strengthen domestic resource mobilisation (DRM), engage with and implement international tax standards, and access high-quality technical guidance and tools. RITI worked through funding and strategic partnerships with the OECD, the World Bank’s Global Tax Programme (GTP), the Platform for Collaboration on Tax (PCT), the African Tax Administration Forum (ATAF) and the International Institute for Sustainable Development (IISD). The programme was structured around four output areas: coordination, international standards, capacity building, and global public goods.
Across the programme lifetime, and particularly during the 2020–2025 period, delivery remained strong despite significant external disruptions, including COVID-19, constraints on UK Official Development Assistance, and the increasing complexity of the global tax reform agenda. Annual Reviews consistently rated performance at A or A+, with the majority of indicators met or exceeded year on year. This included sustained delivery of capacity-building activities and continued support to the implementation of international tax standards.
Key achievements include the expansion and diversification of training and technical assistance delivered at scale; strengthened implementation of international tax standards, including increased readiness for the Common Reporting Standard (CRS), Automatic Exchange of Information (AEOI) and Country-by-Country Reporting (CbCR); increased availability and uptake of global public goods such as toolkits, databases, guidance and e-learning products; and progress towards more inclusive global tax governance, with greater engagement by developing countries.
Overall, RITI delivered substantial results across all four pillars, although the strength and nature of the available evidence varies by outcome area. RITI made a credible and material contribution to increased revenue mobilisation, particularly through technical assistance interventions, notably through the OECD (and UN) Tax Inspectors Without Borders (TIWB) and IISD-supported work. Partner‑reported evidence indicates that the GTP and other delivery partners supported the mobilisation of partner‑reported revenues in the billions of pounds, primarily at the level of individual interventions rather than system‑wide outcomes. These results provide a plausible picture of RITI’s contribution to revenue outcomes, though the reliance on self‑reported partner data, limited counterfactual and gaps in national revenue reporting constrain the ability to draw broader conclusions. RITI supported developing countries to play a more active role in international tax standard‑setting processes, with increased engagement in the Inclusive Framework and the Global Forum.

The programme also produced a large volume of high-quality global public goods, exceeding most targets, with plausible evidence that these resources informed policy reforms and supported revenue mobilisation, although attribution to global public goods alone is challenging. Capacity-building activities reached very large numbers of officials and institutions, but monitoring data is weighted more towards scale and outputs than longer-term outcomes.

Major lessons learned, evidence generated and recommendations

Across the programme, a consistent lesson is that scale and reach increased materially using hybrid and virtual delivery approaches. These approaches enabled wider coverage and participation. However, experience also shows that certain types of reform—such as audits, sensitive policy dialogue and technical deep dives—continue to require sustained in-person engagement and long-term relationships to translate increased capacity into revenue outcomes. Evidence from IISD shows that revenue gains emerged most strongly from long‑running, in‑depth advisory engagements, illustrating the time lag between technical assistance and measurable revenue outcomes.

A second key lesson is that impact attribution remains difficult. Partner reporting more readily captures outputs, such as numbers of trainings delivered, toolkits produced and missions undertaken, than durable outcomes including adopted reforms, improvements in compliance and revenue gains. In practice, technical assistance can only ever contribute to sustainable revenue gains where partner governments take ownership and implement reforms, drawing on the support provided. Several partners have begun to strengthen their monitoring systems, including through the work of the PCT Monitoring and Evaluation Subgroup, GTP results tracking and the use of evaluation evidence. However, progress in this area remains uneven.

A third lesson concerns coordination. RITI achieved strong coordination and collaboration at headquarters level, with examples including joint work on tax incentives, toolkits and shared training activities. By contrast, coordination at country level remains harder to evidence consistently and should be strengthened in future programme design and reporting.

Based on these lessons, recommendations for future programming are to: (i) embed clearer expectations and measurement of coordination at country level; (ii) invest in impact measurement that goes beyond counts of activities; (iii) maintain hybrid delivery models while protecting resources for deeper engagement where needed; and (iv) continue to support the inclusion of developing countries in international tax standard setting and implementation.

How this report was conducted

This PCR draws primarily on: (i) Annual Reviews from 2020–2025; (ii) partner completed PCR evidence submissions and (iii) programme financial and management records. The evidence assessing output and outcomes was evaluated and scored by a governance advisor from outside the RITI programme team thereby providing an independent assessment.
Actions following approval of this report

Outstanding actions following approval of this PCR relate to closure administration and knowledge capture, including continued receipt/archiving of final audited statements where due, and ensuring that any post closure interactions (attendance at partner conferences, sharing of publications) take place without programme funding. FCDO will also ensure that any remaining closure actions comply with the requirement that programme funds cannot be used beyond end dates.

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£35,000,000	£28,530,745.37
Timeframe	The anticipated programme timeframe at BC sign off was from Oct 2018 to 31 March 2023	Oct 2018 to 30 November 2025. RITI had two no cost extensions.
Outcomes	Improved capacity of developing countries to increase revenues from taxes	The TADAT indicator[1] does not provide a meaningful assessment of improved capacity since (1) it only focusses on tax administration performance; (2) few countries have undergone repeat assessments to evaluate change; and (3) individual reports are not readily accessible to the public.
[1] “Number of developing countries supported through RITI that have seen an improvement in their TADAT scores”.

Overall assessment of programme outcomes, sustainability and VfM

RITI’s outcomes logic remained consistent throughout implementation. The programme was built on the premise that strengthening capability in tax policy and administration, alongside supporting the adoption and implementation of international tax standards and the production of global public goods that provide shared evidence, tools and knowledge, would contribute to improved domestic resource mobilisation (DRM). Annual Reviews indicate that RITI remained on track over its lifetime and delivered strongly against its output areas, particularly in relation to capacity building and support for the implementation of international tax standards. This level of performance was sustained even during periods of reduced ODA and significant delivery disruption caused by COVID-19.
Evidence from delivery partners indicates that capacity improvements and reform support were delivered at scale, including through the expansion of technical assistance footprints and increased training volumes across multiple partners. For example, the Global Tax Programme (GTP) reached 114 countries cumulatively by June 2025 and delivered extensive training activity.
In relation to international standards and transparency, OECD evidence points to widespread support for the implementation of global standards and sustained growth in developing country participation. For example, the number of developing countries committed to implementing the Common Reporting Standard increased from 29 to 54 over the programme lifetime.
Delivery approaches underpinning these results included: (i) train-the-trainer and local expertise models, such as Global Forum networks and ATAF’s African expert base; and (ii) the embedding of reforms within broader institutional processes, including alignment between GTP-supported work and World Bank operations and policy dialogue.
RITI aimed to achieve three overarching objectives:
- enable developing countries to increase domestic revenues for public services and inclusive growth;
- make international tax standard-setting more inclusive of developing country perspectives; and
- provide global public goods and build capacity in tax policy and administration.
1. Revenue increase: Has RITI enabled developing countries to increase domestic revenues?
RITI has contributed to increased domestic revenue, although the evidence is strongest at the level of individual interventions rather than at a system-wide outcome level.
Contributions to domestic revenue occurred primarily through three channels:
- Tax Inspectors Without Borders (TIWB): USD 2.0 billion[2] in additional revenues generated during RITI’s lifetime. During this period, developing country members of the Global Forum identified an additional EUR 14.5 billion revenue through the implementation of tax transparency standards.
  [2] As of the writing of this report in January 2026, final figures had not yet been confirmed.
- IISD: USD 1.3 billion in identified revenue gains between 2019 and 2023, including USD 222 million in recurrent annual gains.[3]
  [3] These are extra revenues that should be collected by government counterparts thanks to the lasting effect of the reforms IISD contributed to.
- GTP: Among countries that implemented at least one GTP-supported reform between 2020 and 2024, 60% (30 countries) recorded a higher tax-to-GDP ratio in 2024 compared to 2021.
Macro-level revenue data for low-income and lower-middle-income countries between 2019 and 2023 shows mixed trends, and data gaps undermine any aggregate conclusions.[4] This reinforces that partner-reported results provide the strongest available evidence of revenue impact, rather than country-level tax ratio data alone. Overall, RITI plausibly contributed to increased domestic revenues, but results rely heavily on self-reported partner data and assume no counterfactual.
[4] Out of 75 countries reviewed, only 27 had compete data for both years. Among these, 14 countries recorded an increase in tax-to-GDP ratios, while 13 experienced a decline; none showed no change. Notable increases occurred in Burkina Faso, Lesotho, Mozambique and Zimbabwe. Decreases were observed in Angola, Kenya, Rwanda and Zambia. However, data gaps remain significant, with 48 countries lacking comparable figures for one or both years. Source: World Bank’s Tax Revenue (% of GDP) data.
2. Inclusive standard-setting: Has RITI helped make international tax standard-setting more inclusive of developing country perspectives?
RITI significantly enhanced the inclusion of developing countries in international tax standard-setting. There is clear evidence that developing countries became more engaged and more influential in global processes. However, more granular evidence on the depth and distribution of influence would strengthen the assessment, including how actively developing countries shaped negotiating positions, whether capacity or resource constraints limited meaningful participation, and how participation varied geographically.
Key evidence includes:
- Inclusive Framework on Base Erosion and Profit Shifting (BEPS): Developing countries represent 50% of the Inclusive Framework membership, provide the co-chair, and joined the Steering Group. Their influence is reflected in outcomes such as the Qualified Domestic Minimum Top-Up Tax under the Global Minimum Tax, Amount B in transfer pricing as a simplification measure for low-capacity contexts, and the shaping of the Subject to Tax Rule to protect source country taxing rights.
- Global Forum on Transparency and Exchange of Information for Tax Purposes: Nineteen additional developing countries joined the Global Forum, which now has 172 members. This engagement translated into expanded use of exchange of information; and 21 additional CRS commitments, 16 first-time exchanges, and 20 commitments to the Crypto-Asset Reporting Framework (CARF).
3. Global public goods: Has RITI provided global public goods, and is there evidence these have supported increased tax collection?
RITI funded a substantial body of global public goods across the OECD, World Bank, ATAF, IISD and the PCT, with outputs greatly exceeding log frame targets. These include toolkits, databases, policy notes, analytical models and tax reform frameworks.
Evidence that these global public goods contributed to increased revenue is plausible but not systematically documented. Links to revenue gains appear stronger where global public goods were combined with capacity building and advisory support. Examples include the association between GTP-supported reforms and increased tax-to-GDP ratios in reform-adopting countries, and IISD advisory work linked to revenue increases through redesigned fiscal regimes.
4. Capacity building: To what extent has RITI contributed to building capacity in tax policy and administration?
RITI made significant investments in capacity building and exceeded nearly all log frame targets. While quantitative data demonstrates extensive reach and delivery, it remains challenging to draw definitive conclusions at outcome level on sustained capacity improvements based solely on the available information.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.

The programme’s theory of change remained unchanged throughout its lifetime. However, the emphasis of monitoring evolved over time. Initially, monitoring focused predominantly on quantitative output measures, such as numbers of individuals trained and global public goods produced. Over the programme lifecycle, there was increased interest in quality, beneficiary feedback and evidence of impact. The programme also increasingly emphasised the inclusion of developing countries in global tax processes, reflecting changes in the external context and wider debates on global tax governance.

## C: Detailed Output Assessment

Output Number and Title	1. [COORDINATION] Improved coordination among international organisations in their support of improved DRM by developing countries
Output Score	A
Impact weighting (%)	10%	Impact weighting revised since last AR?	No

Output Indicator	Final Logframe Target	Final Result Achieved
1.1 Number of working level meetings attended by all four PCT partners during reporting period	136	153
1.2 Number of Principals' meetings attended by all four PCT partners	12	11
1.3 Standalone PCT website developed, launched and kept up to date, so that international organisations have easily accessible and updated information on PCT partners' activities	>60,000 unique users	User data unavailable

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

The Platform for Collaboration on Tax (PCT) is a G20-mandated mechanism that brings together the IMF, OECD, UN and World Bank to improve coordination on international tax reform. Under RITI, this output focused on strengthening coordination among the four PCT partners. The results framework tracked the frequency of working-level technical meetings, strategic coordination at senior management level, and information sharing through shared platforms.
This output was met, with strong performance on technical coordination and sustained engagement at senior levels throughout the programme. Evidence points to regular and structured engagement across partners, alongside the development and maintenance of shared tools to support transparency and information exchange.
OI 1.1 – Technical coordination:
The PCT Technical Working Group (TWG) has met regularly since 2019. The TWG is composed of senior technical experts from each of the four partner organisations and leads working-level coordination. These meetings enable effective internal communication, ensure partners are kept informed of organisational priorities, and support delivery of the PCT workplan across all four workstreams. The regularity and continuity of these meetings demonstrate a sustained commitment to high-level technical coordination and collaboration across institutions.
OI 1.2 – Strategic oversight:
The PCT Principals, comprising senior director-level managers, also met regularly during the programme period. The Principals provide strategic direction and approve the PCT workplan. Together with development partners, they form the Partnership Council, which monitors progress and endorses the annual workplan and budget. At their most recent meeting in September 2024, the Principals approved the workplan covering four workstreams (international tax, tax and SDGs, and MTRS) and supported the PCT’s contributions to the Financing for Development (FfD4) process in 2025.
OI 1.3 – Information sharing and transparency:
The PCT website, launched in 2020, has become a central platform for transparency, communication and information sharing on the PCT and its partners’ domestic resource mobilisation (DRM) activities. The site is regularly updated with new resources and improved navigation features. Although user analytics data cannot be independently verified, the PCT Secretariat reports that the website is a crucial mechanism for transparency, communication and knowledge dissemination. The website hosts the Tax Project Database (TPD), which provides public access to detailed information on DRM projects delivered by the four PCT partners. The TPD includes interactive tools such as a country project map and organisation-based activity views and is considered the most comprehensive publicly available database of DRM activities from technical assistance providers.
Lessons learned and recommendations
Experience under this output highlights that the PCT model helps align positions, reduce duplication and amplify the collective influence of multilateral organisations. This has particular value for developing countries navigating increasingly complex global tax debates. It also shows that tools such as the Tax Treaty Negotiations Toolkit and the forthcoming e-learning module on Tax Incentive Principles are more effective when aligned with countries’ reform cycles and capacity needs.
A key lesson from the results framework is that Output 1 indicators focused largely on activity and output metrics, such as meeting frequency and web presence, rather than on whether coordination improved in practice. While regular meetings demonstrate effort, they do not in themselves evidence the quality or strategic effectiveness of coordination. A recommendation for future programming is therefore to include more qualitative or outcome-level indicators, such as case studies, examples of reduced duplication, or evidence of joint workplans or jointly produced guidance.

Output Number and Title	2. [INTERNATIONAL STANDARDS] Effective design and implementation of international tax standards
Output Score	A+
Impact weighting (%)	20%	Impact weighting revised since last AR?	No

Output Indicator	Final Log frame Target	Final Result Achieved
2.1 Share of developing country participation in key events/consultations/working parties	30%	34%
2.2 Number of developing countries drafting new legislation/other reforms in line with BEPS standards (over the reporting period).	7	79
2.3 Number of developing countries committed to implement the Common Reporting Standard (cumulative).	29	54

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

Output 2 assesses developing countries’ participation in, alignment with, and implementation of international tax standards, primarily those developed through the OECD/G20 Inclusive Framework and the Global Forum. Three indicators capture distinct aspects of engagement: participation in international standard-setting processes, domestic adoption of international tax standards, and commitment to global tax transparency standards.
This output was exceeded across all indicators. Qualitative evidence also supports strong performance, showing that developing countries not only participated in international processes but also shaped key reforms. Participation was particularly strong during negotiation periods, and there are clear examples of developing country influence over technical rules designed to protect source-country taxing rights.
OI 2.1 – Participation and influence in standard-setting:
Average participation by developing countries in the OECD’s tax transparency and reform initiatives exceeded the target over the programme period. Participation increased during most of the programme but dipped slightly towards the end. The shift to virtual meetings lowered barriers to participation for some countries, although engagement was highest during key negotiation phases. This suggests that developing countries prioritised engagement when decisions were most consequential. Developing countries played an influential role in shaping rules that protect their interests, including Amount B, which simplifies transfer pricing for routine transactions and was proposed by developing countries, and in global minimum tax discussions, where they influenced both the Subject to Tax Rule (to enable source countries to tax where tax treaties provide for no or very limited residence taxation) and on the rule order to ensure that source countries retain the first right to tax under the new system.
OI 2.2 – Adoption of international tax standards:
Many developing countries took steps to align their domestic tax laws with the Base Erosion and Profit Shifting (BEPS) standards, which aim to address tax avoidance by multinational corporations. Over the programme lifetime, OECD experts supported the drafting of more than 75 new laws.
OI 2.3 – Commitment to global transparency standards:
Between 2019 and 2025, developing countries significantly expanded their participation in the Common Reporting Standard (CRS) for the automatic exchange of financial account information.[5] During this period, 21 additional countries committed to adopting CRS, bringing the total number of participating developing countries to 54, and 16 countries began automatic exchanges for the first time. Implementation quality improved, with 90% of CRS legal framework peer reviews assessed as satisfactory. However, only 48% of developing countries received a satisfactory rating under the first round of CRS effectiveness reviews, which led to the provision of targeted technical support.
[5] The Common Reporting Standard (CRS) is an international standard developed by the OECD and promoted by the Global Forum to fight offshore tax evasion. Under CRS, countries agree to automatically exchange financial account information evey year. It helps tax authorities identify hidden offshore assets and ensure people pay the right amount of tax.
An independent review examined the effectiveness of OECD support to developing countries on international tax standards. The review found that most developing countries consider OECD support to be very useful for implementing global tax rules and for participating in standard-setting processes, although its impact was less pronounced in relation to the two-pillar solution.[6]
[6] The two-pillar solution is a global agreement developed by the OECD and G20 to make international tax rules fairer and address challenges from digitalisation to globalisation. The goal is to ensure that big corporations pay their fair share of taxes and reduce harmful tax competition between countries.
Lessons learned and recommendations
Experience under this output demonstrates that developing countries can exert meaningful influence over international tax standards when they are effectively included in standard‑setting processes. This is evidenced by their role in shaping Amount B, the Subject to Tax Rule and elements of the Global Minimum Tax. While the use of virtual meetings widened access, experience also shows that engagement peaked during decisive negotiation periods, indicating that participation intensifies when outcomes are most salient.
Looking ahead, any future programme should build on support for the implementation of international tax standards and place greater emphasis on evidence of those standards being used to generate revenues in developing countries. Experience from RITI shows that reform does not end when standards are adopted; effective implementation is equally critical.

Coordinated cross-government engagement significantly enhances the UK’s influence in multilateral tax processes. FCDO engagement with the OECD throughout the RITI programme was consistently effective. The department was among the most active contributors to the Advisory Steering Group for the OECD’s tax and development programme, providing constructive inputs that helped shape the direction of the work. Close coordination with HM Treasury and HMRC enabled the UK to present a unified and coherent positing. FCDO also played a valuable role in ensuring alignment across related international platforms, including the Addis Tax Initiative, the UN, and the Platform for Collaboration on Tax.

Output Number and Title	3. CAPACITY BUILDING: Improved capacity of developing countries to design tax policy and collect revenues
Output Score	A+
Impact weighting (%)	50%	Impact weighting revised since last AR?	No

Output Indicator	Final Logframe Target	Final Result Achieved
3.1 Number of Tax Inspectors Without Borders programmes running	50	143
3.2 Number of tax administration officials trained	24,500	183,000
3.3 Number of Tax Inspectors Without Borders Pilots in new areas running (Criminal investigations, AEOI, Digitalisation of Tax Administrations, CbCR and VAT)	26	63
3.4 Number of training programmes conducted annually by ATAF	131	132
3.5 Number of participants from ATAF member countries to have attended ATAF training programmes annually	9,100	9,929
3.6 Number of ATAF members participating in-country programmes delivered through peer-to-peer support, ATAF internal and external consultants[7]	2023: 25 / 2024: 30 / 2025: 35	2023: 77 / 2024: 47 / 2025: 43
3.7 Number of developing countries that have received tax technical assistance from the GTP	90	114
3.8 Number of developing country tax officials trained to strengthen tax policy and administration capacities through the GTP	2,475	3,530
3.9 Number of countries receiving advisory services and training on mining taxation, tax incentives reform, and international tax by IISD	2019-2023: 59-64 / 2024-2025: 40 per year	111
[7] Indicator 3.6 changed in 2023. Previously, it was "Number of technical assistance interventions delivered annually".

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

Output 3 covers capacity-building support to developing country tax administrations and finance ministries, delivered through four partners: Tax Inspectors Without Borders (TIWB), the African Tax Administration Forum (ATAF), the Global Tax Programme (GTP), and the International Institute for Sustainable Development (IISD). The output indicators focus primarily on the scale of delivery, including the volume of technical assistance programmes, numbers of officials trained, and training activities delivered, rather than on the quality or durability of capacity gains.
This output was exceeded across nearly all indicators, often by a large margin. Delivery at scale was a clear strength of the programme. However, the monitoring, evaluation and learning (MEL) framework does not allow a systematic assessment of whether technical capacity improved in a sustained, institutional sense.
OI 3.1 – TIWB programme expansion:
The TIWB initiative expanded significantly over the programme lifetime, delivering more than 140 programmes. Demand for TIWB support was higher than initially anticipated. As initial capacity gaps were addressed, more complex audit issues emerged, increasing demand for ongoing and more advanced support.
OI 3.2 – OECD capacity building:
OECD capacity-building delivery expanded substantially through the use of virtual learning, enabling broader and more diverse course coverage across OECD tax activities and delivery in up to eight languages. The programme now trains tens of thousands of officials annually, with demand remaining strong, particularly for live and in-person sessions. An independent review found that more than 80% of participants reported that OECD tax and development capacity-building activities improved their knowledge, job performance and internal processes.
OI 3.3 – Scope of TIWB support:
The majority of TIWB activity focused on supporting countries to undertake transfer pricing audits, enabling them to raise billions of pounds in additional tax revenue from multinational companies.[8] Over time, the programme expanded beyond its core transfer pricing offer to include support on Country-by-Country reporting, Automatic Exchange of Information, VAT, the Global Minimum Tax and tax digitalisation. Demand for support with criminal investigations increased significantly and became a well-established part of the offer.
[8] Since 2012, TIWB has helped realise more than USD2.3 billion in additional revenue, with USD2 billion generated during the RITI’s duration.
OI 3.4–3.6 – ATAF capacity building:
Between 2019 and 2025, ATAF delivered 132 specialised training programmes, exceeding annual milestones in most years. Training covered a wide range of technical areas in tax administration and was delivered primarily through a peer‑to‑peer approach, led by experts from ATAF member revenue administrations. In total, ATAF trained nearly 10,000 officers—substantially exceeding planned targets—from dozens of member countries, with delivery conducted in three languages (English, French and Portuguese).
ATAF’s training and technical assistance strengthened the capacity of member and non‑member African tax administrations to identify, assess and collect tax revenues more effectively. These outcomes were driven primarily through tailored technical assistance, including support for value added tax compliance regimes for cross‑border digital services, transfer pricing audits, digital services tax and significant economic presence measures, as well as other interventions such as withholding tax and tax legislative reforms.
The reported figures reflect treasury‑received collections reported by member administrations and tracked at case level. These revenues arose from audits and compliance actions that applied ATAF‑supported capacity‑building tools and methodologies and are attributed where a clear link exists between ATAF support and the enforcement approach used.[9]
[9] ATAF’s technical support to members, has contributed to USD 5.4 billion in tax assessments, USD 2.4 billion in revenue raised, and 71 legislative and regulatory reforms.
OI 3.7 and 3.8 – Global Tax Programme:
Since its launch in 2018, the World Bank’s GTP expanded from 28 to 114 countries by June 2025, with a focus on boosting domestic revenue, particularly in Sub-Saharan Africa. The GTP delivered more than 500 training events across 75 countries, reaching over 3,500 tax and customs officials. It has become the World Bank’s main platform for tax reform support, contributing to policy reforms and institutional capacity building. Among countries that adopted at least one GTP-supported reform, 60% (30 countries) recorded an increase in their tax-to-GDP ratio in 2024 compared to 2021.
GTP analytical and advisory work also informed World Bank lending operations, including IDA‑financed programmes, helping to embed tax policy and administration reforms within broader public financial management support.
OI 3.9 – IISD support:
IISD supported 111 countries through a combination of long-term deep-dive programmes, flexible advisory services, regional training and partnerships with organisations including the OECD, ATAF and CIAT. Deep-dive engagements provided multi-year, sequenced assistance in 11 countries and underpinned the most significant reform and revenue gains. Advisory work expanded to more than 90 countries by 2025, supporting reforms in areas such as mineral pricing, transfer pricing, tax incentives and treaty negotiation. Regional and online training reached over 2,800 officials, with more than 90% reporting increased capacity and relevance to country needs. Follow-up evidence shows governments independently applying IISD-supported tools and models, institutionalising inter-agency coordination, and using improved procedures in audits, fiscal modelling and policy design.
Lessons learned and recommendations
Experience under this output indicates that virtual training significantly expanded reach, but in-person engagement remains essential for complex technical topics. The most effective delivery combined virtual preparation with targeted, in-person missions. While the TIWB programme initially benefited from a strong supply of expertise, supported by UNDP collaboration and member contributions, by 2025 it became increasingly difficult to maintain sufficient expertise as resources declined despite continued high demand. A recommendation for future programming is to prioritise sustainable pipelines of expertise, including regional pools.
Capacity-building interventions were most effective where IISD combined research, advisory support, training and policy dialogue, rather than relying on one-off interventions. Strong partnerships with organisations such as the OECD and ATAF increased effectiveness and supported the continued application of skills after IISD engagement ended.
A further lesson is that reliance on quantitative activity metrics limits the ability to assess whether institutional capacity has improved. Tools such as TADAT could provide a proxy for outcome-level progress, but their usefulness is constrained by the low number of repeat assessments and limited publication of results. A recommendation for future programmes is therefore to incorporate qualitative indicators, case studies, institutional capacity metrics and evidence on policy implementation outcomes.

Output Number and Title	4. GLOBAL PUBLIC GOODS: Increased number of high-quality toolkits, policy papers and research papers available to support policymaking and implementation by developing countries
Output Score	A
Impact weighting (%)	20%	Impact weighting revised since last AR?	No

Output Indicator	Final Log frame Target	Final Result Achieved
4.1 Number of toolkits, policy papers and research papers published by ATAF to support policy-making and implementation in its member states	73	104
4.2 Number of global public goods produced by GTP (TPAF/Diamond Modules and documents/toolkits/notes)	81	85
4.3 Increased number of developing countries in OECD's revenue statistics database	17	47
4.4 Number of practice notes, published associated materials, training programmes and databases produced by IISD	35	85
4.5 Number of knowledge management documents prepared by GTP	68	74
4.6 Number of PCT toolkits released for public consultation per year	9	7

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

This output was exceeded in terms of delivery volumes, with strong performance across four of the five partner institutions and only a minor shortfall against the target for the number of PCT toolkits released. However, while partners provided individual examples linking global public goods to policy reforms and administrative improvements, this evidence was not collected systematically through the programme’s monitoring, evaluation and learning framework. On this basis, an overall score of A is assessed as appropriate.
This output was exceeded, with strong performance across four of the five partner institutions and only a minor shortfall against the target for the number of PCT toolkits released. While partners have provided individual examples linking GPGs to policy reforms and administrative improvements, this evidence was not collected systematically through the programme’s monitoring, evaluation and learning framework.
OI 4.1 – ATAF research and knowledge products:
ATAF significantly exceeded its research and knowledge-sharing targets, producing a substantial body of work that informed tax policy and administration across Africa. Between 2019 and 2025, ATAF published more than 100 research papers, toolkits, guidelines, policy briefs and technical notes, attracting tens of thousands of downloads and strong engagement from member countries. Outputs addressed priority issues including illicit financial flows, tax expenditures, digital economy taxation, gender and tax, and global tax reforms, including the two pillar solution. ATAF’s research directly influenced legislation and administrative practices in at least nine member states and supported technical assistance requests in areas such as high-net-worth individual taxation. Flagship publications, including the African Tax Outlook and the African Multidisciplinary Tax Journal, further strengthened ATAF’s role as a thought leader in African tax administration.
OI 4.2 and OI 4.5 – Global Tax Programme:
Between 2018 and 2025, the World Bank’s Global Tax Programme produced 85 global public goods, including tax toolkits, databases, e-learning platforms and analytical models, alongside 74 knowledge management documents designed to organise and share best practice. These resources supported countries to design tax policies, adopt international standards and implement reforms. Knowledge management documents played an important role in translating technical expertise into practical guidance for policy makers and tax administrations.
OI 4.3 – OECD Revenue Statistics:
OECD Revenue Statistics expanded coverage from 92 countries in 2018 to 139 countries, primarily through the inclusion of developing countries. The database now includes over half of countries in each income group, covering 58% of low-income countries, 63% of lower-middle-income countries and 67% of upper-middle-income countries. It remains the most comprehensive, annually updated and freely available dataset of its kind, enabling more detailed cross-country research and analysis.
OI 4.4 – IISD knowledge products:
IISD’s Tax and Sovereign Debt Programme produced more than 80 knowledge products, including blogs, articles, explainers, practice notes and technical guides. These outputs covered themes such as mining taxation, mineral pricing, international tax reform, tax incentives and development finance, and were closely informed by country-level advisory work in contexts including Guinea, Argentina, Peru, Mongolia and Zambia. Evidence of uptake is strong. Flagship publications, such as The Future of Resource Taxation and the Guide on Understanding the Global Minimum Tax, generated significant demand for follow-on technical assistance, with governments requesting support on variable royalties, production-sharing contracts, turnover taxes and Global Minimum Tax implementation. Usage data and sustained interest in the most-viewed publications indicate growing relevance, particularly on mining taxation, tax incentives and UN-led tax reforms.
OI 4.6 – Platform for Collaboration on Tax:
During the programme period, the PCT advanced the development and dissemination of global tax resources, although delivery fell slightly below target. Key outputs include multilingual toolkits on Transfer Pricing Documentation, Taxation of Offshore Indirect Transfers, Addressing difficulties in accessing comparables data for transfer pricing analyses, Tax Treaty Negotiations, and the Tax Treaty Negotiations online e-learning module. In 2025, the PCT published the Tax Incentives Principles to support governments in balancing social objectives and revenue risks, and work is on-going with respect to revising the Medium-Term Revenue Strategy framework to reflect eight years of implementation experience. To improve accessibility and uptake, several products are being transitioned into interactive formats, including e-learning modules.
Lessons learned and recommendations
Experience under this output indicates that global public goods are most effective when they are practical, accessible and responsive to country reform needs and timelines. Interactive formats, such as web-based toolkits and e-learning modules, are more effective than static documents.
Collaboration with regional organisations enhances relevance and uptake. Working with partners such as CIAT, IDB, ADB and ATAF helps ensure that global public goods reflect regional priorities, are disseminated more widely and gain legitimacy and local ownership.
Evidence also shows that combining global public goods with capacity building increases their effectiveness. Experience from IISD and the GTP demonstrates that knowledge products are more impactful when paired with in-country advisory work, reform diagnostics and hands-on technical assistance.

D: Value for Money

RITI demonstrated strong value for money over its lifetime. This was achieved primarily through: (i) increased efficiency generated by hybrid and virtual delivery models; (ii) effective use of partner comparative advantages and shared resources to reduce duplication; and (iii) delivering support where there were genuine opportunities for reform because support was embedded within partner’s on-going platforms/frameworks at country level. Annual Reviews consistently note that VfM measurement at programme level was challenging, reflecting the demand-led nature of technical assistance and the breadth of beneficiary reach. However, qualitative evidence of improvements in economy and efficiency over time were provided. Future programming in this space should seek to work with partners to identify ways of measuring and reporting VFM in quantitative terms.

Economy:
Partners reduced delivery costs by shifting activities online where appropriate and by making greater use of regional expertise, particularly through ATAF, while maintaining strong technical quality. ATAF also actively managed administrative costs and expanded language-appropriate delivery, which reduced interpretation costs over time.
Efficiency:
The shift to remote and blended delivery substantially increased training reach, as evidenced by the scale of OECD training activity and the approaches adopted by the Global Forum. In parallel, the Platform for Collaboration on Tax (PCT) model leveraged the combined resources and expertise of four institutions to produce joint outputs, avoiding the creation of parallel structures and reducing duplication.
The OECD/IISD joint work provides a further example of this approach. The BEPS in Mining programme is a fully integrated initiative delivered in full partnership, making efficient use of the resources of both institutions, including collaboration with ATAF in Africa.
Effectiveness and cost-effectiveness:
Partner evidence provides examples of high returns and meaningful reform outcomes. Relatively modest investments in technical expertise and advisory support contributed to substantial and, in some cases, recurrent revenue gains for partner governments. This includes IISD’s quantified return‑on‑investment framing and the GTP’s ability to leverage World Bank lending operations informed by analytical work.
FCDO’s ability to earmark GTP funding to specific policy areas aligned with UK policy priorities enabled greater focus and quicker delivery of pilot projects and the development of relevant frameworks (eg Climate Policy Assessment Tool, Tax and Gender research and policy advice, and Tax Expenditure reporting).
Equity:
Evidence indicates improved access through virtual delivery, including broader participation and increased female participation across many training activities, alongside specific workstreams focused on gender and tax, such as those supported by the GTP. However, disaggregation beyond gender remains limited.

E: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.

Overall programme risk reduced from Moderate to Minor in the later years of implementation as the programme matured and approached closure, as reflected in successive Annual Reviews. Over the life of the programme, the principal risks identified included political economy constraints in partner countries; delivery challenges in fragile and conflict-affected contexts; funding uncertainty linked to ODA reductions; partner capacity constraints; and the risk of duplication across a complex, multi-partner portfolio.
Operational and contextual risks were mitigated through flexible delivery approaches and adaptive portfolio management. In particular, partners adjusted delivery models during the COVID-19 period by shifting to remote and hybrid modalities and adapted sequencing of activities in response to political instability or implementation constraints in partner countries.
Financial risks associated with reductions in ODA were mitigated through partners rapidly adapting workplans, maintaining delivery momentum and exercising strong forecasting discipline. Medium-term funding risks were recognised across partners in the later years of the programme. Mitigation measures included diversification of funding sources and efficiency measures, such as ATAF’s sustainability workstream and increased partner fundraising efforts.
Risks relating to coordination and duplication were managed through regular quarterly engagement, the encouragement of information sharing and communication among partners, and the use of PCT coordination mechanisms. However, programme evidence consistently indicates that coordination at country level is harder to demonstrate and remains an area for improvement in future programme design and reporting. Notwithstanding this, the OECD/IISD partnership and ATAF (in Africa) integrated their work at country level, helping to ensure coordination in delivery. Further coordination was achieved with Tax Inspectors Without Borders (TIWB) programmes, which often ran alongside, or subsequent to, BEPS in Mining deep‑dive engagements.
Safeguarding and fiduciary risks remained within FCDO risk appetite throughout the programme. No concerns were raised through programme management reporting, and quarterly monitoring processes included counter-aid diversion and safeguarding as standing agenda items.

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.

The approved Business Case budget for RITI was £35 million. Actual total expenditure over the life of the programme was £28,530,746.37 as of 30 November 2025, as set out in the table below. The programme end date was extended through several no-cost extensions from the original March 2023 closure date to 30 November 2025. These extensions enabled continued delivery, supported orderly programme close-down, and improved the utilisation of remaining funds.
Project	Spend from 01 April to 30 Nov 2025	Total Spend over life of the programme to 30 Nov 2025
Platform for Collaboration on Tax Secretariat (PCT)	100,000	1,353,000
Support for the World Bank’s Global Tax Programme (GTP)	950,000	5,275,000
Support to OECD for Centre for Tax Policy and Administration	704,308.56	13,297,000.56
Support to African Tax Administration Forum (ATAF)	300,000	2,584,305
Secondees to ATAF	0	232,491.92
Support to Intergovernmental Forum for Mining, Minerals, Metal and Sustainable Development (IISD)	400,000	3,437,966
RITI Monitoring and Learning	0	106,116
RITI Flexi Fund	0	2,104,702.35
Total	2,454,308.56	28,530,746.37

Although delivery and expenditure were affected by COVID-19 and reductions in ODA, partners adapted quickly and flexibly. Activities were reprioritised and delivery modalities adjusted, including shifts to remote and hybrid approaches, while maintaining strong performance against outputs. Financial forecasting and oversight were managed through regular engagement with partners and proactive monitoring. No concerns were reported regarding partner financial performance, and audited financial statements were consistently reported as up to date.
FCDO maintained robust programme management and oversight throughout implementation. Quarterly meetings with each partner covered budgets, financial performance, risk management, counter-aid diversion and safeguarding. No safeguarding or fiduciary concerns were raised through these processes. The programme did not hold any assets.
From a value for money perspective, the programme demonstrated good economy and efficiency. Economy was supported through adaptive delivery models, cost-conscious approaches by partners, and the ability to scale activities without proportionate increases in overheads. Efficiency was enhanced through flexible programme management, the use of earmarked funding to align delivery with evolving FCDO policy priorities (notably within GTP workstreams), and strong partner responsiveness to changing financial and contextual constraints.
Lessons learned
Several lessons emerged from programme management and partner performance. The use of earmarked funding proved to be an effective model for multilateral engagement where close strategic alignment with UK policy priorities was required. Recruitment constraints meant that secondment ambitions to ATAF were only partially realised, suggesting that future programmes should adopt more flexible resourcing models. The Flexi Fund was not utilised as originally intended, in part due to funding reductions. Finally, instances of overlap across partner delivery reinforce the need for stronger coordination mechanisms and clearer attribution of results in future programmes.

Programme-level approach to monitoring and evaluation
RITI’s monitoring approach relied on quarterly workplan tracking and Annual Reviews, with risks identified, discussed and mitigated through routine engagement with partners. Annual Reviews also incorporated periodic beneficiary feedback, including through virtual stakeholder engagement. Over time, partner monitoring systems were strengthened, including through partner-led evaluations and enhanced results tracking.
This approach supported effective programme management by informing risk mitigation, delivery decisions and adaptations to external shocks, including COVID-19 and changes in the funding environment. It also enabled prioritisation of activities within a constrained financial context, although, as noted elsewhere, monitoring remained more effective at tracking outputs and delivery than at evidencing longer-term outcomes and impacts.

Date of last narrative financial report	WB PCT	Date of last audited annual statement	WB / Period ending 30/06/2025 / (due Sept 2025)
Date of last narrative financial report	WB GTP	Date of last audited annual statement	WB / Period ending 30/06/2025 / (due Sept 2025)
Date of last narrative financial report	OECD	Date of last audited annual statement	OECD / Period ending 30/12/2024 / (The 2024 report will be issued at the end of 2025)
Date of last narrative financial report	ATAF	Date of last audited annual statement	ATAF – due May / Period ending 31/12/2024
Date of last narrative financial report	IISD	Date of last audited annual statement	IISD / Period ending 31/03/2025 / (FY 24-25 due mid-June 2025)