## Educate the Most Disadvantaged Children in Bangladesh (EMDC) Annual Review

Title: Educate the Most Disadvantaged Children (EMDC) in Bangladesh
Programme Value £ (full life): £38.5 million		Review date: April 2024 to March 2025
Programme Code : 300580	AMP start date: 15/11/2021	AMP end date: 30/9/2029

Summary of Programme Performance
Year	2022	2023	2024	2025
Overall Output Score	A	A+	A+	A+
Risk Rating	Major	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/assets/images/icon-document.svg
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0005297.xlsx

A. SUMMARY AND OVERVIEW

Description of programme
1. Educate the Most Disadvantaged Children (EMDC) is £38.5 million bi-lateral FCDO programme in Bangladesh over eight years targeting children, particularly girls and children with disabilities (CWD). These children were either not accessing education, or at substantial risk of drop out due to financial hardships, distance from school or victims of harmful traditional practices such child marriage and climate vulnerability. Recurring political unrest disrupted the academic calendar and school operations over the last year, which led some parents refraining from sending children to school. There is an estimated 7 million Out of School Children (OoSC) in Bangladesh at primary and secondary level.
  [note] https://bangladesh.unfpa.org/en/topics/child-marriage , UNFPA 2023.
  [note] Locations such as Sylhet, Netrokona, Jamalpur and Bhola are particularly vulnerable to flooding.
  [note] Annual Primary School Statistics (APSS) 2024 and BANBEIS 2023 reports.
2. EMDC will support 360,000 marginalised children, including girls, children with disabilities, ethnic minorities, and those in areas most affected by climate change. The objectives of EMDC will be achieved through four main activities:
  1. ‘Catch Up’ education for 300,000 children (60% girls), up to 10-month course, focussing on foundational learning (reading, writing and numeracy) and life skills enabling children to transition to primary schools.
  2. Education for 60,000 children (60% girls), up to 40 months, through ‘accelerated learning’ approach. This is an intensive education approach for Out of School Children (OoSC) who have never enrolled or dropped out from education, where access to Government of Bangladesh (GoB) schools is limited. This includes testing an innovative learning modality, i.e. Multi-Grade, Multi Level (MGML), which enables children of different ages and ability to learn in the same space.
  3. Technical Assistance (TA) to the Bureau for Non-Formal Education (BNFE) and the Directorate of Primary Education (DPE), to improve their capacity to deliver second chance education for out of school children.
  4. Research and evaluation to identify best practice supporting out of school children and use as evidence to influence national policies and programmes.
3. EMDC is delivered by two implementing partner (IP’s), UNICEF and BRAC; both have long records of education programme delivery in Bangladesh. UNICEF engages five downstream partners in running schools. UNICEF and BRAC delivers education through Learning Centres (LCs) in targeted areas.
4. Consistent with UK development priorities EMDC targets regressive social norms that act as barriers to girls in accessing education. Working with parents and communities, the programme increases awareness on demerits of early marriage, and benefits of routine immunization, birth registration, and child protection measures.
5. The study on the impact and sustainability of EMDC’s catch-up education highlights gender-specific learning patterns, i.e. male learners showing stronger performance in oral expression and numerical reasoning, while female learners excel in reading and structured writing tasks. To address gender disparity in education, EMDC is supporting gender-inclusive classrooms, use gender-sensitive teaching practices and challenge stereotypes in communities and at homes.
6. Conversations with teachers showed a genuine shift in attitudes in supporting students particularly girls. In addition, it is EMDC is supporting system-wide policy reforms, investing in teacher professional development, and engaging communities; all critical for achieving gender equality and empowering all students.
7. EMDC programme has embedded child and teacher well-being into its implementation by integrating mental health and psychosocial support (PSS) into programming. In addition, the programme has incorporated climate change mitigation and adaptation strategies, ensuring interventions are not only protective and inclusive, but also resilient and future oriented.
8. Throughout this AR period (April 2024- March 2025) EMDC-B faced closures of Learning Centres due to cold and heatwaves, fire incidents, and political disruptions following political turmoil in June-August 2024.
9. This AR drew on technical expertise of a UK Based Education Adviser (EA) with previous involvement in primary education in Bangladesh; a CBS EA and programme managers at post; desk review of programme reports, cross-cutting advisory support including from a Social Development Adviser, field visits in in northern Bangladesh and slums in Dhaka; and conversations with Implementing Partners (IPs).
10. In a declining global ODA context, EMDC is a good example of targeted delivery of education to the most disadvantaged children. Lessons learned and evidence generated from the programme has successfully influenced national programme for Out of School Children (OsSC).
Summary supporting narrative for the overall score in this review
1. The overall output score is A+. Out of five outputs, three moderately exceeded and two met the targets. Targets on enrolment and completion rates, teachers’ training, and student transition to GoB schools, were all exceeded. The programme has reached 243,677 out-of-school and at-risk children across Bangladesh. Over 95% of Catch-Up education graduates transitioned and retained in formal schools, showing strong learning continuity.
2. 1,629 Learning Centres (LCs) established (1,338 currently operational), with community ownership. Over 300,000 community members are engaged. Engagement with communities and role Centre Management Committees (CMSs) in tackling barriers to girls' education is evidenced by demonstrable shift in attitudes, especially among fathers/men in challenging social norms supporting early and child marriage.
3. Implementing Partners (IPs) have strengthened teacher capacity, e.g. conversations with teachers during visit to UNICEF schools demonstrated improved capacity in teachers to teach Multi-Grade & Multi-Level (MGML) education; teachers at BRAC schools also demonstrated better capacity.
4. TA to Government of Bangladesh (GoB) has had good results. Department for Primary Education (DPE) and the Bureau for Non-Formal Education (BNFE) with TA for integration of skill-focused literacy model within national development programme. TAs to BNFE helped to secure regular allocation from government to deliver non-formal education for OoSC.
5. FCDO’s South Asia Research Hub’s study on the impact and sustainability of EMDC’s catch-up education has confirmed its strong relevance to meeting needs of marginalised children, supporting their return to formal schools. The study findings and recommendations has been disseminated with national stakeholders.
6. EMDC is leveraging support for education for Out of School Children (OoSC) from Government of Bangladesh, and demonstrating sustainability, particularly through working with local communities. Impact is currently limited to children reached directly, is expected to have a transformative effect, through evidence and TA to influence policy and programme decisions across the national education system.
7. Unlike many other education programmes, EMDC is actively collecting the information required to assess impact on children’s learning. Significant changes were made in programmes’ design and delivery to secure the required literacy and numeracy gains. Through this programme, FCDO has made investments in expanding global research on education for OoSC – a valuable public good.
8. The EMDC not only met but surpassed expectations, delivered results at scale, strengthened the national system, and generated convincing evidence for sustainability and replication. This exceptional performance justifies a rating of A+.

Major lessons and recommendations for the year ahead
Lessons
1. Floods and political unrest disrupted the academic calendar and school operations, necessitating regular contingency planning. Remedial plans are crucial to respond to unforeseen school closures due to natural disasters.
2. Effective engagement, better coordination and collaboration with the government at different levels- but most importantly at the Upazila and District levels- is critical for sustainability of activities.
3. A mechanism needs to be developed for the teachers to ensure their effective engagement and support for students with disabilities, removing any gender bias in classroom and shifting entrenched social norms.
4. Budget constraints and uncompetitive salaries make it difficult to attract and retain qualified staff, affecting programme quality.
5. Teachers need regular refreshers in pedagogy and curriculum to effectively support students transitioning to government schools.
6. If funds for the programme are reduced in the coming years, an exit strategy should be discussed with view to support students through the OoSC component in the Primary Education Development Programme (PEDP).

Recommendations
1. By December 2025, FCDO and IPs to develop an academic calendar to overcome the challenge of overlapping school hours between BRAC and UNICEF schools and Government Primary Schools (GPs) as well as unforeseen school closures due to natural disasters.
2. By December 2025, IPs should put in operation a plan to build capacity of Teachers and members of Centre Management Committees (CMC) on gender equity, so they are better able to engage with local governments as well as tackle social attitudes, norms and perceptions hindering girls’ access to education.
3. By January 2026, BRAC will complete assessments of assistive devices for children with disabilities to ensure suitability and appropriate usage of these devices. This should include screening, and inclusion approaches to enhance enrolment of Children with Disabilities (CWDs).
4. By December 2025, a reassessment of the salary structure for teachers to be completed.
5. By December 2025, additional refreshers on MGML education necessary to deliver effective teaching to students with different ability and age groups will be completed.
6. By April 2026, FCDO with the IPs to review the ToC and Log Frame and explore whether targets in outputs 1, 2 and 3 can be stretched further or consolidate the programme for the time left to focus on either of MGML or Cohort Teaching.
7. By December 2025, FCDO and IPs will jointly develop exit strategy for the programme considering the ODA allocation situation and aligning with Country Business Plan.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programmes theory of change, including any changes to outcome and impact indicators from the original business case.
1. The EMDC programme’s original Theory of Change remains extant. The ToC outlines how Bangladesh’s most marginalised children will acquire foundational skills—literacy, numeracy, and life skills—through two proven education models. It also shows how the programme will contribute to evidence-based policymaking and strengthen institutional capacity among state and non-state actors to support out-of-school children’s education. Additionally, it fosters community-led initiatives to enhance local accountability in education and raise awareness on social issues.
2. While the core assumptions and priorities outlined in the Business Case continue to hold, two outcome indicators (3.1 and 3.2) were revised to make them aligned with the outcome. One output level indicator on climate changed to align with ICF KPI. Also, result narrative of one indicator, and targets in 3 indicators were revised.
3. EMDC is consistent with FCDO principles of do no harm and leaving no one behind. There are strong mechanisms in place ensuring the most vulnerable children are able to access learning offer under protective environment.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
1. EMDC is on track in achieving the outcomes. It has achieved all the milestones against the outcome indicators. The programme demonstrated strong coherence with national education strategies and sector programmes, addressing learning gaps of the out-of-school children and reducing dropout rates by sending them in schools. The programme reached target group and improved academic outcomes for marginalized children.
2. 93% children reached required learning competencies to enable transition. 99% of catch-up education graduates transitioned to formal schools and over 94% are continuing their education. Targets on tackling barriers to girls' education were exceeded. Accelerated and alternative learning packages are both delivering quality education. 30% of the learners transitioned to formal school and completed primary cycle.
3. EMDC provided technical assistance for design of two national programmes for OoSC. These are initiated by BNFE with its own budget. The BNFE is using data generated from real time monitoring system supported by this programme. Key R&E products were completed; expected to inform future policy dialogue and advocacy.
4. Although the budget for research component was paused due to ODA cuts, two research studies led by UNICEF Innocenti and SARH, assessed effectiveness of different learning models delivered by EMDC. The findings are expected to inform policy dialogue in 2025/26. EMDC has influenced national education efforts, contributing to the design of the Remedial Learning Package implemented by the Government of Bangladesh under PEDP4.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio.
1. EMDC should continue as per design. The programme has successfully delivered a full cycle of catch-up education in the AR period. The programme continues to be highly relevant in addressing the educational needs of marginalized children in Bangladesh, particularly in the wake of the COVID-19 pandemic. By aligning closely with the formal curriculum and involving stakeholders such as local communities, parents, and government authorities, the program ensured a smooth transition back to formal schooling. Strategic placement of Learning Canters near marginalized communities enhanced accessibility, addressing barriers such as distance and socio-economic challenges. The programme's diagnostic approach allowed for tailored support, meeting students at their current academic levels and addressing specific learning gaps.
2. It was clear from conversations with teachers, community leaders and parents that children, particularly those from low-income households would not have reached age and grade appropriate learning milestones without attending EMDC schools. Based on results, performance of IPs, active engagement EMDC schools with GPs and BNFE, learning from EMDC fed into design of national programme for OoSC. Research and Evidence component lagging behind in previous years made expected progress and will continue next year without funding from the programme.

## C. DETAILED OUTPUT SCORING

	Output Title	Children who have dropped out of education complete quality catch-up education.
	Output number:		1	Output Score: A+
	Impact weighting (%):		30%	Weighting revised since last AR? No

Indicator(s)					Milestone(s) for this review 2025	Progress 2025
1.1 Number of children enrolled in the catch-up programmes, disaggregated by gender. Gender parity as a minimum requirement.					BRAC 20,000 / (50% girls)	Moderately exceeded (A): / BRAC- 20,001(Girls: 58%, Children with Disabilities: 849).
1.2 Percentage of enrolled children completing catch-up education					BRAC- 90%	Moderately exceeded (A+): / BRAC- 99.32% (Boys 99.18%, Girls: 99.42%)
1.3 Percentage of trained teachers applying their acquired knowledge and skills in teaching learning					BRAC -80%	Moderately exceeded (A+): / BRAC 100%

Briefly describe the output’s activities and provide supporting narrative for the score.
1. Output 1 covers ‘catch up’ education for OoSC, or children with low learning and those who had not reached grade level competencies. Overall, achievements exceeded targets for enrolling children and gender parity. Disadvantaged children were identified through household survey as well as actively engagement with local education authority and communities. Catch-up education was delivered through 800 LCs.
2. Almost all students graduated (boys: 99.18% and girls: 99.42%) against the target of 90%. Students with disabilities achieved a graduation rate of 98.07% while children from ethnic backgrounds had an impressive rate of 99.66%. Rigorous monitoring, functional CMC, and attractive teaching learning contributed to high rate of completion.
3. All 800 female teachers received basic, subject-based and refresher training on accelerated teaching-learning pedagogy. 100% of those trained teachers have applied accelerated teaching learning pedagogy in the classroom at different levels, which has significantly surpassed the target by 20%. Monitoring data, confirmed through field visits, showed that about 80% of teachers performed at ‘good’ level (scoring 3 or above out of 4), 20% performed at a ‘fair’ level (scoring 2), and no teacher at ‘poor’ level. This reflects a strong overall performance and effective capacity-building efforts for teachers.
4. On completion of catch-up, approximately 99% of the catch-up graduates transitioned to formal primary schools. Pupil attendance and performance in formal schools is tracked by Centre Management Committees (CMCs) and programme staff indicating good collaboration between EMDC and GoB.

Describe any changes to this output during the past year, and any planned changes because of this review.
No changes were made within the review period.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Recommendations	Progress
By December 2024, FCDO and IPs shall review the teacher salaries, incentives, and other offers within the scope of available programme budgets. Teacher motivation is central to success of EMDC-B.	In consultation with FCDO, BRAC reviewed and proposed revised budget aligning with budget forecasted under the EMDC-B.

Lessons
LCs need to be in allocation which is easily accessible for students and for the parents to monitor if students are attending lessons. The link between LCs and Government Primary Schools (GPS) are crucial in making sure transition of students proceed smoothly.
Recommendations
by December 2025. IPS to explore whether it is viable, to co-locate and integrate catch-up learning in Government Primary Schools, supporting efficient and timely transition of students.

	Output Title	OoSC who face barriers to attend formal education access and complete quality alternative education
	Output number:		2	Output Score:			A+
	Impact weighting (%):		30%	Weighting revised since last AR?			No

Indicator(s)					Milestone(s) for this review	Progress
2.1 Number of out of school children in alternative education					53,025 / (50% Girls) / (9,375 new)	Moderately exceeded (A+): / 54,948 / (53% Girls) (8091 new)
2.2 Percentage of enrolled children completing alternative education					25%	Moderately exceeded (A+): / 29% / On track to achieve the cumulative target of 80% by end of cycle in Year 5.
2.3 Percentage of trained teachers applying acquired knowledge and skills in delivering alternative education					80%	Moderately exceeded (A+): 100% teachers (all female) are applying skills against the target of 80%.

Briefly describe the output’s activities and provide supporting narrative for the score.
1. This output focusses on the provision of 45 months long alternative education (i.e. MGML), targeting remote locations where access to GoB schools is extremely limited. Despite initial challenges, overachievement in enrolment and completion has been possible through active engagement of local communities. In Bandarban, ethnic minority children from the Mro, Marma, Tripura, and Tanchangya communities are exclusively served.
2. All teachers received pedagogic training to implement MGML in classroom along with regular refreshers training. Of the 100% teachers applying their acquired knowledge and skills in teaching learning, 78% teachers performed ‘good’ and 22% performed ‘fair’. No teachers are found to be `poor’ Training efficacy is measured by assessments of students throughout the learning cycle.
3. The EMDC programme uses a three-tiered model to build capacity, with UNICEF providing expert support in pedagogy, assessment, and inclusion. Around 50 Master Trainers continuously mentored 1,448 community teachers through annual basic and subject-based training as well as bi-monthly refreshers. Programme Organizers visited each Learning Centre at least four times a month.
4. The programme operates through 1,338 well-equipped Learning Centres, using Courtyard-based (CYLC) and Personalised Learning System (PLS) models, and is led by trained community teachers. Despite 147 dropout of students due to slum evictions and migration- retention remains high, reflecting the programme’s inclusive and effective approach.
5. To address the dropout issue, UNICEF has developed a strategy to ensure continuity in education, i.e. re-enrol displaced children in one of the neighbourhood LCs. If they migrate to an EMDC location, they can enrol in the nearby LCs; otherwise, efforts are made to place them in other educational institutions.

Describe any changes to this output during the past year, and any planned changes because of this review.
For output Indicator 2. 2, the yearly completion rate targets were revised in the log frame and agreed with UNICEF as 15%, 25%, 20% reaching 80% at the end.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Recommendations	Progress
IPs shall explore how screening and inclusion approaches can be further improved to enhance enrolment of CWDs. IPs can review the Government’s SEND framework (under PEDP4) to adapt/revise into CWD strategies.	FCDO supported EQIP-B programme helped the government to develop the SEND (Special Educational Needs and Disabilities) Framework outlining how children with learning difficulties or disabilities are supported in education. UNICEF have drawn on learnings SEND framework to inform their work under EMD, reflecting cross-programme synergy.

Lessons learned:
Right targeting is critical to make sure that the most disadvantaged OoSC get access to education. Despite of intensive social mobilisation, community engagement and revision of screening tools, it is challenging to convince parents to bring CWDs into the LCs, because of social stigma and shame. Also, parents are not confident that the LCs have adequate physical facilities to address the needs of the CWDs. Targeting in urban areas proved complex; in Dhaka the population was very mixed, with poorest households directly next to higher income ones. BRAC’s pre-existing knowledge of target communities increased precision of targeting. Whilst IP’s have identified some CWD’s, during field engagement the FCDO team found that the methodology for screening was not fully understood by some staff.
[note] Washington Group Scale Disability Questionnaire
Recommendation:
Following the MoPME approved SEND Framework (supported by EQUIP-B), targeting of the most disadvantaged children should be strengthened, with particular attention given on increasing capacity of teachers for targeting CWDs.

	Output Title	Communities are engaged to overcome socio-cultural barriers to education and better awareness of climate change (UNICEF, BRAC).
	Output number:		3	Output Score:		A+
	Impact weighting (%):		10%	Weighting revised since last AR?		No

Indicator(s)					Milestone(s) for this review		Progress
3.1 % of communities engaged with advocacy and awareness raising activities, with gender parity (50/50) in activities					UNICEF- 80% of target communities / BRAC - 80% (20 parents out of 25 per school)		Moderately Exceeded (A+): UNICEF- 100% / BRAC- 86.64% (22.16 parents out of 25 per school)
3.2 Percentage of CMC (Centre Management Committees) members who take demonstrable actions to overcome socio-cultural and other barriers to children's continuation and completion of education, especially girls					UNICEF: 40% of community members have been involved in two actions.		Substantially Exceeded (A++): 90% (50% female)
3.3 (ICF) Number of people (individuals) whom the programme has supported to prepare for and deal with the effects of climate change.					UNICEF: Module for children’s skill development on CC adaptation is included in life skill package. / BRAC: Module and teacher guide developed to deliver lessons on disasters and climate change risks.		Met (A) Climate resilience integrated through DRR planning, green LC models, and updated skill modules. / Orientation module developed. Action plan guideline is in the process of development.

Briefly describe the output’s activities and provide supporting narrative for the score.
1. The output 3.1 captures girls’ enrolment and retention in education, awareness of community and parents on issues/barriers to girls' education such as child marriage, and regressive cultural norms. Communities are engaged through CMC meetings, parents’ meetings, community dialogues, home visits and campaigns. Conversations with community members- both men and women- showed improved understanding of how education is crucial to girls’ empowerment, participation and social mobility.
2. CMC members, especially women and girls took active actions to challenge socio-cultural and other barriers to completion of girls’ education. These actions include members providing free spaces for establishing schools, volunteering to make learning materials, providing hygiene kits for girls and helping children with commute to learning centres. Communities provided 300 rent-free Learning Centres, along with support for electricity, water, sanitation and furniture. They also established alternative learning spaces. 40 LCs were hosted inside Government Primary Schools.
3. Climate change adaptation and mitigation strategies supported resilience and ensured continuation of education. Following heatwaves in 2024, BRAC adjusted school timings and closed schools to safeguard students. When Cyclone REMAL damaged 160 schools, particularly in Bhola and heavy rainfall caused flash floods affecting schools in Sylhet and Sherpur, efficient and timely response ensured minimal damage.
4. Given the vulnerability to the impact of climate change and natural disasters in Bangladesh, both IPs have emergency preparedness plans in place; developed through working closely with Ministry of Disaster Preparedness and Relief (MoDMR) and Local Government at Upazila and District level.
5. Education impacts livelihoods by creating pathways to avail pre-vocational skills training opportunities followed by employability in informal sector and enhancing self-employment. Also, education gained through attending learning centres supported by EMDC has provided boys and girls with choices to continue further education and employability, ultimately contributing to poverty reduction and well-being.
Describe any changes to this output during the past year, and any planned changes because of this review.
1. In consultation with the IPs, two indicators were added to the log frame in February 2025.
2. Progress on recommendations from the previous AR (Annual Review) (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
Recommendations	Progress
By March 2025, the IPs shall remodel Disaster Risk Reduction (DRR) and Education in Emergency (EiE) plan into ‘climate change mitigation and adaptation plan’.	BRAC continued with adaptive measures to address learning loss, collaborating with its Climate Change Programme (CCP) to develop climate-related educational content, and revise risk register. UNICEF developed different modules and teachers’ guides for orientations on disaster and climate change risks to communities.

1. Lessons learned: Climate change is significantly impacting LCs, leading to school closures, learning losses, and challenges in accessing education. Extreme weather events like floods, storms, and heatwaves are causing physical damage to school buildings, disrupting learning, and forcing schools to be used as emergency shelters. These disruptions resulted in long school closures with a few LCs closed for at least one month due to flood and heatwave.
2. Recommendation: Using the evidence generated by EMDC, FCDO and IPs should lobby policymakers to invest in climate-resilient school infrastructure.
	Output Title	Evidence on how to support OoSC to learn is generated and shared with stakeholders
	Output number:		4		Output Score:		A+
	Impact weighting (%):		15%		Weighting revised since last AR?		No

Indicator(s)				Milestone(s) for this review		Progress
4.1 Number of policy briefs, working paper, reports, etc generated based on research, studies, assessments, and evaluations				UNICEF 1 / BRAC 2		Met (A) / UNICEF 1 / BRAC 4
4.2 Number of policy dialogues and knowledge products dissemination events organised				1 knowledge product developed. / Dissemination of knowledge products.		Moderately exceeded (A+). / BRAC-Four audio visual products developed and disseminated with government (DPE and BNFE) and other stakeholders. / UNICEF-Six audio visual products developed and disseminated with government and other stakeholders.

Briefly describe the output’s activities and provide supporting narrative for the score.
1. UNICEF Bangladesh and Innocenti completed the first draft of a research report on catch-up education. This is the first of four planned knowledge products to be delivered by the end of the programme. The research brief will be shared with FCDO soon.
  [note] Innocenti is the Global Office of Research and Foresight of UNICEF. UNICEF Innocenti works for and with children and young people to seek solutions to their most pressing challenges through research activities.
2. BRAC conducted an endline assessment of the accelerated education model. Findings show majority (94.7%) of parents, members of community and teachers think the model is pivotal in facilitating children's return to regular schools. While progress is notable, sustained investment is essential to maintain and build on these gains.
3. During this reporting year, BRAC organised four lessons-learned events to share programme insights with local government stakeholders. News coverage of these events appeared in seven different local media outlets.
4. The reduction in ODA funding impacted on Indicator 4.1 and 4.2, suspending the procurement of a research and evidence provider. UNICEF submitted one policy document and BRAC four, all completed with own funds. The component targets were modified to address the funding gap.
Describe any changes to this output during the past year, and any planned changes because of this review.
No changes during the reporting period. The indicators and milestones for the remaining year may need adjustment depending on how the programme is resourced considering cuts in ODA funding.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Recommendations	Progress
Recommendation: By March 2025, FCDO and IPs to develop a joint evidence generation plan and an advocacy strategy to ensure challenges, lessons learned, and good practices are documented and used to influence OoSC policy.	An evidence plan has been prepared by UNICEF. UNICEF is closely working with FCDO for updating the plan so that challenges, lessons learned, and good practices are documented and used to influence GOB OoSC policy.

Recommendations:
The database developed and maintained by IPs should be actively used for studies and assessments thus minimising use of consultants for research and evidence generation. This will improve sustainability of programme activities by demonstrating relevance of programme data for advocacy.
	Output Title Capacity of BNFE strengthened to deliver education for OoSC.
	Output number:	5		Output Score: A
	Impact weighting (%):	15%		Weighting revised since last AR? No

Indicator(s)			Milestone(s) for this review		Progress
5.1 Number of TAs (Technical Assistance) provided to the BNFE			2		Met (A) 2
5.2 BNFE's capacity developed in programme design and monitoring			TA support provided for developing real time monitoring system (RTM)		Met (A): The development of the RTM system is at final stage and ready for integration within BNFE’s regular programmes.

Briefly describe the output’s activities and provide supporting narrative for the score.
1. UNICEF extended TA to BNFE on OoSC, supporting development of skill-based training, pathways for mainstreaming students into formal schools and operationalising Non-Formal Education Board for certification.
2. UNICEF supported revitalization of the Non-Formal Education (NFE) Board, including training of assessors. This has enabled the Board to provide certification not only for direct BNFE programmes but also for trainings under other ministries and NGOs.
3. UNICEF helped shape BNFE’s flagship national programmes, i.e. Alternative Learning Opportunity for Out of School Children (ALO, $17m for 3 years) programme and SKILFO-2nd phase, providing skill-focused literacy programme at pre-vocational level to 100,000 young people in 16 districts. Both are funded by GoB, ensuring sustainability. Government has requested UNICEF to continue with TA.
4. The TA has been catalytic in building capacity of Ministry of Primary and Mass Education (MoPME) and Bureau of Non-Formal Education (BNFE) by strengthening monitoring and evaluation of non-formal education and influencing the design of the Primary Education Development Programme 5 (PEDP5). Together these helped to improve GOB capacity for addressing education needs of OoSC and to develop policies supporting NFE. This has led to improving the efficiency and effectiveness of education for OoSC.

Describe any changes to this output during the past year, and any planned changes because of this review.
The indicators were changed in Feb 2025.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Recommendations	Progress
FCDO to deepen engagement with BNFE in the coming year, leveraging EMDC and Education Quality Improvement Programme – Bangladesh (EQUIP-B) TA support and investment to support policy dialogue on inclusive and accessible education.	Increased engagement with EQUIP-B has led to strengthening of the Bangladesh National Qualifications Framework (BNQF), thus improving access to non-formal education for OoSC.
[note] EQUIP-B is a FCDO funded bilateral programme focusing on technical support to GoB to support education sector reform.

Lessons Learned:
TA should be demand led and therefore UNICEF and FCDO should encourage BNFE to use them strategically.
Recommendation:
IPs should actively engage with GoB on assessing how TA is contributing towards strengthening of systems and if found positive, lobby BNFE to allocate budget for scale up.

D: VALUE FOR MONEY

Key cost drivers and performance
Economy: The key costs of the programme are teacher salary, training, monitoring, LC (Learning Centre) costs and TA.
VfM performance compared to the original VfM proposition in the business case.
1. Economy: The main key cost driver for BRAC and UNICEF is procurement (teaching and learning materials, and office equipment). The cost per child per year for BRAC is £53 and for UNICEF it is around £41, which is lower than the Business Case predicted cost of £53-£63. BRAC measured learning cost, teachers cost, infrastructure cost and supervision cost as a percentage of the total cost. The teacher development cost was 16% of total teachers against the yearly budgeted cost of 18%. Teacher costs include salary and capacity building expenses.
2. Efficiency: 99% of enrolled children in UNICEF schools transitioned to formal schools after achieving Foundational Literacy and Numeracy (FLN) competences. Among children aged 10 and above, 100% gained basic reading skills significantly above the 80% target, while 95% acquired foundational numeracy. Follow-up data show 95% of learners remained in school one year later. These results were independently validated by a study by the South Asia Regional Research Hub. These outcomes were achieved at a cost of only £45 per child per year for UNICEF and £64.78 for BRAC, representing good VfM.
3. UNICEF’s MGML model has enabled 29% of learners to transition into formal education within just two years of rollout. Among children aged 10+, 95% demonstrated reading proficiency, and 99% of the 54,948 enrolled children achieved grade level numeracy. After six months, over 90% of transitioned learners remained enrolled in schools, confirming long-term educational impact. Despite the complexity of reaching remote and marginalized populations, this was achieved at a reasonable cost of £86 per child per year, reflecting good VfM through a flexible, inclusive, and scalable model.
4. Beyond direct learning outcomes, targeted TA to Directorate of Primary Education (DPE) has strengthened national remedial learning strategies, while collaboration with the Bureau of Non-Formal Education (BNFE) is helping shape a more responsive, coordinated, and accountable Non-Formal Primary Education (BNFE) System. Over 300,000 community members, including 50% women have been mobilized, reinforcing social capital and local ownership.
5. Effectiveness: To measure the effectiveness of the programme, BRAC maintained two indicators. First, there is the transition rate, in which the percentage of EMDC graduates who transitioned back to formal school is calculated. For this indicator, BRAC EMDC achieved 99.74% against the milestone of 90%. Secondly, there is the retention rate, in which the percentage of EMDC graduates who have transitioned back to formal school and continue study for at least one year is calculated. In this indicator, BRAC calculated the percentage of students who graduated after the second year of the programme and were retained in formal schooling in the third year of the programme. Here, a rate of 99.39% against the milestone of 80% was achieved.
6. For UNICEF, 99.1% of the students who participated in the catch-up education completed the course. 100% teachers are reported as applying their acquired knowledge and skills. Monitoring data validated through field visits showed 78% teachers performed at ‘good’ level (score ≥3 out of 4), and the remaining 22 per cent at ‘fair’ level (score ≥2 out of 4), with none assessed as poor. This indicates effectiveness of training, mentoring, and supervision.
7. Equity: Equity is embedded through rigorous use of disaggregated data, including gender, socio-economic status, disability, and ethnicity. Most children, including 55% girls, come from disadvantaged backgrounds, including families from lowest income groups and ethnic minority communities. Income data show approximately 30% of families earn less than £55 per month, underscoring commitment to target the poorest households. Only 1.3% of children come from families earning £100 or more.
8. Nearly all teachers are women, recruited from within the communities where they serve. This approach has built trust with families, encouraged girls’ enrolment and retention, and provided employment and leadership pathways for disadvantaged young women. Teachers benefited from professional development, turning skills into economic empowerment.
9. In Bandarban and other regions with high ethnic diversity, the programme incorporated multilingual teaching strategies, with use of textbooks written in five ethnic languages.
10. Downstream partners have fully adopted UNICEF’s Prevention of Sexual Exploitation and Abuse (PSEA) policies. Awareness-building activities have been implemented with children, caregivers, teachers, and CMC members. Robust reporting mechanisms are operational across all learning centers.
Assessment of whether the programme continues to represent value for money.
Throughout the implementation process, IPs used resources (technical expertise, partnerships, resource mobilisation, outreach, advocacy, etc.), delivering results maximising VfM. To maximise the impact of the programme the results (outputs and outcomes) and costs were clearly defined. The 3Es – economy, efficiency, effectiveness as well as equity were well considered. This included making sure results are targeted at the poorest and include sufficient targeting of women and girls, so the programme was able to deliver maximum effectiveness, efficiency and economy for each intervention.

E: RISK

Overview of risk management
1. EMDC’s overall risk rating is moderate. The EMDC programme incorporates a comprehensive risk analysis framework, identifying and addressing risks and assumptions associated with each outcome. A detailed risk register and mitigation strategy was developed at the outset of the programme.
2. The EMDC risk register identifies eight risks with mitigating actions; one has a major residual risk, four have moderate and three have minor. IP’s have risk registers, feeding into a combined risk register. All risks fall within FCDO’s risk appetite. The Logical Framework is regularly reviewed, and risk registers updated. Prior to formalizing agreements, all partners undergo micro-assessments and evaluations related to safeguarding and the Prevention of Sexual Exploitation and Abuse (PSEA). Each partner has designated two focal points trained on PSEA and safeguarding to ensure compliance and institutional accountability.
3. Financial and Fiduciary. Robust mitigation measures are in place consistent with the FCDO’s zero tolerance of fraud. Fraud registers are maintained by partners. Due Diligence Assessments (DDA) recommendations are followed up on a quarterly basis. IPs have strong financial systems aligned with FCDO requirements, regularly monitored and supported by training, including a session facilitated by FCDO in early 2025. Before formalizing partnerships, UNICEF conducted micro-assessments of downstream partners on financial systems. Both IPs conduct regular quality assurance through programmatic visits, spot checks, and financial audits.
4. Safeguarding risk After mitigation, safeguarding risks are moderate. BRAC and UNICEF have strong safeguarding policies and reporting mechanisms. Both maintain safeguarding registers to record incidents, and report cases to FCDO. Comprehensive PSEA assessment was conducted prior to engagement of (five) NGOs as delivery partner for UNICEF. UNICEF provided targeted orientations on safeguarding to 300 staff, 1,613 teachers, more than 11,000 CMC members, and about 240,000 parents, reinforcing its zero-tolerance approach to abuse. Various reporting mechanisms- accountability boxes, hotlines, and display boards are in place in LCs.
5. Reputational risk: Repeated ODA budget cuts may lead to loss of credibility with partners, including with GoB. These risks are mitigated through pro-active engagement with IPs to ensure there is minimal impact on access to learning. The residual risk remains moderate.
6. Service delivery risks increased due to climate shocks. Cyclones and floods have impacted on EMDC delivery in some locations. Both IP’s have emergency preparedness plans in place; FCDO added two indicators related to Climate Change in the Log Frame.
7. Policy and Programme Delivery: There is a risk that TA provided by EMDC will fail to influence GoB's approach to OoSC. Close collaboration with DPE and BNFE have helped to reduce the risk.
8. Weak community engagement—supported by incentives and accountability mechanisms—has enhanced local ownership. Sub-national authorities are actively involved, and community contributions remain vital to sustaining LCs. Given the current unstable political environment, risks especially related to political transitions need to be well managed. With continued collaboration with government and partners, adaptive strategies, and strong community engagement, it is recommended that this risk be considered as minor in the updated risk assessment.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Progress Monitoring and Coordination
1. FCDO meet IP’s quarterly to monitor and review programme progress and challenges. IPs submit progress reports to inform discussions and planning, in line with FCDO's reporting requirements. Achievements against all outputs are on track. A structured governance mechanism is in place, outlining partnership and reporting expectations. Quarterly meetings and biannual partner coordination sessions facilitate reviews of results, risks, and emerging issues, ensuring strong alignment between FCDO and UNICEF & BRAC.
2. All partners submit progress reports on time, in every quarter. The reporting quality is generally found to be satisfactory. Responses to the Due Diligence Assessment (DDA) were reasonable, with all actions completed or underway to our agreed timelines. For BRAC out of 13 Action 9 has been completed and 4 are in progress. UNICEF DDA refresher is in progress. No fraud and safeguarding cases were reported during this reporting period and FCDO continues to make it clear that it has zero tolerance towards fraud and corruption.
Delivery Approach
UNICEF delivers through 5 downstream partners, all with track records of successful delivery in Bangladesh and working to FCDO standards and requirements. BRAC delivers utilising their in-house capacity. BRAC Field offices manage school operations, with two (2) Divisional Managers and one Deputy Manager collaborating with a group of Upazila Managers and Programme Organizers. The programme team meets once a week, while the field team meets once a month to discuss updates, work plans, challenges, strategies for overcoming them, and deliverables.
[note] Jagoroni Chaka Foundation, JAAGO Foundation, FIVDB, VERC, CODEC
Research and Evidence
Good progress has been made for Output 4, R&E. Innocenti and South Asia Research Hub -SARH) are engaged in evidence generation supported by workplans.

Financial Management
1. IPs have good financial management in place to keep the programme delivery on track. Funds were disbursed to UNICEF in six-monthly in advance against an agreed work plan, expenditure report and forecast, and BRAC payments were made in arrears on a quarterly basis against actual expenditures and accordingly to the PrOF guidelines. Prior to each payment FCDO assessed progress against work plans. Up to 31st March 2025, FCDO disbursed £3,250,000 to UNICEF against the agreed amount and £1,295,734 to BRAC as arrears against the forecast £1,386,770. The total programme allocation for the reporting period was £4,500,000, and the actual expenditure was £4,547,852. In line with the Accountable Grant (AG) Arrangement, and Contribution arrangement FCDO disbursed arrears to BRAC and six-monthly advance payments to UNICEF. During the reporting period, partners submitted fund requests on time with adequate supporting documentation. The FCDO programme managers verified all the financial reports and fund requests in line with FCDO’s guidance.
2. Audit: BRAC shared their audit report with FCDO covering the period from April 2023 to March 2024 submitted in May 2025. There were no major adverse findings in BRAC Report. UNICEF conducts audit based on its framework arrangement and submitted a certified financial statement in July 2024 which demonstrated full compliance with financial and fiduciary best practices.
3. Regular audit and spot checks have been conducted with partners covering different locations. The programme activities are reviewed and marked positively. There are a few minor observations which UNICEF is in the process of addressing. All DPs have developed action plan based on observations and recommendations and UNICEF is closely following up.
4. Commercial: Accountable Grant (AG) arrangements are in place with BRAC, and Contribution Arrangement is in place between FCDO and UNICEF. UNICEF engaged five downstream partners to deliver catch-up education, whilst BRAC delivers using in-house capacity. Both partners scoped to identify disadvantaged communities and beneficiaries to determine optimal locations for LCs.
5. Assets Management: In this review period, few assets were purchased by BRAC. BRAC provided the asset list to FCDO for verification. FCDO carried out asset spot checks of IPs on 5 February 2025 and found all items were identifiable and clearly labelled. FCDO AR team visiting LCs in Gaibandha also checked on assets procured by BRAC. BRAC and UNICEF follow competitive processes for procuring goods and services.
6. Fraud/Internal Control: IPs have internal oversight, control and risk management mechanisms. For UNICEF no fraud was reported during AR period and for BRAC one theft (a fan) and a fire case were reported.
7. Safeguarding: IP’s have safeguarding/ PSEA policies in line with international standards. All implementing partners and consultants have signed a code of conduct, and targeted training on PSEA and fraud risk mitigation was provided in 2024. Safeguarding mechanisms are reviewed during the DDA process and are monitored frequently. IPs have assessed downstream partners safeguarding capability and provided training to front-line and programme personnel. No safeguarding incident was reported during this period. Safeguarding measures—such as suggestion boxes, hotlines, visual boards, and “good touch, bad touch” posters—have been implemented in all Learning Centres (LCs), alongside regular awareness session with CMCs and parents.
8. Recommendations: February 2026.FCDO to provide Safeguarding refresher training to BRAC and UNICEF.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
1. Rigorous and multi-dimensional approach to monitoring was taken to assess effectiveness of EMDC. This covers all aspects of the programme, from front line delivery to programme, financial and risk management. This includes a regular quarterly reporting, and field visits.
2. All data are captured in the Real-Time Monitoring (RTM) system, which teachers use daily to track student attendance and assessments. A robust Monitoring and Results Framework, co-developed with FCDO, guides systematic tracking of outputs, outcomes, and impact. The framework integrates diverse data sources including RTM, partner reports, and technical assistance records. This integrated system guarantees programme’s alignment with programme objectives, response to emerging needs, and consistent delivery.
3. Evidence: EMDC seeks to generate evidence on what works for OoSC, utilising innovative learning methods. Although delayed due to ODA budget reductions, two strands of research were planned. One is already published with results showing effectiveness of the catch-up programme and remedial learning.
4. Learning: FCDO and IPs have followed a continuous cycle of learning during the programme through the sharing of data and outcomes; ongoing technical support to partners, enabling strategic adjustments to address challenges such as slum evictions in Dhaka, heatwave in 2024 and unstable political environment. EMDC integrated climate resilience into its planning, including through ‘green LCs’ and Disaster Risk Reduction (DRR) and Education in Emergency (EiE) strategies. Strong collaboration with education authorities ensured alignment with national reforms for advancing equitable education for Bangladesh’s most vulnerable children.
Date of last narrative financial report	BRAC Audit Report April 2023 - March 2024UNICEF Internal Audit of the Bangladesh Country Office 2022	Date of last audited annual statement	BRAC May 2025 / UNICEF May 2025