## Annual Review

Title: Tackling Deadly Diseases in Africa Programme 2 (TDDAP2)
Programme Value £ (full life): £95,000,000		Review date: May 2025
Programme Code: 300585	AMP start date: 25/05/2023	AMP end date: 31/03/2028

Summary of Programme Performance
Year	2024	2025
Overall Output Score	A	A
Risk Rating	Major	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0003099.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0004865.xlsx

GLOSSARY

Africa CDC - Africa Centre of Disease Control and Prevention / AMA - African Medicines Agency / Annual Review - AR / APEX - Africa Programmes and Expertise Department / ARRO - Africa Rapid Response to Outbreaks / AVoHC - Africa Volunteers Health Corps / AU - African Union / CSO - Civil Society Organisation / CBS - Community Based Surveillance / DEFRA - Department for Environment, Food & Rural Affairs / DHSC - Department of Health and Social Care / DRC - The Democratic Republic of the Congo / ECOWAS - Economic Community of West African States / EPR - Emergency Preparedness and Response / EU - European Union / FAO - UN’s Food and Agriculture Organisation / FCDO - Foreign, Development and Commonwealth Office / GAVI - Global Alliance for Vaccines and Immunisation / GEA - Gender Equality Act / GEDSI - Gender Equality, Disability and Social Inclusion / GEFA - Global Evaluation Framework Agreement / GEMFA - Global Evaluation and Monitoring Framework Agreement / GHIs - Global Health Initiatives / GHS - Global Health Security / HRG - Humanitarian Response Group / HMG - Her Majesty’s Government / HSOT - Humanitarian Stabilisation Operations Team / ICF - International Climate Finance / IDI - The Infectious Diseases Institute / IDS - International Development Strategy / IDSR - Integrated Disease Surveillance and Response / IFRC - International Federation of the Red Cross and Red Crescent / IPD - Institut Pasteur de Dakar	IHR - International Health Regulations / IANPHI - International Association of National Public Health Institutes / IPC - Infection Prevention and Control / JEAP - Joint Emergency Preparedness Action Plan / JEE - Joint External Evaluation / KPI - Key Performance Indicator / MEL – Monitoring Evaluation and Learning / M&E - Monitoring and Evaluation / MoU - Memorandum(s) of Understanding / NAPHS - National Action Plans for Health Security / ODA - Official Development Assistance / PPPR - Pandemic preparedness, prevention, and response / PRO - Programme Responsible Owner / PROF - Programme Operating Framework / SRO - Senior Responsible Owner / RCCE - Risk Communication and Community Engagement / RED - Research and Evidence Directorate / SEAH - Sexual Exploitation, Abuse and Harassment / SDG - Sustainable Development Goals / SURGE - Strengthening and Utilising Response Groups for Emergencies / TASS - Transforming African Surveillance Systems / ToC - Theory of Change / ToR - Terms of Reference / UK - United Kingdom / UKHSA - UK Health Security Agency / UK-PHRST - UK-Public Health Rapid Support Team / UNICEF - United Nations International Children’s Emergency Fund / VFM - Value for Money / WHO - World Health Organisation

## A: SUMMARY AND OVERVIEW
Description of programme
The Tackling Deadly Diseases in Africa Programme 2 (TDDAP2) aims to save lives and reduce the impact of disease outbreaks on populations in Africa whilst protecting populations around the world, including the UK. Building on lessons and achievements of TDDAP1 and other epidemic responses, this programme, working in partnership with countries and regional institutions, aims to strengthen health security capacity and support African leadership to prevent, detect and respond to health emergencies. TDDAP2 works at regional, national and community levels with the following objectives:
• Strengthening African regional health security through direct support to key regional institutions, including the Africa Centre for Disease Control (Africa CDC) and the World Health Organization/Africa Regional Office (WHO/AFRO).
• Strengthening health security capabilities at national and community level through a national component that provides focused technical assistance to Democratic Republic of Congo (DRC), Ghana, Kenya, Malawi, and Uganda.
• Reducing the impact of disease outbreaks in African countries and communities through rapid, emergency support via the Africa Rapid Response to Outbreaks (ARRO) fund.
Building on lessons from TDDAP1, TDDAP2 adopts a comprehensive Health Systems Strengthening and One Health approach to optimise impact and results, integrating climate change, gender equality, and social inclusion considerations into its core activities. An independent Monitoring, Evaluation and Learning (MEL) component ensures continued learning and promotes a responsive and adaptive approach to implementation.
Summary supporting narrative for the overall score in this review
Overall, TDDAP2 programme is assessed as meeting expectations during this second annual review (AR) period when assessed against programme outputs (Table 1). It has delivered meaningful early achievements, particularly in emergency response to outbreaks and developing the health workforce in Africa for rapid mutual support during health emergencies.

The TDDAP2 programme fully spent its allocated budget during the annual review period. In terms of spend per component, the regional component had the highest spend at 54%, followed by ARRO at 32%. The national component partner was contracted during the review period, resulting in 10% of spend. The contract for the MEL component commenced in Q4, with 1.2% of overall spend. Africa CDC indirect spend through various partners was 3.5%.

Table 1. Assessment of progress against TDDAP2 log frame Outputs
	Overall Outputs Assessment	Met Expectation A
	Outputs Description	Weighting	Score
1.	Improved participation of communities and civil society in surveillance mechanisms and national health security governance.	10%	B
2.	Stronger core public health functions and capacity in focus countries	15%	A
3.	Strategic partnerships with key African health institutions to strengthen capacity on emergency preparedness and response.	40%	A
4.	Expertise, financial, logistical, and technical support for rapid containment and response to emerging outbreaks	30%	A+
5.	Robust information is generated and used by government, communities and partners for evidence-based decisions, programme adaptation and lesson learning.	5%	A

Timely and targeted support for Marburg Virus Disease (MVD) and Cholera responses through ARRO has enabled embedding of community engagement and reduced the impact of these disease outbreaks. Training of African Volunteer Health Corps (AVoHC) through WHO AFRO and Africa CDC has strengthened capacity within Africa to respond to outbreaks and strengthened coordination between regional health security agencies.

FCDO's early investment in the Africa CDC/WHO AFRO Joint Emergency Action Plan for Public Health Emergencies in Africa (JEAP) led to significant achievements during the AR period. These included the publication of JEAP's first annual report, a Monitoring, Evaluation and Learning plan, a Resource Mobilization Strategy, and a communications plan. This has supported raising of $360m to date for Health Emergencies preparedness and response through the global Pandemic Fund by Africa governments and institutions, including the Africa CDC.
The national component and MEL component were recently awarded and are yet to demonstrate significant outputs beyond inception activities. The ability of TDDAP2 to demonstrate greater agility was tested through pivoting of resources to mpox and Ebola response in DRC and Uganda through the national component. Delays in mobilisation however limited contribution to the response through this route during the AR period.
Major reductions in Official Development Assistance (ODA) by bilateral donors late in the AR period are changing the landscape of external support to health security in Africa. Countries responsiveness to these will determine ongoing ability of the programme to fully deliver the intended outputs.
Major lessons and recommendations for the year ahead
TDDAP2 is making progress to achieve its overall objectives and in the next year should implement the following recommendations:
1. Direct funding to Africa CDC should further enhance collaboration with WHO AFRO through the Joint Emergency and Preparedness Action Plan (JEAP) and across UK government engagements that support Africa CDC.
2. Monitoring of regional partners should be intensified as they scale up their programmes portfolio, including ensuring Institute Pasteur de Dakar’s surveillance capacity remains high quality throughout expansion.
3. TDDAP2 should streamline joint working with investments in Global Health Initiatives (GHIs) that have health security objectives (Global Alliance for Vaccines and Immunisation (Gavi), Global Fund to Fight AIDS, Tuberculosis and Malari and the Coalition for Epidemic Preparedness Innovations (CEPI)) and other Government Partners including DHSC, UKHSA and DEFRA. For Gavi, this should include TDDAP2 supporting integration of community awareness initiatives in preventive vaccination campaigns and promoting donor coherence at the UK-hosted Global Fund replenishment in 2025.
4. TDDAP2 should be a core part of joint FCDO work to accelerate progress under the Lusaka Agenda, and The AU Roadmap to 2030 & beyond including on community engagement and Africa CDC’s new strategy on health financing. TDDAP2 needs to ensure all delivery partners adhere to Lusaka Agenda principles, including promoting integrated planning and service delivery and minimising programmatic burden on countries.
5. The national component contractor should review workplans in focus countries to prioritise enhancing meaningful community engagement in health security. Thematic technical assistance to enhance inclusion of climate impacts, GEDSI and One Health policies in national action plans for health security (NAPHS) must also be targeted at each country’s stage of review and development.
6. The ARRO component should improve complementarity with the other programme elements to provide greater impact. For example, by integrating community engagement activities and structures used during an outbreak response into country programme workplans as appropriate, to ensure ongoing inclusion of these communities in the health security architecture.
7. The adaptable and flexible nature of the programme should continue and routes for rapid pivoting based on emerging threats should be identified, based on the experience of additional mpox work contracted to Palladium.
8. The upcoming Monitoring, Evaluation and Learning workshop to review the Theory of Change (ToC) and log frame should facilitate prioritisation and complementarity of activities, given the uncertain funding outlook and rapid changes in the overall health security landscape.
In February 2025, the UK Prime Minister took the decision to reduce the UK’s Official Development Assistance (ODA) to the equivalent of 0.3% of GNI by 2027. Significant shifts will be required across the ODA portfolio to achieve this and the TDDAP2 programme will enter a transition period during the next AR period. It is recommended to take a rigorous approach to this prioritisation work to ensure modernised approaches to development centred on establishing long-term partnerships of mutual interests are progressed in parallel to delivering value for money and impact to best support the people it benefits.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
The expected impact of TDDAP2, assuming its outcomes are achieved and assumptions met throughout the programme, is a reduction in harmful effects from infectious disease threats among African populations and globally. TDDAP2 combines complementary interventions at regional, national, and community levels to enhance compliance with international health regulations and support effective national and cross-border responses to achieve impact. The underpinning logical framework covers the four dimensions of the programme (community, national, regional, and rapid response) as inputs, with corresponding outputs and interrelated outcomes.
The landscape of external support to health security in Africa has significantly shifted during the AR period. Alongside substantial decreases in ODA, withdrawal of large donors from technical, political and response functions will heavily impact health systems reliant on external support and are likely to threaten health gains. Continental actors including through Africa CDC and WHO AFRO have strongly called for a rapid scale up of domestic financing and leadership, but the immediate nature of much of the external funding withdrawal and absence from policy discourse remains highly disruptive. Consequently, the assumptions underlying the theory of change—specifically regarding donor and political commitment and sustained resource allocation towards health security at regional, national, and community levels—are concurrently being tested to an unforeseen extent.
Whilst partnership and political leadership between Africa CDC and WHO AFRO has been sustained to progress the JEAP, the plan is likely to struggle to attract significant additional external funds to the extent anticipated, given the current funding environment. Reductions in ODA from the United Kingdom (UK) may also affect TDDAP2's capacity to deliver the necessary technical support and resources to achieve its objectives.

These fundamental changes will affect programme design, necessitating a revision of the programme’s theory of change and an assessment of achievable outputs and outcomes within the new context. A business case addendum is anticipated by the next annual review to reflect these adjustments. However, the change in context also offers an opportunity to more effectively demonstrate how the programme components mutually reinforce and combine to support outcome attainments in the theory of change.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
TDDAP2 is in its second year as a programme and most implementing partners have only recently been contracted. As such, the programme is not assessed at impact and outcome level although process milestones and progress against some indicators are recorded and demonstrate early progress towards interventions to meet outcome indicators (Table 2).
Table 2: Review of Impact and Outcome Indicators
Type	Indicator	2025 Milestone	Progress
Impact 1	Improved detection and response leading to increase in outbreaks identified and reduction in number of Public Health Emergencies	Baseline data	Met
Impact 2	Reduced mortality rate from outbreaks in the WHO AFRO region.	Not assessed
Outcome 1.1	Increased IHR implementation capacity in priority countries.	Not Assessed
Outcome 1.2	Increased community capacity to prepare for, prevent, detect, and respond to outbreaks as reported by external evaluation.	National component supplier contract awarded, and implementation commenced	Achieved: Contract awarded to consortium led by Palladium and implementation phase commenced with five countries
Outcome 2.1	# of Africa Volunteers Health Corps (AVoHC) / to Strengthening & Utilizing Response Groups in Emergencies (SURGE) Teams deployments to country specific or multi-country/regional outbreaks.	1) scoping missions in at least 30 countries 2) 20 countries completed training 3) At least 2000 African responders ready to be deployed in the first 24-48 hours of an emergency.	Achieved: 30 countries have completed scoping missions, 29 countries have completed the training and 3) 2321 responders are onboarded (52% female).
Outcome 2.2	# of Joint Emergency Action Plan (JEAP) activities funded and implemented.	1) JEAP proposal signed 2) DDA complete 3) Technical Assistance in place	Partially achieved: (1) JEAP WHO component agreement signed, and implementation commenced. Africa CDC agreement pending (2) finalisation of DDA in progress 3) Agreed Africa CDC Technical assistance in place and progressing on deliverables.
Outcome 2.3.	% improvement of regions reporting complete surveillance data supported through Institut Pasteur de Dakar (IPD).	IPD proposal and Agreement finalised, funds disbursed, and implementation commenced	Achieved
Outcome 3	Measured improvement in response pillars funded through ARRO as determined through evaluation.	ARRO request responded to, and funds disbursed in a timely manner and meets deliverables.	Achieved

Baseline data from Africa CDC outlined that over the past three years (2022-2024), there has been a 40% increase in identified outbreaks across Africa and in the first month of 2025 alone, outbreaks reached 40% (84) of 2024’s total. Several key requirements for achieving the outcomes and impact were put in place during the AR period in addition to the existing ARRO fund for outbreak response. These included agreements with Institut Pasteur de Dakar (IPD) and a revised agreement with WHO AFRO for JEAP. The TDDAP2 national component contract was signed on 12 September 2024, with country programmes launched in 4 of the 5 focus countries and delivery of country workplans commenced.
Community engagement in health security has been demonstrated in rapid response ARRO support e.g. through the International Federation of the Red Cross and Red Crescent (IFRC) mpox regional emergency appeal for risk communications and community engagement activities in east DRC and immediate neighbouring countries (Burundi, Uganda, Rwanda).
The rapidly shifting funding landscape for global health security will negatively impact on health security actions in the foreseeable future. At the regional level, whilst reporting of outbreaks may reflect improvements in coordination with continental bodies, the uncertain funding landscape is likely to stall continuing improvements and weaken the ability of African governments and their regional bodies and multilateral organisations to prevent development of these outbreaks into public health emergencies and timely containment. The national component is at an early implementation stage, with the attainment of outcomes and impact largely contingent on factors beyond the contractor’s control, such as political will and funding necessary to conduct Joint External Evaluations (JEEs) and revise National Action Plans for Health Security (NAPHS). Consequently, the TDDAP2 Programme team has commissioned a review of the impact of ODA reductions by bilateral donors on the health security infrastructure in Africa.
The previous annual review anticipated the log frame would be updated by 2025 which was not achieved due to delays in onboarding the MEL supplier, however this has now been finalised along with other component agreements. It remains important to review the outcome indicators with a broad set of stakeholders to ensure the log frame clearly demonstrates the link between output, outcome, and impact level indicators. Independent MEL input will further develop the indicator methodologies and clarify milestones for the future years of the programme.
A significant reduction of ODA funding and stable or declining domestic investment would require a programme review, reprioritisation and likely revision of output in addition to outcome indicators. The overall intended impact would likely remain, but the extent to which TDDAP2 would contribute to this would be reduced.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
This annual review provides consistent evidence that the programme should continue, based on its strategic value and progress towards set outcomes. It represents a crucial element to achieving FCDO’s stated ambitions in strengthening global health security for the benefit of populations in Africa as well as protecting the health of the UK population. In the context of a high risk of major outbreaks and threats to UK national interest, the programme is making satisfactory progress and remains highly strategic as a health security programme with a remit covering both national and regional objectives for Africa. The programme represents value for money in achievements to date, the interlinked ways of working across national and regional levels, and the costs avoided by reducing infectious disease outbreaks with associated impacts on human and economic development.
C: DETAILED OUTPUT SCORING

Output Title	Improved role of communities and civil society in the governance of and surveillance mechanisms for national health security.
Output number:		1	Output Score:	B
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Evidence of country progress with CSO engagement and participation in health security.	1) Contract with Palladium complete / 2) Country Leads assigned / 3) Official launch in 5 countries / 4) workplan drafted for each country	Moderately not met / Contract with Palladium agreed, country leads recruited, workplans drafted and launch events completed as scheduled aside from DRC which was delayed due to security concerns.
1.2 Evidence of country progress with strengthening community-based surveillance (C/EBS).	1) Contract with Palladium complete / 2) Country Leads assigned / 3) Official launch in 5 countries / 4) workplan drafted for each country	Moderately not met / Contract with Palladium agreed, country leads recruited, workplans drafted and launch events completed as scheduled aside from DRC which was delayed due to security concerns.

Briefly describe the output’s activities and provide supporting narrative for the score.
This output achieved most set milestones as planned during the AR period. The AR review assessed however it did not yet demonstrate the depth of community engagement needed against output indicators to assure the AR review team that it was satisfactorily on course to achieve output 1. As such, the output was assessed as moderately not meeting expectations.
Progress towards Output 1 is reflected in the successful procurement of a supplier and inception activities of the national component of TDDAP2 where most of the planned activities contributing to this output will sit. The contract for this programme of work was signed on 12 September 2024 between FCDO and the Palladium led consortium.
After evaluating a set of competitive bids, the contract was awarded to Palladium with their five consortium partners (below) due to a locally based approach balanced with global expertise. Palladium is a leader in the delivery of health security and technical assistance for health systems strengthening, which we will leverage to provide overall strategic and technical direction across the National Component. Palladium’s experts will be drawn upon particularly in the key strategic areas of pandemic prevention, preparedness and response (PPPR); governance and joint accountability; multisectoral data for health security; domestic resource mobilisation; end-to-end supply chain solutions; and community engagement in health security.
- Resolve to Save Lives (RTSL) is a consortium partner and global leader in epidemic preparedness and prevention. RTSL bring a network of experts who have shaped health security best practice in leadership, governance, financing, and accountability, including in Uganda, DRC, and Kenya.
- The African Field Epidemiology Network (AFENET) has a presence in over 40 countries and offers excellent reach to the National Component, with in-house capacity exceeding 700 field epidemiology practitioners. AFENET will lead on country progress towards implementing strategy and capacity building activity for workforce development for health security.
- Integrated Quality Laboratory Services (IQLS) strengthen and promote One Health laboratory capacities across Africa. IQLS will bring a network of experts skilled in the integration of One Health into laboratory capacity building for amplified health security outcomes.
- The Infectious Diseases Institute (IDI) global health team are set to accelerate the implementation of the International Health Regulations 2005 (IHR), laboratory strengthening, and disease surveillance. Delivering in Uganda, IDI will promote Ugandan best practice to the other four countries, including in disease surveillance.
- Halcyon is an Africa-based global health organisation which will provide technical assistance on the intersection of climate change and health security.
Inception period activities delivered by Palladium included a 5-day launch event (04 - 08 November 2024 in Nairobi, Kenya) with FCDO, consortia partners and regional stakeholders, and country launches in Ghana, Kenya, Malawi and Uganda. The DRC launch was postponed due to security concerns. Country launches successfully mobilised the necessary high level political buy-in for participation in mechanisms for national health security. There was limited evidence of involvement of communities or civil society in these inception activities and to date, evidence suggests that communities remain largely end recipients of assistance rather than actively shaping country plans.
Further to these events, during the inception period, Palladium has established country teams in each TDDAP2 focus country, set out initial log frames, key performance indicators, country engagement strategies and established country steering committees. Palladium has met all inception phase and first quarter deliverables including an inception exit strategy, risk register, Value for Money (VFM) framework, and sustainability plans.
The country workplans received have incorporated recommendations from TDDAP2 commissioned scoping reports. They provide some detail on planned community-focussed activities across five countries with delivery mechanisms including community-based surveillance and training activities in emergency response. Although partners have been identified and community-based surveillance included in workplans - there is limited evidence of meaningful engagement with CSOs across focus countries during the inception period. To avoid CSOs becoming programme recipients rather than active stakeholders in shaping the programme priorities –an ongoing focus is needed on authentic engagement with community leaders and organisations as co-production partners and not end-recipients of technical assistance.
Given the nature of global health security, TDDAP2 was designed to be adaptive to emerging infectious disease threats and response requirements. FCDO and Palladium agreed that TDDAP2 was well positioned to provide additional targeted support in affected countries - such as the mpox and Ebola response led by the Governments of DRC and Uganda. - while maintaining focus on the programme core scope of national systems strengthening. Although the need was rapidly identified, the implementation of this work has been slow to start and to date there has been no outputs from the mpox pivot through the national TDDAP2 components in DRC and Uganda due to the challenges of Palladium pivoting to this work whilst in inception phase.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

The national component that is largely responsible for delivering activities towards this output has met most milestones to date. However, changes in the global health security environment pose a risk to future delivery and may necessitate a revision of workplans. In Ghana, for instance, training district-level staff on risk communication and community engagement has historically depended on funding from other donors, which has now been largely withdrawn.
TDDAP2 has instructed a reworking of the national costed workplans in light of ODA reductions by bilateral donors that came to light after submission of the workplans and in line with the final TDDAP2 allocation for the national component for the next AR period.
Other key recommendations for the coming year included in the next section (Output 2).
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
All last year’s recommendations have been successfully completed:
• Tetra Tech was contracted in year 1 to review data system for TDDAP2. They completed reviews for all 5 countries to inform the revision of the log frame indicators. The findings and recommendations of the Data Systems Reviews undertaken by Tetra Tech, including recommendations for adapted log frame indicators have been considered by Palladium as well as our MEL supplier ITAD. The AR determined that a significant review of the TADDAP2 log frame was required to better demonstrate the causal relationship between outputs and outcomes and clarify the extent to which these are attributable to TDDAP2.
• Palladium have completed due diligence of potential civil society and community-based organisation partners and will be expected to engage them more directly in implementation phase

Recommendations for the year ahead:
Recommendations	Deadline
Revision of log frame and theory of change to reflect impact of ODA reductions on global health security architecture in Africa.	July 2025
Palladium to clearly demonstrate embedding of communities and civil society organisations in prioritisation of activities and sustainable actions at sub national level.	June 2025
Palladium to expedite and complete support of the mpox and Ebola response in DRC and Uganda including community engagement.	July 2025

Output Title	Stronger core public health functions and capacity in focus countries
Output number:			2	Output Score:		A
Impact weighting (%):			15%	Weighting revised since last AR?		No
Indicator(s)		Milestone(s) for this review			Progress
2.1 % of intended workforce trained		1) National component awarded. / 2) Country Leads assigned / 3) Official launch in 5 countries / 4) workplan drafted for each country			Met / • Contract with Palladium agreed, country leads recruited and launch events complete. / • Workforce training included as an element of the country workplans with some preparatory works ongoing including mapping of needs.
2.2 Completeness and timeliness of Integrated Disease Surveillance and Response (IDSR) in priority countries.		1) Contract with Palladium complete / 2) Country Leads assigned / 3) Official launch in 5 countries / 4) workplan drafted for each country			Met / Contract with Palladium agreed, country leads recruited and launch events complete. / • IDSR development is included as element of the country workplans across focus countries and identified as a priority area for delivery in implementation phase.
2.3 Progress towards establishing or operationalising National One Health Plans.		1) Contract with Palladium complete / 2) Country Leads assigned / 3) Official launch in 5 countries / 4) workplan drafted for each country			Met / Contract with Palladium agreed, country leads recruited and launch events complete, including recruitment of One Health thematic advisor. / • Launch events and inception activities have engaged relevant stakeholders including ministries at national and district level – including Veterinary, Agriculture and Human health. / • Progress varies according to country context, with support to Malawi progressing One Health Policy whereas in Ghana operationalisation of One Health policy is stalled pending agreement of all relevant departments.
2.4 Country progress on operationalising climate informed approaches to health security.		1) Complete contracting with climate and health security expert / 2) Complete contracting with climate consortium partner			Met / Contract with Palladium agreed, country leads recruited and launch events complete, including recruitment of Climate Change & Health Security thematic advisor. Halcyon have been successfully sub-contracted to provide technical assistance on the intersection of change and health security across the programme.
2.5 Progress towards ensuring core public health systems are accessible to all.		1) Assign GEDSI lead / 2) Complete a GEDSI approach plan			Met / Palladium have delivered a Gender Equality, Disability and Social Inclusion (GEDSI) Approach. GEDSI leads are listed personnel and in place for both the National Component and the MEL Component. / In addition, FCDO APEX MEL Advisor available for any additional GEDSI review.
2.6 # of sustainability measures achieved in priority countries against targets set.		1) Develop a sustainability plan			Met / A sustainability plan was completed by National Component partner Palladium. The sustainability plan sets out specifically how the programme supported interventions will be sustained beyond the programme life through, for example, identifying and working with and through their ‘institutional homes’.

Briefly describe the output’s activities and provide supporting narrative for the score.
The national component has remained on track, with evidence that it is well positioned to progress work on programme objectives and respond to the changing environment and country needs.
Progress is reflected in the successful procurement of a supplier and inception activities of the national component of TDDAP2 where most of the planned activities contributing to this output sit. Sub-contracting has been completed with thematic leads on One Health, Climate and GEDSI.
Consortia launch events included discussion on all core elements of public health functions in the focus countries, including IDSR development, status of JEE and NAPHS, One Health policy and coordination mechanisms. These have been incorporated into each country’s workplan including political economy analyses to contextualise the needs and opportunities of each context.
In the initial stages the programme has progressed FCDO strategic priorities including the leaving no-one behind agenda – ensuring development is inclusive of people with disabilities, across genders and vulnerable groups. Workplans including focus on these areas within the context of strengthening national and district health security are commendable and provide promising evidence of FCDO’s added value.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
Inception activities identified a need to revisit the log frame, theory of change and country workplans, particularly looking across the programme. Greater clarity on how programme activities need to meaningful and measurable change at output level for both output 1 and 2 is required. Palladium have appointed a MEL lead and allocated resource to work with ITAD on this area, which should also consider the impacts of ODA reductions on ability of countries to progress all elements of the programme.
Moving into implementation phase, synergies across the programme must become clearer including how ARRO and regional investments can be leveraged to maximise the impact of national components e.g. Africa CDC have engaged Palladium and others on how the JEAP could support the country level work and further requested direct engagement with the National Public Health Institutes (NPHIs). Getting regular data flows and linked indicators across the national and regional components is a priority to ensure national and regional level surveillance and indicators are complementary.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
The focus for the year ahead will be effective transition for the National Component partner Palladium from the inception phase to implementation. Palladium must ensure that they are joined up with all stakeholders at several levels, including at regional level and close working with FCDO advisors at post overseeing the overall FCDO health portfolio in countries.
The recommendations from the last AR remain as ongoing in nature but have been achieved in principle through the procurement of a supplier and delivery of the national component e.g. they are included in Palladium’s costed and detailed Y1 country workplans – as well as flagged and prioritised during individual country launches.
Recommendations for the year ahead:
Recommendations	Deadline
Palladium to review workplans with national stakeholders in focus countries in light of ODA reductions and prioritise work accordingly.	July 2025
Palladium to allocate thematic technical assistance to focus countries to enhance inclusion of Climate impacts, GEDSI and One Health policies in NAPHS targeted at each country’s stage of review and development.	September 2025
Palladium and ITAD to work collaboratively with FCDO and programme stakeholders to update log frame and theory of change.	July 2025

Output Title	Strategic partnerships to key African health institutions to strengthen capacity on emergency preparedness and response.
Output number:		3	Output Score:	A
Impact weighting (%):		40%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 # of AVoHC / SURGE Teams trained for deployment to country specific or multi-country/regional outbreaks.	1) At least 30 countries engaged through scoping missions / 2) 20 countries completed training / 3) At least 2000 African responders cumulatively ready to be deployed in the first 24-48 hours of an emergency.	Met / Reporting as of March 2025: / 1) 30 countries have completed scoping missions / 2) 29 countries have completed the training / 3) Cumulative total of 2321 responders are onboarded (52% female).
3.2 Timely reporting on JEAP secretariat's governance and management aspects of JEAP implementation.	1) JEAP proposal signed / 2) DDA for Africa CDC complete / 3) Technical Assistance in place	Moderately Not Met / 1) JEAP proposal approved in early 2025 and funding commitment signed with WHO. Current funding to the JEAP is through WHO/AFRO. / 2) Draft Africa CDC DDA submitted in March 2025. / 3) Technical assistance is in place and supporting Africa CDC’s broader capacity building and delivery of its public health mandate for local manufacturing of health products.
3.3 # of partnerships for regional disease surveillance established by Institut Pasteur Dakar (IPD)	1) IPD formal proposal received. / 2) IPD DDA concluded. / 3) Budget and log frame finalised. / 4) First Payment disbursed	Met / 1) Formal proposal finalised and submitted. TDDAP2 support is focused on advancing regional surveillance and outbreak response readiness. / 2) The DDA for IPD was concluded and approved. Findings have been translated into an action plan for IPD to address for timely monitoring of progress against recommendations. / 3) Budget for 2024/25 agreed, and up to £3m agreed for remainder of strategic partnership. Log frame developed in March 2025. / 4) The first TDDAP2 contribution disbursed in Q4 FY 2024/25 (£250,000).

Briefly describe the output’s activities and provide supporting narrative for the score.
AVoHC SURGE: Within the regional component WHO-AFRO has continued to be TDDAP2’s most substantial funding partner for the second year of programming. During the AR period, WHO AFRO trained 973 additional AVoHC-SURGE members who are now ready for deployment. Eight member states were supported to develop emergency preparedness country roadmaps. Work is progressing well on the workforce platform which is at an advanced stage and aims to enhance the management and deployment of trained public health emergency responders across the region
Joint Emergency Preparedness Action Plan (JEAP): FCDO’s early investment to the JEAP during the previous AR period to AVhOC-SURGE (see reporting above) and for the JEAP Secretariat was channelled through WHO. In December 2024, a refreshed JEAP proposal for secretariat and programme support was received, focused on scaling up technical working group initiatives across all pillars of the JEAP and resource mobilization. We signed a funding agreement with WHO AFRO in March 2025 for their component of the JEAP. Support to the Secretariat has been crucial to institutionalizing the JEAP by establishing its foundational functions, particularly in the programme management office which led to tangible results in the areas of resource mobilization, communication and Monitoring, Evaluation, Accountability, and Learning (MEAL). The JEAP produced its first ever annual report during the AR period and is now equipped with a MEAL plan, a Resource Mobilization Strategy and a comprehensive Communications Plan. Direct funding to Africa CDC is awaiting finalisation of the DDA process.
In addition, TDDAP2 is contributing to UK government investments in strengthening Africa CDC to deliver an expanding health mandate. During the AR period, this has included completion of a draft DDA (following some delays) in March 2025 to guide UK direct funding approach to Africa CDC and support broader mobilisation efforts. TDDAP2 also provided technical assistance (through DAI) to Africa CDC’s Platform for Harmonized Africa Health Products Manufacturing (PHAHM) with deliverables that included a situational analysis of the African therapeutics and diagnostics manufacturing ecosystem, supply landscape assessment and analyses that informed development of a draft strategy. The outputs will inform proceedings at an Africa CDC hosted High-Level Side event for African Health Ministers at the upcoming 78th World Health Assembly on market shaping strategies for sustainable health products manufacturing in Africa. Finally, a Senior Strategy and Policy Advisor, seconded by UKHSA and funded by TDDAP2 since January 2025, is providing expert advice to improve Africa CDC’s health policy and strategy and is guided by a cross UK government (DHSC, FCDO, UKHSA) board.
Institut Pasteur de Dakar (IPD) is a non-profit organisation set up in 1896 as Africa’s first microbiology laboratory. The Institute is a world class infectious disease research facility and undertakes public health services including vaccine production, surveillance, advanced education, and acts as an international reference laboratory. A new IPD-FCDO Partnership managed by FCDO’s Research and Evidence Directorate’s (RED) GHS Team will advance public health, life science and innovation at IPD. In 2024/25, TDDAP2 joined the IPD/FCDO partnership, advancing IPD’s public health department strategy, deploying operational rather than research funding. The core aims will be to advance regional surveillance and outbreak response readiness, the establishment of “One Health” observatories across Senegal’s diverse geographical regions, and a unit with enhanced health economics expertise for regional and national public health policy. We successfully transferred the budget to RED for TDDAP2 support to IPD in January 2025. All milestones for the strategic partnership with IPD in 2024/25 have been achieved.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
This output mostly progressed as planned during the AR period. No significant changes are planned because of this Annual Review, however key focal areas for the coming year are included in the final section.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
During the Africa GHS team’s WHO AFRO/AVoHC SURGE monitoring visit, it was understood that a key remaining challenge continued to be meeting the set timeframe for deploying volunteers during health emergencies. WHO AFRO confirmed that this would be a priority for in 2025 to work on the processes and agreements with Health Ministers to enable timely release of volunteers.
Recommendations for the year ahead:
Recommendation	Deadline
ITAD and programme partners review log frame and theory of change relating to regional component.	March 2026
Ensure TDDAP2 investments at the regional level (IPD, AVoHC, JEAP) are complementary including to other UK health investments	March 2026
Engage with the African Constituency Bureau for the Global Fund and Africa CDC to prioritise African leadership of the Lusaka Agenda including increasing domestic financing for health security in Africa	May 2026
Conduct site visit(s) of IPD regional surveillance sites to determine ongoing capacity and feasibility of scale-up.	April 2026

Output Title	Expertise, financial, logistical, and technical support for rapid containment and response to emerging outbreaks
Output number:		4	Output Score:		A+
Impact weighting (%):		30%	Weighting revised since last AR?		No
Indicator(s)		Milestone(s) for this review		Progress
4.1 % of formal requests to access ARRO fund assessed, submitted to – and decided by – SRO within 7 working days.		80% - 90%		Met / The ARRO intervention decisions and implementation were overall timely. During the MVD outbreak in Rwanda the formal request to access the ARRO fund was assessed, submitted, and decided by the Senior Responsible Owner (SRO) within 3 working days (inside the stipulated 7 working days). This swift decision-making was critical in ensuring the necessary resources and support were mobilised promptly to address the outbreak effectively.
4.2 % of approved ARRO fund assessments disbursed for outbreak response within 6 weeks.		1) 80% of interventions funded that are aligned with formal host government or regional GHS institution response plans. / 2) 80% of interventions meeting KPIs put forward by partners where applicable (e.g. for appeals).		Exceeded / 1) All ARRO funding released supported interventions aligned with response plans, either developed by individual countries (e.g. Rwanda’s Marburg response plan), regional public health institutions (e.g. the joint WHO AFRO/Africa CDC continental response plan for mpox) or emergency appeals in support of national needs (e.g. IFRC regional appeal for cholera in Southern Africa). / 2) With the exception of IFRC’s mpox response in east DRC, all interventions supported by ARRO for cholera, mpox and viral haemorrhagic fevers have met KPIs. The escalating conflict in eastern DRC resulted in IFRC suspending mpox response activities for a two-month period, which was communicated to FCDO very promptly.

Briefly describe the output’s activities and provide supporting narrative for the score.
Over 2024/25, ARRO funding has been allocated to numerous outbreak responses (including cholera, mpox and viral haemorrhagic fevers), as well as the development of updated protocols and guidelines. Two multi-country outbreaks have been significantly supported through ARRO funding (cholera in Southern Africa and mpox outbreaks in Central Africa), as well as both financial and technical engagement channelled to support VHF responses in three individual countries. Further details on these activities include:
Guidelines: The scale of mpox outbreaks in central Africa, including in new populations and with transmission dynamics not previously documented, represented an important opportunity to strengthen and standardise guidelines for national and regional response plans. The WHO Emergencies Programme, supported by ARRO, has initiated a systematic review of literature using the Grading of Recommendations, Assessments, Development and Evaluation (GRADE) methodology to strengthen consistency and rigour in evaluating mpox clinical care packages. Results will be used to finalise an evidence based optimized mpox supportive care protocol. In parallel, lessons from both the Rwanda and Tanzania Marburg outbreaks have also provided an opportunity to strengthen supportive care guidelines. These will have a lasting impact, supporting future care provided in new outbreaks.
Cholera: Investments into IFRC’s southern Africa regional emergency appeal over 2023/24 enabled implementation of community based oral rehydration points, decentralised referral to cholera treatment centres and, as outbreaks were controlled, pre-positioning stocks and rehabilitation of water and hygiene infrastructure in preparedness for the next season. In 2024/25, cholera support continued via FCDO’s humanitarian Standby Partnership mechanism and facilitated deployment to Comoros for an Operations Support and Logistics Officer to WHO to support the cluster, strengthening stock and supply chain management and capacity building for longer term capability on cholera preparedness, readiness and response.
Mpox: WHO declared a Public Health Emergency of International Concern in August 2024. Recognising the risk of regional expansion of the outbreaks, ARRO investments were aligned with the WHO AFRO/Africa CDC joint continental response plan, the first of its kind in support of national government response plans, demonstrating the unique role of ARRO in pan-African support to outbreaks. Several Standby Partnerships facilitated deployments to Burundi for the International Organisation for Migration’s (IMO) public health activities, focused on needs assessments for effective response, including at points of entry and for mobile populations, to prevent further spread. ARRO support was additionally focused on IFRC’s mpox regional emergency appeal for risk communications and community engagement activities in east DRC and immediate neighbouring countries (Burundi, Uganda, Rwanda). With the escalation of conflict and rapidly deteriorating humanitarian situation in eastern DRC since early 2025, several ARRO implementing partners suspended activities. Following a temporary pause on project implementation, IFRC re-evaluated epidemiological and geographic factors within the new conflict and mass displacement contexts to ensure appropriate allocation of resources against priority needs.
Viral Haemorrhagic Fevers: 2024/25 saw an increased number of Viral Haemorrhagic Fever (VHF) alerts and outbreaks reported on the continent, requiring technical support, coordination and funding to support responses.
In October 2024, the Government of Rwanda declared a Marburg outbreak, concentrated in Kigali and primarily in hospital settings. Over the course of the outbreak, the Africa Global Health Services Team was pivotal in the x-HMG response, including ensuring appropriate programming. Intervention decisions and implementation were notably timely, with the formal request to access the ARRO fund assessed, submitted to and decided by the Senior Responsible Officer (SRO) within 3 working days of the outbreak being declared. Swift decision-making was critical in ensuring necessary resources and support were mobilised to address the outbreak effectively. Funds were efficiently disbursed for the outbreak response within the required 6-week timeframe with the funds being received on 15 October 2024. By 07 November 2024 54% of the total funds had already been spent or committed, demonstrating the rapid financial response to the outbreak.
All ARRO funding disbursements were aligned with and in support of national, continental or emergency appeal response plans, reflecting synergy with the regional TDDAP2 component. The January 2025 mid-term report on the WHO AFRO/Africa CDC Continental Response plan for mpox outbreaks identified lessons relevant for areas where ARRO had prioritised investments including the value of a coordinated and harmonized response via a “One-Team, Plan, Budget, M&E framework”. Furthermore, tailored and contextualized Risk Communication and Community Engagement methods, including social/multi-media, were key for building trust to enhance contact tracing and uptake of vaccines. Finally, the development of standardized protocols, guidelines and standard operating procedures across African member states led to a more coordinated response.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
This output progressed as planned during the AR period of the programme. No significant changes are planned because of this Annual Review, however key focal areas for the coming year are included in the final section.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
A 2023/24 recommendation was to review the ARRO Fund “assessment to trigger support” criteria. This was progressed collaboratively by the Programme Responsible Owner and Global Health Security Adviser. Three key amendments were made:
- Step 1: addition of an initial assessment on whether sufficient programme management capacity is in place to properly programme manage and allocate funding for outbreak needs.
- Step 2: Addition of guidance at step 2 on critical factors that may limit accurate assessment of outbreak severity from the very early stages of an outbreak. Limiting factors include quality and timeliness of epidemiological data, official declaration of an outbreak, transparency on stage of investigation/response plans, competition between response partners, and quality of coordination mechanisms. Therefore, a reminder is now included that technical judgement is needed alongside “thresholds” for appropriately determining allocating ARRO funding.
- Step 3: Addition of a requirement to confirm that the objectives for funding requested are aligned to official national/regional response plans, thereby ensuring coherence of activities with coordinated outbreak needs.
Over 2024/25, the Africa GHS Team has demonstrated a critical role in FCDO support to outbreak preparedness, response and evaluation efforts. As the TDDAP2 programme matures, it will be important to explore join up between the ARRO component and the other elements of the programme, including activity alignment/overlap with the national and regional components, and seek support from the MEL component for updating the monitoring and evaluation metrics. As frequency of outbreaks increases, in part driven by climate change, environmental degradation and shifts in human/animal/environment interactions, One Health is becoming a more urgent priority to integrate into Global Health Security programming. A key recommendation for ARRO in 2025/26 is to explore formalising agreements and mechanisms to draw in essential One Health support in outbreak preparedness, response or evaluation. This is particularly important in the context of rationalised budgets and efficiencies of ODA approaches ahead of a reduction to UK ODA in 2027.
Recommendations for the year ahead:
Recommendation	Deadline
Drive efficiencies of ARRO investments with national and regional TDDAP2 components, to determine synergies and support ongoing health security strengthening in recipient countries and regional processes	September 2025
Ensure ARRO monitoring and evaluation metrics are well aligned in theory of change and log frame to overall programme outcomes and impact through ITAD-led review	July 2025
Collaborate with FCDO’s Health Emergencies Readiness Team to guideline development and sharing of lessons from each outbreak across partners to enhance ongoing development of continental health security capacity.	March 2026
Develop x-HMG mechanisms for rapid support on One Health aspects of outbreak preparedness, response or evaluation.	March 2026

Output Title	Robust information is generated and used by government, communities and partners for evidence-based decisions, programme adaptation and lesson learning.
Output number:			5	Output Score:		A
Impact weighting (%):			5%	Weighting revised since last AR?		No
Indicator(s)		Milestone(s) for this review			Progress
5.1 Number of effective, fair, and good quality assessments to verify results on an annual basis.		• MEL supplier contract signed, and inception phase commenced. / • Programme monitoring visit completed, BTOR and recommendations finalised.			Met / Commercial MEL contract with ITAD Limited signed in December 2024. Accelerated four-month inception phase expected to complete May 2025 with move to implementation June 2025. / • Monitoring visit by FCDO TDDAP2 Advisers in November 2024. Discussions during the visit and recommendations helped identify several areas for prioritisation in 2025.
5.2 100% of recommendations are on track every year of the programme where agreed and feasible.		• 80% of DDA, AR and MEL recommendations on track.			Met / 100% of recommendations from previous annual review and Due Diligence Assessment recommendations are being addressed and monitored through TDDAP’s delivery plan. / - Review of the ARRO “assessment to trigger support” criteria was completed and updated with key amendments (elaborated under output 4). / - A VFM framework and Gender Equality, Disability and Social Inclusion (GEDSI) Approach Plan have been completed by National Component partner Palladium. Data disaggregation agreed for indicators as follows: National level: Use of GEDSI impact indicators measuring the integration of the Washington Group of Questions. Community level: GEDSI impact indicators that measure stakeholder diversity i.e. disaggregated by gender, age, and other relevant vulnerability markers. / • MEL recommendations from last AR all completed: / - Findings and recommendations of the TDDAP2 country mapping (Triple Line) and Data Systems Review (Tetra Tech) reports incorporated into the technical criteria for MEL component procurement. / - Due Diligence Assessment of Africa CDC in process. Draft DDA report submitted to Programme team.

Briefly describe the output’s activities and provide supporting narrative for the score:
All milestones for this annual review have been met, with notable highlights outlined below.
The Monitoring Evaluation and Learning supplier was successfully contracted to a consortium led by ITAD in partnership with Tropical Health, the Infectious Diseases Institute (IDI), and Kinshasa School of Public Health (KSPH) commenced their four-month inception phase in February 2025.

ITAD’s key objectives for TDDAP2 to enhance performance and coordination, delivering desired outcomes and sustainability are:
- Systematic collection of data from all TDDAP2 components.
- Assessment of TDDAP2’s performance and overall impact against the Theory of Change.
- Analysis, synthesis, and presentation of information from monitoring and evaluations to improve programme results.
Monitoring visits have further enabled satisfactory achievement of milestones for this output. These included a visit from our Health Advisor and Health Policy Adviser (regional component) to WHO’s Health Emergencies Operations in Kenya to gain an overview of WHO AFRO’s role in supporting the country office on national health priorities and facilitating collaboration through the WHO Emergency Preparedness and Response (EPR). This visit observed operational elements including SURGE training and Emergency Operations Centre (EOC). Understanding and information was gained of capacity and readiness built using FCDO investment, including training and operations coordination for event management and effective implementation of the EPR programme.

ITAD completed a commission to gather insights on changes in GHS ODA funding late in the AR period and their repercussions. They analysed the impact of reduced ODA on TDDAP2's health security efforts in five focus countries and regional investments. Despite uncertainties about the full scale of funding cuts, there is already clear evidence that health security interventions across Africa, will be severely affected. ITAD also provided recommendations on adapting TDDAP2 to maximize impact under three budget scenarios, This work will support the TDDAP2 team in its decision making and enable it to prioritise its investments where they will have the greatest impact in this new context. The primary audience includes FCDO’s Africa Human Development Group and Global Health Directorate.
 Recommendations from existing DDAs with WHO AFRO and IDI are on track and being monitored on our delivery plan – with 2 out of the 4 safeguarding actions with WHO AFRO completed. IDI’s DDA is managed at post by the team in Kampala and recommendations from the WHO AFRO DDA are reviewed at least quarterly.
Describe any changes to this output during the past year, and any planned changes as a result of this review:
Output 5.2 wording was altered to read “100% of recommendations are on track every year of the programme where agreed and feasible.” This suggests that recommendations are meeting their set timelines, whereas “implemented” suggested that all recommendations must be complete by annual review time which, in some cases, might not be feasible/appropriate. Key focus areas for the coming year are included in the next section.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead:
All recommendations from the previous AR have been completed as listed in the results table.
The TDDAP2 team will continue to support ITAD in collaborating with other stakeholders across TDDAP2 components to ensure effective implementation and impact of the MEL Component. This is a critical component for efficient coordination of TDDAP2’s components and effective delivery of the programme’s desired outcomes and impact.

Recommendation	Deadline
Support ITAD to hold a successful face to face MEL workshop with stakeholders from across TDDAP2 in Nairobi.	June 2025
Complete a Due Diligence Assessment of Africa CDC, IRFC and UNICEF.	June 2025
Follow up on recommendations made in this Annual Review and Due Diligence Recommendations.	Ongoing

## D: VALUE FOR MONEY
Key cost drivers and performance
The programme budget for 2024/25 has been allocated across several key components:
Key cost drivers for the programme include contribution to pooled funding for outbreaks, fees including for short term TA/expert fees; asset costs including office space, vehicles and IT equipment; training and capacity development expenses, travel, and overheads.
- Support to WHO AFRO spent £5.3m. WHO AFRO has continued to strengthen health emergency preparedness and response, meeting all set deliverables and contributing to the programme’s overall success.
- TDDAP2 ARRO component spent £3.2m. This fund has supported multiple partners, including Standby Partners, CANADEM, UNICEF, IFRC/RED, and REDR, to enhance rapid response capacity across the region.
- National and Community Technical Assistance supplier, Palladium: spent £1m. Palladium completed the inception phase of the programme and has entered implementation, providing technical assistance at both national and community level in the five focus countries.
- Technical support to Africa CDC, spent £353k. This component was delivered through UKHSA, DAI, and KPMG, and has focused on strengthening institutional capacity and development of policy in support of Africa CDC’s remit.
- TDDAP2 MEL supplier, ITAD Ltd, spent £125k to date on inception phase activities.
During the AR period, VFM monitoring has been applied at several key stages, including:
- Assessing proposals for ARRO funding.
- Reviewing partner reports (to ensure objectives are met and funds spent effectively).
- Assessing progress against the log frame to include VfM indicators.
- Agreeing Accountable Grants and memoranda of understanding with key partners.
- Undertaking competitive processes to appoint partners in an open market for MEL and National components.
Assessment of whether the programme continues to represent value for money
TDDAP2 is in its second year as a programme, with some implementing partners recently contracted and a new agreement with Africa CDC still pending. Therefore, the programme has not yet been evaluated for Value for Money (VfM) at impact and outcome levels, although progress against some indicators has been noted.

The TDDAP 2 has delivered effectively against the majority of programme interventions for which programme resources were applied, demonstrably achieving good value for money for interventions for outbreak response. Through the ARRO component, TDDAP2 has been assessed as providing value for money in response to the Marburg Virus Disease (MVD) outbreak in Rwanda, based on rapid disbursement and outbreak containment efforts. The recent contracting of implementing partners for the national and MEL component means that we are as yet unable to record significant results from these investments.

A full value for money approach and framework will be developed with the support of the MEL supplier, ITAD in the next AR period to support continuous monitoring of TDDAP2’s value for money proposition as presented in the business case. Given the landscape of reducing ODA, the vfm framework will compare vfm across TDDAP2 components and consider sustainability of future funds and alternative financial models as appropriate.
The TDDAP2 programme is augmenting UK investments in health through support and coordination of FCDO and cross government response to outbreaks, research and protection of the UK public. As such, the programme is contributing to the UK health security objectives in addition to national interests.
Progress against the 5 E’s of FCDO’s value for money framework
Economy
Grant agreements and contracts were procured swiftly and at reasonable cost, drawing on the advice of commercial department colleagues to achieve cost savings where possible. The team leveraged established commercial framework agreements (GDD & GEMFA) and partnership that has full array of health suppliers. For the national and MEL components a competitive tender process was used to identify the optimum partners and FCDO commercial colleagues provided benchmarked and capped market leading fee rates for technical assistance.
The ARRO mechanism disbursed £500k to the British High Commission, Rwanda, for the Rwanda outbreak within six weeks of approval, with over 50% of funds spent or committed within three weeks. The use of experienced partners such as the UK Emergency Medical Team (UK-EMT), IFRC, and UNICEF ensured quality and reliability while reducing administrative overheads. The British Red Cross framework agreement and IFRC’s existing volunteer network provided cost-efficient mobilisation without requiring additional set-up expenditure.
Efficiency
All milestones under the national component were successfully delivered and on time. FCDO and Palladium have identified and finalised the key KPIs for the component and 50% of the fees are directly linked to the successful delivery of the KPIs. All ARRO funding decisions were made within the target 7 working days, and funds reached partners within the expected six-week window. In Rwanda, critical care support provided 1,370 nursing interventions, 92 bedside mentoring sessions, and support to 60 surgical cases. IPC teams trained 162 health professionals and developed 16 SOPs and national guidelines. EMS teams trained 338 staff and delivered tailored IPC resources. These results reflect a high output yield relative to cost, with the cost-per-beneficiary appearing efficient and good VfM given the breadth and depth of support delivered.
Having a diverse route to market for the programme that includes MoU Accountable Grants and contracts allows a faster, flexible approach to tackling outbreaks, making best use of a range of implementing partners and addressing critical needs in diverse pillars of outbreak response as appropriate. These included clinical care, infection control, pre-hospital services, psychosocial support, and risk communication and community engagement. TDDAP2 support to the Rwanda MVD outbreak included the UK-EMT and partners strengthening national capacity in Rwanda’s Central Hospital University Kigali (CHUK), while UNICEF and IFRC contributed to a coordinated response at community level that contributed to containment of the outbreak.
The continental mpox Action plan developed in partnership between WHO-AFRO and Africa CDC permits the efficient alignment of TDDAP2 response to need and appropriate targeting of our resource and expertise, increasing the coherence of the continental mpox response.
Effectiveness
During the AR period, interventions through ARRO have been closely aligned with outbreak needs and national priorities. In addition to direct TDDAP2 support to outbreaks including the Rwanda MVD outbreak, the Africa GHS team routinely facilitates coordination between FCDO departments and cross government, including UK-PHRST and DHSC, to enhance the impact of UK support to outbreak responses, and strong preparedness measures against imported cases. Consequently, TDDAP2 support to the Rwanda MVD outbreak contributed to the containment of the outbreak, which was confirmed by Rwanda and WHO on 20th December 2024.
Africa CDC’s continental mpox response dashboard provides real time monitoring of all aspects of the response including progress in containing the outbreak, disaggregated by country and region.
While it is too early to demonstrate impact of TDDAP2 support to strengthening health systems and multisectoral at country level, strong alignment of workplans to clear outputs and outcomes will support measurable and sustained improvements in countries’ ability to prevent and mount timely and effective response to outbreaks.
Equity
Gender, disability and social inclusion has been central to programming decisions owing to the impacts of outbreaks disproportionately affecting women, children and the most vulnerable. During the AR period, equity considerations were evident across inputs (e.g. localisation), outputs (e.g. inclusive training) and intended outcomes (e.g. strengthened capacity in remote or underserved areas), in line with the “Leave No One Behind” agenda.
ARRO targeted high-risk, under-supported countries such as Burundi, where bilateral programming was unavailable, and high risk of cross border transmission and instability from neighbouring DRC. The IFRC’s local networks ensured outreach to vulnerable communities and UNICEF’s focus on mental health and community engagement addressed social dimensions often overlooked in emergency responses.
At the regional level, supporting the Africa CDC/WHO JEAP that has a specific workstream to strengthen community engagement approaches for effective health emergencies prevention, detection, and response interventions.

Nationally, Palladium, the National Component partner, developed Gender Equality, Disability and Social Inclusion (GEDSI) plans and indicators to ensure that outputs in the five focus countries are categorized by gender, age, disability, and other vulnerability markers as appropriate.
For communities, through country workplans, work has commenced to ensure inclusive civil society and community participation in strengthening disease prevention and response mechanisms including for public health emergencies. This will include raising awareness of and countering harmful traditional practices that negatively impact women and girls, persons with disabilities, and other vulnerable groups, particularly during health emergencies.

Cost-Effectiveness
Although full outcome or impact data are not yet available, investments in institutional capacity (e.g. SOPs, national guidelines) and human capital (e.g. training at scale) are expected to yield sustained public health benefits, reducing future outbreak costs by containing outbreaks and reducing disease burden within and across countries. The breadth of impact across clinical and community-based components also points towards potential cost-effective gains in reduced morbidity and mortality, particularly in fragile settings.
Overall, the programme continues to represent good Value for Money and should be continued based on performance to date. It has delivered timely, targeted, and well-coordinated responses to disease outbreaks in line with both national needs and FCDO strategic objectives. The programme’s contribution to regional outbreak preparedness, plans for national capacity strengthening, and inclusive, localised delivery, particularly in communities, also complements broader FCDO priorities across health systems strengthening, resilience, and localisation.

Recommendation	Deadline
Review Value for Money framework and indicators with MEL support for implementation and finalise for the programme duration	Aug-2025

E: RISK
Overview of risk management

During this AR process we revised the overall risk rating to Major. The TDDAP2 risk landscape has shifted due to rapid changes in African health security and ODA reductions by bilateral donors. We now face four significant risks: Safeguarding, Public Service Delivery & Operations, and two Reputational risks, all outside our appetite even after mitigation measures. These have been escalated, while the remaining risks are within acceptable limits.
The table below shows the new risk rating:
Risk Category	Number of Risks per Category	Highest Net Risk Rating	TDDAP2 Risk Appetite per Category
1. Strategy & Context	5	Major	Receptive
2. Policy & Programme Delivery	8	Major	Receptive
3. Public Service Delivery & Operations	1	Major	Cautious
4. Safeguarding	1	Major	Cautious
5. Financial & Fiduciary	3	Moderate	Receptive
6. Reputational	2	Major	Cautious
7. People	1	Moderate	Cautious

Public Service Delivery and Operations
The risk is when ODA pressures threaten ability to deliver planned budget. This risk is outside of appetite and TDDAP2 will mitigate by adopting a flexible, adaptive approach in tailoring activities and funding as needed, in agreement with implementing partners.
Reputational
There are two reputational risks: 1. Suppliers in country do not align with FCDO key messaging, impacting programmes reputation and 2. TDDAP’s work to improve government accountability through Civil Society organisations and media organisations may damage partners’ and FCDO’s relationship with the government. The appetite for these risks were assessed as cautious but following recent re-evaluation of these risks during the AR process, they are now outside of appetite. We will continue to manage these risks by ensuring robust communications plan are in place, with careful communication and engagement with partners. We will continue to escalate specific choices that create reputational risks and will regularly review and monitor these risk appetites.
People Risk
Our people risk appetite remains cautious, reflecting a limited risk rating, however there are risks to the core team members on being too stretched or engaging in risky environments. FCDO and Implementation organisations’ duty of care policies are routinely reviewed and applied for deployments and monitored through due diligence assessments We have evaluated the risk associated with Africa GHS personnel as part of our annual review. During the AR period, the programme had several vacancies in the team. The TDDAP2 SRO was changed during this period and recruitment efforts are currently underway for the senior programme manager position. Additional support was periodically drawn from the broader FCDO network to support the TDDAP2 team.
Strategy and Context
The appetite level for Strategy and Context has been revised down from ‘eager’ to ‘receptive’, acknowledging that numerous elements are beyond our control. The associated risks include conflict and increasing instability in regions with fragile states at the centre of current outbreaks.
Safeguarding Risks

The net risk for programme beneficiaries being harmed by delivery partners or downstream partners in countries is ranked as major. The risk appetite for Safeguarding has been reviewed based on the recommendation of year 1 Annual review and has been raised from ‘minimal’ to ‘cautious’ with safeguarding controls and checks remaining in place.

Risks of SEAH are considered through enhanced Due Diligence Assessments for all new partners. Risks are regularly monitored with existing partners to mitigate and escalate as needed during regular project review meetings and public health emergencies. The risk register for partners is reviewed in preparation for each quarterly meeting. All supplier staff are expected to complete safeguarding training annually, enlisting support from the FCDO safeguarding hub as required.

Currently, two DDAs for IFRC and UNICEF are in progress. All current TDDAP2 partners have received the latest FCDO Fraud and Safeguarding letters and have acknowledged receipt. WHO AFRO specifically is progressing well on this risk category.
Climate and Environment Risks
Health emergencies spanning from climate shocks will increase demands on ARRO fund and the after-effects of climate shocks can restrict access and compromise health security systems in countries. TDDAP2 monitors and implements mitigating actions that include:
- Suppliers actively monitoring this risk in their risk registers and update FCDO regularly.
- Programme team is maintaining close communications with country posts to be kept abreast of the operating environment.
- The programme team reviewing and reprioritising resources to tackle the effects of emerging climate shocks as necessary.
Fiduciary Risks
Financial and fiduciary risk (such as fraud, aid diversion or mismanagement of funds) is rated as moderate. This risk could result in funds not reaching the intended destination and thus impact the success of the programme, creating poor VfM and heightening reputational risk. Mitigating actions by the TDDAP2 programme team include:
- Ensuring Due Diligence Assessments (or central assurance agreements) are in place for all partners, and by using a third party to manage funds if necessary (see above).
- Scrutinising technical and financial reports and annual audited financial statements and conducting regular financial and asset spot checks of the supplier, (organising field trips).
- Ensuring clear guidelines on fraud, bribery and corruption and reporting requirements are stated in agreements.
WHO AFRO has appointed a dedicated Emergency Preparedness and Response cluster officer to lead on Risk management and mitigation strategies. The officer will join our regular programme management meeting in preparation for the quarterly meeting. WHO AFRO DDA action plan is reviewed on a regular basis and good progress has been made is completing recommendations. As an example, in terms of capacity to deliver, WHO AFRO has achieved more than 50% of their target for international expertise to support country offices.
The 2023 and 2024 WHO AFRO comprehensive risk assessment was completed for all 47 WCOs in the Africa Region. The risk assessment exercise was completed on 31 December 2024. 85% Audit reports closed as of March 2024.
There are significant challenges in DRC faced by the British Red Cross and French Red Cross due to the instability in the region and planned activities have been suspended. To mitigate this risk to delivery, IFRC was granted a no cost extension to their contract during the AR period.
Managing risks
The TDDAP2 programme team will continue to review risk on a fortnightly basis amongst programme managers, and every 6 weeks with the wider team. Risk is discussed with each partner during the quarterly meetings. Any risk which is above the programme’s risk appetite is escalated and reviewed. We review our risk registers with our partners every quarter and discuss risk management with partners as part of our standard reporting. We encourage partners to escalate risks outside of appetite when they arise.
Two disbursements were made to IFRC using FCDO’s guidelines for disbursements in a humanitarian context which removed the need for a DDA prior to the first payment. The risk of disbursing the second prior to completion of a new DDA was evaluated and determined to be low and exceptionally a second payment was made to meet pressing need. IFRC was assessed to be a longstanding and credible humanitarian partner of FCDO, operating through 14 country clusters, many of which implement routine and emergency programmes supported by FCDO. A DDA has now been completed and is under review for finalisation in June 2025.
This section has been completed using information from our programme risk register, delivery plan, meetings readouts, partner reports and discussions with FCDO Health Advisers.

Recommendations	Deadline
Review the programme’s risk register, updating mitigations, re-assess likelihood and impact ratings and ensure all risks are current and are being appropriately managed.	Aug-25
Review risk ratings based on ODA cuts by bilateral donors including to regional partners (WHO AFRO)	Jun-25
Work with IFRC/BRC to update understanding of security risks in DRC and flexibly provide no cost extensions as needed to manage delivery of work	Jun-25
Establish quarterly review meetings with FCDO Health Advisers at Post	Sept-25

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
Summarise the performance of partners and FCDO, notably on commercial and financial issues.
WHO-AFRO has continued to be TDDAP2’s most significant partner for the second year of programming, as the recipient of the majority of TDDAP2 funds during the Annual Review period and with a multi-year agreement in place. During this AR period, FCDO approved an increase in contribution totalling £3.9m. This represented an additional £1.1m towards outbreaks Emergency Response for use in the WHO AFRO Region and an additional £2.8m towards the WHO AFRO and the Africa Centres for Disease Control and Prevention Joint Action Plan for Strengthening Public Health Emergency Readiness and Response in Africa (JEAP). This was approved by WHO AFRO and FCDO under MoU Amendment No.4 on 06 March 2025 and disbursed in the same month.
WHO AFRO submits reports ahead of the quarterly meetings that cover technical, financial and programme managements sections. Key messages on risks and finances are covered at the high-level quarterly meetings to ensure that all staff are aware of important messages on finance and compliance. We hold ad-hoc programme management meetings on a regular basis before the quarterly meeting.
The overall spend rate for all WHO AFRO components is good at 80%. For mpox and Marburg outbreaks specifically, the implementation rate is over 93%. During our quarterly call on 1 April 2025, WHO AFRO demonstrated clear allocations of the FCDO investment in JEAP.
WHO AFRO Business Management System (BMS) has been rolled out to all WHO staff. To maintain agile workforce in anti-fraud and anti-corruption efforts, a certification programme for WHO staff to become certified fraud examiners (CFE) has been launched.
Institute Pasteur Dakar: All four milestones for the strategic partnership with IPD in 2024/25 have been achieved. TDDAP2 support is focused on advancing regional surveillance and outbreak response readiness in Senegal and West Africa through sentinel and syndromic surveillance, One Health observatories and expanded epidemic intelligence capacity. We successfully disbursed £250k to our partner Institute Pasteur Dakar through Research and Evidence Directorate’s Global Health Security programme in January 2025. The TDDAP2 programme team will work with RED in overseeing finances and progress against due diligence recommendations.
Africa CDC: For this period, we have indirectly supported Africa CDC at the regional level through two contractual arrangements.
• An MoU was signed with UKHSA for the secondment of a UKHSA senior strategy and policy advisor to the office of the Director General, Africa CDC, through a competitive recruitment process.
• We successfully implemented our contract with DAI on progressing Africa CDC’s work stream on strengthening the pharmaceutical industry in Africa, with Deliverables 1 2 & 4 completed. After a short delay, the full contract is expected to conclude by mid-May and will support Africa CDC’s participation in the World Health Assembly in May 2025.
• The DDA implemented by KPMG was finalised and report submitted to FCDO in March 2025. We are accruing the payment for KPMG to the next financial year.
Summary of financial spend for year 2024/25:
Project Number	Project Description/ Name	Budget Allocation	% Spend/Disbursed 2024/25
300585-401	300585-401 Fund for Rapid Response to outbreaks in Sub Sahara Africa - Multiple partners include: Standby Partners, CANADEM, UNICEF, IFRC/RED, REDR…	3,191,912.28	100%
300585-402	300585-402 National and Community Technical Assistance Components - Palladium	1,000,000.00	100%
300585-403	300585-403 Support to World Health Organisation Africa Regional Office (WHO AFRO)	5,254,314.48	100%
300585-404	TDDAP2 Monitoring, Evaluation and Learning Component – ITAD ltd	125,000.00	Reported in the APEX Accruals register
300585-405	Support to the implementation of the Africa CDC to strengthen health emergency preparedness and response in the Africa Region. In direct support from UKHSA, DAI and KPMG.	352,696.63	80% two transactions need processing
300585-407	TDDAP2 travel and admin expenditure	16,908.58	47% awaiting expenses claim due to duty travel arranged late in financial year 2024/25.

Palladium was awarded the TDDAP2 National component contract in September 2024 and successfully mobilised and completed Milestones 1-15 Deliverables (inception). The partner is on track to complete the remaining deliverables for FY24/25.
ITAD was awarded the contract for our Monitoring and Evaluation component and mobilised successfully, with inception phase commencing in February 2025.
Financial Performance
The financial performance of existing partners has been good in this second AR period. Notably, WHO-AFRO and BRCS/IFRC (through ARRO) have been adept at programming additional funds at short notice to respond to need and contribute to the programme’s objectives.
The ARRO component has effectively disbursed funds to Marburg and mpox responses, with payments processed within agreed timelines. The ongoing mpox emergency necessitated further funding for the IFRC appeal with an uplift payment of £1m made to IFRC in February 2025. We have also successfully agreed a contribution agreement with UNICEF for Emergency Mpox Response and Resilience Strengthening in Burundi for £800k during this AR period.
Commercial:
The National and MEL components were sourced competitively via FCDO’s GDD and GEMFA framework. The programme team worked with commercial to develop a sourcing strategy that was favourable to the market with multiple competitive bids submitted. These opportunities were published externally for early market engagements and procurement opened to the 13 suppliers on Health and Climate lot 2 on GDD Framework. These bids were evaluated and moderated with the awards based on scores achieved against the technical and financial criteria outlined.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

During this review period we have conducted several field visits to monitor progress as follows:

1. Nairobi – September 2024 Regional Component – monitoring of WHO SURGE initiative. Gained overview of WHO AFRO’s role in supporting the country office on national health priorities. Understanding of deployment experience for AvHOC responders and challenges with timely release by employers to meet 24-48 hours WHO target for response. Improved understanding of the EOC’s operational elements, capacity and readiness, including training and operations coordination for event management and appreciation of challenges.
2. Nairobi – September 2024 National Component/Inception phase launch. Discussions highlighted the importance of early consideration of cross-sectional elements of the One Health, climate and GEDSI programme components. Underlined the importance of strong coordination between regional and national level component stakeholders (i.e. Africa CDC, WHO, and Palladium) to ensure outcomes are maximised. This includes sharing indicators across both levels drawn from the JEAP.
3. Technical and coordination support to Posts and across UK government for effective and coordinated outbreak responses in Rwanda (November 2024, MVD), DRC (July 2024, mpox) and Burundi (February 2025, mpox).
4. Senegal – February 2025: Regional Component/IPD strategic partnership visit with RED on surveillance and public health intelligence
5. Egypt – February 2025: Africa CDC/GAVI 2nd Vaccine and other Health Products Manufacturing Forum for Africa Union Member States
6. Ethiopia – March 2025: Regional Component/Africa CDC Partnership monitoring visit with UKHSA
7. Ghana – March 2025: National Component/Annual Review visit to meet newly appointed Palladium country and regional team leader and MEL specialist. Critical inputs were provided on country workplans, engagement with country stakeholders and discussions on need for adaptability in light of reduced ODA.

This Annual Review was drafted by an independent public health registrar based in another FCDO team together with the immediate programme team and has undergone a series of quality assurance checks before publication. The review was completed through desk research, interviews with staff and partners and a site visit to Ghana in March 2025.

We have sought advice and input from the Operational Excellence team (which includes Risk, Finance, VfM and Evaluation Advisors) before undergoing review by the Human Development Team Leader and the Head of APEX.

Evidence

The TDDAP independent MEL supplier was mobilised in February this year using ToRs rated by FCDO’s EQUALS as “Excellent’. This component has 3 broad objectives:
- Monitoring and results verification to ensure ongoing, systematic, quality collection of data from all TDDAP2 components.
- Endline Evaluation to assess TDDAP2’s performance and overall impacts against the ToC.
- Evidence Dissemination and Learning to analyse, synthesise and present information generated from monitoring and evaluations (and from any other evidence generating activities undertaken by delivery partners) and use it to continuously improve the programme’s ability to achieve results.

Learning

TDDAP2 learning has taken various forms and has been ongoing during this review period:
- Integrating the health security reports from the 5 focus countries commissioned into our procurement process for the National Component supplier Palladium and our MEL Supplier ITAD.
- Integrating lessons learnt outbreak response and field visits into WHO-AFRO quarterly meetings and the wider WHO-AFRO Regional Dialogue meeting. Key action points are recorded and acted upon.
- Due Diligence Assessments of WHO-AFRO and IPD highlighted several areas to address and actions on these are ongoing and monitored.
- Learning through action, for example reviewing the ARRO decision tree process on an ongoing basis; and holding a hybrid launch event for the National Component in Nairobi including Palladium, their consortium partners, FCDO staff (both centre and post) and regional stakeholders.
- During outbreaks in Africa this year (including Marburg and Ebola) the TDDAP2 Team have coordinated the FCDO/HMG response alongside providing support to Posts. Work has included horizon scanning, reviewing data and outbreak trajectory, providing advice, coordination within and beyond FCDO, preparing briefings, engaging regional networks and partners, and identifying funding sources from other CMPs.
- Sharing progress and challenges with APEX’s programme Management network to facilitate learning and development.

The programme team will ensure real-time learning throughout programme implementation to have an adaptive approach through regular reporting meetings with implementing partners, field visits to see work first hand and, where relevant, speaking to partner staff and programme beneficiaries and engaging in continental health sector review events.

One of two recommendations last year was to review the log frame based on various recommendations within that AR and include more tangible milestone indicators. We will be updating the log-frame along these lines with the help of our independent MEL supplier ITAD in June 2025.

Our second recommendation was to consider including the country HSI6 score as a Key Performance Indicator, to track improvements in country health security. Our National Component Partner Palladium will carry forward this recommendation in discussion with the Africa GHS Team and MEL supplier.

Recommendations	Deadline
ITAD to hold an in-person MEL workshop with all TDDAP2 stakeholders to refine the ToC and log-frame across the programme	June 2025
Programme team to conduct site visits to national and regional partners, including support from across Health Cadre to provide independent assessment	March 2026