## Annual Review – Demographic Transition

Title: Mozambique Demographic Transition – Waala Programme
Programme Value £ (full life): £ 34.32m		Review date: 26 July 2025
Programme Code: 300586	AMP start date: 26/07/2021	AMP end date: 31/03/2027

Summary of Programme Performance
Year	2021	2022	2023	2024
Overall Output Score	A	B	A	A
Risk Rating

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/90000021.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0006396.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

The Programme is designed to support the Government of Mozambique, along with other key stakeholders, in managing and accelerating progress towards a sustainable rate of demographic transition. It aims to do that by strengthening service delivery systems and creating an enabling environment for evidence-based policymaking, strategic planning, and effective programming.
A central focus of the Programme is on improving the quality and accessibility of essential services — so as not to leave women and girls behind. This is being achieved by leveraging multilateral funding across the health, education, and social sectors, supporting initiatives that invest in and increase demand for comprehensive family planning and reproductive health services, and promoting the adoption of cost-effective service delivery models at the local level. The Programme also stimulates the generation, analysis, and use of high-quality official data to inform planning processes, monitor progress towards national development goals, and enhance the accountability of decision-makers. By capitalising on the UK’s convening power and strong partnerships, the Programme seeks to influence policy change, identify sustainable health financing solutions, and address barriers that hinder the advancement of demographic transition objectives.
In 2024, the programme encountered two challenges: the political crisis surrounding Mozambican national elections and a significant reduction in U.S. funding for the health and social sectors. These disrupted implementing partners’ activities, diverting their attention to ensuring the security of staff and working with partners to mitigate the impact of the abrupt cuts affecting Sexual Reproductive Health and Rights (SRHR) interventions. On the other hand, the current debates on funding increased the UK’s strategic influence in the sector in advancing donor alignment, encouraging prioritization, and supporting the decentralization of service delivery. This aligns with the new Mozambican government feeling pressure to enhance public service impact and optimize partner funding.

Summary supporting narrative for the overall score in this review.
The programme received an overall “A” score, maintaining the performance level from the previous year.
The programme has made progress in meeting targets for quality assurance in health facilities, with scorecards proving effective in driving improvements. Further, training 9,500 community health workers positions the government well towards its 2027 targets. On the data front, the programme produced high-quality demographic analyses that informed national and provincial strategies. Over 160 officials were trained on using population data for planning and policy, reflecting increased interest in data to action.
The programme ensured that 98 health facilities are now using a functional logistics system. Commodity accuracy reached 88% in spot-checked facilities, and stockouts dropped from 63% to 20% in Nampula and 73% to 25% in Zambezia. Self-injectable contraception was scaled across all districts in Nampula. Support to the education sector enabled the identification of three high-impact pilot initiatives focused on improving basic learning in early grades, and a gender analysis informed the Global Partnership on Education application. The women economic empowerment component identified options for integrating women economic empowerment in the child grant scheme. On policy and influencing, high-level advocacy engagements advanced the importance of demographic priorities and positioned Mozambique as a flagship country under the Lusaka Agenda.
In parallel, the programme commissioned three assessments to strengthen delivery: a SEAH assessment related to family planning services, a review of the youth and adolescent service model’s acceptability and effectiveness, and a political economy analysis of data use.

Major lessons and recommendations for the year ahead
No.	Lessons for 2025
1	The agreement requiring a domestic contribution by the Government of Mozambique (GoM) toward UNFPA contraceptive procurement, lacks a traceable mechanism to ensure funds are used for contraception and no other products, raising concerns about accountability and commitment. Moreover, the targets set at 5% by 2025 are too modest to drive impact on health financing, despite being relevant for fostering national ownership. There is potential to accelerate domestic resource mobilisation including through World Bank payments by results and UN matching mechanisms.
2	US funding reduction and the wider global decline in Official Development Assistance (ODA) has had a negative impact on the coverage and quality of health services in Mozambique. The abrupt funding cut raises questions on the long-term feasibility of aid-based delivery. It also presents an opportunity for the government and partners to take practical steps towards greater resource optimization and prioritization.
3	Integrating new concepts into existing government programmes - such as Women’s Economic Empowerment (WEE) into cash transfers – requires time invested in building trust and securing strong support from both government and partners. Thus, programming flexibility and adaptability are crucial for successful implementation.
4	The approach taken to engage districts in the design and mobilization of the new World Bank programme was insufficient to ensure ownership and empowerment. As a result, there is currently no clear evidence that districts are leveraging the programme to access funding to address their specific local challenges.
5	Generating high-quality demographic data per se is not sufficient to inform policies. To this end, sustaining government capacity and overcoming barriers to political commitment are essential. A Political Economy Analysis (PEA) on data use revealed that weak statistical literacy, low capacity at subnational levels, low buy-in from key ministries, and fragmented cross-sector coordination hinder efforts to embed demographics in planning, despite the great progress in embedding demographics into key strategic documents.

No.	Recommendations	Lead	Deadline
1	Adapt the programme to the 0.3% ODA context by planning a responsible exit strategy through the development of options for scaling up during 2025 and transitioning key initiatives that can be delivered through domestic systems or other donor support in the outer years.	DT team	December 2025
2	Use women economic empowerment (WEE) intervention to convene stakeholders and co-develop an approach to strengthen social protection financing and programming.	FCDO/ / FSDMoc	December 2025
3	Ensure that resource optimization and prioritization underpin the continued collaboration with the health sector by identifying options, discussing them with health partners and translating them into mutual commitments.	DT team/ / Health Partners Group	August 2025
4	Use education troika leadership to influence and closely monitor education sector’s use. of global financing mechanisms.	DT team/ UNICEF	December 2025
5	Based on the results of the SEAH study engage with key government and networks for policy discussions on areas of implementation.	BHC	March 2025
6	Enforce partners’ adherence to UK branding compliance and link it to disbursements	UNFPA	December 2025
7	Agree mitigation actions as a result of the climate and environmental risk assessment with all partners	BHC/UNFPA/ World Bank	March 2026

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The programme’s theory of change remains valid, with no major revisions to the impact indicators, which continue to focus on an increased Human Development Index and a reduced child dependency ratio by curbing early and unwanted pregnancies — particularly among adolescents — and decreasing child marriage. The core assumption for this theory is that this is underpinned and sustained by providing girls with realistic alternatives, primarily through access to quality education in turn unlocking income-generating opportunities and self-efficacy.
Outcome Indicator 1 was revised to reflect the World Bank’s programme’s shift in focus from national (“percentage of the state budget spent on health” ) to district-level (“percentage of target districts receiving direct grants from the programme.”), and better aligning with the programme’s focus on supporting local health expenditure and planned execution.
Outcome indicator 2 was revised to include provincial-level measures, as national Contraception Prevalence Rate (CPR) data were insufficient to track the programme’s progress. These additional indicators better reflect changes in the eight target districts; help interpret national trends; and better assess progress attributable to UK’s direct contribution and implementation challenges.
Outcome indicator 3 was revised to better track the number of costed national and provincial social sector strategies that integrate population dynamics, aligning with ongoing data-driven policy discussions and budget prioritization. This change strengthens the link between evidence use and programme impact across youth, health, education, and social action sectors.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
At the impact level, Mozambique’s child dependency ratio (Indicator 1) was initially estimated at 83% in 2020, but revised data, informed by improved vital registration systems and recent surveys supported by this Programme, now places it at 88.9% for that year. Since then, the ratio has shown a gradual decline, reaching 84.3% in 2024. This means there are approximately 84 children aged 0–14 for every 100 working-age persons aged 15–64. This retrospective adjustment underscores the need to reset milestones in line with more accurate data and highlights the continued importance of investing in education, health, and economic opportunities for young people—particularly in the northern provinces, where the youth burden remains highest.
[note] Age Dependency Ratio by Country 2025 - World Population Review; World Development Indicators | DataBank - The World Bank Group
Mozambique’s Human Development Index (Impact Indicator 2) reached 0.493 in 2023, placing the country 182nd out of 193, reflecting ongoing challenges in life expectancy, education, and income, despite a modest improvement from 0.477 in 2022. While 2024 estimates are not yet available, the upward trend suggests the country has already surpassed the 0.468 target set for end of 2024 and is potentially on track to approach the programme’s final milestone of 0.51.
[note] hdr2025reporten.pdf - Human Development Report, 2025
Considering the above, the programme is moderately on track. In the year ahead, efforts will focus on strengthening decision-makers’ understanding of these trends and encouraging them to prioritize targeted actions— particularly in education, health, and youth employment—to address the drivers of high dependency and low human development.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio.
The Programme was designed to support the strengthening of service delivery systems and enable evidence-based policymaking, strategic planning, and effective programming. The programme has a central focus on improving the quality and accessibility of essential services - particularly for women and girls. Based on the analysis of outcome and output achievements, the programme remains broadly on track to reach its intended outcomes, particularly in terms of numbers of beneficiaries reached, capacity building, integration of interventions and value for money. The UK’s convening power plays a pivotal role in promoting policy dialogue, advancing donor coordination, and encouraging the prioritisation of demographic transition objectives. It is also contributing to the ongoing quest to establish sustainable health financing mechanisms. The Theory of Change remains relevant and well-aligned with programme objectives, offering a solid framework for tracking progress – more so in the context of current financing constraints. The Demography programme aligns well with broader FCDO priorities – particularly in reference to growth and jobs and a modernised development approach - and contributes meaningfully to the overall portfolio. It supports the business plan objectives and strategic goals, particularly in service delivery and the wider inclusive development goal thus justifying its continuation.

## C. DETAILED OUTPUT SCORING

Output Title	District and community health services strengthened for the benefit of mother and child
Output number:		1	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	Yes- from 0% to 15%
[note] This output relates to the World Bank Health Systems Strengthening Programme, which transitioned from Phase 1 (closed last period, hence 0% weighting) to early implementation of Phase 2 during this period (15% weighting).

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of DHs and Health Centres Type I with quality assurance teams in place and implementing at least one scorecard-based performance assessment per year.	District Hospitals (DH): 44 / Health Centres (HC): 37	MODERATELY EXCEEDED: 45 DH and 56 HC have quality assurance teams. All heath facilities implemented one scorecard- based performance assessment in 2024
1.2 APS trained, assigned to a community village.	9,500 CHW	MET: 9,507 CHW were trained and deployed to communities
[note] APS stands for Agentes Polivalentes the Saúde – community health workers

Briefly describe the output’s activities and provide supporting narrative for the score.
The programme moderately exceeded expectations on Output Indicator 1.1. As demonstrated in the previous World Bank-funded programme, scorecards have proven to be an effective tool for monitoring and driving improvements. This output’s activities comprised establishing quality assurance teams in 81facilities, having them conduct quality assessments to inform targeted action plans. Although this output is on track, some areas need further attention. These include fully understanding the scorecards’ findings and assessing whether the resulting action plans have sufficient quality and ambition to address underperformance. Additionally, many health facilities reported poor and unreliable internet connectivity. This has led to errors and incomplete submissions - undermining the purpose of investing in electronic data management. Although one of the World Bank’s Disbursement-Linked Indicator (DLI) relates to internet connectivity in health facilities, and this target has been reported as achieved, the validity of this result remains questionable.
[note] The achievements under Outputs 1.1 and 1.2 are linked to the Ministry of Health’s District and Community Health Services Revitalization Programme, supported through World Bank-managed pooled funding. This funding includes contributions from a multi-donor trust fund that incorporates UK’s and two other donors’ funds. As such, the results achieved are a collective outcome of the broader World Bank programme and not attributable solely to UK support.
[note] Team composition varies from 5 to 8 elements with a diversity of training backgrounds and responsibilities, from doctors, nurses, technicians (laboratory, pharmacy, statisticians), administrative staff, nutritionists, psychologists.
Output indicator 1.2 met the target of deploying 9,500 trained community health workers (CHWs). Training covered nutrition, contraception, and prevention of common infections such as malaria, diarrhoeal diseases and respiratory infections, identification and referral of severe cases, and data capturing using a mobile app.
The government and partners agreed on combining requalification of existing CHWs and training new ones to reach the target of 14,000 active CHWs by 2027. However, several challenges - primarily administrative and financial inefficiencies - continue to threaten success of the rollout of CHWs. These include: a lack of guidelines for the use of the mobile health application, delays and inconsistencies in CHW subsidy payments, and shortages of essential materials for training and deployment including a starter kit of medicines and supplies.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
Over the past year, this output has evolved to reflect the transition into the new operation, the District and Community Health Services Revitalisation Programme (DCHSR). Specifically, indicator 1.1 was refocused to capture the local capacity to assess quality of services. Indicator 1.2 was revised from its focus on “coverage of institutional births” to “training and integration of CHWs”. The definition of these indicators will remain unchanged with incremental targets towards the end of the programme.

Progress on recommendations from the previous AR lessons learned this year and recommendations for the year ahead.

Progress on recommendations from the previous AR
Recommendation	Progress
Request the World Bank to share the final implementation completion report (ICR) and use VfM lessons to inform the new programme.	Met: World Bank shared the ICR, to which the programme team members contributed with insights during its elaboration. The key VfM lesson was that pooled funding boosts efficiency, cost-effectiveness and alignment toward shared goals. However, there are challenges such as slower decision-making, reduced donor visibility, and complex governance structures, which are risks that can be treated. This led to the decision to join the new programme through a MDTF, which is gaining traction evidenced by increased number of donors onboard.
Ensure close monitoring of programme’s progress. Make changes in logframe to reflect new indicators.	Met: DT programme team actively monitored the transition from phase out of previous programme into mobilization of new programme, allowing for mutual feedback and adaptation across both programmes. Evidence of this is the revision of output indicators and DLIs to accommodate lessons from the previous programme.

Key lessons learnt this year.

1. Disbursement delays in the first operation were linked to late commitment and ODA cuts.
2. Early engagement in the new operation via the MDTF helped safeguard UK’s reputation.
3. UK’s proactive role positioned it to lead the approach to address family planning funding gaps.

Learning aims/ recommendations for the coming year.

1. Shift focus from quantifying volume of activities to quality of outputs – World Bank/ co-financiers.
2. Improve the verification process to encourage evidence-based reporting that reflects how outputs translate into meaningful change on the ground – World Bank/ MISAU.

Output Title	Strengthened production and use of quality demographic data and intelligence in planning and implementation
Output number:		2	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	Yes, down from 35% to 20%
[note] Reactivation of the WB component and effective mobilization of the women economic empowerment component implied a new redistribution of the weightings across the 5 components

Indicator(s)	Milestone(s) for this review	Progress
2.1 Preliminary and final data products produced (2022 Demography Health Survey (DHS), Household survey (IOF) and policy briefs)	3 in-depth studies based on DHS and IOF data modelling finalized	EXCEEDED: Three in-depth studies completed using DHS and IOF data. These data sets also informed key national policy frameworks (ENDE, PES, PESS) and supported the production of provincial briefs to guide decentralized planning and budgeting
2.2 Government engagement and commitment to having a policy on demography, with emphasis on the benefits of integrating population dynamics in decision-making and action	175 national and subnational government officials and parliamentarians trained on using DD briefs and analysing DD data	MODERATELY NOT MET: 167 national and provincial level officials were trained on DD modelling, planning, and data use.

Output indicator 2.1 met expected targets, as the final Demographic and Health Survey (DHS) and Household Budget Survey (IOF) datasets produced the expected analytical outputs, namely: (i) A demographic dividend profile based on the National Transfer Accounts (NTA) methodology; (ii) A contraceptive dynamics analysis examining unmet need, use, discontinuation, and method switching; (iii) A fertility analysis by birth order, teenage pregnancies, and determinants, with provincial-level estimates. Additionally, the produced data informed the development of key government strategies, including the National Development Strategy (ENDE 2025–2044), the Annual Economic and Social Plan (PES), and the Health Sector Strategic Plan (PESS 2025 - 2034), and the draft Demographic Dividend Action Plan, aligned with youth strategy. The above data also formed the basis of provincial level reports in Nampula and Cabo Delgado, to be used to support subnational planning and budgeting.
While the indicator is on track, the extent of practical use of data remains unclear. There is no systematic way to monitor how data informs resource allocation or service delivery. The lack of recent census data and scepticism towards projections from the 2017 census also hinder detailed planning, with some provinces and sectors not fully engaging with the evidence.
Output 2.2 moderately did not met expectations, with 167 national and subnational officials trained – just 8 participants short of the planned target -, due to lower turnout than anticipated. Trainings comprised a series of targeted engagements including a national workshop led by the University of Cape Town, provincial level training in Chiúre, Cabo Delgado province, and a regional session in Johannesburg with follow-up brief development. The sessions were positively received, reflecting government institutions’ growing appreciation of demographic analysis and its integration into policy, planning and budgeting.
[note] University of Cape Town is UNFPA’s downstream partner leading the National Transfer Accounts modelling to forecast demographic dividend considering the demographic transition and economic growth trends.
Results are visible, notably in the involvement of newly trained officials in the development of the above strategies and action plans. However, the real test lies in the extent to which trained officials are applying these concepts in day-to-day work and translating their interest into commitments to change policy and practice informed by data. Institutional mechanisms to sustain capacity beyond individual trainings are underdeveloped.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Indicators for this output were refined to better reflect the programme’s shift from data production to data use and from isolated policy outputs to sustained institutional engagement. Indicator 2.1 evolved from tracking the release of DHS and IOF reports to focusing on how data is accessed, interpreted, and applied in planning, with an emphasis on generating evidence of use at national and subnational levels. Indicator 2.2 was revised to move beyond counting policy documents to assisting and monitoring capacity to digest and use data to influence planning and decision-making. These changes have enabled more accurate tracking of government uptake and cross-sector collaboration. For the coming year, the programme will focus on strengthening follow-up mechanisms to assess how data and acquired analytic skills are applied, and on supporting institutions to embed and monitor demographic analysis into routine planning processes.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

Progress on recommendations from the previous AR

Recommendation	Progress
Conduct a political economy analysis (conducted by UNFPA or other supplier) after DHS final report is released. Finalise stakeholder mapping and engage in informal conversations with key informants. Collect evidence through a diversity of sources (including the media).	Met: PEA was conducted by the policy and programme manager and UNFPA following the release of the DHS 2022–23 final report. / Stakeholder mapping was completed. Findings and the final report were synthesized and shared with FCDO DT programme.

Key lessons learnt this year.
1. This year reaffirmed that while the production and dissemination of high-quality data is essential, it is not sufficient to drive policy and action. The absence of mechanisms for tracking and accounting for evidence translation continues to limit its impact.
2. Capacity-building nearly reached numerical targets, but the application of skills remains inconsistent, as many well-trained officials operate in environments of limited institutional support (including a lack of clear mandates, planning tools, and leadership backing).
3. While demographic transition and population dynamics are increasingly referenced in national policy documents, the follow-through on implementation is weak, indicating that policy inertia remains a barrier, reflecting deeper institutional challenges - such as fragmented mandates, limited accountability, political sensitivity around population issues, and a lack of incentives for evidence-based planning.
Learning aims/ recommendations for the coming year.
1. Share PEA results and translate insights into a focused and actionable change strategy, which should identify reform champions, address institutional bottlenecks, and apply feasible incentives to promote the use of data in decision-making – UNFPA/ FCDO.
2. Shift from ad hoc efforts to institutionalized systems, by developing a monitoring framework to track how key datasets are being used across sectors and provinces – UNFPA.

Output Title	Increased demand and access to quality sexual and reproductive health services at all levels (Last mile delivery)
Output number:		3	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	Yes, down – from 35% to 30%

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of health facilities in target districts with a functional logistics management information system (LMIS) - Zambezia and Nampula	Nampula: 45/45 / Zambezia: 40/55 / Total: 85	SUBSTANTIALLY EXCEEDED: / Nampula: 45 / Zambezia: 53 / Total: 98
3.2 Percentage of the health facilities where spot check shows that the commodities were delivered in the right quantity (> 2x consumption)	Zambezia: 12 HF with commodities at the right quantity out of the 16 health facilities where spot check will be conducted. / Nampula: 12/16 HF	MODERATELY EXCEEDED: / Zambezia: 14/16 / Nampula: 14/16
3.3 Monitoring demand satisfaction from clients of self-injection (survey/ field visit)	Number of health service providers trained on self-injections: / Private sector: 45 / Public sector: 760 (changed to 380)	NOT MET: / Private sector – 0 / Public sector – 146

Briefly describe the output’s activities and provide supporting narrative for the score. Output 3.1 exceeded the expectation, as 98 health facilities (13 percentage points more than the expected 85) have a functional Logistics Management Information System (LMIS) in place in both provinces. Nampula met the target of 100% of health facilities in the target districts – up from 83% in the previous year. Zambezia increased in coverage from 58% in the previous year to 95% at present, against the expected 73%. This is a significant improvement given its lower baseline mark against a larger number of health facilities in this province. Currently, facilities, deposits and warehouses nationwide, have migrated to the new management system – nSIMAM. The new system aims to enhance data storage, interoperability, and provide real-time visibility of stocks and requests, supporting decision-making across all health system levels. To ensure effective use and maintenance, 51 providers (27 in Nampula, 24 in Zambezia) were trained. The focus for the coming year will be on addressing system sustainability and effective service delivery.
Output 3.2 exceeded expectations for both provinces, with 88% of spot-checked facilities (28 of 32) reporting the correct quantities of commodities, against a target of 24 (75%). Stockouts have significantly declined since the 2021 ADIS survey, from 63% to 20% in Nampula and from 73% to 25% in Zambezia. To monitor compliance and improve supply chain management and stock levels, key performance indicators were defined and integrated into the M&E approach. These indicators target critical issues such as discrepancies in documentation, inventory record accuracy, stock levels at facilities, expiry date management, unusable stock, and overstock risks. However, the US funding cuts threaten to reverse these gains. FCDO and Health Partners are working with the government to prioritize and optimize existing resources to safeguard family planning services.
Output 3.3 was not met. Although the original milestone was not fully met, the programme made strong progress and is laying critical groundwork. Self-injectable contraception was successfully scaled up across all districts in Nampula in the previous year and expanded in Sofala and Maputo with other donors’ support in public health facilities. However, the target of offering self-injection family planning in private clinics and pharmacies will not move forward. Although early steps were taken, the rollout has been paused. This is because there are still global discussions happening about the price of the product, and there are concerns that offering it too cheaply now could make it hard to keep the service going in the future.
The revised target is to train 380 public facility providers (down from the original 780) by December 2025, which is achievable. The programme will continue monitoring and supporting trained healthcare providers to increase demand for the self-injectables. UNFPA remains engaged in discussions to ensure solutions that promote long-term gains of the expansion of self-injectables in both public and private sectors.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
The output indicators were adjusted to improve health facilities’ accuracy in reporting progress and enhance commodity supply chain responsiveness. This improved monitoring of the extent to which health facilities were requesting appropriate quantities of essential supplies (including contraceptives). It also improved scrutiny of warehouse requests against facility needs, and enabled better triangulation with spot-checks and field visits. For 2025/26, the aim is to see all target health facilities updating and synchronizing data on the logistics management system within three days; measure demand satisfaction for self-injection beyond trained providers and strengthen engagement and mentoring of both healthcare providers and beneficiaries to this end.

Progress on recommendations from the previous AR
Recommendation	Progress
Add an outcome that tracks contraceptive prevalence rates at district level; engage in discussions with provincial government and implementing partners supporting other family planning and SRHR programmes to develop joint metrics and analytics, share evidence and align messaging.	Met: An outcome indicator to track the modern contraceptive prevalence rate (mCPR) at the district level has been developed and incorporated in implementing partner’s logframe. Arrangements with potential implementing partners are underway, with the first evaluation expected to take place by December 2025.
Use ODA uplift as opportunity to explore the potential of partnerships with the private sector in the provision of family planning services to expand coverage and capitalize on social marketing expertise to inform demand generation approaches.	Met: the uplift funded the testing of communication approaches to strengthen social behaviour change strategies to expand coverage.
Use ODA uplift to demonstrate to Government and partners the added value of using evidence-based adolescent-centred FP demand creation approaches to increase access to FP.	Partially Met: this faced delays, as an enquiry on adolescents SRHR required ethical approval, with ethics protocol only submitted in April 2025. However, a desk review was completed in 2024, generating recommendations for a co-creation workshop scheduled for early July, which will generate recommendations to adapt the current approaches to services targeting adolescents.

Key lessons learnt this year.
Training healthcare providers alone does not translate into increased uptake of self-injectables. It requires close follow-up to consolidate on the confidence of healthcare providers and beneficiaries alike, based on the broader models of empathetic service provision and guided self-care.

Although the idea of expanding contraceptives to the private sector was locally driven, progress is now hinged on ongoing global-level negotiations between the supplier, Pfizer, and major donors - particularly the Bill & Melinda Gates Foundation. Their concern is that the proposed subsidised pricing model, while improving short-term access, can hinder the development of a sustainable private sector approach by setting unrealistic low prices that may not be feasible in the long term.

Learning aims/ recommendations for the coming year.
1. Promote joint efforts between the Health Partners Group (HPG) and government to sustain FP commodities procurement, distribution and services amid funding cuts, by proposing prioritization and cost-cutting approaches while protecting effectiveness of the interventions – FCDO.
2. Strengthen the design and relevance of adolescent-centred FP demand generation approaches and serve as a model for future programming and advocacy - UNFPA.

Output Title	Improved access to services and opportunities for adolescent girls and young women.
Output number:		4	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	Yes, up – from 10% to 15%

Indicator(s)	Milestone(s) for this review	Progress
4.1 Percentage of girls and young people engaged that have benefited from child grant and complementary interventions	Agreement with implementing partners. / Work plan agreed.	MET: Agreement signed with FSDMoc, with Muva signed up as downstream partner. A workplan for each of the institutions in the project has been agreed.
4.2 Number of key influencers including parents, men and boys and community leaders who are active in delaying unintended pregnancies and early marriage	WEE proposal defines target group representing decision makers and sets out activities to address gender norms underlying unintended pregnancies and early marriage	MET: Scoping study defined the household (not only women) as the core of intervention. SRHR modules will be integrated in the empowerment package targeting beneficiaries’ caretakers. / FSDMoc already in the process of identifying partners to deliver the modules.

Briefly describe the output’s activities and provide supporting narrative for the score.
Output indicator 4.1 met the expectations. After a lengthy period of negotiations with the government (the National Institute of Social Action – INAS, and the Ministry of Labour, Gender and Social Action – MTGAS) and potential implementing partners, the government signalled commitment to support the initiative, and it became a consensus that FSDMoc would be the most appropriate implementing partner for this component.

Output indicator 4.2 met the expectations. The scoping study results, which were validated by the government, identified the households as the core of the intervention, as opposed to just the caretakers. This provides a lever for the project to target household decision makers to address gender norms underlying unintended pregnancies. SRHR modules will be integrated in the household level empowerment package in three districts in Nampula province (Nacala-a-velha, Ilha de Moçambique and Ribáue). FSDMoç and Muva conducted a stakeholder mapping exercise that identified partners to work with on the modules at the district and community levels based on an assessment of the beneficiaries’ profile.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
In the previous reporting period, Output 4.2 remained undefined, pending the results of the mobilization phase as measured by Output 4.1. Following the scoping study, a strategic milestone was established to ensure the integration of SRHR into the planned WEE intervention. This milestone would align activities with the needs and priorities of the target group, thereby reinforcing a beneficiary-centred approach. Looking ahead, both indicators under Output 4 will be harmonized to enable tracking of the intervention’s outreach.

Progress on recommendations from the previous AR lessons learned this year and recommendations for the year ahead.
This is the first year of activities for this component, therefore there were no recommendations from last year.

Lessons learnt this year.
As funding priorities shift, there's a chance to move resources from delivering services directly to building strong partnerships. This can help create a supportive environment that attracts long-term, innovative funding for social protection.

Recommendations for the year ahead

1. Utilise the project launch as a platform to elevate the visibility of the importance of women’s economic empowerment within social protection programmes. This moment can be instrumental in generating government interest and securing long-term commitment to the cause – FCDO/ FSDMoc
2. Harness the programme’s governance mechanisms to build a strong, multi-stakeholder partnership that can champion the launch of a broader movement focused on mobilizing financial resources to support a robust and replicable poverty alleviation model centred on women’s economic empowerment - FCDO.

Output Title	Collaboration and communication on the demography transition agenda
Output number:		5	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
5.1 Joining up bilateral and central funding to leverage all UK funds in Moz towards the Demography transition agenda	SCALE Pilot intervention concept note approved by the Centre and Post / Entry points to influence prioritization of GHI/MISAU commitments to Lusaka Agenda objectives are identified	NOT MET: The SCALE funded technical assistance supported the gender analysis, but the scoping exercise to develop the pilot concept note was not finalized due to the political unrest. Following the reduction in pilot slots linked to the 0.3 percent funding cut, the Mozambique pilot has been paused until budget prospects are clearer. / MET: GFA adviser's engagement supported securing country’s commitment as a Lusaka Agenda flagship country. Three key national priorities identified as entry points to influence.
5.2 Influencing strategic partners for increased cross sector collaboration to drive the demography agenda	Number of high-level influencing engagements focused on the demography agenda: 2	EXCEEDED: Nine high-level engagements were linked to the demography agenda.

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 5.1 did not meet expectations. A scoping exercise was carried out between October and February 2024 with technical assistance from the SCALE programme to identify promising foundational learning interventions in Mozambique. The process surfaced three options: enhanced support for “Aprender+,” a targeted instruction model (TaRL), and strengthening school councils to improve accountability and inclusion. It also helped define strategic entry points and built alignment with key partners including the World Bank, UNICEF, and TaRL Africa. In parallel, a gender analysis was successfully completed through SCALE technical assistance and directly informed the GPE application, which was approved and will begin implementation in mid-2025.
However, the required concept note to access centrally supported pilot funding was not submitted. The scoping exercise, which was a prerequisite for the concept note was disrupted by political unrest and ongoing delays in key government appointments within the Ministry of Education and Culture. Without these in place, in-depth consultations on the ground could not take place. In addition, the new 0.3% budget ceiling has led to a general pause in new pilot approvals, with a likely reduction in the number of countries supported. As a result, Mozambique’s pilot concept did not advance, and the indicator was not met. Going forward, this component will focus on supporting the implementation of the GPE programme through the active engagement of the Education Adviser as part of the donor leadership team (the Troika) composed of three main actors involved in the sector dialogue and support to the Ministry of Education and Culture (MEC).
Regarding the Lusaka Agenda, the Global Fund Accelerator adviser to Mozambique played an important facilitator role, sustaining dialogue among partners, drafting key documents, and advocating for alignment around the Lusaka Agenda and joint financing mechanisms in Mozambique with the following results: (i) Mozambique’s agreement to become a lead collaborating country under the Lusaka Agenda, with three national priorities identified during a high-level joint mission; (ii) development of a draft roadmap for aligning health metrics. A key entry point to advance the Lusaka Agenda is the urgency created by global financing shifts and USG funding cuts, positioning the LA to emphasizing efficiency, alignment, and sustainability.
Output Indicator 5.2 exceeded the expectations, with multiple high-level engagements across sectors and platforms to advance the demography agenda in Mozambique. Key influencing moments included: Vice-Minister of Finance participation in at the 57th annual Commission for Population and Development outlined GoM objectives for population and development, and recognized the challenges and opportunities of the demographic transition; Ambassador for Day 2025 elevated youth voices and gender equality in diplomatic discussions with the First Lady and the new Minister of Labour, Gender and Social Action; FCDO Africa Director Visit featured an SRHR teach-in showcasing Mozambique’s progress and challenges; Cabo Delgado Forum demonstrated potential to integrating demographic data into local planning, with replication underway; FAMOD Roundtable promoted disability-inclusive demographic data systems; High Commissioner visit to Sofala province emphasized data-driven planning and girls’ education with provincial leaders; Minister of Health meeting with key FP partners drove alignment on Family Planning funding gaps.
The high-level engagements not only exceeded targets but are promoting recognition of the importance of demographic dynamics among key stakeholders, highlighting the need to institutionalize these dialogues into formal planning and budgeting processes to ensure sustained cross-sector collaboration and policy impact. In parallel, UNICEF, with FCDO support, co-led the Gender Working Group, while also using its role as incoming Troika lead in the Education sector to strengthen policy dialogue and lay the foundation for continued engagement through 2025.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

The milestones for Output 5.1 were revised to track the contributions of the Policy and Programme Manager and the Health and Education Advisers in aligning programme-funded initiatives with government priorities. Through their engagement with the Government of Mozambique, the Global Fund, UNICEF, and UNFPA - and in coordination with the Head of Mission’s influencing role and governance structures - they are helping to embed the demography agenda across sectors. The target for the next annual review is to reduce fragmented influencing efforts by developing a unified policy and influencing framework with clear success indicators, including value for money.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

Progress on recommendations from the previous AR
Recommendation	Progress
Conduct demographic agenda discussions in Cabo Delgado and Nampula provinces. Disseminate governance structure in Zambezia province.	Partially Met: after the workshops in Cabo Delgado, preparations underway for the Nampula workshop, government transition did not allow for socialization of the governance structure at central level. The programme is tapping into the WISH policy and systems CMP, for support in the implementation of a coordination mechanism to influence and advance the demographic transition agenda in Mozambique.
Share the provincial experience and lessons with central government structures and assess appetite for a national platform.
Roll out and align the governance structure with activities led by UNFPA data and family planning components.
Develop a VfM strategy and framework for the programme ensuring compliance with FCDO guidelines and alignment with the VfM indicators developed by programme partners.	Not Met: this work is on-going and led by the policy and programme manager.

Key lessons learnt this year.
Opportunities for influencing are many, but they require coordination and need to be anchored in key strategic objectives. To this end, the policy and programme manager reduced her time working with UNFPA to focus more on in-house FCDO policy work and leadership of this component.
Learning aims/ recommendations for the coming year.
1. Develop a policy and influencing roadmap that aligns with broader post’s policy goals and includes a clear monitoring and evaluation (M&E) plan – FCDO policy leads.
2. Follow-through on gender and foundational learning priorities in GPE and GEA grant applications by having the Education Adviser, leveraging their role as Troika lead through UNICEF, closely monitoring the implementation of these priorities – FCDO/ UNICEF.
## D: VALUE FOR MONEY

Key cost drivers and performance

VfM performance compared to the original VfM proposition in the business case.

Economy
UNFPA FP - the programme continues to make savings through the existing UNFPA prices vs the standard agreements. To date, £544,000 has been saved, allowing the project to purchase additional contraceptives and expand access to essential commodities. E.g. Levoplant (contraceptive implant) was procured at £5.07 per set vs. the standard £7.42. All contraceptives procured are World Health Organization pre-qualified, ensuring both cost-efficiency and quality.
UNFPA DD - the unit cost of technical assistance decreased significantly over time, reflecting improved cost-efficiency. E.g., in 2023, training of 83 INE provincial staff cost an average of £132 per participant for a multi-day workshop (approx. £44/day), compared to £86.40 per participant in 2024. These rates remain well below international benchmarks, reflecting cost-efficiency gains through INE local delivery.
FSDMoc WEE - is under the inception phase. However, agreed economy indicators will look at: (i) procurement Benchmarking of reports on savings achieved through competitive bidding or local sourcing while including variance analysis between budgeted and actual costs for key inputs (consultants, equipment, travel); (ii) Consultant Fee Rationalization to compare average consultant fees by seniority and expertise against market rates and highlight any cost savings from using local or regional experts.

Efficiency
UNFPA FP – Cost per Couple Year of Protection (CYP) averaged £2.50 across 2022–2024, with £1.95 in 2022, well below the baseline of £2.75. In ensuring integrated services at all points of entry, 89 out of 100 sites now offer at least three FP methods, exceeding the target of 40.
UNFPA DD – In 2024, the project budget increased by £200,000 compared to 2023, reaching £937,000. Despite this growth, administrative and HR costs decreased slightly in absolute terms from £315,000 to £310,000 and dropped significantly as a share of the total budget. This reflects improved delivery efficiency, with more resources directed toward direct implementation. However, sustaining this efficiency will be essential as the project enters its final year.
FSDMoc WEE - will focus on the ratio of programme to administrative costs to track the share of funds going directly to programme delivery vs. overheads. This will be used to demonstrate lean management and resource prioritization.

Effectiveness
UNFPA FP – Cost per unintended pregnancy averted was £10.00 in 2024, below the milestone of £13.08, preventing 950,000 unintended pregnancies. Cost per maternal death averted was £9.50, significantly lower than the baseline of £1,520, with a projected 1,000 maternal deaths prevented. This reflects the efficiency gains from targeted family planning interventions that reduce maternal mortality through the prevention of unintended pregnancies, unsafe abortions and related complications.
UNFPA DD- User satisfaction with demographic data products is being rolled out in 2025 to assess the relevance and utility of data products. This will target 75% of users with an opportunity to rate products. 60% of provincial users reported increased confidence in using demographic data.
FSDMoc WEE- Outcome level indicators will be used to measure percentage of households reporting improved financial decision-making and percentage of women reporting increased control over household income or savings.
World Bank – The project has a 70% payment for results component that requires independent verification. By end of 2024, only 17% of the PforR funds and 0% of the Investment Project Financing (IPF) components had been utilized, representing just 12% of the total program expenditure. Timely and technically sound verification of indicators before payments will drive effectiveness.

Equity
UNFPA FP - Community Health Workers (CHWs) contributed to all FP services in Zambézia and Nampula, improving access in remote areas. Adolescent and Youth-Friendly Services (AYFS) saw a 42.5% increase in youth reached from 2023 to 2024 across both provinces. Female attendance rose by 39.7%, and male attendance by 48.2%.
UNFPA DD - There is evidence to show that DHS data is disaggregated by sex, region, education, and wealth through the STAT compiler. Currently, INE’s SDG Portal tracks 105 indicators, enhancing visibility of vulnerable groups.
FSDMoc WEE - will measure % of beneficiaries who are women, youth (15–25), rural, plus geographic equity such as underserved provinces or districts.
World Bank – has intentionally and consistently targeted underserved districts reaching women and children at both health facility and in communities. 35.5% of community health providers are women.

Assessment of whether the programme continues to represent value for money.
The programme continues to deliver value for money across its components, with gains in economy through cost-saving service integration and targeted training investments that enhance delivery without significant cost increases. While delivery through government systems limits precise unit cost tracking, regular monitoring ensures efficiency in resource use and alignment with intended outcomes.
Effectiveness is reflected in the programme’s influence on national and subnational planning. DHS and IOF data informed key policy frameworks (ENDE, PES, PESS), and provincial briefs can support decentralised budgeting. In the education sector, the programme helped identify three scalable learning interventions and aligned with key partners through the GPE application process. Although pilot funding was not secured due to external delays, the groundwork laid has positioned the programme to influence future sector reforms.

The programme also demonstrated strong policy leverage, with high-level engagements advancing the demographic agenda. Mozambique’s leadership role under the Lusaka Agenda, the development of a roadmap for health metric alignment, and cross-sector dialogues ranging from youth empowerment to disability-inclusive data underscore the programme’s strategic influence. These efforts promote sustainability and alignment, particularly in the face of shifting global financing.
On equity, the programme maintains a clear focus on underserved populations, especially in northern provinces. However, further work is needed to define and track equity metrics more systematically. Strengthening outcome measurement, refining VfM benchmarks—particularly under the FSDMoc component—and embedding equity reporting across all components will be critical to sustaining inclusive and impactful progress.

E: RISK

Overview of risk management

Throughout the year, the Safeguarding risk level remained above the BHC’s risk appetite. This was promptly escalated and addressed, with a subsequent safeguarding study clarifying key concerns and prompting a reassessment of the risk appetite. The risks linked to strategy and context, policy and programme delivery, reputational, financial and fiduciary and public service and operations stayed within acceptable limits.

The results from the Safeguarding study highlighted the need for increased investments by securing dedicated funding for training, reporting, and safeguarding efforts, including the appointment of safeguarding leads within the UNFPA project. Many more recommendations as described in the full report and herein the evidence section will be followed up.

Mozambique’s general elections in October 2024 triggered over five months of post-election violence, severely disrupting project implementation. Transport and communication systems were intermittently inaccessible, and public gatherings were sporadically suspended. Vandalism of health infrastructure further hindered access to sexual and reproductive health services and delayed key health interventions.

The December–March rainy season brought additional strain, with Cyclones Chido, Dikeledi, and Jude impacting Nampula and Zambezia provinces. These events further weakened the health system and disrupted service delivery.

Funding uncertainties also intensified. The announced closure of USAID operations and future reductions in UK ODA will jeopardize the continuity of family planning and broader health services. These developments may necessitate restructuring or even the closure of some interventions, which would negatively affect the delivery of family planning and broader health services. In response, BHC leadership is working with the Ministry of Health and partners to find sustainable solutions to the financing problem and maintain essential service delivery.

A climate and environmental risk assessment carried out on the Demography programme revealed high vulnerability to climate-related disasters. To mitigate this, the programme will collaborate with UNFPA, UNICEF, the World Bank, and FSDMoc to implement risk-reduction measures, with ongoing oversight by the SRO/PRO and cluster.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

The programme achieved a 91% budget execution rate, despite facing multiple challenges. Delays in mobilising uplift interventions, post-election violence, the rainy season, and the late start of the Women’s Economic Empowerment (WEE) project all contributed to slower spending. For instance, delays in uplift mobilisation shortened the implementation period of PSI’s public-private self-injection interventions from one year to just seven months, limiting the reach and impact on intended beneficiaries. Similarly, the late mobilization of the WEE component reduced the planned 8-month inception phase to five months, affecting the timely rollout of key activities and reducing forecasted budgets. As a mitigation strategy, UNFPA FP made advanced procurement of contraceptives for 2026. Although the SEAH study under Component 103 was successfully completed, other planned research activities did not materialise, further contributing to the underspending. Overall, the programme demonstrated strong financial management by adapting to evolving circumstances while maintaining a high execution rate.

All implementing partners have consistently submitted their reports on time and with the expected level of quality. Regular monthly coordination meetings with UNFPA and co-financier discussions facilitated by the World Bank have ensured that the Demography Cluster receives timely updates on implementation progress. This has helped shorten the feedback loop between reporting and action. Additionally, the demography cluster meets once a week to align interventions and ensure prompt delivery of the programme.

As a new implementing partner, FSDMoc is still in the process of refining its forecasting and reporting practices. Efforts are ongoing to establish effective ways of working and improve accuracy of forecasting. The five-month inception report was received, and it is expected to set a strong foundation and establish a clear direction for future collaboration.

Following the closure of the Muva project under the Social Protection programme, in March 2025, project assets were transferred to the Demography programme for use by Muva - downstream partners of FSDMoc. These assets will be jointly monitored annually by FSDMoc and the BHC Programme Manager to ensure proper use and accountability. Assets procured under the UNFPA Family Planning (FP) component are still in use at the health facilities.

Delivery chain risk maps have been periodically updated, and for FSDMoc, a more detailed review will be conducted once the inception report and its annexes are submitted.

The 2023 Annual Review recommended improvement in branding and visibility for FP commodities. During a recent field visit to Zambezia, improvements in branding were observed at health facilities, including the use of stickers, banners, roll-ups, and on branded reading materials. However, branding remains insufficient at medical warehouses and pharmacies, where many commodity cartons still lack UKAid branding. This gap is recurrent and will require targeted follow-up to ensure full visibility and compliance with UK branding guidelines.

UNFPA is implementing recommendations from its audit report. The World Bank audit reports covering 2023 and 2024 were duly received and reviewed.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
Monitoring during the review period included two joint field visits with implementing partners, providing critical insights that have shaped programming decisions. The first visit with The World Bank took place in Manhiça (Maputo Province) and Chibuto (Gaza Province) from 12-20 September 2024. This coincided with the launch of the new District Health operation, focusing on programme mobilization, identifying early challenges, and assessing opportunities for co-financing. The second joint monitoring visit with UNFPA took place from 14–17 April 2025 in Zambezia Province (Nicodala and Mocuba districts) coinciding with the World Bank’s second joint mission. As a result, the Demography Cluster joined UNFPA in Zambezia. Comments on the World Bank mission report have since been shared.
The site visits with UNFPA highlighted significant progress in family planning service coverage at health facilities, schools, and through community health initiatives. However, post-election violence and USAID funding cuts severely disrupted logistics, particularly the delivery of family planning commodities from warehouses to health facilities, affecting last-mile delivery. In response, provincial and district hospitals have been empowered to identify short- and medium-term solutions, while long-term strategies are being discussed at the central level. The visit also demonstrated strong local ownership of the interventions, with Zambezia’s project leads actively adapting the project and seeking sustainable solutions within the directorate and with other local implementing partners.
Despite challenges stemming from post-election violence and a change in government, the programme demonstrated some resilience. Strategic reprogramming was undertaken to address delays and maintain implementation momentum. Focus will be on ensuring that progress is duly verified before funds can be disbursed. Beneficiary engagement by the demography cluster included discussions on contraceptive preferences, yielding valuable qualitative feedback on long-acting vs short-acting family planning methods. Positive feedback, particularly from women, affirmed the relevance and acceptability of services.

A young mother with her daughter after receiving counselling on family planning. “I was really happy when the door-to-door activist approached me to speak about family planning options. She gave me the options, and I found the implant option to be the best method because it lasts much longer”, © UNFPA Mozambique/2024/Mbuto Machili

 “I chose Sayana Press because it doesn’t affect my body, and I feel better with it. I had tried the implant, but my period didn’t stop or would last too long. I have a one-year-old daughter, and I only want another child when she turns four, so I can take better care of her.”
Photo: © UNFPA Mozambique/Mbuto Machilli

Evidence
Two major pieces of research were completed during the year and have informed programmatic adjustments:

SEAH Study
This evaluation revealed that reporting mechanisms - such as complaint boxes, user offices, health committees, and gender-based violence (GBV) desks - exist for general feedback and service complaints, however, they are not specifically designed to receive, document, or respond to SEAH cases.
The Demography Cluster will engage with key stakeholders including UNFPA, MISAU, the British High Commission, the SEAH Network, and other health partners to jointly develop fit-for-purpose SEAH reporting mechanisms. The programme will prioritise advocacy and support for a coordinated system that is both survivor-centred and functionally integrated into the health service architecture. These efforts will be reflected in the upcoming year’s safeguarding workplan.

Political Economy Analysis of Data Use
The second major evidence product was a Political Economy Analysis (PEA) on the use of demographic data in policy and governance processes in Mozambique. The analysis highlights that, while national data systems have improved over the years, serious structural barriers persist. Challenges remain around technical capacity at subnational levels, data system integration, coordination across institutions, and ensuring consistent use of data in decision-making. In some rural and underserved areas, local governments face challenges in accessing and analysing disaggregated data particularly by geography, sex, and age. Short-term training efforts have helped, but sustaining capacity remains difficult due to staff turnover and programme transitions.

To address these issues, the Demography Cluster is exploring more sustainable, long-term solutions, including the potential for an institutionalised Masters-level training programme in demography. The programme also aims to promote participatory planning processes where local leaders and communities use disaggregated data to set priorities and monitor service delivery. In partnership with UNFPA and other data actors, there are also plans to assess the feasibility of establishing peer learning mechanisms across districts and provinces—allowing for horizontal knowledge exchange and problem-solving on the use of demographic data in decision-making.

Learning
Over the past year, the programme has embedded a range of learning processes to strengthen delivery, foster collaboration, and respond adaptively to a shifting context. These included the development of an SRHR advocacy strategy which contributed to the approval of Mozambique’s national FP strategy under the FP2030 agenda. The strategy not only help frame the demographic rationale for family planning but also supported more coordinated messaging among government and partners.

A family planning (FP) gap analysis was used effectively to convene partners and government counterparts in discussions around funding shortfalls following the reduction in USAID support. The integration of co-financiers into the Programme Implementation Unit has also proven to be a valuable innovation, enabling improved oversight and tracking of progress. Regular learning opportunities through joint monitoring visits, meetings with provincial administrators, participation in technical working groups, and post-based learning events have kept the programme grounded in real-time realities and responsive to stakeholder feedback.

These learning processes surfaced several critical insights. At the programme level, UK diplomacy and technical engagement continue to be highly valued. Despite relatively limited bilateral resources, the UK’s credibility and influence have helped to shift mindsets, align development agendas, and advance policy reform—particularly around FP financing and data use. However, the year also exposed persistent weaknesses in safeguarding mechanisms, with the SEAH assessment confirming that current complaint and reporting structures do not adequately support survivors or respond to cases effectively. This finding underscores the need for a coordinated, fit-for-purpose approach to SEAH reporting and accountability.

Another important insight from the political economy analysis of demographic data use was the need to strengthen the link between centralised data systems and local government capacity, particularly in rural and underserved areas. Without sustained investment in decentralised systems and long-term training, the full potential of data to inform service delivery and resource allocation may not be realised. The analysis also underscored the value of supporting locally led, participatory planning processes where data is actively used by communities and decision-makers. Efforts to promote women’s economic empowerment (WEE) revealed that technical solutions alone are insufficient. Without strong government ownership and commitment, WEE initiatives risk remaining peripheral to broader policy priorities. Nonetheless, the current fiscal constraints created an opening to work more closely with government counterparts to explore efficiency gains and identify policy entry points, including through social protection systems.
Date of last narrative financial report	UNFPA (DD/FP) 30th April 2025 / FSDMoc 15th April 2025 / World Bank 27th March 2025	Date of last audited annual statement	December 2024 – WB / March 2025- UNFPA